## SNSPPU
Type | Author | Project | Traveler/Procedure | REV | Received | Drafts Folder | Sent for Approval | Left to Sign | Approved | Disapproved | In Pansophy | Approved Folder | Requests/Changes/Notes
Procedure | K.MACHA | SNSPPU | CP-SNSPPU-CAV-ASSY-HELV | R1 |  | 2020-03-09 | [5 empty] | 2020-03-11
Procedure | C.WILSON | SNSPPU | CP-SNSPPU-CAV-VTA-OPS | R1 |  | 2020-02-03
Procedure | K.MACHA | SNSPPU | CP-SNSPPU-CM-ENDC-INST | R1 |  | 2020-07-31
Procedure | K.MACHA | SNSPPU | CP-SNSPPU-CST-COUP-INST | R1 |  | 2020-07-29
Procedure | K.MACHA | SNSPPU | CP-SNSPPU-CST-TOOL-PREP | R1 |  | 2020-07-29
Listing | GARY | SNSPPU | SNSPPU_MasterTravelerListing_25June2020_Cheng | R1 | 2020-07-17
Traveler | KURT MACHA | SNSPPU | SNSPPU-CAV-ASSY-HELV | R1 |  | 2020-03-19 | [5 empty] | 2020-07-14
Traveler | FOREHAND | SNSPPU | SNSPPU-CAV-BAKE | R1 | 2020-07-23 | [7 empty] | Needs a bake procedure
Traveler |  | SNSPPU | SNSPPU-CAV-CHEM-CLN-FPC | R1
Traveler |  | SNSPPU | SNSPPU-CAV-CHEM-HPR | R1
Traveler | PASHUPATI | SNSPPU | SNSPPU-INSP-CAV | R1 | 2020-06-11 | 2020-09-10 | 2020-09-17 | Dhakal, Aaron, Edaly
Traveler |  | SNSPPU | SNSPPU-CAV-INSP-FPC | R1
Traveler |  | SNSPPU | SNSPPU-CAV-INSP-HEHDF (SNSPPU-INSP-HEHDF) | R1 |  | 2020-08-24 | 2020-08-24 |  | 2020-08-24 |  |  | 2020-09-10
Traveler |  | SNSPPU | SNSPPU-CAV-INSP-HEHDP (SNSPPU-INSP-HEHDP) | R1 |  | 2020-08-24 | 2020-08-24 | Kwilson |  |  |  | 2020-09-10
Traveler |  | SNSPPU | SNSPPU-CAV-LEAK-FPC | R1
Traveler | PASHUPATI | SNSPPU | SNSPPU-CAV-TRANS-TSTD (SNSPPU-CAV-ASSY-TSTD) | R1 | 2020-06-11 | [7 empty] | NEEDS A PROCEDURE
Traveler | K DAVIS | SNSPPU | SNSPPU-CAV-VTRF (SNSPPU-VTRF-CAV) | R1 | [7 empty] | 2020-09-10
Traveler | K DAVIS | SNSPPU | SNSPPU-CAV-VTRF (SNSPPU-VTRF-CAV) | R2 |  |  | 2020-08-13 |  | 2020-08-24 |  |  | 2020-09-10
Traveler | K.MACHA | SNSPPU | SNSPPU-CMA-AMGV-LEAK | R1 |  |  | 2020-06-25 |  | 2020-08-04 |  |  | 2020-09-01
Traveler | OWEN | SNSPPU | SNSPPU-CMA-FT08P-LEAK (SNSPPU-CM-LEAK-FT08P) | R1 | 2020-06-25 |  | 2020-06-25 |  | 2020-07-15 |  | Y | 2020-07-20
Traveler | GARY | SNSPPU | SNSPPU-CM-ASSY-CMA (SNSPPU-CMA-CMASS-ASSY) | R1 | 2020-08-03 | 2020-08-07 | 2020-08-07 | ED DALY
Traveler | FISCHER | SNSPPU | SNSPPU-CM-ASSY-CMASS | R1 | 2020-07-22
Traveler | MARCHLIK | SNSPPU | SNSPPU-CM-ASSY-SFTS | R1 | 2020-06-26
Traveler |  | SNSPPU | SNSPPU-CM-ASSY-SHIP | R1
Traveler |  | SNSPPU | SNSPPU-CM-CSHK-RFCBL | R1
Traveler |  | SNSPPU | SNSPPU-CM-INSP-CMMC | R1
Traveler |  | SNSPPU | SNSPPU-CM-INSP-ELFT | R1 |  | 2020-08-24
Traveler |  | SNSPPU | SNSPPU-CM-INSP-EQFH | R1
Traveler |  | SNSPPU | SNSPPU-CM-INSP-FT08P | R1 | x |  | 2020-07-15 |  | 2020-08-04 |  | Y
Traveler |  | SNSPPU | SNSPPU-CM-INSP-GVPA | R1
Traveler |  | SNSPPU | SNSPPU-CM-INSP-HMDR | R1
Traveler | GARY | SNSPPU | SNSPPU-CM-INSP-IMAG (SNSPPU-INSP-IMAG) | R1 | 2020-08-03 | 2020-08-07 | 2020-08-07 |  | 2020-08-13
Traveler |  | SNSPPU | SNSPPU-CM-INSP-INFF | R1 | x |  | Y |  | Y |  | Y
Traveler | MARCHLIK | SNSPPU | SNSPPU-CM-INSP-INFF (SNSPPU-INSP-INFF) | R1 |  | 2020-05-21
Traveler |  | SNSPPU | SNSPPU-CM-INSP-JTV | R1
Traveler |  | SNSPPU | SNSPPU-CM-INSP-JTVA | R1
Traveler |  | SNSPPU | SNSPPU-CM-INSP-OCBL (OUT/CON BELLOWS) | R1
Traveler | GARY | SNSPPU | SNSPPU-CM-INSP-OMAG (SNSPPU-INSP-OMAG) | R1 | 2020-08-03 | 2020-08-14 | 2020-08-07 |  | 2020-08-19
Traveler | MARCHLIK | SNSPPU | SNSPPU-CM-INSP-PRPA | R1 | [7 empty] | 2020-07-14
Traveler |  | SNSPPU | SNSPPU-CM-INSP-RENCPP (PARALLEL PLATE) | R1
Traveler |  | SNSPPU | SNSPPU-CM-INSP-RFCBL | R1
Traveler |  | SNSPPU | SNSPPU-CM-INSP-RPIPE | R1
Traveler | MARCHLIK | SNSPPU | SNSPPU-CM-INSP-SFR (SNSPPU-INSP-SFR) | R1 | 2020-06-16 |  | 2020-06-25 |  | 2020-07-21
Traveler |  | SNSPPU | SNSPPU-CM-INSP-SM | R1
Traveler |  | SNSPPU | SNSPPU-CM-INSP-SPIPE | R1
Traveler |  | SNSPPU | SNSPPU-CM-INSP-THRM (SNSPPU-INSP-THRM) | R1 | x |  | 2020-05-28 |  | 2020-07-21 |  | Y | 2020-07-14
Traveler | MARCHLIK | SNSPPU | SNSPPU-CM-INSP-THRMST (SNSPPU-INSP-THRMST) | R1 | 2020-06-11 |  | 2020-07-02 |  | 2020-07-21 |  | Y
Traveler | MARCHLIK | SNSPPU | SNSPPU-CM-INSP-TPHT | R1 | [7 empty] | 2020-07-14
Traveler | MARCHLIK | SNSPPU | SNSPPU-CM-INSP-TPHTB | R1 | [7 empty] | 2020-07-14
Traveler | HUQUE | SNSPPU | SNSPPU-CM-INSP-TUNC | R1 |  | 2020-04-16 | [5 empty] | 2020-07-14
Traveler |  | SNSPPU | SNSPPU-CM-INSP-TUNF | R1 |  | 2020-03-19
Traveler |  | SNSPPU | SNSPPU-CM-LEAK-CMMC | R1
Traveler |  | SNSPPU | SNSPPU-CM-LEAK-GVPA | R1
Traveler | MARCHLIK | SNSPPU | SNSPPU-CM-LEAK-INFF | R1 |  | 2020-04-23 | [5 empty] | 2020-07-14
Traveler |  | SNSPPU | SNSPPU-CM-LEAK-RPIPE | R1
Traveler |  | SNSPPU | SNSPPU-CM-LEAK-SPIPE | R1
Traveler | MARCHLIK | SNSPPU | SNSPPU-CM-LEAK-THRM | R1 |  |  | 2020-04-29 |  | 2020-05-19 |  |  | 2020-07-14
Traveler | MARCHLIK | SNSPPU | SNSPPU-CM-LEAK-THRMST | R1 |  |  | 2020-05-19 |  | 2020-06-02 |  |  | 2020-07-14
Traveler | MARCHLIK | SNSPPU | SNSPPU-CM-LEAK-TPHT | R1 | [7 empty] | 2020-07-14
Traveler | MARCHLIK | SNSPPU | SNSPPU-CM-LEAK-TPHTB | R1 |  | 2020-04-14 | [5 empty] | 2020-07-14
Traveler | FOREHAND | SNSPPU | SNSPPU-CST-ASSY | R1 | 2020-07-23 | 2020-08-24 | [6 empty] | King asked for cernox var name changes
Traveler |  | SNSPPU | SNSPPU-CST-INSP-BLBP | R1 |  | 2020-08-24
Traveler |  | SNSPPU | SNSPPU-CST-INSP-BLBPRE (RETURN) | R1
Traveler |  | SNSPPU | SNSPPU-CST-INSP-BLBPSE (SUPPLY) | R1
Traveler |  | SNSPPU | SNSPPU-CST-INSP-PRPA (SNSPPU-CM-INSP-PRPA) | R1 |  | 2020-03-19 | [5 empty] | 2020-07-14
Traveler |  | SNSPPU | SNSPPU-CST-INSP-SFR | R1 | 2020-06-16
Traveler |  | SNSPPU | SNSPPU-CST-INSP-SW2C | R1 |  | 2020-08-24
Traveler |  | SNSPPU | SNSPPU-CST-INSP-TPHTB | R1 |  | 2020-04-14
Traveler |  | SNSPPU | SNSPPU-CST-LEAK-AMGV | R1 | x |  | 2020-06-25 |  | 2020-08-04 |  | Y
Traveler | KWILSON | SNSPPU | SNSPPU-CST-LEAK-GVLV | R1 | 2020-06-18 | 2020-08-24
Traveler |  | SNSPPU | SNSPPU-CST-LEAK-PRPA (SNSPPU-CM-LEAK-PRPA) | R1 |  | 2020-03-19 | [5 empty] | 2020-07-14
Traveler |  | SNSPPU | SNSPPU-CST-LEAK-TPHT | R1 |  | 2020-04-08
Traveler |  | SNSPPU | SNSPPU-CST-LEAK-TPHTB | R1 |  | 2020-04-08
Traveler | OWEN | SNSPPU | SNSPPU-ELEC-FT08P-CHK | R1 | x |  | 2020-07-15 | Kushnick |  |  | Y | 2020-09-01
Traveler | OWEN | SNSPPU | SNSPPU-INSP-FT08P | R1 | [7 empty] | 2020-09-01
Traveler |  | SNSPPU | SNSPPU-INSP-HEHDF-WELD | R1
Traveler |  | SNSPPU | SNSPPU-INSP-HEHDP-WELD | R1
Traveler | K.WILSON | SNSPPU | SNSPPU-INSP-HES (SNSPPU-CAV-HES) | R1 | 2020-07-13 |  | 2020-07-15 |  | 2020-08-06 |  | 2020-08-06 | 2020-09-03
Traveler |  | SNSPPU | SNSPPU-INSP-HES-WELD | R1
Traveler | M.DICKEY | SNSPPU | SNSPPU-INV-BLBFA | R1 |  |  | 2020-05-04 |  | 2020-05-04 |  |  | 2020-07-14
Traveler | M.DICKEY | SNSPPU | SNSPPU-INV-BLBP | R1 | [7 empty] | 2020-02-26
Traveler | M.DICKEY | SNSPPU | SNSPPU-INV-BLIPT | R1 |  |  | 2020-05-04 |  | 2020-05-04 |  |  | 2020-02-26
Traveler | M.DICKEY | SNSPPU | SNSPPU-INV-CAV | R1 | [7 empty] | 2020-02-26
Traveler | GARY | SNSPPU | SNSPPU-INV-CMMC | R1 | 2020-06-04 |  | 2020-06-18 |  | 2020-06-30
Traveler | M.DICKEY | SNSPPU | SNSPPU-INV-DCXCU (SNSPPU-CM-RECV-DCXCU) | R1 | [7 empty] | 2020-09-01
Traveler | M.DICKEY | SNSPPU | SNSPPU-INV-DCXCU (SNSPPU-CM-RECV-DCXCU) | R2 | [7 empty] | 2020-09-01
Traveler | GARY | SNSPPU | SNSPPU-INV-EQFH | R1 | 2020-06-18 |  | 2020-06-18 |  | 2020-06-30 |  |  | 2020-07-14
Traveler | M.DICKEY | SNSPPU | SNSPPU-INV-FPC | R1 | [7 empty] | 2020-02-26
Traveler | M.DICKEY | SNSPPU | SNSPPU-INV-FT06P | R1 | [7 empty] | 2020-07-14
Traveler | M.DICKEY | SNSPPU | SNSPPU-INV-FT10P | R1 | [7 empty] | 2020-07-14
Traveler | GARY | SNSPPU | SNSPPU-INV-GVPA | R1 | 2020-06-18 |  | 2020-06-18 |  | 2020-06-30 |  |  | 2020-07-14
Traveler | M.DICKEY | SNSPPU | SNSPPU-INV-HEHDF | R1 | [7 empty] | 2020-02-26
Traveler | M.DICKEY | SNSPPU | SNSPPU-INV-HEHDP | R1 | [7 empty] | 2020-02-26
Traveler | M.DICKEY | SNSPPU | SNSPPU-INV-HEIBA | R1 |  |  | 2020-06-18 |  | 6/30/202 | 2020-06-18
Traveler | M.DICKEY | SNSPPU | SNSPPU-INV-HES | R1 | [7 empty] | 2020-02-26
Traveler | M.DICKEY | SNSPPU | SNSPPU-INV-HLS | R1 | [7 empty] | 2020-02-26
Traveler | M.DICKEY | SNSPPU | SNSPPU-INV-HMDR | R1 | [7 empty] | 2020-02-26
Traveler | M.DICKEY | SNSPPU | SNSPPU-INV-IMAG | R1 | [7 empty] | 2020-02-26
Traveler | M.DICKEY | SNSPPU | SNSPPU-INV-JTV | R1 | [7 empty] | 2020-02-26
Traveler | M.DICKEY | SNSPPU | SNSPPU-INV-JTVA | R1 | [7 empty] | 2020-02-26
Traveler | M.DICKEY | SNSPPU | SNSPPU-INV-JTVIB | R1 |  |  | 2020-05-04 |  | 2020-05-19 |  |  | 2020-07-14
Traveler | M.DICKEY | SNSPPU | SNSPPU-INV-JTVOB | R1 |  |  | 2020-05-04 |  | 2020-05-19 |  |  | 2020-07-14
Traveler | M.DICKEY | SNSPPU | SNSPPU-INV-LDS12 | R1 | x |  | 2020-07-06 |  | 2020-07-13 |  | Y | 2020-07-14
Traveler | M.DICKEY | SNSPPU | SNSPPU-INV-LDS34 | R1 | x |  | 2020-07-06 |  | 2020-07-13 |  | Y | 2020-07-14
Traveler | M.DICKEY | SNSPPU | SNSPPU-INV-LDS34H | R1 | x |  | 2020-07-06 |  | 2020-07-14 |  | Y | 2020-07-14
Traveler | M.DICKEY | SNSPPU | SNSPPU-INV-OMAG | R1 | [7 empty] | 2020-02-26
Traveler | M.DICKEY | SNSPPU | SNSPPU-INV-OMAGRE | R1 | x |  | 2020-07-29 |  | 2020-08-06
Traveler | M.DICKEY | SNSPPU | SNSPPU-INV-OMAGSE | R1 | x |  | 2020-07-29 |  | 2020-08-06
Traveler | M.DICKEY | SNSPPU | SNSPPU-INV-PBD | R1 | [7 empty] | 2020-02-26
Traveler | M.DICKEY | SNSPPU | SNSPPU-INV-PRPA | R1 | [7 empty] | 2020-02-26
Traveler | M.DICKEY | SNSPPU | SNSPPU-INV-RENC | R1 | [7 empty] | 2020-02-26
Traveler | GARY | SNSPPU | SNSPPU-INV-RPIPE | R1 | 2020-06-18 |  | 2020-06-18 |  | 2020-06-30 |  |  | 2020-07-14
Traveler | M.DICKEY | SNSPPU | SNSPPU-INV-SENC | R1 | [7 empty] | 2020-02-26
Traveler | M.DICKEY | SNSPPU | SNSPPU-INV-SFR | R1 | [7 empty] | 2020-02-26
Traveler | M.DICKEY | SNSPPU | SNSPPU-INV-SM | R1 | [7 empty] | 2020-07-14
Traveler | GARY | SNSPPU | SNSPPU-INV-SPIPE | R1 | 2020-06-18 |  | 2020-06-18 |  | 2020-06-30 |  |  | 2020-07-14
Traveler | M.DICKEY | SNSPPU | SNSPPU-INV-THRM | R1 | [7 empty] | 2020-02-26
Traveler | M.DICKEY | SNSPPU | SNSPPU-INV-TJVIB | R1
Traveler | M.DICKEY | SNSPPU | SNSPPU-INV-TPHP | R1 | [7 empty] | 2020-02-26
Traveler | M.DICKEY | SNSPPU | SNSPPU-INV-TPHT | R1 | [6 empty] | Y | 2020-02-26
Traveler | M.DICKEY | SNSPPU | SNSPPU-INV-TUNC | R1 |  | 2020-04-20 | [5 empty] | 2020-07-14
Traveler | M.DICKEY | SNSPPU | SNSPPU-INV-VV | R1 | [7 empty] | 2020-02-26
Traveler | M.DICKEY | SNSPPU | SNSPPUT-CM-LEAK-INFF | R1
Traveler | PASHUPATI | SNSPPU | SNSPPU-TUNE-CAV-RFIN (SNSPPU-CAV-RFIN) | R1 | 2020-06-11 |  | 2020-09-03 |  | 2020-09-03 |  | 2020-09-03 | 2020-09-10
Traveler | M.DICKEY | SNSPPU | SNSPPU-VTA-CSHK-FT08P | R1 | x |  | 2020-06-25 |  | 2020-08-05 |  | Y | 2020-09-10

## AUP
Received | Author | Project | Traveler/Procedure | REV | Que | Drafts | Sent for Approval | Left to Sign | Approved | Disapproved | In Pansophy | In Approved Folder? | Requests/Changes/Notes
| Common Travelers | AUP | AUP-ASSY-CMN-BRZAS |  |  | 2020-06-18
| Common Travelers | AUP | AUP-ASSY-CMN-FLBRZ |  |  | 2020-06-18
| Common Travelers | AUP | AUP-INSP-CMN-CURING |  |  | 2020-08-24 | 2020-09-08
| Common Travelers | AUP | AUP-INSP-CMN-DN40 |  |  | 2020-08-24
| Common Travelers | AUP | AUP-INSP-CMN-DSCCRM |  |  | 2020-08-24 | 2020-09-08
| Common Travelers | AUP | AUP-INSP-CMN-FTPCSN |  |  | 2020-08-24 | 2020-09-08
|  | AUP | AUP-INSP-CMN-FTROD | R1 |  | 2020-09-08 | 2020-09-08
| H-HOM Damper | AUP | AUP-ASSY-DAMP-CLASSY |  |  | 2020-04-15
| H-HOM Damper | AUP | AUP-ASSY-DAMP-FASSY |  |  | 2020-04-15
| H-HOM Damper | AUP | AUP-ASSY-DAMP-FLGWLD |  |  | 2020-04-15
| H-HOM Damper | AUP | AUP-ASSY-DAMP-HKTEE |  |  | 2020-04-15
| H-HOM Damper | AUP | AUP-ASSY-DAMP-INCAN |  |  | 2020-04-15
| H-HOM Damper | AUP | AUP-ASSY-DAMP-NLASSY |  |  | 2020-04-15
| H-HOM Damper | AUP | AUP-ASSY-DAMP-TBASSY |  |  | 2020-04-15
| H-HOM Damper | AUP | AUP-INSP-DAMP-DN100 |  |  | 2020-04-15
| H-HOM Damper | AUP | AUP-INSP-DAMP-EXPIPE |  |  | 2020-04-15
| H-HOM Damper | AUP | AUP-INSP-DAMP-FLMCH |  |  | 2020-04-15
| H-HOM Damper | AUP | AUP-INSP-DAMP-HOOK |  |  | 2020-04-15
| H-HOM Damper | AUP | AUP-INSP-DAMP-ITUBE |  |  | 2020-04-15
| H-HOM Damper | AUP | AUP-INSP-DAMP-LDMCH |  |  | 2020-04-15
| H-HOM Damper | AUP | AUP-INSP-DAMP-NBLID |  |  | 2020-04-15
| H-HOM Damper | AUP | AUP-INSP-DAMP-OCLID |  |  | 2020-04-15
| H-HOM Damper | AUP | AUP-INSP-DAMP-TEE |  |  | 2020-04-15
| H-HOM Feedthrough | AUP | AUP-ASSY-HHOMFT-BRZAS |  |  | 2020-04-20
| H-HOM Feedthrough | AUP | AUP-ASSY-HHOMFT-FASSY |  |  | 2020-04-20
| H-HOM Feedthrough | AUP | AUP-ASSY-HHOMFT-FLBRZ |  |  | 2020-04-20
| H-HOM Feedthrough | AUP | AUP-INSP-HHOMFT-CURING |  |  | 2020-06-17
| H-HOM Feedthrough | AUP | AUP-INSP-HHOMFT-DN40F |  |  | 2020-04-20
| H-HOM Feedthrough | AUP | AUP-INSP-HHOMFT-DSCCRM |  |  | 2020-06-17
| H-HOM Feedthrough | AUP | AUP-INSP-HHOMFT-FTHMRD |  |  | 2020-06-17 | 2020-09-08
| H-HOM Feedthrough | AUP | AUP-INSP-HHOMFT-FTPCSN |  |  | 2020-06-17
| H-HOM Field Antenna | AUP | AUP-ASSY-FANT-BRZAS |  |  | 2020-04-20
| H-HOM Field Antenna | AUP | AUP-ASSY-FANT-FASSY |  |  | 2020-04-20
| H-HOM Field Antenna | AUP | AUP-ASSY-FANT-FLBRZ |  |  | 2020-04-20
| H-HOM Field Antenna | AUP | AUP-INSP-FANT-CABL |  |  | 2020-04-17
| H-HOM Field Antenna | AUP | AUP-INSP-FANT-CURING |  |  | 2020-06-17
| H-HOM Field Antenna | AUP | AUP-INSP-FANT-DN40 |  |  | 2020-04-17
| H-HOM Field Antenna | AUP | AUP-INSP-FANT-DSCCRM |  |  | 2020-06-17
| H-HOM Field Antenna | AUP | AUP-INSP-FANT-FTPCSN |  |  | 2020-06-17
| H-HOM Field Antenna | AUP | AUP-INSP-FANT-FTROD |  |  | 2020-06-17
| H-HOM Field Antenna | AUP | AUP-INSP-FANT-HOOK |  |  | 2020-04-17
| V-HOM Coupler | AUP | AUP-ASSY-VHOM-BRZAS |  |  | 2020-04-20
| V-HOM Coupler | AUP | AUP-ASSY-VHOM-FASSY |  |  | 2020-04-20
| V-HOM Coupler | AUP | AUP-ASSY-VHOM-FLBRZ |  |  | 2020-04-20
| V-HOM Coupler | AUP | AUP-INSP-VHOM-CURING |  |  | 2020-04-20
| V-HOM Coupler | AUP | AUP-INSP-VHOM-DN40 |  |  | 2020-06-17
| V-HOM Coupler | AUP | AUP-INSP-VHOM-DSCCRM |  |  | 2020-04-20
| V-HOM Coupler | AUP | AUP-INSP-VHOM-FTPCSN |  |  | 2020-06-17
| V-HOM Coupler | AUP | AUP-INSP-VHOM-FTROD |  |  | 2020-06-17
| V-HOM Coupler | AUP | AUP-INSP-VHOM-HOOK |  |  | 2020-06-17
| CHEM | AUP | AUP-CHEM-COMP-DEGR |  |  |  | 2020-07-06 |  | 2020-07-16
| INVENTORY | AUP | AUP-INV-CURING |  |  |  | 2020-06-15 |  | 2020-06-15
| INVENTORY | AUP | AUP-INV-DSCCRM |  |  |  | 2020-06-15 |  | 2020-06-15
| INVENTORY | AUP | AUP-INV-FTHMRD |  |  |  | 2020-06-15 |  | 2020-06-15
| INVENTORY | AUP | AUP-INV-FTROD |  |  |  | 2020-06-15 |  | 2020-06-15
| INVENTORY | AUP | AUP-INV-VH25H |  |  |  | 2020-07-29 |  | 2020-07-29
| CHEM | AUP | CP-AUP-CAV-CHEM-ACID |  |  | 2020-06-08 | 2020-06-08 |  | 2020-06-09 |  |  | 2020-06-10
| CHEM | AUP | CP-AUP-CAV-CHEM-DEGR |  |  | 2020-06-08 | 2020-06-08 |  | 2020-06-09 |  |  | 2020-06-10

## C20-C75
Received | Author | Project | Traveler/Procedure | REV | Que | Drafts | Sent for Approval | Left to Sign | Approved | Disapproved | In Pansophy | In Approved Folder? | Requests/Changes/Notes
|  | C20 | A LISTING OF C20 TRAVELERS/PROCEDURES
x |  | C20 | C20-CPR-DISA |  |  |  | Y |  | Y |  | Y
|  | C75 | A LISTING OF C75 TRAVELERS/PROCEDURES
|  | C75 | C75-ASSY-BPIP |  | Y
x |  | C75 | C75-CAV-INSP-FLG-COMP |  |  |  | Y
|  | C75 | C75-CMA-RECBP-ASSY |  | Y
x |  | C75 | C75-CM-RECV-CAPTOR-R1 |  |  |  | Y |  | Y |  | Y | Y
|  | C75 | C75-CPR-ASSY-DESTST |  | Y
|  | C75 | C75-CPR-ASSY-WDLC |  | Y
x |  | C75 | C75-CPR-CHEM-COMP |  | Y
|  | C75 | C75-CPR-DGLG-LEAK
x |  | C75 | C75-CPR-INSP-HOML-R2 |  |  |  | Y |  | Y |  | Y | Y
|  | C75 | C75-CPR-LAP-HOME |  | Y
x |  | C75 | C75-CPR-RECV-NEXTOR-R1 |  |  |  | Y |  | Y |  | Y | Y
x |  | C75 | C75-CU-ASSY-HELV-R1 |  |  |  | Y |  | Y |  | Y | Y
x |  | C75 | C75-CU-ASSY-TUNE-R1 |  |  |  | Y |  | Y |  | Y | Y
|  | C75 | C75-VTA-CPR-LEAKD |  |  |  | 2020-08-25
|  | C75 | C75-VTA-CPR-LEAKW |  |  |  | 2020-08-25
x |  | C75 | CP- C75-CAV-CHEM-BCP-FLNG-R1 |  | Y |  | CP-C75-CAV-CHEM-BCPFL-R1
x |  | C75 | CP-C75-ACID-ETCH-ENDD |  | Y |  | CP-C75-CHEM-ENDD
x |  | C75 | CP-C75-CAV-CHEM-FLAP-R1 |  |  |  | Y |  | Y |  | Y | Y
x |  | C75 | CP-C75-CAV-CHEM-USC-R1 |  |  |  | Y |  | Y |  | Y | Y
x |  | C75 | CP-C75-CM-BPIP-PUMPSL-R1 |  |  |  | Y |  | Y |  | Y | Y
x |  | C75 | CP-C75-CM-INST-MLI-R1 |  |  |  | Y |  | Y |  | Y | Y
x |  | C75 | CP-C75-CPR-CHEM-DEGR-HOML-R1 |  |  |  | Y |  | Y |  | Y | Y
x |  | C75 | CP-C75-CPR-CHEM-DGLG-R1 | [6 empty] | Y |  |  | Haven't received updated version
|  | C75 | CP-C75-CPR-DMAG-COMP-R1 |  |  |  | Y |  | Y |  | Y | Y
|  | C75 | CP-C75-CPR-LAP-COMP-R1 |  |  |  | Y |  | Y |  | Y | Y
x |  | C75 | CP-C75-CPR-VTRF |  | Y |  | 2020-08-11

## P1
Received | Author | Project | Traveler/Procedure | REV | Que | VAL AREA | Drafts | Sent for Approval | Left to Sign | Approved | Disapproved | In Pansophy | In Approved Folder? | Requests/Changes/Notes
| DRURY | P1 | P1-ACTS-CM | R1 |  | 2020-09-03 | 2020-09-03 | TO BE REVIEWED
| ASHLEY | P1 | P1-CHEM-CAV-BAKE | R1 |  | 2020-08-06 | 2020-08-06
| ASHLEY | P1 | P1-CHEM-CAV-DEGR | R1 |  | 2020-08-28 | 2020-08-28 | 2020-08-28 |  | 2020-09-03 |  | 2020-09-08 | 2020-09-08
2020-09-02 | ASHLEY | P1 | P1-CHEM-CAV-HEP | R1 |  | 2020-09-02 | 2020-09-02 | 2020-09-08 |  | 2020-09-09 |  | 2020-09-14 | 2020-09-14
| ASHLEY | P1 | P1-CHEM-CAV-HPR | R1 |  | 2020-08-28 | 2020-08-28
| ASHLEY | P1 | P1-CHEM-CAV-HPRN | R1 |  | 2020-09-08 | 2020-08-28 | 2020-08-28 |  | 2020-09-03 |  | 2020-09-08 | 2020-09-08
| ASHLEY | P1 | P1-CHEM-CAV-LAP | R1 |  | 2020-08-06 | 2020-08-06 | ASHLEY TO REVIEW
| ASHLEY | P1 | P1-CHEM-COMP-CLN | R1 |  | 2020-09-08 | 2020-08-06 | READY FOR APPROVAL
| FOREHAND | P1 | P1-CLNRM-CAV-ASSY | R1 |  | 2020-09-03 | 2020-09-03 | FIX / READY FOR APPROVAL
| FOREHAND | P1 | P1-CLNRM-CAV-TSTD | R1 |  | 2020-09-04 | 2020-09-04 | FIX / READY FOR APPROVAL
| FISCHER | P1 | P1-CMA-ASSY | R1 |  | 2012-09-04 | 2020-09-04
| FISCHER | P1 | P1-CMA-COAX | R1 |  | 2013-09-06 | 2020-09-06
| FISCHER | P1 | P1-CMA-COLD | R1 |  | 2012-07-16 | 2020-07-16
| FISCHER | P1 | P1-CMA-SFR | R1 |  | 2012-07-13 | 2020-07-13
| FISCHER | P1 | P1-CMA-SWEEP-INSP | R1 |  | 2020-08-06 | 2020-08-06 | TO BE REVIEWED
| FISCHER | P1 | P1-CMA-THTD-INSP | R1 |  | 2020-08-06 | 2020-08-06 | TO BE REVIEWED
| FISCHER | P1 | P1-CMA-THTS-INSP | R1 |  | 2020-08-06 | 2020-08-06 | TO BE REVIEWED
| FISCHER | P1 | P1-CMA-VV | R1 |  | 2020-07-16 | 2020-07-16
| FISCHER | P1 | P1-CMAWS2-CMAS-ASSY | R1 |  | 2020-09-03 | 2020-09-03 | TO BE REVIEWED
| FISCHER | P1 | P1-CMAWS3-SFR-ASSY | R1 |  | 2020-09-03 | 2020-09-03 | TO BE REVIEWED
| FISCHER | P1 | P1-CMAWS3-VV-ASSY | R1 |  | 2020-09-03 | 2020-09-03 | TO BE REVIEWED
| FISCHER | P1 | P1-CMAWS4-BPIP-ASSY | R1 |  | 2020-09-03 | 2020-09-03 | TO BE REVIEWED
| FISCHER | P1 | P1-CMAWS4-CM-ASSY | R1 |  | 2020-09-03 | 2020-09-03 | TO BE REVIEWED
| FISCHER | P1 | P1-CMA-WSPT-INSP | R1 |  | 2020-08-06 | 2020-08-06 | TO BE REVIEWED
| DRURY | P1 | P1-COMM-CM | R1 |  | 2013-02-25 | 2013-02-25
|  | P1 | P1-CST-ASSY | R1 |  | 2020-09-03 | 2020-09-03 | READY FOR APPROVAL
|  | P1 | P1-CST-BPIP | R1 |  | 2012-08-08 | 2012-08-08
| FOREHAND | P1 | P1-FURN-CAV-BAKE | R1 |  |  | 2020-08-06
| AARON | P1 | P1-INSP-ADPT (TO BE RM FROM P1/USE C100R) | R1 |  | 2020-09-08 | 2020-08-06 | 2020-09-08 |  | 2020-09-09 |  | 2020-09-14 | 2020-09-14
| AARON | P1 | P1-INSP-DSRF | R1 |  | 2020-08-06 | 2020-08-06 | TO BE RM P1 / USE C100R
| AARON | P1 | P1-INSP-FLNG
| AARON | P1 | P1-INSP-FPFT | R1 |  | 2020-08-06 | 2020-08-06
| AARON | P1 | P1-INSP-GVWG | R1 |  | 2020-08-06 | 2020-08-06 | LIANG TO REVIEW
| AARON | P1 | P1-INSP-HELV | R1 |  | 2020-07-30 | 2020-08-06 | 2020-08-06 |  | 2020-08-13 |  | 2020-08-13 | 2020-08-13
| AARON | P1 | P1-INSP-HMFT | R1 |  | 2020-08-06 | 2020-08-06
| AARON | P1 | P1-INSP-WGD-RCYC | R1 |  | 2020-09-02 | 2020-09-02 | LIANG TO REVIEW
| AARON | P1 | P1-INSP-WIN | R1 |  | 2020-08-06 | 2020-08-06 | TO BE RM P1 / USE C100R
| AARON | P1 | P1-INSP-WINM | R1 |  | 2020-08-06 | 2020-08-06 | NEEDS REVIEW
| FOREHAND | P1 | P1-TSTMS-COAX-INSP | R1 |  | 2020-08-06 | 2020-08-06 | TO BE REVIEWED
| FOREHAND | P1 | P1-TSTMS-DIO-INSP | R1 |  | 2020-08-06 | 2020-08-06
|  | P1 | P1-VTA-CAV-COOL | R1 |  | 2012-06-12
|  | P1 | P1-VTA-HOM | R1 |  | 2020-09-03 |  | HAIPENG TO REVIEW
|  | P1 | P1-VTA-CAV-HPRF | R1 |  | 2020-09-03 |  | TOM POWERS TO REVIEW
|  | P1 | P1-VTA-HOM-COOL | R1 |  | 2012-06-13 |  | IS THIS NEEDED?
| MACHA | P1 | P1-WELD-WIN-ASSY | R1 |  | 2020-06-29 | 2020-06-29 | 2020-08-13 |  | 2020-08-19 |  | 2020-08-28 | 2020-09-01
|  |  | P1-TUNE-CAV-RFIN | R1 |  | 2020-09-03 | 2020-09-08 | SENT TO ROLAND 9/22/20
|  |  | P1-CMA-HELV-REWRK | R1 |  |  |  | FISCHER TO WRITE
|  |  | P1-CMA-WIN-LEAK | R1 |  |  |  | IS THIS NEEDED?
|  |  | P1-TUNE-WINCR-RFIN | R1 |  |  |  | IS THIS NEEDED?
|  |  | P1-CHEM-STTL-CLN | R1 |  |  |  | IS THIS NEEDED?
|  |  | P1-CHEM-GVWG-CLN | R1 |  |  |  | IS THIS NEEDED?
|  |  | P1-CHEM-VALV-CLN | R1 |  |  |  | IS THIS NEEDED?
|  |  | P1-CHEM-COMP-HPR | R1 |  |  |  | IS THIS NEEDED?
|  |  | P1-ACC-CM-INST | R1 |  |  |  | TO BE WRITTEN
|  |  | P1-ACC-CM-COMM | R1 |  |  |  | TO BE WRITTEN

## OTHERS
Received | Author | Project | Traveler/Procedure | REV | Que | Drafts | Sent for Approval | Left to Sign | Approved | Disapproved | In Pansophy | In Approved Folder? | Requests/Changes/Notes
|  | L2PRD | A LISTING OF L2PRD TRAVELERS/PROCEDURES
x | ARI | L2PRD | CP-L2PRD-CST-FPC-RPLC |  |  |  | 2020-07-20
|  | sto | A LISTING OF STP TRAVELERS/PROCEDURES
x | Steve | STP | CP-STP-CAV-CHEM-BAKE-R1 |  |  |  | 2020-06-09
2020-09-02 | ASHLEY | STP | STP-CAV-CHEM-HEP | R4

## Sheet2
Received | Author | Project | Traveler/Procedure | REV | Que | Drafts | Sent for Approval | Left to Sign | Approved | Disapproved | In Pansophy | In Approved Folder? | Requests/Changes/Notes
|  | AUP | A LISTING OF AUP TRAVELERS/PROCEDURES
|  | AUP | AUP-ASSY-CMN-BRZAWS |  | Y
|  | AUP | AUP-ASSY-CMN-FLBRZ |  | Y
|  | AUP | AUP-INSP-CMN-CURING |  | Y
|  | AUP | AUP-INSP-CMN-DN40 |  | Y
|  | AUP | AUP-INSP-CMN-DSCCRM |  | Y
|  | AUP | AUP-INSP-CMN-FTPCSN |  | Y
|  | AUP | AUP-INSP-CMN-FTROD |  | Y
|  | C20 | A LISTING OF C20 TRAVELERS/PROCEDURES
x |  | C20 | C20-CPR-DISA |  |  |  | Y |  | Y |  | Y
|  | C75 | A LISTING OF C75 TRAVELERS/PROCEDURES
|  | C75 | C75-ASSY-BPIP |  | Y
x |  | C75 | C75-CAV-INSP-FLG-COMP |  |  |  | Y
|  | C75 | C75-CMA-RECBP-ASSY |  | Y
x |  | C75 | C75-CM-RECV-CAPTOR-R1 |  |  |  | Y |  | Y |  | Y | Y
|  | C75 | C75-CPR-ASSY-DESTST |  | Y
|  | C75 | C75-CPR-ASSY-WDLC |  | Y
x |  | C75 | C75-CPR-CHEM-COMP |  | Y
|  | C75 | C75-CPR-DGLG-LEAK
x |  | C75 | C75-CPR-INSP-HOML-R2 |  |  |  | Y |  | Y |  | Y | Y
|  | C75 | C75-CPR-LAP-HOME |  | Y
x |  | C75 | C75-CPR-RECV-NEXTOR-R1 |  |  |  | Y |  | Y |  | Y | Y
x |  | C75 | C75-CU-ASSY-HELV-R1 |  |  |  | Y |  | Y |  | Y | Y
x |  | C75 | C75-CU-ASSY-TUNE-R1 |  |  |  | Y |  | Y |  | Y | Y
|  | C75 | C75-VTA-CPR-LEAKD |  |  |  | 2020-08-25
|  | C75 | C75-VTA-CPR-LEAKW |  |  |  | 2020-08-25
x |  | C75 | CP- C75-CAV-CHEM-BCP-FLNG-R1 |  | Y |  | CP-C75-CAV-CHEM-BCPFL-R1
x |  | C75 | CP-C75-ACID-ETCH-ENDD |  | Y |  | CP-C75-CHEM-ENDD
x |  | C75 | CP-C75-CAV-CHEM-FLAP-R1 |  |  |  | Y |  | Y |  | Y | Y
x |  | C75 | CP-C75-CAV-CHEM-USC-R1 |  |  |  | Y |  | Y |  | Y | Y
x |  | C75 | CP-C75-CM-BPIP-PUMPSL-R1 |  |  |  | Y |  | Y |  | Y | Y
x |  | C75 | CP-C75-CM-INST-MLI-R1 |  |  |  | Y |  | Y |  | Y | Y
x |  | C75 | CP-C75-CPR-CHEM-DEGR-HOML-R1 |  |  |  | Y |  | Y |  | Y | Y
x |  | C75 | CP-C75-CPR-CHEM-DGLG-R1 | [6 empty] | Y |  |  | Haven't received updated version
|  | C75 | CP-C75-CPR-DMAG-COMP-R1 |  |  |  | Y |  | Y |  | Y | Y
|  | C75 | CP-C75-CPR-LAP-COMP-R1 |  |  |  | Y |  | Y |  | Y | Y
x |  | C75 | CP-C75-CPR-VTRF |  | Y |  | 2020-08-11
|  | L2PRD | A LISTING OF L2PRD TRAVELERS/PROCEDURES
x | ARI | L2PRD | CP-L2PRD-CST-FPC-RPLC |  |  |  | 2020-07-20
|  | SNSPPU | A LISTING OF SNSPPU TRAVELERS/PROCEDURES
| K.MACHA | SNSPPU | CP-SNSPPU-CAV-ASSY-HELV | R1 |  | 2020-01-14 | [5 empty] | 2020-03-11
| C.WILSON | SNSPPU | CP-SNSPPU-CAV-VTA-OPS | R1 |  | 2020-02-03
| K.MACHA | SNSPPU | CP-SNSPPU-CM-ENDC-INST | R1 |  | 2020-07-31
| K.MACHA | SNSPPU | CP-SNSPPU-CST-COUP-INST | R1 |  | 2020-07-29
| K.MACHA | SNSPPU | CP-SNSPPU-CST-TOOL-PREP | R1 |  | 2020-07-29
2020-07-17 | GARY | SNSPPU | SNSPPU_MasterTravelerListing_25June2020_Cheng
| KURT MACHA | SNSPPU | SNSPPU-CAV-ASSY-HELV | R1 |  | 2020-03-19 | [5 empty] | 2020-07-14
2020-07-23 | FOREHAND | SNSPPU | SNSPPU-CAV-BAKE | R1 | [8 empty] | Needs a bake procedure
2020-06-11 | PASHUPATI | SNSPPU | SNSPPU-CAV-INSP | R1
|  | SNSPPU | SNSPPU-CAV-INSP-HEHDF-R1 |  |  | 2020-08-24
|  | SNSPPU | SNSPPU-CAV-INSP-HEHDP-R1 |  |  | 2020-08-24
2020-06-11 | PASHUPATI | SNSPPU | SNSPPU-CAV-RFIN | R1
2020-06-11 | PASHUPATI | SNSPPU | SNSPPU-CAV-TRANS-TSTD | R1 | [8 empty] | NEEDS A PROCEDURE
| K DAVIS | SNSPPU | SNSPPU-CAV-VTRF | R1 | [7 empty] | 2020-02-26
| K DAVIS | SNSPPU | SNSPPU-CAV-VTRF | R2 |  |  | 2020-08-13 |  | 2020-08-24
| K.MACHA | SNSPPU | SNSPPU-CMA-AMGV-LEAK | R1 |  |  | 2020-06-25 |  | 2020-08-04
2020-08-03 | GARY | SNSPPU | SNSPPU-CMA-CMASS-ASSY | R1 |  |  | 2020-08-07 | ED DALY
2020-06-25 | OWEN | SNSPPU | SNSPPU-CMA-FT08P-LEAK | R1 |  |  | 2020-06-25 |  | 2020-07-15 |  | Y | Y
2020-07-22 | FISCHER | SNSPPU | SNSPPU-CM-ASSY-CMA | R1 |  | 2020-08-07
2020-07-22 | FISCHER | SNSPPU | SNSPPU-CM-ASSY-CMA-R1_Final | R1
2020-06-26 | MARCHLIK | SNSPPU | SNSPPU-CM-ASSY-SFTS | R1
|  | SNSPPU | SNSPPU-CM-INSP-ELFT |  |  | 2020-08-24
x |  | SNSPPU | SNSPPU-CM-INSP-FT08P | R1 |  |  | 2020-07-15 |  | 2020-08-04 |  | Y
x |  | SNSPPU | SNSPPU-CM-INSP-INFF | R1 |  | 2020-05-21 | Y |  | Y |  | Y
| MARCHLIK | SNSPPU | SNSPPU-CM-INSP-PRPA | R1 | [7 empty] | 2020-07-14
2020-06-16 | MARCHLIK | SNSPPU | SNSPPU-CM-INSP-SFR-R1 |  |  |  | 2020-06-25 |  | 2020-07-21
x |  | SNSPPU | SNSPPU-CM-INSP-THRM-R1 |  |  |  | 2020-05-28 |  | 2020-07-21 |  | Y | SNSPPU-INSP-THRM-P1; 7/14/2020
2020-06-11 | MARCHLIK | SNSPPU | SNSPPU-CM-INSP-THRMST-R1 |  |  |  | 2020-07-02 |  | 2020-07-21 |  | Y
| MARCHLIK | SNSPPU | SNSPPU-CM-INSP-TPHT | R1 | [7 empty] | 2020-07-14
| MARCHLIK | SNSPPU | SNSPPU-CM-INSP-TPHTB | R1 | [7 empty] | 2020-07-14
| HUQUE | SNSPPU | SNSPPU-CM-INSP-TUNC | R1 |  | 2020-04-16 | [5 empty] | 2020-07-14
|  | SNSPPU | SNSPPU-CM-INSP-TUNF | R1 |  | 2020-03-19
|  | SNSPPU | SNSPPU-CM-LEAK-FT08P | R1 |  |  | 2020-06-25 |  | 2020-07-15 |  |  | SNSPPU-CMA-FT08P-LEAK-R1; 7/20/20
| MARCHLIK | SNSPPU | SNSPPU-CM-LEAK-INFF | R1 |  | 2020-04-23 | [5 empty] | 2020-07-14
| MARCHLIK | SNSPPU | SNSPPU-CM-LEAK-PRPA | R1 | [7 empty] | 2020-07-14
| MARCHLIK | SNSPPU | SNSPPU-CM-LEAK-THRM | R1 |  |  | 2020-04-29 |  | 2020-05-19 |  |  | 2020-07-14
| MARCHLIK | SNSPPU | SNSPPU-CM-LEAK-THRMST | R1 |  |  | 2020-05-19 |  | 2020-06-02 |  |  | 2020-07-14
| MARCHLIK | SNSPPU | SNSPPU-CM-LEAK-TPHT | R1 | [7 empty] | 2020-07-14
| MARCHLIK | SNSPPU | SNSPPU-CM-LEAK-TPHTB | R1 |  | 2020-04-14 | [5 empty] | 2020-07-14
2020-07-23 | FOREHAND | SNSPPU | SNSPPU-CST-ASSY | R1 |  | 2020-08-24 | [6 empty] | King asked for cernox var name changes
|  | SNSPPU | SNSPPU-CST-INSP-BLBP | R1 |  | 2020-08-24
|  | SNSPPU | SNSPPU-CST-INSP-PRPA | R1 |  | 2020-03-19 | [5 empty] | SNSPPU-CM-INSP-PRPA-R1: 7/14/20
2020-06-16 |  | SNSPPU | SNSPPU-CST-INSP-SFR | R1
|  | SNSPPU | SNSPPU-CST-INSP-SW2C | R1 |  | 2020-08-24
|  | SNSPPU | SNSPPU-CST-INSP-TPHTB | R1 |  | 2020-04-14 | [5 empty] | SNSPPU-CM-INSP-TPHTB-R1; 7/14/20
x |  | SNSPPU | SNSPPU-CST-LEAK-AMGV | R1 |  |  | 2020-06-25 |  | 2020-08-04 |  | Y
2020-06-18 | KWILSON | SNSPPU | SNSPPU-CST-LEAK-GVLV | R1 |  | 2020-08-24
|  | SNSPPU | SNSPPU-CST-LEAK-PRPA | R1 |  | 2020-03-19 | [5 empty] | SNSPPU-CM-LEAK-PRPA-R1; 7/14/20
|  | SNSPPU | SNSPPU-CST-LEAK-TPHTB | R1 |  | 2020-04-08
|  | SNSPPU | SNSPPU-CST-LEAK-TPHT-R1 |  |  | 2020-04-08
x | OWEN | SNSPPU | SNSPPU-ELEC-FT08P-CHK | R1 |  |  | 2020-07-15 | Kushnick | Y |  | Y
| OWEN | SNSPPU | SNSPPU-INSP-FT08P | R1
2020-07-13 | K.WILSON | SNSPPU | SNSPPU-INSP-HES | R1 |  |  | 2020-07-15 |  | 2020-08-06 |  | 2020-08-06
2020-08-03 | GARY | SNSPPU | SNSPPU-INSP-IMAG | R1 |  | 2020-08-07 | 2020-08-07 |  | 2020-08-13
| MARCHLIK | SNSPPU | SNSPPU-INSP-INFF | R1
2020-08-03 | GARY | SNSPPU | SNSPPU-INSP-OMAG |  |  | 2020-08-14 | 2020-08-07 |  | 2020-08-19
2020-06-16 | MARCHLIK | SNSPPU | SNSPPU-INSP-SFR | R1 |  |  | 2020-06-25 |  | 2020-07-21
2020-04-20 | MARCHLIK | SNSPPU | SNSPPU-INSP-THRM | R1 |  |  | 2020-05-28 |  | 2020-07-21 |  | Y | 2020-07-14
2020-06-11 | MARCHLIK | SNSPPU | SNSPPU-INSP-THRMST | R1 |  |  | 2020-07-02 |  | 2020-07-21 |  | Y
| M.DICKEY | SNSPPU | SNSPPU-INV-BLBFA | R1 |  | 2020-04-29 | 2020-05-04 |  | 2020-05-04 |  |  | 2020-07-14
| M.DICKEY | SNSPPU | SNSPPU-INV-BLBP | R1 | [7 empty] | SNSPPU-INV-BLBP-R1; 2/26/20
| M.DICKEY | SNSPPU | SNSPPU-INV-BLIPT | R1 |  |  | 2020-05-04 |  | 2020-05-04 |  |  | 2020-02-26
| M.DICKEY | SNSPPU | SNSPPU-INV-CAV | R1 | [7 empty] | 2020-02-26
2020-06-04 | GARY | SNSPPU | SNSPPU-INV-CMMC | R1 |  |  | 2020-06-18 |  | 2020-06-30
| M.DICKEY | SNSPPU | SNSPPU-INV-DCXCU | R1 | [7 empty] | 2020-02-26
| M.DICKEY | SNSPPU | SNSPPU-INV-DCXCU | R1 | [7 empty] | 2020-02-26
2020-06-18 | GARY | SNSPPU | SNSPPU-INV-EQFH | R1 |  |  | 2020-06-18 |  | 2020-06-30 |  |  | 2020-07-14
| M.DICKEY | SNSPPU | SNSPPU-INV-FPC | R1 | [7 empty] | 2020-02-26
| M.DICKEY | SNSPPU | SNSPPU-INV-FT06P | R1 | [7 empty] | 2020-07-14
| M.DICKEY | SNSPPU | SNSPPU-INV-FT10P | R1 | [7 empty] | 2020-07-14
2020-06-18 | GARY | SNSPPU | SNSPPU-INV-GVPA | R1 |  |  | 2020-06-18 |  | 2020-06-30 |  |  | 2020-07-14
| M.DICKEY | SNSPPU | SNSPPU-INV-HEHDF | R1 | [7 empty] | 2020-02-26
| M.DICKEY | SNSPPU | SNSPPU-INV-HEHDP | R1 | [7 empty] | 2020-02-26
| M.DICKEY | SNSPPU | SNSPPU-INV-HEIBA | R1 |  |  | 2020-06-18 |  | 6/30/202 | 2020-06-18
| M.DICKEY | SNSPPU | SNSPPU-INV-HES | R1 | [7 empty] | 2020-02-26
| M.DICKEY | SNSPPU | SNSPPU-INV-HLS | R1 | [7 empty] | 2020-02-26
| M.DICKEY | SNSPPU | SNSPPU-INV-HMDR | R1 | [7 empty] | 2020-02-26
| M.DICKEY | SNSPPU | SNSPPU-INV-IMAG | R1 | [7 empty] | 2020-02-26
| M.DICKEY | SNSPPU | SNSPPU-INV-JTV | R1 | [7 empty] | 2020-02-26
| M.DICKEY | SNSPPU | SNSPPU-INV-JTVA | R1 | [7 empty] | 2020-02-26
| M.DICKEY | SNSPPU | SNSPPU-INV-JTVIB | R1 |  |  | 2020-05-04 |  | 2020-05-19 |  |  | 2020-07-14
| M.DICKEY | SNSPPU | SNSPPU-INV-JTVOB | R1 |  |  | 2020-05-04 |  | 2020-05-19 |  |  | 2020-07-14
x | M.DICKEY | SNSPPU | SNSPPU-INV-LDS12 | R1 |  |  | 2020-07-06 |  | 2020-07-13 |  | Y | 2020-07-14
x | M.DICKEY | SNSPPU | SNSPPU-INV-LDS34 | R1 |  |  | 2020-07-06 |  | 2020-07-13 |  | Y | 2020-07-14
x | M.DICKEY | SNSPPU | SNSPPU-INV-LDS34H | R1 |  |  | 2020-07-06 |  | 2020-07-14 |  | Y | 2020-07-14
| M.DICKEY | SNSPPU | SNSPPU-INV-OMAG | R1 | [7 empty] | 2020-02-26
x | M.DICKEY | SNSPPU | SNSPPU-INV-OMAGRE | R1 |  |  | 2020-07-29 |  | 2020-08-06
x | M.DICKEY | SNSPPU | SNSPPU-INV-OMAGSE | R1 |  |  | 2020-07-29 |  | 2020-08-06
| M.DICKEY | SNSPPU | SNSPPU-INV-PBD | R1 | [7 empty] | 2020-02-26
| M.DICKEY | SNSPPU | SNSPPU-INV-PRPA | R1 | [7 empty] | 2020-02-26
| M.DICKEY | SNSPPU | SNSPPU-INV-RENC | R1 | [7 empty] | 2020-02-26
2020-06-18 | GARY | SNSPPU | SNSPPU-INV-RPIPE | R1 |  |  | 2020-06-18 |  | 2020-06-30 |  |  | 2020-07-14
| M.DICKEY | SNSPPU | SNSPPU-INV-SENC | R1 | [7 empty] | 2020-02-26
| M.DICKEY | SNSPPU | SNSPPU-INV-SFR | R1 | [7 empty] | 2020-02-26
| M.DICKEY | SNSPPU | SNSPPU-INV-SM | R1 | [7 empty] | 2020-07-14
2020-06-18 | GARY | SNSPPU | SNSPPU-INV-SPIPE | R1 |  |  | 2020-06-18 |  | 2020-06-30 |  |  | 2020-07-14
| M.DICKEY | SNSPPU | SNSPPU-INV-THRM | R1 | [7 empty] | 2020-02-26
| M.DICKEY | SNSPPU | SNSPPU-INV-TJVIB | R1
| M.DICKEY | SNSPPU | SNSPPU-INV-TPHP | R1 | [7 empty] | 2020-02-26
| M.DICKEY | SNSPPU | SNSPPU-INV-TPHT | R1 | [6 empty] | Y | 2020-02-26
| M.DICKEY | SNSPPU | SNSPPU-INV-TUNC | R1 |  | 2020-04-20 | [5 empty] | 2020-07-14
| M.DICKEY | SNSPPU | SNSPPU-INV-VV | R1 | [7 empty] | 2020-02-26
| M.DICKEY | SNSPPU | SNSPPUT-CM-LEAK-INFF | R1
x | M.DICKEY | SNSPPU | SNSPPU-VTA-CSHK-FT08P | R1 |  |  | 2020-06-25 |  | 2020-08-05 |  | Y
x | Steve | STP | CP-STP-CAV-CHEM-BAKE-R1 |  |  |  | 2020-06-09