## Plan
SRF Work Center Planning
|  | WORK CENTERS | [22 empty] | Updated 04-11-2013
|  | FABRICATION |  | Inspection |  |  | Tune & Heat Treat |  | Chemistry | [7 empty] | Assembly | [6 empty] | Vertical Test | CMA L2 WS2 | CMA L2 WS3 | CMA L2 WS4 | CMA L2 WS5 | CMA C75 | CMA Other | CMA P1 | CMA SNS PPU | CEBAF |  | CMTF
|  | EBW | Brazing& Sputter | CMM | Other |  | Tuning | Heat Treat | Lapping | Thickness | Bench Chem | De-grease | BCP | HEP | HPR |  | Pre-Assy | Dis-Assy | Assy Evac | Leak Test | Bake | Vertical Test Prep | Slow Bleed | VTA
2017-10-01 | Sun | [13 empty] | HPR1: HPR2:
2017-10-02 | Mon |  | HOM Damper Deposition Parts | L2 bellows/spools L2-295 L2 BLA #2 visual |  |  |  | TC1N1 w/caps; | Twin1 BP; |  | Deposition parts; Test stand parts; Flanges x2; | Lollipop parts; Deposition parts; |  |  | HPR1: OOC HPR2: LSF1-3 |  | C50 pair dis; |  |  | L2-279; L2-281; |  | L2-278/286/116 HOMs and sensors | DQW2 | D1: SIC pull D2: D3: D4: D5: L2-278/286/116 L/precool D6: D7: D8: L2-284 pull; | C50- Disassembly complete LCLSll CM03-HOM's,Tuner repair Cav1, Investigate coupler Cav 4 CM04- Install MC line, Instrumentation flanges, Bayonet box CM05- RF cables, Instrumentation, Tune HOM's, Move to Cantilever CM07- idling, Swap 4 poster tooling Other- | [7 empty] | 1L03
2017-10-03 | Tue | C75 samples; | HOM Damper Hall A Collimator | L2 bellows/spools L2 BLA #2 visual |  |  | J1.3-03; | TC1N1 w/caps 1200C/30h; | Twin1 BP; |  | Deposition parts; LSF1-2; Sample holder; Nb Flanges; View port; | Lollipops; Deposition parts;Dog leg flanges x12; Al ceramic tooling; |  |  | HPR1: OOC HPR2: LSF1-3 |  | L2-261 FP inspect/replace; Lollipops; |  | L2-276 D7/8; LSF1-3; |  |  | L2-279 HOMs and sensors; | L2-284 | D1: SIC L/C/T/W D2: D3: D4: D5: L2-278/286/116 C4K D6: D7: D8: | C50- Disassembly complete LCLSll CM03-HOM's,Tuner repair Cav1, Investigate coupler Cav 4 CM04- Install MC line, Instrumentation flanges, Bayonet box CM05- RF cables, Instrumentation, Tune HOM's CM07- idling Other- | [7 empty] | 1L16 cool down to 4K complete 1L19 ready for 4K cool down 1L17 4K cool down complete 0L03 4K cool down complete 1L20 cool down complete 1L15 cool down complete 1L19 cool down complete 1L21 cool down complete 1L03 cool down complete 1 cryomodule still warm 1L15 relief valve replacement in progress
2017-10-04 | Wed | CRN-5; RFD damper; | Hall A Collimater L2 Bellows | L2 bellows/spools |  |  |  | TC1N1 w/caps 1200C/30h; | Twin1 BP; |  | Deposition parts; LSF1-2; Damper test piece | L2 BLA #2; Deposition parts; LSF1-2; Cu Gaskets; Flanges x4; Twin1; Bellows clamps; Blanks & clamps; BLA Box; |  |  | HPR1: OOC HPR2: L2-288 |  | L2-288 dis |  | L2 BLA #1; DQW2; | L2-276; |  | L2-281 HOMs and sensors; |  | D1: SIC C/T/W D2: D3: D4: D5: L2-278/286/116 C2K/T/W D6: LSF1-3 C2K/T/W D7: L2-279 L/C4K D8: | C50- Disassembly complete LCLSll CM03-HOM's,Tuner repair Cav1, Investigate coupler Cav 4 CM04- Install MC line, Instrumentation flanges, Bayonet box CM05- RF cables, Instrumentation, Tune HOM's CM07- Alignment crew UCM Other- Flex line fab crane lift VV and UCM | [7 empty] | 1L19 ready for 4K cool down 1L17 4K cool down complete 0L03 4K cool down complete 1L20 cool down complete 1L15 cool down complete 1L19 cool down complete 1L21 cool down complete 1L03 cool down complete 1 cryomodule still warm 1L15 relief valve replacement completed
2017-10-05 | Thu | CRN-5; RFD damper; | Hall A Collimater HZB Loads | USLARP HOM L2 bellows/spools |  |  | J1.3-03; | LSF1-2 w/caps 1200C/30h; | Twin1 BP; |  | Nb caps; Deposition parts; Beam tubes; | Deposition parts; Nb/Ti Flanges; L2-295 wipe; L2 covers and clamps; L2 bellow test; 10" flanged can; |  |  | HPR1: OOC HPR2:TD-5 L2-288 |  | L2-288 L2-284 pass out |  |  | L2 BLA #1; DQW2; |  | L2-276 HOMs and sensors |  | D1: SIC W/C/T D2: D3: D4: D5: L2-278/286/116 warm D6: D7: L2-279 C2K/T/W D8: | C50- CM Disassembly complete, Serializing parts LCLSll CM03-HOM's, Close VV, ins vac, re-HOM CM04- Install MC line, Instrumentation flanges, Pressure Test Noon, Bayonet box CM05- Instrumentation, heat stations, Tune HOM's CM07- Cold mass under UCM, Unite CM08- Alignment crew UCM Other- Prep VV at Blue Crab | [7 empty] | 1L17 4K cool down complete 0L03 4K cool down complete 1L20 cool down complete 1L15 cool down complete 1L19 cool down complete 1L21 cool down complete 1L03 cool down complete 1 cryomodule still warm 1L15 relief valve replacement completed CHL1 pumpdown delayed ~5 days after "drilling event" 1L24 BL Vac recovered
2017-10-06 | Fri | CRN-5; | Hall A Collimater HZB Loads | L2 bellows/spools C75 DL USLARP HOM |  |  | J1.3-03; | LSF1-2 w/caps 1200C/30h; | Twin1 BP; |  | Deposition parts; Sample chamber and plate; Beam tube; | Deposition parts; Bellows hardware; |  |  | HPR1: OOC HPR2: |  | L2-bellows study; |  | L2-288 |  |  | L2-281 HOMs; | L2-278 | D1: SIC C/T/W D2: D3: D4: D5: L2-278/286/116 pull D6: D7: L2-279 warm D8: L2-281 L/C2K/T/W | C50- CM Disassembly complete, Serializing parts LCLSll CM03-HOM's, Close VV, ins vac, re-HOM, into CMTF CM04- LC MC line, Instrumentation flanges, Bayonet box CM05- Instrumentation, heat stations, Tune HOM's CM07- Cold mass under UCM, Unite CM08- Alignment crew UCM Other- Prep VV at Blue Crab | [7 empty] | 0L03 4K cool down complete 1L20 cool down complete 1L15 cool down complete 1L19 cool down complete 1L21 cool down complete 1L03 cool down complete 1 cryomodule still warm 1L15 relief valve replacement completed CHL1 pumpdown delayed ~5 days after "drilling event" 1L24 BL Vac recovered 1L15 ready for 4K cool down today CHL1 pumpdown ~Monday
2017-10-07 | Sat
2017-10-08 | Sun | [13 empty] | HPR1: HPR2:
2017-10-09 | Mon | RFD damper; | Deposition parts RFD Damper | L2 VV008 C50 dogleg parts |  |  |  | Deposition parts; 400C/3h | CRN-1 flanges; |  | Deposition cavity & Nb rod; | BLA #2 parts; Deposition parts & valves; L2 Bellows; Flange; C50 flange brackets; | IA-016 setup; |  | HPR1: OOC HPR2: L2-102; L2-130; |  | L2-278 dis/sample; |  | L2-295 D7/8; | L2-288 |  |  |  | D1: SIC C/T/W D2: TC Load D3: D4: D5: D6: D7: L2-279 pull; D8: L2-281 pull; L2-276 L/C4K | C50- CM Disassembly complete, Serializing parts LCLSll CM03-HOM measure, LC VV, align CM, Condition circuiits CM04- LC MC line, Instrumentation flanges, Pressure Test, Bayonet box CM05- Instrumentation, heat stations, Tune HOM's CM07- Cold mass under UCM, Unite CM08- Alignment crew UCM Other- QC VV at Blue Crab | [7 empty] | 1L20 cool down complete 1L15 cool down complete 1L19 cool down complete 1L21 cool down complete 1L03 cool down complete 1 cryomodule still warm 1L15 relief valve replacement completed CHL1 pumpdown delayed ~5 days after "drilling event" 1L24 BL Vac recovered 1L15 4K cool down complete Zero warm cryomodules CHL1 pumpdown Today (we hope) |  | CM03 back in Cave
2017-10-10 | Tue |  | BLA absorber ring 300C/6h; Hall A Col | L2 VV008 C50 dogleg parts L2 HOM/Field Probes |  |  |  | BLA #2 600C/6H; | CRN-1 flanges; |  |  | Deposition parts & valves; Elbows; L2 clamps and blanks; L2-113 bolt holes; L2-106 bolt holes; |  |  | HPR1: OOC HPR2: L2-122; L2-270; |  |  |  | L2-102, L2-130 to rail; | L2-295; |  | L2-288 HOMs and sensors; | L2-279 | D1: SIC C/T/W D2: TC hold D3: D4: D5: D6: Coax L/C/T D7: L2-288 L D8: L2-276 C2K/T/W | C50- CM Disassembly complete, Serializing parts LCLSll CM03-LC VV, Condition circuiits, demag CM CM04- Instrumentation flanges, Add Bayonet box, Close VV sideport CM05- Instrumentation, heat stations, Tune HOM's CM07- Cold mass under UCM, Unite, Develop Tuner/GV Procedure, LC VV, Weld 2 phase piping CM08- Alignment crew UCM Other- QC VV at Blue Crab, Relocate VV from UITF to Floor | [7 empty] | 1L15 cool down complete 1L19 cool down complete 1L21 cool down complete 1L03 cool down complete 1 cryomodule still warm 1L15 relief valve replacement completed CHL1 pumpdown delayed ~5 days after "drilling event" 1L24 BL Vac recovered 1L15 4K cool down complete Zero warm cryomodules CHL1 pumpdown successful- modules still need filling |  | CM03 back in Cave HOM measurements completed
2017-10-11 | Wed | Cern5 | BLA absorber ring 300C/6h; Hall A Col | C50 dogleg parts L2 UCM020 |  |  | L2 Cav | BLA #2 600C/6H; |  |  | EIC Flange/ 1/2 Cell x2, flange; | Deposition parts & valves; L2 blanks x10; 5 cell & hardware; Eyewash station; |  |  | HPR1: OOC HPR2: L2-113; L2-099; |  |  |  | L2-122, L2-270 to rail; |  |  | L2-295 HOMs and sensors | L2-281 | D1: SIC C/T D2: TC hold D3: D4: D5: D6: Coax Warm D7: L2-288 C4K D8: L2-276 warm | C50- CM Disassembly complete, Serializing parts LCLSll CM03-U-tubes, cooldown CM04- LC Bayonet box, Close VV sideport CM05- Instrumentation, RF Cable measurements, heat stations, Tune HOM's CM07- Develop Tuner/GV Procedure, LC VV, 2 phase welding CM08- Alignment crew UCM Other- repack VV at Blue Crab, welding walk overs and LCLS beampipes | [7 empty] | 1L19 cool down complete 1L21 cool down complete 1L03 cool down complete 1 cryomodule still warm 1L15 relief valve replacement completed CHL1 pumpdown delayed ~5 days after "drilling event" 1L24 BL Vac recovered 1L15 4K cool down complete Zero warm cryomodules Still stable at 2K |  | CM03 back in Cave - cool down today HOM measurements completed
2017-10-12 | Thu | Cern5 | BLA absorber ring 300C/6h; Hall A Col | C50 dogleg parts L2-304 L2 UCM020 L2 bellows/spools L2 Tuner |  |  | L2-304 | TD-5 |  |  | Gas distributor; | Deposition parts & valves; L2 bellows x10; L2- 299 hardware and FT; | IA-016 15u; |  | HPR1: OOC HPR2: LSF 1-2 |  | BLA #2 inpection |  |  |  |  | DQW2 sensors; L2-295 |  | D1: SIC W D2: TC hold D3: D4: D5: D6: D7: L2-288 C2K/T D8: L2-276 pull; L2-295 L/C4K | C50- CM Disassembly complete, Serializing parts LCLSll CM03- cooldown CM04- LC Bayonet box, Close VV sideport CM05- Instrumentation, RF Cable measurements, heat stations, Tune HOM's CM07- Develop Tuner/GV Procedure, LC VV, 2 phase welding, heat stations CM08- ucm ready Other- repack VV at Blue Crab, welding walk overs | [7 empty] | 1L21 cool down complete 1L03 cool down complete 1 cryomodule still warm 1L15 relief valve replacement completed CHL1 pumpdown delayed ~5 days after "drilling event" 1L24 BL Vac recovered 1L15 4K cool down complete Zero warm cryomodules Still stable at 2K RF Recovery activities in progress |  | CM03 back in Cave - cool down started Cav temps ~ 135 K, rate~ 5K /hr
2017-10-13 | Fri | Cern5 | Hall A Col | L2-304 L2 bellows/spools |  |  | L2-305; L2-306 | TD-5 |  |  |  | Deposition parts & valves; | IA-320 setup |  | HPR1: OOC HPR2: RDT-2 |  |  |  | LSF1-2; | LSF1-2; |  |  | L2-276 | D1: D2: TC C1.6K/T D3: D4: D5: D6: D7: L2-288 hold D8: L2-295 hold | C50- CM Disassembly complete, Serializing parts LCLSll CM03- cooldown CM04- LC Bayonet box, Close VV sideport CM05- Instrumentation, RF Cable measurements, heat stations, Tune HOM's CM07- Develop Tuner/GV Procedure, LC VV, 2 phase welding, heat stations CM08- ucm ready Other- repack VV at Blue Crab, welding walk overs | [7 empty] | 1L03 cool down complete 1 cryomodule still warm 1L15 relief valve replacement completed CHL1 pumpdown delayed ~5 days after "drilling event" 1L24 BL Vac recovered 1L15 4K cool down complete Zero warm cryomodules CHL fire NL still losing liquid SL starting to turn around C100's drained over night and staerted to warm up linacs currently at 4K |  | CM03 back in Cave - cool down started Cav temps ~ 50 K, rate~ 2K /hr
2017-10-14 | Sat
2017-10-15 | Sun | [13 empty] | HPR1: HPR2:
2017-10-16 | Mon | maint | Hall A columnator; | C50 dogleg parts ; L2-305 |  |  |  | TD-5 | Nb Blanks |  | SS etch flanges; Disc 5u; Nb parts; | L2 parts and HW; Deposition parts; Loads; | IA-320 15u; |  | HPR1: OOC HPR2: L2-289; L2-113; |  |  |  | Deposition valves; L2-297 D7/8; RDT-2; |  |  | LSF1-2 level sensor; |  | D1: SIC D2: TC C4K/T (3) D3: DQW2 L/C2K/T (1) D4: LSF1-2 L/C4K (4) D5: warm D6: LSF1-3 L D7: L2-288 warm D8: L2-295 C2K/T/W (2) | C50- CM Disassembly complete, Serializing parts LCLSll CM03- Testing CM04- LC Bayonet box, Close VV sideport CM05- heat stations, Tune HOM's CM07- Develop Tuner/GV Procedure, LC VV, 2 phase welding, heat stations CM08- ucm ready Other- repack VV at Blue Crab, welding walk overs | [7 empty] | 1L15 relief valve replacement completed CHL1 pumpdown delayed ~5 days after "drilling event" 1L24 BL Vac recovered 1L15 4K cool down complete Zero warm cryomodules CHL fire SL starting to turn around C100's drained over night and started to warm up linacs currently at 4K testing delayed -not clear how long. |  | CM03 back in Cave - 2K since Sunday liquid level imbalance needs to be understood before testing can start (35% supply / 90% return)
2017-10-17 | Tue | CERN-5 | Hall A columnator; | C50 dogleg parts ; L2-305 L2 Tuner Frames L2-306 |  |  | L2-308; |  |  |  |  | L2-304; L2 string hardware; |  |  | HPR1: OOC HPR2: L2-099; L2-106; |  |  |  | L2-113 and L2-289 to rail; BLA #2 (pm); | L2-297; RDT-2; |  |  |  | D1: SIC C2K/T D2: TC C/T D3: DQW2 HOM test D4: LSF1-2 C2K/T D5: warm D6: LSF1-3 C/T/W D7: L2-0288 hold D8: L2-295 warm | C50- CM Disassembly complete, Serializing parts LCLSll CM03- Testing CM04- LC Bayonet box, Close VV sideport CM05- heat stations, Tune HOM's CM07- Develop Tuner/GV Procedure, LC VV, 2 phase welding, heat stations CM08- ucm ready Other- repack VV at Blue Crab, welding walk overs
2017-10-18 | Wed | CERN-5; SNS MB; | HOM loads; C50 WW; | L2-308 L2 Tuner Frames | [6 empty] | EIC-5 half-cells; Nb samples x41; Blanks x4; | L2-305; Deposition valve; |  |  | HPR1: OOC HPR2: L2-102; L2-130 |  |  |  | L2-099 and L2-106 to rail; | L2-297; |  |  |  | D1: SIC C4k D2: TC C/T D3: DQW2 warm D4: LSF1-2 T/W D5: warm D6: Coax L/C2K/T D7: L2-288 pull D8: L2-295 pull | C50/C75- Sample Cavities? LCLSll CM04- LC He circuit, Install Bayonet Box/LC CM05- Tune HOM's, Lower shields CM07- LC VV, 2 phase welding, heat stations, Lollipops out CM08- ucm ready Other- Setup VV for insp @Blue Crab, welding walk overs
2017-10-19 | Thu | CERN-5; SNS MB; | HOM loads; C50 WW; | L2 Tuner Frames L2 bellows/spools | [7 empty] | Twin-1; Ceramic window; Alignment tools; Aluminum oxide parts; Deposition parts; Large beam pipes x2; |  |  | HPR1: OOC HPR2: L2-122; L2-270 |  |  |  | L2-102 and L2-130 to rail; Deposition system | Deposition valve; |  | L2-297 HOMs and sensors; |  | D1: SIC C2K/T D2: TC C/T D3: DQW2 pull; D4: LSF1-2 warm D5: D6: Coax L/C/T D7: D8: | C50/C75- Sample Cavities? LCLSll CM04- Install Bayonet Box/LC CM05- Tune HOM's, Lower shields CM07- LC VV, 2 phase welding, heat stations, Lollipops out CM08- ucm ready Other- Insp VV @Blue Crab, welding walk overs | [7 empty] | linacs currently at 2K Linac testing by Friday? |  | CM03 - Notch measurments complete Cavity 4 coupler retuned ~4E7 Start Emax and Qo this morning
2017-10-20 | Fri | SNS MB; | HOM loads; C50 WW; | L2 Tuner Frames L2 VV018 | [7 empty] | MB-002 and hardware; Deposition system; |  |  | HPR1: OOC HPR2: TD-5 IA-016 |  |  |  | Deposition system; L2-122 and L2-270 to rail; | BLA #2; |  | L2-297 HOMs ; LSF1-2 FGM |  | PSS Certification (a.m.) D1: SIC hold D2: TC C/T D3: RDT-2 L/SC4K D4: LSF1-2 pull D5: D6: D7: L2-297 L/C4K D8: | C50/C75- Sample Cavities? LCLSll CM04- Install Bayonet Box/LC CM05- Tune HOM's, Lower shields CM07- LC VV, 2 phase welding, heat stations, Lollipops out CM08- ucm ready Other- Insp VV @Blue Crab, welding walk overs | [7 empty] | linacs currently at 2K C50-13 and other linac testing to start Sat. morning |  | CM03 - Emax / Qo's started Cavity 8 complete Cavity 7 in progress
2017-10-21 | Sat
2017-10-22 | Sun | [13 empty] | HPR1: HPR2:
2017-10-23 | Mon | EIC-1; |  | L2 Tuner Frames L2 VV018 L2 Mag shielding |  |  | J1.3-05 HOMs; IA-320 FF 96%; |  |  |  |  | L2 hardware |  |  | HPR1: OOC HPR2: L2-299 TD-5 |  |  |  | Deposition system; J1.3-08: HW Coax; |  |  |  | L2-304 | D1: SIC pull D2: TC C4K/T D3: RDT-2 C4K/T (2) D4: LSF1-2 L/C4K (3) D5: D6: Coax hold D7: L2-297 C2K/T (1) D8: | C50/C75- Sample Cavities? LCLSll CM04- Tie up Bayonet Box, Tune HOM's CM05- Tune HOM's, Lower shields CM07- LC VV, LC 2 phase, heat stations CM08- ucm ready Other- welding walk overs, Flex u-tubes | [7 empty] | C50-13 Emax First four cavities, started cav 5 Cavity 1 quench at 16.7 MV/m, FE Onset at 14.1 MV/m Cavity 2 Emax = 13.7 MV/m FE ? Cavity 3 ?? No FE up to 1 hour run gradient Cavity 4 quench at 16.8 MV/m first three cavities in 1L26 (C100-10) checked. Overall performance hits - FE higher, onsets lower, Emax's lower. four cavities in 2L20 (window replacement) checked performance roughly unchanged |  | CM03 Emax / Qo complete on cavities 1, 3, 5, 6, 7, 8 Cavity 8 - quench 16.3 MV/m CW. End group Cavity 7 - quench 16.9 MV/m Heating at tuner side HOM clamp Cavity 6 - quench 16.8 MV/m Cavity 5 - CARM alarm at 14 MV/m FE onset 8.5 MV/m Cavity 4 - quench in pulse mode at ~21 MV/m - cplr needs processing Cavity 3 - quench at 19.6 MV/m No FE Cavity 2 in progress Cavity 1 - Quench at 20.4 MV/m no FE Finish cavity 2 Emax / Qo and attempt to process Cavity 4 coupler vac
2017-10-24 | Tue | Maint down | loads | L2-134 L2 Bellows/spools |  |  | J1.3-05 HOMs; LSFC-08 probe cal; LSFC-09 probe cal; |  |  |  | Half cells x2; Cu pedistals x4; Large bellow pipes x2; 4" SS tube etch; | L2-0304 parts MB-002 parts Flex Hoses x2; L2 clamps Brackets gaskets; L2 Cryo hardware; Alameda gate valve parts; CF rotatable & ECR gun centering tool; Fasteners; |  |  | HPR1: OOC HPR2: L2-304; L2-299 |  | L2-299 new FP; DQW2 N2 backfill and bag; TS34-002; |  | J1.3-08; Deposition system; TD5; | HW Coax; |  |  | DQW2 L2-276 | D1: D2: TC C4K/T D3: RDT-2 Warm D4: LSF1-2 C2K/T/W60K D5: D6: D7: L2-297 warm D8: | C50/C75- Sample Cavities LCLSll CM04- Tie up Bayonet Box, Tune HOM's CM05- Tune HOM's, Lower shields CM07- VV to UITF, LC 2 phase, heat stations, magnet lead soldering CM08- ucm ready Other- welding walk overs , Flex u-tubes
2017-10-25 | Wed | Maint down | loads | C75 Cavities L2 Bellows/spools |  |  | J1.3-05 HOMs; CERN5 tuning freq & FF; |  |  |  | Nb rods x3 & Nb shields x7; Mo Shields x2; | L2 FP (x6); L2 clamps, blanks & seals; Al box and lid; L2-276 hardware; Deposition parts; Spool & nuts; L2 Cu plated bellows x2; L2 SS bellows; |  | Remove SNS MB-02; JL-1 setup; | HPR1: OOC HPR2: L2-304; L2-276 |  | L2-304 new FP; |  | L2-299 D7/8; Deposition system; | J1.3-08 | HW Coax 120C/6h |  | L2-288 | D1: D2: TC C/T D3: RDT-2 warm D4: LSF1-2 warm D5: D6: TD5 L/C/T D7: L2-297 warm D8: | C50/C75- Sample Cavities LCLSll CM04- Tie up Bayonet Box, Tune HOM's CM05- Tune HOM's, Lower shields CM07- VV to UITF, LC 2 phase, heat stations, magnet lead soldering CM08- ucm ready Other- welding walk overs , Flex u-tubes | [7 empty] | C50-13 Emax all cavities Cavity 1 quench at 16.7 MV/m, FE Onset at 14.1 MV/m Cavity 2 Emax = 13.7 MV/m FE ? Cavity 3 14.7 No FE up to 1 hour run gradient Cavity 4 quench at 16.8 MV/m Cavity 5 quench at 8.9 MV/m No FE Cavity 6 Emax at 14 MV/m No FE Cavity 7 Emax at 13.7 MV/m No FE Cavity 8 quench at 15.5 MV/m FE Onset at 7.5 MV/m Tuners on 6, 7 and 8 tested four cavities in 1L26 (C100-10) checked. Overall performance hits - FE higher, onsets lower, Emax's lower. 2L20 (window replacement) checks complete performance roughly unchanged start 2L19 today? |  | CM03 Emax / Qo complete on cavities 1, 3, 5, 6, 7, 8 Cavity 8 - quench 16.3 MV/m CW. End group Cavity 7 - quench 16.9 MV/m Heating at tuner side HOM clamp Cavity 6 - quench 16.8 MV/m Cavity 5 - CARM alarm at 14 MV/m FE onset 8.5 MV/m Cavity 4 - quench in pulse mode at ~21 MV/m - cplr needs processing Cavity 3 - quench at 19.6 MV/m No FE Cavity 2 quench at 20.9 MV/m No FE Cavity 1 - Quench at 20.4 MV/m no FE Finish cavity 2 Emax / Qo and attempt to process Cavity 4 coupler vac
2017-10-26 | Thu | Maint down | loads | C75 Cavities L2 Bellows/spools |  |  | CERN5 tuning freq & FF; L2-134; L2-135; |  |  |  | Flange SS etch; | L2 spools; lollipop parts; Depositon flange tee and hardware; L2 Cryo hardware; |  | JL-1 setup | HPR1: OOC HPR2: L2-288; L2-276 |  | L2-276 new FP; |  | L2-304 D7/8; Deposition system; | J1.3-08 | HW Coax 120C/6h |  | L2-295 | D1: D2: TC C/T D3: RDT-2 pull D4: LSF1-2 pull D5: D6: D7: L2-297 pull D8: | C50/C75- Sample Cavities LCLSll CM04- Tune HOM's, mod HOM cans CM05- Mod HOM cans, Lower shields CM07- Tuner split rings, heat stations, magnet lead heat stationing CM08- ucm ready Other- welding walk overs , Flex u-tubes | [7 empty] | C50-13 Emax all cavities Cavity 1 quench at 16.7 MV/m, FE Onset at 14.1 MV/m Cavity 2 Emax = 13.7 MV/m FE ? Cavity 3 14.7 No FE up to 1 hour run gradient Cavity 4 quench at 16.8 MV/m Cavity 5 quench at 8.9 MV/m No FE Cavity 6 Emax at 14 MV/m No FE Cavity 7 Emax at 13.7 MV/m No FE Cavity 8 quench at 15.5 MV/m FE Onset at 7.5 MV/m Tuners on 6, 7 and 8 tested 1L26 (C100-10) checks complete. Overall performance hits - FE higher, onsets lower, Emax's lower. Using current GMES calibrations, 1L26 is at best 62 MV module. 2L19 checks - 1st two cavities checked. Increased FE |  | CM03 Emax / Qo complete on cavities 1, 3, 5, 6, 7, 8 Cavity 8 - quench 16.3 MV/m CW. End group Cavity 7 - quench 16.9 MV/m Heating at tuner side HOM clamp Cavity 6 - quench 16.8 MV/m Cavity 5 - CARM alarm at 14 MV/m FE onset 8.5 MV/m Cavity 4 - quench in pulse mode at ~21 MV/m - cplr needs processing Cavity 3 - quench at 19.6 MV/m No FE Cavity 2 quench at 20.9 MV/m No FE Cavity 1 - Quench at 20.4 MV/m no FE Re-measuring Qo's after temp bump 4 cavities complete.
2017-10-27 | Fri | Maint down | loads | L2-135 | [6 empty] | Cu blocks; SS wedges | IA-320; Twin-1; Loads and parts; Blanks x7; L2-134; Convoluted tubes |  | JL-1 5u | HPR1: OOC HPR2: LPR bellows; |  | L2-295 pull EZ pics; RDT-x cage with bellows (2) |  | Deposition system (3); | L2-299 (4); J1.3-08 (1) | HW Coax 120C/6h | L2-299 HOMs and sensors; | L2-297 | D1: D2: TC D3: D4: D5: D6: D7: D8: | C50/C75- Sample Cavities LCLSll CM04- Tune HOM's, mod HOM cans CM05- Move cables, Mod HOM cans, Lower shields CM07- Tuner split rings, heat stations, magnet lead heat stationing, Alignment CM08- ucm ready, Other- welding walk overs , Flex u-tubes
2017-10-28 | Sat
2017-10-29 | Sun | [13 empty] | HPR1: HPR2:
2017-10-30 | Mon | Maint down | L2 Bellows; L2 Spools; C50 WW; | L2 Bellows/Spools; L2-135; L2-137; |  |  | J1.3-04; J1.3-05; |  |  |  | Nb wire, SS blanks & hardware | Deposition cord and pump; Berry bolts and hardware; Nb wire, SS blanks & hardware |  | acid change; SNS MB-002 setup | HPR1: OOC HPR2: L2-288 |  | L2-297 pull EZ pics; L2-288 new FP; |  | L2-276 D7/8; | L2-304; Deposition; J1.3-08; |  | HW Coax sensors; |  | D1: D2: TC 4K D3: map dewar; D4: D5: D6: RDTTD-02 C4K/W (no liq) D7: L2-299 L/C4K D8: | C50/C75- Sample Cavities LCLSll CM04- Tune HOM's, mod HOM cans CM05- Verify HOM tuning/cables, Lower shields CM07- String Alignment CM08- receive cavity string, return lollipops, Anti roll, Berry bolts, magnet, alignment Other- welding walk overs , Flex u-tubes | [7 empty] | C50-13 Emax and Qo's all cavities Cavity 1 quench at 16.7 MV/m, FE Onset at 14.1 MV/m Cavity 2 Emax = 13.7 MV/m FE ? Cavity 3 14.7 No FE up to 1 hour run gradient Cavity 4 quench at 16.8 MV/m Cavity 5 quench at 8.9 MV/m No FE Cavity 6 Emax at 14 MV/m No FE Cavity 7 Emax at 13.7 MV/m No FE Cavity 8 quench at 15.5 MV/m FE Onset at 7.5 MV/m All tuners tested 4 Cavities FE free 1L25 (C100-09) checks complete. Overall performance hits - FE higher, onsets lower, Emax's lower. 2L18 checks - almost complete performance about the same |  | CM03 Emax / Qo complete on cavities 1, 3, 5, 6, 7, 8 Cavity 8 - quench 16.3 MV/m CW. End group Cavity 7 - quench 16.9 MV/m Heating at tuner side HOM clamp Cavity 6 - quench 16.8 MV/m Cavity 5 - CARM alarm at 14 MV/m FE onset 8.5 MV/m Cavity 4 - quench in pulse mode at ~21 MV/m - cplr needs processing Cavity 3 - quench at 19.6 MV/m No FE Cavity 2 quench at 20.9 MV/m No FE Cavity 1 - Quench at 20.4 MV/m no FE Re-measuring Qo's after temp bump 8 cavities complete. This week - support llrf checkouts
2017-10-31 | Tue | RFD damper; | C50 WW C75 Load | L2-137 C75 HOM Load |  |  | J1.3-04 L2-310; L2-314; |  |  |  |  | Al gaskets; Bolts; Flange covers; L2-135; Deposition FT |  | HF Spike; | HPR1: OOC HPR2: |  |  |  | L2-305 D5; L2-306 D5; L2-308 D5; L2-288; | L2-276; (3) Deposition(2); J1.3-08; (1) |  | L2-304 HOMs and sensors (4); |  | D1: D2: TC 4K D3: HW Coax L/C4K/T D4: D5: D6: RDTTD-02 W D7: L2-299 C2K/T/W D8: L2-304 L/C4K | C50/C75- Sample Cavities, disassemble waveguides LCLSll CM04- Tune HOM's, mod HOM cans CM05- Verify HOM tuning/cables, Lower shields CM07- String Alignment CM08- receive cavity string, return lollipops, Anti roll, Berry bolts, magnet, alignment Other- welding walk overs , Flex u-tubes | [7 empty] | C50-13 Emax and Qo's all cavities Cavity 1 quench at 16.7 MV/m, FE Onset at 14.1 MV/m Cavity 2 Emax = 13.7 MV/m FE ? Cavity 3 14.7 No FE up to 1 hour run gradient Cavity 4 quench at 16.8 MV/m Cavity 5 quench at 8.9 MV/m No FE Cavity 6 Emax at 14 MV/m No FE Cavity 7 Emax at 16.9 MV/m No FE Cavity 8 quench at 15.5 MV/m FE Onset at 7.5 MV/m All tuners tested 4 Cavities FE free FPC heating tests in progress 1L22 (C100-03) first 4 cavities checked Overall performance hits - FE higher, onsets lower, Emax's lower. 2L18 checks complete - performance about the same move to 2L17 today |  | CM03 Emax / Qo complete on cavities 1, 3, 5, 6, 7, 8 Cavity 8 - quench 16.3 MV/m CW. End group Cavity 7 - quench 16.9 MV/m Heating at tuner side HOM clamp Cavity 6 - quench 16.8 MV/m Cavity 5 - CARM alarm at 14 MV/m FE onset 8.5 MV/m Cavity 4 - quench in pulse mode at ~21 MV/m - cplr needs processing Cavity 3 - quench at 19.6 MV/m No FE Cavity 2 quench at 20.9 MV/m No FE Cavity 1 - Quench at 20.4 MV/m no FE Re-measuring Qo's after temp bump 8 cavities complete. supporting llrf work
2017-11-01 | Wed |  | C50 WW | L2-137; L2-138; C75 HOM Load; |  |  | J1.3-04; L2 FP; |  |  |  | Deposition FT; Nb plates; Nb parts | Deposition FT; Nb plates; Cavity bolt holes x3 |  | N/A | HPR1: OOC HPR2: |  |  |  |  | L2-305 D5; L2-306 D5; L2-308 D5; L2-288 D7/8; |  | L2-276 HOMs; |  | D1: D2: TC 4K D3: HW Coax C4K/T D4: D5: D6: D7: L2-299 warm D8: L2-304 C2K/T/W | C50/C75- Sample Cavities, disassemble waveguides, serialize parts LCLSll CM04- Tune HOM's, Install HOM cans CM05- 50k mli, install into VV CM07- String Alignment, prep tuners CM08- receive cavity string, return lollipops, Anti roll, Berry bolts, magnet Other- welding walk overs , Flex u-tubes | [7 empty] | C50-13 Emax and Qo's all cavities Cavity 1 quench at 16.7 MV/m, FE Onset at 14.1 MV/m Cavity 2 Emax = 13.7 MV/m FE ? Cavity 3 14.7 No FE up to 1 hour run gradient Cavity 4 quench at 16.8 MV/m Cavity 5 quench at 8.9 MV/m No FE Cavity 6 Emax at 14 MV/m No FE Cavity 7 Emax at 16.9 MV/m No FE Cavity 8 quench at 15.5 MV/m FE Onset at 7.5 MV/m All tuners tested 4 Cavities FE free microphonics data collected FPC heating tests in progress 1L23 (C100-06) check out complete Next stop - SL C100's if schedule permits 2L17 checks in progress Next week CHL reconfigure / C50-13 BL connect / no testing. No testing this weekend |  | CM03 Emax / Qo complete on cavities 1, 3, 5, 6, 7, 8 Cavity 8 - quench 16.3 MV/m CW. End group Cavity 7 - quench 16.9 MV/m Heating at tuner side HOM clamp Cavity 6 - quench 16.8 MV/m Cavity 5 - CARM alarm at 14 MV/m FE onset 8.5 MV/m Cavity 4 - quench in pulse mode at ~21 MV/m - cplr needs processing Cavity 3 - quench at 19.6 MV/m No FE Cavity 2 quench at 20.9 MV/m No FE Cavity 1 - Quench at 20.4 MV/m no FE warm up started
2017-11-02 | Thu |  | C50WW | L2-137; L2 Spools |  |  | J1.3-04; L1.3-08; |  |  |  |  | L2 string HW; L2 FT; L2 couplers; IA-016 |  | MB-002 40; | HPR1: OOC HPR2: |  | L2 bellows prep; L2 cavity prep; |  | BLA-2 |  |  | L2-288 D7/8; |  | D1: D2: TC 4K D3: HW Coax D4: D5: D6: D7: L2-299 pull; L2-276 L/C2K/T D8: L2-304 warm/pull | C50/C75- serialize parts LCLSll CM03- Warm up, pull u-tube CM04- Tune HOM's, Install HOM cans CM05- VV alignment CM07- prep/install tuners CM08- Anti roll, Berry bolts, magnet, 2 phase piping Other- welding walk overs , Flex u-tubes
2017-11-03 | Fri |  | C50WW | [8 empty] | MB-002; L2 cavity bolt holes |  | MB-002 20; | HPR1: OOC HPR2: IA-016 G2 |  | L2 bellows prep; L2 cavity prep; |  |  | BLA-2 |  | L2-305/L2-306/L2-308; | L2-299; BLA-2 | supply outage (CB3) D1: D2: TC 4K D3: HW Coax C4K/T/W D4: D5: D6: D7: L2-276 D7-->D3/warm; D8: L2-288 load | C75- serialize parts, machine window assys LCLSll CM03- Warm up CM04- Install HOM cans, Ins Vac LC CM05- VV alignment CM07- Prep/install tuners CM08- Berry bolts, magnet, 2 phase piping Other- welding walk overs , Flex u-tubes | [7 empty] | C50-13 Emax and Qo's all cavities Cavity 1 quench at 16.7 MV/m, FE Onset at 14.1 MV/m Cavity 2 Emax = 13.7 MV/m FE ? Cavity 3 14.7 No FE up to 1 hour run gradient Cavity 4 quench at 16.8 MV/m Cavity 5 quench at 8.9 MV/m No FE Cavity 6 Emax at 14 MV/m No FE Cavity 7 Emax at 16.9 MV/m No FE Cavity 8 quench at 15.5 MV/m FE Onset at 7.5 MV/m All tuners tested 4 Cavities FE free microphonics data collected FPC heating tests in progress 1L23 (C100-06) check out complete Next stop - SL C100's if schedule permits 2L17 checks in progress Next week CHL reconfigure / C50-13 BL connect / no testing. No testing this weekend |  | CM03 Emax / Qo complete on cavities 1, 3, 5, 6, 7, 8 Cavity 8 - quench 16.3 MV/m CW. End group Cavity 7 - quench 16.9 MV/m Heating at tuner side HOM clamp Cavity 6 - quench 16.8 MV/m Cavity 5 - CARM alarm at 14 MV/m FE onset 8.5 MV/m Cavity 4 - quench in pulse mode at ~21 MV/m - cplr needs processing Cavity 3 - quench at 19.6 MV/m No FE Cavity 2 quench at 20.9 MV/m No FE Cavity 1 - Quench at 20.4 MV/m no FE warm up started
2017-11-04 | Sat
2017-11-05 | Sun | [13 empty] | HPR1: HPR2: L2-133; L2-279
2017-11-06 | Mon | SNS MB | C50 WW | L2-138 |  |  |  | Nb Samples (PD1) 600C/10h; |  |  | Dumbell; Moly bolts; Nb pins; Nb covers x9 | CERN-1 and hardware; L2 Clamps blanks and covers; VCR, tees & elbows; L2-137 wipe |  | CERN-1 setup | HPR1: OOC HPR2: L2-131; L2-118 |  | L2-133, L2-279 to rail; |  | L2-134 D7/8; | BLA-2 |  | L2-305/L2-306/L2-308 sensors and HOMs; | L2-304 | CTF DOWN D1: D2: TC hold D3: HW Coax hold D4: D5: L2-305/L2-306/L2-308 load D6: D7: L2-276 pull; D8: L2-288 hold | C75- serialize parts, machine window assys, remove feedthrus LCLSll CM03- Warm up, pull u-tubes CM04- Ins Vac LC CM05- To WS5 CM07- Prep/install tuners CM08- 2 phase piping, Alignment Crew Other- welding walk overs , Flex u-tubes | [7 empty] | C50-13 Emax and Qo's all cavities Cavity 1 quench at 16.7 MV/m, FE Onset at 14.1 MV/m Cavity 2 Emax = 13.7 MV/m FE ? Cavity 3 14.7 No FE up to 1 hour run gradient Cavity 4 quench at 16.8 MV/m Cavity 5 quench at 8.9 MV/m No FE Cavity 6 Emax at 14 MV/m No FE Cavity 7 Emax at 16.9 MV/m No FE Cavity 8 quench at 15.5 MV/m FE Onset at 7.5 MV/m All tuners tested 4 Cavities FE free microphonics data collected FPC heating tests complete 2L17 checks complete This week CHL reconfigure / C50-13 BL connect / no testing. |  | CM03 Emax / Qo complete on cavities 1, 3, 5, 6, 7, 8 Cavity 8 - quench 16.3 MV/m CW. End group Cavity 7 - quench 16.9 MV/m Heating at tuner side HOM clamp Cavity 6 - quench 16.8 MV/m Cavity 5 - CARM alarm at 14 MV/m FE onset 8.5 MV/m Cavity 4 - quench in pulse mode at ~21 MV/m - cplr needs processing Cavity 3 - quench at 19.6 MV/m No FE Cavity 2 quench at 20.9 MV/m No FE Cavity 1 - Quench at 20.4 MV/m no FE warm up complete CM04 into Cave this week
2017-11-07 | Tue | SNS MB; Cu tubes; | C50 WW; inj beam dump; | L2-310; L2 spools; L2-138; | L2-299 optical; |  | MB-002 FF and probes; | Nb Samples (PD1) 600C/10h; |  | EIC-1; (PD2) BCP; | Nb Samples (PD2) BCP; Ring and stud | Beam dump; CRN-1 hardware |  | CERN-1 30u Leak | HPR1: OOC HPR2:L2-281; L2-097; |  | L2-131, L2-118 to rail; |  | IA-016; | IA-016; BLA-2 |  |  | L2-276 | D1: D2: TC 4K D3: HW Coax warm D4: D5: L2-305/L2-306/L2-308 C4K D6: D7: D8: L2-288 hold | C75- serialize parts, machine window assys, remove feedthrus LCLSll CM03-Remove from CMTF CM04- Into CMTF, Ins Vac LC CM05- Warm coupler prep, Beam pipe prep CM07- Prep/install tuners CM08- 2 phase piping, Alignment Crew Other- welding walk overs , Flex u-tubes | [7 empty] | C50-13 Emax and Qo's all cavities Cavity 1 quench at 16.7 MV/m, FE Onset at 14.1 MV/m Cavity 2 Emax = 13.7 MV/m FE ? Cavity 3 14.7 No FE up to 1 hour run gradient Cavity 4 quench at 16.8 MV/m Cavity 5 quench at 8.9 MV/m No FE Cavity 6 Emax at 14 MV/m No FE Cavity 7 Emax at 16.9 MV/m No FE Cavity 8 quench at 15.5 MV/m FE Onset at 7.5 MV/m All tuners tested 4 Cavities FE free CHL2 to 4K in progress 1L13 BL connect starts today |  | CM03 Emax / Qo complete on cavities 1, 3, 5, 6, 7, 8 Cavity 8 - quench 16.3 MV/m CW. End group Cavity 7 - quench 16.9 MV/m Heating at tuner side HOM clamp Cavity 6 - quench 16.8 MV/m Cavity 5 - CARM alarm at 14 MV/m FE onset 8.5 MV/m Cavity 4 - quench in pulse mode at ~21 MV/m - cplr needs processing Cavity 3 - quench at 19.6 MV/m No FE Cavity 2 quench at 20.9 MV/m No FE Cavity 1 - Quench at 20.4 MV/m no FE CM03 removal today CM04 into Cave this week
2017-11-08 | Wed | EIC-5 end cells; and beam tubes; | C50 WW; inj beam dump; | L2-310 L2 Field Probes | CERN-5 optical | [5 empty] | RDT-2 15u | Gasket, bolts and washers | CERN-5 setup | CERN-1 30u Leak | HPR1: OOC HPR2: L2-295; L2-125; |  | L2-281, L2-097 to rail |  |  | L2-134; BLA-2 |  | IA-016 |  | D1: D2: TC 4K D3: HW Coax pul; IA-016 L/C4K D4: D5: L2-305/L2-306/L2-308 C2K/T/W D6: G2 L/C2K/T/W D7: D8: L2-288 C4K | C75- serialize parts, machine window assys, remove feedthrus LCLSll CM03-Remove from CMTF CM04- Into CMTF, Ins Vac LC CM05- Warm coupler prep, Beam pipe prep CM07- Prep/install tuners CM08- 2 phase piping, Alignment Crew Other- welding walk overs , Flex u-tubes | [7 empty] | C50-13 Emax and Qo's all cavities Cavity 1 quench at 16.7 MV/m, FE Onset at 14.1 MV/m Cavity 2 Emax = 13.7 MV/m FE ? Cavity 3 14.7 No FE up to 1 hour run gradient Cavity 4 quench at 16.8 MV/m Cavity 5 quench at 8.9 MV/m No FE Cavity 6 Emax at 14 MV/m No FE Cavity 7 Emax at 16.9 MV/m No FE Cavity 8 quench at 15.5 MV/m FE Onset at 7.5 MV/m All tuners tested 4 Cavities FE free CHL2 to 4K in progress 1L13 hook up: 1L14 side girder connected. 1L12 side today |  | CM03 Emax / Qo complete on cavities 1, 3, 5, 6, 7, 8 Cavity 8 - quench 16.3 MV/m CW. End group Cavity 7 - quench 16.9 MV/m Heating at tuner side HOM clamp Cavity 6 - quench 16.8 MV/m Cavity 5 - CARM alarm at 14 MV/m FE onset 8.5 MV/m Cavity 4 - quench in pulse mode at ~21 MV/m - cplr needs processing Cavity 3 - quench at 19.6 MV/m No FE Cavity 2 quench at 20.9 MV/m No FE Cavity 1 - Quench at 20.4 MV/m no FE CM03 removal today CM04 in Cave - cool down Friday
2017-11-09 | Thu | Sample chamber; | C50 WW; inj beam dump | L2 rework probes; USLarp damper beamtube; L2-314; | [6 empty] | LSFB Cav; SS test components; Nb Disc 5u | L2 hardware | CERN-5 100/100u | CERN-1 setup | HPR1: OOC HPR2: LSFB Cav |  | L2-295, L2-125 to rail; Deposition system wipedown |  | J1.3-09; | BLA-2 |  | L2-134 HOMs and sensors; |  | D1: D2: TC 4K D3: IA-016 SC4K/TC2K/T/W D4: D5: L2-305/L2-306/L2-308 warm D6: D7: L2-134 L/C4K D8: L2-288 C2K/T/W | C75- serialize parts, machine window assys, remove feedthrus LCLSll CM03-Reconfigure beam line CM04- U-tubes 9am, Cooldown CM05- Warm coupler install, Beam pipe prep CM07- Install tuners, Magnet V.taps CM08- 2 phase LC, Ti sheet Other- Flex u-tubes | [7 empty] | C50-13 Emax and Qo's all cavities Cavity 1 quench at 16.7 MV/m, FE Onset at 14.1 MV/m Cavity 2 Emax = 13.7 MV/m FE ? Cavity 3 14.7 No FE up to 1 hour run gradient Cavity 4 quench at 16.8 MV/m Cavity 5 quench at 8.9 MV/m No FE Cavity 6 Emax at 14 MV/m No FE Cavity 7 Emax at 16.9 MV/m No FE Cavity 8 quench at 15.5 MV/m FE Onset at 7.5 MV/m All tuners tested 4 Cavities FE free Two CHL's back on line CHL1 / SC1 > SL CHL2 / SC2 > NL 1L13 hook up: both girders connected. |  | CM04 in Cave - cool down Friday Degaussed
2017-11-10 | Fri | CEBAF coating covers; | inj beam dump | USLarp damper beamtube; L2-314; | L2-066 optical; |  | L2-293 | CERN-5 800C/3h; Nb samples (PD2) 800C/3h |  |  | Nb cavity cooling crucible; Nb chamber | CERN-1; Deposition tubes and connectors; L2-138; L2-310; CRN-5 clean & Deg; Gaskets & Hardware; Adapters & hoses; Bolts & nuts |  | CERN-1 30u | HPR1: OOC HPR2: IA-320; |  | LSFB Cav to Dep Sys |  | J1.3-09; L2-305 D7/8; | BLA-2 |  |  |  | CMTF cooldown D1: D2: TC 4K/W D3: IA-016 C2K/T/W (2) D4: D5: L2-305/L2-306/L2-308 pull D6: D7: L2-134 C2K/T/W (1) D8: L2-288 warm (D8-->D7) | C75- serialize parts, remove feedthrus LCLSll CM03-Reconfigure beam line CM04- U-tubes 9am, Cooldown CM05- Warm coupler install, Beam pipe prep CM07- Install tuners, Magnet V.taps CM08- 2 phase LC, Ti sheet, Coupler sensors Other- Flex u-tubes PCM Returns Monday | CU testing box seam welding-Spradlin | [6 empty] | C50-13 Emax and Qo's all cavities Cavity 1 quench at 16.7 MV/m, FE Onset at 14.1 MV/m Cavity 2 Emax = 13.7 MV/m FE ? Cavity 3 14.7 No FE up to 1 hour run gradient Cavity 4 quench at 16.8 MV/m Cavity 5 quench at 8.9 MV/m No FE Cavity 6 Emax at 14 MV/m No FE Cavity 7 Emax at 16.9 MV/m No FE Cavity 8 quench at 15.5 MV/m FE Onset at 7.5 MV/m All tuners tested 4 Cavities FE free 1L13 / 2L24 - Retest Monday - Wednesday? 1L04 RGA Monitoring of WGVac started (C50 WGVac Trip issue) |  | CM04 in Cave - cool down Friday Degaussed U-tubes 9AM cool down over the weekend
2017-11-11 | Sat
2017-11-12 | Sun | [6 empty] | CERN-5 800C/3h; Nb samples (PD2) 800C/3h | [6 empty] | HPR1: HPR2: |  |  |  |  | Dep system;
2017-11-13 | Mon | C75 Dogleg half-bodies; |  | L2-314 L2 Mag shields; | L2-066 optical; |  | L2-327; L2-293; | CERN-5 800C/3h; Nb samples (PD2) 800C/3h; | C50 WW; |  | Nb Samples (PD2) BCP; | MB-002 |  | SNS HB-SC setup | HPR1: OOC HPR2: MB-002; CERN-1; |  |  |  | J1.3-09; L2-138 D7/8; | BLA-2; L2-305; |  |  | L2-306 | D1: SIC L D2: TC 4K D3: IA-016 pull D4: D5: D6: D7: L2-134 pull D8: L2-288 pull | C75- serialize parts, remove feedthrus LCLSll CM03-Reconfigure beam line CM04- U-tubes 9am, Cooldown CM05- Warm coupler install, Beam pipe prep CM07- Install tuners, Magnet V.taps CM08- 2 phase LC, Ti sheet, Coupler sensors Other- Flex u-tubes PCM --> UITF | [7 empty] | C50-13 Emax and Qo's all cavities Cavity 1 quench at 16.7 MV/m, FE Onset at 14.1 MV/m Cavity 2 Emax = 13.7 MV/m FE ? Cavity 3 14.7 No FE up to 1 hour run gradient Cavity 4 quench at 16.8 MV/m Cavity 5 quench at 8.9 MV/m No FE Cavity 6 Emax at 14 MV/m No FE Cavity 7 Emax at 16.9 MV/m No FE Cavity 8 quench at 15.5 MV/m FE Onset at 7.5 MV/m All tuners tested 4 Cavities FE free 1L13 / 2L24 - Retest starting today |  | CM04 in Cave - cool down in progress
2017-11-14 | Tue |  |  | L2-293; L2 Re-worked probes |  |  | CERN-5 FF ; |  | C50 WW; |  | C75 HC & S-rings (x4); Nb plate; Nb foil; | SNS HB-SC; hardware, flange; L2-314 | IA-016 setup; | SNS HB-SC 60u | HPR1: OOC HPR2: MB-002 |  | J1.3-09 bag for leak check; Lighthouse SW maint.; MB-002 |  | Lighthouse SW maint. CERN-1 | L2-138; |  | L2-305 HOMs and sensors | L2-308 | D1: SIC C/T D2: TC warm D3: D4: D5: D6: D7: L2-305 L/C4K D8: | C75- serialize parts, remove feedthrus LCLSll CM03-Reconfigure beam line CM04- 2K today, RF Waveguides, Tilt module CM05- Warm coupler install, Beam pipe install, Peripherals, JT's CM07- Install/set tuners, MLI, RF cables, Demag VV CM08- 2 phase LC, Ti sheet, Realign beampipe Other- Flex u-tubes | [7 empty] | C50-13 Emax and Qo's all cavities Cavity 1 quench at 18.9 MV/m, FE Free up to Emax Cavity 2 Emax = 14.3 MV/m FE appears unchanged Cavity 3 14.7 No FE up to 1 hour run gradient Cavity 4 quench at 16.8 MV/m Cavity 5 quench at 8.9 MV/m No FE Cavity 6 Emax at 14 MV/m No FE Cavity 7 Emax at 16.9 MV/m No FE Cavity 8 quench at 15.5 MV/m FE Onset at 7.5 MV/m All tuners tested 5 Cavities FE free 2L24 - two cavities completed |  | CM04 in Cave - cool down in progress Pumpdown this morning? HPRF checkout and tuning this afternoon
2017-11-15 | Wed | C75 iris welds (x2) | RFD Samples | L2-327; L2-293; L2 Bellows/spools | [6 empty] | Beam tube and flange; Mo discs; Nb blank; Al clamps |  | IA-016 15u; |  | HPR1: OOC HPR2: |  |  |  | MB-002 | J1.3-09; CERN-1; |  | L2-138 HOMs and sensors | L2-134 | D1: SIC C/T D2: TC pull; RRR L/C/T/W D3: D4: D5: D6: D7: L2-305 C2K/T/W D8: L2-138 L | C75- serialize parts, remove feedthrus LCLSll CM03-Reconfigure beam line CM04- 2K testing CM05- Warm coupler install, Beam pipe install, Peripherals CM07- Install/set tuners, MLI, RF cables CM08- 2 phase LC, Ti sheet, Realign beampipe Other- Flex u-tubes | [9 empty] | CM04 in cave at 2K Tuning cavities SSA troubleshooting
2017-11-16 | Thu | RFD damper; |  | L2-Tuner frame; L2-327; | [6 empty] | IA-016; Nb cavity covers x5; Nb cover 100u; IA-016 Nitric soak; Cu tubes x4; L2 rail wipe; | L2-293, L2-327 wipedown; IA-016; Mo & Nb parts; | IA-320 setup |  | HPR1: OOC HPR2: |  |  |  | MB-002; C50 DL; L2-310 D7/8; L2-293, L2-314, L2-327 D5; | CERN-1; J1.3-09 rollout; C50 DL; | CERN-1 120C/12h |  | L2-288 | D1: SIC C/T D2: RRR T/W D3: D4: RI-009 L/C4K (no liquid) D5: D6: D7: L2-305 warm D8: L2-138 C2K/T/W | C75- serialize parts, remove feedthrus LCLSll CM03-Reconfigure beam line CM04- 2K testing CM05- Warm coupler install, 2 phase LC CM07- Install/set tuners, MLI, RF cables CM08- Install MLI/Mag shields CM09- Receive Cavity string Other- Flex u-tubes |  |  |  | Vault tuners/sweep |  |  |  | Maintenance day today |  | CM04 - Cavity tuning / Coupler tuning / HOM Measurements Cavities 5- 7 - All HOM Qext's appear to be 1e12 or higher (Cavity 7 not properly tuned though)
2017-11-17 | Fri |  | RFD Samples | L2 Bellows |  |  | J1.3-9 |  |  |  | L2 Field probes x2; Indium dissolve test; Dumbells x2; Nb samples x2; Nb tube; | C50 pair wipedown (x2); rail brakes; Cu bellows | IA-320 20u | EIC-1 setup | HPR1: OOC HPR2: IA-016 |  | TS34-002 |  | L2-293, L2-314, L2-327 D5 | MB-002; L2-310; | CERN-1 120C/12h |  |  | D1: SIC C/T D2: RRR pull; C50 DL L/C/T; D3: CERN-1 load D4: RI-009 warm/pull D5: D6: D7: L2-305 pull; D8: L2-138 warm | C75- serialize parts, remove feedthrus LCLSll CM03-Reconfigure beam line CM04- 2K testing CM05- Warm coupler install, 2 phase LC, JT Welding CM07- Install/set tuners, MLI, RF cables CM08- Install MLI/Mag shields CM09- Alignment, Berry bolts Other- Flex u-tubes | SNS End dish | [6 empty] | Recovery from Maintenance period. "Fault Finder" Exercise to be conducted over the weekend |  | CM04 - Cavity tuning / Coupler tuning / HOM Measurements Cavities 1- 7 - Notch measurements complete All HOM measured Qext's so far appear to exceed spec Started Emax / Qo Cavity 1- Reached 16 MV/m so far No FE up to 16 MV/m Qo @ 2K = 2.1E10
2017-11-18 | Sat
2017-11-19 | Sun | [13 empty] | HPR1: HPR2:
2017-11-20 | Mon |  |  | L2-Tuner frame Rework PIC parts | [6 empty] | Nb samples (GC) BCP; Sample chamber and disc | C50 pair wipedown (x1); Test stand parts; C50 shearing tool |  |  | HPR1: OOC HPR2: |  | C50 pair dis and sampling (x1); |  |  | L2-293, L2-314, L2-327 |  | L2-310 HOMs & sensors; |  | D1: SIC C/T D2: C50 pull; D3: CERN-1 C4K (1) D4: RI-009 pull, RI-016 L/C4K (no liqu) (3) D5: D6: D7: D8: L2-138 pull; L2-310 L/C4K (2) | C75- serialize parts, remove feedthrus LCLSll CM03-Reconfigure beam line CM04- 2K testing CM05- Warm coupler install, 2 phase LC, JT Welding CM07- Install/set tuners, MLI, RF cables CM08- Install MLI/Mag shields CM09- Alignment, Berry bolts Other- Flex u-tubes | [7 empty] | "Fault Finder" Exercise / max gradient investigations |  | Currently no power in Cave CM04 - Emax / Qo Cavities 1- 8 - Notch measurements complete All HOM measured Qext's appear to exceed spec Cavity 1 Emax Pulsed 21 MV/m CW 17 MV/m / No FE / Qo = 2.1E10 Cavity 6 Emax > 18 MV/m / No FE / Cavity 7 Emax 21 MV/m / Usable 20 MV/m / No sustained FE / Cavity 8 Emax > 18 MV/m / No sustained FE / Qo 1.8E10 (post quench)
2017-11-21 | Tue |  |  | L2 Bellows | [7 empty] | Cryo pipes; Deposition System wipedown |  |  | HPR1: OOC HPR2:IA-320 |  | C50 pair dis and sampling (x1) |  | Deposition system L2-135 D7/8; BLA-2; |  |  | L2-293, L2-314, L2-327 HOMs and sensors; |  | D1: SIC C/T D2: D3: CERN-1 C2K/T (2) D4: RI-016 C4K D5: D6: D7: D8: L2-310 C2K/T/W (1) | C75- serialize parts, remove feedthrus LCLSll CM03-Reconfigure beam line CM04- 2K testing CM05- Warm coupler install, 2 phase LC, JT Welding CM07- MLI, RF cables, HOMs CM08- Mate to UCM CM09- Alignment, Berry bolts Other- Flex u-tubes Pressure test | [7 empty] | "Fault Finder" Exercise / max gradient investigations
2017-11-22 | Wed |  |  | L2 Bellows | [7 empty] | L2 FPC vacuum line |  |  | HPR1: OOC HPR2: |  |  |  | L2-137 D7/8; MB-002? | L2-135; BLA-2; |  | L2-293, L2-314, L2-327 HOMs and sensors; | L2-138 L2-305 | D1: SIC C/T D2: D3: CERN-1 pull D4: RI-016 D5: D6: D7: D8: L2-310 warm | C75- serialize parts, remove feedthrus LCLSll CM03-Reconfigure beam line CM04- 2K testing CM05- Warm coupler install, 2 phase LC, JT Welding CM07- MLI, RF cables, HOMs CM08- Mate to UCM CM09- Alignment, Berry bolts Other- Flex u-tubes Pressure test
2017-11-23 | Thu | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2017-11-24 | Fri | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2017-11-25 | Sat
2017-11-26 | Sun | [13 empty] | HPR1: HPR2:
2017-11-27 | Mon | Cu | regen; RFD sample; | L2 Bellows |  |  |  | regen | SNS blank-off port seal rework; |  |  | FNAL L2 Bellows x4; SNS flange; IA-320; BPM parts and hardware; Cryo 6' flanges x6; Test stand hardware; SS blanks x4 |  | EIC-1 200u | HPR1: OOC HPR2: IA-320; |  |  |  |  | L2-137 |  | L2-135 HOMs and sensors; | CERN-1; L2-286; | D1: D2: D3: D4: D5: L2-293/L2-314/L2-327 L/pre-cool D6: D7: D8: L2-310 pull; L2-135 L/C4K | C75- serialize parts, remove feedthrus LCLSll CM03-Reconfigure beam line CM04- 2K testing CM05- Warm coupler install, 2 phase LC, JT Welding CM07- Move to cantilever CM08- Mate to UCM, install bearing assy's CM09- Alignment, Berry bolts, Install magnet Other- Flex u-tubes purging | [7 empty] | maint day
2017-11-28 | Tue | out | C50 WW; | L2 Bellows |  |  | CERN-1 | Nb Samples (GC), 800C/3h | RDT-2, RDT-10 CBP; |  |  | FNAL L2 Bellows x4; L2-278 parts & hardware; L2-138 bolt holes; L2-310 bolt holes; L2 116 bolt holes; |  | EIC-1 200u | HPR1: OOC HPR2: MB-002 |  | TS34-002 bake; TS28-010 turbo; CERN-1 dis |  | IA-320; |  |  | L2-137 HOMs and sensors; | L2-310; L2-116; Software debug; | D1: SIC C D2: TC load D3: D4: D5: L2-293/L2-314/L2-327 C4K D6: D7: D8: L2-135 C2K | C75- serialize parts, remove feedthrus LCLSll CM03-Reconfigure beam line CM04- 2K testing, u-tube-railing mods CM05- Warm coupler install, JT Welding, MC line CM07- Move to cantilever, Mag shields CM08- Return lollipops 10 am CM09- Alignment, Berry bolts, Install magnet Other- Walk overs, arrange physics space
2017-11-29 | Wed | out | C50 WW; | maint |  |  | L2-328; |  | RDT-2, RDT-10 CBP; |  | Cones & tubes; Nb sample; | CERN-1 wipe; Lollipops & hardware; L2 couplers x3; CRN-01 hardware; Tee's & flanges x2; String cavity prep. |  | EIC-1 200u | HPR1: OOC HPR2: LSFC-9, |  | J1.3-10 gate valve 1 sub; lollipops; |  | MB-002; | IA-320; |  |  |  | D1: SIC D2: TC D3: IA-320 load (4) D4: D5: L2-293/L2-314/L2-327 C2K/T/W (1) D6: D7: L2-137 load D8: L2-135 top off(2) | C75- serialize parts, remove feedthrus LCLSll CM03-Reconfigure beam line CM04- 2K testing, mod u-tube/railing CM05- Warm coupler install, JT Welding, MC line CM07- Move to cantilever, mag shields CM08- Return lollipops 10am CM09- Alignment, Berry bolts, Install magnet, heaters Other- Walk overs, arrange physics space | [9 empty] | Fast cooldown
2017-11-30 | Thu | C75; | C50 WW; | maint; FNAL L2 Spools; |  |  | L2-330; L2-331 |  | RDT-2, RDT-10 CBP; |  | Nb foils, plates and covers; | EIC-1; Plate; Moly hardware; Reducer,plate, stand-off and studs; Windows x2; Titanium bolts; |  | EIC-1 rinsed; | HPR1: OOC HPR2: CERN-1 |  | J1.3-10 BPM sub; gate valve 1 sub; lollipops; |  | BPM sub; Deposition; |  |  | IA-320 sensors; |  | D1: D2: TC hold D3: IA-320 slow cool 4K D4: D5: L2-293/L2-314/L2-327 warm D6: G2 L/C4K/T D7: L2-137 hold D8: L2-135 C2K/T/W | C75- serialize parts, remove feedthrus LCLSll CM03-Reconfigure beam line CM04- 2K testing, mod u-tube/railing CM05- MC Line install, JT Welding/LC, Low PT, Testing cap install CM07- Instrumentation, HOM Tuning CM08- 2 phase piping, heat stations CM09- Alignment, Berry bolts, Install magnet, heaters Other- UCM from Blue Crab, LERF Module shuffle? | [7 empty] | maint day |  | Cav 8?
2017-12-01 | Fri | C75 | C50 WW; | L2-330; L2-328; Demag valves; |  |  | L2-332; | EIC-1 800C/3h | RDT-2, RDT-10 CBP; |  | Nb stub cav (GC); Eyelets; Ceramics; Ti Bolts; | L2 Spools; hand tools; LSFC-08 hardware; RGA wipe; Ti Bolts; |  |  | HPR1: OOC HPR2: |  | L2-293 fast vent, dis for inspection; |  | CERN-1; Deposition; String prep BPM Sub 2; | BPM sub; MB-002; |  |  | L2-327 | D1: D2: TC 4K D3: IA-320 slow cool 4K/T/W D4: D5: L2-293/L2-314/L2-327 pull D6: G2 pull; D7: L2-137 pull, mag map D8: L2-135 warm | C75- serialize parts, remove feedthrus LCLSll CM03-Reconfigure beam line CM04- 2K testing, mod u-tube/railing CM05- MC Line install, JT Welding/LC, Low PT, Testing cap install CM07- Instrumentation, HOM Tuning CM08- 2 phase piping, heat stations CM09- Alignment, Berry bolts, Install magnet, heaters Other- UCM from Blue Crab, LERF Module shuffle?
2017-12-02 | Sat | [18 empty] | BPM sub;
2017-12-03 | Sun | [13 empty] | HPR1: HPR2:
2017-12-04 | Mon | Cu/cleanup; | C50 WW BB-Maint | L2-330; L2-332 L2-331 FNAL L2 Spools; |  |  |  | EIC-1 800C 3hrs; |  |  | Ti Bolts; | L2-327; L2-328; Ti Bolts; |  | CERN-5 setup | HPR1: OOC HPR2: L2-297 L2-134 |  | L2-327 flange inspection; |  | string prep bellows; L2-328 D7/8; | Deposition; |  |  | L2-135 | CMTF Fast Cool D1: D2: TC 4K D3: IA-320 C4K/T D4: D5: D6: D7: L2-137 L/C4K D8: L2-135 hold | C75- serialize parts, remove feedthrus LCLSll CM03-Reconfigure beam line CM04-Temp Bump/Fast cool CM05- MC Line LC, Instrumentation flanges, vv side port CM07- Instrumentation, HOM Tuning CM08- 2 phase piping, heat stations CM09- Alignment, Install magnet, 2 phase piping Other- Physics space help | [9 empty] | Fast Cool Down ~9-10am
2017-12-05 | Tue | Cu/cleanup; | C50 WW | L2-331; C75 tuner plates; L2 spools; | EIC-1 optical insp; |  | J1.3-07 HOMs; | EIC-1 unload; | C50 WW; |  | Nb samples 20u; Ti bolts; Flange, plug & cam assembly; | L2-330; L2-332; Waveguide & rings; Waveguide tooling; Flextube; Covers, gaskets & clamps; |  | CERN-5 setup | HPR1: OOC HPR2:L2-310 L2-138 |  |  |  | L2-297, L2-134 to rail; L2-330, D5 insert; LSFC-08; | L2-328; CERN-1; |  | LSFC-08 sensors; CERN-1 rad sensors; |  | CMTF U-tubes D1: D2: TC pull, D3: IA-320 warm D4: D5: D6: G2 L/C4K/T D7: L2-137 C2K/T/W D8: L2-135 pull; | C75- serialize parts, remove feedthrus, lap flanges, clean waveguides LCLSll CM03-Reconfigure beam line CM04-Testing, u-tubes 8:30 CTF CM05- RF Waveguides, Faraday Tee Instrumentation flanges, vv side port CM07- RF Cable review 9 am, HOM Tuning CM08- Weld 2 phase piping, heat stations CM09- Alignment, Install magnet, 2 phase piping Other- Physics space help | [7 empty] | Accelerator Restoration in Progress Beam to 9R dump |  | Pump down today? Waveguide jumper in place for Cavity 5 testing.
2017-12-06 | Wed | Cu/cleanup; | RFD Samples | C75 Tuner plates; L2 UCM 018 | [6 empty] | Plate, cover, conatainer & foils; Hook, tee & stub; Cu bean tube; Nb samples; | L2-331; C50 WW; Covers, gaskets & clamps; Al gaskets; |  |  | HPR1: OOC HPR2: L2-276 L2-327 |  |  |  | L2-310, L2-138 to rail; L2-331, D5 insert; | LSFC-08; |  |  | L2-314 | D1: SIC hold D2: RRR L/C4K D3: IA-320 warm D4: D5: D6: D7: L2-137 warm D8: CERN-1 L/C2K/T/W | C75- serialize parts, remove feedthrus, lap flanges, clean waveguides LCLSll CM03-Reconfigure beam line CM04-Testing CM05- RF Waveguides, Faraday Tee Instrumentation flanges CM07- HOM Tuning CM08- Weld 2 phase piping CM09- Alignment, Install magnet, 2 phase piping Other- Physics space help
2017-12-07 | Thu | Cu/cleanup; | L2 spools; C50 WW; | L2 UCM 018; C75 tuner plates; | L2-293 optical insp; |  | J1.3-07 HOMs; |  |  |  | Nb samples 100 u; | L2 covers, gaskets & clamps; |  | CERN-5 30u; | HPR1: OOC HPR2:L2-306 L2-288 |  |  |  | L2-276, L2-327 to rail; L2-332 D5 insert; | L2-332, L2-330, L2-331 D5; |  |  |  | D1: SIC hold D2: RRR warm D3: IA-320 pull D4: RI-024 L/C4K no liquid D5: D6: LSFC-08 L/slow cool /2K/T D7: L2-137 pull, rad survey; D8: CERN-1 warm | C75- remove feedthrus, lap flanges, clean waveguides LCLSll CM03- Idle CM04-Testing CM05- Instrumentation flanges, Bayonet Box LC CM07- HOM Tuning CM08- Weld 2 phase piping/LC CM09- Install magnet, 2 phase piping Other- Physics space help, Weld GHRP lc fixtures. LERF Module shuffle begins | [7 empty] | Accelerator Restoration in Progress 5th Pass Separator Issues Close to Hall D delivery |  | Qo's measured on all cavities but 6. Qo's unchanged with exception of 3 and 4. 3 and 4 lower due to new Field emitters Cavity 5 coupler unscathed after hardline failure. 2 hour run of Cavities 1, 2, 7, 8. Pressure rise took out cavity 1 after 2 hours.
2017-12-08 | Fri | Cu/cleanup; | C50 WW | L2-115; L2-140 |  |  | J1.3-07 HOMs; J1.3-05 HOMs; |  | CERN-5 |  | Al samples x6; | Cavity SC x2; Bellows & tees; |  | TD-5, LSF1-3 setup; | HPR1: OOC HPR2: L2-116 |  | L2-293 full dis |  | L2-288, L2-306 to rail; | L2-332, L2-330, L2-331 D5; |  |  | L2-137 | U-tubes 9am D1: D2: RRR pull D3: D4: RI-024 warm D5: D6: LSFC-08 C2K/T/W D7: D8: CERN-1 warm/pull; | C75- remove feedthrus, lap flanges, clean waveguides LCLSll CM03- Remove beam line CM04-Testing CM05- Instrumentation flanges, Bayonet Box LC, HOM measure; CM07- HOM Tuning CM08- Weld 2 phase piping/LC CM09- Install magnet, 2 phase piping Other- Physics space help, Weld GHRP lc fixtures. | [7 empty] | Accelerator Restoration in Progress 5th Pass Separator Issues NL coldbox trip Access to check on scroll pump at 2L25 FEL module shuffling - partially complete |  | Qo's measured on all cavities Qo's unchanged with exception of 3, 4 and 6. 3 and 4 lower due to new Field emitters Improvement seen on Cavity 6 GDR run on Cavities 3 and 4 - attempt to get data from Faraday Cup unsuccessful Detune test Cavity 1 does not appear to show FPC heating as culprit detuned cavities warm up started
2017-12-09 | Sat | [22 empty] | D4: RI-024 C/W
2017-12-10 | Sun | [13 empty] | HPR1: HPR2: | [8 empty] | D4: RI-024 C/W
2017-12-11 | Mon |  | C50 WW | L2-115; L2-140 C75 Nb discs; |  |  | L2-115; J1.3-07; | GC Nb samples (x3) 800C/3h; |  |  | CERN-5 flange BCP; | L2-116 probes and valve; L2 hardware & valves; TD-5, LSF1-3 |  | TD-5, LSF1-3 10u; | HPR1: OOC HPR2: L2-116 |  | J1.3-10 bagging; L2-116; |  |  | L2-332, L2-330, L2-331 D5; |  |  |  | U-tubes 9am D1: TC L/C4K D2: D3: D4: RI-024 warm D5: D6: LSFC-08 pull D7: D8: | C75- remove feedthrus, lap flanges, clean waveguides LCLSll CM03- Remove beam line CM04-Pull U-tubes, remove from CMTF CM05- LC Ins Vac, Into CMTF CM07- HOM Tuning, Prep shields CM08- Weld 2 phase piping/LC CM09- Weld 2 phase piping Other- Physics space help
2017-12-12 | Tue | Cu/cleanup; |  | L2-144 C75 Nb discs; |  |  | L2-140; J1.3-7 | GC Nb samples (x3) 800C/3h; GC Nb sample (x1) 1000C/3h; |  |  | Cu beam tubes 952 x4; Cu beam tubes 802 x2; 4 Cu beam tubes & SS flanges; PD Nb foil; Nb samples x20; | L2-140 wipe; Deposition wipedown; LSFC-09 Parts; |  | EIC-1 setup | HPR1: OOC HPR2: TD-5 L2-308 |  | J1.3-10 bagging; Deposition wipedown & unload; |  | L2-116 D7/8 |  |  | L2-328 HOMs and sensors; |  | D1: TC D2: D3: D4: RI-024 pull, RI-009 L/C D5: D6: D7: D8: CERN-1 L/C2K/T/W (1) | C75- remove feedthrus, lap flanges, clean waveguides LCLSll CM03- Remove beam line CM04-Pull U-tubes, remove from CMTF CM05- LC Ins Vac, CMTF CM07- HOM Tuning, Prep shields CM08- Weld 2 phase piping/LC CM09- Weld 2 phase piping Other- Physics space help | [7 empty] | Three Halls taking beam 5uA tune beam to Hall A on Carbon target nA beam to Faraday Cup in Hall B Hall C 5 uA beam - Energy Measurement |  | CM05 in the Cave - Cool down starts Thursday
2017-12-13 | Wed | B-TubesCu/cleanup; |  | L2-145 C75 Nb discs; L2 Tuners |  |  | L2-145; | GC Nb samples (x3) 800C/3h; GC Nb sample (x1) 1000C/3h;; TD-5 |  |  | Mo bolts; Nb parts; |  |  |  | HPR1: OOC HPR2: L2-308 |  | L2-308 new FP |  | LSFC-09; | J1.3-10; |  | L2-332, L2-330, L2-331 D5 HOMs and sensors; |  | D1: TC hold 4K D2: D3: D4: RI-009 C/T D5: D6: D7: L2-328 L/C2K/T/W (1) D8: CERN-1 warm/pull | C75- remove feedthrus, lap flanges, clean waveguides LCLSll CM03- Remove beam line spool, warm coupler cav 4 investigation CM04-Remove Bayonet Box, Prep 4 beampipe work CM05- LC Ins Vac CM07- TDR RF cables, Install shields CM08- LC 2 phase circuit CM09- Weld 2 phase piping Other- XMAS PARTY!!!! | [7 empty] | Three Halls taking beam Hall A Ion Chamber FSD problems Hall B - Solenoid problems but back up this morning Hall C - 3 uA beam on Carbon target |  | CM05 in the Cave - Cool down starts Thursday
2017-12-14 | Thu | DL bodies; EIC-5 HC B-TubesCu/cleanup; | Cern-cu 802 BT | C75 Nb discs; L2 Tuners |  |  | CERN-5 probes; | TD-5 | [6 empty] | HPR1: OOC HPR2: LSFC-08 |  | CERN-1 dis |  | L2-308 D7/8 | J1.3-10; L2-116; LSFC-09; |  | L2-332, L2-330, L2-331 D5 HOMs and sensors; |  | U-tubes D1: TC C4K D2: D3: D4: RI-009 C/T D5: D6: D7: L2-328 C2K/T/W (1) D8: | C75- remove feedthrus, lap flanges, clean waveguides LCLSll CM03- Remove beam line spool, warm coupler cav 4 investigation CM04- Prep 4 beampipe work CM05- U-tubes, cooldown CM07- Complete checklist, Install shields CM08- LC 2 phase circuit CM09- Weld 2 phase piping/LC Other- Dewer insert-Spradlin | [7 empty] | Three Halls taking CW beam Hall A 40 uA Hall B < 30nA Hall C - 10 uA |  | CM05 in the Cave - Cool down today
2017-12-15 | Fri | DL bodies; EIC-5 HC B-TubesCu/cleanup; GC Nb SC; TC1N2; TC1TD1; | Cern-cu 802 BT | C75 Nb discs; L2 Tuners |  |  | L2-144; | TD-5 |  |  | CERN-5 blanks BCP; | CERN-5; EIC-1; MB-002; L2-144 wipe; CRN-5 parts; MB-002 parts; L2 valkve & hardware; C50 hardware; | Acid Off-Load | Acid Off-Load? | HPR1: OOC HPR2: MB-002 |  |  |  |  | L2-308 |  | L2-116 sensors & HOMs; LSFC-09; L2-332, L2-330, L2-331 D5 HOMs and sensors; |  | D1: TC C1.7K D2: D3: D4: RI-009 hold D5: L2-332, L2-330, L2-331 L/precool/C4K; D6: G2 L/C/T D7: L2-328 warm D8: L2-116 L/C4K | C75- remove feedthrus, lap flanges, clean waveguides LCLSll CM03- warm coupler cav 4 CM04- beampipe work CM05- cooldown CM07- MLI, VV install CM08- LC 2 phase circuit,solder magnet leads CM09- LC 2 phase circuit Other- Dewer insert-Spradlin, Receive VV&UCM at BC | [7 empty] | Pass change completed -beam to Halls A and B |  | CM05 in the Cave - Cool down in progress Start Testing Monday
2017-12-16 | Sat | [13 empty] | HPR2: CERN-5; CERN-5
2017-12-17 | Sun | [13 empty] | HPR1:
2017-12-18 | Mon | DL bodies; cleanup; |  | C75 Cavities C75 Nb discs L2 Tuners | [6 empty] | GC Nb SC parts weld prep; Nb samples; Nb plates x3 & 1 chamber; | C50 pair wipedown; |  |  | HPR1: OOC HPR2: MB-002 |  | MB-002 |  | CERN-5 D7/8; |  |  |  |  | CMTF pumpdown? D1: D2: D3: D4: RI-009 Hold D5: L2-332, L2-330, L2-331 C2K/T D6: G2 pull D7: L2-328 pull D8: L2-116 hold | C75- remove feedthrus, lap flanges, clean waveguides LCLSll CM03- warm coupler cav 4 CM04- beampipe work CM05- Testing CM07- VV align CM08- LC 2 phase circuit, solder magnet leads CM09- LC 2 phase circuit Other- Receive VV&UCM at BC
2017-12-19 | Tue | DL bodies |  | C75 Cavities L2 Tuners | [6 empty] | GC Nb samples (x43) 20u; |  |  |  | HPR1: OOC HPR2: |  | Lighthouse; C20 pair dis; |  | MB-002 | CERN-5; | CERN-5 120C/12h | LSFC-09 sensors |  | D1: Nb3Sn L/C4K/T D2: D3: D4: RI-009 warm D5: L2-332, L2-330, L2-331 warm D6: LSFC-09 L/slow 4K D7: D8: L2-116 C2K/T/W (1) | C75- remove feedthrus, lap flanges, clean waveguides LCLSll CM03- warm coupler cav 4 CM04- beampipe work CM05- Testing CM07- VV align CM08- LC 2 phase circuit, solder magnet leads CM09- LC 2 phase circuit CM10- pass out from cleanroom Other- Receive VV&UCM at BC
2017-12-20 | Wed | C50 DL |  | C75 Cavities L2 Tuners |  |  |  | GC Nb samples (x43) 1000C/2h |  |  | Nb sample cahmber & Nb plates x3; | Chamber hardware; |  |  | HPR1: OOC HPR2: Lewa Maint |  | AHU Work |  | AHU Work | MB-002 | CERN-5 120C/12h |  |  | D1: Nb3Sn C4K/T D2: D3: D4: RI-009 C/T D5: L2-332, L2-330, L2-331 warm D6: LSFC-09 C2K/T/W D7: CERN-5 L/C4K D8: L2-116 C2K/T/W 0mG | C75- remove feedthrus, lap flanges, clean waveguides, reconfigure RAM area LCLSll CM03- warm coupler repair cav 4 CM04- Configure Beamline for ship CM05- Testing CM07- VV align CM08- solder magnet leads, split rings CM09- HV MLI/Mag shields/Flux gates CM10- Berry bolts/RF Measurements Other- VV S/N 22 from BC to TL
2017-12-21 | Thu | TC1N2; TC1TD1; EIC-5 HC; RFD Damp |  | C75 Cavities L2 Tuners |  |  |  | GC Nb samples (x43) 1000C/2H |  |  | Maint | Maint Plastic flange; SNS parts; |  |  | HPR1: OOC HPR2: Lewa Maint |  | DQW dis; |  | L2-115 D7/8; |  |  |  |  | D1: D2: D3: D4: D5: L2-332, L2-330, L2-331 pull D6: LSFC-09 C4K D7: CERN-5 C2K/T/W D8: L2-116 Warm | C75- remove feedthrus, lap flanges, clean waveguides, reconfigure RAM area LCLSll CM03- warm coupler repair cav 4 CM04- Configure Beamline for ship/ Move to WS6 CM05- Testing CM07- VV align/Move to WS5 CM08- solder magnet leads CM09- HV MLI/Mag shields/Flux gates CM10- Berry bolts, RF Measurements Other- VV S/N 22 to WS4 | [7 empty] | Down
2017-12-22 | Fri |  |  | L2 Cavities | [6 empty] | Maint | Maint |  |  | HPR1: OOC HPR2: |  | Dogleg ceramic dis; |  |  | L2-115 D7/8 |  |  | L2-332, L2-330, L2-331 | D1: D2: D3: D4: D5: D6: LSFC-09 C2K/T D7: CERN-5 warm D8: L2-116 warm | C75- remove feedthrus, lap flanges, clean waveguides, reconfigure RAM area LCLSll CM03- warm coupler repair cav 4 CM04- Configure Beamline for ship/ Move to WS6 CM05- Testing CM07- VV align/Move to WS5 CM08- solder magnet leads CM09- HV MLI/Mag shields/Flux gates CM10- Berry bolts, RF Measurements Other- VV S/N 22 to WS4 | [7 empty] | Down
2017-12-23 | Sat
2017-12-24 | Sun | [13 empty] | HPR1: HPR2:
2017-12-25 | Mon | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2017-12-26 | Tue | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2017-12-27 | Wed | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2017-12-28 | Thu | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2017-12-29 | Fri | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2017-12-30 | Sat
2017-12-31 | Sun | [13 empty] | HPR1: HPR2:
2018-01-01 | Mon | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2018-01-02 | Tue | recover |  | C75 cavities L2 mag sheild L2 VV #22 |  |  | L2-321; | RDT-2, RDT-10 800C/2h |  |  |  | L2 304 Valve, burst disc & Hardawre; L2-304 wipe down; |  |  | HPR1: OOC HPR2: Clean up run L2-304 |  | L2-304 cage; L2-137 cage; |  | L2-140, L2-144, L2-145 D5; |  |  | L2-308 sensors & HOMS; L2-115 HOMs & sensors; |  | D1: D2: D3: D4: D5: D6: D7: CERN-5 pull; L2-308 L/C4K D8: L2-116 pull; | C75- remove feedthrus, lap flanges, clean waveguides LCLSll CM03- warm coupler repair cav 4 CM04- Prep for Valves CM05- Testing, to 2K CM07- Beam Pipes, Warm couplers, Peripherals CM08- solder magnet leads CM09- Mag shields/Flux gates CM10- Fiducialization Other- VV S/N 22 set up for de-Mag, QC | [7 empty] | Winter SAD |  | CM05 at 4K Emax / FE completed all 8 cavities On cavity w/ FE 7 cavities w/ usable gradient 18- 21 MV/m temp bump today? PSS Cert tomorrow - no HPRF until cert complete
2018-01-03 | Wed | TC1N2; TC1TD1; EIC-5 HC; | restore | C75 cavities |  |  | L2-253 | RDT-2, RDT-10 800C/2h |  |  | Nb foil BCP; DQW HOM 100u; Nb tensile samples (x43); | DQW HW; L2-137 HW; |  | Acid load | HPR1: OOC HPR2: L2-137 L2-304 |  | L2-304 new FP; |  | L2-140, L2-144, L2-145 D5; |  |  |  |  | D1: D2: D3: D4: D5: D6: D7: L2-308 C2K/T/W D8: L2-115 L/C4K | C75- remove feedthrus, clean waveguides LCLSll CM03- warm coupler repair cav 4 /LC complete CM04- Prep for Valves, weld CM05- Testing, fast cooldown today CM07- Beam Pipes, Warm couplers, Peripherals CM08- solder magnet leads CM09- at WS 3, Demag components CM10- Fiducialization, magnet install Other- VV 22 set up for QC Dept |  |  | LCSLII flanges (x6) |  |  |  |  | Winter SAD |  | CM05 in progress temp bump today PSS Cert today
2018-01-04 | Thu | TC1N2; TC1TD1; EIC-5 HC; | CERN1 Cu | L2 cavities | [10 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: L2-308 warm D8: L2-115 hold 4K | C75- remove feedthrus, lap flanges, clean waveguides LCLSll CM03- warm coupler repair cav 4 CM04- Weld gas guard valves CM05- Testing CM07- Beam Pipes, Warm couplers, Peripherals CM08- solder magnet leads CM09- Demag components, unite to UCM CM10- Fiducialization Other- VV 22 set up for QC Dept
2018-01-05 | Fri | TC1N2; TC1TD1; EIC-5 HC; C75 HC drawing; |  | L2 VV #22 |  |  |  | DQW HOM 600C/10h; |  |  |  | L2 Bellows (x10+); |  |  | HPR1: OOC HPR2: TD-5 |  | L2-137 new FP; |  | TD-5; L2-304 D7/8; | L2-140, L2-144, L2-145 D5; |  |  |  | D1: D2: TC L/C4K/T D3: D4: D5: D6: D7: L2-308 pull D8: L2-115 hold 4K
2018-01-06 | Sat
2018-01-07 | Sun | [13 empty] | HPR1: HPR2:
2018-01-08 | Mon | TC1N2; TC1TD1; EIC-5 HC; C75 HC drawing; | Cern BT RFD Assy | L2-321; BLA blank flanges (x10) C75 Cavities |  |  | L2-325 L2-315 | DQW HOM 600C/10h; | RDT-2, RDT-10; |  |  | MB-002 parts?; L2 Bellows (x12); Al Gaskets; Fasteners; |  | HF spike; | HPR1: OOC HPR2: MB-002 L2-137 |  | L2 gate vlvs |  |  | L2-140, L2-144, L2-145 |  | L2-140, L2-144, L2-145 HOMs & sensors; |  | D1: SIC load D2: RRR Warm/pull D3: D4: RI-009 C/T D5: D6: TD-5 L/C/T D7: D8: L2-115 C2K/T/W | C75- remove feedthrus, lap flanges, clean waveguides LCLSll CM03- warm coupler repair cav 4 CM04- Weld gas guard valves CM05- Testing CM07- Beam Pipes, Warm couplers, Peripherals CM08- solder magnet leads CM09- Needle bearing installation CM10- Fiducialization Other- VV 22 set up for QC Dept | [7 empty] | CEBAF Restore - Beam to 7E |  | CM05 in progress PSS Cert complete w/ exception of SSA's 3 and 8 U-Tubes 1pm
2018-01-09 | Tue | Bill Out | Cern BT RFD Assy | L2-066 C75 Cav BLA blank flanges (x10) |  |  | L2-315 L2-167 | DQW HOM Out |  |  | DQW HOM 10u (pm); | EIC-1; L2 Bellows x6; 6" Cu gaskets x10; Cold FPC covers & HW; Fasteners; RDT-2 & RDT-10; EIC-1; |  | EIC-1 30u; | HPR1: OOC HPR2: RDT-14 |  | L2 gate vlvs |  | MB-002 D7/8; L2-137 D7/8; | L2-304; |  |  |  | D1: SIC C/T D2: RRR L/C/T/W D3: D4: RI-009 C/T D5: L2-140, L2-144, L2-145 L/precool D6: D7: D8: L2-115 warm | C75- remove feedthrus, lap flanges, clean waveguides LCLSll CM03- warm coupler repair cav 4 CM04- Weld gas guard valves CM05- Testing CM07- Beam Pipes, Warm couplers, Peripherals CM08- solder magnet leads CM09- Needle bearing installation CM10- Fiducialization Other- VV 22 set up for QC Dept | [7 empty] | CEBAF Restore - Maint Day |  | CM05 in progress - 2k
2018-01-10 | Wed | TC1N2; TC1TD1; EIC-5 HC; C75 HC drawing; | DL Windows C50 WW | C75 Cav L2-325 L2-253 BLA blank flanges (x10) batch #2 |  |  | L2-166 L2-165 | RDT-14 800C/3H, 140C/48H/N2 |  | EIC-1; | RDT-10 flanges; | RDT-12 Parts; RDT-10; FPC tools x2; L2-321; L2-253; L2 flages & HW; |  | RDT-10 setup; RDT-10 5u; | HPR1: OOC HPR2: RDT-12 |  | L2 gate vlvs |  | L2-321 D7/8 | L2-137; MB-002; |  | L2-304 HOMs and sensors; |  | D1: SIC C/T D2: RRR T/W D3: D4: RI-009 C/T/W D5: L2-140, L2-144, L2-145 hold D6: TD-5 W/Pull D7: D8: L2-115 pull; L2-304 load | C75- remove feedthrus, lap flanges, clean waveguides LCLSll CM03- move to north end TL CM04- Weld gas guard valves CM05- Testing CM07- Beam Pipes, Warm couplers, Peripherals CM08- solder magnet leads CM09- Needle bearing installation CM10- Fiducialization Other- VV 22 set up for QC Dept | [7 empty] | Acc Restore - Setting up for Physics Cold box trip on Day shift. Recovered on Swings |  | CM05 in progress Extended run Cavities 1 and 2 for Cplr heating Four cavity run
2018-01-11 | Thu | TC1N2; TC1TD1; EIC-5 HC; C75 HC drawing; | DL Windows C50 WW FNAL bellows | C75 Cav L2-315 |  |  | L2-165 L2-153 | RDT-14 800C/3H, 140C/48H/N2 |  |  | Nb sample chamber,covers, plate & Rod; SS flanges x2; Cu beam tubes x2; Al electrode; LCLS-ll FP; Sample chamber & plates; Half cell x2; Beam tubes x2; | 6mmBolts x6; 6mm nuts; Vac tees x3 & flange; Ceramic windows; |  | LSF1-2 setup | HPR1: OOC HPR2: |  | L2 gate vlvs |  | DQW HOM; RDT-12 | L2-321 D7/8 | MB-002 120C 12h |  |  | D1: D2: RRR C/T/W D3: IA-320 L/hold D4: RI-009 W D5: L2-140, L2-144, L2-145 C4K (1) D6: D7: D8: L2-304 hold | C75- remove feedthrus, lap flanges, clean waveguides LCLSll CM03- move to north end TL CM04- LC/ pressure test CM05- Testing CM07- Beam Pipes, Warm couplers, Peripherals, JT valves CM08- alignment Friday CM09- Needle bearing installation/alignment CM10- welding 2-phase Other- VV 22 set up for QC Dept | [7 empty] | Acc Restore - 50 nA CW beam to Hall D on Owl Shift |  | CM05 in progress Four cavity run attempts continue Lost half of day shift and most of swing shift to Breaker Fest '18
2018-01-12 | Fri | TC1N2; TC1TD1; EIC-5 HC; C75 HC drawing; CERN Crab HOM; | DL Windows; CERN bellows; | C75 Cav L2-167 L2-315 |  |  | L2-165 L2-153 | RDT-14 800C/3H, 140C/48H/N2 |  |  |  | L2-066; Lg SS pipes x4; Bag bellows for shipping x11; Clamps; |  | LSF1-2 1.000 u | HPR1: OOC HPR2: RDT-10 LSF1-2 |  | L2-066 cage; L2 gate vlvs |  |  | RDT-12 |  | L2-137 HOMs and sensors; |  | D1: D2: RRR T/W D3: IA-320 C4K/T D4: RI-009 load D5: L2-140, L2-144, L2-145 C4K D6: D7: MB-002 load D8: L2-137 load | C75- Prep for cavities LCLSll CM03- Fly CM03 to WS6 CM04- Leak check, Pressure test CM05- Testing CM07- End Cap, Warm couplers, Peripherals CM08- Alignment CM09- Check alignment & Needle bearing installation CM10- 2 Phase welding Other- Installation align
2018-01-13 | Sat
2018-01-14 | Sun | [13 empty] | HPR1: HPR2:
2018-01-15 | Mon | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8: | C75- Prep for cavities LCLSll CM03- Fly CM03 to WS6 CM04- Leak check, Pressure test CM05- Testing CM07- End Cap, Warm couplers, Peripherals CM08- Alignment CM09- Check alignment & Needle bearing installation CM10- 2 Phase welding Other- Installation align
2018-01-16 | Tue | TC1N2; TC1TD1; EIC-5 HC; C75 HC drawing; CERN Crab HOM (roll); | CERN BTs DL Windows | L2-315 L2-167 L2-166 C75-Nb sample |  |  | L2-153 L2-156 L2-152 |  |  |  | MB-003 DB & EG weld prep; CERN Crab HOM; | L2 Bellows (x12); LSF1-3 parts; misc hardware; SNS tool; L2-325; L2-167; Coupler inst tool; Hardware & Fasteners; |  | RDT-2 setup | HPR1: OOC HPR2: L2-066; LSF1-3; |  | CERN-5 dis and flange inspection |  | RDT-10; | DQW HOM; RDT-12; L2-304 |  |  |  | D1: SIC hold D2: RRR warm D3: IA-320 T D4: RI-009 D5: L2-140, L2-144, L2-145 C2K/T/W D6: RDT-12 L/C1.5/T(pm) D7: MB-002 hold D8: L2-137 C4K (D3-->D5) | C75- Prep for cavities LCLSll CM03- Fly CM03 to WS6 CM04- Leak check, Pressure test CM05- Testing CM07- Ion Pump spool, Warm couplers, Peripherals, LC/PT Line A CM08- Alignment CM09- Check alignment / adjust CM10- 2 Phase welding Other- Align VV to cantilever | [7 empty] | Currently delivering Beam to 4 Halls |  | Breaker repair completed Successful test of Faraday Cup Fast Cool Down today - weather permitting
2018-01-17 | Wed | EIC-5 HC; C75 HC drawing; | CERN BTs DL Windows | C75 test DB (x2) L2-153 | L2-066 |  | L2-152 |  |  |  | CERN-5 flanges ? | RDT-2; Test stand elbows; L2 bellows; L2 string parts; L2-153 wipe; |  | RDT-2 5u | HPR1: OOC HPR2: RDT-14; |  | L2-Gate Valves |  | LSF1-3 D7/8; RDT-14; |  |  | L2-321 HOMs and sensors; L2-304 sensors and HOMs; |  | D1: SIC hold D2: RRR pull D3: IA-320 C4K/T D4: RI-009 D5: L2-140, L2-144, L2-145 HOM/warm D6: RDT-12 pull; RDT-10 L/C/T D7: MB-002 C4K D8: L2-137 C2K/T/W | C75- Prep for cavities LCLSll CM03- Fly CM03 to WS6 CM04- LC/PT Line A CM05- Testing, Fast cool CM07- Warm couplers, Inst. Flanges, LC/PT Line A CM08- Alignment CM09- Check alignment / adjust CM10- 2 Phase welding Other- Align VV to cantilever, Fab demag coils FL04 | [7 empty] | Restore Complete 4 Beams -> 4 Halls! Starting Friday Currently delivering Beam to A, C and D |  | Completed 5 Cavity Run 12- 15 MV/m gradients all day Magnet Test completed-18A for 1 Hour Breaker Replacement today (AM) Back to 2K sometime in PM Fast Cool down tomorrow (
2018-01-18 | Thu | EIC-5 HC; C75 HC drawing; | BB cleaning run; CERN BTs DL Windows; C75 HC drawing; | L2-166 demag L2-152 cmm L2-165 cmm L2 FT; |  |  | L2-155 |  |  |  |  | Test stand parts; L2 spool & bellows; SS bellows; Cryo valves & tees; |  |  | HPR1: OOC HPR2: CERN-5 |  | C50 test stand maint; |  |  | LSF1-3 D7/8 (failed); |  |  |  | D1: SIC D2: RRR C D3: IA-320 C4K/T D4: RI-009 C/T/W D5: L2-140, L2-144, L2-145 warm D6: RDT-14 C D7: MB-002 C2K/T/W D8: L2-137 warm | C75- Prep for cavities LCLSll CM03- Fly CM03 to WS6 CM04- LC/PT Line A CM05- Testing, Fast cool CM07- Warm couplers, Inst. Flanges, LC/PT Line A CM08- Alignment CM09- Check alignment / adjust CM10- 2 Phase welding Other- Align VV to cantilever, Fab demag coils FL04 | [7 empty] | Recovered from 3rd pass separation and beam loss issues 4 beams -> 4 halls. Smooth running for the rest of shifts |  | Fast Cool Down Fail Try again this morning Hopefully Qo measurements tonight
2018-01-19 | Fri | EIC-5 HC; | DL Windows; L2 Bellows (x12); | L2-156 demag L2-152 demag L2-165 demag L2 FT; | L2-066 | [5 empty] | C75 test DB (x2); LSF1-3 flanges; | L2-159; Hoses x10; SC parts; |  |  | HPR1: OOC HPR2: RDT-2; L2-278 |  | LSF1-3 dis; L2-Gate Valves | [6 empty] | D1: SIC D2: RRR W/T D3: IA-320 C2K/T/W D4: RI-009 C/T/W D5: L2-140, L2-144, L2-145 warm D6: RDT-14 C/T D7: MB-002 warm D8: L2-137 pull, L2-321 L/C4K | C75- Prep for cavities LCLSll CM03- Fly CM03 to WS6 CM04- PT Line A,Complete JT weld CM05- Testing CM07- Warm couplers, Inst. Flanges, PT Line A, Bayonet Box CM08- Alignment CM09- Remove lollipops, 2 phase welding CM10- 2 Phase welding, instrumentation Other- Align VV to cantilever, Fab demag coils FL04 | [7 empty] | Four Hall Operations |  | Post fast cool Q0 measurements
2018-01-20 | Sat | [22 empty] | D4: RI-009 C/T/W
2018-01-21 | Sun | [13 empty] | HPR1: HPR2: | [8 empty] | D4: RI-009 C/T/W
2018-01-22 | Mon | MB-003; C75 Test; EIC-5 HC; | C75 DL; Target repair; | RFD; L2 cavities; L2 FPs; |  |  | L2-146 |  | LSF1-3 flanges; TC1N2; TC1TD1; |  | C75 HC (x3); LSF1-3 Flanges; Lsf1-3 Beam tubes; Mo HW; Nb cylinder, plates, chamber & container; | L2-165; Bellows N2 bag; Al end caps x70; Berry bolts; |  | RDT-12, RDT-13, RDT-14 setup | HPR1: OOC HPR2: L2-278 (w/ext rinse); |  | L2-278 new FP; L2 tooling maint. |  | L2-315, L2-325, L2-167 D5; CERN 5; |  |  | DQW2 sensors and HOMs (& LL) | L2-140 (1), L2-145 (2) | D1: D2: D3: IA-320 ? D4: RI-009 C4K/warm D5: D6: RDT-10 L/C/T (check valve open) D7: MB-002 pull; L2-253 L/C4K D8: L2-321 C2K/test | C75- Prep for cavities LCLSll CM03- Fly CM03 to WS6 CM04- PT Line A,Complete JT weld CM05- Testing CM07- Warm couplers, Inst. Flanges, PT Line A, Bayonet Box CM08- Alignment CM09- Remove lollipops, 2 phase welding CM10- 2 Phase welding, instrumentation Other- Align VV to cantilever, Fab demag coils FL04
2018-01-23 | Tue | MB-003; EIC-5 HC; | C75 DL; Target repair; | RFD; L2 cavities; |  |  | L2-146; L2-250; L2-254 |  |  |  | Nb samples (x2); | RDT-12, RDT-13, RDT-14; TC1N2; TC1TD1; L2-155; Bulbs & tools for electricians; Split rings; Braze alloy for DL; |  | RDT-12, RDT-13, RDT-14 40u | HPR1: OOC HPR2: LSF1-3; |  | L2 tooling maint. |  | RDT-2; L2-278 D7/8 | CERN-5; L2-315, L2-325, L2-167 D5; |  |  | L2-144 | D1: D2: RRR W/T D3: IA-320 C4K D4: RI-009 C/T D5: D6: D7: L2-253 C2K/test D8: L2-321 test | C75- Prep for cavities LCLSll CM03- Idle CM04- Complete JT weld CM05- Testing CM07- Inst. Flanges, MC line, Bayonet Box CM08- Tuners CM09- 2 phase welding, heat stations CM10- 2 Phase welding/LC Other- Align VV to cantilever, Fab demag coils FL04 | [7 empty] | Yesterday maintenance day and recovery 2L10-8 tuner cold box trip |  | Fast cool down yesterday SSA 8 preppin for replacement
2018-01-24 | Wed | maint day; | C75 DL; | RFD; L2 cavities; L2 bellows |  |  | L2-252; L2-319 | RDT-13 800C/3h 2N6 |  |  |  | Twin HW; Twin-2; BPM hardware; |  |  | HPR1: OOC HPR2: Twin-2 |  | L2 tooling maint. |  | LSF1-3; | L2-278; L2-315, L2-325, L2-167 D5; |  | DQW2 sensors; | L2-137 | D1: D2: D3: IA-320 C2K/T/W D4: RI-009 pull; field map D5: D6: D7: L2-253 C2K/T D8: L2-321 test/warm | C75- Prep for cavities LCLSll CM03- Idle CM04- Complete JT weld/RT Thursday CM05- Testing CM07- Inst. Flanges, MC line, Bayonet Box, Low PT-noon, RT Thursday CM08- Tuners CM09- 2 phase welding, heat stations CM10- 2 Phase welding/LC Other- Fab demag coils FL04 | [7 empty] | Four Hall Operations 2L16-30 WG Vac deteriorating |  | Post fast cool Q0 measurements
2018-01-25 | Thu | CERN Crab HOM (weld); MB-003; C75 Test; EIC-5 HC; | C75 DL; | RFD; L2 bellows; L2 HOM probes; | IA-114; IA-110; IA-012; |  |  | RDT-13 800C/3h 2N6: |  | TC1TD1, TC1N2 |  | BPM housing (x3); BPM FT(x12); L2 long spools (x2); Lollipop parts; C75 HC (x7); L2 string tooling; L2 bolt holes x2;RDT-2 parts; Cryo valves hoses & flanges; |  |  | HPR1: OOC HPR2:RDT-2; |  | Gun dis; Cleanroom particle survey; |  | TWIN-2 | RDT-2 failed |  | L2-315, L2-325, L2-167 D5 HOMs and sensors; |  | D1: D2: D3: IA-320 warm D4: DQW2 L/C4K D5: D6: LSF1-3 L/C D7: L2-253 test/warm D8: L2-321 warm | C75- Prep for cavities LCLSll CM03- Idle CM04- Complete JT weld/RT 4pm Move CM to WS5 CM05- Testing CM07- MC line, Bayonet Box, RF Waveguides, RT 4pm CM08- Tuners, RF Cables, heat stations CM09- LC 2 phase, Magnet solder CM10- 2 Phase LC Other- Fab demag coils FL04
2018-01-26 | Fri | CERN Crab HOM (weld); MB-003; C75 Test; EIC-5 HC; test weld; | C75 DL; | RFD; L2 bellows; | IA-114; IA-110; IA-012; |  |  | RDT-13 800C/3h 2N6; |  |  | RFD Damper parts; C75 HC (x7); Al alignment tools x4; LSFc-10; Nb Sheets; Nb sample; | Lollipop parts; HD ICE Beam tubes; |  | TC1TD1, TC1N2 setup; | HPR1: OOC HPR2: |  | L2 tooling maint. |  | RDT-2; |  |  | L2-278 HOMs and sensors; |  | D1: L2 FT L/C4K (1st cycle) D2: RRR D3: IA-320 pull, leave open for maint D4: DQW2 C2K/T D5: L2-D5 load D6: LSF1-3 leaked D7: L2-253 pull; L2-278 L/C4K D8: L2-321 pull; L2-304 L/C2K/T/W | C75- Prep for cavities LCLSll CM03- Start rework CM04- Move CM to WS6 CM05- Warming up CM07- Close Bayonet Box, RF Waveguides, Ins Vac LC, E&L Flanges CM08- Tuners, Mu shields, heat stations CM09- LC 2 phase, Magnet solder CM10- 2 Phase LC, MLI, mag shields Other- Fab demag coils FL04, Unload VV-UCM Bluecrab | [9 empty] | warming up
2018-01-27 | Sat
2018-01-28 | Sun | [13 empty] | HPR1: HPR2:
2018-01-29 | Mon | RFD damper; CERN Crab HOM (weld); MB-003; C75 Test; EIC-5 HC; | DL windows; | L2 bellows C75 beamtubes | LSFC-9; |  | LSF5-1 check FF; | Nb sheets 800C/3h |  |  | Nb sheets (PD) 20u; C75 HC (x8); Cu cavity; Al Shearing tools | LSF1-2 & HW; CBP Blanks (x18); Elbows with teflon inserts, coupler; L2 bolt holes; |  | TC1TD1, TC1N2 bulk (per L2 recipe) | HPR1: OOC HPR2: LSF1-2 |  | LSF1-3; BPM sub; |  | L2-152 D7/8; L2-153 D7/8; | RDT-2; |  |  |  | D1: L2 FT C4K /W (2nd cycle) D2: RRR C4K D3: D4: DQW2 C2K/T/W (2) D5: L2-315, L2-325, L2-167 precool (3) D6: LSF1-3 pull; LSF1-3 load/pull D7: L2-278 C2K/T/W (1) D8: L2-304 pull; CERN5 L/C4K (4) | C75- Prep for cavities LCLSll CM03- Start rework CM04- prep 4 end caps CM05- u-tubes 9 am, remove from cave CM07- Ins Vac LC, HOM Measurements, Prep 4 cave CM08- Tuners, Mu shields, heat stations CM09- LC 2 phase, Magnet solder CM10- MLI and mag shields Other- Fab demag coils FL04, Unload VV-UCM Bluecrab, UITF Weld | [7 empty] | Four Hall Operations |  | CM05 Removal SSA 8 Replaced Hardline work in progress
2018-01-30 | Tue | MB-003; C75 Test; EIC-5 HC; | DL windows; | C75 travelers L2-252; L2-250; | LSFC-8, |  | LSF5-1 | Nb sheets 800C/3h; |  |  | Sample plates & chamber; | LSF5-1 & HW; L2 cavities (x3) bolt holes; |  | TC1TD1, TC1N2 bulk (per L2 recipe) | HPR1: OOC HPR2: |  | BPM sub; |  | LSF1-2; | L2-152; L2-153; |  |  |  | D1: L2 FT C4K/W (3rd cycle) D2: RRR D3: D4: DQW2 T D5: L2-315, L2-325, L2-167 C4K (1) D6: RDT-2 L/C/T (3) D7: L2-278 warm D8: CERN5 C2K/T (2) | C75- Prep for cavities LCLSll CM03- Start rework, remove JT's CM04- Bearing retainers, Alignment CM05- Remove from CMTF, Prep for Beampipe work CM07- Into CMTF CM08- Mu shields, Instrumentation, to WS 4 CM09- LC 2 phase, Magnet solder CM10- MLI and mag shields Other- Fab demag coils FL04
2018-01-31 | Wed | MB-003; | DL Windows C50 WW Air Fire Fixturing | L2-252 L2-148 C75 travelers L2 switch brackets |  |  | C75-002 check FF and probes; |  |  |  | Nb sheets (PD) 10u; | TC1TD1, TC1N2; Valves, flanges & HW; HW & gaskets; |  | TC1TD1, TC1N2 bulk (per L2 recipe) | HPR1: OOC HPR2: RDT-14 |  | BPM sub; RDT-2 dis; |  | Twin2; L2-156 D7/8 | LSF1-2; |  | L2-152 HOMs and sensors; | L2-278 | D1: SIC L/C/T D2: Nb3SN sample L/C4K D3: D4: DQW2 C2K/T D5: L2-315, L2-325, L2-167 C2K/T/W D6: LSF1-2 load D7: L2-278 pull; L2-152 load D8: CERN5 warm; | C75- Prep for cavities LCLSll CM03- idle CM04- Bearing retainers, Alignment CM05- Prep for Beampipe work CM07- Into CMTF, Ins Vac LC, gas return CM08- Instrumentation, heat stations CM09- Magnet leads, Instrumentation CM10- Instrumentation, UCM Other- UCM /VV from BlueCrab | [7 empty] | Four hall operation |  | CM07 in cave;
2018-02-01 | Thu | MB-003; | C75 | C75 travelers L2 UCM-024 | L2-273; |  | L2-146; L2-147; | RDT-14 800C/3h & 140C/48h N2 | CBP setup; CERN Cu cavity (x4) CBP setup; | TC1TD1, TC1N2 bulk | C75 HC (x?); CRN1-Cu parts weld prep; | String cages; Cu spacer & tube holder; |  |  | HPR1: OOC HPR2: RDT-2 |  | BPM sub; L2 bellows cleaning; |  | L2-278 | L2-156; |  |  |  | U-tubes 9am Kinney maint D1: SIC C/T D2: D3: D4: DQW2 warm; D5: L2-315, L2-325, L2-167 warm D6: LSF1-2 C/T D7: L2-152 C4K D8: CERN5 warm; | C75- Prep for cavities LCLSll CM03- idle CM04- Bearing retainers, ghrp inserts CM05- Remove BB, Prep for Beampipe work CM07- U-Tubes 9am, cooldown, Ins Vac LC CM08- Instrumentation, heat stations CM09- Magnet leads, Instrumentation CM10- Instrumentation, UCM insp Other- Beam Pipe preassy | [7 empty] | Four hall operation |  | CM07 in cave; Cool down start today
2018-02-02 | Fri | MB-003; | Vacation | L2 UCM-024 L2 HOM feedthrus | L2-234 |  | L2-146; L2-147; L2-148; L2-149; | RDT-14 800C/3h & 140C/48h N2 |  |  |  | IA-114; L2 bellows x6; |  | IA-114 setup; | HPR1: OOC HPR2: LSF1-3 |  | Light bulb change-out; BPM sub; L2 bellows cleaning; |  | RDT-2 | L2-278; L2-315 cold leak, check torque; |  | L2-153 HOMs and sensors; | L2-167 | D1: SIC C/T D2: Nb3SN pull; TC L/C/T/W D3: D4: DQW2 pull; RI-009 L/C/T D5: L2-315, L2-325, L2-167 pull D6: LSF1-2 C/T D7: L2-152 C2K/T/W (Cable 1) D8: CERN5 pull; L2-153 L/C4K (check bottom valve open) | C75- Prep for cavities LCLSll CM03- idle CM04- Bearing retainers, ghrp inserts CM05- Remove BB, Prep for Beampipe work CM07- U-Tubes 9am, cooldown, Ins Vac LC CM08- Instrumentation, heat stations CM09- Magnet leads, Instrumentation CM10- Instrumentation, UCM insp Other- | [7 empty] | Four hall operation |  | CM07 in cave; Cool down
2018-02-03 | Sat | [6 empty] | RDT-14 800C/3h & 140C/48h N2 | [15 empty] | D4: RI-009 C/T
2018-02-04 | Sun | [6 empty] | RDT-14 800C/3h & 140C/48h N2 | [6 empty] | HPR1: HPR2: | [8 empty] | D4: RI-009 C/T
2018-02-05 | Mon | EIC-5 HC; | Vacation | L2 HOM feedthrus C75 travelers |  |  | L2-148 | C75 samples 1000C/2h |  |  | C75 HC (x11); Nb samples x3; Mo nuts; | LSF5-1; C75 samples; C75 HOM load parts; IA-114; Clean room tape; |  | IA-114 25u; | HPR1: OOC HPR2: L2-332; L2-330; |  | L2-315 full dis; |  | L2-165, L2-278, L2-166 D5; | RDT-2; |  | L2-156 HOMs and sensors; |  | D1: SIC hold D2: D3: D4: D5: D6: LSF1-3 L/C/W D7: L2-152 pull; L2-156 L/C4K (cables 2) D8: L2-153 C2K/T/W | GO EAGLES-FLY EAGLES FLY C75- Prep for cavities LCLSll CM03- Tune HOM's CM04- Bearing retainers CM05- Beampipe work CM07- Pump down to 2K, Ins Vac LC CM08- Instrumentation, Prep shields CM09- Alignment CM10- Instrumentation, Unite to UCM Other- | [7 empty] | maint day |  | PSS Cert Tuning cavities and FPCs
2018-02-06 | Tue | EIC-5 HC; | Vacation | L2 Tuners L2 FP Probes | L2-321; MB-003; |  | CM08 HOMs tuning; | C75 samples 1000C/2h |  |  |  | L2 cavity clean & bolt holes; Neg chamber; Vac fittings; Cu elbow; |  | LSF5-1 setup; | HPR1: OOC HPR2: L2-140; L2-308; |  | L2-1 to rail; C75 HOM load; |  | L2-165, L2-278, L2-166 D5; L2-155 D7/8; |  |  |  |  | D1: SIC hold D2: D3: D4: D5: D6: RDT-2 L/C/T D7: L2-156 C2K/T/W D8: L2-153 warm; | C75- Prep for cavities LCLSll CM03- Tune HOM's Priority low CM04- Bearing retainers, Ship alignment CM05- Beampipe work, Remove JT's CM07- Ins Vac LC, testing CM08- Instrumentation,Tune HOM's CM09- Alignment CM10- Instrumentation, Unite to UCM Other- Fab coils for C50 demag | [7 empty] | beam studies; 2L16-30 vacuum issues; |  | Q0's on swings; SSA-8 misbehaving;
2018-02-07 | Wed | EIC-5 HC; | Vacation | L2 Tuners L2 mag shielding L2-254; |  |  | CM08 HOMs tuning; |  |  |  |  | L2 covers, gaskets, clamps & alignment tools; L2-167 bolt holes; L2 flanges x6; |  | LSF5-1 10u; | HPR1: OOC HPR2: L2-135; L2-167; L2-332; |  | L2-2, -3 to rail; |  |  | L2-165, L2-278, L2-166 D5; |  |  |  | D1: SIC C/T D2: D3: D4: D5: D6: RDT-2 C/T D7: L2-156 warm D8: L2-153 hold; | C75- Prep for cavities, weld samples LCLSll PCM- WS6, Remove JT's, WC Investigation 8 CM03- Has been moved to UITF CM04- Bearing retainers, Ship alignment CM05- Beampipe work CM07- Testing CM08- Instrumentation,Tune HOM's CM09- Alignment CM10- Unite to UCM Other- Fab coils for C50 demag | [7 empty] | 4-hall operation; ESR trip; |  | tuning couplers; RF coax elbow #5 heating;
2018-02-08 | Thu | EIC-5 HC; | Vacation | L2 Tuners L2-319; L2 mag shielding | [7 empty] | MB-003; L2 blanks, covers, clamps & alignment tools; |  |  | HPR1: OOC HPR2: L2-137; L2-328; |  | L2-4, -5, -6 to rail; |  | C75 HOM load D1/2; |  |  |  |  | D1: SIC C/T D2: D3: D4: D5: D6: TC1N2 L/C D7: L2-156 hold; D8: L2-153 hold; | C75- Prep for cavities, weld samples LCLSll PCM- WS6, Remove JT's, WC Investigation 8 CM03- Has been moved to UITF CM04- Bearing retainers, Ship alignment CM05- Beampipe work CM07- Testing CM08- 50k shield CM09- Alignment CM10- Unite to UCM Other- Fab coils for C50 demag | [7 empty] | 4-hall operation; beam loss;
2018-02-09 | Fri | EIC-5 HC; | vacation | L2 Tuners L2 mag shielding | [6 empty] | SS flanges; Nb heat shields BCP 15u per side x21; RDT-2 Nitric soak; | Washers; 2 sample heads; Neg Chamber; | MB-003 setup; | Acid change | HPR1: OOC HPR2: RDT-14 RDT-2; |  | L2, -7, -8 to rail; |  |  | L2-165, L2-278, L2-166 D5; L2-155; Twin2; |  |  |  | D1: SIC C D2: TC C D3: D4: D5: D6: TC1N2 L/C D7: L2-156 pull; D8: L2-153 pull; | C75- Prep for cavities, weld samples LCLSll PCM- WS6, Remove JT's, WC Investigation 8 CM03- Has been moved to UITF CM04- Bearing retainers, Ship alignment CM05- Beampipe work CM07- Testing CM08- 50k shield CM09- Alignment CM10- Unite to UCM Other- Fab coils for C50 demag | [7 empty] | Reset optics
2018-02-10 | Sat | [17 empty] | RDT-14
2018-02-11 | Sun
2018-02-12 | Mon | EIC-5 HC; CERN1-Cu1 | BB regen; C75; | L2 Tuners L2-315 FP port; |  |  | IA-110 probes; |  |  |  | Cu beam tubes; | L2-250; L2-319; L2-148; | MB-003 100u; | HF Spike | HPR1: OOC HPR2: LSF5-1; |  | CERN5 dis; |  | J1.3-11 bag; | L2-155; |  | L2-165, L2-278, L2-166 D5 HOMs and sensors; |  | D1: SIC C/T D2: RRR L/C/T D3: D4: D5: L2-165, L2-278, L2-166 L/precool D6: RDT-14 L/C/T D7: D8: | C75- Prep for cavities, weld samples LCLSll PCM- WS6, WC Investigation cav 8, inspect internals CM03- IDLE CM04- Bearing retainers, Ship alignment CM05- Beampipe work CM07- Testing CM08- IDLE CM09- Tuners, VV LC done-QA/QC Insp CM10- Extended tuner, 2 phase piping Other- Fab coils for C50 demag FL04, | [7 empty] | Optics tuning; |  | Q0's completed;
2018-02-13 | Tue | CERN1-Cu1 | C75 1/2 cell; | L2 FP Probes-RW L2-147 L2-254; |  |  | EIC1 probe cal; | Nb samples 800C/3h; |  |  |  | L2-252; clamps/alingment tools; 18x blanks; IA-114; Neg Diff cans x 3; vented bolts x9; |  | IA-110 setup; | HPR1: OOC HPR2: IA-114 |  |  |  | BPM tests; L2-250 D7/8; | J1.3-11; BPM tests; |  | L2-155 HOMs and sensors; |  | D1: SIC C/T D2: RRR Warm D3: D4: D5: L2-165, L2-278, L2-166 C4K D6: D7: L2-155 L D8: | C75- Prep for cavities, weld samples LCLSll PCM- WS6, WC Investigation cav 8, inspect internals CM04- Bearing retainers, Ship alignment, ship measurements CM05- Beampipe work CM07- Testing, FCDown CM08- Hold CM09- Tuners CM10- Weld 2 phase piping, M.Lead heat stations Other- Fab coils for C50 demag FL04, u-tube support | [7 empty] | Optics retune ongoing- High halo counts and beam loss issues |  | Emax / Qo's complete Fast Cool Down in progress
2018-02-14 | Wed | CERN1-Cu1 | C75 1/2 cell; | L2-149; L2-147; | [6 empty] | TD-5 HF x2; 3x C75 HC; Nb sample; Collinator and cooling tubes; | L2-254; EIC1; C75-002; 72" CF6" tube Gaskets; Brass bolts; Collinator and cooling tubes; Cavity body& HW; |  | IA-110 25u; | HPR1: OOC HPR2: |  | IA-114 (nonstandard HW); |  | L2-252 D7/8; L2-254 D7/8; C75 HOM | J1.3-11; L2-250; C75 HOM load D1/2; L2-252; |  | TS34-002 cables; L2 BPM |  | D1: SIC C/T D2: RRR warm D3: D4: D5: L2-165, L2-278, L2-166 C2K/T D6: TDTD1 L/C D7: L2-155 C4K (cables round 3) D8: BPM WDLC | C75- Prep for cavities, weld samples LCLSll PCM- WC Investigation cav 8, inspect internals CM04- Bearing retainers, ship measurements CM05- Beampipe work CM07- Testing CM09- Tuners CM10- Weld 2 phase piping, M.Lead heat stations Other- Fab coils for C50 demag FL04, u-tube support | [7 empty] | Hall A, B, D; beam loss studies; |  | pump down, Q0s
2018-02-15 | Thu | CERN1-Cu1 |  | L2-149; L2 mag shields L2-315 FP port; |  |  |  | MB-003 | EIC1 flanges | C75-002 | Samplesx77; Twin Cav flanges; | EIC1; Twin cavity; Neg Module; L2-148; |  | C75-002 setup; | HPR1: OOC HPR2: IA-114; |  | Torque testing |  | BPM tests; | L2-254 |  | TS34-002 cables; L2-250 HOMs & sensors; |  | D1: SIC C/T D2: D3: D4: D5: L2-165, L2-278, L2-166 HOMs D6: TDTD1 L/C D7: L2-155 C2K/T/W D8: BPM slow cool x1 & WDLC's | C75- Prep for cavities, weld samples LCLSll PCM- WC Investigation cav 8, inspect internals CM04- Bearing retainers, ship measurements CM05- Beampipe work CM07- Testing CM09- Tuners CM10- Weld 2 phase piping, M.Lead heat stations Other- Fab coils for C50 demag FL04, u-tube support | [7 empty] | Back to 4 Hall Ops Some down time due to 5th pass separator Hall C current limited to 15uA due to BLM and halo trips |  | Post FCD Qo's in progress - Cavities 1 and 2 - No real change
2018-02-16 | Fri | RFD Damper |  | L2 mag shields |  |  |  | MB-003 |  |  | RDT-2 15u; Nb plates; | Vacuum HW (GE); Nb plates & bolts; Warm couplers & valves x3; L2 HW kits; |  |  | HPR1: OOC HPR2: TD5; EIC1; RDT-2 |  |  |  | IA-114; BPM tests; TD5; |  |  | TS34-002 cables; |  | D1: SIC C/T D2: D3: D4: D5: L2-165, L2-278, L2-166 warm D6: LSF5-1 L/C/T D7: L2-155 warm; D8: BPM slow cool x1 & WDLC's | C75- Prep for cavities, weld samples LCLSll PCM- Leak check Bline CM02- Remove JT's and HOM Mu caps CM04- Bearing retainers, ship measurements CM07- Testing CM09- Instrumentation, final torque CM10- Weld/LC 2 phase piping, Solder M.Lead Other-
2018-02-17 | Sat | [22 empty] | D8: BPM | [10 empty] | No GN2 - JT valves 10/11 - 4 hrs
2018-02-18 | Sun | 4 hrs no GN2 | 4 hrs no GN2 |  |  |  |  | 4 hrs no GN2 |  |  | 4 hrs No GN2 |  | 4 hrs No GN2 | 4 hrs No GN2 | 4 hrs No GN2 |  | 4 hrs No GN2 |  | 4 hrs No GN2 | 4 hrs No GN2 | 4 hrs No GN2 | 4 hrs No GN2 | 4 hrs No GN2 | 4 hrs No GN2 no backfill
2018-02-19 | Mon | RFD Damper | 802 beamtubes | C75/Nb3Sn pair parts Calibrations |  |  | MB-003 | TC1N2, TC1TD1 600C/10h; |  |  | RDT-14 HF rinse x1; C75 stiffeners weld prep; | L2-305; L2-305 parts; RDT-14; RDT-14 parts; Field probes; Wave guise extensions; |  | C75-002 50u; | HPR1: OOC HPR2: |  |  |  |  | IA-114; |  |  |  | D1: SIC hold D2: D3: D4: D5: L2-165, L2-278, L2-166 pull; D6: D7: L2-155 pull; L2-250 L D8: BPM slow cool x2 & WDLC's | C75- Prep for cavities, weld samples LCLSll PCM- Leak check B-line, remove MC/WC CM02- Remove JT's and HOM Mu caps CM04- Ship measurements CM07- Testing CM09- Instrumentation, final torque CM10- LC 2 phase piping, Solder M.Lead Other- Map HV mag shield | [7 empty] | Beam delivery to 4 halls at reduced currents Still struggling with BL. Also struggling with RF trips. C75 cavities turned off as part of BBU investigation. |  | QO's and Emax's Heater studies on Sunday
2018-02-20 | Tue | RFD Damper | C75 stiffeners; 802 Beamtubes | C75/Nb3Sn pair parts Calbrations L2 SC valves (x8); |  |  | MB-003 tuning; | TC1N2, TC1TD1 600C/10h; |  | C75-002 | Mo pucks; Stiffening rings tube; Nb foil; FPC cap & handle; | L2-253; Cu CERN; Hard ware; |  |  | HPR1: OOC HPR2: RDT-14; L2-305 |  | TS34-002 | [6 empty] | D1: SIC pull; RRR L/C/T D2: C75 HOM loads L D3: D4: D5: D6: LSF5-1 C/T D7: L2-250 C4K D8: BPM x2 & WDLC | C75- Prep for cavities, weld samples LCLSll PCM- Remove MC/WC's CM02- Remove HOM Mu caps, move to WS5, LC BLine CM04- Idle CM07- Testing CM09- Instrumentation, final torque CM10- Solder M.Lead, MLI, Instrumentation Other- Map HV mag shield 206, Prepping for photographer/tour | [9 empty] | heater runs; Q0's;
2018-02-21 | Wed | Cu HDIce unit; | 802 beamtubes; SNS | C75/Nb3Sn pair parts Calbrations C75 travelers |  |  |  | 1200C/3H clean-up; |  |  | Nb parts; | L2-253 & parts; L2 clamps, blanks & gaskets; Test stand down pipes x2; L2-304; Tube, flange & al Rod; |  |  | HPR1: OOC HPR2: L2-253; L2-305 |  | L2-305 w/new FP; |  | RDT-14; |  |  |  |  | D1: RRR test D2: C75 HOMs hold D3: D4: D5: D6: TD5 L/C/T D7: L2-250 C2K/T/W D8: BPM slowC/W x3 | C75- Prep for cavities, weld samples LCLSll PCM- Remove MC/WC's CM02- Remove HOM Mu caps, LC BLine CM04- Idle CM07- Testing CM09- Instrumentation, final torque CM10- Solder M.Lead, MLI, Instrumentation Other- Photographer/Tour | [7 empty] | 1L07 insulating vacuum weak; one C75 cavity restored; |  | magnet test; sheild temperature test;
2018-02-22 | Thu | Cu HDIce unit; |  | C75/Nb3Sn pair parts C75 travelers |  |  | L2-315 probe cal; | C75 HC (12) | C75-002 flanges; MB-003; |  | Nb samples x60; | L2-144; SS tube & flanges; L2-304 HW & parts; CERN-1; Cold ceramic FPC warmer x4; Spool & conflat; Cu plates, gears; |  | TC1N2, TC1TD1 setup; | HPR1: OOC HPR2: L2-304 L2-253 |  | L2-253 w/new FP |  |  |  |  | L2-252 HOMs & sensors; |  | D1: RRR C/T D2: C75 C/T D3: D4: RI-009 C/T/W D5: D6: D7: L2-250 warm; D8: BPM WDLC | C75- Prep for cavities, weld samples LCLSll PCM- Remove MC/WC's CM02- Remove HOM Mu caps, LC BLine CM04- Idle CM07- Testing CM09- Instrumentation, final torque CM10- Solder M.Lead, MLI, Instrumentation Other- | [7 empty] | both C75's restored; beam istability studies; |  | magnet test; warm up tomorrow?
2018-02-23 | Fri | RFD Damper | cleanup run BB | C75/Nb3Sn pair parts HOM Probes C75 travelers |  |  | L2-315 probe cal; | C75 HC (12) | C75-002 flanges; |  | Nb rod 50uM; Top mount fixture 5uM; | Clamps, blanks & gaskets; Nb cones x2; Valves x6; |  |  | HPR1: OOC HPR2: L2-144 L2-304; |  | L2-304 w/new FP; LSF5-1; |  | L2-253 L2-305 D5; L2-319 D5; |  |  | L2-254 HOMs & sensors; L2-250 input cable repair; |  | D1: RRR hold; D2: C75 warm/pull; D3: D4: RI-009 pull; D5: D6: D7: L2-250 pull, L2-252 load D8: BPMpull; IA-114 L/C/T/W | C75- Weld HV components LCLSll PCM- Remove MC/WC's CM02- Remove HOM Mu caps, to WS6 CM04- LC Bline, to WS5 CM07- Testing CM09- Instrumentation, mag shields CM10- Solder M.Lead, MLI, Instrumentation Other- | [7 empty] | 1L07 pumping IV; NL mismatch; |  | magnet troubleshooting;
2018-02-24 | Sat
2018-02-25 | Sun | [33 empty] | GDR four cavity run
2018-02-26 | Mon |  | Hall A columnator; | C75/Nb3Sn pair parts HOM Probes |  |  |  | C75 HC (12) | C75-002 flanges; |  | C75-002 parts; Nb wire; | MB-003 and HW; Valves x5; Al blanks x4; Al seals x9; Ceramic and Mo HW; 1 valve 8 flanges; |  | TC1N2, TC1TD1 50u; | HPR1: OOC HPR2: RDT14 L2-144; |  | L2-144; TS16-003 maint; |  | L2-304 D7/8; RDT14 | L2-319, L2-305, L2-253 D5; |  | L2-250 input cable repair; |  | D1: RRR hold D2: C75 hold D3: IA-320 L/SC4K (3) D4: BPM L/WDLC/SC/W cycle 1 (2) D5: D6: D7: L2-252 C2K/T/W (1) D8: IA-114 pull; L2-254 L/C4K (4) | C75- Weld HV components LCLSll PCM- Remove MC/WC's CM02- Remove HOM Mu caps CM04- LC Bline CM07- Testing CM09- Instrumentation, mag shields, rework tuner 7 CM10- Solder M.Lead, MLI, Instrumentation Other- | [7 empty] | Beam studies |  | magnet test; FE studies;
2018-02-27 | Tue |  | Hall A columnator; C75 | C75/Nb3Sn pair parts |  |  |  | C75 HC (12) |  |  |  | L2 BP ext and flanges; L2 split rings (x8); IA-110HW; L2 Cryo HW; |  | MB-003 setup | HPR1: OOC HPR2: TCIN2; IA-110; |  | TS16-003 maint; IA-114 dis; |  |  | L2-319, L2-305, L2-253 D5; L2-304; RDT14 |  | L2-319, L2-305, L2-253 D5 HOMs and sensors; L2-304 HOMs and sensors; | BPM | D1: RRR pull; D2: C75 pull D3: IA-320 C2K/T/W D4: BPM WDLC/SC cycle 2 D5: D6: RDT14 L/C/T D7: L2-252 warm D8: L2-254 C2K/T/W | C75- Weld HV components, clean parts LCLSll PCM- Remove MC/WC's/Instrumentation flanges CM04- LC B-line CM07- Testing CM09- Instrumentation, mag shields, RF Cables CM10- Solder M.Lead, MLI, Instrumentation, UCM torquing Other- CMNB3 1/4 in house | [7 empty] | Beam to 4 Halls with some time out for Beam Studies |  | Magnet test thwarted by PSS problem. SSG repair work complete (hopefully) PSS recert today Followed by magnet Test potential llrf work today or tomorrow
2018-02-28 | Wed |  | Hall A columnator; C75; | C75/Nb3Sn pair parts C75 CMM tooling HOM Probes |  |  |  |  | C75-002 flanges; |  | IA-114 Nitric flanges; Nb samples; Half cell x1; Anode flanges & rings x20; | IA-110 HW; RDT-2 HW; Cryp HW & Support; |  | MB-003 40e; | HPR1: OOC HPR2: IA-110 |  | IA-110 |  | L2-144 D7/8 TC1N2; L2 BP ext and flanges; |  |  | L2-319, L2-305, L2-253 D5 HOMs and sensors; |  | D1: RRR hold D2: D3: IA-320 warm D4: BPM SC/W/ cycle 2 D5: D6: RDT-14 warm D7: L2-252 pull; D8: L2-254 top off 2K/T/W; | C75- Weld HV components, clean parts LCLSll PCM- Remove MC/WC's/Instrumentation flanges CM04-To WS6 CM07- Testing CM09- Instrumentation, mag shields, RF Cables, torque hardware CM10- Stattion M.Leads, MLI, Instrumentation, UCM torqing , tuner pre-assy Other- LCLS Beam pipe pre assy | [7 empty] | 4 beam ops C75-2 turned off again |  | PSS recert completed Magnet Test completed -X corrector fails FE studies of 1, 2, 4, 6, 7, 8 - all cavities except 8 generate some level of FE.
2018-03-01 | Thu | Cu HDIce unit; | C75; | C75/Nb3Sn pair parts C75 CMM tooling L2 SC magnetic measurement (x3); HOM Probes |  |  |  |  | C75-002 flanges; |  | Field probes x5; Cu cavity 3GHz; Cu HC x1; Cu beam tubes x5; | Wire shelves x2; |  | MB-003 20u | HPR1: OOC HPR2: EIC1; |  | IA-320 pull from cage; IA-114 cage; |  | IA-110 D3/4; TestBPM; | TC1N2; L2-144; |  |  |  | D1: SIC L/C/T D2: D3: IA-320 pull D4: BPM WDLC/SC/W cycle 3 D5: L2-319, L2-305, L2-253 L D6: TC1N2 L/C D7: L2-250 L/C4K D8: L2-254 warm | C75- Weld HV components, clean parts LCLSll PCM- Remove MC/WC's/Instrumentation flanges CM04-To WS6 CM07- Testing CM09- Instrumentation, mag shields, RF Cables, torque hardware CM10- MLI, Instrumentation, UCM torqing , tuner pre-assy Other- LCLS Beam pipe pre assy | [7 empty] | 4 beam ops 1L23-6 bypassed |  | llrf work FE studies SSA investigation today Warm up ~Friday
2018-03-02 | Fri | C75 stiffeners; | C75; | C75-002 L2 Mag shielding C75 CMM tooling |  |  |  |  | Lapping machine heads; |  |  | IA-114 parts; Gate valves x2: Top hats x3: Mo hardware; Nb plates; Coupler flanges HW & valves; |  |  | HPR1: OOC HPR2: IA-114; MB-003; |  |  |  | EIC1 D7/8; | IA-110 |  | L2-144 HOMs and sensors; |  | U-tubes 2pm D1: SIC C/T D2: D3: D4: BPM WDLC/pull D5: L2-319, L2-305, L2-253 preC/W/C4K D6: TC1N2 C1.6K/T D7: L2-250 C2K/T/W D8: L2-254 pull; L2-144 load | C75- Weld HV components, clean parts LCLSll PCM- Remove MC/WC's/Instrumentation flanges CM04-To WS6 CM07- Testing CM09- Instrumentation, mag shields, RF Cables, torque hardware CM10- MLI, Instrumentation, UCM torqing , tuner pre-assy Other- LCLS Beam pipe pre assy | [7 empty] | 4 beam ops; Restricted access later? |  | Warm up in progress
2018-03-03 | Sat
2018-03-04 | Sun
2018-03-05 | Mon | CERN1-Cu2 | DL windows; C50 WW; | L2 Mag shielding L2 SC magnetic measurement (x3); C75 CMM tooling |  |  |  |  | LSF1-3 flanges; |  | C75-002 flange etch; | RDT-14 parts (PM); BPM fasteners; C75-002 and parts; SNS HW; SC-02 |  | RDT-14 setup; | HPR1: OOC HPR2: RDT-13; MB-003; RDT-2; |  | BPM fastener change test; MB-003; L2-304 dis; RDT-14 dis; |  |  | EIC1 failed |  | EIC1 FGM & Cernox; |  | D1: SIC C/T D2: D3: IA-110 L/C4K D4: D5: L2-319, L2-305, L2-253 C2K/T/W D6: TC1N2 C1.6K/T D7: L2-250 pull; D8: L2-144 L/C4K | C75- Weld HV components, Inspect WG's LCLSll PCM- Remove MC/WC's/Instrumentation flanges CM04-Remove MC/WC's CM07- Warmed up, LC Beamline CM08- Verify ucm hardware, Prep for BPM work CM09- RF Cables, torque hardware CM10- Instrumentation, UCM torqing , tuner pre-assy CMNB3- Prep for endcan wach's cutting Other- LCLS Beam pipe pre assy | [7 empty] | 4 Beam Ops 1L13 InsVac needs attention 2L09 off for reasons TBD |  | Warm up in progress U-tubes this morning
2018-03-06 | Tue | CERN1-Cu2 | DL windows; C50 WW; | L2 Mag shielding C75 CMM tooling |  |  | C100-1 tune FF & probe cal |  |  |  | LSF1-3 flange; | RTD-14; DP cam insert; C75-002 parts & HW; L2-304 Parts& HW; |  | RDT-14 10u; | HPR1: OOC HPR2: C75-002; L2-304 |  | BPM fastener change test; |  | MB-003 D7/8 (TS?); RDT-13; L2-SC RDT-2 D3/4; | L2-SC; |  |  |  | D1: SIC C/T D2: D3: IA-110 C2K/T/W D4: D5: L2-319, L2-305, L2-253 warm D6: TC1N2 C1.6K/T D7: D8: L2-144 C2K/T/W; | C75- Weld HV components, Inspect WG's LCLSll PCM- Remove instrumentation flanges, to WS6 CM04-Remove MC/WC's CM07- LC Beamline CM08- Prep for BPM work CM09- RF Cables, Heat stations CM10- Alignment CMNB3- Prep for endcan wach's cutting Other- | [7 empty] | Maint day SL 4K
2018-03-07 | Wed | tbd | DL windows; C50 WW; RFD Damper; | C75 HCs; US Larp HOM | CERN1-Cu2 |  | C100-1 tune FF & probe cal |  | C75 WW (x8); |  |  | RFD Damper; L2-314 wipedown; LSF5-1; Clamps, blanks & covers; |  |  | HPR1: OOC HPR2: C75-002; L2-304; LSF1-3; |  | C75-002; L2-304; BPM tests; |  | LSF1-3; | MB-003 leaked; RDT-13 leaked; RDT-2; |  | L2-SC sensors; |  | D1: SIC C/T D2: D3: IA-110 pull; D4: RI-009 L/C/W D5: L2-319, L2-305, L2-253 warm D6: TC1N2 C1.6K/T/W D7: SC-02 L/C D8: L2-144 warm | C75- Weld HV/WG components, Inspect WG's LCLSll PCM-to WS6 CM03- to WS5 CM04-Remove MC/WC's CM07- Prep for move CM08- Prep for BPM work CM09- Alignment verification, RF Cables CM10- Alignment CMNB3- Prep for endcan wach's cutting Other- No He in the Test Cave- KW on it | [7 empty] | SL 4K (maint day); RF recovery; |  | J1.3-07 warm/hold;
2018-03-08 | Thu | CERN1-Cu2 | DL windows; C50 WW; | C75 HCs; US Larp HOM C75 WGs |  |  | L2-242; |  | C75 WW (x8); |  | IA-110 nitric flanges; RFD Damper; | IA-110; L2-314 parts; RDT-13 HW; SNS gaskets; BPM tools; MB-003 HW; Twin HW; Vac. Hose; |  | LSF5-1 setup; | HPR1: OOC HPR2: L2-314; RDT-13; C75-002; |  |  |  | L2-304 D7/8; | MB-003; |  |  |  | D1: SIC C/T D2: D3: D4: RI-009 C/W D5:L2-319, L2-305, L2-253 hold; D6: LSF1-3 L/C/T; D7: SC-02 C2K/T/W D8: L2-144 pull; |  | CM09- Alignment verification, RF Cables CM10- Alignment | CM08- Prep for BPM work | CM03- at WS5 CM04-Remove MC/WC's | Weld HV/WG components, Inspect WG's | CMNB3- Prep for endcan wach's cutting |  |  |  |  | CM07- Prep for move, needs survey
2018-03-09 | Fri | CERN1-Cu2 | C50 WW; RFD Damper; | C75 HCs; C75 WGs; |  |  | L2-243; |  |  |  | IA-110 Flanges; 802 HC (x4) & BT (x2); Nb crucible; | IA-110 Flanges & HW; LSF5-1 Enthnol rinse; @ 3/4 conflats; Test stand parts; L2-314 parts; Cryo blanks valves, & HW; Cu gaskets; |  | LSF5-1 20u; | HPR1: OOC HPR2: IA-110; Twin-2; MB-003; |  | MB-003 dis |  | RDT-13 D6; C75-002 D7; | L2-304; |  |  |  | D1: SIC C/T D2: D3: RDT-2 L/C/T/W D4: RI-009 C/W D5: L2-319, L2-305, L2-253 W D6: D7: SC-02 warm D8: |  | CM09- Alignment verification, RF Cables CM10- Alignment | CM08- Prep for BPM work | CM03- at WS5 CM04-Remove MC/WC's | Weld HV/WG components, Inspect WG's | CMNB3- Prep for endcan wach's cutting
2018-03-10 | Sat
2018-03-11 | Sun
2018-03-12 | Mon | C75 stiff ring; | DL windows; C50 WW; RFD Damper; | L2-242; C75 WGs; | CERN1-Cu2; |  | L2-255; |  | IA-114 blanks; |  | 802 HC (x4) & BT (x2); | SC-04; L2 CM 4' Vac hose (x3); Faraday HC; L2 Warm ceramic cups (x8); IA-114; RDT-13; RDT-13 Flanges & HW; |  |  | HPR1: OOC HPR2: TC1TD1; MB-003; |  | MB-003; cage IA-114; |  | TWIN2 | RDT-13 (leaked); C75-002; |  | L2-304 HOMs and sensors; C75-002 temp & OST; |  | D1: SIC warm/pull; D2: D3: RDT-2 pull; D4: D5: L2-319, L2-305, L2-253 pull D6: D7: SC-02 pull; L2-304 L/C4K D8: |  | CM09- Alignment verification, RF Cables CM10- Alignment | CM08- Prep for BPM work | CM03- at WS5 CM04-Remove MC/WC's | Weld HV/WG components, Inspect WG's | CMNB3- Prep for endcan wach's cutting |  |  | inj beam studies 1L25 work
2018-03-13 | Tue | Faraday HC; | DL windows; C50 WW; RFD Damper; | C75 HCs; C75 WGs; |  |  | L2-322; |  |  |  | IA-114 blanks; | L2 CM valves (x4); CERN1-Cu2; Mold; IA-114 Parts & HW; RDT-13 HW; LCLS2 HW; |  |  | HPR1: OOC HPR2: RDT-13 IA-114; |  |  |  | MB-003; SC-04 D7; TC1TD1 D6; | TWIN2 | TWIN2 120C/24h; |  | L2-319; | Kinney pump maint D1: D2: D3: D4: D5: D6: D7: L2-304 C2K/T/W D8: C75-002 L/C4K |  | CM09- Alignment verification, RF Cables CM10- Alignment | CM08- Prep for BPM work | CM03- at WS5 CM04-Remove MC/WC's | Weld HV/WG components, Inspect WG's | CMNB3- Prep for endcan wach's cutting
2018-03-14 | Wed | SS weld; | DL windows; C50 WW; RFD Damper; | L2-242; L2-243; C75 HCs; | [6 empty] | 10 am flow hood cal DL parts; Nb bar 20u; | L2 CM flanges (x24); DL parts; L2CM Vacuum parts; Conflat blanks & threaded rod; L2 blanks, gaskets & clamps; CM blanks & tees; |  | 10 am flow hood cal | HPR1: OOC HPR2: L2-314; IA-114 |  | IA-114; J1.3-011 prep.; |  | RDT-13 | MB-003; SC-04; TC1TD1; | MB-003 120C/12h; TWIN2 120C/24h; |  | L2-305; | D1: D2: D3: D4: D5: D6: D7: L2-304 warm D8: C75-002 C1.8K/T/W4K |  | CM09- Alignment verification, RF Cables CM10- Tuners | CM08- Prep for BPM work | CM03- at WS5 CM04-Remove MC/WC's | Weld HV/WG components, Inspect WG's | CMNB3- Prep for endcan wach's cutting |  |  | Xfmr Install Continues NL RF Push Continues CHL1 Pumpdown Monday CEBAF Restore 3/21
2018-03-15 | Thu | clean-up | DL windows; C50 WW; RFD Damper; | C75 WG; C75 HCs; L2-242; |  |  | L2-151 | sample test sheet 900C/3h; |  |  |  | L2-252 wipe down; L2-243 ext rinse; L2 CM conflat tee (x7); RDT-14 hardware; L2-242 ext rinse; |  |  | HPR1: OOC HPR2: L2-314; L2-252; |  | L2-314 new FP; TS34 test stands; |  | IA-114 D3; | RDT-13; SC-04; | MB-003 120C/12h; | SC-04 sensors; TWIN2 sensors; | L2-253; | D1: D2: D3: TWIN2 L/C4K; D4: D5: D6: TC1TD1 L/C/T D7: L2-304 pull;SC-04 L/C (cycle) D8: C75-002 troubleshoot ?warm |  | CM09- Test fit lower shields CM10- Alignment verification, Tuners | CM08- Prep for BPM work | CM03- Beamline LC, Remove WC's CM04- Prep for move to WS6 CM05- Move to WS5 | Inspect WG's, Rework rotary feedthrus | CMNB3- Prep for endcan wach's cutting FL04- Demag supprt |  |  | xfmr Install Continues NL inj beam studies CHL1 Pumpdown Monday CEBAF Restore 3/21
2018-03-16 | Fri | maint | C50 WW; RFD Damper; | DL bodies C75 HCs; L2-255 Lapping blocks |  |  | L2-157 | sample test sheet 900C/3h; | RDT-2 Blanks |  | CERN 802 HC (x4); EIC5 end cells (x2); | IA-110; Al seals; L2 CM tee & HW; Tubing & fittings; String wipe down; |  |  | HPR1: OOC HPR2: IA-110 L2-252; |  | String 11 Rollout L2-252 new FP; Cage IA-110 |  | L2-314 D7/8; L2-242, L2-243, L2-255 D5; | IA-114; |  | IA-114 sensors; | L2-304; | D1: D2: D3: TWIN2 C2K/T/W D4: IA-114 L/SC D5: mag field map D6: TC1TD1 C/T/W D7: SC-04 C1.6K/T D8: C75-002 warm decon/C? | CM11- Delivery? | CM09- Test fit lower shields CM10- Alignment verification, Tuners | CM08- Prep for BPM work | CM03- Beamline LC, Remove WC's CM05- Remove Inst. Flanges | Inspect WG's, Rework rotary feedthrus | CMNB3- Prep for endcan wach's cutting FL04- Demag supprt
2018-03-17 | Sat
2018-03-18 | Sun
2018-03-19 | Mon | C75 DL | DL windows; RFD Damper; | L2-255 DL bodies; |  |  | J1.3-011; |  |  |  | Nb can & foil 10u (PD); | L2-319 ext rinse; L2-255 ext rinse; C50 Rotary FT x12; C75 WW (x10) SC-06 ext rinse; Al flanges; Blanks & HW; |  |  | HPR1: OOC HPR2: |  | EIC1 dis; IA-320 dis; |  | L2-252 D7/8; | L2-314; |  |  |  | D1: D2: D3: TWIN2 hold D4: IA-114 C2K/T/W D5: mag field map D6: TC1TD1 C/T/W D7: SC-04 pull; MB-003 L/C4K D8: C75-002 C4K; | CM11- Delivery? | CM09- Test fit lower shields CM10- Alignment verification, Tuners | CM08- Prep for BPM work | CM03- Beamline LC, Remove WC's CM05- Remove Inst. Flanges | Inspect WG's, Rework rotary feedthrus | CMNB3- Prep for endcan wach's cutting FL04- Demag supprt |  |  | pump down SL |  | pull junction box u-tube
2018-03-20 | Tue |  | RFD Damper; | C75 HCs; L2-322; RFD Damper; |  |  | L2-169; L2-168; | Nb sample 800C/3h (PD); |  |  | RDT-2 blanks; | L2-315; L2-319 parts; L2-315 parts; RDT-2 blanks; RDT-2 parts; Berry bolts and related HW; 1/4" tubing; Vac. Parts; |  | IA-320 setup; | HPR1: OOC HPR2: L2-319; IA-110 |  | IA110; |  | L2-242, L2-243, L2-255 D5; SC-06 D7; | L2-252; |  |  |  | D1: D2: D3: Twin-2 warm D4: IA-114 warm D5: D6: RDT-13 L/C D7: MB-003 C2K/T/W D8: C75-002 C1.8K/T/W | CM11-Alignment, magnet install | CM09- Verify Check List, Tune HOM's CM10- Tuners | CM08- Waiting for BPM Procedures | CM03-Remove WC's, Instrumentation flanges CM05- Move to WS5 | C75-Inspect WG's, Rework rotary feedthrus | LCLSII- Receive VV & UCM, Heat exchanger rework
2018-03-21 | Wed | C50 DL | RFD Damper; | C75 HCs; L2-157; |  |  | BPM FT | Nb sample 800C/3h (PD); | A1, A3 flanges; CERN Cu 1.3 CBP; |  | Nb blanks 5u (GE); CuNb3Sn Samples 15u (AMV) ; C50 flanges; DL bodies; | L2-305 ext rinse; L2-322 ext rinse; Mo bolts; IA-320; A1; A3; Coupler HW & valves; Cryo HW & fittings; Coupler Wipe down; |  | IA-320 25u; | HPR1: OOC HPR2: L2-319; |  | L2-319 new FP; |  | IA-110 D3/4 | SC-06 L2-242, L2-243, L2-255 D5; |  |  |  | D1: D2: D3: Twin-2 pull D4: IA-114 pull D5: D6: RDT-13 C2K/T/W D7: MB-003 warm D8: C75-002 warm | CM11-Alignment, magnet install | CM09- Verify Check List, Tune HOM's CM10- Tuners | CM08- Waiting for BPM Procedures | CM03-Remove WC's, Instrumentation flanges CM05- Move to WS5 | C75-Inspect WG's, Rework rotary feedthrus | LCLSII- Heat exchanger rework |  |  | RF recovery; |  | SSA testing;
2018-03-22 | Thu | C75 DL; | maint | C75 endgroups; RFD Damper L2-151; |  |  | BPM FT |  |  |  | IA-320 flanges nitric; C75 end group weld prep; | L2-157 ext rinse; SS Vav tubes x2; Threaded rod x4; L2 clamps Blanks & gaskets; Al seals; |  | A1, A3 setup; | HPR1: OOC HPR2: L2-315; RDT-2; |  |  |  | L2-319 D7/8; L2-322, L2-157, L2-151 D5; | SC-06; IA-110; L2-242, L2-243, L2-255 D5; |  | SC-06 sensors; L2-314 sensors & HOMs; IA-110 sensors; |  | D1: D2: D3: IA-110 L/SC4K D4: D5: mag field mapping D6: D7: MB-003 pull; SC-06 L/C4K D8: C75-002 pull; L2-314 L/C4K | CM11-Alignment, magnet install | CM09- Verify Check List, Tune HOM's CM10- Tuners | CM08- Waiting for BPM Procedures | CM03-Remove WC's, Instrumentation flanges CM05- Move to WS5 | C75-Inspect WG's, Rework rotary feedthrus | LCLSII- Heat exchanger rework
2018-03-23 | Fri | C75 DB; | ww; target mold test; | C75 endgroups; L2-151; L2-168; |  |  |  |  | CERN Cu 1.3 CBP; |  | A1 & A3 (BCP flanges) | L2-238 US test; L2-151 ext rinse; L2-305 Ext rinse; |  | A1, A3 20u; | HPR1: OOC HPR2: IA-320 L2-315; |  | L2-315 new FP; IA-114 dis; C75-002 dis; |  | RDT-2; L2-322, L2-157, L2-151 D5; | L2-319 |  | L2-242, L2-243, L2-255 D5 sensors & HOMs; |  | D1: D2: D3: IA-110 SC4K/T/W? D4: D5: L2-242, L2-243, L2-255 L/pre-cool; D6: RDT-13 hold; D7: SC-06 C2K/T D8: L2-314 C2K/T/W | CM11-2 phase welding, Ti sheet, magnet lead prep | CM09-Tune HOM's CM10-Set Tuners | CM08- Waiting for BPM Procedures | CM03-Remove WC's, Instrumentation flanges CM07- to WS5 | C75-Inspect WG's, Rework rotary feedthrus | LCLSII- Heat exchanger rework |  |  | RF recovery in progress Beam to 5C
2018-03-24 | Sat
2018-03-25 | Sun
2018-03-26 | Mon | C75 DL; | C75 DL; C75 WW; | L2-169; De-mag L2 valves C75 DL; | C75-002; |  |  | A1, A3 2N6; | CERN Cu 1.3 CBP; |  | A1, A3 flange BCP; A1, A3 outside BCP 10u; AMV grid; | L2-168 ext rinse; L2 Lollipops & tooling; BPM parts & HW; C75 WW; Berry bolts, etc.; flex hoses (x4); 2 3/4 conflat; 6" CF Blank; SS plates x3; SS Tube, Bake; |  |  | HPR1: OOC HPR2: RDT-14; L2-305 |  | string prep; RDT-13 dis; BPM dis; |  | L2-322, L2-157, L2-151 D5; | RDT-2; |  | L2-252 sensors & HOMs; L2-319 sensors & HOMs; |  | D1: D2: D3: IA-110 SC4K/T/W D4: D5: L2-242, L2-243, L2-255 W->120K/C4K D6: RDT-13 pull; D7: SC-06 pull; D8: L2-314 pull; L2-252 L | CM11-2 phase LC, magnet lead prep | CM09- Idle CM10-Set Tuners, MLI | CM08- Waiting for BPM Procedures | CM03-Remove WC's, Instrumentation flanges CM07- to WS5 | C75-Build WG Assy's, Rework rotary feedthrus | LCLSII- Heat exchanger rework
2018-03-27 | Tue | C75 DL; AMV grid; | C75 DL; C75 WW; | C75 DLs; L2 Mag shielding |  |  |  | A1, A3 2N6; | CERN Cu 1.3 CBP; |  | SCIB flanges nitric 30min; RFD Damper; | L2 Valves, flanges & HW; L2 Bellows; Pump drop parts; 4" spool & pop off; Fixture, flange & nut; |  |  | HPR1: OOC HPR2: L2-305 |  | L2-305; L2 tooling; Cage L2-145; |  | L2-315 D7/8; RDT-14; | L2-322, L2-157, L2-151 D5; |  |  | L2-314 | D1: D2: D3: IA-110 SC4K/T (2) D4: D5: L2-242, L2-243, L2-255 C2K/T/W (1) D6: RDT-2 L/C/T/W D7: L2-319 load D8: L2-252 C4K (3) | CM11-2 phase LC, MLI/Mag shields, magnet lead prep | CM09- Idle CM10- MLI, Heat Stations | CM08- Waiting for BPM Procedures | CM03-Remove WC's, Instrumentation flanges CM07- to WS5 | C75-Build WG Assy's, Rework rotary feedthrus | FNAL ON SITE ALL DAY TO DISCUSS FASTENERS. LCLSII- Heat exchanger rework
2018-03-28 | Wed | RFD Damper; C75 end groups | C75 DL; C75 WW; AMV cathode; HZB; | C75 DLs; L2 Mag shielding |  |  |  | A1, A3 2N6; |  |  | RFD Damper #2; A1 6u; Grid cap; Fasteners, holders, flanges & ceramics; Photo cathode wafer, (HF); Scrubber Test 3pm | L2 String Cages; L2-153 ext rinse; | Scrubber Test 3pm | Scrubber Test 3pm | HPR1: OOC HPR2: L2-145 HPR training; |  | C75 window test prep; BPM sub; |  | L2-305 D7/8; | RDT-14; L2-315; L2-322, L2-157, L2-151 D5; |  | L2-322, L2-157, L2-151 D5 HOMs and sensors; | L2-314 | D1: D2: RRR L/C4K D3: IA-110 T4K/W D4: D5: L2-242, L2-243, L2-255 warm D6: RDT-14 L/C/T D7: L2-319 C4K D8: L2-252 C2K/T/W | CM11-MLI/Mag shields | CM09- Instrumentation CM10- Heat Stations | CM08- Waiting for BPM Procedures | CM03-Remove WC's, Instrumentation flanges CM07- Remove Bayonet Box | C75-Build WG Assy's, Rework rotary feedthrus | LCLSII- Heat exchanger rework Receive VV/UCM Blue Crab FM flanges-Welding
2018-03-29 | Thu | RFD Damper #2 | C75 DL; C75 WW; Target Au; | C75 DLs; L2 Short bellows |  |  | AES006 FF and probes; |  |  |  | RDT-2 nitric flanges; AMV cathode weld prep; | L2-169 ext rinse; L2 Carts; L2-156; L2-152; LSF5-1; string cavities (x2) Bellows x2; |  |  | HPR1: OOC HPR2: A1 LSF5-1 |  | L2 Bellows prep; BPM sub; Cage cleaning; |  | C75 DL; |  |  | L2-315 HOMs and sensors; |  | D1: D2: RRR hold D3: IA-110 SC4K/C2K/T/W D4: D5: L2-242, L2-243, L2-255 pull; L2-322, L2-157, L2-151 L/Precool; D6: D7: L2-319 C2K/T/W D8: L2-252 warm | CM11-MLI/Mag shields | CM09- Instrumentation CM10- Heat Stations | CM08- Waiting for BPM Procedures | CM03-Remove Instrumentation flanges CM07- Remove Bayonet Box | C75-Build WG Assy's, Rework rotary feedthrus | LCLSII- Heat exchanger rework Gigi flanges-Welding
2018-03-30 | Fri | AMV cathode; | C75 DL; C75 WW; | C75 DLs; L2 Tuners (x6); |  |  | AES006 FF and probes; |  | CERN Cu 1.3 CBP; |  | Nb plates; | L2-169; Nb plates; Berry bolts & HW; |  |  | HPR1: OOC HPR2: RDT-2 SCIB |  | L2 Bellows prep; BPM sub; L2-238 dis; |  | L2-168, L2-169 L2-305 D5; | C75 DL; |  | L2-315 HOMs and sensors; | L2-242; L2-243; | D1: D2: RRR W/T D3: IA-110 warm D4: D5: L2-322, L2-157, L2-151 warm/C4K D6: D7: L2-319 warm D8: L2-252 pull; |  | CM09- Instrumentation CM10- Heat Stations waiting on parts | CM08- Waiting for BPM Procedures | CM03-Remove Instrumentation flanges CM07- Need decision on BP config | C75-Build WG Assy's, Rework rotary feedthrus | LCLSII- Heat exchanger rework FM flanges-Welding
2018-03-31 | Sat
2018-04-01 | Sun | [13 empty] | HPR1: OOC HPR2:
2018-04-02 | Mon | AMV grid; RFD Damper #1; | C75 DL; C75 WW; | C75 DLs; L2 Short bellows; | [6 empty] | Vac parts; Split rings x17; | L2-165; L2-166; L2-299 ext wipe; |  | End Group replacment | HPR1: OOC HPR2: L2-299 (pm) |  | Cage L2-299; |  | L2-168, L2-169, L2-305 D5; | BPM J1.3-12 |  |  | L2-252; | D1: D2: RRR C/T/W; D3: IA-110 pull; LSF5-1 L/C/T D4: D5: L2-322, L2-157, L2-151 C2K/T D6: D7: L2-319 pull; D8: L2-315 L/C4K | CM11- Ready for WS3 | CM09- Instrumentation CM10- Heat Stations, Repair magnet heater wires | CM08- Waiting for BPM Procedures | CM03-In storage CM05- At WS5, begin gas guard retrofit CM07- Need decision on BP config | C75-Build WG Assy's, Rework rotary feedthrus | LCLSII- Heat exchanger rework FM flanges-Welding |  |  | Beam studies |  | R&K SSA work
2018-04-03 | Tue | RFD Damper #2 | C75 DL; C75 WW; HZB | C75 DLs; L2 Tuners; BPM FT's |  |  | AES006 FF and probes; |  |  | Nb samples; | Nb samples; | L2 string HW; L2 nut plates; L2-155 L2-254 L2-278 L2-252 ext rinse; |  | Acid change; | HPR1: OOC HPR2: recovery cleanup |  | L2-299; Cage L2-252; IA-110 dis; |  |  | L2-168, L2-169, L2-305; |  | SC06 | L2-319; | CTF Down AM D1: D2: RRR W/T D3: LSF5-1 hold D4: D5: L2-322, L2-157, L2-151 (D5-->D8) warm; D6: D7: D8: L2-315 C2K/T/W | CM11- Ready for WS3 | CM09- Instrumentation CM10- Heat Stationing hardware | CM08- Waiting for BPM Procedures | CM05- gas guard retrofit CM07- Need decision on BP config, measure magnet | C75-Build WG Assy's, Rework rotary feedthrus | LCLSII- Heat exchanger rework FM flanges-Welding RFD Damper #1 LC |  |  | RF Recovery |  | R&K SSA work
2018-04-04 | Wed | C75 end groups; | C75 DL; C75 WW; | C75 HCs; L2 Tuners; RFD Damper #2; RFD Damper #1; |  |  | C75 WW; |  |  |  | IA-110 nitric flanges; IA-114 nitric flanges; Nb flanges | L2 HW; L2 bellows x4; |  |  | HPR1: OOC HPR2: L2-299 |  | String prep, bellows, vlv ass'y, Mag chk |  |  |  |  | L2-168, L2-169, L2-305 HOMs & sensors; | L2-255; | D1: C75 DL L/C/T D2: RRR hold D3: LSF5-1 C/T/W? D4: D5: L2-322, L2-157, L2-151 pull; L2-168, L2-169, L2-305 L D6: A1 L/C1.6K/T/W D7: SC-06 L/Thermal Cycle D8: L2-315 warm (Cables) | CM11- Ready for WS3 | CM09- Instrumentation CM10- RF cable installation | CM08- Waiting for BPM Procedures | CM05- gas guard retrofit CM07- Reconfigure Beam Pipe | C75-Build WG Assy's, Rework rotary feedthrus | LCLSII- Heat exchanger rework FM flanges-Welding RFD Damper #1 LC RFD Damper #2 LC RFD Damper #1 Tig |  |  | RF Recovery |  | R&K SSA work
2018-04-05 | Thu | C75 end groups; | C75 DL; C75 WW; Target Au; | C75 HCs; L2 Tuners; C75 end groups; |  |  | C75 WW; |  | SS Plate; |  | Crucible mesh cover; Nb support plate; | IA-114; IA-110; HOM FP fasteners x2; |  |  | HPR1: OOC HPR2:L2-252; L2-299 |  | String prep, bellows, vlv ass'y, Mag chk L2-299 D7/8 | [6 empty] | UITF Cooldown D1: C75 C/T/W D2: RRR pull D3: LSF5-1 C/T D4: D5: L2-168, L2-169, L2-305 Pull/L/C4K; D6: RDT-14 L/C D7: SC-06 P/L/Thermal Cycle D8: L2-315 Warm | CM11- Ready for WS3 | CM09- Instrumentation CM10- RF cable installation | CM08- Waiting for BPM Procedures | CM05- Leak check; F Cup install CM07- Reconfigure Beam Pipe | C75-Build WG Assy's, Rework rotary feedthrus | QCM cooldown LCLSII- Heat exchanger rework RFD Damper #1 LC RFD Damper #2 LC RFD Damper #1 TigRFD |  |  | 1L27A? Vlv? |  | R&K SSA work
2018-04-06 | Fri |  | C75 DL; C75 WW; Target Au; | L2 Tuners |  |  |  | Nb samples 3942, 3706 800C/3h |  |  | Nb samples 3942, 3706 20u BCP; Nb sample 100u; Nb blanks GE 10u BCP; RFD Damper; | L2-319 ext rinse; SC-IB parts; Vac elbows X2; Anodized lollipop parts & HW; RFD Damper; |  |  | HPR1: OOC HPR2: SCIB L2-252 IA-114; |  | L2-252 |  | SCIB on TS16-003; L2-299 D7/8 |  |  |  |  | D1: C75 Pull D2: D3: LSF5-1 T/W D4: D5: L2-168, L2-169, L2-305 C2K/T/W D6: RDT-14 C4K/T /W? D7: SC-06 P/L/Thermal Cycle D8: L2-315 Pull | CM11- Ready for WS3 | CM09- Instrumentation CM10- RF cable installation | CM08- Waiting for restart | CM05- Leak check; F Cup install CM07- Reconfigure Beam Pipe | C75-Build WG Assy's, Rework rotary feedthrus | QCM cooldown LCLSII- Heat exchanger rework RFD Damper #1 LC RFD Damper #2 LC RFD Damper #1 TigRFD |  |  | 2L21 LCW leak |  | R&K SSA work
2018-04-07 | Sat | [17 empty] | L2-252 D7/8; | [15 empty] | R&K SSA work
2018-04-08 | Sun | [13 empty] | HPR1: OOC HPR2: L2-254; L2-278; | [19 empty] | R&K SSA work
2018-04-09 | Mon | HDIce Cu target; | C75 DL; C75 WW; AU Target; | C75 Half Cells; |  |  | L2-245 |  |  | RFD Damper#1 | RFD Damper 50u BCP; L2 flanges BCP & nitric; Anode Grid 5u; L2 flanges x3 | Anode and Cathode AMV; Bellows & elbows; C50 HW; L2 flanges x3; LSF5-1 HW, flanges; |  |  | HPR1: OOC HPR2: L2-156; L2-155; LSF5-1; |  | L2-1, L2-2 to rail; SC-06 Remove; |  | Check on EIC HW | L2-252; L2-299 |  |  |  | RF Maintenance (green rm) D1: D2: D3: LSF5-1 Pull D4: D5: L2-168, L2-169, L2-305 pull D6: RDT-14 pull; D7: SC-06 Pull D8: | CM11- Ready for WS3 | CM09- UCM Fasteners CM10- UCM Fasteners | CM08- Waiting for restart | CM05- Leak check; F Cup install CM07- Reconfigure Beam Pipe, prep shipping | C75-Build WG Assy's, Rework rotary feedthrus | QCM pumpdown 2k LCLSII- Heat exchanger rework RFD Damper #1 LC RFD Damper #2 LC RFD Damper #1 TigRFD ???? |  |  | 4-hall beam operations; |  | R&K SSA work
2018-04-10 | Tue | Anode Grid Repair | C75 DL; C75 WW; HZB; AU Target; | L2 Long bellows; L2-245; C75 Half Cells; |  |  | L2-245 3 GHz; |  | HZB |  | HZB parts;VSR HOM load parts & braze weights; Safety Shower test 3:30; | VSR HOM load parts & braze weights; Bellows tubes x5; | Twin-1 Set-up; Safety Shower test 3:30; | Safety Shower test 3:30; | HPR1: OOC HPR2: L2-165; L2-166; |  | L2-3, L2-4 to rail; |  | LSF5-1;(am) | LSF5-1;(pm) |  | L2-299 HOMs & sensors; L2-252 HOMs & sensors; |  | D1: D2: D3: D4: D5: D6: SC-IB L/SC/C4K/T/Hold D7: L2-299 L/C2K D8: L2-252 L/C4K | CM11- Ready for WS3 | CM09- UCM Fasteners CM10- UCM Fasteners | CM08- Waiting for restart | CM05- Leak check; F Cup install CM07- Reconfigure Beam Pipe, prep shipping | C75-Build WG Assy's, Rework rotary feedthrus | QCM pumpdown 2k LCLSII- Heat exchanger rework RFD Damper #1 LC RFD Damper #2 LC RFD Damper #1 TigRFD ???? |  |  | 4-hall beam operations; |  | R&K SSA work
2018-04-11 | Wed | Maint | C75 DL; C75 WW; HZB; | L2 Long Bellows; C75 Half Cells; |  |  |  | NbTi Flanges 800C/1h; |  |  | Nb samples #3942, #3706; HZB Cooling plates; C50 parts: | 3/8' flex hose x7; VAT valves x6; Mo parts; Bellows, conflats & HW; Small RA valve; NW 78 for string; L2 blanks, gaskets & align tool; | Twin-1 100u | HF spike RDT-6, TD5 setup; | HPR1: OOC HPR2: L2-153; L2-152; |  | L2-5, L2-6 to rail; |  |  |  |  | LCLSII mag Shield; TestL2 FT's |  | D1: D2: D3: LSF5-1 L/C2K/T D4: D5: D6: SC-IB C/C2K/T/W/SC4K D7: L2-299 C2K/T/W D8: L2-252 C2K/T/W Prod2 RF test | CM11- Ready for WS3 | CM09- UCM Fasteners CM10- UCM Fasteners | CM08- Waiting for restart | CM05- Close up valve port and bag openings CM07- S&A, Magnet check, prep shipping | C75-Build WG Assy's, Rework rotary feedthrus | F100 move LCLSII- Heat exchanger rework RFD Damper #1 LC RFD Damper #2 LC RFD Damper #1 TigRFD ???? |  |  | 4-hall beam operations; |  | R&K SSA work, Testing
2018-04-12 | Thu | Maint | C75 DL; C75 WW; HZB; | L2-246; |  |  | C75 CW (1); | NbTi Flanges 800C/1h; Twin-1 800C 3hrs; |  |  |  | RFD Damper#1 L2-245 ext rinse; Studs & HW; SS cavity parts; SS spool x3; Conflat flanges x3; 1.5" bellows; |  | RDT-6, TD5 30u; | HPR1: OOC HPR2: RDT-2; |  | L2-7, L2-8 to rail | [6 empty] | D1: D2: L2 FT L/C/W D3: LSF5-1 warm D4: D5: D6: SCIB 2K/T/W D7: L2-299 Warm D8: L2-252 Warm | CM11- Ready for WS3 | CM09- UCM Fasteners CM10- UCM Fasteners | CM08- Waiting for restart | CM05- Close up valve port and bag openings CM07- S&A, Magnet check, prep shipping | C75-Build WG Assy's, Rework rotary feedthrus | J1.3-05 move LCLSII- Heat exchanger rework RFD Damper #1 LC RFD Damper #2 LC RFD Damper #1 TigRFD ???? |  |  | 4-hall beam operations; |  | R&K SSA work, Testing
2018-04-13 | Fri | Hall A; | C75 DL; C75 WW; HZB; SS Degas | L2 Long Bellows; C75 Half Cells; C75 End Groups; |  |  | C75 CW (1); L2-238 FF (2); L2-246 incoming (3); | Twin-1 800C 3hrs |  |  | NbTi Flanges flash;RFD Damper #2; | Cathode Assy parts (amv); L2-246 ext rinse; |  | RDTTD-01/ RDL-02 setup; | HPR1: OOC HPR2: EIC-1 (1) |  | EIC-1 setup; LSF5-1 dis; |  | L2-245, L2-169, L2-246 D5; RDT-2 Cathode Assy |  |  | L2-299 measure warm Qext2, replace FP cable; | L2-151 fast bleed; L2-305 | D1: D2: D3: LSF5-1 W/P D4: D5: D6: RDT-14 L/C1.8K/T D7: L2-299 Pull; LCLSII Shield Test L/SC4K/W D8: L2-252 warm | CM11- Ready for WS3 | CM09- UCM Fasteners CM10- UCM Fasteners | CM08- Waiting for restart | CM07- Magnet checkout, Beampipe work, prep shipping | C75-Build WG Assy's, Rework rotary feedthrus | LCLSII- Heat exchanger rework |  |  | 4-hall beam operations;
2018-04-14 | Sat | [10 empty] | L2-238;
2018-04-15 | Sun
2018-04-16 | Mon |  | C75 DL; C75 WW; HZB; | C75 FPC BT (x2); L2-247; L2 Bellows; |  |  | SC-04 probe cal; | RDT-6 900 3hr |  |  |  | L2-151 ext rinse; L2-238 HW and HOM blanks; HZB HOM ceramics (x18); Cathode parts; SC-04; SC-04 HW; RDTTD-01/ RDL-02; |  | RDTTD-01/ RDL-02 30u; | HPR1: OOC HPR2: TD-5 L2-238 |  | TS28-011 maint; Cage 151; |  | L2-245, L2-169, L2-246 D5; EIC-1 D3/4; | J1.3-012 bag |  |  |  | D1: D2: L2-FT hold D3: D4: D5: D6: RDT-2 L/SlowC4K C2K/W D7: LCLSII Shield Test pull; D8: L2-252 pull; | CM11- Fastener rework | CM09- Fasteners Rework CM10- Fasteners Rework | CM08- Waiting for restart | CM07- Magnet flange repair, Beampipe work, prep shipping | C75-Build WG Assy's, Rework rotary feedthrus | LCLSII- Heat exchanger leak check |  |  | 4-hall beam operations; 2L-23 misbehavior; Beam studies;
2018-04-17 | Tue |  | C75 DL; C75 WW; HZB | C75 FPC BT (x2); L2-251; L2 Bellows; |  |  | L2-247; | RFD Damper 1 600C/10h; |  |  | C75 FPC BT (x2); C75 EG (x2); RRR samples (BR); Nb disks 2" (8); Nb flange; Nb tubes (2); EIC5 weld prep; | TS28-011 bellows; RFD damper 1 He jacket; L2-305 ext rinse; SC-04; 3G Cu SC; HZB cooling plate; C75 EG x2; C75 BT x2; |  | IA-110 setup; | HPR1: OOC HPR2: L2-151; SC-04; L2-238; |  | L2-238 (blank HOMs) |  | L2-245, L2-169, L2-246 D5; | J1.3-012; EIC-1; L2-245, L2-169, L2-246 D5; |  |  | L2-168 | D1: D2: L2-FT pull; D3: D4: D5: D6: RDT-2 W D7: D8: | CM11- Fastener rework | CM09- Fasteners Rework CM10- Fasteners Rework | CM08- Waiting for restart | CM07- Magnet flange repair, Beampipe work, prep shipping | C75-Build WG Assy's, Rework rotary feedthrus | LCLSII- Heat exchanger leak check |  |  | 4-hall beam operations; RF recovery;
2018-04-18 | Wed | C75CW; | C75 DL; C75 WW; HZB; | BLA (x3); PcM Bellows (x3); C75 Center Stiffening rings |  |  | L2-251; IA-320 FF; | RFD Damper 1 600C/10h; | HW Coax BP; |  | C75 CW (13); C75 Half Cells (x4); | PrCM bellows (x14); L2-305 parts; L2-247 Ext rinse; L2-251 Ext Rinse; L2 flange & 2 bellows; L2-315 Ext rinse; |  | IA-110 25u; | HPR1: OOC HPR2: L2-305; L2-151; |  | L2-151 |  | L2-238 D7/8; SC-04 D6; |  |  | L2-245, L2-169, L2-246 HOMs and sensors and repair FP cable #2; |  | D1: D2: RRR L/C D3: EIC-1 L/C4K D4: D5: D6: RDT-2 SC D7: D8: | CM11- Fastener rework | CM09- Fasteners Rework CM10- Fasteners Rework | CM08- Waiting for restart | CM07- Magnet flange repair, Beampipe work, prep shipping | C75-Build WG Assy's, Rework rotary feedthrus | LCLSII- Heat exchanger leak check |  |  | 4-hall beam operations;
2018-04-19 | Thu | C75 DB (x2); C75 DL; | C75 DL; C75 WW; HZB; | BLA (x3); C75 DL |  |  |  | Elnik Testing; | IA-110 flanges; HW Coax BP; |  | C75 Half Cells (x4); | RFD1 HW; L2 BPM HW; Vac Elbow; Fasteners and HW; |  |  | HPR1: OOC HPR2: RFD2; L2-305; |  | L2-305 |  | L2-247, L2-251, L2-151 D5; | L2-238; SC-04; |  | SC-04 sensors; TS28-007 repair FP cable; L2-245, L2-169, L2-246 repair FP cable #2; |  | D1: D2: RRR W/T D3: EIC-1 C2K/T/W D4: D5: L2-245, L2-169, L2-246 L/precool; D6: RDT-2 T/W D7: D8: | CM11- Fastener rework | CM09- Fasteners Rework CM10- Fasteners Rework | CM08- Waiting for restart | CM07- Magnet flange repair, Beampipe work, prep shipping | C75-Build WG Assy's, Rework rotary feedthrus | LCLSII- Heat exchanger leak check |  |  | 4-hall beam operations;
2018-04-20 | Fri | C75 DL; C75 FPC & EG (x2); | C75 DL; C75 WW; | BLA (x3); L2 VV-24; |  |  | IA-114 FF & freq; | Elnik Testing; | IA-110 flanges; HW Coax BP; |  | C75 DL; C75 Stiff rings x16; | HW Coax; 2 3/4 Conflat flanges x3; String rail; C75 DL; |  |  | HPR1: OOC HPR2: |  |  | L2-272; | L2-305 D7/8; L2-325 D7/8; | L2-247, L2-251, L2-151 D5; |  |  |  | D1: D2: RRR pull D3: EIC-1 warm; D4: D5: L2-245, L2-169, L2-246 C4K D6: RDT-2 Pull, (5mG) SC-04 L/C2K/T/W D7: L2-238 L/C4K; D8: | CM11- Fastener rework CM12 - Roll out on East rail | CM09- Fasteners Rework CM10- Fasteners Rework | CM08- Vent beamline to N2 | CM07- Beampipe work, prep shipping | C75-Build WG Assy's, Rework rotary feedthrus | LCLSII- Heat exchanger leak check
2018-04-21 | Sat
2018-04-22 | Sun
2018-04-23 | Mon | C75 DB (x2); C75 DL; | C75 DL; C75 WW; HZB; | C75 HOM EG (x2); C75 FPC EG (x2); L2 Unplated bellows; |  |  | SC-04 probe cals; |  | BLA flanges (x2); IA-110 flanges; | RFD Damper 1; | RFD Damper 1; | RFD Damper 1; L2-272 methanol wipe in ClnRm; MS Cu test; Coupler brackets; RDT-2; RDT-2 HW; |  |  | HPR1: OOC HPR2: L2-272; RDT-2 |  | BPM HW swap J1.3-08; |  |  | L2-305 leaked; L2-325; | EIC-1 120C/12h; | L2-247, L2-251, L2-151 D5 HOMs & Sensors; | L2-286; SC-04 fast; L2-261 pass out to chem techs; | D1: D2: D3: EIC-1 pull; D4: D5: L2-245, L2-169, L2-246 C2K D6: SC-04 pull; 3GHz L/C/T/W D7: L2-238 C2K/T/W D8: | CM11- Fastener rework CM12 - Roll out on East rail | CM09- Fasteners Rework CM10- Fasteners Rework | CM08- Vent beamline to N2; BPM HW swap; | CM07- Beampipe work, prep shipping | C75-Build WG Assy's, Rework rotary feedthrus | LCLSII- Heat exchanger leak check |  |  | 4-hall ops;
2018-04-24 | Tue | C75 DB (x2); C75 DL; | C75 DL; C75 WW; HZB; | C75 HOM EG (x2); C75 FPC EG (x2); L2 Unplated bellows; |  |  | J1.3-12 As Delivered |  | IA-110 flanges; IA-114 flanges; BLA flanges?; L2-261 FP flange; SC-04 Flanges; |  | C75 Half Cells (x4); SCIB 15u; IA-110 flange Nitric, BCP, HF; SS bodies; CW eyelets; Cu peg boards; | IA-110 degrease; SC-04 & HW; L2 plated bellows (x14); SCIB; C75 HC; HW Coax; SS ice cube trays; FPC cold bellows Restraints; HW Coax; Turnbuckles x2; L2-286 ext rinse; |  |  | HPR1: OOC HPR2: SC-04; L2-272; |  | L2-272 new FP; | L2-286; SC-04 dis & flange inspection; | RDT-2 TS28-004; |  | EIC-1 120C/12h; | L2-325 HOMs & sensors; |  | D1: D2: RRR L/C D3: D4: D5: L2-245, L2-169, L2-246 T/W; D6: 3GHz T/W D7: L2-238 warm D8: L2-325 L/C4K | CM12- Alignment, magnet install, 2 phase piping | CM09- Fasteners Rework CM10- Fasteners Rework | CM08- LC connection, slow pump cavity string, HOM verification tomorrow? | CM07- FNAL on site, Prep for shipping, Shipping frame in TL after lunch | C75-Build WG Assy's, Rework rotary feedthrus | LCLSII- Heat exchanger leak check/PT FL04- Install WG's |  |  | 4-hall ops; RF Recovery;
2018-04-25 | Wed | C75 DB (x2); C75 DL; | C75 DL; C75 WW; HZB; | L2 Probes; C75 HC; C75 WW; |  |  | J1.3-12 As Delivered |  | IA-114 flanges; |  |  | L2-261 ext methanol wipe; L2-261 HW; L2 parts; C75 HC; L2-286 HW; IA-110 blanks SS Rotary FT; Vented bolts; Al gaskets; L2 flanges; CRN-5 polish; |  |  | HPR1: OOC HPR2: L2-286; IA-110; |  | TS28-011 Down-tube |  | L2-272 D7/8; SC-04 D6; | RDT-2; SC-04; |  | RDT-2 sensors; EIC-1 level sensor; |  | D1: D2: RRR W/T D3: RDT-2 SC4K D4: EIC-1 Load D5: L2-245, L2-169, L2-246 warm D6: TD-5 L/C/T/W D7: L2-238 pull; D8: L2-325 C2K/T/W; | CM12- 2 phase piping, RF Measurements | CM09- Fasteners Rework, setup for BPM work CM10- Fasteners Rework | CM08- Leak Check BPM repair, HOM verification | CM07- FNAL on site, Prep for shipping, Shipping frame in TL | C75-Build WG Assy's, Rework rotary feedthrus | LCLSII- Heat exchanger leak check/PT
2018-04-26 | Thu | C75 DB (x2); C75 DL; | C75 DL; C75 WW; HZB; | L2 Probes; C75 HC; C75 WW: |  |  |  | Bleed up furnace for upgrade review | IA-114 flanges; |  | Anode Grid /cage & flange; | IA-114; L2-305 wipe & bolt holes; RDTTD-1; L2-238 & HW; L2 valves & flanges; L2-305 Wipe; 4' flex hoses x3; Flanges w/bellows x4; L2-238 parts; Anode Grid \cage & flange; Test stand tees x3; |  |  | HPR1: OOC HPR2: L2-261; L2-286; |  | L2-286 new FP; | L2-238 L2-305 |  | L2-272; |  |  | L2-238 fast; | D1: D2: RRR warm D3: RDT-2 C2K/T/W (1) D4: EIC-1 C4K D5: L2-245, L2-169, L2-246 pull; D6: (5mG) SC-04 L/C1.5K/T/W; (2) D7: D8: L2-325 warm; | CM12- 2 phase piping/LC | CM09- Fastener Rework, setup for BPM work, Install magnet anti roll CM10- Fasteners Rework, magnet anti-roll | CM08- Re-tune HOM's, Remove pump cart, install magnet anti-roll | CM07- Install ship caps, pressurize ins vac, RF measurements | C75-Build WG Assy's, Rework rotary feedthrus | LCLSII- Heat exchanger leak check/PT
2018-04-27 | Fri | C75 DB (x2); C75 DL; | C75 DL; C75 WW; HZB; | L2 Tuners ; L2 VV-24; | [7 empty] | L2 plated bellows (x14); RDTTD-1 parts; RFD2 wipedown; L2-238 HW; L2-261 HW; |  | IA-114 setup | HPR1: OOC HPR2: L2-305 L2-261; |  | L2-261 new FP; TS34-003; |  | L2-286 (pump cart); |  |  | L2-272 HOMs & sensors; SC04 tighten all bolts; |  | D1: D2: RRR pull; Hall Probe Cal L D3: RDT-2 warm D4: EIC-1 C2K/T/W D5: L2-247, L2-251, L2-151 precool/W/C4K D6: SC04 pull; (20mG) SC-04 L/C1.5K/T/W D7: D8: L2-325 pull; L2-272 load | CM12- 2 phase piping/LC | CM09- Fastener Rework, setup for BPM work, Install magnet anti roll CM10- Fasteners Rework, magnet anti-roll | CM08- Remove pump cart, install magnet anti-roll | CM07- Install ship caps, pressurize ins vac, RF measurements | C75-Build WG Assy's, Rework rotary feedthrus | LCLSII- Heat exchanger leak check/PT
2018-04-28 | Sat
2018-04-29 | Sun
2018-04-30 | Mon |  | 1200C clean; C75 WW | L2 HOMs; L2 FPs; C75 FPC EG |  |  | L2-053; L2-059; |  |  |  | Anode grid BCP; Cathode Qtip; Nb covers; | L2-245 ext rinse; IA-110; Anode grid; Cathode; SCIB; Field probes x2; Vac HW; IA-110; IA-110HW; L2 bellows x3; |  | IA-114 hold; EP repairs; | HPR1: OOC HPR2: L2-238; L2-305; |  | L2-305; | L2-246, remove PICs (reuse L2-246 FP); | L2-286, L2-261 D5; L2-245 new FP D7/8; RFD2; |  |  |  | L2-246; L2-245; L2-169; L2-304; | D1: Hall Probe Cal C2K/T D2: D3: RDT-2 pull D4: EIC-1 pull; D5: L2-247, L2-251, L2-151 C2K/T/W D6: D7: D8: L2-272 C4K; | CM12- LC 2 Phase piping | CM09- Fastener Rework, Install magnet anti roll, Alignment check CM10- Fasteners Rework, magnet anti-roll | CM08- Instrumentation, Into VV | CM07- Install ship caps, pressurize ins vac, RF measurements | C75-Build WG Assy's, Rework rotary feedthrus | LCLSII- Heat exchanger leak check
2018-05-01 | Tue | C75 DB; C75 DL; Anode grid; | L2 Plated Bellows (x7); | L2 HOMs; L2 FPs; C75 FPC EG |  |  |  |  | CERN Cu CBP; H1 BL flanges; |  | Nitric; SCIB 15u; IA-110 Parts; Mo pucks x4; | L2-053 HW; HZB parts; |  |  | HPR1: OOC HPR2: RDL-02; L2-238; |  | TS28-00x rebuild; L2-238; Deposition system; |  | L2-245 D7/8; L2-261, L2-286, L2-305 D5; | RFD2; |  |  | L2-325; | D1: Hall Probe Cal C4K/W D2: C100 FT D3: D4: D5: L2-247, L2-251, L2-151 warm; D6: D7: D8: L2-272 C2K/T/W | CM12- LC 2 Phase piping | CM09- Fastener Rework, Bleed up beam line for BPM rework CM10- Fasteners Rework | CM08- Into VV, alignment | CM07- Alignment crew repeat shipping measurements, data from slap sticks | C75-Build WG Assy's, Rework rotary feedthrus | LCLSII- Heat exchanger leak check |  |  | 4 halls beam
2018-05-02 | Wed | C75 DL | L2 Plated Bellows (x7); | C75 Dumbbell; C75 WG Ext |  |  |  |  | CERN Cu CBP; |  | H1 BL flanges BCP; RDT-2 50u; | L2-059 HW; |  | IA-114 setup | HPR1: OOC HPR2: RDTTD-1; |  | Deposition system; |  | J1.3-09 BPM HW replacement; L2-238 cart; RDL-02; | RDL-02; RFD2; | RFD2 120C/12h; |  |  | D1: Hall Probe pull D2: C100 FT D3: D4: D5: L2-247, L2-251, L2-151 pull; D6: D7: D8: L2-272 warm; | CM12- LC 2 Phase piping | CM09- Fastener Rework, BPM rework-pumpdown CM10- Fasteners Rework | CM08- Into VV, alignment | CM07- Alignment crew repeat shipping measurements | C75-Build WG Assy's, Rework rotary feedthrus | LCLSII- Heat exchanger leak check CM06- Prep HV's for cleannroom |  |  | RF Recovery
2018-05-03 | Thu | C75 |  | C75 Half cells C75 Dumbbell; L2 Unplated bellows |  |  |  |  | CERN Cu CBP; |  | RDT-2, nitric & BCP flanges; | IA-114; |  | IA-114 25u | HPR1: OOC HPR2: |  | cage DQW2; |  | RDTTD-1 D6; | L2-238 cart; RDTTD-1 | RFD2 120C/12h; | L2-245 sensors & HOMs; |  | D1: D2: C100 FT pull; D3: D4: D5: D6: RDL-02 L/C/T D7: L2-245 L/C4K; D8: L2-272 hold; | CM12- Install MLI, Mu shields | CM09- Fastener Rework, Beamline pumpdown/LC CM10- Fasteners Rework, prep for BPM work | CM08- Alignment | CM07- Alignment, Repair List | C75-Build WG Assy's, Rework rotary feedthrus | LCLSII- Heat exchanger leak check
2018-05-04 | Fri | C75; DB&DL HD ice (Sandorfi) |  | L2 Unplated bellows |  |  | H1 probe cal; | PD samples 800C/3h; | CERN Cu CBP; |  | IA-114 flange BCP, HF; PD samples BCP; | DQW2; |  | IA-110 setup; | HPR1: OOC HPR2: DQW2 |  |  | TS28-003; |  | L2-261, L2-286, L2-305 D5; | RFD2 120C/12h; | RFD2 sensors; | L2-151; | D1: Hall Probe Cal L/C2K/T D2: L2 FP L/C4K D3: D4: D5: D6: RDTTD-1 L/C/T D7: L2-245 C2K/T/W D8: L2-272 pull; RFD2 L/C4K | CM12- Install MLI, Mu shields | CM09- Fastener Rework, Beamline pumpdown/LC CM10- Fasteners Rework, prep for BPM work | CM08- Alignment | CM07- Begin repair list | C75-Build WG Assy's, Rework rotary feedthrus | LCLSII- Heat exchanger leak check
2018-05-05 | Sat
2018-05-06 | Sun
2018-05-07 | Mon | C75; DB&DL HD ice (Sandorfi) |  | C75 Half cells; L2 Unplated bellows; L2 VV-24 |  |  | AES-006 |  |  |  | TWIN-1 50u and dip flanges; | IA-110; L2-151 ext rinse; RITH-CT-123, -130; RITH-CT-164, -174; DQW parts; L2-151 parts; L2-272; |  | IA-110 25u; | HPR1: OOC HPR2: RDT-2; SCIB; |  |  | L2-151; TS28-003; TS34-003; |  |  |  | L2-261, L2-286, L2-305 D5 sensors and HOMs; | L2-272; | D1: Hall Probe cal C4K D2: L2 FP L/C4K D3: D4: D5: L2-261, L2-286, L2-305 L/precool/warm/C4K D6: D7: D8: RFD2 C2K/T/W | CM12- Install MLI, Mu shields | CM09- Fastener Rework, Beamline pumpdown/LC CM10- Fasteners Rework, prep for BPM work | CM08- Alignment | CM07- Begin repair list | C75-Build WG Assy's, Rework rotary feedthrus | LCLSII- Heat exchanger leak check
2018-05-08 | Tue | C75; DB&DL | PCW 5pm-3am | C75 Half cells; L2 VV-24 |  |  |  | PCW 5pm-3am |  |  | C75 HC weld prep (x2); | L2-272 ext rinse; EIC1; Test stand parts; Nb polishing sample; Bellows 3034; Cryo HW; L2-272 parts; |  | EIC1 setup | HPR1: OOC HPR2: H1; L2-151; |  | L2-151 cage; L2-272 cage; | L2-272; TS28-003; TS34-003; | DQW2; H1; | H1; RITH-CT-164, -174; |  |  | L2-247; | D1: D2: D3: D4: D5: L2-261, L2-286, L2-305 C2K; D6: D7: D8: RFD2 C4K/T/W; | CM12-Idle CM11-Idle, UCM from Blue Crab | CM09- Fastener Rework, Move to WS4, Demag VV CM10- Fasteners Rework, prep for BPM work | CM08- WS5, JT welding Warm Couplers | CM07- Begin repair list | C75-Build WG Assy's, Rework rotary feedthrus | LCLSII- Heat exchanger leak check BNL -Damper weld R&D- Welding Support-Jiquan |  |  |  |  | LCW 5pm-3am
2018-05-09 | Wed | C75; DB&DL | injector pucks; | C75 Half cells |  |  | CERN1 probe cal; |  |  |  | Nb foil; Nb cam; | EIC1; Al gaskets x24; L2 fasteners; |  | EIC1 40u | HPR1: OOC HPR2: L2-272; L2-151; |  | L2-151 new FP; | TS28-003; TS34-003; |  | DQW2; RITH-CT-123, -130; | DQW2 120C/24h |  | L2-251; | D1: D2: L2 FT pull? D3: D4: D5: L2-261, L2-286, L2-305 C2K/T/W D6: H1 L/C1.5K/T D7: D8: RFD2 warm/pull; | CM12-Idle CM11-Idle, UCM from Blue Crab | CM09- Fastener Rework, Move to WS4, Demag VV CM10- Fasteners Rework, prep for BPM work | CM08- WS5, JT welding Warm Couplers | CM07- Begin repair list | C75-Build WG Assy's, Rework rotary feedthrus | LCLSII- Heat exchanger leak check BNL -Damper weld R&D- Welding Support-Jiquan |  |  | SAD progress: Completed BL turbo hook ups on 4/5 NL C100's - warmup in progress U-tubes removed 1L07 - warm up in progress
2018-05-10 | Thu | C75; DB&DL | HZB | L2 bellows unplated |  |  | CERN1 probe cal; EIC1 probe cal; |  |  |  | RDL & RDTTD1 Clean up BCP; Nb Cathode & Cap; | AES006 and HW; Ti cage parts; Unplated bellows x2; L2 Silver bolts; EIC HW; Nb Cathode & Cap; |  |  | HPR1: OOC HPR2: L2-272; |  | L2-272; | TS28-003; TS34-003; | L2-238 D7/8; L2-151 D7/8; J1.3-10 BPM retrofit; |  | DQW2 120C/24h |  | L2-168 | D1: D2: D3: D4: D5: L2-261, L2-286, L2-305 warm; D6: H1 pull, L/C1.5K/T D7: D8: RFD2 pull | CM12-Idle CM11-Idle, UCM from Blue Crab | CM09- Fastener Rework, Move to WS4, Demag VV CM10- Fasteners Rework, prep for BPM work | CM08- WS5, JT welding Warm Couplers | CM07- Begin repair list | C75-Build WG Assy's, Rework rotary feedthrus | LCLSII- Heat exchanger leak check BNL -Damper weld R&D- Welding Support-Jiquan |  |  | SAD progress: NLC100's - BLVacs's pumping down- started in mid 1e-5 range, now in mid 1e-7 range U-tubes removed 1L07 - warm up in progress
2018-05-11 | Fri | regen | HZB | L2 bellows unplated; L2 mag sheild |  |  | SC04 fasteners; |  |  |  | 2-man rule; shower alarm testing; | EIC1; L2-305 ext rinse; | 2-man rule; shower alarm testing; | 2-man rule; shower alarm testing; | HPR1: OOC HPR2: RDL-02; RDTTD-1; IA-114; |  | AES006 cage; EIC1 cage | TS28-003; TS34-003; | SC04 D6; L2-272 D7/8; | L2-238; L2-151; SC04; | L2-238 120C/12h; | DQW2 sensors and wiring repair; | L2-305 | D1: D2: D3: DQW2 L/C4K D4: D5: L2-261, L2-286, L2-305 pull; D6: SC04 L/C2K/W D7: D8: | CM12-Idle CM11-Idle | CM10- Fasteners Rework, BPM Leak Check CM11- UCM Fastener QC | CM09- Fastener Rework, Instrumentation | CM07- Move to WS6 CM08- JT welding Warm Couplers | C75-Build WG Assy's, Rework rotary feedthrus | LCLSII- Heat exchanger leak check BNL -Damper weld R&D- Welding Support-Jiquan CM02- Into Shipping Frame
2018-05-12 | Sat | [19 empty] | L2-238 120C/12h;
2018-05-13 | Sun
2018-05-14 | Mon | C75; DB&DL; | HZB | L2 bellows unplated; L2 mag sheild |  |  |  | RDL-02; RDTTD-1; |  |  | Nb covers 15u; RDT-2 15u; Nb ring; | SC02;Nb Tee; Coupler wipe x2; Al lollipop part; Cu gaskets; Cryo parts; Coupler fasteners; |  |  | HPR1: OOC HPR2: EIC1; AES006; |  | cage SC02; | L2-305 replace HOMs and FPs; SC04; |  | L2-272; L2 gate valves (x 6); TS28-003; |  | L2-151 sensors & HOMs; L2-238 input cable repair; | L2-286 | D1: D2: D3: DQW2 C2K/T D4: D5: D6: SC04 pull; D7: L2-151 L D8: L2-238 L/C4K | CM12-Idle CM11-Idle | CM10- Fasteners Rework, LC BPM Rework CM11- UCM Fastener QC | CM09- Instrumentation Repair, Tune HOM's | CM08- Warm Couplers, Inst., Testing Cap | C75-Build WG Assy's, Rework rotary feedthrus | LCLSII- Heat exchanger assy R&D- Welding Support-Jiquan CM07- Shipping Cap Test Fit
2018-05-15 | Tue | maint | cleanup run BB | L2 UCM |  | Tuning | CM09 HOMs; H1; |  |  |  |  | SC02 HW (from SC04); CRN-1 Clamps & HW; RA valve; EIC1 HW; L2-286 wipe; Elnik parts; LSF5-1 prep for acid work; |  |  | HPR1: OOC HPR2: SC02; SCIB; AES006; |  | AES006; L2-286 cage; | L2-286; | L2-305 D7/8; SCIB D6; | RITH-PA-x.02; TS28-003; SCIB; L2 Gate Valves |  |  | L2-261 | D1: D2: D3: DQW2 C2K/T/W D4: D5: D6: D7: L2-151 C4K D8: L2-238 C2K/T/W | CM12-Idle CM11-Idle | CM10- Fasteners Rework, LC BPM Rework CM11- UCM Fastener QC | CM09- Instrumentation Repair, Tune HOM's | CM08- Warm Couplers, Inst., Testing Cap | C75-Build WG Assy's, Rework rotary feedthrus | LCLSII- Heat exchanger assy R&D- Welding Support-Jiquan CM07- Shipping Cap Test Fit |  |  | SAD progress: NLC100's - BLVacs's pumping down on ion pumps in low 1e-8 range Bubble run continues - Inj / NL lock up HeP set up in tunnel at 2L02 and 2L12 today
2018-05-16 | Wed | maint; Nb cathode; | L2 bellows unplated; | L2 Tuners RFD Damper #1; |  |  | CM09 HOMs | RDL-02; RDTTD-1; |  |  | LSF5-1 | VSR HOM load; Instrament spool assy; L2-286 parts; Vac hose & cord wipe; |  |  | HPR1: OOC HPR2: L2-286 |  |  |  | SC02 D6; AES006 | RITH-PA-x.05; SC02; L2-305; |  | L2-272 HOMs & sensors; |  | D1: D2: D3: DQW warm/pull D4: D5: D6: SCIB L/SC D7: L2-151 C2K/T/W D8: L2-238 warm | CM12-Idle CM11-Idle | CM10- Fasteners Rework CM11- UCM Alignment Crew RI | CM09- Tune HOM's, Check List, Lower Shields | CM08- Warm Couplers, LC Testing Cap | C75-Build WG Assy's, Rework rotary feedthrus | LCLSII- Heat exchanger assy. CM07- Shipping Cap Re-Test Fit
2018-05-17 | Thu | C75; DB&DL; |  | L2 Tuners L2 bellows unplated; |  |  |  | RDL-02; RDTTD-1; | EIC1 |  | Nb cthode; SS tube; | Al holders; SS flange; Hardware for Nb cathode; L2 HW & fasteners; EIC dumbell; |  |  | HPR1: OOC HPR2: L2-286; |  | L2-286; TS16-003; |  | H1 D6; | AES006; RITH-PA-x.05; H1; |  | L2-305 sensors & HOMs; L2-272 HOMs & sensors; |  | PSS Certs: D1: D2: D3: D4: D5: D6: SCIB C4K/T D7: L2-151 warm D8: L2-238 pull; L2-272 L/C4K | CM12-Idle CM11-Idle | CM10- Fasteners Rework CM11- UCM Weld insp. | CM09- Check List, Lower Shields | CM08- Warm Couplers, LC Testing Cap | C75-Build WG Assy's, Rework rotary feedthrus | OPEN HOUSE CLEANUP LCLSII- Heat exchanger assy. CM07- Cold Mass Lock Down UITF- Welding Support ACC- Welding Support
2018-05-18 | Fri | C75; DB&DL |  | L2 Tuners |  |  |  | RDL-02; RDTTD-1; |  |  | RFD Damper #1 5u; SS windows x4; L2 HOM FT (x10); L2 FP FT (x5); | RFD Damper #1 and parts; L2-053 wipe; Nb/SS cathode; L2 HOM FT (x10); L2 FP FT (x5); Cryo HW; |  |  | HPR1: OOC HPR2: |  | TS34-003; |  | L2-286 D7/8; AES006 D7/8; |  |  | L2-305 sensors & HOMs; SC02 sensors; | L2-238 | D1: D2: RRR L/C/T/W D3: D4: D5: D6: SCIB C2K/T D7: L2-151 pull; L2-305 L/C4K D8: L2-272 C2K/T/W; | CM12-Idle | CM10- Fasteners Rework CM11- String to WS3 | CM09-OH Display | CM08-WarmCouplers, Instrumentation | C75-Build WG Assy's, Rework rotary feedthrus | OPEN HOUSE CLEANUP LCLSII- Heat exchanger assy. CM07- Cold Mass Lock Down CM02- Unload Shipping Frame
2018-05-19 | Sat
2018-05-20 | Sun
2018-05-21 | Mon | C75 StifRng;DB HDIce | WW; DL; | L2 Spools (x2); L2 Tuners; |  |  |  | maint; | EIC1 |  | Nb HC 20u; | L2-056 wipe; L2-157 string prep; RDTTD-01 parts; L2-056 parts; Al gaskets; |  |  | HPR1: OOC HPR2: H1; L2-053; |  | cage L2-053 TS34-003 |  | RFD Damper #1; H1; | L2-286; H1; AES006; |  |  | L2-272 | D1: D2: RRR pull; D3: D4: D5: D6: SC02 L/C/T/W (20mG) D7: L2-305 C2K/T/W D8: L2-272 pull; |  | CM10- Fasteners Rework CM11- String to WS3 | CM09-Reverse OH Display, Checklist, lower shields | CM08- PT, WarmCouplers, Instrumentation | C75-Build WG Assy's, Rework rotary feedthrus | OPEN HOUSE REVERSAL LCLSII- Heat exchanger assy. CM07- Install Shipping Caps, Prep for shipping
2018-05-22 | Tue | C75 DL eyelet | WW; DL; | L2 Mag shield L2 Tuners; |  |  |  | Nb HC 900C/3h; |  |  | Nb covers 15u (GE); EIC1 flanges; Mo rings; C75-SC1 Nitric soak; Mo straps x2; | L2-059 wipe; L2-147 string prep; EIC1 and parts; RFD Damper parts; RDTTD-01 Parts; RFD parts; BackTek controls x2; Nb & Mo parts; L2-056 parts; |  |  | HPR1: OOC HPR2: RDTTD-01; L2-053; |  | L2-053; cage L2-056; TS34-003 |  |  |  |  | L2-286 HOMs & sensors; |  | D1: D2: D3: D4: D5: D6: H1 L/C/T D7: L2-305 warm D8: L2-286 Load |  | CM10- Fasteners Rework, tuner rework CM11- Unite string to UCM | CM09- Lower shields, MLI | CM08- JT Welding, Beampipe Install, Instrumentation | C75-Build WG Assy's, Rework rotary feedthrus | OPEN HOUSE REVERSAL LCLSII- Heat exchanger assy. CM07- NOT SHIPPING, Disassemble shipping CM02- Into Shipping frame, rest in BY |  |  | 1L23 cryomodule to be pulled out of slot and staged in SL near SAB F100 NAB -> SAB -> 1L23 HeP station in place at 2L18 2L12 will not be processed
2018-05-23 | Wed | C75 DB;DL eyelet Geng 5cell BT ext | WW; DL; | L2 Tuners; |  |  |  | Nb HC 900C/3h; |  |  | Nb samples x50; Nb parts x17; | L2-243 string prep; |  |  | HPR1: OOC HPR2: IA-110 EIC1x4; |  | cage EIC1 TS34-003; cage L2-059; |  | L2-053 D7/8; RDTTD-01; | RDTTD-01; |  |  | L2-305 | D1: D2: D3: D4: D5: D6: D7: L2-305 pull; AES006 L/C4K D8: L2-286 C2K | CM12-Idle | CM10- Fasteners Rework, tuner rework CM11- Unite string to UCM, install US tuner, 2 phase piping | CM09- MLI, into VV | CM08- JT Welding, Beampipe Install, Instrumentation, WC's | C75-Build WG Assy's, Rework rotary feedthrus | LCLSII- Heat exchanger assy. CM07- Disassemble shipping CEBAF Module moves 8:30 a.m.
2018-05-24 | Thu | C75; Geng 5cell BT ext | WW; DL; | L2 Mag shield L2 Tuners; |  |  |  | Nb HC 900C/3h; |  |  | Nb samples x50; Mo straps x3; EIC5 DB; | SS tube; Coupler HW; Indium mold; Girder; Test stand flange & Tee; |  |  | HPR1: OOC HPR2: IA-114 L2-056; |  | cage IA-114; cage CERN1; TS34-003; | Girder; | EIC1 D3/4; | L2-053 failed; |  |  |  | D1: D2: D3: D4: D5: D6: RDTTD-01 L/C/T D7: AES006 C2K/T D8: L2-286 T/W (1) | CM12-Idle | CM10- Fasteners Rework, tuner rework CM11- Unite string to UCM, return lollipops | CM09- MLI, into VV | CM08-Low PT, Instrumentation, WC's | C75-Build WG Assy's, Rework rotary feedthrus | LCLSII- Heat exchanger assy. CM07- Disassemble shipping
2018-05-25 | Fri | C75 DB; DL |  | L2 Mag shield L2 Tuners | [7 empty] | Girder parts; L2 flange; |  |  | HPR1: OOC HPR2: IA-114 |  | IA-114; TS34-003; |  |  | EIC1; | EIC1 120C/12h; |  |  | D1: D2: D3: D4: D5: D6: D7: AES006 C2K/T/W D8: L2-286 warm, | CM12-Idle | CM10- Fasteners Rework, tuner rework CM11- Unite string to UCM | CM09- Lower shields, MLI | CM08-Low PT, Instrumentation, WC's | C75-Build WG Assy's, Rework rotary feedthrus | LCLSII- Heat exchanger assy. CM07- Disassemble shipping
2018-05-26 | Sat | [19 empty] | EIC1 120C/12h;
2018-05-27 | Sun
2018-05-28 | Mon | [13 empty] | HPR1: OOC HPR2:
2018-05-29 | Tue | LSF5-1 BT ext; | WW; DL; | C75 Dumbbell; C75 HC (x3); L2 Spools; |  |  |  | maint |  |  | C75 HC (x2) weld prep (pm); Nb covers 15u; RDTTD-01 HF rinse; | SNS tooling; MB-002 wipe; CERN1 and parts; RDTTD-1 parts; RDT parts; |  | KEK-R5 setup; | HPR1: OOC HPR2: C75-SC1; RDT2; L2-056 |  | L2-056; MB-002 cage; |  | RFD2 D7/8; |  |  |  |  | D1: D2: D3: EIC1 L/C2K/T/W; D4: D5: D6: D7: AES006 pull; D8: | CM12-Idle | CM10- Fasteners Rework, tuner rework CM11- Unite string to UCM, drop lollipops | CM09- Alignment in VV | CM08- Instrumentation, WC's, bayonet box | C75-Build WG Assy's, Rework rotary feedthrus | LCLSII- Heat exchanger assy. CM07- Move to WS6 |  |  | Move SL21 from LERF to SAB…WEATHER?
2018-05-30 | Wed | LSF5-1 BT ext; C75 DB; C75 EG; | WW; DL; | L2 Tuners; L2 BPM; C75 HC; |  |  |  | maint |  |  | Twin 1 flanges; Cu HC x2; | Lollipops; IA-110; MB-002 Parts; Rail HW; KEK-R5 Parts; L2-314 Wipe; |  | KEK-R5 25u; | HPR1: OOC HPR2: RDTTD-01; IA-114 |  |  | MB-002 | Girder; L2-056 D7/8; RDTTD-01; | RFD2; RDTTD-01; |  |  | L2-286 | D1: D2: RRR C/T/W D3: EIC1 warm D4: TS28-007A L/C2K/W D5: D6: D7: D8: | CM12-Idle | CM10- Fasteners Rework, tuner rework CM11- Unite string to UCM | CM09- Alignment in VV | CM08- Instrumentation, WC's, bayonet box | C75-Build WG Assy's, Rework rotary feedthrus | LCLSII- Heat exchanger JTs CM07- Move to WS6 |  |  | P1 @ SAB
2018-05-31 | Thu | LSF5-1 BT ext; C75 DB; C75 EG; | WW: DL; | L2 Mag shields; C75 HC; BPM; |  |  |  | maint | IA-110 ease edges; |  |  | L2 bellows; girder #2; String HW; A-frames; Al gaskets; KEK gaskets; Pump drops; L2-319; |  | L2-238 setup; | HPR1: OOC HPR2: CERN1 (x4) KEK-R5 |  | Lollipops; |  | KEK-R5; IA-114 D7/8 | L2-056; girder 1 |  | RFD2 sensors; |  | D1: D2: RRR hold D3: EIC1 pull; EIC1 L/4K D4: TS28-007A warm/pull D5: D6: D7: RFD2 L/C2K/T/W D8: | CM12-Idle | CM10- Fasteners Rework, tuner rework CM11- Welding 2 Phase Piping | CM09- Alignment in VV | CM08- Instrumentation, WC's, bayonet box | C75-Build WG Assy's, Rework rotary feedthrus | LCLSII- Heat exchanger LC CM07- Configure BP's |  |  | 1L16 baseline;
2018-06-01 | Fri | C75 DB; | WW; DL; | L2 Mag shields; C75 HC; |  |  |  | maint |  |  | IA-110 Q-tip flanges; Deposition Cathode (AMV); Nb covers; | IA-110; Deposition Cathode (AMV); Ceramic wedge; L2-060; |  | L2-238 5u; | HPR1: OOC HPR2: MB-002 |  | Lollipops; | girder #2 | BPM subassy; CERN1 D3/4; | IA-114; KEK-R5; |  | L2-056 HOMs & sensors; IA-114 sensors; |  | all gas returned by Monday 6am D1: D2: RRR pull; D3: EIC1 C2K/T/W D4: D5: load D6: KEK-R5 L/C/T D7: RFD2 warm D8: IA-114 L/SC4K/T; | CM12-Idle | CM10- Fasteners Rework, Checklist CM11- 2 Phase Piping LC, Prep for BPM rework | CM09- Alignment in VV, Move to WS5 | CM08- Instrumentation, bayonet box LC, MC Line/WG install | C75-Build WG Assy's, Rework rotary feedthrus | LCLSII- Heat exchanger LC CM07- Move to WS6 |  |  | 1L06 warming | 1L
2018-06-02 | Sat
2018-06-03 | Sun
2018-06-04 | Mon | C75 DL; |  | C75 Dumbbells; SC-07 insp & demag; L2 Mag shields | [6 empty] | C75 HC (x2) weld prep; Nb sample discs (x20); Nb plates & sample chamber | String HW; CPI-LVA-69; CPI-LVA-70; Test HW; Test stand parts; Gaskets; L2-238; |  | A3/RDL-02 setup; | HPR1: OOC HPR2: unavail; MB-002; |  | MB-002; L2 bellows; | RFD2 remove from TS; | BPM subassy; | CERN1; | KEK-R5 load; |  |  | CTF Down D1: D2: D3: EIC1 pull; D4: D5: D6: KEK-R5 pull D7: RFD2 pull; D8: IA-114 warm; | CM12-Idle | CM10- Fasteners Rework, Checklist CM11- 2 Phase Piping LC, Prep for BPM rework | CM09- Alignment in VV, Move to WS5 | CM08- Instrumentation, bayonet box LC, MC Line/WG install | C75-Build WG Assy's, Rework rotary feedthrus | LCLSII- Heat exchanger LC CM07- Move to WS6 |  |  | 1L07 bleed-up BL;
2018-06-05 | Tue | recovery | recovery | C75 Dumbbells; L2 SC-08; L2 VV 030 |  |  |  | recovery | C75-SC1 |  | C75 HC (x2) weld prep; C75-SC1 flanges; A3/RDL-02; | SC-07; c75 HOM Wedge; lollipop HW; string HW; C75-SC1; A3/RDL-02; vacuum HW; L2 FPC HW; CPI-LVA-69; CPI-LVA-70; WW masks (x2); L2 string cav (x2); |  | A3/RDL-02 6u | HPR1: OOC HPR2: |  | L2 bellows; | DQW2; | MB-002 D7/8; | BPM subassy; | KEK-R5 120C/12h; |  |  | CTF Down D1: D2: D3: D4: D5: D6: D7: D8: IA-114 warm | CM12-Idle | CM10- Checklist, to WS4 CM11- 2 Phase Piping LC, Prep for BPM rework, Fasteners | CM10- VV Demag/field map | CM08- Into CMTF, LC Ins Vac; CM09- WC's, Beampime prep | C75-Build WG Assy's, Rework rotary feedthrus | LCLSII- Heat exchanger LC, Assemble stems, seats, actuators
2018-06-06 | Wed | C75 DL; | WW; C75 HOM load; | C75 Dumbbells; L2 Mag shield; L2-VV -030 ; |  |  |  | PD HC 1000C/3h; |  |  | PD HC 20u; C75 HC (x2) weld prep; Sample chamber; | Girder #2; BPM fasteners; DQW HW; Cages (x2); (AP) spools (x7); L2 ext rinse; Spool parts; test stand parts; |  |  | HPR1: OOC HPR2: IA-110; DQW2; |  | L2 mag field meas; | IA-114; | SC-07 D7/8 and bolt swap; | MB-002; RDT-TD01; | KEK-R5 120C/12h;MB-002 120C/12h; |  |  | D1: D2: RRR hold D3: D4: maint; TS28-007A load D5: D6: KEK-R5 L/C2K/T (1) D7: D8: IA-114 pull; CERN1 L/C4K; (2) | CM12-Idle | CM11- Prep for BPM rework, Fasteners, Magnet lead soldering | CM10- to WS4, test fit shields | CM08- LC Ins Vac, PV's CM09- WC's, Beampime prep, Peripherals | C75-Build WG Assy's, Rework rotary feedthrus | LCLSII- Heat exchanger ready for testing CM12- UCM from BC 1L07- Move Demag brackets-rework
2018-06-07 | Thu | C75 DL; | C75 load; DL; | L2 mag shield; L2 SC-08 |  |  |  | PD HC 1000C/3h; |  |  | C75 HC (x2) weld prep; Sample chamber; | Test stand parts; Cages (x2); RDT-2; Counter bracket & HW; |  | Acid change | HPR1: OOC HPR2: C75-SC1; IA-110; |  | IA-110; cage L2-253; cage L2-144; |  | C75-SC1 | SC-07; CPI-LVA-69; CPI-LVA-70; | MB-002 120C/12h; | SC-07; |  | D1: D2: RRR C D3: D4: TS28-007A C4K/W D5: D6: KEK-R5 pull; RDTTD-01 L/C/W D7: SC-07 L/C4K D8: CERN1 C2K/T/W | CM12-Idle | CM11- Prep for BPM rework, Fasteners, Magnet lead soldering CM12-UCM RI's | CM10- Test fit shields, HOM Tuning tomorrow | CM08- LC Ins Vac, PV's, U-tubes tomorrow CM09- WC's, Beampime prep, Peripherals, HPT | C75-Build WG Assy's, Rework rotary feedthrus | Demag bracket-rework |  |  | P1 in 1L07; |  | PCC Cert;
2018-06-08 | Fri | C75 DB; C75 DL; | maint | SC-1.1 (1); L2-025 (2); |  |  | J-10 HOMs | PD HC pull; PD Nb samples 800C/3h; |  |  | IA-114 Nitric soak flanges; Sample Chamber & plates 5u; Nb rod, tube, cylindrical container 20u; C75 DL; Nb samples; Nb sheet; Test plates; | Brazing windows (x24); IA-114;C75 DL; A arm support; |  | HF spike | HPR1: OOC HPR2: A3; RDT-2; |  | cage L2-304; cage L2-315; BPM stud swap CM11; |  | IA-110 D3/4; C75 HOM load; A3 D6; | C75-SC1 |  | C75-SC1 sensors; | SC-08; | CM08 cooldown; D1: D2: RRR T/W D3: D4: TS28-007A warm? D5: D6: C75-SC1 L/SC; D7: SC-07 C2K/T/W; D8: CERN1 warm; | CM12-Idle | CM11- BPM rework, Fasteners, Magnet lead soldering CM12-UCM RI's, JLAB Align Crew | CM10-HOM Tuning | CM08- LC Ins Vac, U-tubes/cooldown CM09- WC's, Beampime prep, Peripherals | C75-Build WG Assy's, Rework rotary feedthrus | Demag bracket-rework |  |  | 1L23 waveguide installation; |  | J1.3-08 cooldown;
2018-06-09 | Sat | [22 empty] | D7:
2018-06-10 | Sun | [13 empty] | HPR2: L2-253; L2-144;
2018-06-11 | Mon | C75 DB; | C75 WW: | L2 UCM 030 |  |  |  | PD Nb samples pull; |  |  | GC samples and BT 30u; | L2-025 ext rinse; Coupler HW; |  | H2/RDT-6/RDTTD-02 setup | HPR1: OOC HPR2: L2-304; L2-315; |  | L2-253; L2-144 to rail; TS34-003; |  | girder #2; RDT-2 D6; | IA-110; C75 HOM load; A3 failed; |  | IA-110 sensors; |  | CMTF pumpdown D1: D2: RRR warm D3: IA-110 L/SC D4: TS28-007A pull; D5: D6: C75-SC1 T/C2K/T/W D7: SC-07 warm; D8: CERN1 pull; MB-002 L/C4K | CM12-Idle | CM11- BPM LC, Fasteners, CM12-UCM RI's | CM10- 50k MLI, into VV | CM08- Testing CM09- WC's, Beampime prep, Peripherals | C75-Build WG Assy's, Rework rotary feedthrus |  |  |  | 1L23 waveguide installation; |  | J1.3-08 cooldown;
2018-06-12 | Tue | C75 DB; |  | L2 Cavity Mag shields; |  |  |  |  | L2-114 flange polishing; RDTTD-01; |  |  | RDTTD-01; H2/RDT-6/RDTTD-02; Alignment tools; Pump drop; Spool & blank; Nb samples x21; RDTTD-01 HW; LSF5-1; |  | H2/RDT-6/RDTTD-02 40u | HPR1: OOC HPR2: L2-243; L2-255; |  | L2-304, L2-315 to rail; TS34-003; |  | SC-08 D7/8; | girder #2; SC-08; RDT-2; |  |  |  | CTF unplanned down D1: C75 HOM load; D2: RRR hold D3: IA-110 C4K/T/W D3-->D8 D4: TS28-007A load D5: D6: C75-SC1 pull D7: SC-07 pull D8: MB-002 D8-->D3; | CM12-Idle | CM11- Fasteners, BPM LC, CM12-UCM RI's, String to WS3 | CM10- Into VV | CM09- WC's, Beampime prep, Peripherals | C75-Build WG Assy's, Rework rotary feedthrus
2018-06-13 | Wed | C75 DB; EIC5; |  | C75 DB (x4) C75 HC (x8) |  |  | L2-025 RF incoming; |  |  |  | IA-016 Flange BCP; | SC-07; L2-025 ext rinse; Lg Tees x10; Beam pipes x4; Girder; LSF5-1; |  | LSF5-1 setup | HPR1: OOC HPR2: L2-319; L2-157; |  | L2-243, L2-255 to rail; TS34-003; | girder #3; |  | TS34-003; | TS34-003; | SC-08 sensors; |  | D1: C75 HOM evacuate D2: RRR pull D3: IA-110 warm; D4: TS28-007A hold; D5: D6: D7: SC-08 L/C4K 5mG (2) D8: MB-002 C2K/T (1) |  | CM11- Fasteners, Magnet lead soldering, 2 Phase LC CM12-UCM RI's, String to WS3 | CM10- Alignment into VV | CM09- WC's, Beampime prep, Peripherals | C75-Build WG Assy's, Rework rotary feedthrus | Repair LERF testing caps
2018-06-14 | Thu | EIC5; |  | C75 HC (x8); L2 Cavity Mag shields; | [6 empty] | LSF5-1 ethanol rinse; |  |  | LSF5-1 20u | HPR1: OOC HPR2: SC-07; RDTTD-01; LFS5-1; |  | L2-319, L2-157 to rail | girder #3; | J1.3-13; |  |  |  |  | D1: C75 HOM C2K/T/W D2: D3: IA-110 pull; field map & minimize D4: TS28-007A hold; D5: D6: D7: SC-08 C2K/T/W100K; D8: MB-002 hold?; |  | CM11- Fasteners, Magnet lead soldering, 2 Phase LC CM12- String to WS3, Unite CM to UCM | CM10- Alignment into VV | CM09- WC's, Beampime prep, Peripherals | C75-Build WG Assy's, Rework rotary feedthrus | Repair LERF testing caps |  |  | 1L07 to north access |  | CM08 emax
2018-06-15 | Fri |  |  | C75 DB (x4); |  |  | LSF5-1; |  |  |  |  | EIC-1 wipe; |  | LSF1-2 setup | HPR1: OOC HPR2: L2-060 A3; |  |  | ia-110 | SC-07 D6; L2-025 D7/8; RDTTD-01 D6; EIC-1 D3; C75 DLs D1; Girder 1L07; | J1.3-13; |  | L2-056 sensors & HOMs; |  | D1: D2: D3: D4: D5: D6: RDT-2 hold D7: SC-08 warm 20mG D8: MB-002 warm; |  | CM11- Fasteners, Magnet lead soldering, 2 Phase LC CM12- String to WS3, Unite CM to UCM | CM10- Alignment into VV | CM09- WC's, Beampime prep, Peripherals | C75-Build WG Assy's, Rework rotary feedthrus | Repair LERF testing caps
2018-06-16 | Sat | [18 empty] | SC-07 (3); L2-025 (2); RDTTD-01 (4); EIC-1 (1); |  | TS34-00 |  | D8: MB-002 pull;
2018-06-17 | Sun
2018-06-18 | Mon | EIC5; |  | L2 mag shields |  |  | LSF5-1; |  |  |  | RFD Damper SS etch; RFD Damper BCP; 2 chanbers, 4 plates 3 foils; | Girder 1L08; LSF1-2 HW; Back Tech x2; | IA-110 setup | LSF1-2 30u | HPR1: OOC HPR2: L2-060; LSF1-2; |  | L2-060 | SC-08 for HPR; | Girder 1L08; | J1.3-13 bag; |  | SC-07 sensors; L2-025 sensors & HOMs; |  | D1: C75 HOMs pull; D2: RRR L D3: EIC-1 L D4: TS28-007A hold D5: D6: RDT-2 SC; D7: SC-08 pull; L2-056 L/C4K; D8: L2-025 L/C4K; |  | CM11- Fasteners, Magnet lead soldering, 2 Phase LC CM12- String to WS3, Instal CGV support, Unite CM to UCM | CM10- Move to WS5 | CM09- WC's, Beampime prep, Peripherals | C75-Build WG Assy's, Windows, Rework rotary feedthrus | Repair LERF testing caps
2018-06-19 | Tue | EIC5; |  | C75 HC; VV 28; | [6 empty] | CERN1.3-1, -4, -5, -6; EIC-5 DB; Nb disks, Nb samples x20; | L2-094 ext rinse; CERN1.3-1, -4, -5, -6; | IA-110 15u; | AES-006 setup; | HPR1: OOC HPR2: L2-059; |  |  |  | L2-053, L2-060 D5; LSF1-2 D3/4; | J1.3-13; Girder 1L08; LSF1-2; |  |  |  | D1: C75 HOMs warm D2: RRR C4K D3: EIC-1 C4K/W (level sensor failed) D4: TS28-007A C4K D5: cool 4K (1) D6: RDT-2 C4K/T/W D7: L2-056 hold; D8: L2-025 C2K/T |  | CM11- Fasteners, Magnet lead soldering, 2 Phase LC CM12- String to WS3, Instal CGV support, Unite CM to UCM | VV installation | CM09- WC's, Beampime prep, Peripherals CM10- WC install, Helium pipe welds | C75-Build WG Assy's, Windows, Rework rotary feedthrus | Repair LERF testing caps
2018-06-20 | Wed | EIC5; |  | VV 28; |  |  | IA-320; |  |  |  | IA-110 flange nitric; Nb strip weld test; 1L07 girder parts; Mo straps x2; | AES-006; Test stand HW; | IA-016 setup; IA-016 15u; | AES-006 10u; | HPR1: OOC HPR2: L2-059; |  | L2-059; | Girder 1L07; |  | SC-08; |  |  |  | CMTF Cooldown D1: C75 HOM hold; D2: RRR W/T D3: EIC-1 pull, maint D4: TS28-007A C4K D5: C4K D6: RDTTD-01 L/C/T/W; D7: L2-056 C2K/T; D8: L2-025 warm |  | CM11- Fasteners, Magnet lead soldering, mag shields CM12- WS3, Unite CM to UCM, return lollipops, welding | VV028- inspect and alignment | CM09- WC's, Beampime prep, Peripherals, leakcheck CM10- Helium pipe welds | C75-Build WG Assy's, Windows, Rework rotary feedthrus | Repair LERF testing caps |  |  | 4K both LINACs; Power outage; |  | cooldown
2018-06-21 | Thu | EIC5; student project |  | 247 mag shield | [6 empty] | NbTi flanges x8 <5u; | SC-08 HW; L2-272; Couplers x2; Coupler flanges x4; |  | C75-SC1/LG-RG setup; | HPR1: OOC HPR2: L2-094; SC-08 |  |  |  | L2-059, L2-053, L2-060 D5; Girder 1L07; |  |  |  |  | CMTF cooldown; D1:C75 HOM hold D2: RRR warm D3: EIC-1 load D4: TS28-007A hold D5: C4K D6: SC-07 5mG C1.5K/T/W D7: L2-056 warm D8: L2-025 pull | CM13 - String roll out | CM11- Fasteners, Magnet lead soldering, mag shields CM12- Return lollipops, welding | VV028- Demag | CM09- Leakcheck, WC's, Beampime prep, Peripherals CM10- Helium pipe welds | C75-Build WG Assy's, Windows, Rework rotary feedthrus | Repair LERF testing caps, Fast cooldown CMTF, |  |  | 4K both LINACs; 1L23 prep for cooldown; |  | temp bump; fast cooldown;
2018-06-22 | Fri | student project |  | L2-201; L2-209; |  |  | IA-320; |  |  |  | NbTi flanges x4 <5u; Mo bolts, samples x2, Nb wire; | AES-006 HW; Vac cart parts; |  | C75-SC1/LG-RG 20u; | HPR1: OOC HPR2: IA-110 L2-094; |  | L2-094; |  | SC-08 cart; | L2-059, L2-053, L2-060; Girder 1L07; |  |  | SC-01.1; L2-025; | D1: C75 DL L; D2: RRR D3: EIC-1 hold D4: TS28-007A hold 4K D5: hold 4K D6: SC-07 20mG L/C/W D7: L2-056 pull/check FP cable D8: | CM13 - Berry bolts, Mag Shields, Welding | CM11- Magnet lead soldering and Torquing CM12- Welding 2 phase | VV028- Demag | CM09- Leakcheck CM10- Helium pipe welds,WC, | C75-Build WG Assy's, Windows, Rework rotary feedthrus | Repair LERF testing caps, CTF U-tube switch, |  |  |  |  | fast cooldown redux; pumpdown 2K;
2018-06-23 | Sat | [26 empty] | CM10 - RT 8-10 AM
2018-06-24 | Sun
2018-06-25 | Mon | maint | recovery; SS 950C degas; | C75 HC (x4); L2-210; L2-209 demag; |  |  | PD SC probe cal (x2); |  |  | RFD Damper 2; | IA-016 nitric; ra valves (x3); | CM kits (x8); Spool pieces; Beam line gaskets x12; LGRG; |  |  | HPR1: OOC HPR2: L2-272; LGRG; |  |  | lollipops; | L2-094 D7/8; DQW2 D5; |  |  |  |  | D1: C75 DL hold D2: RRR; D3: EIC-1 hold; D4: TS28-007A warm; D5: warm; D6: SC-07 20mG C1.5K/T/W (1) D7: D8: maint | CM13 - Berry bolts, Mag Shields, Welding | CM11- Magnet lead Torquing CM12- Welding 2 phase | VV028- Demag | CM09- Leakcheck CM10- | C75-Build WG Assy's, Windows, Rework rotary feedthrus | Repair LERF testing caps, CTF U-tube switch, |  |  | prepare C100 cooldown NL; |  | fast cooldown redux;
2018-06-26 | Tue | beamtubes (JT); | SS 950C degas; | L2-210 demag; L2-211; C75 HC (x4); |  |  | RDTTD-02 probe cal; L2-201; |  |  |  | acid etch CERN1.3-1, -4, -5, -6; JT BT (x21); | L2 Bellows (x9); L2 FPC caps & HW (x8); Lollipop HW; L2 string kit; Al gaskets; Gortex gaskets x30; |  |  | HPR1: OOC HPR2: AES-006 L2-272; |  | L2-272; | BPM Sub; | LGRG D6; Lollipops; | L2-094; DQW2; |  | L2-059, L2-053, L2-060 HOMs & cernox; | L2-325; L2-315; | CMTF pumpdown 2K; D1: C75 DL C4K/W #2 D2: RRR pull; stripline L/C4K D3: EIC1-pull; maint D4: TS28-007A warm D5: L2-059, L2-053, L2-060 L/precool; D6: D7: EIC-1 L/C4K; D8: | CM13 - Berry bolts, Alignment, Magnet Install, 2 phase welding | CM11- CS Alignment CM12- Welding 2 phase | VV028- field mapping, move to Storage | CM09- Prep for cantilever CM10- Testing cap install, VV peripherals | C75-Build WG Assy's, Windows, Rework rotary feedthrus | Repair LERF testing caps |  |  | prepare C100 cooldown NL; |  | pumpdown 2K; Q0 measurements;
2018-06-27 | Wed | HW BT 21 LSFC010 Cav | C75 WW | C75 HC (x4); L2-210 demag L2-211 demag |  |  | L2-209; |  | CBP CERN1.3-1, -4, -5, -6; |  | C75 HC (x2); C75 End Group; | L2-201 ext rinse; RDTTD-02; L2 string kit; CM kits (x8); BPM parts; TWIN-1; Particle counter; L2-252 Bolt holes; L2-168 Bolt holes; L2-322 Bolt holes; L2-168 Bolt holes; Lollipop parts; Cu bellows; |  |  | HPR1: OOC HPR2 AES-006 |  | AES-006; |  | L2-272 D7/8; | LGRG; |  | L2-094 HOMs & cernox; |  | D1: C75 DL C4K/W #3 D2: stripline hold 4K; D3: D4: TS28-007A W D5: L2-059, L2-053, L2-060 W/C4K; D6: LGRG load; D7: EIC-1 C2K/T/W; D8: | CM13 - Berry bolts, Alignment, Magnet Install, 2 phase welding | CM11- CS Alignment CM12- LC 2 phase, Magnet lead soldering | VV028- move to Storage | CM09- Prep for cantilever CM10- Testing cap install, VV peripherals | C75-Build WG Assy's, Windows, Rework rotary feedthrus | Repair LERF testing caps |  |  | prepare C100 cooldown NL; |  | Qo measurements Cav 1 - 2.5E10 at 16 MV/m Cav 2 - 2.0E10 at 11.5 MV/m Cav 3 - 3.4E10 at 16 MV/m Cav 4 - 3.5E10 at 13.5 MV/m Cav 5 - 3.3E10 at 16 MV/m
2018-06-28 | Thu | regen; | C75 WW | C75 DB (x4) L2-502; L2-503; | [6 empty] | Nb covers (UP); | 6" flanges (x10); L2-209 ext rinse; L2 bellows (x6); RDTTD-02 HW; RDT-06; TWIN-1 HW; |  |  | HPR1: OOC HPR2: RDTTD-02; TWIN-1 x3 per tube; |  | L2 Bellows prep; |  | AES-006 D7/8; L2-201, L2-209, L2-210 D5; BPM Sub; | L2-272; CPI-LPA-073 |  |  |  | D1: C75 warm D2: stripline 4K/W; D3: D4: TS28-007A pull D5: L2-059, L2-053, L2-060 C4K (2) D6: LGRG C2K/T/W; (1) D7: EIC-1 warm; D8: L2-094 load; | CM13 - Berry bolts, Alignment, Magnet Install, 2 phase welding | CM11- CS Alignment CM12- LC 2 phase, Magnet lead soldering | VV028- move to Storage | CM09- Prep for cantilever CM10- Testing cap install, VV peripherals, WC's | C75-Rework rotary feedthrus, Machine cell holders | Repair LERF testing caps |  |  | prepare C100 cooldown NL; |  | Qo measurements Cav 1 - 2.5E10 at 16 MV/m Cav 2 - 2.0E10 at 11.5 MV/m Cav 3 - 3.4E10 at 16 MV/m Cav 4 - 3.5E10 at 13.5 MV/m Cav 5 - 3.3E10 at 16 MV/m Cav 6 - 3.4E10 at 16 MV/m Cav 7 - 2.3E10 at 10.5 MV/m Cav 8 - 1.5E10 at 16 MV/m
2018-06-29 | Fri | maint; | C75 WW | DS Spools (x6); C75 DB (x8) L2-503; |  |  | L2-210; PD SC probe cal; |  |  |  |  | L2-210 ext rinse; RDT-06 HW; CM kits (x8); pump cart components; |  |  | HPR1: OOC HPR2: IA-016; RDT-06; |  | L2 Bellows prep; |  | L2-201, L2-209, L2-210 D5; RDTTD-02 (TS16-001); TWIN-1 D3/4; | AES-006; BPM Sub; CPI-LPA-074 | DQW-2 120C/24h; | SC-08 sensors; |  | D1: C75 DL pull; D2: stripline pull; RRR L/C D3: D4: D5: L2-059, L2-053, L2-060 C2K/T/W; (1) D6: LGRG hold D7: EIC-1 pull; map D8: L2-094 C4K (2) | CM13 - Berry bolts, Alignment, Magnet Install, 2 phase welding | CM11- Tuners CM12- LC 2 phase, Magnet lead soldering | VV028- Demag | CM09- Prep for cantilever CM10- Testing cap install, VV peripherals, WC's | C75-Rework rotary feedthrus, Machine cell holders | Repair LERF testing caps |  |  | prepare C100 cooldown NL; |  | eight cavity run ~ 100MV;
2018-06-30 | Sat | [19 empty] | DQW-2 120C/24h;
2018-07-01 | Sun | [19 empty] | DQW-2 120C/24h;
2018-07-02 | Mon | maint; C75 EG (x2); | C75 WW; C75 DL; | L2-505; DS Spools (x6); C75 DB; |  |  | L2-502; L2-503; EIC5 | Clean-up | C75 DL (x8) NbTi Flanges chase threads x9; |  | Uttar parts; | L2-251; L2-169; RDT-6 & HW; IA-110; Bronze Cavity; NbTi flanges x18; NbTi flanges x9; |  |  | HPR1: OOC HPR2: IA-110 |  | L2 Bellows prep; |  | L2-201, L2-209, L2-210 D5; SC-01.1 D7/8; RDT-06 (TS16-001); | SC-01.1; RDTTD-02; TWIN-1 |  | L2-272 HOMs & cernox; DQW2 cernox; SC-08 sensors; |  | D1: D2: RRR C4K D3: D4: D5: L2-059, L2-053, L2-060 pull; D6: SC-08 5mG L/C4K D7: L2-272 L/C4K D8: L2-094 C2K/T/W | CM13 - Berry bolts, Alignment, Magnet Install, 2 phase welding | CM11- Tuners CM12- LC 2 phase, Magnet lead soldering | VV028- Demag | CM09- Prep for cantilever, Pulling Coup CM10- Testing cap install, VV peripherals, WC's | C75-Rework rotary feedthrus, Machine cell holders | Repair LERF testing caps |  |  | prepare C100 cooldown NL; |  | Sat- 7 cavity run in GDR -95 MeV Sun - Quench processing Cav 1 - raised Emx from 18 MV/m to 21 MV/m Started processing attempt on Cav 2- some minor gains (?) wrt to FE
2018-07-03 | Tue | C75 EG (x2); | C75 WW; C75 DL; | L2-505; C75 DB; |  |  | L2-505; EIC5; C100-1probe cal; | clean up | NbTi Flanges chase threads x9; |  | NbTi Flanges; Nb weld test samples; Cu rings x6; | L2-502 ext rinse; L2-503; L2 cages (x4); L2 hand tools; EIC5; NbTi Flanges; Cables & Connectors; EIC5; | Acid Change |  | HPR1: OOC HPR2: IA-110 |  | IA-110 EIC5 cage; | RDTTD-02 |  | RDT-06; L2-201, L2-209, L2-210 D5; | AES-006 120C/24h: |  |  | D1: D2: RRR W/T D3: D4: D5: DQW2 L/C4K; D6: SC-08 5mG C1.5K/T/W D7: L2-272 C2K/T/W; D8: L2-094 warm | CM13 - Berry bolts, Alignment, Magnet Install, 2 phase welding | CM11- Tuners CM12- LC 2 phase, Magnet lead soldering | VV028- Move 2 storage | CM09- WC Removal, to WS4 CM10- Testing cap install, WC's, Instrumentation | C75- Machine cell holders | Repair LERF testing caps |  |  | prepare C100 cooldown NL;
2018-07-04 | Wed | [13 empty] | HPR1: OOC HPR2: | [5 empty] | AES-006 120C/24h; |  |  | D1: D2: D3: D4: D5: DQW2 warm D6: D7: L2-272 warm D8:
2018-07-05 | Thu | Larry1; | C75 DL; | L2-508; L2-509; C75 DB; |  |  | C100-1; L2_505 L2-506; L2-508; |  |  |  | Flanges; | L2-503 ext rinse; L2-505 ext rinse RDTTD-02 Parts; L2 cages (x2); Flanges; | EIC5 setup |  | HPR1: OOC HPR2: RDT-6; RDTTD-02; |  | cage L2-1, L2-2; |  | IA-110 |  |  | SC-01.1 cernox; |  | D1: D2: RRR Warm D3: D4: D5: DQW-2 C4K D6: SC-08 20mG L/C1.5K/T/W D7: L2-272 pull; SC-01.1 L D8: L2-094 pull; AES-006 (3-5mG) L/C4K | CM13 - Berry bolts, 2 phase welding | CM11- Tuners CM12- LC 2 phase, Magnet lead soldering | CM09- to WS4, out of VV | CM10- Testing cap install, WC's, Instrumentation | C75- Machine cell holders | Repair LERF testing caps |  |  |  |  | CAV 8 Mag test
2018-07-06 | Fri | maint. | C75 WW; C75 DL; | L2-509; C75 DB; |  |  |  | NBTI Flanges 800C 2Hrs |  |  | Nb covers, rods & ceramics; Sample chamber; | L2-505 bolt holes; L2-506 ext rinse; |  |  | HPR1: OOC HPR2: |  | cage L2-3, L2-4; |  |  | IA-110 |  | IA-110 Sensors |  | D1: D2: RRR pull D3: D4: D5: DQW2 C2K/T D6: A3 L/C/T/W D7: SC-01.1 thermal cycles D8: AES-006 C4K | CM13 - Berry bolts, 2 phase welding | CM11- Tuners CM12- LC 2 phase, Magnet lead soldering | CM09- to WS4, out of VV | CM10- Testing cap install, WC's, Instrumentation | C75- Machine cell holders | Repair LERF testing caps |  |  |  |  | Pull U-tubes, warmup
2018-07-07 | Sat
2018-07-08 | Sun | [10 empty] | Coupler parts; |  |  | HPR2: L2-315, L2-322;
2018-07-09 | Mon | GE samples; RDT-7; | C75 WW; BB TC Degass | Demag L2 Valves; C75 DB; |  |  | L2-206 IA-320 |  | C75 DL (x6) |  |  | 506 External Rinse | EIC5 125u |  | HPR1: OOC HPR2: L2-168, L2-252; |  | cage L2-5, L2-6; |  | L2-1, L2-2 to rail; RDTTD-02 (16-008) |  |  | L2-201, L2-209, L2-210 sensors HOMs IA-110 level sensor |  | D1: D2: D3: IA-110 L/SC4K D4: D5: DQW2 C2K/T/W D6: RDT-06 L/C4K D7: SC-01.1 5mG C1.5K/T/W D8: AES-006 C2K | CM13 - 2 phase welding | CM11- Prep for storage CM12- Magnet lead soldering, add heat stations | CM09- Inspect bellows, into VV | CM10- WC's, Instrumentation, bayonet box | C75- Machine cell holders | Repair LERF testing caps |  |  |  |  | Warm-up
2018-07-10 | Tue | HW BT 21 Cu 1Cell Larry 1 | C75 WW; | C75DB BPM Chamber |  |  | L2-508; L2-509 IA-320 | SC-04, SC-07, SC-08 900C 3h |  |  | NbTi flanges (x18) | SC-04, SC-07, SC-08; VCR flex Hose; R.A. Valves x8 & HW | EIC5 125u |  | HPR1: OOC HPR2: L2-169, L2-325; |  | cage L2-7, L2-8; | EIC1 | L2-502;L2-503; L2-505; TS34-001 L2-506; TS28-008 L2-3, L2-4 to rail; |  |  |  |  | CMTF u-tubes 9AM D1: D2: D3: IA-110 C2K/T/W D4: D5: DQW2 Warm D6: RDT-06 C2K/T/W D7: SC-01.1 20mG C1.5K/T/W D8: AES-006 T/W | CM13 - 2 phase welding | CM11- Prep for storage CM12- Work Stop | CM09- Prep for storage | CM10- WC's, Instrumentation, bayonet box, JT weld | C75- Machine cell holders | Remove U-tubes from CM08 Repair LERF testing caps |  |  | Prep for c100 Cool |  | U-tubes 9am
2018-07-11 | Wed | Larry 1 | C75 WW; | L2 DS spools, C75 half cell, C75 DB | EIC5 |  | L2-508; L2-509 | SC-04, SC-07, SC-08 900C 3h | C75 DL (x6) |  | Nb Weld Prep Test Samples x6; Nb coupon samples x19 | cryo parts; MC Pipes x4 6"Tees x2 & 6" Blank; Flanges x27 & Tees x10; VCR flex hose x2; L2-508; Barrel polish bars; |  |  | HPR1: OOC HPR2: L2-251, L2-247; |  |  |  | L2-5, L2-6 to rail; | L2-502;L2-503; L2-505; TS34-001 L2-506; TS28-008 | RDT-06 120C/48hrs |  |  | D1: D2: D3: IA-110 warm/pull D4: D5: DQW2 pull, L2-201, L2-209, L2-210 L/precool D6: RDTTD-02 L/C/T/W D7: SC-01.1 warm D8: AES-006 warm | CM13 - 2 phase welding | CM11- Prep for storage CM12- Magnet lead soldering, add heat stations | CM09- Prep for storage | CM08- Prep for shipping CM10- WC's, Instrumentation, bayonet box, JT weld | C75- Machine cell holders | Remove CM08 from CMTF Repair LERF testing caps Build FL04 manifold |  |  | 1L07 WG install |  | CM08 out
2018-07-12 | Thu | C75 Endgroups GE Samples | BB-Regen C75 WW; | L2 Single cell SSC01, L2 spools, C75 DB |  |  | L2-509 EIC5 | Maint. |  | SC-04, SC-07, SC-08 | Nb covers 15u; | IA-110 HW; L2-509;L2 cover plate & flange; |  | SC-04, SC-07, SC-08 setup | HPR1: OOC HPR2: IA-016 |  |  | RDTTD02 dis | LSFC-12 (16-003); L2-7, L2-8 to rail; | L2-502; L2-503; L2-505; TS34-001 | RDT-06 120C/48hrs | L2-506 HOMs & sensors |  | D1: D2: Hall D level sensor D3: D4: D5: L2-201, L2-209, L2-210 W --> 100K/C2K D6: D7: SC-01.1 pull D8: AES-006 pull, L2-506 Load | CM13 - 2 phase welding, CWI Inspection | CM11- Prep for storage CM12- Magnet lead soldering, add heat stations | CM09- Prep for storage | CM08- LC Ins vac CM10- WC's, Instrumentation, bayonet box, JT weld | C75- Machine cell holders | Repair LERF testing caps Build FL04 manifold |  |  | Cool Down to Monday 1L07 WG install |  | SSA5-SSA8 Swap
2018-07-13 |  | RDT 7 | C75 WW | L2-212 C75 DB |  |  | RDT-TD02 L2-211; C100-1 | Maint.(am); |  |  | weld samples 15u; | EIC5 degrease; SC-01 Ext rinse; RDTTD-2 HW; Cage parts; |  | SC-04, SC-07, SC-08 50u unmasked cathode | HPR1: OOC HPR2: IA-016; RDTTD-02 |  | IA-016 |  | L2-508 (28-007) | LSFC-12 | RDT-06 120C/48hrs | L2-502; L2-503; L2-505; LSFC-12 |  | D1: D2: D3: LSF1-2 load; D4: D5: L2-201, L2-209, L2-210 T/W D6: LSFC-12 L/C4K/T D7: D8: L2-506 C4K | CM13 - 2 phase welding, CWI Inspection | CM11- Prep for storage CM12- Magnet lead soldering, add heat stations | CM09- Prep for storage | CM08- LC Ins vac CM10- RF Waveguide/MC line Instrumentation, bayonet box, JT weld | C75- Machine cell holders | Repair LERF testing caps Build FL04 manifold |  |  | 1L07 WG install
2018-07-14 | Sat
2018-07-15 | Sun
2018-07-16 | Mon | RDT 7 | C75 WW | L2 206, L2 207, C75 DB |  |  | L2-206; | maint EIC5 800C 3h |  | SC-04, SC-07, SC-08 | CERN Cu (x4) acetone soak Nb samples 50u; Nb Sample Chamber & covers 5u; | Al gaskets; LSF5-1; | RDT-2 setup |  | HPR1: OOC HPR2: |  | TS-28-001 maint; |  | EZ_ssc_01 IA-016; RDTTD-02 | L2-508; EZ_ssc_01; J1.3-14 bag; |  | L2-508 sensors; L2-502; L2-503; L2-505; HOMs sensors |  | D1: D2: RRR L/C4K D3: LSF1-2 L/C/TW D4: D5: L2-201, L2-209, L2-210 pull, L2-502, L2-503, L2-505 L/precool/W --> 100K/C4K D6: LSFC-12 C2K/T/W D7: L2-508 L D8: L2-506 C2K/T/W | CM13 - 2 phase welding, CWI Inspection | CM11- Prep for storage CM12- Magnet lead soldering, add heat stations | CM09- Prep for storage | CM08- LC Ins vac CM10- RF Waveguide/MC line Instrumentation, bayonet box | C75- Travelers, FL04 Support | Repair LERF testing caps Build FL04 manifold Cooldown 1L22,23,24 |  |  | 3x C100 Cool Down |  | SSA5 Check-out
2018-07-17 | Tue | maint-Sciaky | C75WW Travelers | L2-208 | SC-04, SC-07, SC-08 pressure test |  | RDT-13 probe cal C100-1; H2 probe cal; | EIC,maint | CERN Cu (x4) CBP; |  | CERN Cu (x4) Cu BCP; Nb samples 15u; | C75 manifold (am); 211 ext rinse; LSF5-1 parts; Al plates; T/S Bellows; RDT-13; SC-04, SC-07, SC-08; H2; Chamber; | RDT-2 50u + 50u | RDT-7 setup | HPR1: OOC HPR2: LSF5-1 RDTTD-02 |  | TS-28-001 maint; |  |  | IA-016; RDTTD-02 (16-008); J1.3-14 bag; |  | EZ_ssc_01; IA-016; |  | D1: D2: RRR T/W D3: LSF1-2 test 1.8K/W D4: D5: L2-502, L2-503, L2-505 C2K D6: RDT-06 L/C/T/W D7: L2-508 C4K D8: L2-506 warm | CM13 - 2 phase welding, CWI Inspection, LC | CM11- Prep for storage CM12- Magnet lead soldering, add heat stations | CM09- Prep for storage | CM08- LC Ins vac CM10- RF Waveguide/MC line Instrumentation, LC Process piping RT JT Piping 5pm-8, Area will be closed off!!! | C75- Travelers, FL04 Support | Repair LERF testing caps |  |  | 2x C100 Cool Down 1L25,26 Cool Down |  | SSA5Down | SS
2018-07-18 | Wed | maint-Sciaky | C75 DL | L2 Mag Shields; C75 DB; L2 probes; | SC-04, SC-07, SC-08 pressure test |  | EIC5 probe cal; C100-1; | SC-04, SC-07 SC-08 800C 3h 3n60 | CERN Cu (x4) CBP |  |  | RDT-13 HW; RDT-7; H2 HW; |  | RDT-7 20u | HPR1: OOC HPR2:H2 RDT-13; |  | TS-28-001 maint; |  | LSF5-1; RDTTD-02 (TS16-008); | J1.3-14; |  |  |  | D1: PD coil L/C4K/W D2: RRR L/C D3: LSF1-2 warm/pull D4: D5: L2-502, L2-503, L2-505 C2K/T/W D6: LSFC-12 L/SC2K/T/W D7: L2-508 warm D8: L2-506 pull, EZ_ssc_01 L/thermal cycle 5mG | CM13 - 2 phase LC | CM11- Prep for storage CM12- Magnet lead soldering | CM09- Prep for storage | CM08- LC Ins vac CM10- MC line LC, Instrumentation, LC Process piping **Successful RT** | C75- Travelers, FL04 Support | Repair LERF testing caps
2018-07-19 | Thu | Benchmark Cu-Rings | C75 DL | L2 Mag Shields; C75 Endgroup |  |  | C100-1; L2-206; | SC-04, SC-07, SC-08 800C 3h 3n60 | C75 DL (x3); CERN Cu (x4) CBP |  |  | L2-521 206 ext rinse; BPM Lollipops; Cu Cavity; Al drum; BPM parts; |  |  | HPR1: OOC HPR2: |  | TS-28-001 maint; |  | RDT-13; C75 DL; H2 (16-001); J1.3-14 Rollout (10am) | H2; LSF5-1 EZ_ssc_01 (Bolts) |  |  |  | D1: PD coil C4K/T/W D2: RRR T/W D3: IA-016 L/SC4K/T/W D4: D5: L2-502, L2-503, L2-505 warm D6: RDTTD-02 L/C/T/W D7: L2-508 warm D8: EZ_ssc_01 W/P | CM13 - 2 phase LC | CM11- Prep for storage CM12- Magnet lead soldering, add heat stations | CM09- Prep for storage, to WS6? | CM08- LC Ins vac CM10- MC line LC, Instrumentation, LC Process piping, Tune WC's | C75- Travelers, FL04 Support | Repair LERF testing caps
2018-07-20 | Fri | Manit-Cryopump-regen | C75 DL | L2 Mag Shields; C75 endgroups; EIC5 probes; |  |  | L2-207; L2-208; L2-212; | SC-04, SC-07, SC-08; samples RDT-7 800C 3H | CERN Cu (x4) CBP |  | C75 DL (x9), Beam tubes (x8) | L2-527 207 ext rinse; Beam Tubes (x8) |  | SC-04, SC-07, SC-08 setup | HPR1: OOC HPR2: |  | TS-28-001 maint; |  | L2-521; | RDT-13; | RDT-13 120C 24h RDTTD-02 120C 48h |  |  | D1: PD coil warm up D2: RRR hold D3: IA-016 T/W D4: D5: L2-502, L2-503, L2-505 warm D6: D7: L2-508 warm D8: EZ_ssc_01 L/C1.5K/T/W5mG | CM13 - 2 phase LC CM14 - | CM11- Prep for storage, install tuners CM12- Magnet lead torquing, heat stations | CM09- WS6 CM11- VV | CM08- LC Ins vac CM10- MC line LC, Tune WC's, HOM's, Ins Vac | C75- Travelers, FL04 Support | Repair LERF testing caps Shipping Trailer, unload 2
2018-07-21 | Sat | [6 empty] | RDT-7 800C 3H | [12 empty] | RDT-13 120C 24h RDTTD-02 120C 48h
2018-07-22 | Sun | [6 empty] | RDT-7 800C 3H | [12 empty] | RDT-13 120C 24h RDTTD-02 120C 48h
2018-07-23 | Mon | Cu weld samples, |  | mag shields C75 DB | EZ_ssc_01 |  | IA-114 | samples RDT-7 800C 3H | C100-1 H2 & HW |  | H2 & HW; Nb rods samples x2; Nb samples x16; Mo bolts x2; plug x1; Nb rods x3 & plate x1; | 212 ext rinse; 208 ext rinse; BLA bodies & absorbers (x2); H2 & HW; Test stand parts; |  | SC-04, SC-07, SC-08 5u unmasked cathode | HPR1: OOC HPR2: SC-08, RDT-2 |  |  | EZ_ssc_01 | C75 DL | L2-521; C75 DL |  | L2-521 HOMs & sensors |  | D1: D2: RRR C4K D3: IA-016 pull; LSF5-1 L/C2K/T D4: D5: L2-502, L2-503, L2-505 pull; DQW2 load; D6: RDT-13 L/C2K/T/W D7: L2-508 pull; replace o-rings D8: EZ_ssc_01 Pull; L2-508 L/C4K | CM13 - 2 phase LC CM14 - RF Measurements, berry bolts | CM11- Prep for storage, install tuners CM12- heat stations, prep for alignement | CM11- VV to WS4 | CM08- LC Ins vac CM10- Tune WC's, Ins Vac LC | C75- Travelers, FL04 Support | Repair LERF testing caps Shipping Trailer repair, unload CM02 |  |  | 1l-08,07 Cool Down WG Lerf Mod.
2018-07-24 | Tue | CAV-Nb3 Beam tubes (x8), | BLA bodies & absorbers (x2) C75 DL | C75 DB |  |  | IA-110, IA-016 FF & probes; |  | C100-1 RDT-7 |  |  | IA-320 L2-527 wipe EZ_ssc_01 parts RFD2 L2-208; RFD; IA-320 parts; Turbo parts; SC-08 parts; RFD2 |  | EZ_ssc_01 Setup | HPR1: OOC HPR2: H2; LSFC-12 |  |  | IA-016 | L2-527 (28-007); H2 (TS 16-001), RDT-2 | L2-207 L2-211 L2-509(TS 34-002); L2-206 (TS-28-008) |  |  |  | D1: C75 DL L/C/T/W D2: RRR C4K/T D3: LSF5-1 C2K/T/W D4: D5: DQW2 hold D6: RDTTD-02 L/C4K/T/W D7: L2-521 L/C4K (5mG) D8: L2-508 C2K/T/W | CM13 - 2 phase LC CM14 - RF Measurements, berry bolts | CM11- Prep for storage, 50K shields CM12- Alignment | CM11- Move Cold Mass | CM08- Remove Testing caps, configure beampipes CM10- Ins Vac LC, into CMTF | C75- Travelers, FL04 Support | Repair LERF testing caps Shipping Trailer repair Modify Shipping Caps |  |  | 1l-08,07 4K CHL-1 Cooldown
2018-07-25 | Wed | CAV-Nb3 Beam tubes (x8), Nb3 disks DD | C75 DB polish BLA Absorbers (x2) | IA-110, IA-114, C75 endcell |  |  | IA-016 FF; L2-217; | BLA Absorbers (x2) | EIC5 |  | SC-08 test flanges; | IA-320 Parts; LSFC-12 parts; RA valves x5; BLA HW; RDL-2 parts; |  | EZ_ssc_01 3u | HPR1: OOC HPR2: IA-320; EZ_ssc_01 |  | IA-320 |  | LSFC-12; SC-08 | RDT-2; H2 L2-527 (TS 28-007); |  | L2-207 L2-211 L2-509 (TS 34-002); L2-206 (TS-28-008) |  | D1: C75 pull; PD coil L/C4K/T D2: RRR W/T D3: LSF5-1 warm D4: D5: DQW2 C4K D6: D7: L2-521 C2K(1.6,1.8K)/T/W (5mG) D8: L2-508 warm | CM13 - 2 phase LC CM14 - berry bolts | CM11- Prep for storage, 50K shields CM12- Alignment | CM11- Move Cold Mass | CM08- Remove Testing caps, configure beampipes CM10- in CMTF, prep 4 cooldown | C75- Travelers, FL04 Support | Repair LERF testing caps Shipping Trailer repair, out of test lab Modify Shipping Caps
2018-07-26 | Thu |  | C75 DB polish C75 end groups; C75 DL | IA-110, IA-114, C75 DB |  |  | IA-110, L2-217; L2-218 | BLA Absorbers (x2) | Maint 36 Lap |  |  | RFD2 parts; RFD2Int/ext rinse; |  | RDT-7 Set-up | HPR1: OOC HPR2: RDL-02; RFD2 |  |  |  | EZ_ssc_01; IA-320; | LSFC-12; SC-08; | LSF5-1 120C 48h | SC-08 sensors; |  | D1: PD coil P/L/C/T/W D2: RRR C4K D3: LSF5-1 pull; D4: D5: DQW2 C2K/T/W D6: SC-08 L/C2K/T/W (5mG) D7: L2-521 warm D8: L2-508 pull; | CM13 - 2 phase LC CM14 - berry bolts | CM12- Alignment CM13- UCM from BC | CM11- 50K shields, into VV | CM08- Remove Testing caps, configure beampipes CM10- in CMTF, prep 4 cooldown, demag CM | C75- Travelers, FL04 Support | Repair LERF testing caps (1 to go) Modify Shipping Caps (1 to go)
2018-07-27 | Fri | C75 stiffening rings to endgroups; Press 1/2 Cells CAV-Nb3 | C75 DB polish; BLA Absorbers (x2) C75 DL | IA-110, IA-114, L2-217; |  |  | IA-114 L2-218 | BLA Absorbers (x2); clean up; | Maint 36" RDT-02 RDT-10 |  | C75 stiffening rings BCP (x8); Half cell exp. (GE); Nb plates x2 & cyl; |  |  | Repair | HPR1: OOC HPR2: |  |  |  | RFD2; RDL-2 (TS 16-001) | IA-320; EZ_ssc_01 | LSF5-1 120C 48h | L2-207 L2-211 L2-509 (TS 34-002); L2-206 (TS-28-008) IA-320; EZ_ssc_01 sensors |  | CMTF u-tubes 9AM D1: PD coil test C4K/T/W D2: RRR W/T D3: D4: D5: DQW2 Test D6: LSFC-12 L/C4K/T/W D7: L2-521 pull; torque; L/C4K (20mG) D8: EZ_ssc_01 L/C2K/T/W/ (20mG) | CM13 - 2 phase LC, UCM QC CM14 - berry bolts, SPQA install | CM12- Alignment/Tuners | CM11- Into VV, Swap CM11 with CM04? CM04- Prep for rework | CM08- Remove Testing caps, configure beampipes, install tiedowns CM10- u-tubes 9am, cooldown | C75- Travelers, FL04 Support, Procurements | Repair LERF testing caps (1 to go) R&D Weld, hom wg Modify Shipping Caps (1 to go) |  |  | Pump Down PM 1l-07,23 Heaters |  | Utubes (9:00am)
2018-07-28 | Sat | [6 empty] | clean up; | [12 empty] | LSF5-1 120C 48h
2018-07-29 | Sun | [6 empty] | clean up;
2018-07-30 | Mon | Vac | C75 DL; C75 DB; Press 1/2 Cell | C75 DL flanges; C75 DB; |  |  | AES-07 FF & probes; RDT-10 IA-114; | CR samples; | CBP Maint. |  |  | BLA parts; RDT-7; RFD2 damper rinse); L2-217 Ext rinse; Short rail; Nb sample; C100-1 FPC clean; |  | RDT-7 30µ | HPR1: OOC HPR2: |  | C100-1 cage; | [6 empty] | D1: D2: D3: LSF5-1 L/C2K/T D4: D5: DQW2 pull, L2-207, L2-211, L2-509 Load D6: RDL-02 Load D7: L2-521 C2K(1.6,1.8K)/T/W (20mG) D8: EZ_ssc_01 pull, L2-527 L/C4K (20 mG) | CM13 - UCM QC/Demag, MLI/Mag shields CM14 - berry bolts, SPQA install | CM12- Tuners | CM11- Swap CM11 with CM04 CM04- Prep for rework | CM08- Remove Testing caps, configure beampipes, install tiedowns CM10- Cooldown | C75- Travelers, FL04 Support | Repair LERF testing caps (1 to go) Modify Shipping Caps (1 to go) |  |  | 1l-23 Comm. 1l-07 LERF Cool? |  | Pump Down Tune Cav.
2018-07-31 | Tue | Vac | C75 DL; | C75 DL flanges; C75 DB; |  |  | IA-110 FP; | CR Samples; |  |  |  | RDT-10; C100-1; |  | EZ_ssc_01 Setup | HPR1: OOC HPR2: RDT-7; SC-07; |  |  |  | RFD2; L2-217 D5; RDT-7 (TS16-008); |  |  |  |  | D1: C75 DL L/C/T/W D2: D3: LSF5-1 hold D4: D5: L2-207, L2-211, L2-509 hold D6: RDL-02 C4K/T/W D7: L2-521 warm D8: L2-527 C1.6K/T (D7-->D8) | CM13 - UCM QC/Demag, MLI/Mag shields CM14 - Alignment Crew | CM12- Tuners | CM11- Swap CM11 with CM04 CM04- Prep for rework | CM08- Remove Testing caps, configure beampipes, install tiedowns | C75- Travelers, FL04 Support | Repair LERF testing caps (1 to go) Modify Shipping Caps (1 to go)
2018-08-01 | Wed | Vac | C75 DL; Press | L2 UCM; C75 DB; C75 Flanges |  |  | IA-114, | maint; | H2 & hw; IA-110, CERN Cu media set-up CBP; |  | SC-07 flanges; RDT-10 BCP 5µ; Nb sample chamber; T couple x7; | EZ_ssc_01 Cryo Vac HW; Furnace HW; Chamber Housing; Threaded rod x4; Cryo fastener kits; |  | EZ_ssc_01 3u | HPR1: OOC HPR2: RDT-10; EZ_ssc_01; |  |  |  | SC-07 (TS16-003); L2-208, L2-212, L2-217 D5; | RDT-7; L2-208, L2-212, L2-217; |  |  |  | D1: D2: D3: LSF5-1 C2K/T/W (D8 --> D3) D4: D5: L2-207, L2-211, L2-509 hold D6: RDT-07 L/C/T/W D7: L2-521pull; L2-508 L/C4K D8: L2-527 warm | CM13 - UCM QC/Demag, MLI/Mag shields CM14 - Alignment Crew | CM12- Tuners | CM11- Swap CM11 with CM04 CM04- Prep for rework | CM08- Remove Testing caps, configure beampipes, install tiedowns | C75- Travelers, FL04 Support | Repair LERF testing caps (1 to go) Modify Shipping Caps (1 to go) |  |  | 1l-23,07 comm. C100 Maint |  | Testing
2018-08-02 | Thu | Vac | C75 DL; C75 DB | L2-UCM; L2-218; C75 DB; |  |  | C100-1; | maint; | IA-110; CERN Cu media set-up CBP; |  | H2 & hw; LSFC-09;Nb sample chamber & 2 plates; RDT-7 Nitric soak; T couples x6; | TWIN1 HW; C100-1; Cryo assembly kits x20; BLA brackets; |  | RDT-02 setup | HPR1: OOC HPR2: H2; |  | TS28-001; |  | RDT-10 (TS16-008); EZ_ssc_01; | SC-07; RFD2?; |  | SC-07 sensors; |  | D1: D2: D3: LSF5-1 C2K/T/W D4: D5: L2-207, L2-211, L2-509 precool D6: SC-07 L/C1.6K/T/W D7: L2-508 C2K/HOM/T/W D8: L2-527 C4K (5mG) | CM13 - UCM QC/Demag, Mag shields CM14 - Alignment Crew Magnet, 2 phase piping | CM12- hold | CM04- Prep for rework, procedure generation | CM08- Remove Testing caps, configure beampipes, install tiedowns | C75- Travelers, FL04 Support | Repair LERF testing caps (1 to go), LC Modify Shipping Caps (1 to go) Fab protection covers for CM ends
2018-08-03 | Fri | Vac | C75 DL; BLA (x2) | L2 -Probes; C75 DB; L2 mag shields |  |  | L2-220; AES-07; | BLA (x2) | IA-110; IA-114; |  | RDT-02 flanges; C75 DB; C75 stiff rings; | AES-07; RDT-02; C100-1 HW; L2-218 ext rinse; SC-04 HW; C75 EG (x2); |  | RDT-02 30u | HPR1: OOC HPR2: C100-1; RDT-07; |  | TS28-001; | C75 DL; L2-521; | H2; C75 DL; BPM Sub-Assy15; | RDT-10; EZ_ssc_01; | RFD2 120C 12h | EZ_ssc_01 sensors; |  | D1: D2: D3: LSF5-1 warm; D4: D5: L2-207, L2-211, L2-509 W100K/C4K D6: RDT-10 L/C/T/W D7: L2-508 w/pull, EZ_ssc_01 L/C4K; D8: L2-527 C1.6K/T/W | CM13 - UCM QC/Demag/Alignment Crew, Mag shields CM14 - 2 phase piping, instrumentation | CM12- Tuners | CM04- Prep for rework, procedure generation | CM08- re-configure beampipes, install tiedowns | C75- Travelers, FL04 Support | Repair LERF testing caps (1 to go), LC Modify Shipping Caps (1 to go) Fab protection covers for CM ends
2018-08-04 | Sat | [19 empty] | RFD2 120C 12h |  |  | D7: EZ_ssc_01 C2K/T/W
2018-08-05 | Sun | [19 empty] | RFD2 120C 12h
2018-08-06 | Mon | BT C75 test DB (x2); C75 stiff rings (x2); | BLA (x2); C75 DB; | L2-219; |  |  | AES-07; L2-219; | BLA (x2) |  |  | SC-04 NbTi flanges; | Furnace HW; SC-04 HW; |  |  | HPR1: OOC HPR2: SC-04; KEK-R5; C100-1; |  | C100-1; |  | L2-218 D7/8; | C75 DL |  | L2-208, L2-212, L2-217 D5 sensors & HOMs |  | D1: D2: D3: LSF5-1 pull; IA-320 L/SC/T/ D4: D5: L2-207, L2-211, L2-509 C2K/T D6: D7: EZ_ssc_01 warm; D8: L2-527 pull; L2-206 L/C4K | CM13 - UCM QC/Demag/Alignment Crew, Mag shields CM14 - 2 phase piping, instrumentation | CM12- Tuners | CM04- Prep for rework, procedure generation | CM08- re-configure beampipes, install tiedowns | C75- Travelers, FL04 Support | Repair LERF testing caps (1 to go), LC Modify Shipping Caps (1 to go) Fab protection covers for CM ends Dual Coax window LC
2018-08-07 | Tue |  | BLA (x2); BLA (x3); C75 DB; | L2 -Probes; C75 EG (x1); C75 DB (x1) |  |  | L2-515; L2-518; |  | IA-110; IA-114; |  | C75 DB (x2) 30u; HW Coax beampipe 20u; Nb sample 1:1:2 BCP; Nb sample chamber & Nb covers x2; | BLA body (x3); BLA abs (x3); MB cavity hw; |  |  | HPR1: OOC HPR2: Twin1; |  | TS16-xyz?; TS28-001 |  | C100-1 D7/8; SC-04 TS28-004; KEK-R5 TS16-001; BPM Sub; | KEK-R5; |  |  |  | CMTF Fast Cooldown CMTF pumpdown; D1: C75 DL Load D2: D3: IA-320 W/SC/C4K D4: D5: L2-207, L2-211, L2-509 D5-->D8/W D6: D7: EZ_ssc_01 pull; D8: L2-206 C2K/T/W | CM13 - UCM Demag, Fastener verification CM14 - 2 phase piping, instrumentation | CM12- Tuners | CM04- Beam line reconfig. | CM08- re-configure beampipes, fastener rework | C75- Travelers, FL04 Support | Modify Shipping Caps (1 to go) Fab protection covers for CM ends |  |  | Machine Down, CHL transformer |  | Fast Cool Down Q0
2018-08-08 | Wed |  | C75 DB Polish; | L2-515; C75 DB; Dual Coax window; IA-110; L2-Probes; |  |  | L2-515; | maint; |  | EIC5 | Nb sample chamber & Nb covers x2; Nb foils x22; | L2-219 ext rinse; RDT-07; Beam tubes x5 & Nb rings x4; BLA Absorber boxes; Injector components x2; Tubing, V block clamp, Pirani gauge & cable; BLA restraint bars; LSFC1-3 hw; |  | EIC5 Set-Up | HPR1: OOC HPR2: RDT-07; |  | TS28-001 |  | TWIN1 cart; | L2-218; |  | L2-218 sensors and HOMs; KEK-R5 sensors; |  | D1: C75 DL C/T D2: D3: IA-320 T4K/C2K/T/W D4: D5: L2-207, L2-211, L2-509 pull; L2-208, L2-212, L2-217 load D6: KEK-R5 L/C/T/W D7: L2-218 L/C4K D8: L2-206 warm | CM13 - Fastener verification, CS 2 UCM CM14 - 2 phase piping | CM12- Tuners | CM04- Beam line reconfig. | CM08- re-configure beampipes, fastener rework, JLAB Alignment | C75- Travelers, FL04 Support | Modify Shipping Caps (1 to go) Fab protection covers for CM ends Lerf Support 2L-26 Support
2018-08-09 | Thu |  | C75 DB Polish; | C75 EG; L2-518; L2 HOM probes; |  |  | L2-518; L2-520 | maint; | IA-114; |  | RDT-10 flanges nitric; C75 DB (x2) 30u; Beam tubes x5 & Nb rings x4; Cu cavity; | RDT-10; EIC5; Nb covers & Mo hw; Antennas x3; HW for clean room; |  | EIC5 30um | HPR1: OOC HPR2: |  | TS16-xyz; |  | RDT-07 TS16-008; | SC-04 |  |  |  | Pete OUT PM; D1: D2: D3: IA-320 pull; SC-04 L/C1.6K/T/W D4: D5: L2-208, L2-212, L2-217 precool/W100K D6: KEK-R5 C/T/W D7: L2-218 C2K/T/W D8: L2-206 pull; C100-1 L | CM13 - Complete Fastener Work CM14 - 2 phase piping | CM12- Stand Down | CM04- Beam line reconfig. Remove VV | CM08- JLAB Alignment | C75- Travelers, FL04 Support | Modify Shipping Caps (1 to go) Fab protection covers for CM ends Lerf Welding Support |  |  | Pump Down North Linac
2018-08-10 | Fri | C75 FPC/Rings | C75 DB Polish; 1010 Anneal | L2-spool; |  |  | L2-520 CM08 HOM | 1050C 6h; | IA-114, |  |  | IA-016; IA-016 HW; |  | acid change | HPR1: OOC HPR2: A3; IA-016; RDT-10; |  | TS16-xyz; | IA-320 | TWIN1 D3; A3; | RDT-07; A3; |  | RDT-07 sensors; |  | D1: D2: D3: SC-04 warm D4: D5: L2-208, L2-212, L2-217 C4K D6: RDT-07 L/SC4K/T/hold D7: L2-218 warm; D8: C100-1 C2K/T/W | CM13 - Complete Fastener Work CM14 - 2 phase piping | CM12- Stand Down | CM04- Beam line reconfig. Remove VV | CM08- JLAB Alignment | C75- Travelers, FL04 Support | Modify Shipping Caps (1 to go) Fab protection covers for CM ends
2018-08-11 | Sat
2018-08-12 | Sun
2018-08-13 | Mon |  |  | L2-170; C75 EG; |  |  | L2-220; L2-170; |  | IA-114; IA-110 BT Flange; |  | CERN Cu copper-brite; Nb cover & Clamps; Nb Samples x4; HW Coax weld prep; | HW Coax; LSF1-2 HW; Lollipops; BLA Spacers & Bolts; |  | HF spike; | HPR1: OOC HPR2: LSF1-2; IA-016 |  | IA-016 | L2-521, L2-527 prep for ship; | LSFC-09 TS16-003; | LSFC-09; TWIN1; | TWIN1 120C/24h; | RFD2 sensors; | L2-206; | D1: C75 DL pull; D2: D3: SC-04 pull; D4: D5: L2-208, L2-212, L2-217 C2K/T/W D6: D7: L2-218 pull; D8: C100-1 pull; | CM13 - Idle CM14 - 2 phase piping | CM12- Stand Down | CM04- Remove shields Fastener work, prep for BPM Hardware replacement Wednesday | CM08- Close up for storage, Retune HOM 8A | C75- Travelers | Fab protection covers for CM ends 1L07 Window work
2018-08-14 | Tue |  | C75 DB | L2-520; L2 hom probes; |  |  | L2-224 |  | C50 pair parts; |  | C75 DB (x2) 30u; LSFC-12 Nb removal; LSFC-08 & Unnamed cavity; NB samples -HCL soak; | L2 FPC (x2); CM-04 BPM HW; L2-515; |  | SC-04, SC-07, SC-08 setup; | HPR1: OOC HPR2: |  | setup rail/lollipops; |  | L2-219 D7/8; IA-016 D3; LSF1-2 TS16-008; |  | TWIN1 120C/24h; | LSFC-09 sensors | L2-218; | CMTF multi-cavity run D1: D2: RRR L/C4K D3: D4: D5: L2-208, L2-212, L2-217 warm D6: LSFC-09 L/SC4K; D7: D8: | CM13 - Idle CM14 - 2 phase piping | CM12- Stand Down | CM04- Remove shields Fastener work, prep for BPM Hardware replacement Wednesday | CM08- Close up for storage, Retune HOM 8A | C75- Travelers | Fab protection covers for CM ends 1L07 Window work |  |  | 1L07-3 blanked off WG; Controlled access this morning; |  | multi-cavity run
2018-08-15 | Wed |  | C75 Travelers | C75 EG; IA-110; IA-114; |  |  | L2-228; L2-231; |  | C50 pair parts; |  | 1.3 GHz Conflat tophat; | L2-170 wipe; SC-04, SC-07, SC-08; Test stand parts; Couplers x2; H2 cavity; H2 HW; Coupler blanks x4; |  | SC-04, SC-07, SC-08 5u; | HPR1: OOC HPR2: |  | J04 BPM HW swap; |  | L2-515 D7/8; | IA-016; L2-FPC; LSF1-2 TS16-008; L2-219; | TWIN1 120C/24h; | IA-016 sensors; TWIN1; |  | D1: D2: RRR W/T D3: IA-016 L/SC4K/T D4: D5: L2-208, L2-212, L2-217 pull; RFD2 L/C2K; D6: LSFC-09 C1.6K/T/W D7: D8: | CM13 - Idle CM14 - 2 phase piping | CM12- Stand Down | CM04-Fastener work, BPM Hardware replacement | CM08- Retune HOM 8A | C75- Travelers, Inventory | Fab protection covers for CM ends FNAL Visitors |  |  | RF Recovery; NL LEM 1050MV; |  | Cav 1 FE studies; Impulse response testing;
2018-08-16 | Thu |  | C75 HC EG (x2) polish; | C75 EG; Physics stovepipe; |  |  | L2-213 | clean-up run |  |  | C50 pair parts; SC HC (x5) 15u; C75 HC EG (x2) 30u; Nb sample chamber & components #1; | L2_520 wipe; C75-000; RTD-10; Nb samble chamber & components; Furnace valve & HW; SC-04 HW; |  |  | HPR1: OOC HPR2: SC-04; H2; RDT-10; |  |  |  | L2-FPC to cavity; | L2-515; |  | L2-219 sensors & HOMS; |  | D1: C75 DL L D2: RRR C4K; D3: IA-016 T/C2K/T/W D4: D5: RFD2 T/W; D6: LSF1-2 L/C1.8K/T; D7: D8: L2-219 L/C4K | CM13 - Idle CM14 - 2 phase piping | CM12- Stand Down | CM04-Fastener work, BPM Leak Check | CM08- Retune HOM 8A | C75- Travelers, Inventory | Fab protection covers for CM ends FNAL Visitors |  |  | SL LEM |  | Rad detector studies;
2018-08-17 | Fri |  |  | Physics stovepipe; |  |  |  | clean-up run | CERN Cu CBP; |  | Nb samble chamber & components #2; IA-110 & IA-114 BCP flanges; Nb3Sn coated sample HCL soak; nb part; Nb box; | AES-007 US; LSFC09-02 HW; IA-110; IA-114; |  |  | HPR1: OOC HPR2: C75-000; LSFC09-02 |  | C75-000 cage; | LSFC09-02 | SC-04 16-003; RDT-10 D3; H2 TS16-001; LSFC12-02; | H2; |  | L2-515 sensors & HOMS; | L2-211 fast bleed-up; | U-tubes out D1: C75 DL C4K/T/W D2: RRR T/W D3: IA-016 pull; TWIN1 L/C2K/T/W; D4: D5: RFD2 warm D6: LSF1-2 test/w D7: L2-515 L/C4K; D8: L2-219 C2K/T/W; | CM13 - Idle CM14 - 2 phase piping | CM12- Stand Down | CM04-Fastener work, Cavity 1 tuner rework, BPM Leak Check | CM08- Retune HOM 8A | C75- Travelers, Inventory | Fab protection covers for CM ends 2L07 vacuum FNAL Visitors U-Tube at 9 AM |  |  | Energy recovery; 2L07 tuners; |  | Warm-up; U-tube;
2018-08-18 | Sat | [7 empty] | CERN Cu CBP;
2018-08-19 | Sun | [7 empty] | CERN Cu CBP;
2018-08-20 | Mon | C75 test weld; HW Coax beampipe; SC BT (x4); | C75 HC EG (x2) polish; | Physics stovepipe; L2-224; L2-228; |  |  |  | valve maint; | CERN Cu CBP; |  | A3 flanges; | A3 HW; AES-07 HW; |  | L2-211 setup; | HPR1: OOC HPR2: AES-007 A3 |  | TS16-008 new turbo; |  | C75 DL; | SC-04; C75 DL; H2; RDT-10; |  | SC-04 sensors; RDT-10 sensors; |  | U-tubes; D1: C75 DL pull; D2: RRR warm D3: TWIN1 pull; D4: D5: RFD2 pull; D6: H2 L/C1.6K/T/W D7: L2-515 C2K/T/W; D8: L2-219 pull; | CM13 - CS under UCM CM14 - 2 phase piping | CM12- Tuners | CM04-Fastener work, Cavity 1 tuner rework, BPM Leak Check | CM08- Retune HOM 8A | C75- Travelers, Inventory | Fab protection covers for CM ends 2L07 vacuum U-Tube at 9 AM |  |  | 2L07 tuner recovery; |  | U-tubes; WARM!
2018-08-21 | Tue | HW Coax Beampipe; SC BT (x4); | C75 HC EG (x2) polish; | C75 EG; L2-231; L2-220; |  |  | C50 Tophats |  |  |  | Nb & Mo parts; HF sample; | L2-228 wipe; L2-224 wipe; L2-211 with new HV plugs; L2-211 HW; |  | L2-211 3u; | HPR1: OOC HPR2: SC-07; AES-007; |  | AES-007; |  | L2-224, L2-228, D5; L2-170 D7/8; LSFC09-02 TS16-008; A3 TS16-001; |  |  |  |  | EDM maint a.m.; D1: D2: RRR L/C4K D3: RDT-10 L/SC4K D4: D5: D6: SC-04 L/C1.6K/T/W D7: L2-515 warm/pull D8: | CM13 - Unite CS/UCM CM14 - 2 phase piping LC | CM12- Tuners | CM04-Fastener work, Cavity 1 tuner shimming, Complete beam pipe work | CM08- Retune HOM 8A | C75- Travelers, Inventory | Fab protection covers for CM ends |  |  | 2L07 recovery |  | Warm-up
2018-08-22 | Wed | SC HC (x5); | C75 EG polishing; | L2-220 degauss; L2-213; L2-227; |  |  |  | maint | CERN Cu CBP; |  |  | L2-231 wipe; BLA housing & absorber (x3) a.m.; BLA fasteners; J1 wipe; SC-07 hw; |  |  | HPR1: OOC HPR2: L2-211 |  | TS16-xyz; |  | L2-224, L2-228, L2-231 D5; SC-07 TS16-003; AES-007 D7/8; | A3 leaks; L2-170; LSFC09-02; |  |  |  | D1: C75 DL L/C/T/W; D2: RRR warm D3: RDT-10 C2K/T/W; D4: maint/C4K D5: D6: D7: D8: | CM13 - Unite CS to UCM, Install extended tuner Cav 1 CM14 - 2 phase piping LC | CM12- Tuners | CM04-Fastener work, Complete Cold Mass Mods | CM08- Retune HOM 8A | C75- Travelers, Inventory | Fab protection covers for CM ends LERF Coils/Bellows LCLS HV Mag Shield field mapping |  |  | 2L07 cryo cycle; 1L07 operating;
2018-08-23 | Thu | C75 DB (x2); | BLA absorber (x3) load; | C75 Mag Shields; |  |  | L2-227 | BLA housing (x3) load; |  |  | C75 HC EG (x2); PE-01; | PE-01 cavity; L2-220 ext rinse; C50 pair parts; Boxes x3; Elbow & valve; Adapter; |  |  | HPR1: OOC HPR2: H2 L2-211 |  | L2-211; TS16-xyz; | H2 bottom flange | BLA-201; BLA-200; | L2-224, L2-228, L2-231; AES-007; SC-07; |  | LSFC09-02 sensors; |  | CTF DOWN D1: D2: RRR hold D3: RDT-10 hold; D4: C4K/ warm D5: D6: LSFC09-02 L D7: D8: AES-007 L | CM13 - Install extended tuner Cav 1, Drop lollipops, 2 phase piping CM14 - 2 phase piping LC, MLI | CM12- Tuners | CM04-Finish Check List of Cold Mass Mods, Instrumentation, RF Cable verification | CM08- Retune HOM 8A | C75- Travelers, Inventory | Fab protection covers for CM ends LERF Coils/Bellows LCLS HV Mag Shield field mapping |  |  | 2L07 cryo cycle |  | pressure test
2018-08-24 | Fri | HW Coax BP to cavity; | BLA absorber (x3) 350C | C75 Mag Shields; |  |  |  | BLA housing (x3) 350C; |  |  | GE Nb parts; HW Coax BP to cavity weld prep; | L2-213 ext rinse; C75-000; C50 pair parts; Test stand hose; C50 alignment table; |  | RDTTD-01, RDT-14 setup; | HPR1: OOC HPR2: |  | TS16-xyz; |  | L2-211 D7/8; H2 TS16-001 | BLA-200; BLA-201; |  | L2-170 sensors & HOMs; L2-224, L2-228, L2-231 HOMs & sensors; SC-07 sensors; |  | D1: D2: RRR D3: RDT-10 SC2K/T/W D4: hold 4K D5: D6: LSFC09-02 SC4K/C2K/T/W; D7: L2-170 L/C4K; D8: AES-007 C2K/T/W; | CM13 - Drop lollipops, 2 phase piping CM14 - 2 phase piping LC, MLI | CM12- Tuners | CM04-Complete Cold Mass Mods, Instrumentation, RF Cable verification, Tune HOM's | CM08- Retune HOM 8A | C75- Travelers, Inventory | Fab protection covers for CM ends LERF Coils/Bellows LCLS HV Mag Shield field mapping Low PT CM10 |  |  | Beam
2018-08-25 | Sat |  | BLA absorber (x3) 350C |  |  |  |  | BLA housing (x3) 350C;
2018-08-26 | Sun |  | BLA absorber (x3) 350C |  |  |  |  | BLA housing (x3) 350C;
2018-08-27 | Mon | HW Coax tube & body;SC HC (x3) | BLA absorber (x3) 350C | C75 Mag Shields; C75 waveguide; |  |  |  | BLA housing (x3) 350C; PLC maint; |  |  |  | PE-01 cavity LSFC12-02 wipe; L2-227 ext rinse; J1 ext rinse; IA-110 & 114; |  | maint | HPR1: OOC HPR2: SC-08 PE-01 |  | IA-110 & 114 cage; |  | LSFC12-02 unmount; L2-220, L2-518, L2-520 D5; C75 DL; | L2-211*; C75 DL; |  | L2-211* HOMs & sensors; |  | D1: D2: RRR C4K D3: RDT-10 warm; D4: level sensor test D5: L2-224, L2-228, L2-231 L/pre-cool; D6: LSFC09-02 warm/pull; SC-07 L/C1.6K/T/W D7: L2-170 C2K/T/W D8: AES-007 warm; | CM14 -HV MLI | CM13 - Retrun Lollipops, 2 phase piping/Weld CM12- Tuners | CM04-Instrumentation, RF Cable verification, Tune HOM's | CM08- Prep for storage CM02- Prep for storage | C75- Travelers, Inventory | Fab protection covers for CM ends LERF Coils/Bellows LCLS HV Mag Shield field mapping |  |  | restoring beam to halls
2018-08-28 | Tue | HW Coax tube & body; 952MHz Cu |  | L2 Bellows; C75 WG; |  |  | J1.3-04 HOMs; | PLC Maint; | A3 flange & HW |  |  | SC-08 parts; RDTTD-01 Parts; |  | RDTTD-01, RDT-14 50u; | HPR1: OOC HPR2: PE-01; IA-110 & 114; |  | C50 pair prep; | A3; | SC-08 TS16-003; BPM -15; |  |  |  |  | D1: D2: RRR C4K D3: RDT-10 pull D4: maint D5: L2-224, L2-228, L2-231 W/C4K; D6: H2 L/C2K/T/W; D7: L2-170 warm D8: AES-007 pull; L2-211* load | CM14 -LC CS?, HV MLI/Mag Shields | CM13 - 2 phase piping/Weld CM12- Tuners | CM04-Instrumentation, RF Cable verification, Tune HOM's | CM08- Prep for storage CM02- Into shipping frame | C75- Travelers, Inventory | Fab protection covers for CM ends LERF Coils/Bellows LCLS HV Mag Shield field mapping Load CM02 into Shipping Trailer |  |  | RF recovery;
2018-08-29 | Wed | HW Coax tube & body; 952MHz Cu |  | L2 Bellows; L2 Tuner; |  |  |  | clean-up run; |  |  | A3 flange & HW Nb sample; | EIC-5 ethanol & US; A3 flange & HW; BLA hardware; CPI-LPA-079 & 080; FPC blanks x4; Flex tubes x6; Waveguide; |  |  | HPR1: OOC HPR2: RDTTD-01; IA-110 & 114; |  | IA-110 & 114; | AES-007 |  | BPM -15; SC-08; LPA-077; L2-220, L2-518, L2-520 D5; |  | SC-08 sensors; | AES-007 fast; | D1: D2: RRR C4K D3: D4: maint D5: L2-224, L2-228, L2-231 C2K/T/W4K D6: SC-08 L/C2K/T/W4K D7: L2-170 pull, D8: L2-211 C4K | CM14 -HV MLI | CM13 - 2 phase piping/Weld CM12- Tuners | CM04-Instrumentation, RF Cable verification, Tune HOM's | CM08- Prep for storage CM02- Prep for storage | C75- Travelers, Inventory | Move CM's 02,11,09 to Blue Crab Fab protection covers for CM ends LERF Coils/Bellows LCLS HV Mag Shield field mapping
2018-08-30 | Thu | HW Coax tube & body; 952MHz Cu; C75 DL; | C75 WG; | L2 Bellows; |  |  | J1.3-04 HOMs; | AES-007, 900C/3h |  |  |  | AES-006; AES-007; Beam pipe; Turbo cart parts; |  |  | HPR1: OOC HPR2: EIC-5 |  |  |  | IA-110 & 114; RDTTD-01; TS16-008; L2-213 D7/8; | LPA-079 |  | L2-220, L2-518, L2-520 D5 HOMS & sensors; |  | D1: D2: RRR W/T D3: D4: maint D5: L2-224, L2-228, L2-231 warm D6: SC-08 warm D7: D8: L2-211 warm | CM14 -HV MLI | CM13 - 2 phase piping/Weld CM12- Tuners | CM04-RadCon, Tune HOM's | CM08- Prep for storage CM02- Prep for storage | C75- Travelers, Inventory | Fab protection covers for CM ends LERF Coils/Bellows LCLS HV Mag Shield field mapping
2018-08-31 | Fri | VAC | C75 WG; | L2 Tuners; C75 WG; LCLS2 Bellows |  |  | J1.3-04 HOMs; | AES-007 900C/3h; |  |  |  | A3 parts; C75-000 HW |  |  | HPR1: OOC HPR2: LSFC-12.2 C75-000; |  |  |  |  | IA-110 & 114; RDTTD-01 LPA-080; |  |  |  | D1: D2: RRR warm/pull; D3: D4: maint D5: L2-224, L2-228, L2-231 warm D6: SC-08 warm D7: D8: L2-211 warm | CM14 -HV MLI | CM13 - 2 phase piping/Weld CM12- Tuners | CM04-Tune HOM's | CM08- Prep for storage CM07- Prep for shipping test | C75- Travelers, Inventory | Fab protection covers for CM ends LERF Coils/Bellows Springs and plate for concrete module tests
2018-09-01 | Sat
2018-09-02 | Sun
2018-09-03 | Mon | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2018-09-04 | Tue | HW Coax tube & bod C75 EG to DB; | Inj BPMs; |  |  |  | J1.3-04 HOMs; | AES-006 900C/3h |  | TE01NS00X2 | C75 weld prep 5u; TE01NS00X2; | LSFC-12.2 parts; SC07 & parts; Vac hw; VAT valves x3; |  |  | HPR1: OOC HPR2: SC-07 |  | C75-000; |  | C75 DL | L2-213; IA-110 & 114; |  |  |  | D1: SIC L/C4K; D2: RRR L/C4K; D3: D4: maint D5: L2-224, L2-228, L2-231 pre-cool D6: SC-08 C1.6K/T/W D7: D8: L2-211 C4K | CM14 -HV MLI, Mag Shields | CM13 - 2 phase piping/LC; CM12- Tuners | CM04-Tune HOM's, Electrical checks, into VV | CM08- Prep for storage CM07- Prep for shipping test | C75- Travelers, Inventory | Fab protection covers for CM ends LERF Coils/Bellows Springs and plate for concrete module tests |  |  | BL Vacuum problems;
2018-09-05 | Wed | C75 | Inj BPMs; | C75 EG; L2 Bellows | TE01NS00X2 |  | L2-024; | AES-006 900C/3h; Software test; |  |  | Nb covers x6; Nb chamber x2; Nb foils x4; | L2 lollipop parts; DF bleedup valve; Lollipops; Mo fasteners & plates; |  | AES-007 setup; | HPR1: OOC HPR2: C75-000 RDT-07 |  | L2-lollipops; TS16-001 valve replace; |  | LSFC-12.2 TS16-005; SC-07 TS16-003; C75 DL |  |  | IA-110 & 114 sensors; |  | D1: SIC C2K/T/W D2: RRR T/W D3: D4: D5: L2-224, L2-228, L2-231 warm -> 100K/C4K D6: RDTTD-01 L/C4K/T/W D7: D8: L2-211 C2K/T/W | CM14 - Mag Shields, Fastener Sheets | CM13 - 2 phase piping LC CM12- Tuners | CM04- Electrical checks, into VV | CM08- Prep for storage CM07- Prep for shipping test | C75- Travelers, Inventory | Fab protection covers for CM ends LERF Coils/Bellows Concrete module shipping tests
2018-09-06 | Thu | C75 | Inj BPMs; | L2-bellows; L2-024; |  |  | L2-024; J1.3-04 HOMs; | AES-006 unload; |  |  | C75 weld prep 5u; x2 | L2 lollipop parts; AES-007 |  | AES-007 15u; | HPR1: OOC HPR2: A3; |  | L2-lollipops; |  | C75-000 TS28-003; RDT-07 TS28-004; | SC-07; RDT-07; LSFC-12.2; |  | L2-213 HOMs & sensors; IA-110 & 114 RFIN cable sensors; RDT-07 sensors; |  | D1: SIC P/L D2: RRR warm/pull; C75 DL load D3: RDT-07 L/SC4K D4: D5: L2-224, L2-228, L2-231 C2K/T D6: SC-07 L/C1.6K/T/W D7: D8: L2-211 warm | CM14 - Fastener Sheets | CM13 - 2 phase piping LC, heat stations, prep magnet leads CM12- Tuners | CM04- HOM Verification, into VV | CM08- Prep for storage CM07- Prep for shipping test | C75- Travelers, Inventory | Fab protection covers for CM ends LERF Coils/Bellows Concrete module shipping tests
2018-09-07 | Fri | C75 |  | L2-tuners; L2-bellows; L2 FP (x10); L2 HOM FT (x20); | [6 empty] | C75 weld prep 5u; x1 | DQW2; String hardware; L2-024.1 wipedown L2 cages x2; L2-151; L2-305; |  |  | HPR1: OOC HPR2: |  | L2-lollipops; L2 Bellows prep; |  | A3; L2-024.1 TS28-009; | C75-000; A3; |  | LSFC-12.2 sensors; |  | D1: SIC D2: C75 DL hold D3: RDT-07 C2K/T D4: D5: L2-224, L2-228, L2-231 warm D6: LSFC-12.2 L/SC4K/T/W; D7: L2-213 L/C4K D8: L2-211 warm TS28-009 to VAA | CM14 - Fastener Sheets, Fluxgates | CM13 - 2 phase piping LC, heat stations, prep magnet leads CM12- Tuners | CM04- MLI, into VV | CM08- Prep for storage CM07- Prep for shipping test | C75- Travelers, Inventory | Fab protection covers for CM ends, Install at Blue Crab LERF Coils/Bellows Concrete module shipping tests
2018-09-08 | Sat
2018-09-09 | Sun
2018-09-10 | Mon | C75 |  | L2 bellows; |  |  | L2 HOM FT incoming; | maint | TE01NS00X2 CBP; |  | L2 String Kit; C75 eq weld prep; SC-04, SC-07, SC-08 flash BCP; | DQW2 hw; EIC5 HW; L2-261; L2-025; L2-151 & L2-305 Bolt holes; AES HW; C75 load; |  | SC-04, SC-07, SC-08 setup; | HPR1: OOC HPR2: EIC5; EIC5; |  | L2 Bellows prep; | DQW2 rinse prep; L2-1, L2-2 bolts/flanges; | L2-227 D7/8 | L2-024.1 |  | C75-000 sensors; |  | D1: D2: C75 DL C/T/W D3: RDT-07 pull; C75-000 L/SC4K; D4: D5: L2-224, L2-228, L2-231 pull; L2-220, L2-518, L2-520 L/ D6: KEK-R5 L/C4K/W; D7: L2-213 C2K/T/W D8: L2-211 pull; IA-110 & 114 L | CM14 - Fastener Sheets, Fluxgates | CM13 - prep magnet leads/solder CM12- Tuners | CM04- Into VV, Alignment | CM08- Prep for storage CM07- Install Shipping caps | C75- Travelers, Inventory | Fab protection covers for CM ends, Install at Blue Crab LERF Coils/Bellows
2018-09-11 | Tue | C75 |  | L2-bellows; L2 tuners; |  |  | L2 HOM FT incoming; | maint |  |  |  | TN1N1 HW; L2 cages x2; L2-261 bolt holes; L2-025 Bolt holes; C75 sub assy; 6" flange\pipe; |  | SC-04, SC-07, SC-08 50u; | HPR1: OOC HPR2: TC1N1; DQW2; |  | L2 string tooling and HW prep; cage L2-1, L2-2; | L2-3, L2-4 bolts/flanges; | EIC5 D7/8; | L2-227; |  | L2-024.1 sensors & HOMs; |  | Florence D1: D2: C75DL-pull/L2 FT's L/C4K (x2)/W D3: C75-000 C2K/T/W; D4: D5: L2-220, L2-518, L2-520 hold D6: KEK-R5 C4K/W; D7: L2-213 warm; D8: IA-110 & 114 hold | CM14 - Fastener Sheets, Fluxgates | CM13 - prep magnet leads/solder CM12- MLI, heat stations, mag shields | CM04- Alignment | CM08- Idle CM07- Install Shipping caps, 2 WS6 | C75- Travelers, Inventory | Fab protection covers for CM ends LERF Coils/Bellows
2018-09-12 | Wed |  |  | L2 bellows; L2-522; |  |  |  | SC-04, Sc-07, SC-08 & samples 800C/3h/3N60; | TE01NS00X2 CBP; GE In flange; |  | GE In flange; C75 eq weld prep; Cu cell & Beam tube; | L2 cage prep; AES-007 HW; Tube fittings x16; |  | AES-006 setup; | HPR1: OOC HPR2: AES-007 |  |  |  | L2 HOM FT & FP; | L2-227; EIC5 failed; |  |  |  | Florence D1: D2: L2 FT's C4K/W D3: C75-000 warm; D4: D5: L2-220, L2-518, L2-520 hold D6: KEK C/W D7: L2-213 hold D8: maint; IA-110 & 114 load | CM14 - Prep for cavity string leak check | CM13 - solder magnet leads CM12- MLI, heat stations, mag shields | CM04- Alignment, Move to WS5 | CM08-Spin 180 for warm coupler removal CM07- Install Shipping caps, 2 WS6 | C75- Travelers, Inventory | Fab protection covers for CM ends LERF Coils/Bellows Shipping Trailer into Test Lab 1pm, Unload Concrete Cryostat
2018-09-13 | Thu |  |  | L2-522; L2-523; |  |  | L2-522 | SC-04, Sc-07, SC-08 & samples 800C/3h/3N60; | TE01NS00X2 CBP; |  | Nb caps and sheets 20u (PD); Cylinder parts & separator coupler; | Long spool; RGA wipedown; |  | AES-006 15u; | HPR1: OOC HPR2: AES-007 |  | AES-007; |  | TC1N1 TS16-008; | IA-110 & 114; |  | L2-227 HOMs; | L2-228, L2-231 (fast); | D1: D2: L2 FT's hold D3: C75-000 hold; D4: D5: L2-220, L2-518, L2-520 precool; D6: D7: L2-213 pull; L2-024 C4K D8: IA-110 & 114 pull | CM14 - Prep for cavity string leak check | CM13 - solder magnet leads CM12- MLI, heat stations, mag shields | CM12- VV from Blue Crab | CM08- MC/Warm coupler removal CM04- Prep 4 JT welding,beampipes, and warm couplers | C75- Travelers, Inventory | Fab protection covers for CM ends LERF Coils/Bellows Shipping Trailer 2 b moved on-site
2018-09-14 | Fri | regen |  | L2-542; |  |  | L2-523 | Nb sheets, KEK R5 1000C/3h; | TE01NS00X2 CBP; |  |  | L2-522 ext rinse; L2-523 ext rinse; |  | RDT-07 setup; | HPR1: OOC HPR2: |  |  | EIC5; L2-228, L2-231 pull PICs; | AES-007 cart; | IA-110, IA-114 TC1N1 ; |  | L2-227 sensors; |  | D1: D2: L2 FT's pull; D3: C75-000 hold; D4: D5: L2-220, L2-518, L2-520 W/C4K D6: A3 L/C1.6K/T D7: L2-024.1 C2K/T/W D8: L2-227 L | CM14 - Prep for cavity string leak check | CM13 - solder magnet leads CM12- MLI, heat stations, instrumentation | CM12- VV insp,demag, field mapping | CM08- MC/Warm coupler removal CM04- Prep 4 JT welding,beampipes, and warm couplers | C75- Travelers, Inventory | Fab protection covers for CM ends LERF Coils/Bellows
2018-09-15 | Sat
2018-09-16 | Sun
2018-09-17 | Mon | C75 | start-up | L2 Bellows; VV33; |  |  | L2-542 | Nb sheets, KEK R5 1000C/3h; | TE01NS00X2 CBP; |  | ceramic flash BCP; | L2-523 ext rinse; LSFC9-2 wipe; LSFC hardware; L2-245 bolt holes; L2-242 ext rinse; L2 HW; L2-0059 ext rinse; L2-0056 ext rinse; RDT-14 HW; |  | RDT-07 10u; | HPR1: OOC HPR2: RDT-14; LSFC9-2 |  |  | L2-5, L2-6 bolts/flanges; LSFC12; | L2-522 D5; | IA-110, IA-114; AES-007 D7/8; |  |  |  | D1: D2: D3: C75-000 pull; D4: D5: L2-220, L2-518, L2-520 C2K/T D6: TC1N1 L/C1.6K/T/W D7: L2-024.1 pull; D8: L2-227 C4K | CM14 - Prep for cavity string leak check | CM13 - solder magnet leads CM12- MLI, heat stations, instrumentation | CM12- VV insp,demag | CM08- MC/Warm coupler removal CM04- Prep 4 JT welding,beampipes, and warm couplers | C75- Travelers, Inventory | LERF Coils/Bellows
2018-09-18 | Tue | C75 |  | L2 Tuner; L2 Bellows; L2-543; |  |  | L2-543 | maint. | TE01NS00X2 CBP; |  | C75 eq weld prep (x2) | L2-542 ext rinse; String 15 bolt holes; DQW2 gaskets; DQW2 Assembly HW. |  | SC-04, Sc-07, SC-08 setup; | HPR1: OOC HPR2: RDT-07 |  | crate L2-24.1; TS16-004 ext. cleaning; | L2-7, L2-8 bolts/flanges; | L2-522, L2-523 D5; DQW2 cart; LSFC9-2 TS16-005; RDT-14; | IA-110, IA-114; RDT-14; |  |  |  | D1: D2: D3: D4: D5: L2-220, L2-518, L2-520 warm D6: TC1N1 C/T/W D7: D8: L2-227 C2K/T/W | CM14 - Bag for cavity string leak check | CM13 - solder/heat station magnet leads CM12- RF Cables | CM12- VV field mapping | CM08- MC/Warm coupler removal CM04- JT welding, beampipes, and warm couplers | C75- Travelers, Inventory C100-06- Coming to Test Lab this week, stored on VAA | LERF Coils/Bellows Remove UITF Railings
2018-09-19 | Wed | C75 |  | L2 Bellows; |  |  |  | maint. | TE01NS00X2 CBP; |  | LSFC12 BCP Strip; Sample chamber; | RDT2; Bellows x2: L2-543 ext rinse; |  | SC-04, Sc-07, SC-08 8u; | HPR1: OOC HPR2: RDT2 |  |  |  | L2-522, L2-523, L2-542 D5; | LSFC9-2; | AES-007 120C/20h; |  | IA-110, IA-114; | D1: D2: D3: C75-000 L/SC4K D4: C4K D5: L2-220, L2-518, L2-520 warm, D6: RDT-14 L/C1.6K/T/W D7: D8: L2-227 warm; | CM14 - Bag for cavity string leak check | CM13 - heat station magnet leads CM12- RF Cables, to WS4 | CM12- Cold mass arrives | CM08- MC/Warm coupler removal CM04- beampipes, and warm couplers | C75- Travelers, Inventory C100-06- Coming to Test Lab next week, stored on VAA | LERF Coils/Bellows Remove UITF Railings
2018-09-20 | Thu | C75 |  | L2-Probes; L2-Bellows; |  |  |  | room temp empty run ; | TE01NS00X2 CBP; |  | C75 eq weld prep (x2); Nb cap 5u (GE); EIC-5 Flanges; | L2-543 wipe; L2-503 wipe; L2-503 parts; EIC-5; SC-04 HW; |  |  | HPR1: OOC HPR2: SC-04 |  |  | IA-110, IA-114; | L2-543 D7/8; | L2-522, L2-523, L2-542 | AES-007 120C/20h; | LSFC9-2 sensors; |  | D1: D2: D3: C75-000 /C1.8KT/W D4: maint D5: L2-220, L2-518, L2-520 pull, L2-522, L2-523, L2-542 L D6: LSFC9-2 L/SC4K D7: D8: L2-227 warm; |  | CM13 - Prep 4 Alignment CM14- Bag for cavity string leak check | CM12- Instrumentation check out, fastener check list, Assy review, Shield test fit | CM08-Warm coupler & Inst. flange removal CM04- warm couplers, prep 4 PT, SLAC on-site | C75- Travelers, Inventory C100-06- Coming to Test Lab next Tuesday, stored on VAA | LERF Coils/Bellows UITF HDICE Install Configure RF WG's for FL02
2018-09-21 | Fri | C75 | Nb-SS flange braze (GE); | L2-Probes; L2-Bellows; |  |  |  | empty run 800C/3h/3N60; | TE01NS00X2 CBP; |  | SS tees x2; Nb flanges x2; SS flange; Mini CF & Nb disk 4"; Nb clamps x3; | SS tees x2; Nb flanges x2; SS flange; Tools wipe; Conflat & HW; Bellows x2; |  | L2-212 setup; | HPR1: OOC HPR2: 2.2G; RDT-14; |  | EIC5 cage |  | DQW2 D5; IA-110, IA-114 D7/8; | L2-543; DQW2; | DQW2 120C 24h; | L2-522, L2-523, L2-542 HOMs & sensors; L2-543 HOMs & sensors; |  | D1: SIC L/C/T D2: D3: C75-000 C1.8K/T/warm D4: D5: L2-522, L2-523, L2-542 pre-cool; D6: LSFC9-2 C2K/T/W D7: D8: L2-227 pull; L2-543 L/C4K |  | CM13 - CS Alignment CM14- Bag for cavity string leak check | CM12- Instrumentation check out, fastener check list, Assy review, Shield test fit | CM08-Warm coupler & Inst. flange removal CM04- warm couplers, prep 4 PT, SLAC on-site | C75- Travelers, Inventory C100-06- Coming to Test Lab next Tuesday, stored on VAA | LERF Coils/Bellows UITF HDICE Install Configure RF WG's for FL02
2018-09-22 | Sat
2018-09-23 | Sun | [22 empty] | D8: L2-543 C2K
2018-09-24 | Mon | C75; |  | L2-Probes; L2-Bellows; |  |  | J1.3-12 HOMs | Elnik Upgrade | TE01NS00X2 CBP; |  | Nb35n samples x4; | L2-212; EIC5 HW; |  | L2-212 5u; | HPR1: OOC HPR2: LSFC12; EIC5; |  |  |  | RDT-14; | RDT-14; IA-110, IA-114; | DQW2 120C 24h; | IA-110, IA-114 sensors; |  | D1: SIC C/T D2: D3: C75-000 hold D4: D5: L2-522, L2-523, L2-542 W/C4K D6: TC1N1 L/C2K/T/W D7: IA-110, IA-114 load/SC4K D8: L2-543 leaks/warm |  | CM13 - CS Alignment CM14- Bag for cavity string leak check | CM12- Instrumentation check out, fastener check list, Assy review, Shield test fit; HOMs | CM08-Warm coupler & Inst. flange removal CM04- warm couplers, prep 4 PT, | C75- Travelers, Inventory C100-06- Coming to Test Lab next Wednesday, stored on VAA | LERF Coils/Bellows UITF HDICE Install Configure RF WG's for FL02
2018-09-25 | Tue | CEBAF separator; | Nb-SS flange braze (GE); | L2-Bellows |  |  | J1.3-12 HOMs | Elnik Upgrade |  |  | C75 HOM EG weld prep; Nb3Sn samples; | L2-212 parts; L2-212 HW; L2-208 HW; 6" spools x3; EBW parts; RF power coupler; |  | L2-208 setup; | HPR1: OOC HPR2: SC-04; G2 L2-212; |  | cage L2-212; | TS16-004 prep; | EIC5 7/8; |  |  | AES-007 test stand sensors; |  | D1: SIC Pull D2: D3: C75-000 pull; D4: maint D5: L2-522, L2-523, L2-542 C2K/T/W D6: RDT-14 L/C/T D7: IA-110, IA-114 C4K D8: L2-543 warm maint |  | CM13 - Idle CM14- LC Good, back to WS2. | CM12- Install lower 50k shields, remeasure HOM's | CM08-Warm coupler, remove tophats and ship restraints CM04- warm couplers, RT Weld | C75- Travelers, Inventory C100-06- Coming to Test Lab next week stored on VAA | LERF Coils/Bellows UITF HDICE Install-ongoing Configure RF WG's for FL02- complete today
2018-09-26 | Wed | C75; | Nb-SS flange braze (GE); | L2 Spools |  |  | J1.3-12 HOMs | Elnik Upgrade |  |  | Mo HW; Nb covers & rod; Tcouples for Elnick x7; | L2-208; SNS HW; Valves, bellows & HW; Mo HW; Nb covers & rod; |  | L2-208 5u; | HPR1: OOC HPR2: RDT-7; L2-212; |  | L2-212; BNNT test stand TS16-004; | TS16-004 prep; | RDT-7 TS16-005; SC-04 TS16-003; | EIC5; RDT-7; | DQW2 120C 24h; | DQW2 sensors; |  | D1: SIC L/C/T D2: RRR L/C; D3: D4: maint D5: L2-522, L2-523, L2-542 warm; D6: RDT-14 hold D7: IA-110, IA-114 C2K/T/W D8: L2-543 pull; blank lid L/pull; EIC5 L/C4K |  | CM13 - Idle | CM12- Install MLI, into VV | CM08-Warm coupler, remove tophats and ship restraints CM04- warm couplers, RT Weld | C75- Travelers, Inventory C100-06- Test Lab next week stored on VAA, Prep area, paperwork | LERF Coils/Bellows UITF HDICE Install-ongoing
2018-09-27 | Thu | C75 |  | L2 Tuners L2-504 |  |  |  | Elnik Upgrade |  |  |  | FPC header parts; LCLS2 Coupler Parts SC-04 HW; SC-07 HW; SNS HB HW; FPC top hats & Gaskets x8; FPC blanks & gaskets x8 |  | Acid change; | HPR1: OOC HPR2: L2-208; SC-07; |  | L2 US gate valve; | L2-543 retorque; | L2-212 D7/8; C75 DL; G2; | SC-04; G2; |  | BNNT sensors; RDT-7 sensors; |  | D1: SIC C/T D2: RRR W/T; D3: D4: maint D5: L2-522, L2-523, L2-542 warm; D6: RDT-7 L/sC/T; D7: IA-110, IA-114 SC4K D8: EIC5 C2K/T/W4K | CM14- Idle, UCM after UITF | CM13 - CS Alignment | CM12- Install MLI, into VV | CM08- remove WC's CM04- add warm couplers, RT Weld | C75- Travelers, Inventory C100-06- Test Lab next week stored on VAA, Prep area, paperwork | LERF Coils/Bellows UITF HDICE Install-ongoing WC Support fit ups
2018-09-28 | Fri | C75; |  | L2VV L2-531 |  |  | L2-504; LSFC-xx probes; | Elnik Upgrade |  |  | Nb samples HCL soak x10; Nb strip; 2.2 GHz flanges & parts; | Al seals; |  | HF Spike; | HPR1: OOC HPR2: L2-208; |  | L2-208 |  |  | C75 DL; L2-543; |  | SC-04 sensors; |  | D1: SIC D2: RRR warm/pull; BNNT L/C4K/T/W (commissioning); D3: D4: D5: L2-522, L2-523, L2-542 pull; DQW2 L/C4K; D6: RDT-7 sC/T/W D7: IA-110, IA-114 C2K/T/W; D8: EIC5 warm | CM14- Idle, UCM after UITF | CM13 - CS Alignment | CM12- Install MLI, into VV | CM08- remove WC's CM04- add warm couplers, RT Weld | C75- Travelers, Inventory C100-06- Test Lab next week stored on VAA, Prep area, paperwork | LERF Coils/Bellows UITF HDICE Install-ongoing WC Support fit ups
2018-09-29 | Sat
2018-09-30 | Sun | [13 empty] | HPR2: L2-1; L2-2; |  | cage L2-3, L2-4; |  | L2-208 cart
2018-10-01 | Mon | Larry1; | L2 Bellows | IA-016; IA-008; |  |  | L2-531; C75-004; | Elnik Upgrade |  | HB-071 before EP |  | FPC header parts; FPC top Hats (x8); Berry Bolt kits (x2) CAV-504 ext rinse; S/S Angle (x16) |  | HB-071 setup | HPR1: OOC HPR2: L2-2, L2-3; |  | cage L2-5, L2-6; TS16-xyz rebuild |  | L2-1; | L2-208; L2-212; |  |  |  | D1: SIC pull; D2: BNNT C2K/T/W D3: D4: D5: DQW2 C2K/T/W D6: SC-04 L/C/T/W (0mg) D7: IA-110, IA-114 hold; D8: EIC5 pull; | CM14- Idle, UCM from Blue Crab | CM13 - Tuners | CM12- into VV, prep 4 alignment | CM08- remove WC's CM04- add warm couplers, MC line | C75- Travelers, Inventory C100-06- Test Lab Thursday 10-4 stored on VAA, Prep area, paperwork | LERF Coils/Bellows UITF HDICE Install-ongoing WC Support fit ups
2018-10-02 | Tue | Larry1; HW Coax repair; | L2 Bellows | IA-320; L2-UCM; |  |  | L2-526; L2-532; | Elnik Upgrade |  | HB-071 post EP | C75-005 EG weld prep; | L2 Bellows (x2) |  | HB-071 60u | HPR1: OOC HPR2: L2-4; L2-5; HB-071 single pass; |  | cage L2-7, L2-8; TS16-xyz rebuild |  | L2-2; L2-3; C75 DL; SC-07 TS16-008; |  |  | L2-212 sensors and HOMs; |  | D1: SIC L/C2K/T/W D2: BNNT w/T D3: D4: level sensor cal D5: DQW2 warm; D6: SC-04 sC/T/W (20mG) D7: IA-110, IA-114 pull; L2-212 L/C4K; D8: leak checking; | CM14-CS Idle | CM13 - Tuners CM14- UCM RI | CM12- VV alignment | CM08- remove WC's CM04- MC line, Low PT, Close VV side port | C75- Travelers, Inventory C100-06- Test Lab Thursday 10-4 stored on VAA, Prep area, paperwork | LERF Coils/Bellows UITF HDICE Install-ongoing WC Support fit ups |  |  | beam to all four halls;
2018-10-03 | Wed | C75 |  | L2-UCM; L2-526 demag; L2-532; |  |  | LSFC probe | Elnik Upgrade | [5 empty] | TE01NS00X2-01, TE01NS00X2-02 setup; | HPR1: OOC HPR2: L2-6; L2-7; |  | TS16-011 rebuild | C75-000; DQW2; EIC1; | L2-4; L2-5; | C75 DL; SC-07 leaked; |  |  |  | D1: SIC C2K/T/W D2: Hall D level sensor L/C/T/W D3: D4: D5: DQW2 pull; D6: D7: L2-212 C2K/T/W; D8: leak check | CM14-CS Idle | CM13 - Tuners CM14- UCM RI | CM12- VV alignment | CM08- remove WC's CM04- MC line, Low PT, Close VV side port | C75- Travelers, Inventory C100-06- Test Lab Thursday 10-4 stored on VAA, Prep area, paperwork | LERF Coils/Bellows UITF HDICE Install-ongoing WC Support fit ups |  |  | beam to all four halls;
2018-10-04 | Thu | C75 |  | L2 Bellows; L2-532; |  |  | LSFC probe | Elnik Upgrade |  | HB-071; | SC-07 flange BPC; | SC-08 hardware; 2.2GHz HW; Test stand parts; L2 BL gaskets; |  | TE01NS00X2-01, TE01NS00X2-02 30u; | HPR1: OOC HPR2: L2-8 SC-08; RFD2; |  | TS16-011 rebuild | SC-07 dis; | L2-6; L2-7; |  |  |  |  | D1: SIC W D2: C75 DL Load D3: D4: D5: D6: G2 L/C4K/sW; D7: L2-212 pull; AES-007 L/C4K; D8: leak check | CM14-CS Idle | CM13 - Tuners CM14- UCM RI, Alignment Crew | CM12- Idle | CM08- remove WC's CM04- MC line, Low PT, Close VV side port | C75- Travelers, Inventory C100-06- To Test Lab. Truck on-site 9 am. VAA | LERF Coils/Bellows UITF HDICE Install-ongoing |  |  | beam to all four halls; 1L20-3,4 WG vacuum poor;
2018-10-05 | Fri | C75; |  | L2 Bellows; L2-Tuner; |  |  |  | Elnik Upgrade |  |  | C75 stiff rings weld prep; TC1N1 internal Nitric soak one hour; | EIC5 washdown; |  | maint; | HPR1: OOC HPR2: HB-071; 2.2GHz; |  | TS16-011 rebuild | EIC5; | L2-8; RFD2 D5; L2-208 D7/8; SC-08 TS16-003; 2.2GHz TS16-005; |  |  |  |  | D1: SIC hold, D2: C75 DL C4K/T/W D3: D4: D5: D6: G2 slow warm D7: AES-007 C2K/T/W D8: leak check | CM14-CS Idle | CM13 - Tuners CM14- UCM RI, Alignment Crew | CM12- Idle | CM08- remove WC's CM04- MC line, Low PT, Close VV side port | C75- Travelers, Inventory C100-06- VAA | LERF Coils/Bellows UITF HDICE Install-ongoing |  |  | beam to all four halls; 1L20-3,4 WG vacuum poor but stable;
2018-10-06 | Sat | [18 empty] | RFD2; | RFD2 120C/12h;
2018-10-07 | Sun | [19 empty] | RFD2 120C/12h;
2018-10-08 | Mon | HW Coax repair; |  | L2 Bellows |  |  | C100-RI-027; | Elnik Upgrade |  |  | C75 Stiff rings weld prep; | EIC5 2% Liquinox; L2 FPC parts (RA Valves x8 & HW); Bronze Cavity; 3GHz Cu cavities x2; CBP Cu covers x4 & rods x2; vacuum pump parts; SNS-HB-071 bolts (acetone in R&D) |  | Maint; TE01NS00X2-01, TE01NS00X2-02 setup; | HPR1: OOC HPR2: SC-07; |  | TS16-011 rebuild |  |  | L2-208; SC-08; 2.2GHz; |  | SC-08 sensors; RFD2 sensors; |  | D1: SIC pull, D2: C75 DL pull; D3: D4: D5: RFD2 L/C4K; D6: 2.2 GHz load (isol valve open?) /C1.5K/T D7: AES-007 pull, L2-543 L/C4K; D8: leak check | CM14-CS move to WS3 | CM13 - Tuners CM14- UCM RI, Alignment Crew | CM12- To WS5, | CM08- move to WS4 CM04- Move to WS6, Low PT, Close VV side port | C75- Travelers, Inventory C100-06- VAA | LERF Coils/Bellows UITF HDICE Install-ongoing BLA leak checks (x5); |  |  | beam to all four halls;
2018-10-09 | Tue | C75 cavities; |  | L2 Bellows; EZ-SSC-02; EZ-SSC-05 |  |  | C100-RI-027; | Elnik Upgrade |  |  | C75 stiff rings weld prep; | L2-531 ext rinse; TC1N1; L2 FPC parts; EIC5 hardware; C75-005 & stiff rings; Cu Gaskets x24; HB-071 HW; BLA restraining Bars & HW; |  | TE01NS00X2-01, TE01NS00X2-02 70u; | HPR1: OOC HPR2: EIC5 |  | Bag string; TS16-011 rebuild; HB-071; | C75 DL; | SC-07 D6; L2-531, L2-504 D5; C75 DL; |  |  | L2-208 HOMs & sensors; |  | D1: D2: D3: D4: D5: RFD2 C2K/T/W D6: SC-08 L/C/T (0mG) D7: L2-543 C2K/T/W D8: leak check | CM14-CS move to WS3 | CM13 - Tuners CM14- UCM RI | CM08- Remove VV, Inspect bellows | CM12-WC, Instrumentation CM-10- Out of CMTF | C75- Travelers, Inventory C100-06- VAA |  |  |  | beam to all four halls; RF recovery;
2018-10-10 | Wed | C75 cavities; | BLA (x5) visual; | EZ-SSC-04 flanges & fasteners; L2 Bellows (unplated); |  |  | C100-6 hardware inventory; | Elnik Upgrade |  |  |  | Mircea Cu in oven test ; EZ-SCC-02, EZ-SCC-05 wipedown; SNS-HB-072 bolts; FNAL L2 bellows (x11); |  | TC1N1, A1, A3 setup; | HPR1: OOC HPR2: HB-071 |  |  |  | EIC5 D7/8; EZ-SSC-02 TS28-006; | SC-07 leaked; J1.3-015; |  |  | AES-007 fast; | D1: D2: D3: D4: level sensor cal D5: RFD2 warm D6: SC-08 C/T (20mG) D7: L2-543 warm; D8: L2-208 L/C4K | CM14-CS move to WS3 | CM13 - Tuners CM14- UCM Mate to CS | CM08- Remove VV, Inspect bellows | CM12-WC's, Instrumentation CM-10- Out of CMTF, Remove WC's | C75- Travelers, Inventory C100-06- VAA
2018-10-11 | Thu | C75 cavities; | FNAL L2 bellows (x11); | L2 bellows; L2 mag shields; |  |  |  | Elnik Upgrade | SC-07 |  | RDT-10 Nitric & HCl; | KEK-R5; CEBAF RA valves (x12); SC-07; HB-072 parts & HW; Berry Bolts |  | TC1N1, A1, A3 setup; | HPR1: OOC HPR2: |  |  | AES-007; | HB-071 D7/8; Ion pump inst. J1.3-15; | EIC5; EZ-SSC-02; C75 DL; L2-531, L2-504 D5; |  | EZ-SSC-02 sensors; L2-543 input cable repair; |  | D1: D2: D3: D4: warm D5: RFD2 warm D6: SC-08 pull; D7: L2-543 pull; EZ-SSC-02 L/C4K D8: L2-208 C2K/T/W |  | CM13 - Tuners CM14- UCM Mate to CS, Demag small parts | CM08- Re-assemble Mag shileds, Instrumentation checkout | CM12-WC's, Instrumentation flanges CM-10- Remove Inst. Flanges & WC's | C75- Travelers, Inventory C100-06- VAA, Refresher Training 11 a.m. | C100-RI-027 bellows replacement, meet @9:30 today
2018-10-12 | Fri | C75 cavities stiffening rings; | FNAL L2 bellows (x11); | L2 mag shields; |  |  |  | Elnik Upgrade |  |  |  | 9:30am J1.3-015 rollout; L2-Long Spools (x2); SC-07 & HW & parts; vacuum HW & parts; |  | TC1N1, A1, A3 30u; | HPR1: OOC HPR2: N3; RDT-10; |  | J1.3-015 rollout; |  | N3 TS16-008; | HB-071 failed; |  | L2-531, L2-504, L2-542 sensors & HOMs; L2-543 input cable repair; |  | D1: D2: D3: D4: D5: RFD2 pull; L2-531, L2-504, L2-542 load; D6: D7: EZ-SSC-02 C2K/T/W D8: L2-208 warm; | J1.3-015 rollout; | CM13 - Tuners CM14- UCM Mate to CS, Demag small parts | CM08- Re-assemble Mag shileds, Instrumentation checkout | CM12-WC's, Instrumentation flanges CM-10- Remove Inst. Flanges & WC's | C75- Travelers, Inventory | C100-RI-027 bellows replacement
2018-10-13 | Sat | [22 empty] | D7: EZ-SSC-02 thermal cycles
2018-10-14 | Sun | [22 empty] | D7: EZ-SSC-02 Thermal cycles/warm
2018-10-15 | Mon | 5C75-005; |  | L2 mag sheilds; L2-532; |  |  | J1.3-15 passbands; L2-514; | vent; cleanup run 1200C/3h; | HB-072; |  | SC-07 Flanges 2sec BCP; RDT-14 & RDTTD-01 ext. BCP; | FNAL L2 bellows (x9); AES-007 hardware; EZ-SSC-05 wipe; AES-007 acetone wipe and 1% USC; L2-094 acetone wipe and 1% USC; DS long spool (x2); |  | KEK-R5 setup; | HPR1: OOC HPR2: SC-07; AES-007 |  | AES-007 cage; cage L2-094; |  | RDT-10 D3/4; |  |  |  |  | D1: D2: C75 DL L/C/T/W D3: D4: D5: L2-531, L2-504, L2-542 hold; D6: D7: EZ-SSC-02 pull; EIC5 L/C4K D8: L2-208 pull; L2-543 load | J1.3-015- RF measurements; Alignment, | CM13 - Tuners CM14- UCM Mate to CS, Demag small parts | CM08- Instrumentation checkout, HOM tuning | CM12-WC's, Instrumentation flanges CM-10- Remove Inst. Flanges & WC's | C75- Travelers, Inventory CM04- Instrumentation flanges, ship cap test fit | C100-RI-027 bellows replacement C100-06- To assy floor
2018-10-16 | Tue | C75 DL; LSFC-12 repair; | FNAL L2 bellows (x8); | L2 BLA (x5); L2-514; |  |  | J1.3-08 HOMs; L2-532; | RDTTD-01, RDT-14 2N6; | HB-071 hom flange; HB-072; |  | Nb foil box | L2-526 ext rinse; KEK-R5; aluminum gaskets; berry bolt kit; sm bellows (x8); HB-071 and HW; |  | KEK-R5 40u; | HPR1: OOC HPR2: L2-094; AES-007; |  | AES-007; |  | EZ-SSC-05 TS28-006; L2-526 D5; SC-07 TS16-003; | EZ-SSC-05; RDT-10; |  |  |  | D1: D2: C75 pull; D3: D4: D5: L2-531, L2-504, L2-542 precool; D6: N3 L/C/T/W D7: EIC5 C2K/T/W D8: L2-543 C4K | J1.3-015- Magnet install | CM13 - Tuners CM14- UCM Mate to CS | CM08- HOM tuning, stepper/limit switch verification | CM12-WC's, Instrumentation flanges CM-10- Remove Inst. Flanges & WC's, Reconfig beam pipes | C100-06- Remove warm tuners, secondary waveguides CM04- Instrumentation flanges, ship cap test fit | C100-RI-027 - In MS for end dish machining |  |  | RF recovery
2018-10-17 | Wed | C75 DL; |  | L2 BLA x5 |  |  | L2-536; | RDTTD-01, RDT-14 2N6; |  | HB-072 |  | HB-072; L2-532 ext rinse; L2 BLA body (x2); L2 BLA ceramic (x2); |  | HB-072 setup | HPR1: OOC HPR2: HB-071; L2-094; |  | L2-094; | C75 DL | L2-532, L2-526 D5; AES-007 D7/8; | SC-07; EZ-SSC-05; |  | EZ-SSC-05 sensors; |  | D1: L2 FT L; D2: BNNT load; D3: D4: RDT-10 L/SC4K D5: L2-531, L2-504, L2-542 W/C4K D6: N3 C/T/W D7: EIC5 W D8: L2-543 C2K/T/W | J1.3-015- Magnet install, berry bolts | CM13 - Tuners CM14- UCM Mate to CS | CM08- Install lower 50k shields, HOM verification | CM12-WC's, Instrumentation flanges, MC Line CM-10- Remove Inst. Flanges & WC's, Reconfig beam pipes | C100-06- Remove warm tuners, secondary waveguides CM04- Instrumentation flanges, ship cap test fit | C100-RI-009 - In for HV removal
2018-10-18 | Thu | C75 DL; | BLA ceramic (x2); | C75 cavity x2 |  |  | J1.3-08 HOMs; L2-538; | BLA body (x2); |  |  | RDTTD-01 6.7u BCP; | RDTTD-01 HW; L2 WG vacu pipes; |  | HB-072 55u; | HPR1: OOC HPR2: TC1N1; HB-071 |  | HB-071 |  | L2-532, L2-526 D5; | AES-007; | EIC5 120C/12h; | SC-07 sensors; |  | D1: L2 FT cycles; D2: BNNT C4K; D3: D4: RDT-10 SC4K (2nd attempt) D5: L2-531, L2-504, L2-542 C2K/T/W D6: SC-07 (0mG) L/C/T/W; D7: EIC5 pull; EZ-SSC-05 L/thermal cycles D8: L2-543 W | J1.3-015- Magnet install, berry bolts | CM13 - Tuners CM14- UCM Mate to CS, fit/weld 2 phase piping | CM08- HOM verification, MLI, into VV | CM12- WC's, Instrumentation flanges, MC Line CM-10- Remove Inst. Flanges & WC's, Reconfig beam pipes | C100-06- Remove warm tuners, secondary waveguides CM04- Instrumentation flanges, ship cap test fit | C100-RI-009 - In for HV removal
2018-10-19 | Fri | HW Coax beampipe; | BLA ceramic (x2); |  |  |  | L2-539; L2-541; | BLA body (x2); |  |  |  | HB-072 1% liquinox 1hr w/mvmt; HB-072 USC DI water only; |  | HB-072 20u; | HPR1: OOC HPR2: RDTTD-01; |  | cage HB-072 am; |  | HB-071; RDTTD-01 TS16-001; TC1N1 TS16-008; C75 DL; | RDTTD-01; C75 DL; AES-007; | EIC5 120C/12h; | EIC5 flange re-torque; |  | D1: L2 FT cycles/W D2: BNNT C2K/T/W D3: D4: RDT-10 warm; D5: L2-531, L2-504, L2-542 warm; D6: D7: EZ-SSC-05 (20mG) C2K/T/W D8: L2-543 pull; AES-007 L/C4K | J1.3-015- Magnet install, berry bolts | CM13 - Tuners CM14- UCM Mate to CS, fit/weld 2 phase piping | CM08- into VV | CM12-Instrumentation flanges, MC Line CM-10- Remove Inst. Flanges & WC's, Reconfig beam pipes | C100-06- Remove warm tuners, secondary waveguides CM04- Instrumentation flanges, ship cap test fit | C100-RI-009 - In for HV removal LCLS F05 to ship from FNAL-coming here |  |  | 4 hall opeations, Hall A problems; 1L20 wg vacuum problem;
2018-10-20 | Sat
2018-10-21 | Sun
2018-10-22 | Mon | HW Coax beampipe; |  | C100-RI-009 HOM inspection; L2-514; |  |  | setup tuning bench for C100; C100-RI-009; |  |  | HB-072 |  | RDT-14 parts; bag/N2 BLA 201; AES-006 acetone wipe and 1% USC; Flange & HW; Cryo blanks x6; Field probes x3; EZ-SSC-03 wipe down; Couplers 83 & 84; Coupler blanks x4; |  | RDT-14 setup; | HPR1: OOC HPR2: |  |  | EZ-SSC-03; | EZ-SSC-03; | TC1N1; HB-071; L2-094 failed; | HB-071 120C/24h | TC1N1 sensors; |  | D1: D2: BNNT warm test; D3: D4: RDT-10 pull; D5: L2-531, L2-504, L2-542 pull; D6: RDTTD-01 L/C/T/W D7: EZ-SSC-05 pull; EIC5 L/C4K D8: AES-007 C2K/T/W | J1.3-015- Magnet install, berry bolts | CM13 - Tuners CM14- UCM Mate to CS, fit/weld 2 phase piping | CM08- MLI, into VV | CM12-Instrumentation flanges, MC Line CM-10- Remove Inst. Flanges & WC's, Reconfig beam pipes | C100-06- Prep for grinding CM04- Instrumentation flanges, ship cap test fit | C100-RI-016 - In for HV removal LCLS F05 IS HERE, remove from frame, download sensor data
2018-10-23 | Tue | HW Coax beampipe; | BLA removal; | C100-RI-009 HOM inspection; L2 536; L2-538; |  |  | setup tuning bench for C75 |  |  |  | L2 FPC accessories (x8); CBP Cu blanks x4 | RDT-14; L2-514 ext rinse; RDT-10 parts; |  | RDT-14 6.7u; | HPR1: OOC HPR2: RDT-10; RDT-14; |  | L2-094 cage; |  | RDT-14; | EZ-SSC-03; BLA 2A; RDT-14; | HB-071 120C/24h |  | L2-543 fast bleed -->tuning; | D1: SIC L D2: BNNT pull; RF Cables L D3: D4: D5: D6: TC1N1 L/C/T/W; D7: EIC5 C2K/T/W D8: AES-007 warm | J1.3-015- Magnet install, berry bolts | CM13 - Tuners/ steppers-piezos CM14- UCM Mate to CS, fit/weld 2 phase piping | CM08- into VV | CM12- Move to WS6 for F5 work CM-10- Remove Inst. Flanges & WC's, Reconfig beam pipes | C100-06- Grind lockdowns/tuner stacks CM04- Instrumentation flanges, ship cap test fit | C100-RI-016 - In for HV removal LCLS F05- taking sensor date, move to WS5
2018-10-24 | Wed | HW Coax beampipe; | regen BB; | L2-539; L2-541; |  |  | 5C75-004 FF and freq check; |  |  |  | LSFC-10; LSFC-10 Cu weld prep; PJ1-1 5u BCP; | L2 BLA body (2C, 2D); L2 BLA ceramic (2C, 2D); LSFC-10; |  | EIC1 setup; | HPR1: OOC HPR2: L2-094 PJ1-1 |  | BLA visual (x2); C100-RI-009 sealing; |  | RDT-10; | RDT-10; | HB-071 120C/24h | EZ-SSC-03 sensors; |  | D1: SIC C2K D2: RF Cables C/T D3: D4: D5: D6: RDT-14 L/C/T/W D7: EIC5 warm; D8: AES-007 pull; HB-071 L/C4K; | J1.3-015- Magnet install, berry bolts | CM13 - Tuners/ steppers-piezos CM14- UCM Mate to CS, fit/weld 2 phase piping | CM08- Alignment in VV | CM-10- Remove Inst. Flanges & WC's LCLS F05- taking sensor date, move to WS5 | C100-06- Grind lockdowns/tuner stacks CM04- WS6 Instrumentation flanges, ship cap test fit CM12- WS6-IDLE | C100-RI-016 - In for HV removal
2018-10-25 | Thu | LSFC-12 beam tube to cell; LSFC-09 repair | BLA 2C, 2D bodies; | L2 Bellows; L2-539; C75 DL bodies (x4) |  |  | 5C75-004 FF and freq check; 5C75-005 FF and freq check | BLA 2C, 2D ceramics; | C100-RI-009 (FPC); C100 Tophat |  | QPRJN04; Sample plates x3 | EIC1; LSFC-12, LSFC-09; EZ-SSC-04 & HW; C100-RI-027; BPM furnace HW; RA valve x2; |  | EIC1 30u; | HPR1: OOC HPR2: |  |  | IA-110, IA-114 TS Removal | BLA 2A; BLA 2B; L2-532, L2-526, 514 D5; L2-094 D7/8; PJ1-1; | TS28-006; L2-532, L2-526, 514; |  |  | AES-007 fast bleed-->optical inspection; | D1: SIC C/T D2: RF Cables C/T/pull, L/C4K; D3: D4: RDT-10 L/SC4K D5: D6: RDT-14 D7: EIC5 pull; D8: HB-071 C2.10 K/T/W; | J1.3-015- Magnet install, berry bolts | CM13 - Tuners/ steppers-piezos CM14-weld 2 phase piping, return lollipops | CM08- Alignment in VV | CM-10- Remove warm couplers. Beamline reconfig complete LCLS F05- Post ship Alignment | C100-06- Grind lockdowns/tuner stacks, add Wach's CM04- WS6 Instrumentation flanges CM12- WS6-IDLE | C100-RI-016 - In for HV removal
2018-10-26 | Fri | LSFC-10 repair; | BLA 2C, 2D bodies; | C75 DL bodies (x4); L2-Bellows; |  |  | 5C75-005 FF and freq check; L2-543 beadpull; | BLA 2C, 2D ceramics; |  |  | C100-RI-009 (FPC); C100 Tophat; RRR Sheets (6); SC-04, SC-07, SC-08; | bag/N2 BLA 2A BLA 2B; AES-006 parts; SC-04, SC-07, SC-08; TE1AES-022; |  | acid change | HPR1: OOC HPR2: AES-006; SC-07; |  |  | AES-007; IA-110, IA-114 dis inner adapter; EIC5; | CPI-PA-083; CPI-PA-084; | L2-094 ; L2-532, L2-526, 514; PJ1-1; |  |  |  | D1: SIC C/T D2: RF Cables C4K/T/W; D3: D4: RDT-10 SC4K/T/C2K/T/W; D5: D6: RDT-14 pull: D7: EZ-SSC-03 L/thermal cycles; D8: HB-071 C2.0K/T/W; | J1.3-015- Magnet install, berry bolts | CM13 - Tuners/ steppers-piezos CM14-weld 2 phase piping, return lollipops | CM08- Alignment in VV | CM-10- Remove warm couplers. Beamline reconfig complete LCLS F05- Install WC's | C100-06- Grind lockdowns/tuner stacks, add Wach's CM04- WS6 Instrumentation flanges CM12- WS6-IDLE | C100-RI-016 - In for HV removal
2018-10-27 | Sat | [6 empty] | BLA 2C, 2D ceramics;
2018-10-28 | Sun | [6 empty] | BLA 2C, 2D ceramics;
2018-10-29 | Mon | LSFC-10 repair; | BLA 2C, 2D bodies; HB 73 Hardware Prep | L2-539; C75 DL; |  |  | C100 tuning bench swithout: C100-RI-027 | BLA 2C, 2D ceramics; |  |  | RDTTD-01 5u BCP; | RDTTD-01 & HW; EIC1 HW; valves x3; covers |  | acid change | HPR1: OOC HPR2: LSFC-9; HB-072; |  |  | RFD; EZ-SSC-01, EZ-SSC-02, EZ-SSC-05; | SC-07 TS16-003; TE1AES-022 TS16-001; | SC-07; CPI-PA-083; CPI-PA-084; TE1AES-022; |  | L2-532, L2-526, 514 sensors & HOMs; | EIC5 fast bleed -->optical inspection | D1: SIC C/T; D2: RF Cables D3: D4: RDT-10 pull; D5: L2-532, L2-526, 514 L/precool; D6: PJ1-1 L/C2K/T/W; D7: EZ-SSC-03 C2K/T/W (20mg) D8: HB-071 pull; | J1.3-015- Magnet install, berry bolts | CM13 - Tuners/ steppers-piezos CM14-LC 2 phase piping, palletize lollipops | CM08- Alignment in VV | CM-10- Remove warm couplers. LCLS F05- Install WC's | C100-06- Wach's cutting complete, open bridging areas CM04- WS6 Instrumentation flanges CM12- WS6-IDLE | C100-RI-016 - In for HV removal
2018-10-30 | Tue | 96mm BT; | BLA 2C, 2D bodies; | L2-Tuner; L2 Bellows; |  |  | C100-RI-027 | BLA 2C, 2D ceramics; | SC-07; |  |  | SC-07 & HW; SC-08 HW; |  | EZ-SSC-01, EZ-SSC-02, EZ-SSC-05 setup; | HPR1: OOC HPR2: SC-08; RDTTD-01; HB-072; |  | HB-072; | HB-071; |  |  |  | TE1AES-022 sensors; | HB-071 fast bleed-up; | D1: SIC C/T; D2: RF Cables D3: D4: D5: L2-532, L2-526, 514 W/C4K D6: TE1AES-022 L/C2K/T/W (0mg); D7: EZ-SSC-03 warm; D8: | J1.3-015- Magnet install, berry bolts | CM13 - Tuners/ steppers-piezos CM14-LC 2 phase piping, break down rail system | CM08- Alignment in VV | CM-10- Remove warm couplers. LCLS F05- Install WC's, Modify shipping Caps | C100-06- Cut process piping, disconnect beam pipies, remove endcans. CM04- WS6 Instrumentation flanges CM12- WS6-IDLE | C100-RI-016 - In for HV removal Retrieve tooling for HV Welding & C100 CM rework |  |  | Tuner Repair 2L25-7-CMA
2018-10-31 | Wed | 96mm BT; | BLA 2C, 2D bodies; | C100-RI-027; L2 Bellows; |  |  |  | BLA 2C, 2D ceramics; RRR Sheets (6) TE01NS000X2-01, TE01NS000X2-02, 900c 3hrs; |  |  | 96mm BT weld prep (am); DQWR copper brite/ss etch; C75-004, 005 & BT (x4) weld prep (KM to bring from MS); | C100-RI-016; SC-04 HW; Braided tubing; |  | EZ-SSC-01, EZ-SSC-02, EZ-SSC-05 75u; | RDT-10; C100-RI-009; SC-08; |  |  |  | HB-072 D7/8; SC-08 TS16-005; RDTTD-01 TS16-001; RDT10; |  |  | L2-094 sensors & HOMs; EZ-SSC-03 leak check & sensors; |  | D1: SIC C/T; D2: RF Cables warm; D3: D4: D5: L2-532, L2-526, 514 C2K/T; D6: D7: EZ-SSC-03 pull; EZ-SSC-03 L/thermal cycles; D8: L2-094 L/C4K | J1.3-015- Magnet install, berry bolts, 2 phase piping | CM13 - Tuners/ steppers-piezos CM14- LC 2 phase piping, Solder magnet leads | CM08- IDLE | CM-10- Remove warm couplers. LCLS F05- Install WC's, test fit shipping Caps, Install coupler restraints? | C100-06- Move to WS2, retrieve tooling from warehouses CM04- WS6-IDLE CM12- WS6-IDLE
2018-11-01 | Thu | 96mm BT; C75-00x BT; |  | L2 spool; C100-RI-027; |  |  |  | RRR Sheets (6) TE01NS000X2-01, TE01NS000X2-02, 900c 3hrs; |  |  | Nb plate (FM); EIC1 flanges; EZ-SSC-01, EZ-SSC-02, EZ-SSC-05 ext BCP; | wipe down BLA 2C, 2D & boxes; EZ-SSC-01, EZ-SSC-02, EZ-SSC-05; FMCBRA Tubing; EIC1; |  | EZ-SSC-01, EZ-SSC-02, EZ-SSC-05 25u; | HPR1: OOC HPR2: C100-RI-009 |  | C100-RI-009 |  | SC-07 TS16-003; | SC-08; HB-072; RDTTD-01; RDT10; |  | RDT10 sensors; |  | D1: SIC C/T; D2: RF Cables pull; D3: D4: RDT10 L/SC4K; D5: L2-532, L2-526, 514 HOM test/warm; D6: RDTTD-01 L; D7: EZ-SSC-03 thermal cycles/W (0mg) D8: L2-094 C2K/T | J1.3-015- Magnet install, berry bolts, 2 phase piping | CM13 - Tuners/ steppers-piezos CM14- LC 2 phase piping, Solder magnet leads | CM08- IDLE | CM-10- Remove warm couplers. LCLS F05- Install WC's, test fit shipping Caps, Install coupler restraints? | C100-06- Remove tophats, inst. flanges, etc. retrieve tooling from warehouses CM04- WS6-IDLE CM12- WS6-IDLE
2018-11-02 | Fri | C75-00x BT; | DQWR copper brite/ss etch; | L2 probes; C100-RI-027; | [7 empty] | EZ-SSC-01, EZ-SSC-02, EZ-SSC-05 & bag all; C100 lollipops; |  | TE1G-001, TE1G-003 setup; | HPR1: OOC HPR2: |  |  |  | C100-RI-009; | SC-07; | HB-072 120C/24h; | SC-08 sensors; |  | D1: SIC C/T; D2: RF cables pull; D3: D4: RDT10 C2K/T/W; D5: L2-532, L2-526, 514 warm; D6: RDTTD-01 C2K/T/W; D7: EZ-SSC-03 warm; D8: L2-094 warm; | J1.3-015- Magnet install, berry bolts, 2 phase piping | CM13 - Tuners/ steppers-piezos CM14- LC 2 phase piping, Solder magnet leads | CM08- IDLE | CM-10- Remove warm couplers. LCLS F05- test fit shipping Caps, Install coupler restraints | C100-06- Remove Cold Mass from VV CM04- WS6-IDLE CM12- WS6-IDLE
2018-11-03 | Sat | [19 empty] | HB-072 120C/24h;
2018-11-04 | Sun | [19 empty] | HB-072 120C/24h;
2018-11-05 | Mon | C75-004 BT flange; | Reconfig P&E | L2-Bellows; |  |  |  | MAINT | EZ-SSC-001 inspect flanges; |  |  | L2 FPC tools and blanks (x8); BPM HW; RFD2; String cages x2; TE1G-001, TE1G-003; L2 Cav ext rinse (x4); RFD2 manual rinse; |  | TE1G-001, TE1G-003 50u; | HPR1: OOC HPR2: EZ-SSC-001; RFD2; |  | L2 lollipop prep; | L2 BPM sub Dis; EZ-SSC-03 remove from TS28-006; |  | C100-RI-009 failed; | HB-072 120C/24h; | SC-07 sensors; |  | D1: SIC pull; D2: D3: D4: D5: L2-532, L2-526, 514 hold; D6: SC-08 L/C/T (0mg, 2Konly) SRFOps D7: D8: HB-072 L/C4K; | J1.3-015- Magnet install, berry bolts, 2 phase piping | CM13 - Tuners/ steppers-piezos CM14- LC 2 phase piping, Solder magnet leads | CM08- IDLE | CM-10- Remove warm couplers. LCLS F05- test fit shipping Caps, Install coupler restraints, move to WS6 | C100-06- Heat stations, SF Tooling, move VV CM04- WS6-IDLE CM12- WS6-IDLE
2018-11-06 | Tue | ANL CVC; | HB-073 flange inspect/lap; | C100-RI-027; C75-005; |  |  | C100-RI-016; C100-RI-027; | MAINT | TE1G-001, TE1G-003; |  | RDT-2 10u; Cu rod (x8); EZ-SSC-03 ext BCP; | BPM sub and HW; String cages x2; L2 bellows (x5); L2 RA valve; EZ-SSC-03 US & 2bag for shipping; L2 Cav bolt holes (x4); KEKR5 parts; |  | RDT-10, TE1NS001, TE1NS002 setup; | HPR1: OOC HPR2: SC-04; KEKR5; |  | L2 lollipop prep; | C100-RI-009 dis; | RFD2 D5; EZ-SSC-001 TS16-008; |  |  |  | C100-RI-009 fast; L2-x (x4); | D1: SIC L/C/T; D2: D3: D4: D5: L2-532, L2-526, 514 pull; heater maint D6: SC-07 L/C2K/T/W (0mg, 2Konly) PD test; D7: D8: HB-072 C2K/T/W Tom Powers test; | J1.3-015- Magnet install, berry bolts, 2 phase piping | CM13 - Tuners/ steppers-piezos CM14- Solder magnet leads, alignment | CM08- IDLE | CM-10- Remove warm couplers. LCLS F05- Install shipping Caps, Finish instrumentation, move to WS6, short trip to Richmond | C100-06- Heat stations, SF Tooling, move VV CM04- WS6-IDLE CM12- WS6-IDLE |  |  |  | beam studdies; LLRF work;
2018-11-07 | Wed | ANL CVC; | HB-073 flange lap; | C75-005; C100-RI-016; |  |  | EIC-1 | MAINT |  |  | Nb parts 5u (GE); RDT-10, RDT-14 nitric soak; TE1G-003 flange & external BCP; | RDT-10; TE1NS001; TE1NS002; TE1G-003; L2 Cav ext rinse (x4); RDT-14 & HW; C100 HW; EIC1; |  | RDT-10, TE1NS001, TE1NS002 10u; | HPR1: OOC HPR2: LSFC-9; |  | TS28-006 new RGA; L2 lollipop prep; |  | SC-04 TS16-005; KEKR5 TS16-001; | EZ-SSC-001; |  |  | L2-x; | D1: SIC C/T; D2: L2 Bellows L/C4K/T/W D3: D4: D5: D6: EZSSC-001 L/C2K/T/W D7: D8: HB-072 warm; | J1.3-015- Magnet install, berry bolts, 2 phase pipE weld | CM13 - Tuners/ steppers-piezos CM14- Solder magnet leads, alignment | CM08- IDLE | CM-10- Remove warm couplers. LCLS F05- Trip completed, instrumentation fix & download today | C100-06- Lollipop install, move VV CM04- WS6-IDLE CM12- WS6-IDLE | Leak check bellows
2018-11-08 | Thu | ANL CVC; | DL Sputter Nb Anneal | C75-005; L2 bellows; |  |  |  | MAINT |  | HB-073 |  | Nb samples & wire; C75 shearing tool; BLA alingment tooling; M6 bolts; |  | HB-073 setup; | HPR1: OOC HPR2: TE1NS001; EIC1 four passes; |  | IA-114 dis; C75-000 dis; |  | L2 upstream gate valve; LSFC-9 TS16-003; TE1NS001 TS28-004; | RFD2; SC-04; KEKR5; | RFD2 120C/12h; | SC-04 sensors; | L2-x; | D1: SIC C/T; D2: L2 Bellows Pull/L/C4K/T/W D3: D4: D5: D6: KEKR5 L/C2K/T/W D7: D8: HB-072 pull; | J1.3-015- Magnet Alignment, berry bolts, 2 phase pipe weld | CM13 - Tuners Set Limits CM14- Solder magnet leads, alignment | CM08- IDLE | CM10- Remove warm couplers, 1/2 done CM12- Weld RT joint, beamline config for LERF | C100-06- Lollipop install, prep VV CM04- WS6-IDLE LCLS F05- Second trip to Richmand today, truck here 8:30am | Move concrete cryostat?
2018-11-09 | Fri | ANL CVC; | Nb Anneal DL Sputter; L2 bellows & spools; | L2-Bellows C75-004; | C75-000 optical insp.; |  | C75-004; C75-005; | MAINT | C100-RI-009 flange polishing; |  |  | L2 lollipops; L2 Cav bolt holes (x2); |  | HB-073 hold; | HPR1: OOC HPR2: RDT-14, RDT-2; RDT-10; |  | TS28-006 new RGA; |  | EIC1 D3/4; BPM Sub; | LSFC9; TE1NS001 leaked; | RFD2 120C/12h; | LSFC9 sensors; | L2-x; | D1: SIC C/T; D2: D3: D4: D5: D6: SC-04 L/C/T/W (0mg, 2Konly) SRFOPS D7: D8: | J1.3-015-berry bolts, 2 phase pipe weld | CM13 - Tuners Set Limits CM14- Solder magnet leads, alignment | CM08- Move to WS6 | CM10- Remove warm couplers CM12- Weld RT joint, beamline config for LERF | C100-06- Lollipop install, prep VV CM04- WS6-IDLE LCLS F05-Trip to Nebraska today, return Monday | C100-RI-027 HV welding Move concrete cryostat?
2018-11-10 | Sat | [10 empty] | L2 lollipops; L2 Bellows;
2018-11-11 | Sun |  | L2 Spools; | [11 empty] | TE1NS001; | [6 empty] | RFD2 sensors;
2018-11-12 | Mon | ANL CVC; | L2 Spools | L2 Bellows; | HB-071 optical insp.; |  | C75-005; C100-RI-027; | commissioning; |  |  | C100-RI-009 Q-tip FPC flange and tophat; HW Coax weld prep; | HB-073 1%; HB-073 large USC; L2 Bellows (6); L2 Cav bolt holes (x4); EZ-SSC-04 HW; C100-RI-009; 2.2GHz and HW; L2 HW |  | HB-073 60u; | HPR1: OOC HPR2: EZ-SSC-04; |  | EZ-SSC-01 dis; |  | RDT-2; RDT-10; BPM Sub; TE1NS001 TS28-004; | EIC1 failed; |  |  | L2-x; | D1: SIC C/T; D2: D3: D4: D5: RFD2 L; D6: D7: D8: | J1.3-015-berry bolts, 2 phase pipe weld | CM13 - Tuners Set Limits CM14- Solder magnet leads, alignment | CM08- Move to WS6 | CM10- Remove warm couplers CM12- Weld RT joint, beamline config for LERF | C100-06- Lollipop install, prep VV CM04- WS6-IDLE LCLS F05-Trip to Nebraska today, return Monday | C100-RI-027 HV welding Move concrete cryostat?
2018-11-13 | Tue |  |  | L2-074; C75-004; L2 Bellows; | AES-007 optical inspection (RG); |  |  | commissioning; |  |  |  | L2 lollipop carriages; L2 Bellows (6); |  | C75-002 setup; | HPR1: OOC HPR2: HB-073 (1p) EZ-SSC-01; IA-114; |  | receive lollipops from chem; C100-RI-009 dirty assy; cage IA-114; |  | EZ-SSC-04 D7/8; | BPM sub; TE1NS001; |  |  | L2-x; | D1: SIC C/T; D2: D3: D4: TE1NS001 L/C2K; D5: RFD2 C4K; D6: RDT-14 L/C2K/T/W D7: D8: | J1.3-015-berry bolts, 2 phase LC | CM13 - Tuners Set Limits CM14- Solder magnet leads, alignment | CM10- Prep for bellows inspection | CM12- beamline config for LERF, Inst. Flanges, RF Waveguides CM04- LC MC line | C100-06- Lollipop install, retrieve tooling CM08- WS6-IDLE LCLS F05- Remove from frame, prep for Alignment | C100-RI-027 HV welding
2018-11-14 | Wed | ANL CVC; | TE01 Cavity L2 Bellows | CALIBRATION; L2 bellows & spools; |  |  | C75-004; |  |  | HB-073 | S/S flanges (x20); Cu components (x20); RDT-2 10u; | L2 Bellows; RDT-10; C75-002; HB-073 bag in N2; |  | C75-002 15u; | HPR1: OOC HPR2: RDT-10; EZ-SSC-01; |  | L2 lollipops; C100-RI-009 dirty assy; HB-072 bag under vacuum; |  | IA-114 TS28-009; RDT-10 TS28-007A; | EZ-SSC-04; C100-RI-009 leaked; EIC1; |  | EZ-SSC-04; | L2-x; | D1: SIC C/T; D2: BNNT Load D3: D4: TE1NS001 T/W; D5: RFD2 C2K/T/W; D6: LSFC9 L/SC4K/C2K/T/W D7: D8: | J1.3-015-berry bolts, 2 phase LC | CM13 - Tuners Set Limits CM14- Solder magnet leads, alignment | CM10- Prep for bellows inspection, out of VV | CM12- beamline config for LERF, Inst. Flanges, RF Waveguides CM04- LC MC line | C100-06- Tooling review, remove SF section CM08- WS6-IDLE LCLS F05- Post ship alignment | C100-RI-027 HV welding
2018-11-15 | Thu | ANL CVC; RF Seperator Power Coupler Cu; | TE01 Cavity | HWCoax-1; |  |  | C75-004; C100-RI-009; | [6 empty] | acid change | HPR1: OOC HPR2: TE1NS002; |  | L2 Bellows conditioning; |  | EZ-SSC-01 TS16-008; | RDT-10; |  | RDT-10 sensors; |  | D1: SIC C/T; D2: BNNT C4K/T D3: RDT-10 load D4: TE1NS001 pull/TS/L/C4K D5: RFD2 warm/cool(?); D6: LSFC9 SC4K/C2K/T/W D7: EZ-SSC-04 L/thermal cycles/C4K; D8: | J1.3-015-berry bolts, 2 phase LC | CM13 - Tuners Set Limits CM14- Solder magnet leads, alignment | CM10- Prep for bellows inspection, out of VV | CM12- beamline config for LERF, Weld conflat on Line C, Inst. Flanges, RF Waveguides CM04- Fastener Check list, Data review | C100-06- Remove SF sections CM08- WS6-IDLE LCLS F05- Move CM onto blocks, Inspect restraints Concrete Cryostat move to lay down yard C100 VV- Move to VAA@1:30PM will require South Crane | C100-RI-027 HV welding/LC
2018-11-16 | Fri | RF Seperator Power Coupler Cu; | TE01 Cavity | L2-145; |  |  | C75-004; |  |  |  | RDT-2 coating HW; C100 probesx2; | C100-RI-009 and HW; RDT-2 parts; |  | HF Spike; | HPR1: OOC HPR2: C100-RI-009; |  | L2 string prep demag; L2 Bellows conditioning; |  | RDT-10 TS28-004; TE1NS002 D6; 2.2GHz D6; | IA-114; EZ-SSC-01; |  | IA-114 sensors; |  | D1: SIC C/T/W; D2: BNNT C2K/T/W D3: RDT-10 pull, check o-rings, RDT-10 L/SC4K/T; D4: TE1NS001 C2K/T/W D5: RFD2 warm D6: EZ-SSC-01 L/C/T/W; D7: EZ-SSC-04 C2K/T/W; D8: IA-114 L/SC4K | J1.3-015-berry bolts, 2 phase LC | CM13 - Tuners Set Limits CM14- Solder magnet leads, alignment | CM10- Prep for bellows inspection, remove Mag shield caps | CM12- beamline config for LERF, Cold Shock conflat on Line C, Inst. Flanges, MC Line LC CM04- Fastener Check list, Data review | C100-06- Remove SF sections CM08- WS6-IDLE LCLS F05- Inspect restraints, install ship caps, Load into frame? | C100-RI-027 HV LC C100-RI-016 HV welding
2018-11-17 | Sat | [15 empty] | L2 US gate;
2018-11-18 | Sun
2018-11-19 | Mon | HWCoax-2 BT; env cavity; | Vac. | C100-RI-027; L2 bellows |  |  | L2-145; L2-064; | Test run (AP); |  | HB-071; |  | RFD2 HW; HWCoax-1; Cryo group headers; |  | HB-071 setup; | HPR1: OOC HPR2: C100-RI-009; |  | C100-RI-009; TS28-010 RGA Replacement; |  |  | TE1NS002; |  |  | RFD2 | D1: RF cable L/C4K/T; D2: BNNT pull, RRR L/C4K; D3: RDT-10 C2K/T/W D4: TE1NS001 pull; map 0mg; EIC1 L/C4K; D5: RFD2 pull; D6: 2.2 GHz L/C2K/T/W100K; D7: EZ-SSC-04 hold; D8: IA-114 C4K/T/W; | J1.3-015-berry bolts, 2 phase LC | CM13 - Tuners Set Limits CM14- Solder magnet leads, alignment | CM10- bellows inspection complete, install mag shield end caps, inst. Check | CM12- beamline config for LERF,Inst Flanges, MC Line LC CM04- Fastener Check list, Data review | C100-06- Cut process piping CM08- WS6-IDLE LCLS F05- on the road to SLAC. | C100-RI-016 HV welding Move LCLS Cryomodules off UITF roof, prep for tile placement Tuesday
2018-11-20 | Tue | env cavity; | Vac. | C100-RI-027; L2-074; |  |  | C100-RI-027; L2-074; J1.3-10 HOMs; | Test run (AP); |  |  | test bolt; | TE1AES-022 (ext wipedown); bellows (x3); HWCoax-1; HB-071 1% USC; HB-071 Di only; |  | HB-071 60u; | HPR1: OOC HPR2: |  | cage L2-1, L2-2 |  | C100-RI-009 D7/8; RFD2; |  |  |  |  | D1: RF cable C4K/test; D2: RRR T/W; D3: RDT-10 hold; D4: EIC1 C2K/T/W; D5: D6: 2.2GHz C2K/T/W ; D7: EZ-SSC-04 C2K/T/W; D8: IA-114 warm; | J1.3-015-berry bolts, 2 phase LC | CM13 - Tuners Set Limits CM14- Solder magnet leads, alignment | CM10- Verify/Tune HOM's, Install caps/lower shields | CM12- beamline config for LERF,Inst Flanges CM04- Fastener Check list, Data review | C100-06- Cut process piping CM08- WS6-IDLE LCLS F05- on the road to SLAC. | C100-RI-016 HV welding Move CM's back to UITF when able
2018-11-21 | Wed | Vac | Vac. | L2-064; |  |  | J1.3-10 HOMs; L2-146; |  |  |  |  | HWCoax-1 (2 hr); |  | SC-07, SC-08, SC-04 setup; | HPR1: OOC HPR2: TE1NS-001; HB-071 (1p) |  | TS28-010 RGA Replacement; |  | TE1AES-022 TS28008; | C100-RI-009; TE1AES-022; |  |  |  | D1: RF cable pull?; D2: RRR pull; D3: RDT-10 pull; D4: EIC1 warm; D5: D6: TE1NS002 L/C2K/T/W; D7: EZ-SSC-04 warm; D8: IA-114 warm; | J1.3-015-berry bolts, 2 phase LC | CM13 - RF Cables, heat stations CM14- Solder magnet leads | CM10- Tune HOM 8A, Install shields, Verify HOM's | CM12- beamline config for LERF,Inst Flanges CM04- Move to WS6 | C100-06- Onto transfer rail CM08- Move to WS5 | C100-RI-016 HV welding Move 2 CM's back to UITF
2018-11-22 | Thu | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2018-11-23 | Fri | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2018-11-24 | Sat
2018-11-25 | Sun | [13 empty] | HPR2: L2-1; L2-2;
2018-11-26 | Mon | TE-01; | TE01 Cavity | L2-146; L2-064 demag; | HB-071; |  | C100-RI-027; |  |  | HB-071; |  |  |  | SC-07, SC-08, SC-04 hold for chiller repair; | HPR1: OOC HPR2: L2-3; L2-4; |  |  |  | L2-1, L2-2 to rail; | RFD2; | TE1AES-022 75C/4h; | C100-RI-009 test stand sensors; |  | D1: D2: D3: D4: D5: D6: LSFC-09 L/C2K/T/W; D7: EZ-SSC-04 pull; D8: IA-114 pull; C100-RI-009 L/C4K; | J1.3-015-berry bolts, 2 phase LC | CM13 - RF Cables, heat stations CM14- Solder magnet leads | CM10- Tune HOM 8A, Install shields, Verify HOM's | CM12- beamline config for LERF,Inst Flanges CM08- Prep 4 WC insall | C100-06- Cut Process piping, Onto transfer rail CM04- Prep 4 ship | C100-RI-016 HV welding
2018-11-27 | Tue | DQWC-01; DQWC-02; | DQWC-01; DQWC-02; | L2-Tuner; L2-146 demag; | EIC5 optical inspection (FM); |  | C100-RI-027; | Nb samples (PD) 1000C/3h; | C100-RI-027 |  |  | HB-071; HPR wand head, gasket, nozzles, retainers; |  | SC-07, SC-08, SC-04 60u; | HPR1: OOC HPR2: L2-5; L2-6; |  |  |  | L2-3, L2-4 to rail; |  |  | RFD2 sensors; TE1AES-022 sensors; |  | D1: D2: L2 Bellows L/C4K D3: D4: EIC1 pull; PJN7-1 L/C4K (no liquid)/W D5: RFD2 L/C4K D6: TE1NS001 L/C2K/T/W D7: TE1AES-022 Load; D8: C100-RI-009 C2K/T/W; | J1.3-015-berry bolts, 2 phase LC | CM13 - Inst, RF Cables, heat stations CM14- Solder magnet leads | CM10- Weld shields, MLI, into VV | CM12- beamline config for LERF,Inst Flanges CM08- WC install | C100-06- On transfer rail. CM04- Prep 4 ship | C100-RI-016 HV welding VV from BC
2018-11-28 | Wed |  | DQWC-01; DQWC-02; | C100-RI-027; L2 Tuners; |  |  | C100-RI-027; | Nb samples (PD) 1000C/3h; | C100-RI-027; RDT-10; |  | Nb plates and ring 20um; Samples and HW for Nb3Sn; | SC-07, SC-08, SC-04; C100-RI-027 flange; long bellows (x6); drive nut & Screw; vac parts hoses (x3), Tees (x30); |  | SC-07, SC-08, SC-04 20u; | HPR1: OOC HPR2: L2-7; L2-8; |  | TS-28 test stands; L2 Bellows test; |  | L2-5, L2-6 to rail; |  | EIC1 120C/12h; |  |  | D1: Nb3Sn L/C4K D2: L2 Bellows pull; L2 Bellows L/C4K D3: D4: PJN7-1 C4K (no liquid)/W D5: RFD2 C2K/T/W D6: D7: TE1AES-022 C4K; D8: C100-RI-009 warm; | J1.3-015-berry bolts, 2 phase LC | CM13 - Inst, RF Cables, heat stations CM14- Solder magnet leads | CM10- Weld shields, MLI, into VV | CM12- beamline config for LERF,Inst Flanges CM08- WC install | C100-06- On transfer rail. CM04- Prep 4 ship | C100-RI-016 HV welding VV from BC
2018-11-29 | Thu | DQWC-01; DQWC-02; Caps |  | C75 DL; C100-RI-016; C100-RI-027; |  |  | L2-146 | Nb samples (PD) 800C/3h; | C100-RI-027; |  |  | C100-RI-027; HB-071 parts; C100 black covers (x8 sets); |  | RDT-14, RDTTD-01, RDT-10 setup; | HPR1: OOC HPR2: HB-071; TE1NS-002; RDT-02 |  | cage C100-RI-027; |  | L2-7, L2-8 to rail; |  | EIC1 120C/12h; |  |  | All dewars warming by COB; D1: Nb3Sn test/warm D2: L2 Bellows pull; D3: D4: PJN7-1 C4K (no liquid)/W D5: RFD2 warm; D6: D7: TE1AES-022 C2K/T/W; D8: C100-RI-009 pull; | J1.3-015-berry bolts, Mag shields | CM13 - Inst, RF Cables, heat stations CM14- Solder magnet leads | CM10- Survey and alignment | CM12- beamline config for LERF,Inst Flanges CM08- WC install | C100-06- On transfer rail. CM04- Prep 4 ship | C100-RI-016 HV welding VV inspect; prep for Demag
2018-11-30 | Fri | Ari Caps |  | L2-Tuner; | [6 empty] | C100 HOM FT (x2)?; | C100-RI-027 parts; |  |  | HPR1: OOC HPR2: C100-RI-027; HB-071; |  | HB-071; | RFD2; | J1.3-16 |  |  |  | RFD2 fast; C100-RI-009 fast; | CTF Maint Down, planned power outage AM D1: D2: D3: D4: PJN7-1 warm; D5: RFD2 pull; D6: D7: TE1AES-022 warm; D8: | J1.3-015-berry bolts, Mag shields | CM13 - Inst, RF Cables, heat stations CM14- Solder magnet leads | CM10- Survey and alignment | CM12- beamline config for LERF,Inst Flanges CM08- WC install | C100-06- On transfer rail. CM04- Prep 4 ship | C100-RI-016 HV welding VV inspect; prep for Demag
2018-12-01 | Sat | [17 empty] | HB-071 D5;
2018-12-02 | Sun
2018-12-03 | Mon | Ari Caps |  | C100-RI-016; L2-Bellows | [6 empty] | Nb furnace caps weld prep; HW COAX beam tubes & flanges (x8); | RDT-14, RDTTD-01, RDT-10; Elbows (x3); HW COAX beam tubes & flanges (x8); | HWCoax setup; | RDT-14, RDTTD-01, RDT-10 30u; | HPR1: OOC HPR2: C100-RI-027; |  | C100-RI-027; |  | bag J1.3-16; | HB-071; | HB-071 120C/24h; |  |  | CTF Maint Down D1: D2: D3: D4: D5: D6: D7: D8: | J1.3-015-berry bolts, MLI, Mag shields | CM13 - Inst, RF Cables, heat stations CM14- Solder magnet leads | CM10- Move to WS6 | CM12- Prep for LERF CM08- MC Line, VV port | C100-06- On transfer rail. CM04- Prep 4 ship | C100-RI-016 LC VV inspect; prep for Demag
2018-12-04 | Tue | Ari Caps; HW Coax BT; | cleanup run BB, LB; | L2-VV032; C100-RI-016; |  |  | C100-RI-016; C100-RI-xx; |  |  |  | Nb covers 5u; Nb furnace caps weld prep; | L2 Lg pipes, valve, & Tees; | HWCoax 50um (no flip); | AES-007 setup | HPR1: OOC HPR2: RDT-10; TE1NS-001; | 0 |  | IA-114; | C100-RI-027 D7/8; |  | HB-071 120C/24h; |  |  | PSS cert AM D1: D2: D3: D4: D5: D6: D7: D8: | J1.3-015-berry bolts, Mag shields | CM13 - Inst, RF Cables, heat stations CM14- Clamp magnet leads | VV 32- onto Cantilever, demag | CM12- Deliver to LERF, truck here 7:30a.m. CM08- MC Line, VV port | C100-06- On transfer rail. CM04- Prep 4 ship, install caps | VV inspect; prep for Demag LERF, Deliver CM, install bellows on CM1 US end, move into place.
2018-12-05 | Wed | Ari Caps | BB maint.; | C100-RI-xx; C75 DL; C100-RI-yy; |  |  | C100-RI-yy; | VESDA Test |  |  | Nb covers GE 5um; | AES-007; |  | AES-007 20u | HPR1: OOC HPR2: |  | VESDA | VESDA | RDT-10 (AM); TE1NS-001 (AM); VESDA | J1.3-16; C100-RI-027; | HB-071 120C/24h; |  |  | D1: D2: D3: D4: D5: D6: D7: D8: | J1.3-015-berry bolts, Mag shields | CM13 - Inst, RF Cables, heat stations CM14- Clamp magnet leads | VV 32- onto Cantilever, demag | CM12- Deliver to LERF, truck here 7:30a.m. CM08- MC Line, VV port | C100-06- On transfer rail. CM04- Prep 4 ship, install caps | LERF, Align CM's
2018-12-06 | Thu | Ari Caps | L2 Bellows; | C100-RI-039; C100-RI-056; |  |  | C100-RI-039; C100-RI-056; |  |  |  | C75-002 (30min Nitric); |  |  |  | HPR1: OOC HPR2: |  | TS28-010 RGA swap; |  |  |  |  | C100-RI-027 HOMs and test stand magnetometer; |  | D1: D2: D3: D4: D5: field map D6: D7: D8: field map | J1.3-015-berry bolts, Mag shields | CM13 - Inst, RF Cables, heat stations CM14- Clamp magnet leads | CM13 move from WS3 | CM08- MC Line, VV port | C100-06- On transfer rail. CM04- Prep 4 ship, Final instrumentation and RF checks | CM12- Work in LERF, Align CM's
2018-12-07 | Fri | Ari Caps | L2 Bellows; | L2-Tuner; C100-RI-039; C100-RI-056; C100-RI-055; |  |  | C100-RI-056; |  | C100-RI-039; C100-RI-056; |  | Nb covers 5u; Cu Cylinder & discs x2 | Cu & SS end plates; |  |  | HPR1: OOC HPR2: AES-006; C75-002; |  |  |  |  | TS28-010; J1.3-16; |  |  |  | D1: D2: D3: D4: field map D5: HB-071 L/pull D6: D7: D8: C100-RI-027 L; | J1.3-015-berry bolts, Mag shields | CM13 - Move to WS4 CM14- Alignment | CM13 move from WS3 | CM08- MC Line, VV port, Pressure test | C100-06- On transfer rack CM04- Prep 4 ship, Final RF checks; Put in frame | CM12- Work in LERF, Align CM's
2018-12-08 | Sat
2018-12-09 | Sun
2018-12-10 | Mon | Furnace caps; | muload Cu cavity; | C100-RI-039; |  |  |  |  | C100-RI-056; |  |  | C100-RI-039 and parts; Berry bolts, nuts, threaded sleeves; Beam pipe and valve; |  | RTD-10, TE1NS-001, TE1NS-002 setup; | HPR1: OOC HPR2: AES-006; |  | AES-006; |  |  | TS28-010; J1.3-16; |  |  |  | D1: SIC L; D2: D3: EIC1 L; D4: PJN7-1 hold; D5: D6: D7: D8: C100-RI-027 hold; | J1.3-015-berry bolts, Mag shields | CM13 - Move to WS4 CM14- Alignment | CM13 move from WS3 | CM08- MC Line, VV port, Pressure test | C100-06- On transfer rack | CM12- Work in LERF, Align CM's
2018-12-11 | Tue | Maint; | muload Cu cavity; | C100-RI-056; C100-RI-053; |  |  | C100-53; C100-RI-055; |  | C100 tophat; |  | furnace caps 10u; RDT-2 15u; | C100-RI-056; |  | RTD-10, TE1NS-001, TE1NS-002 hold; | HPR1: OOC HPR2: C100-RI-039; |  | L2 cavity inventory; |  | AES-006 cart; |  |  |  |  | D1: SIC hold; D2: D3: EIC1 hold; D4: PJN7-1 hold; D5: maint; D6: D7: D8: C100-RI-027 hold; | J1.3-015-berry bolts, Mag shields | CM15- UCM from Blue Crab, Visual Insp. CM14- Alignment | CM13 -Instrumentation, RF cables | CM08- MC Line, VV port, Pressure test CM10- Inst. Tee's, VV side port welding | C100-06- Prep Tee's, move rail? | LERF- Cryo can connections made up, LC, Beam pipe mods complete-cleaning/bake UCM into North Loading Zone
2018-12-12 | Wed | VAC | muload Cu cavity; TE011; | C100-RI-051; C100-RI-055; |  |  | C100-RI-053; | furnace caps 1000C/3h; | C100-RI-055; |  | TE011 (Cu plates, Beam tubes, probe tip) | RTD-10, TE1NS-001, TE1NS-002; C100-RI-056 and parts; TE011 (probe, feed through); clamps x8; |  | RTD-10, TE1NS-001, TE1NS-002 30u; | HPR1: OOC HPR2: C100-RI-056; C100-RI-039; |  | C100-RI-039; | [6 empty] | D1: SIC hold; D2: D3: EIC1 hold; D4: PJN7-1 hold; D5: maint; D6: D7: D8: C100-RI-027 hold; | J1.3-015-berry bolts, Mag shields | CM15- UCM Visual Insp. CM14- Alignment | CM13 -Instrumentation, RF cables | CM08- MC Line, VV port, Pressure test CM10- Inst. Tee's, VV side port welding, VV Relief | C100-06- Prep Tee's, move rail? | LERF- LC Cryo can Connections, Beam pipe mods complete-cleaning/bake
2018-12-13 | Thu | Vac | TE011; | C100-RI-049; |  |  |  | furnace caps 1000C/3h; | C100-RI-053; |  |  | C100-RI-055 and parts; C100 HV plugs; |  | IA-114 setup; | HPR1: OOC HPR2: C100-RI-056; |  | C100-RI-056; |  | C100-RI-039 D3; |  |  |  |  | D1: SIC hold; D2: D3: EIC1 hold; D4: PJN7-1; D5: maint; D6: D7: D8: C100-RI-027 hold; | J1.3-015-Add HV fluxgates | CM15- UCM Visual Insp., Fastener spread sheet CM14- Alignment, heat stations | CM13 -inside VV and covered for weekend scaffold work | CM08- MC Line, complete JT welding CM10- VV side port welding, VV Relief | C100-06- Prep HV Tee's, Rework 50k shield MLI | LERF- Valve game-all BL vacs on DS IP Modify GHRP Spool Test fit 50k shields Complete guard vacuum circuit and Cryo can plumbing
2018-12-14 | Fri |  | TE011; | C100-RI-049 (2); C100-RI-053 (1); |  |  | C100-RI-051; | cleanup run 1200C; |  |  | furnace caps 5u; Nb covers 10u (GE); SC-04, SC-08, EZ-SSC-05 ext 5u; C100-RI-053 HOMs & F.P. | C100 HV plugs; IA-114; C75-002; C100-RI-053 HOMs & F.P. |  | IA-114 15u; | HPR1: OOC HPR2: RDT-10; RDT-2 |  |  |  |  | C100-RI-039; |  | C100-RI-039 HOMs & test stand magnetometer only; |  | D1: SIC hold; D2: D3: EIC1 hold; D4: PJN7-1 pull; D5: HB-071 L; D6: D7: D8: C100-RI-027 hold; | J1.3-015-Add HV fluxgates, finish fastener spreadsheet | CM15- UCM Visual Insp., demag CM14- heat stations, prep for tuners | CM13 -inside VV and covered for weekend scaffold work | CM08- LC MC Line, complete JT welding CM10- VV side port welding, VV Relief | C100-06- Prep HV Tee's, Rework 50k shield MLI | LERF- Install GHRP spool and cryo jumpers, establish vacuums
2018-12-15 | Sat
2018-12-16 | Sun | [10 empty] | C100-RI-053 & Field Probe; |  |  | HPR2: C100-RI-056; C100-RI-053;
2018-12-17 | Mon | maint | TE011; | L2-bellow; C100-RI-051; |  |  | C75-000 probes; C100-RI-049; | SC-04, SC-08, EZ-SSC-05 & samples load; | C100-RI-051; |  | SC-04, SC-08, EZ-SSC-05 ext 5u; | C75-002 parts; |  |  | HPR1: OOC HPR2: C75-002; C100-RI-053; |  | C100-RI-053; TS28009 turbo |  | C100-RI-056 D7; |  |  |  |  | CTF Operational D1: SIC C2K/T; D2: D3: EIC1 C4K; D4: C100-RI-039 L; D5: HB-071 hold; D6: D7: D8: C100-RI-027 C4K; | J1.3-015-Add HV fluxgates, finish fastener spreadsheet | CM15- UCM Visual Insp., demag CM14- heat stations, prep for tuners | CM13 -inside VV and covered for weekend scaffold work | CM08- LC MC Line, complete JT welding CM10- VV side port welding, VV Relief | C100-06- Prep HV Tee's, Rework 50k shield MLI | LERF- establish vacuums
2018-12-18 | Tue |  | TE011; | C100-RI-47; C100-RI-51; |  |  | C100-RI-43 | SC-04, SC-08, EZ-SSC-05 3N60; | C100-RI-049; |  |  | coupler hook x2; unistrut; Chem Room Maint. |  |  | HPR1: OOC HPR2: C75-002; |  | C75-002; |  | C100-RI-053; | C100-RI-056; TS28009 turbo |  |  |  | D1: SIC C2K/T; D2: L2 Bellows L/C4K/W; D3: EIC1 hold; D4: C100-RI-039 C4K; D5: HB-071 hold; D6: D7: D8: C100-RI-027 C2K/T/W; | J1.3-015-Finish Checklist, finish fastener spreadsheet | CM15- UCM Ready CM14- heat stations, prep for tuners | CM13 -inside VV and covered for weekend scaffold work | CM08- Instrumentation flanges CM10- VV side port welding, VV Relief | C100-06- Prep HV Tee's, Rework 50k shield MLI | LERF- MLI, 50K shields, Instrumentation
2018-12-19 | Wed |  |  | L2 bellows; |  |  | C100-RI-47 | SC-04, SC-08, EZ-SSC-05 3N60; AP samples 800C/3h/2N0; | C100-RI-43; |  | AMV Nb samples 15u x60; C100-RI-051 HOMs | C100-RI-051 & parts; RDT-10; |  |  | HPR1: OOC HPR2: C75-002; C100-RI-051; RDT-10; |  |  |  | RDT-10 D6; C75-002 (TS28-006 D7/8); | C100-RI-053; |  | C100-RI-056 HOMs & test stand magnetometer only; C100-RI-053; |  | D1: SIC 2K; D2: D3: EIC1 hold 4K; D4: C100-RI-039 C2K/T/W; D5: HB-071 C4K; D6: D7: C100-RI-056 L/C4K; D8: C100-RI-027 warm; | J1.3-015-Finish Checklist, finish fastener spreadsheet | CM15- Ready CM14- heat stations, prep for tuners | CM13 -inside VV and covered for weekend scaffold work | CM08- Instrumentation flanges CM10- VV side port welding, VV Relief | C100-06- Prep HV Tee's, Rework 50k shield MLI | LERF- MLI, 50K shields, Instrumentation
2018-12-20 | Thu |  | TE011; | L2-Tuner; C100-RI-43; |  |  | C-100's | AP samples 800C/3h/2N0; | C100-RI-051 tophat; C100-RI-043; |  |  | 2 3/4" gaskets x100; string brakes; cavity blanks & clamps; C100-RI-051 HOMs; Room Maint. |  | Acid Change (Sulfuric In); SC-04, SC-08, EZ-SSC-05 setup; | HPR1: OOC HPR2: |  | C100-RI-051; |  |  | RDT-10; C75-002; |  | No Crane; RDT-10 sensors; |  | D1: SIC C2K/T; D2: D3: EIC1 warm; D4: C100-RI-039 warm; D5: HB-071 C2K (pm); D6: RDT-10 L/SC4K; D7: C100-RI-056 C2K/T/W; D8: C100-RI-027 warm; | J1.3-016 - roll out | CM15- Mate UCM to CS15 CM14- heat stations, prep for tuners | No Work - ACW | CM08- Instrumentation flanges, remove tuner ports CM10- VV side port welding, VV Relief | C100-06- Prep HV Tee's, Rework 50k shield MLI | LERF- Start ins vac and leak check Work with FNAL visitors to instal/remove M mounts on J7
2018-12-21 | Fri | maint | shutting down | L2 bellows; |  |  | Cleanup | AP samples 800C/3h/2N0; |  |  | AP sample box 10u; | Room Maint. |  | SC-04, SC-08, EZ-SSC-05 hold; | HPR1: OOC HPR2: |  | CL | EA | N | U | P | No Crane |  | D1: SIC C2K/T/W; D2: D3: EIC1 warm; D4: C100-RI-039 warm; D5: HB-071 T/W; D6: RDT-10 C2K/T/W; D7: C100-RI-056 warm; D8: C100-RI-027 warm; | J1.3-016 - Bellows restraints | CM15- Mate UCM to CS15 CM14- heat stations, prep for tuners | NO Work - ACW | CM08- Low pressure test CM10- VV Relief | C100-06- Prep HV Tee's, Rework 50k shield MLI, build C100 fixture | LERF- Start ins vac and leak check
2018-12-22 | Sat | [25 empty] | NO Work - ACW
2018-12-23 | Sun | [25 empty] | NO Work - ACW
2018-12-24 | Mon | [13 empty] | HPR1: OOC HPR2: | [11 empty] | No Work - ACW
2018-12-25 | Tue | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8: |  |  | No Work - ACW
2018-12-26 | Wed | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8: |  |  | NO Work - ACW
2018-12-27 | Thu | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8: |  |  | No Work - ACW
2018-12-28 | Fri | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8: |  |  | NO Work - ACW
2018-12-29 | Sat | [25 empty] | NO Work - ACW
2018-12-30 | Sun | [25 empty] | NO Work - ACW
2018-12-31 | Mon | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8: |  |  | No Work - ACW
2019-01-01 | Tue | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8: |  |  | No Work - ACW
2019-01-02 | Wed | startup | startup | L2 bellows C100-RI-047 |  |  |  | AP samples (x3) 800C/3h/2N6; | C100-RI-047 |  |  | C100 cavity tree; Nb Rods, Nb plates, HW; spool, blanks, reliefs, VCR fittings; |  | Chill Sump then Spike; | HPR1: OOC HPR2: clean-up; C100-RI-051; | [7 empty] | C100-RI-027 fast; | D1: SIC Hold D2: D3: EIC1 C4K; D4: C100-RI-039 pull; D5: HB-071 pull; D6: RDT-10 pull; D7: C100-RI-056 pull; D8: C100-RI-027 pull; C100-RI-053 L/C4K | J1.3-016 - RF measurements, Process piping pre fab | CM15- Mate UCM to CS CM14- heat stations, prep for tuners | CM13- Uncover, remove from VV | CM08- Low pressure test, Prep for Ship CM10- VV Relief, Warm Couplers | C100-06- Rework 50k shield MLI, Complete rework list | LERF- Open CC Ins Vac bellows, investigate leak path
2019-01-03 | Thu | testing, testing… | cleanup run BB, LB; | L2 bellows |  |  | C100-RI-027 FPC; | AP samples (x3) 800C/3h/2N6; | C100-RI-047 |  | HW port tubes & end caps weld prep; C100-RI-043 HOM; FM plate; | C100-RI-056 parts; C100-RI-043; SC-04, SC-08, EZ-SSC-05; Beam dump, flange, ceramic break; FM plate; RDTTD-01 parts; C100 blanks & gaskets; |  | SC-04, SC-08, EZ-SSC-05 8u; | HPR1: OOC HPR2: C100-RI-056; RDTTD-01; |  | C100-RI-043 cage; | C100-RI-056; | C100-RI-051 D7/8; |  |  |  | C100-RI-039 slow; | UITF Cooldown D1: SIC hold D2: D3: EIC1 hold; D4: D5: D6: D7: D8: C100-RI-053 C2K/T | J1.3-016 - Alignment, RF measurements, Process piping pre fab | CM15- Mate UCM to CS CM14- heat stations, tuners | CM13- Instrumentation, Fastener List | CM08- Siphon Tubes, E&L flanges, Low pressure test, Prep for Ship CM10- Warm Couplers, Weld shipping restraints | C100-06- Rework 50k shield MLI, Complete rework list | LERF- Leak check Ins Vac
2019-01-04 | Fri |  | Nb heat treatment; | L2 Tuners L2 Bellows |  |  |  | maintenance; |  |  | HW end caps weld prep; UP cavity chamber, HW, Nb Rods; TE1G001, ring, flange; | HB-073; C100-RI-043 parts; |  |  | HPR1: OOC HPR2: C100-RI-043; C100-RI-056 (brackets to backteck); |  | Cage HB-073; C100-RI-056; |  | RDT-TD01 D6; | C100-RI-051; |  | C100-RI-051 magnetometers and HOMs; |  | D1: SIC hold D2: D3: EIC1 C2K/T/W; D4: PJN7-1 L/C4K D5: D6: D7: D8: C100-RI-053 HOM/warm | J1.3-016 - Alignment, RF measurements, Process piping pre fab | CM15- Mate UCM to CS CM14- heat stations, tuners | CM13- Instrumentation, Fastener List | CM08- Siphon Tubes, E&L flanges, Low pressure test, Prep for Ship CM10- Warm Couplers | C100-06- Rework 50k shield MLI, Complete rework list | LERF- Leak check Ins Vac
2019-01-05 | Sat | [15 empty] | C100-RI-043; |  | C100-RI-056;
2019-01-06 | Sun | [13 empty] | HPR2: C100-RI-043;
2019-01-07 | Mon | HWCoax-2 end caps; | L2 bellows; | L2-bellows |  |  | C100-RI-016 |  |  |  |  | C100-RI-027 wipe; C100 blanks, gaskets, HV plugs; C100-RI-027 parts; gas fittings; bolts; |  |  | HPR1: OOC HPR2: C100-RI-027; |  |  |  | C100-RI-043 D7/8; | C100-RI-056 D3/4; |  | C100-RI-056 magnetometers and HOMs; |  | D1: D2: D3: EIC1 pull; D4: PJN7-1 pull; D5: D6: RDT-TD01 L; D7: C100-RI-051 L/C4K D8: C100-RI-053 pull; | J1.3-016 -Install SPQA, RF measurements, Process piping pre fab | CM15- Mate UCM to CS CM14- heat stations, tuners | CM13- Instrumentation, Fastener List | CM08- Prep for Ship, M-Mounts CM10- Warm Couplers | C100-06- Rework 50k shield MLI, Complete rework list | LERF- Leak check Ins Vac, Punch List
2019-01-08 | Tue | HWCoax-2 end caps; | L2 bellows; | L2-spools |  |  | J1.3-016 passbands; |  |  |  | FM plate; SC-04 beam line flanges; EZ-SSC-05 HF rinse; | HB-073 parts; SC-04 parts; |  |  | HPR1: OOC HPR2: HB-073; C100-RI-027; |  | C100-RI-027; | IA-110; |  | C100-RI-043; |  | C100-RI-043 magnetometers and HOMs; C75-002 cernox; |  | D1: D2: D3: C100-RI-056 L/C4K D4: PJN7-1 L; D5: D6: RDT-TD01 hold; D7: C100-RI-051 C2K/T; D8: | J1.3-016 -Install SPQA, RF measurements, Weld process piping | CM15- Mate UCM to CS CM14- heat stations, tuners-steppers | CM13- Instrumentation, Fastener List | CM08- Prep for Ship, VV side port, Piping leak check CM10- Warm Couplers | C100-06- Rework 50k shield MLI, Complete rework list | LERF- Leak check Ins Vac, Punch List R&D weld- Jiquan
2019-01-09 | Wed | TE1G001, ring, flange; | Nb heat treatment; | L2-DS Spools; L2-tuners; C100-RI-016; |  |  | J1.3-016 passbands; C100-RI-047; |  |  |  | EZ-SSC-05 HF x10; HWCoax-1 weld prep; ANL Cu tubes; | HWCoax-1; Brackets, compression fittings; |  | IA-110 setup | HPR1: OOC HPR2: SC-04 HB-073; |  | HB-073; |  | C100-RI-027 D7/8; |  |  |  | C100-RI-053 slow; | D1: D2: Hall probe cal L; D3: C100-RI-056 C2K/T/W D4: PJN7-1 hold; D5: D5-->D3; D6: RDT-TD01 hold; D7: C100-RI-051 D7-->D8; D8: C100-RI-043 L/C4K | J1.3-016 -Install SPQA, RF measurements, Weld process piping | CM15- Mate UCM to CS CM14- heat stations, tuners-steppers | CM13- Instrumentation, Fastener List | CM08- Prep for Ship, VV side port, Piping leak check CM10- Warm Couplers | C100-06- Rework 50k shield MLI, Complete rework list | LERF- Leak check Ins Vac, Punch List
2019-01-10 | Thu | HWCoax-1; |  | C100-RI-047; C100-RI-049; L2-tuners |  |  | C100-RI-047; C100-RI-049; |  | C75 warm window; C100-RI-047; |  | HW Nb Plate; Nb box; E Z-SSC-05 1h HF; RDL-02 & caps & tube; |  |  | IA-110 15u; | HPR1: OOC HPR2: RDT-10 |  |  | EIC1; | HB-073 D7/8; SC-04 D6; | C100-RI-027; SC-04; |  | C100-RI-027 magnetometers & HOMs; |  | D1: D2: Hall probe cal C2K; D3: C100-RI-056 D3-->D8 warm; D4: PJN7-1 hold; D5: D6: RDT-TD01 C/T; D7: C100-RI-051 pull; C100-RI-027 L/C4K; D8: C100-RI-043 C2K/T; | J1.3-016 -Install SPQA, RF measurements, Weld process piping | CM15- Mate UCM to CS CM14- heat stations, tuners-steppers | CM13- Instrumentation, Fastener List | CM08- Prep for Ship, VV side port CM10- Warm Couplers | C100-06- Rework 50k shield MLI, Complete rework list | LERF- Leak check Ins Vac, Circuit conditioning, return gas to CHL, Punch List
2019-01-11 | Fri | ANL Cu tubes; |  | C100-RI-049; C100-RI-047; L2-bellows |  |  | J1.3-013 HOMs; C100-RI-049; C100-RI-047; | Sample Run | SCIB |  |  | MC line pipes, Tees, flanges, valve & HW; C100-RI-056 wipe; C100-RI-056 HW; |  |  | HPR1: OOC HPR2: RDL-02 RDT-10, |  |  | C100-RI-053 test HW; |  | HB-073; | HB-073 120C/24h; | SC-04 sensors; |  | D1: D2: Hall probe cal W70K; D3: C100-RI-056 pull; D4: PJN7-1 C4K/W; D5: D6: SC-04 L/C/T D7: C100-RI-027 C2K/T/W D8: C100-RI-043 D8-->D7, W; | J1.3-016 -Install SPQA, RF measurements, Weld process piping, Weld Ti Sheilds | CM15- Mate UCM to CS CM14- heat stations, tuners-steppers | CM13- Instrumentation, Fastener List | CM08- Prep for Ship, VV side port CM10- Warm Couplers | C100-06- Rework 50k shield MLI, Complete rework list | LERF- Leak check Ins Vac, Circuit conditioning, return gas to CHL, Punch List
2019-01-12 | Sat | [13 empty] | HPR2: C100-RI-056 (6Pass); | [5 empty] | HB-073 120C/24h; |  |  | D4: PJN7-1 C4K/W;
2019-01-13 | Sun | [17 empty] | C100-RI-056 D3/4; |  |  |  |  | D4: PJN7-1 C4K/W;
2019-01-14 | Mon | ANL Cu tubes; | HD-Ice; | L2-bellows; C100-RI-055; C100-RI-047; |  |  | C100-RI-049; | RDL-02 800C/3h, 140C/48h/25mTorr N2; | SCIB; window; |  | HWCoax-2 weld prep; AP sample box; FH Cu cavity and flanges x2; | C100-RI-049; SCIB and HW; HD-Ice Cu coil; Pipe fittings; |  |  | HPR1: OOC HPR2: G2; |  |  |  | RDT-10 TS-16-001; G2 TS-16-008; | C100-RI-056; |  | C100-RI-056; |  | D1: SIC C/T; D2: D3: C100-RI-056 L/C4K; D4: PJN7-1 SC/W; D5: D6: SC-04 pull; FHC3A L/SC4K D7: C100-RI-027 D7-->D8, warm; D8: C100-RI-043 pull; HB-073 L/C2K; | J1.3-016 -Install SPQA, Weld process piping, Weld Ti Sheilds | CM15- Mate UCM to CS, Cavity 1 tuner CM14- heat stations, tuners-steppers | CM13- Instrumentation, Fastener List | CM08- Prep for Ship, Move to WS6 CM10- Warm Couplers, MC line, LPT | C100-06- Rework list | LERF- Install new Ins Vac gauge, calibrate EV's
2019-01-15 | Tue | ANL Cu tubes; | HD-Ice; | L2 bellows; L2 spools; |  |  | C100-RI-055; C100-RI-047; | RDL-02 800C/3h, 140C/48h/25mTorr N2; |  |  | TE1G-001 flash BCP & flanges; C100 HOMs | C100-RI-049 HW; TE1G-001 HW; L2 Gaskets; |  |  | HPR1: OOC HPR2: C100-RI-049 LSFC-12; |  | cage C100-RI-055; |  |  | RDT-10 D6; |  |  | C100-RI-051; C100-RI-043; | D1: SIC C/T; D2: D3: C100-RI-056 C2K/T; D4: D5: D6: FHC3A C2K/T/W; D7: C100-RI-027 pull; C75-002 L/SC4K/T D8: HB-073 T/W; | J1.3-016 -Install SPQA, Weld process piping | CM15- Remove lollipops CM14- heat stations, tuners-steppers | CM13- Tune HOM's, Install lower shields, Fastener List | CM08- Prep for Ship, Move to WS6 CM10- MC line, LPT, E&L Flanges | C100-06- Rework list | LERF- calibrate EV's, U-tubes?
2019-01-16 | Wed | LSFC-10 roll; clean-up? |  | L2-spools L2-tuner |  |  | C100-RI-047; | RDL-02 800C/3h, 140C/48h/25mTorr N2; |  |  | GE Nb flanges & S/S conflats; TE-011 Cu; nb foils x10; SC-09, SC-10, SC-11, SC-12 10u external; | C100-RI-055 & HW; TE-011 & parts; L2 FPC & HW; lamp; | ACW | ACW | HPR1: OOC HPR2: IA-110; C100-RI-055; C100-RI-049 (10Pass); |  | cage IA-110; C100-RI-049; |  | LSFC-12; |  |  | RDT-10 D6 Sensors and Thermometry; |  | D1: SIC C/T; D2: D3: C100-RI-056 warm; D4: D5: D6: G2 L/C4K/W; D7: C75-002 SC4K/T/W; D8: HB-073 warm | J1.3-016 -Align SPQA, Weld process piping, Ti sheets | CM15- Remove lollipops CM14- heat stations, tuners-steppers | CM13- Tune HOM's, Install lower shields, Fastener List | CM08- Prep for Ship, Move to WS6 CM10- MC line, LPT, E&L Flanges | C100-06- Rework list | LERF- calibrate EV's, U-tubes?
2019-01-17 | Thu | HWCoax-2; |  | C100-RI-043 L2 Mag shield |  |  | J1.3-013 HOMs; C100-RI-043; | RDL-02 800C/3h, 140C/48h/25mTorr N2; |  |  | HW coax pipe; TE-011 Cu Bright; NbTi flanges (x2); | C100-RI-047; L2 FPC; | ACW | ACW | HPR1: OOC HPR2: TE1G-001; C100-RI-055 (6Pass) mid-morning; |  | C100-RI-055; | TS28-002 rebuild; | [5 empty] | D1: SIC C/T; D2: D3: C100-RI-056 warm D4: D5: D6: G2 C4K/T/W D7: C75-002 SCK/T; D8: HB-073 pull; | J1.3-016 -Align SPQA, Weld process piping, Ti sheets, berry bolts | CM15- Fit/weld process piping, MLI CM14- 2K leak check, mag shields | CM13- Tune HOM's, Install lower shields, Fastener List | CM08- Prep for Ship CM10- MC line LC, LPT, E&L Flanges | C100-06- Rework list, traveler mods | LERF- CHL Trip this morning, reliefs venting Weld HPR cage
2019-01-18 | Fri | HWCoax-2; LSFC-10 roll; |  | C100-WG spools L2 Mag shield |  |  | J1.3-013 HOMs; C100-RI-043; |  | C100 leak test fixtures; | C75-004; C75-005; | EZ-SSC-05 HF internal rinse (up to 10x); SC-13, SC-14, SC-15, SC-16 10u external; RDT-06; | C100-RI-047 HW; L2 CM HW; SC-08 HW; RDL-02; Tee & zero reducer; | ACW | ACW | HPR1: OOC HPR2: C100-RI-047 RDL-02; SC-08; |  |  |  | C100-RI-055; C100-RI-049 D7/8; RDL-02; TE1G-001 TS16-008; | L2 FPC; RDL-02; |  |  | C100-RI-027; C100-RI-056; | D1: SIC C/T; D2: D3: C100-RI-056 pull; D4: D5: D6: RDT-10 L/SC2K/T D7: C75-002 C2K/T/W; D8: | J1.3-016 -Align SPQA, berry bolts | CM15- Fit/weld process piping, MLI CM14- 2K leak check, mag shields | CM13- Tune HOM's, Install lower shields, Fastener List | CM08- Prep for Ship CM10- MC line LC, LPT, E&L Flanges | C100-06- Rework list, traveler mods | LERF- CHL Trip this morning, reliefs venting Weld HPR cage
2019-01-19 | Sat
2019-01-20 | Sun
2019-01-21 | Mon | [9 empty] | ACW |  |  |  | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2019-01-22 | Tue | HWCoax-2; | C100 WG & windows; | L2 Tuners; L2 mag shields; |  |  | J1.3-013 HOMs; |  | C100 leak test fixtures; |  | ACW | L2 CM HW; Bellows x5; M8 nitronic bolts (x16); RA valves (x8); | ACW | ACW | HPR1: OOC HPR2: RDT-06; C100-RI-047 (10Pass); |  | C100-RI-047 |  |  | L2 FPC; C100-RI-049; TE1G-001; |  |  |  | D1: SIC warm; D2: RRR L/C/T; D3: D4: PJN7-1 SC/W; D5: D6: RDL-02 L/C2K/T/W; D7: D8: | J1.3-016 -Align SPQA, berry bolts; leak check; | CM15- Fit/weld process piping, MLI CM14- mag shields, inst | CM13- Tune HOM's, Install lower shields, Fastener List | CM08- Prep for Ship CM10- Tune WC's, Inst. | C100-06- Rework list, traveler mods | LERF- Temp bump Weld HPR carts
2019-01-23 | Wed | HWCoax-2; | C100 WG & windows; |  |  |  | J1.3-008 HOMs; J1.3-013 HOMs; | test run; |  |  | ACW | C100-RI-043; LSFC-12 HW; L2 parts wipe down; |  |  | HPR1: OOC HPR2: C100-RI-049; RG nozzle test; |  | cage C100-RI-043; | C100-RI-055 and -049 bottom flange only; SC-04; | SC-08 TS16-003 (auto pump test); | SC-08; |  | SC-08 sensors; |  | D1: SIC pull; D2: RRR W/T; D3: D4: PJN7-1 SC/W; D5: D6: TE1G-001 L/C/T; D7: D8: | J1.3-016 -Align SPQA, berry bolts, 2K LC,Inst | CM15- Fit/weld process piping, MLI CM14-RF Cables, inst | CM13- Install lower shields, Verify HOM's, Fastener List | CM08- Inserts/Caps/ship inst. ,RF Data CM10- Tune WC's, Inst. | C100-06- Rework list, traveler mods | Weld HPR carts Align new 4 poster
2019-01-24 | Thu | Cu; | C100 WG & windows; | C100 Cavity WG (x2); L2 mag shields; |  |  |  | RDT-6 TBD; |  |  |  | SC-04 & HW; C100 Gate Valves (x2); |  |  | HPR1: OOC HPR2: LSFC-12-03; C100-RI-055; RG nozzle test; |  |  | C100 rail tooling; | C100-RI-047 D3/4; C100-RI-049 D7/8; |  |  |  |  | D1: Nb3Sn sample L/C4K D2: RRR W/T; D3: D4: PJN7-1 SC/W; D5: D6: SC-08 L/C2K/T/W (0mG); D7: D8: | J1.3-016 - Instrumentation, berry bolts, MLI, mag shields | CM15- Fit/weld process piping, MLI CM14-RF Cables, inst | CM13- Weld lower shields, MLI, into VV | CM08- Prep for Ship, into trailer tomorrw CM10- Install M-Mounts, Punch List | C100-06- Rework list, traveler mods | Weld HPR carts Move remaining modules off UITF
2019-01-25 | Fri | Cu; | C100 WG & windows; | C100 Cavity WG (x5); |  |  |  | RDT-6 TBD; |  |  | Nb box; Nb samples HF; | C100 Gate Valve HW; |  |  | HPR1: OOC HPR2: SC-04; TE1G-001 |  |  | C100 rail tooling; | LSFC-12-03 TS16-005 auto-pump; C100-RI-055 D7/8; | C100-RI-047; C100-RI-049; |  | C100-RI-047; C100-RI-049; |  | D1: Nb3Sn sample C4K D2: D3: C100-RI-047 L/C4K; D4: PJN7-1 pull; D5: D6: SC-08 2K/T/W (20mG); D7: D8: | J1.3-016 - MLI, mag shields | CM15- Fit/weld process piping, MLI CM14-RF Cables, inst | CM13- MLI, into VV | CM08- Prep for Ship, into trailer CM10- Install M-Mounts, Punch List | C100-06- Rework list, traveler mods | Weld HPR carts
2019-01-26 | Sat | [10 empty] | C100 parts; |  |  | HPR2: C100-RI-049 (2P, PM) |  | C100-RI-049 | C100-RI-049 |  | C100-RI-055; |  | C100-RI-055; |  | D3: C100-RI-047 C2K/T; D7: D8: | [5 empty] | Ship J1.3-08 to SLAC
2019-01-27 | Sun | [22 empty] | D3: C100-RI-047 D3-->D7, warm; D7: D8:
2019-01-28 | Mon | Cu; | C100 WG & windows; | C100 Cavity WG (x4); C100 GuardVac WG (x2) |  |  |  | AP sample 800C 3N60; |  |  | PD Nb samples x15; AMV Nb & Cu QPR x6; | C100-RI-043 HW; C100 rail tooling; C75-004; Cylinder x6, electrodesx24, flanges x12; |  |  | HPR1: OOC HPR2: C100-RI-043 (6p); |  |  |  | C100-RI-049 TS28-010; TE1G-001 TS16-008; | LSFC-12; |  | LSFC-12; | C100-RI-055 slow; C100-RI-047 fast; | D1: SIC L/C/T D2: D3: C100-RI-047 pull; D4: D5: D6: LSFC-12 L/SC2K/T (0mG); D7: D8: | J1.3-016 - MLI, mag shields | CM15- Fit/weld process piping, MLI CM14-RF Cables, inst | CM13- MLI, into VV | CM08- on the road; CM10- Install M-Mounts, Punch List | C100-06- Rework list, traveler mods | Weld HPR carts
2019-01-29 | Tue |  | C100 WG & windows; | C100 Window assy (x8); C100 GuardVac WG (x2) |  |  | J1.3-14 HOM tuning; | AP sample 800C 3N60; Test Run; | C100 - TH-01 & 06 |  | FM plate; C100 HOMs x4; | C100-RI-055 ext wipe; C100-RI-055 & -047 HW; C100 string prep; C100 - TH-01 & 06 & HW; |  |  | HPR1: OOC HPR2: RDT-06; C100-RI-055; C100-RI-043; |  | C100-RI-043; | C100-RI-047 | RDT-06 D6; | C100-RI-049; TE1G-001; RDT-06; |  | C100-RI-049 | C100-RI-049 slow; | D1: SIC C/T D2: D3: D4: D5: D6: LSFC-12 warm; D7: FHC3A L/sC2K/T/W; D8: | J1.3-016 - HV MLI, mag shields | CM15- LC process piping, Magnet lead soldering CM14- Tune HOM's, clearance lower shields | CM13- Ready for alignment in VV |  | C100-06- Rework list, traveler mods | Weld HPR carts CM10- Shipping Punch List
2019-01-30 | Wed | HW Coax-2 | C100 WG & windows; | C100 GuardVac WG (x3) L2-Bellows |  |  | J1.3-14 HOM tuning; |  |  |  |  | LSF5-1 wipe USC RG; LSF5-1 HW; C100 string prep; C100-RI-047 ext wipe; |  |  | HPR1: OOC HPR2: nozzle change; LSF5-1 (3P); nozzle change; C100-RI-055; |  | C100-RI-055; |  | C100-RI-043 D3/4; |  |  |  |  | CTF compressor/kinney 1 test D1: SIC hold D2: D3: D4: D5: D6: LSFC-12 pull; TE1G-001 L; D7: FHC3A T/W; D8: | J1.3-016 - MLI, mag shields | CM15- LC process piping CM14- Tune HOM's, clearance lower shields | CM13- alignment in VV |  | C100-06- Rework list, traveler mods | Weld HPR carts CM10- Shipping Punch List
2019-01-31 | Thu | HWCoax-2 | C100 WG & windows; | C100 GuardVac WG (x3); L2 spools; |  |  | 5C75-002 w/GE; |  |  |  | HWCoax-2 tube weld prep; C100-RI-049 HOMs; | C100 gate valve HW; C100 string prep; L2-536 ext rinse; LSFC12-3 parts; |  |  | HPR1: OOC HPR2: C100-RI-047; LSFC12-3; |  |  | C100-RI-049 | LSF5-1 TS28-011; C100-RI-055 D3/4; SC-04 TS28-007; | C100-RI-043; |  | C100-RI-043; |  | D1: SIC C/T D2: D3: D4: D5: D6: RDT-06 L/C/T/W D7: FHC3A hold; D8: C100-RI-043 L/C4K; | J1.3-016 - MLI, mag shields | CM15- LC process piping CM14- Tune HOM's, clearance lower shields | CM13- alignment in VV |  | C100-06- Rework list, traveler mods | Weld HPR carts CM10- Shipping Punch List
2019-02-01 | Fri | HW Coax-2 | C100 WG & windows; | L2-Bellows; L2 VV; |  |  | 5C75-002 w/GE; |  |  |  |  | C100 string prep; L2-538 ext rinse; C100 windows x8; |  |  | HPR1: OOC HPR2: C100-RI-049 C100-RI-047; |  | C100-RI-047; |  | LSFC 12-3 TS16-005 | LSF5-1; C100-RI-055; SC-04; |  | C100-RI-055; SC-04 sensors; LSF5-1 to VSA; |  | D1: SIC C/T D2: D3: C100-RI-055 L/C4K; D4: D5: D6: TE1G-001 L/C2K/T/W; D7: FHC3A pull; D8: C100-RI-043 C2K/T/W; | J1.3-016 - Fastener Spread sheet | CM15- LC process piping, Magnet lead soldering-heat stations CM14-Verify HOM's, weld lower shields | CM14- VV from Blue Crab, Demag | CM13- Warm couplers, Beam pipe prep, JT fitment | C100-06- Rework list, traveler mods | Weld HPR carts CEBAF BPM welding CM10- Shipping Punch List UCM from Blue Crab
2019-02-02 | Sat | [17 empty] | C100-RI-047;
2019-02-03 | Sun
2019-02-04 | Mon | HW Coax-2 | C100 WG & windows; | LSF9-1 HC (x6); L2-Spools; C100-WG (x4) |  |  | 5C75-002 w/GE; |  | C50 blank flanges (x2); |  |  | C100 string prep; L2-539 ext rinse; RDTTD-01 & parts; C100 WG x2; C100 Cu gaskets; Tubing x3; L2CASS HW; 6' flange x2; |  |  | HPR1: OOC HPR2: C100-RI-049 |  | C100-RI-049; C100 gate valves; |  |  | C100-RI-047; |  | C100-RI-047 sensors & HOMs; LSFC12-3 sensors; | C100-RI-043 slow; | D1: D2: D3: C100-RI-055 C2K/T/W; D4: D5: D6: D7: SC-04 L/C2K/T/W100K (0mG) D8: C100-RI-043 pull; C100-RI-047 L/C4K; | J1.3-016 - Move to WS3, UCM to WS3, Inspect UCM | CM15- LC process piping, Magnet lead heat stations, Move to East 4 poster CM14- Move to WS4 | CM14- MLI, Into VV | CM13- Warm couplers, JT fitment, Install jumpers/GHRP cap, Weld ship hold down hardware | C100-06- Rework list, traveler mods | Weld HPR carts CM10- Shipping Punch List
2019-02-05 | Tue | HW Coax-2 | Nb anneal; | LSF9-1 HC (x7); C100 WG; L2-UCM | [6 empty] | C50 blank flanges (x2); | C100 string prep; C100 WG x6; L2 CM beam pipes, Tees, flanges; |  |  | HPR1: OOC HPR2: RDTTD-01; |  |  | L2-D5; | C100-RI-049 D3/4; | LSFC12-3; |  |  |  | D1: SIC pull, Nb3Sn L/C4K/T D2: D3: C100-RI-055 warm; D4: D5: D6: D7: SC-04 warm; D8: C100-RI-047 C2K/T/W; | J1.3-016 - UCM to WS3, Inspect UCM, Fastener SS | CM15- LC process piping, Weld PT caps, Magnet lead heat stations | CM14- MLI, Into VV | CM13- Warm couplers, JT fitment, LC jumpers/GHRP cap, Weld ship hold down hardware | C100-06- Rework list, traveler mods | Weld HPR carts CM10- Shipping Punch List
2019-02-06 | Wed | HW Coax-2 | Nb anneal; | LSF9-1 HC (x7); L2-Spools; L2-UCM; |  |  | J1.3-10 HOMs; | test run; | C100-RI-055 FPC tophat; |  |  | C100 string prep; Berry Bolts; C100 bolts; C100-RI-055 HW & tophat; C100-RI-055 wipe; |  |  | HPR1: OOC HPR2: C100-RI-055 overnight (10P); |  | C100 gate valves; C100 WGs; | C100-RI-055; L2 D5 unload; | RDTTD-01; | C100-RI-049; |  | C100-RI-049; | C100-RI-055 fast; | D1: Nb3Sn D2: D3: C100-RI-055 pull; C100-RI-049 L/C4K; D4: D5: D6: D7: SC-04 sC2K/T/W (20mG); D8: C100-RI-047 warm; | J1.3-016 - Inspect UCM, Fastener SS | CM15- LC process piping, Weld PT caps, Magnet lead heat stations | CM14- MLI, Into VV | CM13- Warm couplers, JT fitment, LC jumpers/GHRP cap, Weld ship hold down hardware | C100-06- Rework list, traveler mods | Weld HPR carts CM10- Shipping Punch List
2019-02-07 | Thu | weld testing |  | L2-spools; LSF9-1 HC |  |  | J1.3-10 HOMs; |  |  |  |  | C100 string prep; C100-RI-047 HW; BCP box & stand; roll cart; C100 WG boxes; |  |  | HPR1: OOC HPR2: |  | C100 gate valves; C100 WGs; | C100-RI-047; |  | RDTTD-01; |  |  | C100-RI-047 fast; | D1: Nb3Sn L/C/T D2: D3: C100-RI-049 C2K/T/W; D4: D5: D6: RDTTD-01 L; D7: SC-04 warm; D8: C100-RI-047 pull; | J1.3-016 - Inspect UCM, Fastener SS | CM15- LC/PT process piping, Magnet lead heat stations | CM14-Into VV, Ready for alignment | CM13- Warm couplers, Weld ship hold down hardware, Inst flanges | C100-06- Rework list, traveler mods | Weld HPR carts CM10- Shipping Punch List, retune HOM's, Machine shipping inserts
2019-02-08 | Fri | weld testing | Cu anneal | L2-Bellows |  |  | J1.3-10 HOMs; |  |  |  | C50 flange; | C100 string prep; cages; |  |  | HPR1: OOC HPR2: C100-RI-055; |  | C100-RI-055 TS28-004; C100 WGs; |  | L2-536 D5; L2-538 D5; L2-539 D5; |  |  | LSFC12-3 sensors; |  | D1: D2: D3: C100-RI-049 pull; D4: D5: D6: RDTTD-01 C2K/T/W; D7: SC-04 hold; D8: | J1.3-016 - Fastener Spread Sheet | CM15- LC/PT process piping | CM14-Alignment in VV | CM13- Warm couplers, Weld ship hold down hardware, Inst flanges | C100-06- Rework list, traveler mods | Weld HPR carts CM10- Shipping Punch List
2019-02-09 | Sat | [17 empty] | C100-RI-055 D3/4;
2019-02-10 | Sun
2019-02-11 | Mon | LSFC10 Cu | mini CF (GE); | LSF9-1 HC (x7); | [6 empty] | FM Nb plate; GE Nb sheet; | C100 string prep; L2 FPC cups, valves, & HW; Cu gaskets (x15); Sample chamber HW; |  |  | HPR1: OOC HPR2: |  | C100 WG/windows; |  |  | C100-RI-055; L2-D5; |  | LSF5-1 sensors; L2-D5 HOMs & sensors; | C100-RI-055 slow; | D1: D2: D3: D4: D5: D6: LSFC12-3 L/hold D7: SC-04 hold; D8: | J1.3-016 - Bearing blocks,Cav 1 tuner | CM15- LC/PT process piping repair | CM14- Inst tee's, open shield door mli | CM13- Inst flanges, Testing cap, beam line work, Bayonet box, mc line | C100-06- Rework list, traveler mods, routing forms done, clean parts | CM10- Shipping Punch List, Install ship caps
2019-02-12 | Tue | LSFC10 Cu | tensile buttons; | L2 BLA; C100 Windows; LSF9-1 HC (x5); | [6 empty] | Nb sample chamber; Nb plate (FM); | C100 string prep; |  |  | HPR1: OOC HPR2: |  | cage C100-8; cage C100-7; WG/windows; |  | C100-RI-055 D3/4; | C100-RI-055; |  | C100-RI-055 sensors & HOMs; |  | D1: SIC L/C/T D2: RF Cables L/C4K/T D3: C100-RI-055 L/C4K; D4: D5: L2-536, L2-538, L2-539 L/precool/W->100K/C4K; D6: LSFC12-3 SC2K/T/W D7: SC-04 SC2K (20mG); D8: |  | CM15- LC/PT process piping repair J1.3-016 - Bearing blocks,Cav 1 tuner |  | CM13- Inst flanges, Testing cap,Bayonet box, mc line CM14- Inst tee's, open shield door mli, WC's | C100-06- Rework list, traveler mods, routing forms done, clean parts | CM10- Shipping Punch List, Install ship caps Install wheels J1.3-09 at Blue Crab
2019-02-13 | Wed | LSFC10 Cu; HWCoax2; | mini CF (GE); | C100 Windows & WG; |  |  | J1.3-10; | testing | C100 waveguide; |  | Nb sample box; | C100 waveguides & windows; C100 string prep; |  |  | HPR1: OOC HPR2: |  | Cage C100-6; cage C100-5; WG/windows; | [6 empty] | D1: SIC C/T D2: RF Cables C4K/T/W; D3: C100-RI-055 C2K/T/W; D4: D5: L2-536, L2-538, L2-539 C4K; D6: D7: SC-04 T/W; D8: |  | CM15- Weld Process piping repair J1.3-016 - Bearing blocks,Cav 1 tuner, heat stations | CM09- From Blue Crab | CM13- Bayonet box, Process piping leak check, tune WC's CM14- Weld gas gaurds | C100-06- Bench top Cu gasket sealing tests for Secondary WG spool | CM10- Shipping Punch List. CM09- Back from Blue Crab
2019-02-14 | Thu | FM plate; | mini CF (GE); Nb plate (FM); | C100 Windows & WG & gaskets; |  |  | L2-077; | testing | C100 waveguide; |  | RDTTD-02 and caps; Nb samples 60 x100um (AP); | C100 waveguides x2 & windows x3; C100 string prep; rings; HPR cart; |  |  | HPR1: OOC HPR2: RDTTD-02; |  | WG/windows; | [6 empty] | D1: SIC C/T D2: RF Cables hold; D3: C100-RI-055 warm/pull; D4: D5: L2-536, L2-538, L2-539 C2K/T; D6: D7: SC-04 warm; D8: |  | CM15- PT/LC Process piping repair J1.3-016 - Bearing blocks,Cav 1 tuner, heat stations | CM09- Transport to N 4 Poster | CM13- Bayonet box, Process piping leak check, tune WC's CM14- Weld gas gaurds | C100-06- Bench top Cu gasket sealing tests for Secondary WG spool | CM10- Shipping Punch List. Shipping Frame into the bldg.
2019-02-15 | Fri | FM plate; | Nb plate (FM); | C100 Windows & WG & gaskets; |  |  | L2-073; | testing; RDTTD-02; | K-24 (PD SC); C100 WG; |  |  | L2-541; C100 waveguides & windows; C100 string prep; |  |  | HPR1: OOC HPR2: TE1G-003; |  | WG/windows; | C100-RI-055; |  |  |  |  | LSF5-1 sensor by RG; C100-RI-055 slow; | D1: SIC C/T D2: RF Cables hold; D3: D4: LSF5-1 L/C4K; D5: L2-536, L2-538, L2-539 HOM survey, D5-->D4? Warm; D6: D7: SC-04 pull; D8: load |  | CM15- PT/LC Process piping repair J1.3-016 - Cav 1 tuner, heat stations, weld process piping | CM09- Transport to N 4 Poster | CM13- Bayonet box, Process piping leak check, tune WC's CM14- Weld gas gaurds | C100-06- Bench top Cu gasket sealing tests for Secondary WG spool | CM10- Module into frame. Prep for ship tomorrow.
2019-02-16 | Sat | [15 empty] | WG/windows; | [10 empty] | RT JT Weld CM13 |  | Ship CM10 to SLAC
2019-02-17 | Sun
2019-02-18 | Mon |  |  | L2-077; C100 WG and Windows; |  |  |  | RDTTD-02; |  |  | LSFC-12-03 w/AMV; Crucible, cover, container; Nb coupons x30; | C75-002 USC Liquinox, USC DIW; C75-002 HW wipe and blow down; LSFC-12-03; Oil Injection Hdr; Ion pump & misc; C100 gaskets; C100 windows & WG; |  |  | HPR1: OOC HPR2: |  |  |  | L2-541 D5; |  |  |  |  | D1: SIC C/T/W D2: RRR L/C/T D3: D4: LSF5-1 warm; D5: D6: TE1G-003 L/C/T/W; D7: D8: load |  | CM15- Alignment J1.3-016 - Cav 1 tuner, heat stations, weld process piping | CM09- Remove Tuners | CM13- Into CMTF, Evac ins Vac CM14- WC's, beampipe prep | C100-06- Bench top Cu gasket sealing tests for Secondary WG spool | CM10- On it's way to SLAC
2019-02-19 | Tue | LSFC-10; |  | L2-077 De-mag; C100 WG and Windows; L2-073; |  |  | L2-073; |  |  |  | LSFC-12-03; FM Nb plate | LSFC-12-03; Coupler HW; C100 windows & WG; |  |  | Contingency HPR2: RDTTD-02; C75-002; |  | WG/windows; |  | RDTTD-02 |  |  |  |  | D1: SIC P/L D2: RRR/C/T D3: D4: LSF5-1 C2K/T/W D5: D6: D7: D8: load |  | CM15- Alignment J1.3-016 - Cav 1 tuner, weld process piping | CM09- Remove Tuners | CM13- Prep for cooldown CM14- WC's, beampipe prep | C100-06- Bench top Cu gasket sealing tests for Secondary WG spool | CM10- On it's way to SLAC
2019-02-20 | Wed | maint | C100 WG and Windows; cleaning run; | C100 WG and Windows; L2-bellows; | [7 empty] | L2-073; L2-077; CM pipes, Tees, Flanges, HW; C100 windows & WG; |  |  | Contingency HPR2: TE1NS-001; |  | WG/windows; |  | C75-002; |  |  |  |  | D1: SIC C/T D2: Nb3Sn CPW L/C2K D3: D4: LSF5-1 pull/L/C4K D5: D6: RDTTD-02 L/C/T/W D7: D8: load |  | CM15- Alignment/Tuners J1.3-016 - weld process piping, remove lollipops | CM09- Remove Tuners | CM13- Prep for cooldown, Ins Vac LC CM14- WC's, beampipe prep | C100-06- Bench top Cu gasket sealing tests for Secondary WG spool | Align North 4 poster
2019-02-21 | Thu | maint; Nb; | Bronze sample (GE); | L2-bellows; L2-spools; L2 BLA; |  |  | L2? |  |  |  | HWCoax-2 pipe & flanges (x2); RDTTD-02 nitric soak & HF rinse; | L2-073; L2-077; HWCoax-2; L2 Bellows (x4); RDTTD-02; CM Assy RA valves (x7), flanges, pipes, HW; |  | K-24 Setup; | HPR1: OOC HPR2: Contengency |  | WG/windows; |  | L2-073, L2-077 D5; | C75-002 (leak); |  |  |  | D1: SIC C/T D2: Nb3Sn CPW C4K D3: D4: LSF5-1 L/C2K/T D5: D6: D7: load D8: warming |  | CM15- Tuners J1.3-016 - weld process piping, remove lollipops | CM09- Remove Tuners | CM13- Prep for cooldown, Ins Vac LC, return gas CTF CM14- WC's, beampipe prep | C100-06- Bench top Cu gasket sealing tests for Secondary WG spool | North 4 poster rail lockdown
2019-02-22 | Fri | HWCoax-2 | Bronze sample; | L2-BLA; L2 Bellows |  |  | L2-345; L2-346; |  |  |  |  | K-24; L2 Bellows (x2); Berry bolts; conflat tee; L2 FPC PICs; |  | K-24 30u; | HPR2: RDTTD-02 |  | WG/windows; |  | RDTTD-02; | L2 D5; C75-002; |  |  |  | U-tubes/CMTF cooldown D1: SIC C/T D2: Nb3Sn CPW C2K D3: D4: LSF5-1 warm D5: D6: D7: D8: |  | CM15- Steppers/piezos/set J1.3-016 - weld/LC process piping | CM09- prep for move | CM13- Ins Vac LC, U-tubes 9 a .m. CM14- WC's, beampipe prep | C100-06- Bench top Cu gasket sealing tests | North 4 poster rail lockdown/align
2019-02-23 | Sat | [13 empty] | HPR2:
2019-02-24 | Sun | [13 empty] | HPR2:
2019-02-25 | Mon | HWCoax-2 | Bronze sample; | L2-BLA; L2 Bellows; L2-345; | [6 empty] | Bronze sample (GE); s/s flange; |  |  |  | HPR1: OOC HPR2: C100-RI-043; C100-7; K-24 |  | C100 WG |  |  |  |  | L2 D5 sensors & HOMs; C75-002; |  | CMTF pump D1: SIC C2K/T D2: Nb3Sn Pull, D3: D4: D5: D6: RDTTD-02 L/C/T/W D7: D8: C75-002 L |  | CM15- Heat stations, MLI, 2K pumpdown J1.3-016 - LC process piping, Solder magnet leads | CM09- Move to N4P | CM13- CMTF@4K CM14- WC's, DS Testing cap | C100-06- Prep tooling | North 4 poster rail lockdown/align Modify Cu strapping for VEP
2019-02-26 | Tue | Nb heat treatment | Bronze sample; | L2-Bellows; L2-078; L2-086; |  |  | L2-346 bead pull; L2-078; L2-086; |  |  |  | RDT-2 15u & HW; | RDT-2; CM Assy WG x4; TE1NS-002; |  |  | HPR1: OOC HPR2: C100-6; C100-5; RDT-2; |  | cage C100-RI-051; cage C100-3; |  | C100-8(043); C100-7; K-24; |  |  |  |  | D1: SIC C/T D2: RF Cables L/C4K; D3: D4: D5: L2-073, L2-077, L2-541 L/pre cool; D6: D7: D8: C75-002 SC/T |  | CM15- Heat stations, MLI, 2K pumpdown/lc J1.3-16 - LC process piping, Solder magnet leads |  | CM14- WC's, DS Testing cap, weld restraint hardware CM07- Remove MC Line, Inst flanges | C100-06- Prep tooling, Mod Travelers | CM09- Install lollipop tooling onto disassembly rail
2019-02-27 | Wed | Nb heat treatment | L2 Bellows; | L2-BLA; L2-086; |  |  | L2-078; L2-086; |  |  |  |  | L2-345; L2 bellows; CM Assy WG x4; Neoprene gaskets; bellow hose, lead screw, drive nut; HPR carts x4; |  |  | HPR1: OOC HPR2: TE1NS-002; C100-RI-051; C100-3; |  | cage C100-2; cage C100-1; |  | C100-6; C100-5; |  |  |  |  | D1: SIC P/L D2: RF Cables W/P/L D3: D4: D5: L2-073, L2-077, L2-541 W ->100K/C4K; D6: K-24 L/C/T/W; D7: D8: C75-002 warm; |  | CM15- Heat stations, MLI J1.3-16 - LC process piping, Solder magnet leads |  | CM14- WC's, DS Testing cap CM07- Remove MC Line, Inst flanges | C100-06- Prep tooling, Mod Travelers
2019-02-28 | Thu | Nb heat treatment | maint; Bronze sample; | L2-BLA; L2-343; L2-344; |  |  | L2-343; L2-344; |  |  |  | TE1G001 nitric flanges; | Injector Puck Assy; L2-086; L2-078; L2-clamps; bolts; |  |  | HPR1: OOC HPR2: C100-2; C100-1; |  |  |  | C100-4(051); C100-3; RDT-2 & TE1NS-002; |  |  |  |  | D1: SIC C/T D2: RF Cables 4K; D3: D4: D5: L2-073, L2-077, L2-541 C2K/T; D6: D7: D8: C75-002 pull; |  | CM15- Alignment, MLI CM16 - LC process piping, Solder magnet leads | CM09- Idle | CM14- WC's, DS Testing cap CM07- Remove WC's, Inst flanges | C100-06- Prep tooling, Mod Travelers | Hardware on order for N. 4 poster, replace hardware, off-site load test
2019-03-01 | Fri | HWCoax2 | Bronze sample; | L2-BLA; L2-343; L2-344; |  |  |  | 900C 3h; | Flanges; |  |  | Viewer parts; Quarts window; 2 3/4 flange & connector x5; |  | SC-04, SC-08, EZ_SSC-05 setup; | HPR1: OOC HPR2: LSFC12-04; TE1G001; |  |  |  | C100-2; C100-1; LSFC12-04; |  |  |  |  | D1: SIC C/T D2: RF Cables 4K; D3: D4: D5: L2-073, L2-077, L2-541 T/W D6: D7: D8: |  | CM15- MLI, Fastener spread sheet CM16 - LC process piping, Solder magnet leads | CM09- Idle | CM14- MC Line, DS Ion pump, Bayonet box CM07- Remove WC's, Inst flanges | C100-06- Prep tooling, Mod Travelers, RF spool leak test fixture ready | replace hardware on N4P
2019-03-02 | Sat
2019-03-03 | Sun
2019-03-04 | Mon | LSFC10 | L2 Bellows; | L2-Bellows; L2 BLA L2-085; |  |  | L2-085; | maint; |  |  | HW (UP); Flanges (AMV); LSFC-12 (help); TD5 ext BCP; | RFD2 LPR; FPC, gasket, flange; RFD-2; RFD-2 HW; |  | SC-04, SC-08, EZ_SSC-05 40u | HPR1: OOC HPR2: maint 4h am |  |  |  |  | C100-6R; |  |  |  | CMTF U-tubes a.m. fast cooldown D1: SIC hold; D2: RRR L; D3: D4: D5: L2-073, L2-077, L2-541 hold; D6: D7: D8: C75-002 L; |  | CM15- MLI, Fastener spread sheet, RF cables CM16 - Solder magnet leads & heat station | CM09- Idle | CM14- MC Line, 2K LC CM07- Remove WC's, Inst flanges | C100-06- Prep tooling, Mod Travelers, RF spool leak test fixture ready | replace hardware on N4P Weld Cold Protection cups-Mircea
2019-03-05 | Tue | LSFC10; | Cu beam tubes; | L2-Bellows; L2-BLA L2-085; L2-105; |  |  | L2-105; | TD5, RDT14 2N6 | Flanges; |  | Ext BCP SC-08, EZ_SSC-05; | RFD2 HW; L2 Gate valves; L2 BPM; SC-04, SC-08, EZ_SSC-05; |  | SC-04, EZ_SSC-05 setup; | HPR1: OOC HPR2: OOC |  | cage RFD2; |  | L2-078, L2-086, L2-345 D5; | C100-6R; |  |  | C100-6R; | CMTF U-tube replacement a.m.; D1: SIC C/T; D2: RRR C/T; D3: D4: D5: L2-073, L2-077, L2-541 hold; D6: D7: D8: C75-002 SC4K; |  | CM15- Fastener spread sheet, RF cables, Instrumentation CM16 - heat station magnet leads | CM09- Move to N4P | CM14- MC Line LC, 2K LC CM07- Remove WC's, Inst flanges | C100-06- Prep tooling, Mod Travelers | Weld Cold Protection cups-Mircea CM09- Move string onto 4 poster
2019-03-06 | Wed | LSFC10; JLEIC-CC; | injector pucks; | L2-BLA; L2-bellows; | [6 empty] | SC-04, EZ_SSC-05 ext BCP | C100 window; SC-04, EZ_SSC-05; |  | SC-04, EZ_SSC-05 20u; | HPR1: OOC HPR2: OOC |  |  |  | L2-078, L2-086, L2-345 D5; | C100-6R; |  |  | L2-536 (FE) | D1: SIC C/T; D2: RRR warm; D3: D4: D5: D6: D7: D8: C75-002 T/C2K/T/W, |  | CM15- Fastener spread sheet, RF cables, prep lower shields CM16 - CS Alignment |  | CM14- Inst flanges, close ins vac, tune WC's CM07- Remove WC's, Inst flanges | C100-06- Prep tooling, Mod Travelers | Weld Cold Protection cups-Mircea CM09- Lower cavs 1-4, cut process piping
2019-03-07 | Thu | HWCoax2 JLEIC-CC; | injector pucks; | L2-BLA; L2-bellows; | [6 empty] | C20 WG strip Cu; TD5, RDT14 6.5u BCP; HWCoax2 weld prep; EZ_SSC-05, SC-04 Nitric flange soak; | L2 Lollipops; L2 BPM kit; GE SC; L2 string parts; C100 items out C/R; |  | SC-08, TE1NS-01 setup | HPR1: OOC HPR2: OOC |  | L2 BPM; L2 Gate valves; Scroll pump rebuild; | [5 empty] | L2-538 (Qualified) | D1: SIC C/T; D2: RRR pull; D3: D4: D5: D6: D7: D8: C75-002 C4K/T/W, |  | CM15- Fastener spread sheet, HOM's CM16 - CS Alignment | CM15- Move here when can | CM14- Inst flanges, close ins vac, evac ins vac CM07- Remove WC's, Inst flanges | C100-06- Prep tooling, Mod Travelers | Weld/LC Cold Protection cups-Mircea CM09- Cut process piping, disassemble cavities and CC's
2019-03-08 | Fri | HWCoax2 JLEIC-CC; | 1200C Clean | L2-BLA; L2-bellows; |  |  | L2-508 shop; | 1000C/3h; |  |  |  | L2 Lollipops; L2 String HW; L2-085; |  | SC-08, TE1NS-01 hold; | HPR1: OOC HPR2: OOC |  | L2 Bellows; | [5 empty] | L2-539 (Qualified) | CMTF U-tubes; D1: SIC C/T; D2: magnet test L; D3: D4: D5: D6: K-24 L/C/T D7: D8: C75-002 warm; |  | CM15- Tune HOM's CM16 - CS Alignment, Tuners | CM15- Move here when can | CM14- Evac/LC ins vac CM07- Remove WC's, Inst flanges | C100-06- Receive string | Weld/LC Cold Protection cups-Mircea CM09- Cut process piping, disassemble cavities and CC's
2019-03-09 | Sat
2019-03-10 | Sun
2019-03-11 | Mon | LSFC10; | Inj. Electrode | L2-Tuners; HWCoax2; |  |  | J1.3-15 HOMs; L2-227, L2-526; | regen; |  |  | EZ-SSC-05 covers & HW; TE1G-001 covers; | L2 cages (x4); L2 lollipops; L2 bellows (x6); L2-1 bolt holes; LSFC-12-04 HW; TD-5 HW; TE1G-001 covers, HW; 2 3/4 blanks; |  | SC-08, TE1NS-01 hold; | HPR1: OOC HPR2: LSFC-12-04; |  | L2 String Prep; C100 String roll-out! | [6 empty] | D1: SIC hold; D2: magnet test C4K/T/W; D3: D4: load; D5: D6: NS-002 SC4K/T/W; D7: D8: C75-002 SC4K; |  | CM15- Move to WS4, Tune HOM's CM16 - Tuners | CM15- Tune HOM's, checklist | CM14- LC ins vac CM07- Remove WC's | C100-06- Receive string 11am | LC Cold Protection cups-Mircea CM09- Prep for final 4 cavities
2019-03-12 | Tue | LSFC10; | L2 Bellows (8) | L2-Tuners; L2 bellows; |  |  | C75-000; | EZ-SSC-05 900C/3h 3N60; |  |  | EZ-SSC-05 HW; coating HW; SC-08 ext BCP & Nitric flange soak; JLEIC-CC weld prep; LSFC-10 Cu etch in R&D; | L2 bellows (x2); L2-2, L2-3, L2-4 bolt holes; 12 GeV pump drop; SS can; Ion pump; |  | SC-08, TE1NS-01 20u; | HPR1: OOC HPR2: TD5; TE1G-001; SC-08; |  | L2 String Prep; |  | LSFC-12-04 TS16-003; TD5 TS16-001; |  |  |  |  | D1: SIC hold; D2: magnet test P/L/C4K/T/W; D3: D4: D5: D6: D7: D8: C75-002 hold |  | CM16 - Tuners, heat stations, inst. | CM15- Tune HOM's, 50K shields, Inst check | CM14- LC ins vac CM07- Remove WC's | C100-06- RF measurements, instrumentation | CM09- Prep for final 4 cavities
2019-03-13 | Wed |  |  | L2-Bellows; L2-089; |  |  | J1.3-15 HOMs; C100 RF; L2-089; L2 bare 9-cells (x4); | EZ-SSC-05 900C/3h 3N60; | flanges (x6) (GE); |  | Furnace plates (x4); flanges (x6) (GE); RDT-2 15um; | MC HW, Pipes, Tees, flanges; L2-5, L2-6 bolt holes; RDT-2; bellows (x4); turn buckles (x8); |  | RDT-10 setup; | HPR1: OOC HPR2: TE1NS-01; RDT-14; |  | L2 String Prep; |  | SC-08 TS28-D7/8; | LSFC-12-04; |  | TD-5 sensors; LSFC-12-04; |  | D1: SIC pull; D2: magnet test P/L/C4K/T/W; D3: D4: D5: D6: TD5 L/C/T; D7: D8: C75-002 SC4K; |  | CM16 - Tuners, heat stations | CM15- Tune HOM's, 50K shields | CM14- LC ins vac CM07- Remove WC's | C100-06- RF measurements, instrumentation, fit process piping | CM09- Drop final 4 cavities, remove Cold Couplers
2019-03-14 | Thu |  |  | L2-BLA; C75 DL; L2-087; |  |  |  | ceramic plates 500C/3h; | HOM load flange; |  | RDT-10 flanges; | RDT-10; L2-7, L2-8 bolt holes; Cu gaskets (x16); alignment tool; String prep; gauge package; L2 beam pipe extender; |  | RDT-10 15u; Acid change (pm); | HPR1: OOC HPR2: RFD2; RDT-2; |  | L2 String Prep |  | RDT-14; TE1G-001 D?; TE1NS-01; | SC-08; |  | SC-08 and Tflex coax; |  | D1: D2: magnet test P/L/C4K/T/W; D3: D4: D5: D6: LSFC-12 L/SC4K/T/W (0mG) D7: D8: C75-002 T4K; |  | CM16 - Complete tuners, set piezo preloads, heat stations | CM15- 50K MLI, Into VV, prep for alignment | CM14- Ready for CMTF CM07- Remove WC's | C100-06- instrumentation, fit/tack process piping | CM09- Remove mag shields/MLI/instrumentation
2019-03-15 | Fri |  |  | L2 Bellows; L2-BLA; C75 DL; |  |  | uncage bare 9-cells; |  |  |  | HWCoax2 weld prep; | L2 beam pipe extender; L2 bolts (x100); L2-343; |  | EZ-SSC-05, RDTTD-02 setup; HF spike; | HPR1: OOC HPR2: RDT-10; TE1NS-02; |  |  |  | RFD2; L2-078, L2-086, L2-343 D5; |  |  | TEG001; |  | CMTF 4-cavity run; D1: D2: Nb3Sn CPW L/C2K/W; D3: D4: D5: D6: LSFC-12 W/T D7: SC-08 L/C4K; D8: C75-002 hold; |  | CM16 - instrumentation, heat stations | CM15- Align Cold Mass in VV | CM14- Ready for CMTF J07 - relocate to UITF | C100-06- instrumentation, fit process piping | CM09- Dis-assemble cavities, Rework HV's
2019-03-16 | Sat | [25 empty] | Finish Alignment |  | Fit/weld process piping | Pull U-tube
2019-03-17 | Sun | [13 empty] | HPR2: L2-1; L2-2; | [8 empty] | D7: D8: C75-002 C4:
2019-03-18 | Mon | HWCoax2; LSFC12; | JLEIC-CC; L2 bellows; | L2-BLA; L2 bellows; C75 DL; |  |  |  |  | HwCoax2 Flanges (x8) |  |  | EZ-SSC-05, RDTTD-02 ; |  | EZ-SSC-05, RDTTD-02 8u; | HPR1: OOC HPR2: L2-3; L2-4; |  | Cage L2-5, L2-6; |  | L2-1, L2-2 on rail; RDT-10; RDT-2; TE1NS-02 D6; | L2 D5; |  |  |  | U-tubes 9am; D1: SIC L/C2K/T; D2: D3: D4: D5: D6: RDT-14 L/C/T D7: SC-08 C2K; D8: C75-002 C2K/T; |  | J16 - HV Bellows exam, Mag shields J17- Move UCM from N4 post to S4 post | J15 - Move to WS5 | J07 - Move to North High Bay J13- Out of CMTF J14- into CMTF | C1006-06- Fit/Weld Process Piping, Remove beampipe from endcans, rework | J13 - Pull U-tubes Remove J13 from cave PCM- Move module to Western UITF spot
2019-03-19 | Tue | Maint. | L2 bellows; | L2-Bellows; RFD HOM test box; |  |  |  |  | HwCoax2 Flanges (x8) |  | TD-5 3u; | L2-105; TD-5 HW; |  | 5C75-004 setup; | HPR1: OOC HPR2: L2-5; L2-6; |  | Cage L2-7, L2-8; C75-002 dis; |  | L2-3, L2-4 on rail; RFD2 on test stand; |  |  | L2 D5 sensors and HOMs; |  | C3 commisioning 10am--> (motor failure); D1: SIC C/T (D7 --> D1); D2: D3: D4: D5: L2-078, L2-086, L2-345 L/precool; D6: RDT-14 Warm D7: SC-08 T; D8: C75-002 W; |  | J16 - Rf cables, instrumentation, Mag shields | J16- VV from BC, QC, Demag | J13- Config for shipping J15 - WC, instrumentation flanges, JT Welding | C100R-06- Process Piping, beam pipes | J14 in CMTF - align, Demag, Fastener checklist J09 - Disassembly
2019-03-20 | Wed |  | cleanup run; | L2-Bellows; L2-BLA; C75-DL; | [6 empty] | Coating HW; HWCoax3; Cover; AP HF sample; | EZ-SSC-05 parts; ClRm Vac; GC Flange & valve; Viewer ports & HW; |  | 5C75-J-004 hold; | HPR1: OOC HPR2: L2-7; L2-8; |  |  |  | L2-5, L2-6 on rail; | RFD2; |  |  |  | D1: SIC C/T; D2: magnet test L/C4K/T; D3: D4: D5: L2-078, L2-086, L2-345 W/C2K; D6: TEG001 L/SC4K/T; D7: SC-08 W; D8: C75-002 W; |  | J16 - Rf cables, instrumentation Mag shields | J16- QC, Demag | J13- Config for shipping J15 - Beam pipe, WC, instrumentation | C100R-06- Process Piping, beam pipes | J14 in CMTF - align, Demag, WG, Condition Circuits J09 - Disassembly
2019-03-21 | Thu | HWCoax2; LSFC10; | Bronze sample; | L2-Bellows; |  |  | 5C75-002 beadpull & passbands; |  |  |  |  | BLA bolts; | Etch Rate Sample | 5C75-J-004 60u; | HPR1: OOC HPR2: EZ-SSC-05; TD-5; |  |  |  | L2-7, L2-8 on rail; TD-5; LSFC-09 TS26-006; |  | RFD2 120C 12h; |  |  | D1: SIC C/T; D2: D3: D4: D5: L2-078, L2-086, L2-345 T/W; D6: TEG001 C2K/T/W; D7: SC-08 pull; D8: C75-002 pull; |  | J16 - Move to WS4; J17- Move UCM from N4 post to S4 post; | J16- QC, Demag, prep lower shields | J13- Config for shipping J15 - Beam pipe, WC, instrumentation | C100R-06- Process Piping, beam pipes | J14 in CMTF, Condition circuits, Return gas J09 - Disassembly
2019-03-22 | Fri | HWCoax3; | Bronze sample; | L2-Tuners; L2-BLA |  |  | 5C75-RI-004; J09 dis; |  |  |  |  | 5C75-J-004; |  | 5C75-J-004 40u; | HPR1: OOC HPR2: RDTTD-02; |  |  | DQW2 dis; |  | LSFC-09; | RFD2 120C 12h; | RFD2 sensors; |  | CMTF U-tubes? D1: SIC W; D2: BNNT load; D3: D4: D5: L2-078, L2-086, L2-345 warm; D6: TD5 L/C/T/W D7: D8: |  |  | J13- Tune HOM's | J13- Config for shipping J15 - Beam pipe, WC, instrumentation | C100R-06- Process Piping, Evac 2K, beam pipes | Remove J3 and PCM from UITF roof J14 - U-Tube Party/ Cooldown CMTF
2019-03-23 | Sat | [26 empty] | J13- Config for shipping J15 - Beam pipe | C100R-06- Weld process piping | J14 - Cooldown
2019-03-24 | Sun
2019-03-25 | Mon | HWCoax3; Hall C vac line; | Bronze sample; | 5C75-RI-004; L2-Bellows; | 5C75-RI-007; |  | 5C75-RI-007; |  |  |  | RDT-06 flange BCP; Coating HW (UP); | DQW2 HW; DQW2; L2 cages x4; |  | C75-J-002 setup; | HPR1: OOC HPR2: DQW2; RDTTD-01 (4P); |  | L2 Gate Valve; |  | EZ-SSC-05 TS16-003; RDTTD-01 pump cart?; RDTTD-02 D6; | RDTTD-02; J1.3-17 bag; |  | LSFC-09 sensors; TE1NS-02 sensors; | L2-514; | CMTF pumpdown; D1: SIC hold D2: BNNT C4K/T D3: D4: D5: L2-078, L2-086, L2-345 pull; RFD2 L/C4K/T; D6: TE1NS-02 L/SC4K/T D7: SC-08 L/C4K D8: LSFC-09 L |  | J16-RF cables |  | J13- Perform shipping alignment J15- Install WC's, Add ghrp cap/jumpers, HPTest | C100R-06- Complete welding of process piping
2019-03-26 | Tue | C75 Dogleg; | C75 DL; | 5C75-RI-004; L2-Bellows; | 5C57-RI-004; |  | J13 HOM tuning; |  |  |  | Beam tube; C75 DL x5; | L2 FPC HW; L2-514 bolt holes; |  | C75-J-002 20u; | HPR1: OOC HPR2: RDT-06; TE1NS-001; |  | L2 lollipop prep (outside); |  | DQW2 D7/8; RDTTD-01 D3; | J1.3-17; |  |  | L2-532; | D1: SIC pull/L; D2: BNNT C4K/T D3: D4: D5: RFD2 C2K/T/W D6: TE1NS-02 C2K/T/W; D7: SC-08 C2K/T/W D8: LSFC-09 SC4K/W |  | J16-Move to WS4 | J16- Complete Instrumentation and Checklist | J13- Perform shipping alignment J15- Install WC's, Complete JT welding, LC jumpers | C100R-06- Evacuate He circuit
2019-03-27 | Wed |  | C75 windows; | 5C75-RI-007; L2-Bellows; |  |  | J16 HOM tuning; 5C75-J-004 freq & BP; | RDT-06 800C/3h, 140C/48h wN2; |  | 5C75-J-004; 5C75-RI-004; | LSFC-12 coating removal (w/MB); Sample chamber; | L2-514 bolt holes; L2-532 bolt holes; L2-089; L2 BLA (x2); |  | maint | HPR1: OOC HPR2: L2-514 |  |  | L2 D5 unload; | DQW2 D7/8; L2-089, L2-085, L2-105 D5; TE1NS-001 D6; | RDTTD-01; TE1NS-001; J1.3-17; |  | RDTTD-01 sensors; | L2-zzz; J1.3-17; | D1: SIC C/T/W; D2: BNNT C2K/T/W; D3: D4: D5: RFD2 W D6: RDTTD-02 L/C/T/W; D7: SC-08 warm; D8: LSFC-09 warm; | J17- Move UCM from North 4 Poster |  | J16- Test fit lower shields, Tune HOM's | J13- Perform shipping alignment J15- Install WC's, LC jumpers, Install testing cap | C100R-06- Evacuate He circuit, bag for LC
2019-03-28 | Thu |  | L2 BLA (x2); C75 | L2-Bellow; |  |  | J16 HOM tuning; | RDT-06 800C/3h, 140C/48h wN2; |  |  | LSFC-12 coating removal; HF sample 8h soak; | L2-094 bolt holes; LSFC-12; bellow stretcher; |  | maint | HPR1: OOC HPR2: SC-04; |  |  |  | L2-089, L2-085, L2-105 D5; DQW2 D7/8; J1.3-17 cav 8; |  |  | TE1NS-001; | L2-aaa; | D1: SIC W/pull; D2: BNNT pull; D3: field map (for GC); RDTTD-01 L; D4: D5: RFD2 W; D6: TE1NS-001 L/SC4K/T; D7: SC-08 pull; D8: LSFC-09 pull; |  |  | J16- Install lower shields, verify HOM's, Weld shields | J13- complete remaining checklist items, Install shipping caps J15- Install testing cap /ionpump, LPT 2K circuit | C100R-06- LC He circuit, MLI onto 2k
2019-03-29 | Fri |  | L2 BLA (x2); C75; | L2-Bellows; |  |  |  | RDT-06 800C/3h, 140C/48h wN2; |  |  | Nb foil; | L2-538 & L2-539 bolt holes; Tees (x10); alingment HW; RDT-06 parts & HW; |  | maint | HPR1: OOC HPR2: RDT-10; |  | C75 doglegs D2; |  | J1.3-17 cav 8; | DQW2 D7/8; |  |  | L2-bbb; | D1: SIC L/C/T D2: D3: RDTTD-01 pull, RDTTD-01 L/SC4K; D4: D5: RFD2 pull; D6: TE1NS-001 C2K/T/W; D7: D8: |  |  | J16- Cold Mass into VV | J13- Move CM to WS6 J15- Complete IP, install, add Bayonet box | C100R-06- Instrumentation, MLI | Bring in Shipping frame, load CM13
2019-03-30 | Sat | [26 empty] | J15- RT JT plumbing High Bay closed till completed. |  | Ship CM13
2019-03-31 | Sun | [18 empty] | J1.3-17; | [8 empty] | C1006R-Instrumentation
2019-04-01 | Mon | C75 DL; | Feedthough (Suba); C75 DL; | 5C75-RI-00X; L2-Bellows; | 5C75-RI-aaa; |  |  | RDT-06 pull; |  |  |  | L2 String prep; L2 lollipop parts; 5C75-J-004; |  | 5C75-J-005 setup; HF Spike | HPR1: OOC HPR2: |  | L2 BPM sub; |  | C100-RI-024 TS28-011; | L2-089, L2-085, L2-105 D5; J1.3-17 rollout; |  |  |  | CMTF Fast CD; D1: SIC hold; D2: Magnet test L D3: RDTTD-01 hold; D4: D5: D6: TE1NS-001 pull; D7: D8: |  | J17- Delivery | J16- Cold Mass in VV, add support posts, Prep for alignment | J15- Complete IP, install, add Bayonet box, MC Line, Inst flanges | C100R-06- Instrumentation, Mag shields, MLI | CM13 at SLAC
2019-04-02 | Tue | C75 DL; | C75 DL; BLA (x2) | 5C75-RI-001; | 5C75-RI-bbb; |  |  | 5C75-J-004 800C/3h; |  |  |  | L2 String prep; L2-bellows (x8); |  | 5C75-J-005 55u; | HPR1: OOC HPR2: |  | U/S Vlv Ass'y; Lollipop; |  | LSFC-04 coating; RDT-10 D6; |  |  | L2-089, L2-085, L2-105 HOMs & sensors; |  | D1: SIC C/T; D2: Magnet L/test D3: RDTTD-01 C2K/T/W10K; D4: C100-RI-024 L/C4K/W; D5: L2-089, L2-085, L2-105 L/precool; D6: D7: D8: |  | J17- RF Measurements, Berry bolts, magnet install, process piping | J16- Align Cold Mass in VV | J15- Complete IP, install, LC Bayonet box, MC Line, Inst flanges | C100R-06- Instrumentation, Mag shields, MLI
2019-04-03 | Wed | C75 DL; | C75 DL; BLA (x2) | 5C75-RI-001; L2-Tuner; | 5C75-RI-ccc; |  |  | 5C75-J-004 800C/3h; | 5C75-J-002 flanges (GE); C75 blanks (GE); |  |  | L2 String prep; 5C75-J-005 L2-077 bolt holes; L2-239 bolt holes; L2-541 bolt holes; L2-073 bolt holes; |  | 5C75-J-005 45u; | HPR1: OOC HPR2: |  | L2 BPM sub; L2 bellows; Lollipop; Cage L2-1-->4 | EZ-SSC-05 | C75 DL D2; | RDT-10; DQW2; |  | RDT-10; |  | D1: SIC C/T; D2: Magnet test C4K/T D3: RDTTD-01 SC4K/T D4: C100-RI-024 C4K/W; D5: L2-089, L2-085, L2-105 W/C4K; D6: RDT-10 L/SC4K; D7: D8: |  | J17- Berry bolts, process piping | J16- Align Cold Mass in VV | J15- LC Bayonet box, MC Line, Inst flanges | C100R-06- Instrumentation, Mag shields, MLI
2019-04-04 | Thu | C75 DL; RFD Beamtubes; | C75 DL; BLA (x2) | L2-Bellows; L2-Tuner; | 5C75-RI-ddd; |  | 5C75-J-004 freq & BP; | 5C75-J-004 pull; |  | 5C75-RI-007; 5C75-J-005 | C75 blanks (GE); 5C75-J-002 (GE) flanges 5u BCP; | L2 String prep; 5C75-J-002 (GE); C75 blanks (GE); |  |  | HPR1: OOC HPR2: |  | L2 BPM sub; |  |  | EZ-SSC-05; |  |  |  | D1: SIC C/T; D2: RRR Load; D3: RDTTD-01 C2K/T; D4: C100-RI-024 C4K/W; D5: L2-089, L2-085, L2-105 C2K/T; D6: RDT-10 C2K/T/W; D7: D8: |  | J17- Fiducialize cavities, process piping | J16- Move to WS5 | J15- Inst flanges, LC MC line J16- Prep for beamline work/WC's | C100R-06- Instrumentation, Mag shields, MLI
2019-04-05 | Fri |  | BLA (x2) | 5C75-RI-001; L2-Bellows; | 5C75-RI-eee; |  | L2-bare-1 RF in; L2-bare-2 RF in; L2-bare-3 RF in; L2-bare-4 RF in; | 5C75-J-005 800C/3h; |  |  | HW COAX3 | L2 String prep; BLA Blank Flgs (x 21); 5C75-J-004; RDT-06; L2 TS elbows; |  | 5C75-J-004 setup | HPR1: OOC HPR2: 5C75-J-002 (GE); RDT-6; |  | Mag meas; |  |  | L2 BPM sub; C75 DL D2; |  |  |  | CMTF U-tubes; D1: SIC Pull; D2: RRR C/W/T; D3: RDTTD-01 W D4: C100-RI-024 C4K/W; D5: L2-089, L2-085, L2-105 HOMs/W; D6: RDT-10 W/SC4K/T/W; D7: D8: |  | J17- process pipe welding, Ti sheet | pCM - Remove 50k shields; inspect couplers | J15- Torque C and CL flanges J16- Beamline & WC's | C100R-06- Instrumentation, Mag shields, MLI | J14 - pull U-tube; Warm up
2019-04-06 | Sat | [22 empty] | D4: C100-RI-024 C4K/W; |  | Weld Process piping |  |  |  | J14 - pull U-tube; Warm up(?)
2019-04-07 | Sun | [10 empty] | String tools; |  |  | HPR2: L2-01; L2-02 |  |  |  | RDT-6 TS16-001; |  |  |  |  | D4: C100-RI-024 C4K/W;
2019-04-08 | Mon | C75 DL; | C75 DL; | L2-087; | 5C75-RI-005; |  | Cage L2 Bare Cav X 2; |  |  |  | Nb parts (UP); | 5C75-J-004; WFPC kit (MS); |  | 5C75-J-004 30u; | HPR1: OOC HPR2: L2-03; L2-04; |  |  |  | J1.3-18 Assy | RDT-6; |  |  |  | CMTF U-tubes; D1: D2: RRR W/T; D3: RDTTD-01 C2K/T/W -> 10K (adjust mag fields) D4: C100-RI-024 C4K/W; D5: L2-089, L2-085, L2-105 pull; D6: D7: D8: |  | J17- process pipe welding, Ti sheet | pCM - inspect coupler 8 | J15 - into CMTF J14 - U-tubes, out of CMTF J16 - BL and WC work | C100R-06- Instrumentation, Heat stationing
2019-04-09 | Tue | C75 DL; | C75 DL; Bz Samples; | L2-347; L2-348; | 5C75-RI-00? |  | L2-348; |  |  |  | LSFC-04 & 09 Nb Removal; AMV gun parts; | L2-087; L2-344; |  |  | HPR1: OOC HPR2: L2-05; L2-06; |  |  | D5 tested cavities (x2); | J1.3-18 Assy |  |  |  |  | D1: D2: RRR pull D3: RDTTD-01 C4K/C2K/T/W; D4: C100-RI-024 C4K/W; D5: D6: RDT-6 L; D7: D8: |  | J17- process pipe welding, Ti sheet; Lk Chk | pCM - rework coupler 8 | J14 - Prep for shipping J16 - BL and WC work | C100R-06- Heat stationing, cold tuners | J15 - Prep for cooldown, Ins Vac LC
2019-04-10 | Wed | C75 DL; | C75 DL; | L2-348 | 5C75-RI-00? |  | 5C75-J-004 Tune; |  |  |  | HW Coax1 Weld Prep; | BLA assembly kit (SW); L2-347; warm BT pump drop (x4); MC lines & HW; |  |  | HPR1: OOC HPR2: L2-07; L2-08; |  |  |  | J1.3-18 Assy; |  |  |  |  | CTF C3 testing (8:30-->12); Pair Pump B motor replacement; D1: D2: Magnet test L/C2K/T; D3: RDTTD-01 W ->10K/SC4K; D4: C100-RI-024 C4K/W; D5: D6: RDT-6 C2K/T; D7: D8: |  | J17- LC process piping | pCM - Rework WC8, torque fasteners, HOM measurements | J14 - Prep for shipping HOM measurements, Beampipe J16 - BL and WC work | C100R-06- Cold Tuners | J15 - Demag 4 pm, prep for cooldown, calibrate ev/pv's, Ins Vac LC
2019-04-11 | Thu | HW Coax3; | Bz samples | 5C75RI-005 | 5C75-RI-00? |  | 5C75-J-004 tune; |  | 5C75-J-004; |  |  | BPM Subassy kit; L2 BLA kits; RDT-2; beam tubes(x4); |  | RDTTD-02, RDL-02 setup; | HPR1: OOC HPR2: RDT-2 |  |  |  | J1.3-18 Assy; L2-344 D5; |  |  |  |  | D1: SIC L/C/T D2: Magnet test C2K/T D3: RDTTD-01 C2K/T/W -> 10K (adjust mag fields) D4: C100-RI-024 C4K/W; D5: D6: RDT-6 C2K/T; D7: D8: |  | J17- LC process piping, HV MLI,Mag shileds | pCM - Rework WC3, torque fasteners, Instrumentation | J14 - Prep for shipping J16 - BL and WC work, configure for LERF | C100R-06- Cold Tuners | J15 - prep for cooldown, return gas, Repeat Demag?
2019-04-12 | Fri | HW Coax3; | Bz samples; C75 DL; | L2-Bellows; 5C75RI-003; 5C75RI-005; | 5C75-RI-00? |  | 5C75-J-005 BP; |  |  |  | Nb sample (sulfuric soak); RDL-02 flanges; | L2-348; RDTTD-02, RDL-02; MC lines & HW; WFPC & bolts; |  | RDTTD-02, RDL-02 40u; | HPR1: OOC HPR2: |  |  |  | L2-344, L2-087 L2-347 D5; |  |  |  |  | CMTF U-tubes; D1: SIC warm; D2: Magnet test Warm; D3: RDTTD-01 C4K; D4: C100-RI-024 C4K/W; D5: D6: RDT-6 C2K/T; D7: D8: |  | J17- 2k LC, MLI, Mag shields | pCM - Tune HOM's, Insrumentation | J14 - Prep for shipping J16 - BL and WC work, configure for LERF, HP Test | C100R-06- Cold Tuners | J15 - U-tubes 8am, Cooldown UITF- Move CM's back
2019-04-13 | Sat | [18 empty] | Bag string; | [5 empty] | J17- 2k LC, MLI, Mag shields |  |  | C100R-06- Cold Tuners
2019-04-14 | Sun
2019-04-15 | Mon | HW Coax3; | C75 DL; | RFD HOM Damper; 5C75RI-003; |  |  | 5C75-RI-005; 5C75-RI-001; pCM HOMs; |  | 5C75-J-004; |  | AUP BP; C75 DL (x5); | BLA kit; L2-B-352; L2-B-353; C75 DL (x5); sm bellows (x8); |  | C75-RI-004 setup; | HPR1: OOC HPR2: RDTTD-02; |  |  |  | RDTTD-02; RDT-2; | Bag string; J1.3-18; L2-344, L2-087 L2-347 D5; RDT-2 leaked; | DQW2 120C/24h; |  |  | CMTF pumpdown; D1: SIC hold; D2: Magnet pull, RRR L/C/T; D3: RDTTD-01 C2K/T/W10K D4: C100-RI-024 C4K/W; D5: D6: D7: D8: | J17- 2k LC, MLI, Mag shields |  | pCM - Verify HOM's, Weld shields | J14 - Prep for shipping Install ship gauges J16 - BL and WC work, configure for LERF, Complete JT welds | C100R-06- Cold Tuners | J15 - Cooldown
2019-04-16 | Tue | AUP BP; HW Coax1; | Test Box; | 5C75-RI-003; L2 Bellows; |  |  | 5C75-RI-002; 5C75-RI-006; |  | 5C75-J-004; |  | Nb Beam Tube; Nb coating HW; TE1NS-001 nitric flanges; | Test Box; 5C75-J-002; L2 string cages (x4); Cryo HW; 8' pipe (x3), 12' pipe, flange; L2 CM gage kits (x2); L2 gaskets; |  | C75-RI-004 55u; | HPR1: OOC HPR2: RDT-10 |  | cage 5C75-J-002; BPM Sub; |  | L2-348 D7/8; RDT-10; | RDT-10; | DQW2 120C/24h; | L2-344, L2-087 L2-347 D5; |  | D1: SICpull/ L/C; D2: RRR W/T; D3: RDTTD-01 C2K/T/W; D4: C100-RI-024 C4K/W; D5: L2-344, L2-087 L2-347 L/precool; D6: RDTTD-02 L/C/T/W; D7: D8: | J17- MLI, Mag shields |  | pCM - Weld shields, MLI, into VV | J14 - Complete BL work J16 - BL and WC work, configure for LERF, Complete JT welds | C100R-06- Cold Tuners
2019-04-17 | Wed | HW Coax1; | Test Box; | L2 BLA; L2 Bellows; 5C75-RI-002; |  |  | 5C75-RI-008; |  |  | 5C75-J-004 | HWCoax2; | BLA kit; C75-RI-004; 5C75-J-004; HWCoax2; L2 CM gage kits (x2); L2-086 bolt holes; L2-078 bolt holes; |  | C75-RI-004 45u; | HPR1: OOC HPR2: 5C75-J-002 (3Pass); RDL-02; |  | BPM Sub; | EZSSC-05; |  | J1.3-18 rollout; L2-348 (x2); L2 Gate valves; | DQW2 120C/24h; |  |  | D1: SIC C/T; D2: RRR C4K; D3: RDTTD-01 warm; D4: C100-RI-024 C4K/W; D5: L2-344, L2-087 L2-347 warm/C4K; D6: RDT-10 SC4K/P; D7: D8: | J17- Move to WS3 J18- Receive string |  | pCM - Into VV, Prep for Alignment | J14 - BL Work Complete, shipping align J16 - BL and WC work, configure for LERF, Complete JT welds | C100R-06- Cold Tuners, Nitronic rods | Shipping frame out of TL
2019-04-18 | Thu | HW Coax2; | Test Box; | 5C75-RI-002; L2 Bellows |  |  |  |  | EZSSC-05; |  | HWCoax2 parts; TE1NS-002, TE1G-001 nitric; FM Beam tubes; | 5C75-J-004; L2 string 19 prep; L2 BPM; BLA; L2 Bellows (x8); EZSSC-05; |  | TE1NS-002, TE1G-001 setup; | HPR1: OOC HPR2: TE1NS-001; 5C75-J-002 (3Pass); |  | 5C75-J-002; BPM Sub; |  | RDL-02; L2-B-353 D7/8; | L2 Gate valves; |  | L2-348 sensors & HOMs; |  | D1: SIC C/T; D2: RRR W/T; D3: RDTTD-01; D4: C100-RI-024 C4K/W; D5: L2-344, L2-087 L2-347 C2K/T/W; D6: RDT-10 C2K/T/W; D7: D8: L2-348 L/C4K; | J18- RF measurements, Berry bolts, magnet install, 2 phase piping | J17- Unite UCM to CS | pCM - prep for VV Alignment | J14 - Ship Alignment J16 - Testing cap, WC's | C100R-06- Cold Tuners, Nitronic rods | LERF Warm up begins New Assembly Rail delivery
2019-04-19 | Fri | HW Coax2; |  | 5C75-RI-008; |  |  | C75-RI-004 freq & FF; |  |  | C75-RI-004; |  | L2 string 19 prep; |  | TE1NS-002, G001 20u; | HPR1: OOC HPR2: RDTTD-02 |  | BPM Sub; |  | 5C75-J-002; | L2-B-353; |  | L2-B-353 HOMs & sensors; |  | D1: SIC warm; D2: RRR pull; D3: RDTTD-01 pull; D4: C100-RI-024 C4K/W; D5: L2-344, L2-087 L2-347 W; D6: RDL-02 L/C/T; D7: L2-B-353 L/C4K; D8: L2-348 C2K/T/W; | J18- RF measurements, Berry bolts, magnet install, 2 phase piping | J17- Unite UCM to CS, fit process piping | pCM - VV Alignment | J14 - Ship Alignment finish by noon, HOM measurements/tuning J16 - Testing cap, Tune WC's, MC Line RT for CM16- Scheduled for 4/20 @7 am | C100R-06- Cold Tuners, Nitronic rods | Crane training North Crane
2019-04-20 | Sat | [28 empty] | RT for CM16- Scheduled for 7 am
2019-04-21 | Sun
2019-04-22 | Mon | HWCoax-2; | 1200 Cleanup; | L2 BLA; 5C75-RI-006; |  |  | 5C75-RI-003; J1.3-18 PB; | Nb plate (AP) 800C/3h/3N60; | 5C75-J-004; BLA; | 5C75-RI-001; | SS HW (MB); TE1NS-002 parts; TE1G001 parts; Nb plate (AP); | L2-145; L2-064; L2-074; C75-RI-004; BLA (x2); | load acid; | 5C75-RI-001 setup; | HPR1: OOC HPR2: TE1G001 |  | BLA Sub; | SC-08; | RDTTD-02 L2-064, L2-074, L2-145 D5; | 5C75-J-002; |  | 5C75-J-002; | L2 Qualified Cavities | D1: SIC pull; D2: D3: D4: C100-RI-024 pull, L/C4K/W; D5: L2-344, L2-087 L2-347 hold; D6: D7: HE-353 C2K/T/W; D8: L2-348 pull; 5C75-J-002 L/SC4K/T; | J18- Berry bolts, 2 phase piping, Instrumentation, Ti shields | J17- Unite UCM to CS, Cav1 tuner, fit/weld process piping | pCM - VV Alignment | J14 - RF/HOM measurements/tuning, Shipping Caps Ship Trailer in 8am J16 - Testing cap, MC Line, 2 phase LC | C100R-06- Cold Tuners, Nitronic rods | LERF Disassembly
2019-04-23 | Tue | HWCoax-2; |  | L2-Bellows; Beam tube weld sample; |  |  |  | Nb plate (AP) 800C/3h/3N60; |  |  | AMV HW; HF sample (7hours); | AMV HW; BLA; Lower Cold Box CHL kits (x9); | HWCoax-1 setup; | 5C75-RI-001 55u; | HPR1: OOC HPR2: TE1NS-002; TE1NS-001 |  | Lollipop (dirty prep); BLA Sub; |  |  | L2-064, L2-074, L2-145 D5; C75 DL; |  |  | L2 Qualified Cavities | CMTF Fast Cooldown D1: D2: D3: D4: C100-RI-024 C4K/W; D5: L2-344, L2-087; L2-347 hold; D6: RDTTD-02 L; D7: HE-353 warm D8: 5C75-J-002 C2K/T; | J18- Berry bolts, 2 phase piping, Ti shields, Instrumentation | J17- Remove Lollipops | pCM - VV Alignment | J14 - RF/HOM measurements/tuning Ship Trailer in 8am J16 - Testing cap, MC Line, LPT | C100R-06- Cold Tuners, Nitronic rods | LERF Disassembly
2019-04-24 | Wed | HWCoax-2; | L2 BLA; | L2-Bellows; |  |  |  | C75-RI-004 800C/3h; | 5C75-J-004; table maint; EZSSC-05; |  | SC-08 Nitric flange soak; RDL-02 flanges BCP; | HWCoax-1; AMV HW; Lower Cold Box CHL kits (x8); RDL-02 HW; | HWCoax-1 10u; | 5C75-RI-001 25u; | HPR1: OOC HPR2: |  | Lollipop (dirty prep); L2 bellows prep; BLA Sub; | SC-08 (Alex); |  | Gate Valve; |  | L2-064, L2-074, L2-145 D5; | L2 Qualified Cavities | D1: SIC L; D2: D3: D4: C100-RI-024 C4K/W; D5: L2-064, L2-074, L2-145 load/precool; D6: TDTTD-02 C/T/W; D7: HE-353 hold; D8: 5C75-J-002 C2K/T/W; | J18- Alignment | J17- heat stations, magnet lead stations | J03 - Remove from VV | PCM- Prep for WC's J16 -Ion Pump Install MC Line, LPT | C100R-06- Cold Tuners, Nitronic rods | LERF Disassembly J14- Ships Today
2019-04-25 | Thu | HWCoax-2; | L2 BLA; | L2-Bellows; |  |  |  | C75-RI-004 800C/3h; |  |  | Gun replica Assy S/S etch; | L2 assy parts; AMV HW; 5C75-RI-001; L2 BL Bellows & valve; BLA alignmt HW; |  | 5C75-RI-001 20u; | HPR1: OOC HPR2: RDL-02; |  | Lollipop (dirty prep); BLA; | TS34-002; |  | Gate Valve; |  |  | L2 Qualified Cavities | D1: SIC pull/L/C/T; D2: D3: D4: C100-RI-024 C4K/W; D5: L2-064, L2-074, L2-145 W/C4K; D6: TE1NS-001 L/SC4K/T D7: HE-353 pull; D8: 5C75-J-002 warm; | J18- CS Alignment | J17- heat stations, Split rings, Complete 2 phase welding | J03 - Prep/Remove from VV | PCM- Prep for WC's, Instrumentation J16 -Ion Pump Install MC Line LC, LPT, close JT Port | C100R-06- Cold Tuners, Nitronic rods | LERF Disassembly, Move CM12, Remove ICR bellows
2019-04-26 | Fri | HWCoax-2; | L2 BLA; 1200C Clean | L2-063; L2-Bellows; |  |  | C75-RI-004 freq & BP; L2-063; L2-083; | RDL-02 800C/3h, 140C/48h/N2; |  |  |  | L2 BLA;AMV HW; L2-146; |  |  | HPR1: OOC HPR2: |  | BPM Sub; |  | HE-352 D7/8; L2-146 D7/8; | BLA? |  |  | L2 Qualified Cavities | D1: SIC C/T; D2: C75DL L/C4K/T/W; D3: D4: C100-RI-024 W/Pull; D5: L2-064, L2-074, L2-145 C2K/T/W; D6: TE1NS-001 C2K/T/W; D7: D8: 5C75-J-002 pull; | J18- Berry bolts, Ti sheets | J17- heat stations, LC 2 phase, split rings | J03 - Remove from VV | PCM- WC's, Fab tie downs J16 MC Line LC, close JT Port | C100R-06- Cold Tuners, Nitronic rods | LERF Disassembly
2019-04-27 | Sat | [6 empty] | RDL-02 800C/3h, 140C/48h/N2; | [16 empty] | Ti sheets | J17- LC 2 phase |  | J16- Move to WS6 |  | Remove coils from FL02
2019-04-28 | Sun | [6 empty] | RDL-02 800C/3h, 140C/48h/N2;
2019-04-29 | Mon | HWCoax2; |  | L2-083; L2-159; |  |  |  | HWCoax-1 800C/3h; | 5C75-J-004; table maint; EZSSC-05; | 5C75-RI-001; |  | L2 Lollipop parts; CM flanges & HW; |  | maint; 5C75-RI-004 setup; | HPR1: OOC HPR2: |  | Lollipops; |  |  | L2-146; HE-352; |  |  |  | D1: SIC warm; D2: C75DL cycle; D3: D4: C100-RI-024 L/C4K/T/W; D5: L2-064, L2-074, L2-145 pull; D6: RDT-10 L/SC4K/T/W; D7: D8: | J18- Berry bolts, Ti sheets Complete 2 phase welds/LC | J17- split rings | J03 - Complete BL work, Remove from VV | PCM- Warm Couplers, Establish Beam Line Vac | C100R-06- Cold Tuners, Nitronic rods | LERF- CM12 returns to Test Lab, to WS5 CM16 loaded ready for delivery
2019-04-30 | Tue | HWCoax2; |  | L2-159; L2-160; |  |  | 5C75-RI-001 freq & BP; L2 BPM FT's; | HWCoax-1 800C/3h; | 5C75-J-004; EZSSC-05; |  | Nb sample; | EZSSC-05; 5C75-RI-004; 5C75-RI-001; String tools; L2-1, L2-2 boltholes; |  | 5C75-RI-004 30u; | HPR1: OOC HPR2: LSFC10; RDL-02; |  | Lollipops; cage L2-1; cage L2-2; Mag Meas; |  | RDL-02; | BLA sub; |  | L2-146; HE-352; | Cav 8; | D1: SIC pull; D2: C75DL pull; D3: D4: C100-RI-024 C4K/T/W; D5: D6: RDT-10 pull; D7: HE-352 L/C4K; D8: | J18- Berry bolts, LC 2 phase welds | J17- split rings, tuners | J03 - prep 4 BL work | PCM- WC's, Fab tie downs, Instrumentation flanges | C100R-06- Cold Tuners, Nitronic rods | LERF- CM16 Delivered to LERF, into position, JLAB align
2019-05-01 | Wed | OCD1; |  | L2-Bellows; L2-160; |  |  | L2 BPM FT's; | HWCoax-1 800C/3h; 5C75-RI-001 800C/3h; | 5C75-J-004; |  | 5C75-J-004; Nb box; Window; | 5C75-J-004; L2-083; L2-159; L2-063; EZSSC-05 HW; |  | acid change; | HPR1: OOC HPR2: EZSSC-05; |  | Lollipops; |  | L2-063, L2-083, L2-159 D5; | RDL-02; |  |  |  | D1: D2: Nb sample D3: RDTTD-01 D4: C100-RI-024 pull; D5: D6: RDL-02 L/C2K/T; D7: HE-352 C2K/T/W D8: L2-146 L/C4K | J18- LC 2 phase welds, HV MLI, Mag shields | J17- tuners | J03 - BL Work | PCM- WC's, Fab/ install tie downs, Instrumentation flanges, JT weld | C100R-06- Cold Tuners, Nitronic rods, MLI | LERF- CM16 Prep for beam line work
2019-05-02 | Thu | OCD1; |  | L2-Bellows; HOM damper; |  |  | 2.45 GHz; C75-RI-004 FF & freq; | 5C75-RI-001 800C/3h; | C75-RI-004; |  |  | L2-3, L2-4 boltholes; BLA (x3); HWCoax-1 & parts; | HWCoax-1 setup; | HF spike; HE-353 setup; | HPR1: OOC HPR2: LSFC-10; |  | cage L2-3; cage L2-4; Tools; |  | EZSSC-05; | L2-063, L2-083, L2-159 D5; |  |  |  | D1: D2: Nb sample pull/Load D3: D4: C5-1 & C5-2 L/C4K/T/W; D5: D6: RDL-02 C2K/T; D7: HE-352 warm; D8: L2-146 C2K/T; | J18- LC 2 Phase,HV MLI, Mag shields | J17- tuners | J03 - BL Work,Out of VV, Fasteners | PCM- WC's, Instrumentation flanges, MC Line | C100R-06- Cold Tuners, Nitronic rods, MLI | LERF- CM16 install beam line spool/LC
2019-05-03 | Fri | Nb cover |  |  |  |  | 2.45 GHz; C75-RI-003 FF & freq; C75-J-005 FF & freq; | 5C75-RI-001 800C/3h; AP Test Run room temp/1mTorr N2; | C75-RI-004; |  | Nb sample (HF); Nb samples (PD); Cu & S/S (AMV); Ti bolts (AP); | L2-5, L2-6 boltholes; L2-7, L2-8 boltholes; HE-353; | HWCoax-1 20u; | HE-353 3u; | HPR1: OOC HPR2: HWCoax-1; |  |  |  | LSFC10; | EZSSC-05; |  | L2-063, L2-083, L2-159 D5; EZSSC-05; |  | Pull U-tube D1: D2: Nb sample D3: D4: C5-1 & C5-2 C4K/T/W; D5: L2-063, L2-083, L2-159 L/precool; D6: EZSSC-05 L/C1.6K/T/W; D7: HE-352 pull; D8: L2-146 C2K/T/W; | J18- 2 phase LC, HV MLI, Mag shields | J17- prep 4 Alignment | J03- Out of VV, FSS | PCM- WC's, Instrumentation flanges, MC Line | C100R-06- Cold Tuners, Nitronic rods, MLI | LERF- CM16 install Cryogenic bellows J15- U-tube removal, start warm up
2019-05-04 | Sat | [28 empty] | RT Test PCM, CMA Limited entry 7AM
2019-05-05 | Sun | [13 empty] | HPR2: L2-1; L2-2;
2019-05-06 | Mon |  |  | L2-160; RFD Hom damper; Upstream bellow; |  |  | 5C75-RI-001 freq & BP; cage HE-364; | Nb sample 600C/3h; | C75-RI-004; |  | TE1G001, TE1NS002 Nitric flanges; | HE-353 parts; L2 FPC parts/hw; LERF HW; |  | TE1G001, TE1NS002; setup; | HPR1: OOC HPR2: L2-3; L2-4; |  | cage L2-5; cage L2-6; |  | L2-1; L2-2; HWCoax-1 D3/4; |  |  |  |  | Pull U-tubes D1: D2: Pb sample L/C4K/T/W; D3: RDTTD-01 pull; mag field mapping/adj (min) D4: C5-1 & C5-2 C4K/T/W; D5: L2-063, L2-083, L2-159 W/C2K; D6: EZSSC-05 warm; D7: D8: L2-146 pull; | J18- HV MLI, Mag shields | J17- Alignment | J03- Fasteners, Visual inspection | PCM- WC's, Instrumentation flanges, MC Line J12- Beam line Prep | C100R-06- Nitronic rods, MLI 2K | LERF- CM16 Beam line bellows (take 4) J15- Warming J18- QC UCM-N.4 poster
2019-05-07 | Tue | Nb cover | Nb samples; | L2-088; RFD Hom damper |  |  | L2-160; |  | C75-RI-004; |  |  | HE-364; HE-353; TE1G001, TE1NS002; |  | TE1G001, TE1NS002 25u; | HPR1: OOC HPR2: L2-5; L2-6; HE-353 (6Pass overnight) |  | cage L2-7; cage L2-8; |  | L2-3; L2-4; HE-364 D7/8; | HWCoax-1; |  | HWCoax-1; |  | D1: SIC L/C/T D2: RRR L/C4K; D3: HWCoax-1 L/C4K; D4: C5-1 & C5-2 pull/VSA sensors/load; D5: L2-063, L2-083, L2-159 T/W; D6: D7: D8: | J18-LC 2 Phase, HV MLI, Mag shields | J17- Alignment | J03- FSS | PCM- WC's, Instrumentation flanges, MC Line, Install tie downs J12- Beam Line reconfig US | C100R-06- Nitronic rods, MLI 2K | LERF- CM16 Beam Line bellows, bench LC J18- QC UCM- N. 4 poster
2019-05-08 | Wed | OCD1; | Nb samples | L2-088; C75RI-NbSn1; |  |  | L2-088; L2-109; | SC-08; |  | C75-RI-004; | C75-RI-004 flange BCP; S/S pipes (x4); Nb covers; | L2-160; C75-RI-004; LEFR bellows & HW; 5C75-RI-004 HW; |  | 5C75-RI-001 setup; | HPR1: OOC HPR2: L2-7; L2-8; |  | HE-353; |  | L2-5; L2-6; | HE-364; |  | HE-364 |  | D1: SIC C/T D2: RRR C/T; D3: HWCoax-1 C1.5K/T/W4K; D4: C5-1 & C5-2 C4K/T/W; D5: L2-063, L2-083, L2-159 warm; D6: D7: D8: | J18- HV MLI, Mag shields | J17- Alignment | J03- FSS | PCM- MC Line & LC, tie downs J12- Beam Line reconfig US/DS | C100R-06- Nitronic rods, MLI 2K | LERF- CM16 Cryogenic bellows, LC J18- QC UCM-N.4 Post, alignment L2 shipping trailer returning;
2019-05-09 | Thu | Nb cover | Nb samples | L2-103; L2-109; L2-Bellows; |  |  | L2-115; 2.45 GHz; | SC-08; |  |  |  | L2-088; HE gaskets; 5C75-RI-001 |  | 5C75-RI-001 30u; | HPR1: OOC HPR2: 5C75-RI-004; HE-353 |  | 5C75-RI-004 indium prep (Alex); |  | L2-7; L2-8; |  |  |  |  | D1: SIC C/T D2: Pb sample L/C2K/T/W; D3: HWCoax-1 C1.5K/T/W4K; D4: D5: L2-063, L2-083, L2-159 warm; D6: D7: D8: HE-364 L/C4K; | J18- HV MLI, Mag shields | J17- Alignment, Tuners | J03- FSS, move to WS3 East | PCM- MC Line & LC , Ship Alignment J12- Beam Line reconfig US/DS | C100R-06- MLI 2K | LERF- CM16 Beam line bellows install/ LC J18- QC UCM-N.4 Post
2019-05-10 | Fri | Nb cover |  | L2-Bellows; L2-109; |  |  | 2.45 GHz; | SC-08 800C 3N60; | 5C75-RI-001; | 5C75-RI-001; 5C75-RI-NBSN1 | LSFC Cu etch; | L2-103; |  | 5C75-RI-NBSN1 setup; | HPR1: OOC HPR2: |  | 5C75-RI-004; |  | HE-353; |  |  |  |  | D1: SIC C/T D2: Pb sample C4K/T/W; D3: HWCoax-1 C1.5K/T/W4K; D4: D5: L2-063, L2-083, L2-159 pull; D6: D7: DQW2 L/C4K; D8: HE-364 Warm; | J18- HV MLI, Mag shields | J17- Move to WS4 | J03- Prep for BPM work | PCM- Ship Alignment J12- Beam Line reconfig US/DS | C100R-06- Nitronic rods, MLI 2K | LERF- CM16 Cryogenic bellows, LC J18- Move to WS3 West
2019-05-11 | Sat | [6 empty] | SC-08 800C 3N60; | [11 empty] | bag J1.3-19 | [9 empty] | LERF- Shields/MLI in ICR
2019-05-12 | Sun | [6 empty] | SC-08 800C 3N60;
2019-05-13 | Mon | Nb cover |  | L2-115; L2-Bellows; |  |  | L2-104; | SC-08 800C 3N60; |  | HWCoax2 |  | L2-109; Clean Rm curtains; RA valves (x15); Bellows (x16); Bbolts (x32); |  | 5C75-RI-NBSN1 80u; | HPR1: OOC HPR2: 5C75-RI-004; RDT-10 |  |  |  | L2-160, 088, 103 D5; | HE-353; J1.3-19; L2-160, 088, 103 D5; | HWCoax-1 120C/6h; | HE-353; |  | D1: SIC C/T; D2: Nb Sample L/C2K/T/ D3: HWCoax-1 pull; D4: D5: D6: D7: DQW2 C2K/Test/W; D8: HE-364 WDLC/pull; HE-353 L/C4K; | J18- FS Sheet | J17- Prep VV J03- Prep for BPM work | J17- Move to WS4 | PCM- Prep for bellows replacement J12- Beam Line reconfig US/DS, prep for ship alignment | C100R-06- Adjust cold tuner, prep Space Frame | LERF- CM16 Cryogenic bellows J18- UCM Move to WS3 West
2019-05-14 | Tue | LSFC-08; |  | L2-BLA; L2-104; |  |  | J1.3-12 HOMs; | SC-08 800C 3N60; |  |  |  | L2-115; 5C75-RI-NBSN1 | HWCoax2 setup; | 5C75-RI-NBSN1 40u; | HPR1: OOC HPR2: |  |  |  | 5C75-RI-004 D3/4; L2 BLA; RDT-10 D6; | HE-364; | HWCoax-1 120C/6h; | L2-160, 088, 103 D5; |  | D1: SIC C/T; D2: Nb Sample Pull; D3: D4: D5: L2-160, 088, 103 L/precool; D6: D7: DQW2 warm/pull; HE-364 L/WDLC/C4K; D8: HE-353 C2K/T/W; | J18- FS Sheet, Move to WS3 | J03- Prep for BPM work J18- Move UCM | J17- Tuners, mag shields | PCM- bellows replacement J12- ship alignment, measure HOM's | C100R-06- Adjust cold tuner, prep Space Frame | LERF- CM16 Cryogenic bellows, LC J18- UCM Move to WS3 West
2019-05-15 | Wed | LSFC-09, LSFC-12; |  | L2-104; L2-120; |  |  | L2-120; 5C75-RI-001; | 5C75-RI-NBSN1 800C/2h; |  |  |  | HWCoax2; BLA body, flanges, HW; FNAL bellows (x2); L2 gaskets; RDTTD-02 HW; split rings (x6); | HWCoax2 150u; | SC-08, RDTTD-02, EZSSC-05 setup; | HPR1: OOC HPR2: RDTTD-01; 5C75-RI-NBSN1 (3pass); |  | J1.3-19 rollout; |  |  | 5C75-RI-004; L2 BLA; RDT-10; |  | 5C75-RI-004; RDT-10; DQW2 input cable; |  | D1: SIC C/T/W; D2: Nb Sample L/C4K/T?; D3: 5C75-RI-004 L/C4K; D4: D5: L2-160, 088, 103 warm/C2K; D6: RDT-10 L/SC4K; D7: HE-364 C2K/T/W; D8: HE-353 hold @4K; | J19- 2 phase piping | J03- Prep for BPM work J18- Unite UCM to CS | J17- Tuners, mag shields | PCM- bellows replacement J12- ship alignment, Tune HOM's? | C100R-06- Adjust cold tuner, prep Space Frame | LERF- CM16 Cryogenic bellows, LC J19- Deliver CS
2019-05-16 | Thu | LSFC-12; | HDIce? | L2-DS spools; L2-Bellows; |  |  | L2-116; 5C75-RI-001 freq & BP (pm); J1.3-12 HOMs; J1.3-19; | 5C75-RI-NBSN1 800C/2h; | 5C75-RI-001; | HWCoax2; | Nb box, caps & foil; | FNAL bellows (x9); SC-08, RDTTD-02, EZSSC-05; L2-104; |  | SC-08, RDTTD-02, EZSSC-05 8u; | HPR1: OOC HPR2: |  | 5pm Power Out | cage L2-083; | L2 BLA; L2-115, L2-109 D5; 5pm Power Out | L2 BLA; 5pm Power Out |  | 5pm Power Out; |  | Test Lab Power Glitch, CTF Outage D1: SIC hold; D2: RRR L/C/T; D3: 5C75-RI-004 C2K/T/W; D4: D5: L2-160, 088, 103 T/W; D6: RDT-10 SC2K/T/W; D7: HE-364 warm D8: HE-353 C4K; | J19- 2 phase piping | J03- Prep for BPM work, test software win10 J18- UCM Align, Unite UCM to CS | J17- Tuners, mag shields, RF cables | PCM- bellows replacement J12- Tune HOM's, Prep for shipping | C100R-06- Adjust cold tuner, prep Space Frame | LERF- CM16 Cryogenic bellows LC, close up ICR
2019-05-17 | Fri | Secure Equip. 5-7AM power Out | Secure Equip. 5-7AM power Out | L2-DS spools; L2-120; |  |  | 5C75-RI-NBSN1 tune freq & FF, set probes; | Secure Equip. 5-7AM power Out; regen; RDTTD-01 & samples 800C/3h, 120C/48h/N2; | 5C75-RI-001; |  |  | HE-352; | 5-7AM power Out | 5-7AM power Out; HE-352 setup & 8u; | HPR1: OOC HPR2: Clean Up Run 2 hr. RDTTD-02 (pm); |  | Clean CR | Clean CR | Clean CR L2 BLA; | L2 BLA; |  |  |  | D1: SIC pull; D2: RRR W/T; D3: 5C75-RI-004 warm; D4: D5: L2-160, 088, 103 warm D6: RDT-10 SC2K/T/W; D7: HE-364 warm; D8: HE-353 C2K/T/W; | J19- 2 phase piping | J03- Prep for BPM work, test software win10 J18- UCM Align, Unite UCM to CS | J17- Tuners, mag shields, RF cables | PCM- bellows replacement J12- Tune HOM's, Prep for shipping | C100R-06- Adjust cold tuner, prep Space Frame | LERF- CM16 Cryogenic bellows LC, close up ICR Shipping frame in
2019-05-18 | Sat | [6 empty] | RDTTD-01 800C/3h, 120C/48h/N2; | [10 empty] | RDTTD-02, | RDTTD-02,
2019-05-19 | Sun | [6 empty] | RDTTD-01 800C/3h, 120C/48h/N2;
2019-05-20 | Mon |  | BB cleaning; | L2-116; 5C75-RI-NbSn1; |  |  | L2-147 | RDTTD-01 800C/3h, 120C/48h/N2; HWCoax2 800C/4h; | 5C75-RI-001; | 5C75-RI-NbSn1 |  | FPC hardware kit (x8) |  | maint; 5C75-RI-NbSn1 setup; | HPR1: OOC HPR2: HE-352; |  |  | HE-364 fast; HE-353 fast; | L2 BLA; | L2-115, L2-104, L2-109 D5; |  | 5C75-RI-004 OST and sensor removal; L2-115, L2-104, L2-109; |  | D1: D2: RRR W/pull; Nb sample L/C/T D3: 5C75-RI-004 pull; D4: D5: L2-160, 088, 103 pull;L2-115, L2-104, L2-109 L D6: RDTTD-02 L; D7: HE-364 pull; D8: HE-353 pull, DQW2 L/C4K | J19- Alignment, 2 phase piping | J03- Prep for BPM work J18- Unite UCM to CS | J17- Tuners, mag shields, RF cables | PCM- bellows replacement J15- Remove from Test Cave | C100R-06- Adjust cold tuner, prep Space Frame | LERF- Ins Vac LC, Condition He circuit
2019-05-21 | Tue |  |  | L2-DS spools; L2-147; |  |  |  | HWCoax2; | 5C75-RI-NbSn1 blanks; | 5C75-RI-NbSn2; |  | 5C75-RI-001; J1.3-03 BPM hardware; 5C75-RI-NbSn1; |  | 5C75-RI-NbSn1 25u; | HPR1: OOC HPR2: L2-083; HE-352; |  | HE-352; cage 105; | 5C75-RI-004 | L2 BPM; | L2 BLA; |  |  |  | D1: D2: D3: D4: D5: L2-115, L2-104, L2-109 precool; D6: RDTTD-02 C2K/T; D7: D8: DQW2 C2K/T; | J19- Alignment, 2 phase piping, magnet install | J03- Slow Bleed up CS J18- Unite UCM to CS | J17- Tuners, mag shields, RF cables | PCM- RT Wednesday 5pm, Instrumentation flanges J15- Remove Bayonet Box, Prep for BL work | C100R-06- Adjust cold tuner, prep Space Frame | LERF- Ins Vac LC, Gas returning to CHL
2019-05-22 | Wed | Nb Cover | injector electrode; | L2-Mag shield; RFD Damper brazed parts; |  |  | 5C75-RI-NbSn2 check FF & freq; | maint run; | 5C75-RI-NbSn1 blanks; |  | 5C75-RI-001; 5C75-RI-NbSn1 blanks; Nb samples; | 5C75-RI-001; HE-349; Cav-147; |  | RDT-06, RDL-02, RDT-05 setup; | HPR1: OOC HPR2: L2-105; L2-083; |  | L2-083; | HE-353; | HE-352 D7/8; J1.3-03 BPM hardware; |  |  |  |  | D1: D2: D3: D4: D5: L2-115, L2-104, L2-109 W/C2K; D6: RDTTD-02 Pull; RDT-10 L/SC2K/T/W; D7: D8: DQW2 W; | J19- Alignment, 2 phase piping | J03- Replace BPM Hardware,LC J18- Unite UCM to CS | J17- mag shields, RF cables | PCM- RT Wednesday 5pm J15- Prep for BL work | C100R-06- prep for Space Frame | LERF- Ins Vac LC, Gas returning to CHL, Cooldown Stubby comes home, into CMTF
2019-05-23 | Thu |  |  | 5C75-RI-NbSn1; 5C75RI-NbSn2; L2-131; |  |  | 5C75-RI-001 Qext; | maint run; | 5C75-RI-NbSn1; |  | 5C75-RI-001 flanges; RFD Damper brazed parts; | RDT-06, RDL-02, RDT-05; |  | RDT-06, RDL-02, RDT-05 10u; | HPR1: OOC HPR2: RDTTD-01; L2-105; |  | L2-105; |  | L2-083 D7/8; L2-BPM; L2-116, L2-147, L2-120 D5; | HE-352; |  |  |  | D1: D2: D3: field map, HWCoax-1 L D4: D5: L2-115, L2-104, L2-109 T/W; D6: D7: D8: DQW2 pull; | J19- 2 phase piping, berry bolts, instrumentation | J03- LC BPM Hardware J18- Unite UCM to CS, Install Cav1 tuner | J17- Instrumentation, mag shields | PCM- RT failed, discuss plan J15- Remove ion pump, configure 4 shipping | C100R-06- Space Frame first section | LERF- Cooldown SRF Team Bldg Event
2019-05-24 | Fri | maint; |  | L2-Mag Shields; L2-131; |  |  | L2-133?; | Nb samples 800C/3h; | 5C75-RI-NbSn1; | 5C75-RI-NbSn2; | 5C75-RI-NbSn1; DQW damper 100u; | 5C75-RI-NbSn1; 5C75-RI-001 and HW; String bellows x9; |  | 5C75-RI-NbSn2 setup; | HPR1: OOC HPR2: 5C75-RI-001; 5C75-RI-NbSn1 3P; |  |  |  | L2-105 D7/8; L2-BPM; L2-116, L2-147, L2-120 D5; RDTTD-01; | L2-083; RDTTD-01; |  | HE-352; | L2-1; L2-2; | D1: D2: D3: HWCoax C4K D4: D5: L2-115, L2-104, L2-109 Warm; D6: RDTTD-01 L/C2K/T/W; D7: HE-352 L/C4K; D8: | J19- 2 phase piping, instrumentation | J03- LC BPM J18- 2 phase piping, Remove lollipops | J17- Instrumentation, RF cables | PCM- Work plan J15- configure 4 shipping | C100R-06- Space Frame first section | LERF- Cooldown Weld cav stands
2019-05-25 | Sat | [21 empty] | L2-3;
2019-05-26 | Sun | [15 empty] | 5C75-RI-NbSn1 TS28-006; | [6 empty] | D3: HWCoax C2K/T
2019-05-27 | Mon | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: HWCoax C2K/T D4: D5: D6: D7: D8:
2019-05-28 | Tue |  | L2 spools; L2 bellows; |  |  |  | prep L2-131; | maint |  |  |  | String Prep; carriages; L2-1; L2-2; L2-3; |  | 5C75-RI-NbSn2 80u; | HPR1: OOC HPR2: 5C75-RI-NbSn1 3P; |  | L2 mag meas.; | Lollipops; | 5C75-RI-NBSN1 TS 006; | L2 BPM; L2-116, L2-147, L2-120 D5; L2-105; |  | L2-105; L2-116, L2-147, L2-120; | L2-4; | D1: D2: D3: HWCoax C2K/T D4: D5: L2-115, L2-104, L2-109 Pull; D6: D7: HE-352 C2K/T/W; D8: L2-105 L/C4K; | J19- 2 phase piping, instrumentation | J03- Install ship manifold J18- Mag shields, heat stations | J17- Instrumentation, RF cables | PCM- Weld JT repair J15- configure 4 shipping, remove testing cap | C100R-06- Close SF sections | LERF- Charge He manifolds Weld cav stands
2019-05-29 | Wed | C50 windows; | L2 spools; L2 bellows; | HPR Fixture (SC); L2-Bellows; |  |  | J1.3-17 HOMs; | maint |  |  | Steel pipes x2; | Lollipops & HW; 5C75-RI-NbSn2; |  | 5C75-RI-NbSn2 40u; | HPR1: OOC HPR2: RDT6; |  |  |  | L2 bellows; RDT6; | RDT6; 5C75-RI-NbSn1; |  |  | L2-5; L2-6; | D1: D2: D3: HWCoax C2K/T; D4: D5: L2-116, L2-147, L2-120 L/precool; D6: RDT-10 L/SC4K/T; D7: HE-352 warm/pull; 5C75-RI-NbSn1 L/C4K; D8: L2-105 C2K/T/W; | J19- 2 phase piping, instrumentation | J03- Install ship manifold, LC J18- Mag shields, heat stations, Magnet leads | J17- HOM Tuning, lower shields | PCM- RT of weld repair J15- configure 4 shipping, remove testing cap | C100R-06- Close SF sections, alignment of monuments | FYI- RT scheduled for Thursday May 30th 5 pm.
2019-05-30 | Thu | C50 windows; | L2 Bellows | L2-BLA; L2-Bellows; |  |  | L2-333 | 5C75-RI-NbSn2 800C/2h; |  |  | Nb and Mb parts BCP; Nb caps and foils; Cu discs; | L2 tools; L2-4; L2-5; L2-6; |  | L2-131 setup; | HPR1: OOC HPR2: 5C75-RI-NbSn2 (3p); RDTTD-02; |  | Lollipops; cage L2-1; cage L2-2; spring clamps; | L2-083; L2-105; |  |  |  |  | L2-7; L2-8; | D1: D2: D3: HWCoax warm; D4: D5: L2-116, L2-147, L2-120 warm; D6: RDT-06 L/C/T/W D7: 5C75-RI-NbSn1 C2K/T/W; D8: L2-105 Warm/pull; | J19- 2 phase piping, LC, instrumentation | J03- FSS J18- Weld 2 phase piping, heat stations, Magnet leads | J17- Install lower shields, verify HOM's | PCM- RT of weld repair J15- configure 4 shipping, install ship manifold LC | C100R-06- Close SF sections, heat stationing | RT scheduled for Thursday May 30th 5 pm. NL07 CMTF - Install degauss coils, WG's in progress
2019-05-31 | Fri | C50Windows; | L2 Bellows; Nb sample anneal; | L2-Bellows; L2-333; |  |  | L2-334 | 5C75-RI-NbSn2 800C/2h; RDTTD-02 NL137 800C/3h/120C/48/N2; |  |  | SCIB; | L2-131; String Prep; L2-7; L2-8; SCIB; |  |  | HPR1: OOC HPR2: RDTTD-01, L2-131 1P; 5C75-NbSn1 |  | Lollipops; cage L2-3; cage L2-4; spring clamps; | L2-083; | [5 empty] | D1: D2: D3: HWCoax warm; D4: D5: L2-116, L2-147, L2-120 warm; D6: RTD-10 Load/SC2K/T D7: 5C75-RI-NbSn1 warm/pull; D8: | J19- 2 phase piping, LC, instrumentation | J03- FSS J18- Weld 2 phase piping, heat stations, Magnet leads | J17- Weld lower shields, MLI | PCM- Weld remaining JT piping J15- configure 4 shipping, install ship manifold LC | C100R-06- Close SF sections, alignment of monuments | NL07 CMTF - Install degauss coils, WG's in progress
2019-06-01 | Sat | [6 empty] | RDTTD-02 NL137 800C/3h/120C/48/N2; | [6 empty] | HPR2: |  | String Prep | [10 empty] | J15- Complete ship beam line work | Space frame and intercepts | Break down SSA boxes bldg 36
2019-06-02 | Sun | [6 empty] | RDTTD-02 NL137 800C/3h/120C/48/N2; | [8 empty] | String Prep
2019-06-03 | Mon | C50Windows; | RFD Damper; | L2-334; |  |  | J1.3-17 Tune HOM's, 5C75-RI-NbSn2 FF, freq and probes; | RDTTD-02 NL137 800C/3h/120C/48/N2; |  |  | DQW HOM 100u; PD Nb samples; Ti parts (AP); Sample chamber & plates; | L2 FPC HW; L2-333; L2-131; DQW HOM & HW; Long spools & bellows; L2 Vacuum header; |  | L2-131 1.5u; maintenance; | HPR1: OOC HPR2: |  |  |  | 5C75-NbSn1 TS28-006; |  | HWCoax1 120C/6h; | L2-116, L2-147, L2-120; |  | D1: D2: Nb Sample L/C4K; D3: HWCoax pull; D4: D5: L2-116, L2-147, L2-120 pull/L; D6: RTD-10 SC2K/T D7: D8: | J19- LC 2 phase piping instrumentation,MLI | J03- FSS J18- Weld 2 phase piping, heat stations, Solder Magnet leads | J17- Evaluate HOM's, Weld lower shields, MLI | PCM- Weld remaining JT piping J15- configure 4 shipping, install m-mounts, Ship alignment | C100R-06- Close SF section, install thermal straps | NL07 CMTF - WG's in progress, establish vacuums, install fluxgates UCM from Blue Crab onto N4 post
2019-06-04 | Tue | C75 eyelets; | RFD Damper; | L2-BLA; |  |  | 5C75-RI-NbSn2 FF, freq and probes; | DQW HOM 600C/10h; |  |  | Ti parts (AP); | L2-334; |  | L2-131 setup; L2-131 1.5u; | HPR1: OOC HPR2: L2-083; EZSSC-05; |  |  |  | L2-333,D5; EZSSC-05; | 5C75-NbSn1; | HWCoax1 120C/6h ; | HWCoax1; |  | D1: D2: Nb Sample L/C4K; D3: D4: D5: L2-116, L2-147, L2-120 hold; D6: RDTTD-01 L/C/T/W; D7: 5C75-NbSn1 L/C2K/T/W D8: | J19- LC 2 phase piping instrumentation,MLI | J03- FSS, Checklist J18- Weld,LC 2 phase piping, Solder Magnet leads | J17- MLI, into VV | PCM- Weld remaining JT piping J15- install m-mounts, prep for ship | C100R-06- Weld shield bellows, install thermal straps | NL07 CMTF - establish vacuums, Instrumentation Tentative- Next PCM RT scheduled for 6/8 @8am
2019-06-05 | Wed | Nb cylindrical welds (GE); C75 eyelets; | RFD Damper; | RFD beampipe; C75RI-NbSn2; |  |  | L2-295; | DQW HOM 600C/10h; |  |  | Mb BCP; Nb cylindrical welds (GE); Ti Parts (AP); | L2-286 HW; Mb nuts; L2-131; Ti rods; |  | L2-131 tear down; HE-353 setup; | HPR1: OOC HPR2: RDTTD-02; L2-131 1p; L2-286; |  |  |  | L2-083 D7/8; L2-334, L2-333 D5; | EZSSC-05; |  | EZSSC-05; |  | D1: D2: Nb Sample L/C4K; D3: maint; HWCoax1 L/C4K/T; D4: D5: L2-116, L2-147, L2-120 precool; D6: EZSSC-05 L/C2K/T/W; D7: 5C75-NbSn1 warm/pull (PM); D8: | J19- LC 2 phase piping instrumentation,HV MLI,Mag shields | J03- FSS, Checklist J18- LC 2 phase piping, Solder Magnet leads | J17- Into VV, Align | PCM- Weld remaining JT piping J15- Prep for shipment | C100R-06- Close SF section, install thermal straps | NL07 CMTF - establish vacuums, Instrumentation, U-tubes first phase?
2019-06-06 | Thu | Nb cylindrical welds (GE); C75 eyelets; | Au sputter; L2 spools | L2-Tuner; C75-RI-NbSn2; |  |  | L2-295; C75-RI-NbSn2 beadpull; | DQW HOM 600C/10h; |  |  | Nb sample chamber; |  |  | HE-353 12u; Acid change; | HPR1: OOC HPR2: L2-286; HE-353 overnight; |  | L2-286; |  | RDTTD-02; HE-349; | L2-083 D7/8; |  | L2-083 D7/8; |  | CMTF U-tubes D1: TC L; D2: RRR L/C D3: HWCoax1 C2K/T/W D4: D5: L2-116, L2-147, L2-120 w/hold; D6: RDT-10 L/SC4K/2K/T/W D7: L2-083 L/C2K; D8: | J19- HV MLI,Mag shields, FSS | J03- Lower shield Test fit, tune HOM's J18- Weld/ LC 2 phase piping, Heat station Magnet leads | J17- Align in VV | PCM- Weld remaining JT piping, LPT J15- Prep for shipment, Tune HOM's | C100R-06- Tooling setup, Prep for alignment | NL07 CMTF - U-tubes 9:30
2019-06-07 | Fri | Nb cylindrical welds (GE); C75 eyelets; | L2 spools Au sputter; | L2-Spools; L2-Bellows; |  |  |  | Nb sample 2N6; |  |  | DQW HOM 10u; 5C75-NbSn1 nitric flanges; | DQW HOM; L2-295; RFD Damper; |  | HF spike; 5C75-RI-NbSn2 setup; | HPR1: OOC HPR2: 5C75-RI-NbSn1 |  |  |  | L2-333, L2-334, L2-286 D5; | RDTTD-02 HE-349; |  |  |  | D1: TC pull; D2: RRR W/T; D3: HWCoax1 C2K/T/W; D4: D5: L2-116, L2-147, L2-120 C4K; D6: RDT-10 SC4K/2K/T/W; D7: L2-083 /T/W; D8: | J19- Mag shields, FSS, Checklist | J03- tune HOM's J18-Prep for CS align Heat station Magnet leads, LC 2 Phase | J17- move to WS5 | PCM- LPTest J15- Prep for shipment, move to WS6 | C100R-06- Remove lollipops, prep for alignment | NL07 CMTF - Move vaporizer VV from UITF to WS4 Scheduled- Next PCM RT scheduled for 6/8 @7am. TATL 3420
2019-06-08 | Sat | [6 empty] | Nb sample 2N6; | [6 empty] | HPR2: | [8 empty] | D3: | [5 empty] | RT at 7am on PCM final weld
2019-06-09 | Sun | [6 empty] | Nb sample 2N6; | [6 empty] | HPR2:
2019-06-10 | Mon | Nb parts; | Au sputter; Nb anneal; | L2-337; RFD Damper; |  |  | L2-338; |  |  |  |  | 5C75-RI-NbSn2; string prep; |  | 5C75-RI-NbSn2 30u; | HPR1: OOC HPR2: L2-1; L2-2; 5C75-RI-NbSn2 overnight; |  | string prep; 5C75-RI-NbSn1; 5C75-RI-NbSn2; |  |  | L2-333, L2-334, L2-286 D5; |  | HE-349; |  | D1: D2: RRR Pull; D3: HWCoax1 hold; D4: D5: L2-116, L2-147, L2-120 C2K; D6: RDTTD-02 L/C/T/W; D7: L2-083 pull; HE-349 L/C4K; D8: | J19- Checklist | J19- Align UCM to rails J18-LC 2 Phase, Prep for CS align, torque Magnet leads | J03- Tune HOM's, install lower shields | PCM- LC Piping, close VV side port J17- Prep for beam line work and WC's | C100R-06- Remove lollipops | J15- At WS6, Prep for shipping
2019-06-11 | Tue | Nb parts; | Au sputter; Ti anneal; | L2-338; L2-BLA; |  | L | J1.3-03 HOM's; |  | Warm coupler components (x3); |  | RFD BCP, Cu Bright; RFD Damper flange S/S; | SSMMSC parts; |  | AES-006 setup; | HPR1: OOC HPR2: L2-3; L2-4; |  | cage L2-5; cage L2-6; |  | L2-1; L2-2; 5C75-RI-NbSn2 TS28-006; |  |  | L2-333, L2-334, L2-286 D5; |  | CMTF u-tubes D1: TC L/C/T; D2: D3: D4: D5: L2-116, L2-147, L2-120 test/warm; D6: D7: HE-349 C2K; D8: | J19- Move to WS3 | J19- Transfer CS J18- LC 2 Phase, Prep for CS align | J03- Install lower shields, verify HOM's | PCM- LC Piping, close VV side port J17- Beam line work and WC's, JT's | C100R-06- CS Alignment | J15- At WS6, Prep for shipping, trailer in today NL07- U-tubes 10am?
2019-06-12 | Wed | Nb parts; C75 windows; | Regen | L2-338 degauss; L2-341; |  |  | L2-337; L2-342; |  | Warm coupler components (x3); |  | Sample holder; Nb blank; RDT-6 flange BCP; | Cage 5C75-RI-001; L2-337; AES-006; HE-354; Warm coupler components; RDT-6 parts; SCIB and HW; MC lines & HW; |  | AES-006 60u; | HPR1: OOC HPR2: L2-5; L2-6; |  | cage L2-7; cage L2-8; |  | L2-3; L2-4; | 5C75-RI-NbSn2; |  | L2-333, L2-334, L2-286 sensors; |  | D1: TC pull D2: D3: D4: D5: L2-116, L2-147, L2-120 warm; D6: D7: HE-349 test/warm; D8: 5C75-RI-NbSn2 L/C4K/C2K/t/; | J19- QC/Demag ucm @WS3 | J19- Demag small parts J18- Prep for CS align | J03- verify HOM's, weld shields | PCM- LPT, n-mount procedure J17- Beam line work and WC's, JT's | C100R-06- CS Alignment | J15- At WS6, Load in shipping trailer NL07- Cold
2019-06-13 | Thu | C75 windows; | RFD Damper; | L2-341 degauss; HPR fixture (SC); |  |  | L2-341; | NbDSamples 3N60; |  |  | Nb foil (x40); Nb blanks (x3); Nb sample box; | L2-338; BLA kits (x3); BLA body (x2); Valve & conflat components (x8 kits); RDTTD-01 & HW; SSMCLN clamps; |  | AES-007 setup; | HPR1: OOC HPR2: SCIB; L2-7; L2-8; AES-006 overnight; |  |  |  | L2-5; L2-6; SCIB TS16-008; HE-354 D7/8; |  |  |  |  | D1: TC L/C/T; D2: RRR L/C D3: D4: D5: L2-116, L2-147, L2-120 pull; L2-333, L2-334, L2-286 L/precool; D6: D7: HE-349 warm; D8: 5C75-RI-NbSn2 warm; | J19- QC/Demag ucm @WS3 | J19- Demag small parts, tranfer CS J18- Prep for CS align | J03- MLI, into VV | PCM- Tune Cav8, n-mount procedure, close VV side port J17- Beam line work and WC's, weld JT's | C100R-06- CS Alignment | J15- At WS6, shipping trailer NL07- Cold
2019-06-14 | Fri | C75 windows; | RFD Damper; | L2-BLA; L2-295 partial; L2-Bellows; |  |  | L2-133 (string 9); | NbDSamples 3N60; | Warm coupler components (x2); |  | Nb sample plates 30um (x20) AP; | L2-341; L2-342; AES-007; |  | AES-007 60u; | HPR1: OOC HPR2: RDTTD-01; RDT-6; 5C75-RI-001; |  |  |  | L2-7; L2-8; | SCIB HE-354; |  | SCIB | D5-1 | D1: TC pull; D2: RRR W/T; D3: D4: D5: L2-333, L2-334, L2-286 W/C2K; D6: SCIB L/SC4K/T/W D7: HE-349 pull; D8: 5C75-RI-NbSn2 pull; |  | J19- tranfer CS, unite UCM to CS J18- Prep for CS align | J03- Align in VV | PCM- Tune Cav8, n-mount procedure J17- Beam line work and WC's, JT's | C100R-06- CS Alignment | J15- Leave for SLAC
2019-06-15 | Sat | [22 empty] | D5: L2-333, L2-334, L2-286 T/W;
2019-06-16 | Sun
2019-06-17 | Mon | Nb crucible; | RFD Damper; HDIce; Au Sputter | L2-BLA; L2-342; |  |  | L2-133 (string 9); L2-295; | Nb sample 1000C/3h; | Warm coupler components (x4); EIC-1; |  | C75 blanks; EZSSC-05 30u & Nitric flanges; EIC1; | EZSSC-05; Berry Bolts; dogs legs (x2); 5C75-RI-NbSn1 & HW; EIC-1; |  | 5C75-J-005 setup; | HPR1: OOC HPR2: AES-007 1p; 5C75-RI-NbSn1 |  |  | EZSSC-05; |  | J1.3-20 investigation; |  |  | D5-2 | D1: D2: RRR pull; L/C/T/W D3: D4: D5: L2-333, L2-334, L2-286 pull; D6: RDTTD-01 L/C2K/T/W; D7: D8: |  | J19- tranfer CS, unite UCM to CS J18- CS to UCM alignment | J03- Move to WS 5 | J03- Prep for BL work & WC's J17- Beam line work, HPT, MC Line | C100R-06- Heat stations, RF Cables | J15- Arrived @ SLAC, Vac intact PCM- Move in fromt of Weld Area,Tune Cav8, n-mount procedure VV from BC
2019-06-18 | Tue | Nb crucible; C75 windows; | HDIce; Inj apertures; |  |  |  | L2-133 (string 9); L2-295; C75-J-004 probes; HE-353 FF; | RDT-6 800C/3h; 140C/48h N2; |  |  | Inj apertures; | C100 beampipes; 5C75-J-005; Inj apertures; |  | 5C75-J-005 30u; | HPR1: OOC HPR2: EIC-1; 5C75-RI-NbSn1; 5C75-RI-001; |  | 5C75-RI-NbSn1; 5C75-RI-001; |  | L2-337, L2-338, L2-341 D5; L2-BLA prep; | J1.3-20 investigation; L2-337, L2-338, L2-341 D5; |  |  | D5-3 | PSS Certification a.m. D1: TC L/C4K; D2: RRR W/T D3: D4: D5: D6: D7: D8: |  | J19- tranfer CS, unite UCM to CS J18- CS to UCM alignment | J07- Move to WS4, Remove VV | J03- WC's, BL work J17- Beam line work, MC Line, final JT weld | C100R-06- Heat stations, RF Cables | PCM- Tune Cav8, n-mount procedure
2019-06-19 | Wed | Nb crucible; C75 windows; | Inj apertures; | L2-BLA; |  |  | L2-281; L2-131; L2-118; | RDT-6 800C/3h; 140C/48h N2; | Warm coupler components (x4); C75-J-004 |  |  | C100 beampipes; |  | maint; 5C75-RI-002 setup; | HPR1: OOC HPR2: EIC-1; |  |  |  | 5C75-RI-001 D3/4; 5C75-RI-NbSn1 TS28-006; | J1.3-20 investigation; |  | L2-337, L2-338, L2-341 D5; |  | D1: TC C2K/T/W; D2: RRR C/T D3: D4: D5: L2-337, L2-338, L2-341 L D6: D7: D8: |  | J19- unite UCM to CS J18- CS to UCM alignment | J07- Remove shields | J03- WC's, BL work J17- MC Line, final JT weld, LPT | C100R-06- Heat stations, RF Cables, prep EC's | PCM- Tune Cav1, n-mount procedure Weld waveguide for MS RT scheduled for Saturday June 22nd 7AM
2019-06-20 | Thu | C75 windows; | Inj apertures; | L2-Bellows; L2-Spools; L2 BLAs; L2-281 |  |  | L2-118; L2-281 | RDT-6 800C/3h; 140C/48h N2; | C75-J-004; |  |  |  |  | 5C75-RI-002 70u; | HPR1: OOC HPR2: |  |  |  | L2-BLA; | 5C75-RI-NbSn1; 5C75-RI-001; |  |  |  | D1: TC pull; TC L; D2: RRR warm; D3: D4: D5: L2-337, L2-338, L2-341 precool/W/C2K; D6: D7: D8: |  | J19- unite UCM to CS J18- CS to UCM alignment | J07-FSS | J03- WC's, weld PV's J17- MC Line LC, Add Bayonet box, LC 2 phase | C100R-06- Heat stations, RF Cables, prep EC's, close shield,MLI | PCM- N-Mount procedure
2019-06-21 | Fri | C75 windows; | Inj apertures; | L2-Tuners; L2-BLAs; |  |  |  |  | C75-J-004; |  | C75-J-004 flanges; | 5C75-RI-002; C75-J-004; |  | 5C75-RI-002 30u; | HPR1: OOC HPR2: |  |  |  |  | L2-BLA; |  | 5C75-RI-001 mag & therm; 5C75-RI-NbSn1 thermal; | L2-331 PvsF; | D1: TC C/T/W; D2: RRR pull; D3: 5C75-RI-001 L/C4K; D4: D5: L2-337, L2-338, L2-341 T/W; D6: D7: 5C75-RI-NbSn1 L/SC4K D8: |  | J19- Add bearing block assy's J18-CS to UCM alignment | J07-FSS | J03- WC's, weld PV's, HPT J17- MC Line LC, Bayonet box , LC 2 phase | C100R-06- Heat stations, RF Cables, prep EC's, close shield,MLI | PCM- Move to storage
2019-06-22 | Sat | [28 empty] | RT J1.3-17 and J1.3-03 @7AM
2019-06-23 | Sun | [13 empty] | HPR2:
2019-06-24 | Mon | C75 windows; | HD Ice; | L2-spools; RFD Damper; L2-BLA; |  |  | 5C75-RI-002 FF & freq; | [6 empty] | 5C75-RI-003 setup; | HPR1: OOC HPR2: EIC1; RDT-6; |  |  | DQW1; | J1.3-20 dis; L2-BLA; RDT-6; |  |  |  |  | D1: TC pull; TC L/C4K; D2: D3: 5C75-RI-001 C2K/T/C1.8K/T/W; D4: D5: L2-337, L2-338, L2-341 pull; D6: D7: 5C75-RI-NBSN1 SC4K/T/C2K; D8: |  | J19- Add bearing block assy's, Weld 2 phase piping, prep magnet leads J18- Install tuners | J07-FSS | J03- WC's, Inst flanges J17- MC Line LC, LC 2 phase | C100R-06- Alignment, RF Measurements, prep EC's, close shield,MLI | PCM- Close up, move to storage
2019-06-25 | Tue | C75 windows; | HD Ice; | HPR fixture; L2-BLA; |  |  | C100-6R; |  |  |  |  | HE-351; 5C75-RI-002; DQW parts; L2 BLA; L2-536 parts; SS pipes x4 tee's HW; |  | 5C75-RI-003 60u; | HPR1: OOC HPR2: L2-536 DQW1 |  |  | DQW1; | HE-351 D7/8 & torque flanges; EIC1 D3/4; | HE-351; L2-BLA leaked; RDT-6; |  |  |  | D1: TC C2K/T; D2: D3: 5C75-RI-001 warm; D4: D5: D6: RDT-6 L/C2K/T/W --> 20K; D7: 5C75-RI-NBSN1 T/W; D8: |  | J19- Weld 2 phase piping, prep magnet leads J18- Install tuners | J07-FSS | J03- WC's, Inst flanges, LPT J17- LC 2 phase, Inst flanges, RF Waveguides | C100R-06- review/retune hom's? Prep EC's, close shield & MLI | PCM- Move to storage
2019-06-26 | Wed | C75 windows; | 1200 C | L2-281; L2-065; L2-Bellows; |  |  |  | 5C75-RI-002 450C/3h, 800C/3h; |  |  |  | 5C75-RI-003; Bellows x6; String HW; |  | 5C75-RI-003 40u; | HPR1: OOC HPR2: L2-536; |  | L2-536; | L2-BLA |  | EIC1; |  | 5C75-RI-001 mark quench locations; EIC1; HE-351; | L2-286; | D1: TC C2K/T; D2: D3: 5C75-RI-001 pull; D4: D5: D6: RDT-6 C2K/T/W; D7: 5C75-RI-NBSN1 pull; EIC1 L/SC4K; D8: HE-351 L/C4K; |  | J19- Weld 2 phase piping, Install Cav 1 tuner J18- Install tuners, mag shields | J07-FSS | J03- WC's, Inst flanges, LPT J17- LC 2 phase, Inst flanges, close VV sport | C100R-06- prep EC's, install outer mag shields
2019-06-27 | Thu | C75 windows; | L2 BLA; RFD Damper; | L2-065; |  |  | L2-065; | 5C75-RI-002 450C/3h, 800C/3h; | BLA flange; |  | C75 flanges; | BLA; C75 flanges; |  | 5C75-J-002 setup; | HPR1: OOC HPR2: 5C75-J-004 |  | cage 5C75-J-004; | 5C75-RI-001; | L2-BLA; DQW1 D5; L2-536 D7/8; |  |  |  |  | D1: TC C2K/T; D2: D3: D4: D5: D6: D7: EIC1 C2K/T; D8: HE-351 C2K/T/W; |  | J19- Weld 2 phase piping J18- Install tuners, HV Mag shields | J07-FSS | J03- WC's, Inst flanges, LC 2 phase J17- Inst flanges, 2 phase LC | C100R-06- Outer Mag shield, fiducialize SF
2019-06-28 | Fri | C75 windows; | L2 BLA; | L2-068; Coupler gaskets; |  |  | L2-068; | 5C75-RI-002 450C/3h, 800C/3h; |  |  |  | 5C75-J-002; L2 string gaskets; L2 FPC HW; |  | 5C75-J-002 30u; | HPR1: OOC HPR2: 5C75-J-004 |  | 5C75-J-004 |  | L2-BLA; | L2-536; L2-BLA; |  | L2-536; |  | D1: TC C1.5K/T/W; D2: D3: D4: D5: D6: D7: EIC1 T/warm; D8: HE-351 warm; |  | J19- Remove magnet tooling, Prep magnet leads J18- Install Steppers/piezos, mag shields | J07-FSS | J03- WC's, Inst flanges J17- Inst flanges, 2 phase LC, close ins vac | C100R-06- fiducialize SF, prep VV
2019-06-29 | Sat
2019-06-30 | Sun
2019-07-01 | Mon | C75 windows; | BLA; | L2-BLA; L2-Bellows; L2-065 Degauss; |  |  | 5C75-RI-002; 5C75-RI-003; |  |  |  |  | L2-065; L2-bellows; L2 gaskets; |  | RDTTD-01 & RDTTD-02 setup; | HPR1: OOC HPR2: |  |  |  | 5C75-J-004 D3/4; DQW1 D5; |  |  |  |  | D1: TC pull; D2: D3: D4: D5: D6: D7: EIC1 hold; D8: HE-351 Hold; |  | J19- Prep magnet leads, Cav 1 tuner J18- mag shields, MLI | J07-FSS | J03- WC's, Inst flanges, LC 2 phase J17- Inst flanges, 2 phase LC, close ins vac | C100R-06- Install Cold Mass into VV, Assemble W2C BP's
2019-07-02 | Tue | C75 windows; | BLA; | C75 DL; L2-BLA; |  |  | 2.45GHz |  |  |  | 5C75-J-002 nitric soak flanges; | L2-068; 5C75-J-002; 5C75-RI-003; L2-BLA; |  | RDTTD-01 & RDTTD-02 20u; | HPR1: OOC HPR2: |  | cage L2-1, L2-2; |  | string prep; DQW1 D5; | 5C75-J-004 |  | L2-536; |  | D1: TC L/C1.5K/T; D2: D3: D4: D5: D6: D7: EIC1 hold; D8: HE-351 pull; L2-536 L |  | J19- Solder magnet leads, Cav 1 tuner, remove lollipops J18- mag shields, MLI, to WS4 | J07- FSS, move to N.4 Post | J03- WC's, Inst flanges, Close rect. port J17- Close ins vac, ready for CMTF | C100R-06- Install CM into VV, BL back on scope, Assemble W2C BP's
2019-07-03 | Wed | C75 DL; | BLA; | HPR fixture; |  |  | HE-353 FF; | 5C75-RI-003 450C/3h, 800C/3h; |  |  | Nb3Sn crucible & brackets & top plate 5u; | secondary heater (bake); L2-gaskets; BLA; |  | 5C75-RI-002 setup; | HPR1: OOC HPR2: |  | cage L2-3, L2-4; |  | string prep |  |  |  |  | D1: D2: D3: D4: D5: D6: D7: EIC1 hold; D8: L2-536 hold |  | J19- Solder magnet leads, LC 2 phase C100R-06- Install End Cans onto rails? | J18- mag shields, MLI,Instrumentation | J03- WC's, MC Line Inst flanges J17- ready for CMTF | C100R-06- Position VV, align crew J07- FSS
2019-07-04 | Thu | [6 empty] | 5C75-RI-003 | [6 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: EIC1 hold; D8: L2-536 hold
2019-07-05 | Fri | vac |  | L2-tuners; |  |  | 2.4GHz | 5C75-RI-003 pull; |  |  |  | string prep; |  | 5C75-RI-002 hold; | HPR1: OOC HPR2: RDTTD-01; |  |  |  | string prep | DQW1; | DQW1 120C/24h; |  |  | D1: D2: D3: D4: D5: D6: D7: EIC1 hold; D8: L2-536 hold |  | J19- Solder magnet leads, LC 2 phase C100R-06- Install End Cans onto rails | J18- mag shields, MLI, Instrumentation | J03- MC Line, Inst flanges J17- Ready for CMTF | C100R-06- Align Crew, VV Positioned, End Cans J07- FSS
2019-07-06 | Sat | [19 empty] | DQW1 120C/24h;
2019-07-07 | Sun | [13 empty] | HPR2: L2-1, L2-2 | [5 empty] | DQW1 120C/24h;
2019-07-08 | Mon | RDT 2; | L2-bellows | L2-Bellows; C75 DL; |  |  | 5C75-RI-003; |  |  |  |  | L2-BLA; 5C75-RI-002; |  | 5C75-RI-002 30u; EP Acid Change; | HPR1: OOC HPR2: L2-3; L2-4; |  | cage L2-5, L2-5; |  | L2-1, L2-2 on rail; RDTTD-01; | RDTTD-01; | DQW1 120C/24h; | 5C75-J-004; |  | D1: TC pull; D2: D3: 5C75-J-004 L/C4K; D4: D5: D6: RDT-6 Pull; D7: EIC1 SC4K/T/W; D8: L2-536 C2K/T/W; |  | J19-Add Cav 1 tuner, remove lollipops, solder magnet leads J18- Move to WS4, review assy | J07- Move to WS6N, FSS | J03- MC Line assy/LC, Inst flanges J17- Ready for CMTF | C100R-06- Align CM in VV NL07- Beam line work | Vac group waveguide welding
2019-07-09 | Tue | RDT 2; Beam focus test; | L2-bellows | RF Separator; L2 BLAs |  |  |  |  | 5C75-J-005; |  | TE01NS-01 20u & Nitric; | L2-BLA; 5C75-J-005; cart; |  | EP HF spike; 5C75-RI-005 setup; | HPR1: OOC HPR2: L2-5; L2-6; |  | cage L2-7, L2-8; |  | L2-3, L2-4 on rail; D5 to VAA; |  | DQW1 120C/24h; |  |  | D1: TC L/C/T/W; D2: D3: 5C75-J-004 C2K/T/W; D4: D5: D6: RDTTD-01 L/C/T/W; D7: EIC1 W/pull; 5C75-RI-NBSN1 L/SC4K/T; D8: L2-536 warm; |  | J19-, stop plates, GV bracket, solder magnet leads J18- Move to WS4, review assy |  | J03- MC Line assy/LC, Inst flanges J17- Ready for CMTF | C100R-06- Align CM in VV, End Cans onto rail NL07- Remove from test cave | J07- WS6N, FSS Vac group waveguide welding
2019-07-10 | Wed | Weld Test Maint | RFD Damper | RF Separator; L2 BLAs; |  |  | 5C75-RI-002 FF & Freq; |  |  |  | C75 eyelets & windows (x5); 2.45GHz; | BLA HW kits (x5); RDTTD-02 HW; |  | 5C75-RI-005 75u; | HPR1: OOC HPR2: L2-7; L2-8; |  |  | D5 test stand; | L2-5, L2-6 on rail; L2-342, L2-065, L2-068 D5; |  | DQW1 pull | DQW1; | D5 | D1: TC pull; D2: D3: 5C75-J-004 warm; D4: D5: D6: RDTTD-01 pull; D7: 5C75-RI-NBSN1 SC4K/T/W; D8: L2-536 pull; |  | J19- Remove lollipops, solder magnet leads | J18- review assy, RF cables, invar rods, instrumentation | J03- MC Line LC, RF waveguides/measurements J17- Ready for CMTF | C100R-06- Align CM in VV, End Cans onto rail NL07- Remove from test cave | J07- WS6N, FSS Vac group waveguide welding
2019-07-11 | Thu | Doglegs C100 Weld Test |  | L2 BLAs; |  |  | 5C75-RI-002 FF & Freq; 5C75-J-005; | 2.45GHz 900C/3h; |  |  | 5C75-RI-005; | 5C75-RI-005; |  | 5C75-RI-005 25u; | HPR1: OOC HPR2: RDTTD-02; TE01NS-01 |  |  | 5C75-J-004; | L2-7, L2-8 on rail; L2-342, L2-065, L2-068 D5; |  |  |  |  | D1: TC L/C/T/W; D2: D3: 5C75-J-004 pull; D4: D5: DQW-1 L; D6: D7: 5C75-RI-NBSN1 P/L/SC4K/T; D8: |  | J19- Remove lollipops, solder magnet leads, 2 phase LC | J18- RF cables, Heat stations, instrumentation | J03- LC Ins Vac J17- Into CMTF | C100R-06- End Cans onto rail/align, tophats,WT's NL07- Move in fromt of welding area for BL Reconfig | J07- Prep for BPM hardware replacement Vac group waveguide welding
2019-07-12 | Fri | Doglegs; C100 Weld Test | Cryo pump | HPR fixture; L2-BLA; |  |  | 5C75-RI-002 FF & Freq; 5C75-J-005; | 2.45GHz 900C/3h; | C75 windows (x2); blanks; 5C75-RI-002; |  |  | L2-BLA abs; |  | EP maint; 5C75-RI-003 setup; | HPR1: OOC HPR2: 5C75-RI-NBSN2; |  |  |  | J1.3-20 bag; L2-342, L2-065, L2-068 D5; RDTTD-02; | L2-342, L2-065, L2-068 D5; |  |  |  | D1: TC pull; D2: D3: D4: D5: DQW-1 C2K; D6: D7: 5C75-RI-NBSN1 C4K/T/W; D8: |  | J19- solder magnet leads, 2 phase LC | J18- RF cables, Heat stations, instrumentation | J03- LC Ins Vac J17- Reconfigure Test Cave | C100R-06- End Cans onto rail/align, tophats,WT's NL07- BL Reconfig | J07- Prep for BPM hardware replacement Vac group waveguide welding
2019-07-13 | Sat
2019-07-14 | Sun
2019-07-15 | Mon | Doglegs; C100 Weld Test | RFD Damper; | L2-279; RFD Damper; HPR fixture; |  |  | 5C75-J-005; 5C75-J-004 probe cal; |  | 3.9GHz CBP; |  |  | 5C75-RI-003; HE-354 bottom flange & HW; C100-RI-086 plasma; |  | 5C75-RI-003 30u; | HPR1: OOC HPR2: HE-354; |  | C75 cage; | HE-354 bottom flange; 5C75-J-004 | L2-BLA; 5C75-RI-NBSN2; |  |  | L2-342, L2-065, L2-068 D5; |  | D1: TC L/C/T/W; D2: D3: D4: D5: DQW-1 T/W; D6: RDTTD-02 L/C2K/T/W; D7: 5C75-RI-NBSN1 pull; D8: |  | J19- solder magnet leads, 2 phase LC, magnet intercepts | J18- RF cables, Heat stations, instrumentation | J03- LC Ins Vac J17- Reconfigure Test Cave | C100R-06- align End Cans, tophats,WT's NL07- BL Reconfig | J07- Prep for BPM hardware replacement Vac group waveguide welding
2019-07-16 | Tue | C100 Weld Test | RFD Damper; | L2-279; L2 BLA; |  |  | 5C75-RI-003 freq & FF, probes; |  | 5C75-RI-002; |  | RDT-6 HF rinse; Nb samples (x6); Nb beam tube & S/S flange; | L2 BLA (x2); 5C75-J-004 & HW; 5C75-RI-005; C75 cage parts; RGA; |  | HE-353 setup; | HPR1: OOC HPR2: 5C75-J-004; |  |  |  | HE-354; | J1.3-20; L2-BLA; 5C75-RI-NBSN2; |  |  |  | D1: TC pull; D2: D3: 5C75-RI-NBSN1 L/SC4K/T; D4: D5: DQW-1 warm; D6: D7: D8: 5C75-RI-NBSN2 L/C2K/T/W; |  | J19- 2 phase LC, magnet intercepts, heat stations | J18- RF cables, Heat station torquing, instrumentation | J03- LC Ins Vac J17- Reconfigure Test Cave | C100R-06- align End Cans, tophats,WT's NL07- BL Reconfig | J07- Bleed up for BPM hardware replacement Vac group waveguide welding
2019-07-17 | Wed | HW COAX2 FT; CERN weld test; | RFD Damper; | C75 WG; L2 BLA; |  |  |  | 5C75-RI-005 450C/3h, 800C/3h; | 5C75-RI-002; |  | RFD Damper; 5C75-RI-002; | 5C75-RI-002; |  | HE-353 35u; | HPR1: OOC HPR2: RDT-6; |  | 5C75-J-004; |  | RDT-6; | HE-354; |  |  |  | D1: D2: TC L/C/T/W; D3: 5C75-RI-NBSN1 pull; D4: 5C75-RI-NBSN1 L/SC4K/T; D5: DQW-1 pull, L2-342, L2-065, L2-068 L/precool/warm/C2K; D6: maint D7: D8: 5C75-RI-NBSN2 warm | J20- Receive CS | J19- 2 phase LC, magnet intercepts, heat stations | J18- RF cables, Heat station torquing, instrumentation | J03- LC Ins Vac, m-mounts J17- Reconfigure Test Cave, condition CM circuits | C100R-06- Prep for SEC beam pipe, WT's NL07- LC RF windows | J07- Bleed up for BPM hardware replacement Vac group waveguide welding
2019-07-18 | Thu | CERN weld test; | RFD Damper; | L2 bellows; L2 BLA; |  |  | 5C75-RI-005 freq & FF; Tune HOM's CM18 WS4 | 5C75-RI-005 450C/3h, 800C/3h; | 5C75-J-005; |  | HE-353 HW; 5C75-RI-002 HF inside; coating HW; FM beam tubes & flanges; | C100-RI-086 plasma; 5C75-J-005; 5C75-RI-002; HE-353 keep wet; HE-353 HW; L2 string & brakes; L2 HW; C100 BT parts; |  | HE-353 42u; | HPR1: OOC HPR2: 5C75-J-004; TE1NS-002; |  | pass out J1.3-20; J1.3-xx BPM; |  | L2-BLA; | HE-354; RDT-6; |  |  |  | CMTF u-tubes D1: SIC L/C/T; D2: TC pull; D3: D4: 5C75-RI-NBSN1 warm; D5: L2-342, L2-065, L2-068 test/warm; D6: maint D7: D8: 5C75-RI-NBSN2 pull/cable test/L/C4K; | J20- Receive CS, ~11am After u-tubes | J19- magnet heat station leads, CS alignment | J18- HOM tuning | J03- m-mounts, RF measurements J17- U-tubes 9am, cooldown | C100R-06- Prep for SEC beam pipe,WT's, Secondary WG Testing NL07- LC RF windows | J07- BPM hardware replacement, pump down/LC Vac group waveguide welding
2019-07-19 | Fri |  | L2 BLA; cleanup run; | L2 spools; C75 WG; |  |  | (1) J1.3-20 passbands; plasma system; |  | 5C75-J-005; |  |  | 5C75-RI-002 parts; |  | 5C75-RI-007 setup; | HPR1: OOC HPR2: HE-353; 5C75-RI-002; |  |  |  | 5C75-J-004; | L2-BLA; |  | HE-354 sensors and HOMs; |  | D1: SIC C/T/; D2: TC L/C/T/W; D3: D4: 5C75-RI-NBSN1 pull; D5: L2-342, L2-065, L2-068 warm; D6: RDT-6 L/C2K/T/W; D7: HE-354 L/C4K; D8: 5C75-RI-NBSN2 C2K/T/W; | J20- fit 2 phase piping | J19- CS alignment | J18- HOM tuning,lower shields | J03- m-mounts, RF measurements J17- cooldown | C100R-06- SEC beam pipe, Secondary WG Testing NL07- LC RF windows | J07-BL pump down/LC Vac group waveguide welding
2019-07-20 | Sat
2019-07-21 | Sun
2019-07-22 | Mon | OCD1 tubes and NbTi flanges; | Nb Sample w/Ti 1200C/4h; | L2-Bellows; |  |  | plasma system; J1.3-18 homs; BPM FT; | HE-353 w/samples 3N60; | C75 flange; 5C75-J-005; |  | Mo parts; RG beam tube and flange parts weld prep; | L2-115 bolt holes; RG BT, parts & HW; L2-115 HW; |  | 5C75-RI-007 65u; | HPR1: OOC HPR2: 5C75-RI-002; |  | cage L2-115; 5C75-RI-002; L2 gate valve LC; | 5C75-RI-NBSN2; TS34-001 unloaded; |  | 5C75-J-004 leaked; |  |  | L2-1; | D1: SIC C/T D2: D3: D4: D5: L2-342, L2-065, L2-068 hold; D6: D7: HE-354 C2K/T; D8: 5C75-RI-NBSN2 pull to VAA; | J20- fit 2 phase piping | J19- CS alignment | J18- HOM tuning,lower shields | J03- m-mounts, RF measurements J17- cooldown | C100R-06- SEC beam pipe, Secondary WG Testing NL07- LC RF windows | J07-BL pump down/LC Vac group waveguide welding
2019-07-23 | Tue | OCD1 tubes and NbTi flanges; | Nb Sample w/Ti 1200C/4h; | L2-bellows; |  |  | plasma system; | HE-353 w/samples 3N60; | 5C75-J-005; Doglegs; 5C75-RI-003; |  | 5C75-RI-NBSN2 nitric soak; C75 flange; | 5C75-RI-NBSN2; 5C75-RI-007; L2-1 string prep; L2-cages; BPM subassy; warm WG; shims; cavity parts x20; |  | 5C75-RI-007 35u; | HPR1: OOC HPR2: L2-115; |  |  |  | 5C75-RI-002; |  |  |  | L2-2; L2-115; | D1: SIC C/T D2: Magnet test Nb L/C4K/T D3: D4: 5C75-RI-NBSN1 L/SC4K/T D5: L2-342, L2-065, L2-068 pull; D6: 16-003 L/C1.5K/T/W; D7: HE-354 HOMs/W; D8: | J20- fit 2 phase piping, Alignment | J19- Prep tuners, heat stations | J18- 50K MLI, into VV | J03- Cav tune,RF measurements, shipping caps J17- Testing | C100R-06- Prep REC beam pipe, Secondary WG Testing, weld SEC process piping NL07- LC RF windows | J07-BL pump down, FSS Vac group waveguide welding
2019-07-24 | Wed | NbTi flanges; RG beam tube and flange parts; | WG blister test; | L2-bellows; HPR fixture; L2-BLA; |  |  | HE-349 bp; L2-133 bp; | HE-353 pull; H7, H8 2N0; | 5C75-RI-003; Doglegs; |  | Nb box & block (GC); Mo rings (GE); Cylindrical box & lid (RG); Transition ring (SW); Nb rings (AP); | L2-cages; L2-2 string prep; L2-279 (USC, DI); L2 ship manf; windows & HW; Nb box; |  | HE-353 setup; | HPR1: OOC HPR2: |  | cage L2-279; BPM Sub String prep; |  | L2-115; | 5C75-RI-002; |  | 5C75-RI-002; | L2-3; | D1: SIC C/T D2: D3: D4: 5C75-RI-NBSN1 SC4K/T; D5: D6: 16-003 warm/pull; 16-003 L/C4K/T; D7: HE-354 hold; D8: | J20- fit 2 phase piping, SPQA install/align | J19- Install tuners, heat stations | J18- Into VV, Alignment | J03- HOM's,prep for shipping J17- Testing | C100R-06-Install REC beam pipe, Secondary WG Install, weld SEC process piping NL07- LC RF windows | J07-BL pump down, FSS Vac group waveguide welding
2019-07-25 | Thu | RG beam tube and flange parts; |  | L2-spools; |  |  | 5C75-RI-005 freq & FF; plasma system; | H7, H8 pull; | 5C75-RI-003; |  | Mo HW; Port tube; Nb disks (x3); | HE-353 parts; HE-353; L2-279 HW; L2-3 string prep; BLA valves (x5); |  | HE-353 10u; | HPR1: OOC HPR2: L2-279; 5C75-RI-NBSN2; |  | carriages on the rail; cage L2-1; cage L2-2; |  | L2-115; | C75-RI-002; |  |  | L2-4; | D1: SIC C/T D2: Magnet test Nb L/C4K/T D3: D4: 5C75-RI-NBSN1 SC4K/T; D5: D6: 16-003 C1.5K/T/W D7: HE-354 pull; D8: | J20- fit 2 phase piping, SPQA install/align | J19- Install tuners, heat stations | J18- Alignment | J03- prep for shipping, onto truck J17- Testing | C100R-06-Install REC beam pipe, Secondary WG Install, weld SEC process piping NL07- LC Ins vac | J07-BL pump down, FSS Vac group waveguide welding
2019-07-26 | Fri | LSF9; |  | L2-BLA |  |  | plasma system; | Nb corners, Nb resonator 900C/3h; | 5C75-RI-003; Doglegs; | 5C75-RI-005; |  | HE-353 & cage; L2-4 string prep; BPM FT; 5C75-RI-005; L2 FPC HW; |  | setup 5C75-RI-005; | HPR1: OOC HPR2: HE-353; L2-279; |  | String prep; L2-279; C75-RI-002 prepare for HPR; L2 US valve sub; |  |  | L2-115; |  | L2-115; | L2-5; | D1: SIC C/T D2: Magnet test Nb pull; D3: D4: 5C75-RI-NBSN1 C2K/T/W; D5: D6: D7: D8: | J20- fit 2 phase piping, SPQA align | J19- Install tuners, heat stations |  | J18- prep for beam pipe and WC work J17- Testing | C100R-06- Secondary WG Install, weld process piping, LC He circuits NL07- Move to storage | J03- Off the dock 9am-ish J07-BL pump down, FSS, wait for WS4 Vac group waveguide welding
2019-07-27 | Sat
2019-07-28 | Sun | [15 empty] | HE-353;
2019-07-29 | Mon | LSF9; |  |  |  |  | 5C75-RI-007 freq & FF; | Nb corners, Nb resonator pull; | Doglegs; |  | C100 waveguide; Nb tube; Mo HW; 5C75-J-005; RF seperator; | 5C75-RI-003; 5C75-J-005; 5C75-RI-005; L2-5 string prep; L2 FPC HW; C100 WG; 5C75-RI-NBSN2; Mo HW; |  | 5C75-RI-005 30u; | HPR1: OOC HPR2: HE-353; C75-RI-002; |  | L2 US valve sub; BPM sub; |  | L2-279; |  |  |  | L2-6; | D1: SIC C/T; D2: Magnet test Ta L/C2K/T; D3: D4: 5C75-RI-NBSN1 C2k/T/W; D5: D6: D7: L2-115 L/C4K; D8: | J20- Weld 2 phase piping, instrumentation | J19- Install tuners, heat stations, instrumentation | J19-Set VV | J18- Install beam pipes, WC's, JT welding J17- Testing | C100R-06- Secondary WG Install, Set tuners, NL07- Move to storage? | J07-FSS, wait for WS4 Vac group waveguide welding
2019-07-30 | Tue | LSF9; | BCMs; |  |  |  | L2-133 BP; |  | Doglegs; |  | 5C75-RI-003; Nb resonator box; Nb samples; Nb sample chamber; BCMs; RF seperator; | L2-6 string prep; 5C75-RI-007; RDTTD-02 HW; RF sep; BCMs; MC lines; 5C75-RI-003; |  | maintenance & acid change | HPR1: OOC HPR2: RDTTD-02, 5C75-RI-NBSN2; |  | L2 US valve sub; Lollipops; 5C75-RI-NBSN2; |  | BPM sub; C75-RI-002; RDTTD-02; HE-353; | L2-279; 5C75-J-004; |  |  | L2-7; | CMTF Degauss, Fast C/D; D1: SIC warm; D2: Magnet test Ta warm; D3: D4: 5C75-RI-NBSN1 pull; maint D5: D6: D7: L2-115 C2K/T/W; D8: | J20- Weld 2 phase piping, instrumentation | J19- Install tuners, instrumentation J07-FSS, wait for WS4 |  | J18- Install beam pipes, WC's, JT welding J17- Testing | C100R-06- Secondary WG Install, LC He circuits NL07- Move to storage? | Vac group waveguide welding VV from Blue Crab
2019-07-31 | Wed | LSF9; | BCMs; |  |  |  | plasma system; | 5C75-RI-007 450C/3h, 800C/3h; | Doglegs; |  | doglegs (x6); Nb caps (x6); RF sep; | L2-364; L2-7 string prep; MC lines; |  | spike; L2-364 setup; | HPR1: OOC HPR2: 5C75-RI-NBSN2; |  | L2 Bellows; Lollipops; L2 US valve sub; |  | 5C75-RI-NBSN2; | HE-353; C75-RI-002; BPM LC; |  | HE-353; L2-279; C75-RI-002; | L2-8; | D1: SIC hold; D2: Magnet test Ta C2K/T; D3: D4: D5: D6: RDTTD-02 L/C/T/W; D7: L2-115 warm; D8: L2-279 L/C4K; | J20- Weld 2 phase piping, instrumentation | J19- Install tuners, instrumentation, to WS4 J07-FSS, wait for WS4 | J19- shield fit up | J18- Install beam pipes, WC's, JT welding, HPT J17- Testing | C100R-06- Secondary WG Install, LC He circuits NL07- Move to storage? | Vac group waveguide welding
2019-08-01 | Thu | LSF9; | RF Sep; | L2-BLA; L2 spools; |  |  | plasma system; | 5C75-RI-007 pull; GE Samples 800C/3h; | maint; |  | LSF; Mo rod; | L2-8 string prep; RDT6 HW; |  | L2-364 60u hot; set chiller 20F for Fri; | HPR1: OOC HPR2: RDT6; |  | mag field measurements; |  |  | 5C75-RI-NBSN2; |  | 5C75-RI-NBSN2; |  | D1: SIC pull/L/C/T; D2: D3: C75-RI-002 L/C4K D4: 5C75-RI-NBSN2 L/SC4K/T/W D5: D6: D7: L2-115 pull; HE-353 L/C4K D8: L2-279 C2K/T/W; | J20- Weld 2 phase piping-LC, Ti shields instrumentation | J07-FSS, wait for WS4 | J19- shield mods, mag shields, instrumentation | J18- Install beam pipes, WC's, JT welding | C100R-06- Secondary WG Install, Close bridging areas, weld | ***RT this Saturday for J1.3-18 @7A.M.*** Vac group waveguide welding UCM from Blue Crab
2019-08-02 | Fri | C100 flange; regen; |  | C75 Nb disks |  |  | C75-RI-007; | Mo bolts & cleanup 1000C/3h; | maint; |  |  | L2-364 |  | L2-364 20u cool; | HPR1: OOC HPR2: L2-364 |  | string prep; cage L2-3; cage L2-4; |  | RDT6; |  |  |  | L2-115; | Compressor 3 testing (am) D1: SIC hold; D2: D3: C75-RI-002 C2K/T/W (pm); D4: 5C75-RI-NBSN2 SC4K/fill; D5: D6: RDT-10 L; D7: HE-353 hold; D8: L2-279 warm; | J20- Weld 2 phase piping-LC instrumentation | J07-FSS, wait for WS4 | J19- RF cables, Inst check | J18- Install beam pipes, WC's, JT welding J17- Testing | C100R-06- Secondary WG Install, Weld bridging rings-tuner ports | Vac group waveguide welding
2019-08-03 | Sat | regen; | [5 empty] | pull Mo bolts | [15 empty] | D4: 5C75-RI-NBSN2 test/C2K/T/W D7: HE-353 C2K/T/W |  | J07- Move to WS3N |  |  |  | RT for J1.3-18 @7A.M.
2019-08-04 | Sun | [13 empty] | HPR2: L2-1; L2-2; |  | install caps on HE-364;
2019-08-05 | Mon | recovery; LSF9; | BCMs; | R&D feedthru; Nb discs; |  |  | C75-RI-007; | HE-364 w/samples 3N60; | C75 blanks; |  | GE Nb samples; Nb3Sn covers & HW; | L2 warm & cold FPC parts; L2 lollipop; HE-353 & parts; |  | 5C75-RI-007 setup; | HPR1: OOC HPR2: L2-3; L2-4; HE-353 overnight; |  |  |  | L2-1, L2-2 on rail; |  |  | L2-279 tune HOMs; |  | CMTF two-Kinney operation D1: SIC pull; D2: D3: D4: 5C75-RI-NBSN warm D5: D6: D7: HE-353 pull; D8: L2-279 pull; L2-279 hold | J20- Weld 2 phase piping-LC, Ti sheets instrumentation | J07-FSS, wait for WS4 | J19- RF cables, Inst check,FSS | J18- Install beam pipes, mc line, Bayonet box, Inst flanges | C100R-06- Prep for fiducialization, remove EC stands, align W2C beam pipies | Vac group waveguide welding
2019-08-06 | Tue | C75 DL windows; | BCMs; | R&D feedthru; L2-BLA; |  |  | J1.3-19 HOMs; | HE-364 pull; | 5C75-RI-003; C75 blanks; |  | 5C75-J-004 HF Qtip; C75 blanks; | 5C75-RI-007; |  | 5C75-RI-007 30u; | HPR1: OOC HPR2: L2-5; L2-6; |  | 5C75-RI-003 cage; |  | L2-3, L2-4 on rail; |  |  |  |  | CMTF two-Kinney operation D1: D2: Magnet test Nb L D3: C75-RI-002 pull; D4: 5C75-RI-NBSN pull D5: D6: RDT-10 pull; RDT6 L D7: D8: L2-279 C4K | J20- LC 2 phase piping, mli | J07-FSS, wait for WS4 | J19- Tune HOM's, Lower shields | J18- Install beam pipes, mc line , Bayonet box, Inst flanges | C100R-06- Fiducialize VV, Move to WS5 | Vac group waveguide welding
2019-08-07 | Wed | C75 DL windows; | BCMs; | L2-BLA; L2-Bellows; R&D Feedthrus; |  |  | J1.3-19 HOMs; L2-295 tuner install; |  | 5C75-J-004; RDTTD-01; |  | Cu strips; Plates & pin; 5C75-RI-003; | C75 blanks; 5C75-RI-003 & HW; TE01NS-001 & parts; tube fittings; S/S system parts; |  |  | HPR1: OOC HPR2: L2-7; L2-8; |  | L2-053 cage; | C75-RI-002; | L2-5, L2-6 on rail; | HE-353 |  | HE-353 |  | D1: D2: Magnet test Nb C4K/T/W15K/C2K/T/W; D3: D4: D5: D6: RDT6 C2K/T/W; D7: HE-353 L/C4K; D8: L2-279 C4K; | J20- LC 2 phase piping, mli, mag shields | J07-FSS, wait for WS4 | J19- Tune/Verify HOM's, Lower shields | J18- Install beam pipes, mc line LC, Inst flanges, 2K LC | C100R-06- Beam Pipe work, Secondary wg's, outbd tuners | Vac group waveguide welding
2019-08-08 | Thu | C75 DL | BCMs; | L2-spools; L2-bellows; |  |  | C75-RI-005; HE-364 BP 95% FF; |  | long spools; plate maint; |  | scrubber maint; RDTTD-01; | L2-053 HW; L2 beam pipe & HW; |  | scrubber maint; | HPR1: OOC HPR2: 5C75-RI-003; L2-053; RDTTD-01; |  |  |  | L2-7, L2-8 on rail; |  |  |  |  | D1: SIC L/C/T; D2: Magnet test pull; D3: D4: D5: D6: RDT6 warm; D7: HE-353 C2K/T/W; D8: L2-279 D8-->D7, warm; | J20-HV mli, mag shields | J07-FSS, wait for WS4 | J19- Weld shields, Into VV | J18- Inst flanges, RF waveguides | C100R-06-Beam Pipe work, LC ins vac,PT | Vac group waveguide welding J17- Warm up
2019-08-09 | Fri | C75 DL | BCMs; | L2-BLA; C75 WG; |  |  | HE-364 BP 95% FF; C75-RI-007; |  | long spools; plate maint; |  | Nb discs; HIPIMS parts; 5C75-J-004; | L2-bellows; 5C75-J-004; |  | HE-364 setup; | HPR1: OOC HPR2: scrubber maint; |  | L2-053; |  | RDTTD-01; |  |  |  |  | U-tubes CMTF am D1: SIC C/T; D2: RRR L/C/T/W; D3: D4: D5: D6: RDT-6 pull; D7: HE-353 warm; D8: L2-279 warm; | J20-HV mli, mag shields, move to WS3 | J07-FSS, wait for WS4 | J19- Prep for Alignment CM in VV | J18- Inst flanges, RF waveguides | C100R-06-Beam Pipe work, LC ins vac,PT | Vac group waveguide welding J17- Warm up/ Out of CMTF
2019-08-10 | Sat | [13 empty] | scrubber maint; | [13 empty] | C100R-06- Into CMTF?
2019-08-11 | Sun | [13 empty] | L2-053;
2019-08-12 | Mon | C75 DL; LSF9; | RFD; | L2-BLA; L2 bellows; |  |  | L2-295 tuner install; |  | RDTTD-02; |  | LSF9; HIPIMS parts; | HIPIMS parts; | BFPE | HE-364 10u (20F); | HPR1: OOC HPR2: TE01NS-001; 5C75-RI-003 pm; |  | cage L2-060; 5C75-RI-003; |  | L2-053; TE01NS-001 D6; | bag J1.3-21; BLA; |  |  |  | CTF Oil Migration issues, no Kinney Pump D1: SIC C4K; D2: RRR warm; D3: D4: D5: D6: RDTTD-01 L/C/T/W; D7: HE-353 pull; D8: L2-279 leak check top plate/FGM system tests; | J20-mag shields, move to WS3 | J20- Unite with UCM, Add bearing assys J07-Wait for WS4 | J19- Prep, Align CM in VV | J18- Inst flanges, 2 phase LC J17- Ins Vac LC, Prep for beamline work | C100R-06- In CMTF, Align module | Vac group waveguide welding
2019-08-13 | Tue | LSF9; | RFD; | L2-BLA |  |  | 5C75-RI-007; 5C75-RI-005; L2-295 tuner install; |  | 5C75-RI-007; RDTTD-02; |  | RDTTD-02; | L2-060 HW; RDF2 & HW; RDTTD-02 & HW; | BFPE | RDTTD-02, SC-04, RDTTD-01 setup; | HPR1: OOC HPR2: L2-060; HE-364; |  | cage HE-364; | HE-353; | 5C75-RI-003 D3/4; | BLA; J1.3-21; TE01NS-001; |  | TE01NS-001; |  | D1: SIC hold; D2: RRR pull, TC L/C/T/W; D3: D4: D5: D6: TE01NS-001 L/SC4K/T; D7: L2-279 Load/leaks; D8: FGM system tests; |  | J20- Unite with UCM, Add bearing assys J07-Wait for WS4 | J19- Align CM in VV | J18- Inst flanges, close Ins vac J17- Ins Vac LC, beamline work | C100R-06- Ins Vac LC, PT, LC U-tubes | Vac group waveguide welding
2019-08-14 | Wed | LSF9 | Nb stress relief; | L2-Bellows; L2-BLA; |  |  | 5C75-RI-005; HE-364 FF 95% |  | 5C75-RI-007; |  | Nb disk & sample; | RDTTD-02, SC-04, RDTTD-01; girder parts; | BFPE | RDTTD-02, SC-04, RDTTD-01 60u (20F); | HPR1: OOC HPR2: RFD2; L2-060; |  | L2-060; cage RFD2; | L2-103; |  | 5C75-RI-003; BLA; J1.3-21; |  |  |  | D1: SIC C2K; D2: TC C/T/W; D3: D4: D5: D6: TE01NS-001 C4K/T; D7: L2-279 pull; D8: FGM system tests; |  | J20- Unite with UCM, bearing assys,Install Cav 1 tuner/GV support, J07-Wait for WS4 | J19- Align CM in VV, Move to WS5 | J18- LC Ins vac J17- beamline work, shipping prep | C100R-06- Ins Vac LC, PT, LC U-tubes | Vac group waveguide welding
2019-08-15 | Thu | LSF9 |  | L2-BLA; C75 WG; |  | 0 | 5C75-RI-005; |  | 5C75-RI-007; |  | HIPIMS S/S flange, beam tubes x4; LSF9 end groups; plug; | L2-103 HW; girder parts; LSF9 end groups; | BFPE | HE-353 setup; | HPR1: OOC HPR2: L2-103 RDTTD-01; |  | cage L2-103; cage L2-286; | L2-286; | J1.3-21 FPC and HOM; L2-060 D5; RFD2 cart; | 5C75-RI-003; BLA; |  |  |  | D1: SIC C/T; D2: D3: D4: D5: D6: TE01NS-001 C2K/T/W; D7: D8: FGM system tests; |  | J20- Verify bearings, remove lollipops J07-Move to WS4 | J07- Verify FSS | J18- Ins Vac LC J17- beamline work, shipping prep J19- Prep for BL/WC work, Fit/Weld JT piping | C100R-06-Gas back, purge U-tubes | Vac group waveguide welding
2019-08-16 | Fri | LSF9 | cleaning run; | L2-BLA; ILC DB; |  |  | Tune HOM's CM07; L2-295 BP; |  | 5C75-RI-007; |  |  | HE-353 (DI overnight); HE-364 parts; L2-286 HW; | BFPE | HE-353 3u (20F); | HPR1: OOC HPR2: L2-286 L2-103; |  | RDTTD-01; L2-103; |  | J1.3-21; BLA; | 5C75-RI-003; BLA; RFD2; |  | 5C75-RI-003 OSTs; |  | CMTF Cooldown; D1: SIC C/T; D2: TC L/C/T/W; D3: D4: D5: D6: TE01NS-001 SC4K/T D7: L2-279 load/C4K; D8: FGM system tests; |  | J20- Fit/weld process piping, heat stations | J07- Tune HOM's | J18- Ins Vac LC, Replace leaky magnet flange J17- beamline work, shipping prep J19- Prep for BL/WC work, Weld JT piping | C100R-06- Vaporizer/U-tubes, Cooldown | Vac group waveguide welding
2019-08-17 | Sat
2019-08-18 | Sun
2019-08-19 | Mon |  | L2 Bellows; | L2 Bellows; |  |  |  |  | 5C75-RI-005; L2-spools; |  | 5C75-RI-007; LSF9-1 and parts; | 5C75-RI-007; LSF9-1; Girder HW; Coupler loop; |  |  | HPR1: OOC HPR2: HE-353; L2-286 |  | L2-286; |  | L2-343 D7/8; L2-060, L2-103 D5; C20 Girders; | J1.3-21; |  |  |  | D1: SIC C/T; D2: TC pull; D3: 5C75-RI-003 L/C4K D4: D5: D6: TE01NS-001 C2K/T/W; D7: L2-279 C2K/T/W D8: FGM System test; |  | J20- Fit/weld process piping, heat stations | J07- Tune HOM's | J18- Ins Vac LC, Replace leaky magnet flange J17- beamline work, shipping prep J19- Prep for BL/WC work, Weld JT piping | C100R-06- Vaporizer/U-tubes, Cooldown | Vac group waveguide welding
2019-08-20 | Tue | LSF9-1; |  | RFD samples; ILC DB x3; |  |  | J1.3-17 HOMs pre-ship; |  | 5C75-RI-005; |  |  | Girder HW; |  |  | HPR1: OOC HPR2: HE-364 |  | RDT-5 clamp test; |  | L2-286 D7/8; C20 Girders; | L2-053, L2-060, L2-103 D5; |  |  |  | D1: SIC C/T; D2: TC L/C/T/W; D3: 5C75-RI-003 C2K/T/W D4: D5: D6: RDTTD-01 L/C/T/W; D7: L2-279 warm; D8: FGM System test; |  | J20- Fit/weld process piping, heat stations, prep magnet leads | J07- Verify HOM's, weld lower shields, into VV | J18- Ins Vac LC J17- shipping prep, HOM's J19- Warm couplers, Beam line work, Weld JT piping, HPT | C100R-06- CMTF @2K, JT seat leak | Vac group waveguide welding LCLSII CM11 back from Blue Crab
2019-08-21 | Wed | LSF9-1; | Coupler loop; | L2 BLA; |  |  | J1.3-17 HOMs pre-ship |  | 5C75-RI-005; |  | LSF9 & stiffening rings; | VAT Valves; Girder HW; RGA; Girder carts; |  | HE-349 setup; | HPR1: OOC HPR2: HE-364 |  | HE-364; cage L2-536; | L2 String rollout!!! | C20 Girders; | BLA; L2-286 D7/8; L2-343 D7/8; |  | L2-343 D7/8; |  | D1: SIC C/T; D2: TC W/P; D3: 5C75-RI-003 warm; D4: D5: D6: RDTTD-01; D7: L2-279 pull; D8: | J21- Deliver string | J20- Fit/weld process piping, heat stations | J07- MLI, into VV, prep for alignment | J18- Ins Vac LC J17- shipping prep, HOM's J19- Warm couplers, Beam line work, Weld JT piping | C100R-06- Warming up | Vac group waveguide welding LCLSII Shipping Trailer into Test Lab
2019-08-22 | Thu | LSF9-1; |  | L2 BLA; |  |  | J1.3-17 HOMs pre-ship |  | 5C75-RI-005; |  | RFD samples; WG flanges; | MC lines & HW; BLA body & absorber; L2-536 HW; L2-279 bolt holes; LSF9 8xHC; RDL-02 HW; KM WG; 5C75-RI-005; |  | HE-349 60u; | HPR1: OOC HPR2: RDL-02 |  |  | L2-279 bottom flange; | C20 Girders; |  |  | L2-286 D7/8; |  | D1: SIC C/T; D2: TC L/C/T/W D3: 5C75-RI-003 pull/load; D4: D5: D6: RDTTD-01 pull; D7: L2-286 L C/4K; D8: L2-343 L/C4K; | J21- RF measurements, Berry bolts, fit 2 phase piping, align magnet spool | J20- Weld process piping/LC, waiting for magnet intercepts | J07- Align CM in VV | J18- Ins Vac LC J17- shipping prep, HOM's, Inserts/caps J19- Warm couplers, Beam line work | C100R-06- Warming up/seat replacement | Vac group waveguide welding J17- Into Shipping Trailer?
2019-08-23 | Fri | LSF9-1; | BLA absorbers; | L2 Bellows; L2 BLA | [6 empty] | AMV Cu SC x2; LSF9 8xHC; 5C75-RI-005; | 5C75-RI-005; LSF9 8xHC; HE-349 (x2); L2-279 HW; |  | HE-349 20u; | HPR1: OOC HPR2: L2-279; L2-536; |  |  |  | RDL-02; C20 Girders; BLA; VAT 28, VAT 48; HE-364 D7/8; |  |  |  |  | D1: SIC C/T; D2: TC pull; D3: 5C75-RI-003 C4K; D4: D5: D6: D7: L2-286 C2K (2); D8: L2-343 C2K/T/W (1); | J21- Berry bolts(hardware out of stock), fit/ weld 2 phase, install magnet | J20- Weld process piping/LC, waiting for magnet intercepts | J07- Align CM in VV | J18- Ins Vac LC J19- Warm couplers, Beam line work | C100R-06- Seat rplacement | Vac group waveguide welding J17- Into Shipping Trailer RT for CM19 5PM-7PM
2019-08-24 | Sat | [17 empty] | L2-053, L2-060, L2-279; |  |  |  |  | D7: L2-286 T/W; | [5 empty] | J17- Leave 4 SLAC
2019-08-25 | Sun
2019-08-26 | Mon | LSF9-1; | FeedThroughs | 2.45 GHz; C75 DL; | [7 empty] | L2 string BPM parts; L2 bellows; C100 girder parts; BLA absorbers x4; |  | HE-349 15u; | HPR1: OOC HPR2: L2-536; |  | L2-536; | L2-Lollipop | BLA; | HE-364; L2-053, L2-060, L2-279 D5; L2-Gate vlvs; |  | L2-286 cable check; | L26R cav x bleedup; | CMTF cooldown? D1: SIC topoff/T D2: Magnet test Nb L/H; D3: 5C75-RI-003 C2K/T/W; D4: D5: D6:RDL-02 L/C2K/T/W D7: L2-286 pull; L2-286 L/C4K D8: L2-343 pull; EIC-1 L/P/ChkSensors/L/ | J21- fit/weld 2 phase, install magnet, Alignment | J20- LC process piping Heat staions | J07- Move to WS5 J11- Move to WS4 | J18- Move to WS6 J19- Warm couplers, Beam line work | C100R-06- Cooldown | Vac group waveguide welding
2019-08-27 | Tue | LSF9-1; |  | 2.45 GHz; ILC dumbbells; |  |  | C75-J-004 Coupling Re-Check; |  |  |  | C75 Nb Blanks x4 10u; LSF9 stiff rings; | L2 bellows; L2 string hardware; C100 girder parts; C75 HPR blanks; FPC HW (x8); |  | HE-351 setup; arduino & maint; | HPR1: OOC HPR2: HE-349; |  | L2 6R mag meas.; | DQW off TS34003; | RFD2 D5; L2-536 D7/8 | BLA; RFD2; C20 girder BT; | RFD2 wrap for bake 120C 6hrs; | RFD2; HE-364; L2-053, L2-060, L2-279; D5; | L26R cav x bleedup; | CMTF pumpdown? D1: SIC D2: Magnet test Nb hold; D3: 5C75-RI-003 wdlc/pull; D4: D5: L2-053, L2-060, L2-279 L/C4K; D6: RDL-02 L D7: L2-286 C2K/T/W; D8: EIC-1 SC4K | J21- Berry bolts, fit/ weld 2 phase, install magnet, Alignment | J20- LC process piping Prep for alignment | J11- Remove from VV, drop shields | J07- Prep for WC's, Instrumentation flanges J19- Warm couplers, MC line, Beam line work, instrumentation |  | Vac group waveguide welding J18- WS6, Idle
2019-08-28 | Wed | LSF9-1; | JLEIC HOM load samples; | L2 Bellows; |  |  |  | HE-349 & sample 3N60; |  |  | LSF9 DBs x4 & EGs x2; | L2 cages; 5C75-J-004; C100 girder parts; HE-351; L2-lollipop parts; L2-bolt holes; |  | HE-351 teardown; EP acid change; | HPR1: OOC HPR2: |  | HE-349 cap install; L2 6R mag meas.; |  | BPM subassy; | L2-536 C20 girder BT; C75-RI-003; | RFD-2 bake 120C-6hrs; |  | L26R cav x bleedup; | D1: SIC D2: Magnet test C/T/W D3: 5C75-RI-003 pull; D4: D5: L2-053, L2-060, L2-279 C2K; D6: RDL-02 T/W D7: L2-286 T/W/C2K; D8: EIC-1 T/W; | J21- Berry bolts, fit/ weld 2 phase, Instrumentation | J20- CS to UCM alignment, prep tuners | J11- Move to WS3N | J07- Install warm couplers,instrumentation flanges J19- Beam line work, Inst flanges, Bayonet box |  | Vac group waveguide welding
2019-08-29 | Thu | LSF9-1; | RFD Damper; | L2-BLA; |  |  |  | HE-349 3N60; |  |  | LSF9 1/2 cavs; | PJ1-1 & parts; C20 girder parts; LSF9; L2 cages; L2-bolt holes; |  | HF spike; | HPR1: OOC HPR2: 5C75-J-004; PJ1-1; |  | String 6R bellows; |  |  | pump maint; | RFD-2 unwrap; |  | L26R cav x bleedup; | D1: SIC D2: D3: D4: D5: L2-053, L2-060, L2-279 C2K/T; D6: RDL-02 warm; D7: L2-286 C/T/W; D8: EIC-1 warm; | J21- Berry bolts,weld 2 phase, Instrumentation | J20- CS to UCM alignment, prep tuners J11- Idle |  | J07- Install warm couplers,instrumentation flanges J19- Beam line work, Inst flanges, Bayonet box, evacuate 2 phase |  | Vac group waveguide welding
2019-08-30 | Fri | LSF9-1; | HZB-Samples | L2-BLA |  |  | HE-349 |  |  |  |  | L2 cages; L2 bolt holes; L2-string prep; L2-lollipop parts; |  | HE-349 setup; | HPR1: OOC HPR2: |  | 5C75-J-004; | DQW2 uncage; | C100 Girder BT; | BPM subassy; |  | L2-536; | BPM; | D1: SIC D2: Mag pull; TC L/C/T D3: D4: D5: L2-053, L2-060, L2-279 T/W; D6: D7: L2-286 warm; D8: EIC-1 pull; L2-536 L/C4K; | J21- Weld 2 phase/LC, Instrumentation | J20- CS to UCM alignment, Install tuners J11- Idle |  | J07- Install warm couplers,instrumentation flanges J19- Beam line work, Inst flanges, Bayonet box, evacuate 2 phase |  | Vac group waveguide welding
2019-08-31 | Sat
2019-09-01 | Sun
2019-09-02 | Mon | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2019-09-03 | Tue | maint; |  | L2-Tuner |  |  |  |  | 3.9GHz CBP; |  |  | L2 bolt holes; C75 blanks; HE-349; |  | HE-349 10u (20C); | HPR1: OOC HPR2: 5C75-J-004; |  | L2 bellows conditioning; Lollipops; BPM | BPM |  | PJ1-1; |  |  | L2; L2; | D1: SIC warm; D2: TC pull; D3: D4: D5: L2-053, L2-060, L2-279 warm; D6: RDL-02 pull; D7: L2-286 pull; HE-364 L/C4K D8: L2-536 C2K | J21- Weld 2 phase/LC, Instrumentation | J20- Waiting on magnet parts, Install tuners, Mu shields |  | J07- Install warm couplers,instrumentation flanges J19- Beam line work, Inst flanges, Bayonet box, LPT |  | Vac group waveguide welding J11- Idle C100-06R- Remove U-tubes, out of CMTF Clear UITF roof
2019-09-04 | Wed | maint; |  | C75 DL; L2 bellows; |  |  |  |  | L2 Bellows; 3.9GHz CBP; |  | RDL-02 BCP flanges; Nb foils; | L2 bolt holes; RDL-02; |  | RDT-06, TD-5 setup; | HPR1: OOC HPR2: HE-349; |  | Lollipops; L2 US Gate valve; |  | 5C75-J-004; | BPM |  |  | L2-279; L2-053; | D1: SIC pull; RRR L/C/T D2: TC L/C/T/W; D3: D4: D5: L2-053, L2-060, L2-279 pull; MagField; RFD-2 L/C4K; D6: D7: HE-364 C2K (D8 --> D7); D8: L2-536 /T/W; | J21- Weld 2 phase/LC, Instrumentation | J20- Solder magnet leads, verify alignment Install tuners |  | J07- Install warm couplers,instrumentation flanges, weld JT's J19- Beam line work, Inst flanges, Bayonet box, LPT |  | Vac group waveguide welding J11- Idle CM18- Into CMTF PCM- Move to WS5N
2019-09-05 | Thu | maint; |  | L2-BLA |  |  |  |  | 3.9GHz CBP; |  |  | L2 bolt holes; RDT-06, TD-5; |  | RDT-06, TD-5 20u; | HPR1: OOC HPR2: RDL-02; |  | cage L2-1, L2-2; cage L2-3, L2-4; |  | mag field measurements/degausing; | 5C75-J-004; |  |  |  | D1: RRR T/W; D2: TC T/W; D3: PJ1-1 L; D4: D5: RFD-2 T; D6: D7: HE-364 W; D8: L2-536 C2K; | J21- Weld 2 phase/LC, Instrumentation | J20- Solder magnet leads, verify alignment, prep tuners |  | J07- Install warm couplers,instrumentation flanges, weld JT's J19- Beam line work, Inst flanges, Bayonet box |  | Vac group waveguide welding J11- Remove magnet heat stations CM18- clean circuits, prep u-tubes PCM- Move to WS5N, N-Mount installation
2019-09-06 | Fri | maint; |  | Top plate; 2.45 GHz; L2 Main lever |  |  |  | RDL-02 & Samples 800/3h, 120/48h; | 3.9GHz CBP; |  |  | L2 bolt holes; |  | HE-351 setup; | HPR1: OOC HPR2: RDT-6; |  |  |  | RDT-6; | C20 beam tube; |  | 5C75-J-004; |  | CMTF cooldown D1: RRR W/; D2: TC pull/L/C/T; D3: PJ1-1 C4K/T/W; D4: 5C75-J-004 L; D5: RFD-2 C4K; D6: D7: HE-364 pull/load C4K; D8: L2-536 T/W; | J21- Weld 2 phase/LC, Instrumentation | J20- Solder magnet leads, verify alignment, prep tuners |  | J07- Install warm couplers,instrumentation flanges, weld JT's J19- Beam line work, Inst flanges, Bayonet box |  | Vac group waveguide welding J11- Remove magnet heat stations CM18- clean circuits, prep u-tubes PCM- N-Mount installation
2019-09-07 | Sat | [6 empty] | RDL-02 & Samples 800/3h, 120/48h; | [15 empty] | D5: RFD-2 T;
2019-09-08 | Sun | [6 empty] | RDL-02 & Samples 800/3h, 120/48h; | [6 empty] | HPR2: L2-1; L2-2;
2019-09-09 | Mon |  | injector degas; | 2.45 GHz |  |  | string 9 cavities; 5C75-RI-003; | RDL-02 & Samples pull; | 3.9GHz CBP; |  |  | SC-09, SC-11, SC-12, SC-14, SC-16; |  | HE-351 60u; | HPR1: OOC HPR2: L2-3; L2-4; |  | cage L2-5, L2-6; |  | L2-1, L2-2 to rail; |  |  |  | L2-286; | CMTF pumpdown; D1: RRR W/P D2: Magnet Test L; D3: PJ1-1 C/T/W; D4: 5C75-J-004 C4K; D5: RFD warm; D6: RDT-6 L/C2K/T; D7: HE-364 C4K; D8: L2-536 pull; | J21- Weld 2 phase/LC, Ti sheets, Instrumentation | J20- Solder magnet leads, prep tuners |  | J07- Install warm couplers,instrumentation flanges, HPT J19- Beam line work, Inst flanges, Bayonet box |  | Vac group waveguide welding J11- Remove magnet heat stations PCM- N-Mount installation
2019-09-10 | Tue |  | feedthrough; | 2.45; |  |  | 5C75-RI-003; | 5 single cells Ari 900C/3h; | 3.9GHz CBP; |  | Nb sample; Nb furnace caps; | HE-351; L2-286 btm flng, ext clean, bolt holes; |  | maint; HE-351 7u; | HPR1: OOC HPR2: L2-5; L2-6; |  | cage L2-7, L2-8; |  | L2-3, L2-4 to rail; |  |  |  | BPM; | D1: Fix heater; D2: Magnet Test C/T/W; D3: PJ1-1 C/T; D4: 5C75-J-004 C4K; D5: RFD hold; D6: RDT-6 warm; D7: HE-364 C2K/T/W; D8: | J21- Weld 2 phase/LC, Ti sheets, Instrumentation | J20- heat station magnet leads |  | J07- Install warm couplers,instrumentation flanges, Weld x-ray joint J19- Beam line work, Inst flanges, LC Bayonet box |  | Vac group waveguide welding J11- Edit Disassembly Procedure PCM- N-Mount installation
2019-09-11 | Wed | maint; |  | LSF9-1; |  |  | 2.45 GHz BP? |  | 3.9GHz CBP; |  | R&D beamtubes (x4); | HE-351; |  | HE-351 13u; | HPR1: OOC HPR2: L2-7; L2-8; |  |  |  | L2-5, L2-6 to rail; |  |  |  |  | D1: TC L/C/T; D2: Magnet Test C2K/T; D3: PJ1-1 C/T/W; D4: 5C75-J-004 C2K/T (29 torr); D5: RFD hold; D6: RDT-6 warm; D7: HE-364 warm; D8: | J21- Ti sheets, Instrumentation | J20- Heat station magnet leads |  | J07- Install warm couplers,instrumentation flanges, J19- Beam line work, Inst flanges, LC Bayonet box |  | Vac group waveguide welding J11- Edit Disassembly Procedure PCM- N-Mount installation
2019-09-12 | Thu | Nb Beam Tubes x4 |  | LSF9-1; |  |  | J1.3-01 HOMs; | EZ-SSC-03 975C/3h; | 3.9GHz CBP; |  | Mo HW; | EZ-SSC-03; HE-351; |  | SC-09, SC-11, SC-12 setup (20F); | HPR1: OOC HPR2: RDL-2; HE-351; |  | L2-286 drop bottom flange and cage; |  | L2-7, L2-8 to rail; |  |  |  | L2-536; | D1: TC T/W; D2: Magnet Test; D3: PJ1-1 C/T/W; D4: 5C75-J-004 C2K/T/W; D5: RFD pull; D6: RDT-6 pull; D7: HE-364 pull; D8: | J21- 2 Phase LC, Instrumentation, MLI | J20- Heat station magnet leads, Tuners | J20- Prep VV | J07- Install MC line, instrumentation flanges J19- Inst flanges, close Ins Vac |  | Vac group waveguide welding J11- Edit Disassembly Procedure PCM- HOM's
2019-09-13 | Fri | Nb Beam Tubes x4 | 1200 Cleanup; | LSF9-1; L2 BLA; C75 DL; |  |  | J1.3-01 HOMs; | HE-351; | 3.9GHz CBP; |  | Nb samples 100u; | SC-09, SC-11, SC-12; HE-351 bag for furnace; L2-286 parts; |  | SC-09, SC-11, SC-12 Ari 20u (20F); | HPR1: OOC HPR2: L2-286 HE-349 |  | L2-536 drop bottom flange and cage; HE-351 furnace caps; |  | RDL-2; |  |  |  |  | D1: TC pull; D2: D3: PJ1-1 C/T/W; D4: 5C75-J-004 warm; D5: D6: D7: D8: | J21- MLI, HV Mag shields | J20- verify alignment,Tuners, Move to WS3E |  | J07- Install MC line, instrumentation flanges J19- Inst flanges, LC Ins Vac |  | J11- Edit Disassembly Procedure PCM- HOM's
2019-09-14 | Sat | [26 empty] | RT Scheduled for 7am
2019-09-15 | Sun
2019-09-16 | Mon | Nb Beam Tubes x4 | L2 Spools WG? | LSF9-1; L2-BLA |  |  | L2-118 BP; |  | 3.9GHz CBP; |  | No acid work 1-2PM | C100 Girder; L2 cold coupler HW; L2-060 ext rinse & bolt holes; |  | EZ-SSC-03, SC-14, SC-16 setup (20F); | HPR1: OOC HPR2: L2-536; HE-349; |  | HE-349, blanks on HOMs; |  | L2-286 D5; | Bag String; |  |  |  | D1: SIC L; D2: D3: PJ1-1 C2K/T/W D4: 5C75-J-004 hold; D5: D6: RDL-2 L/C/T; D7: D8: | J21- MLI, HV Mag shields | J20- Tuners, Move to WS3E |  | J07- 2 phase LC, Install MC line, instrumentation flanges J19- Inst flanges, LC Ins Vac |  | J11- Begin disassembly PCM- HOM's CM21- UCM from BC
2019-09-17 | Tue | HW-Coax 2 pick-up coupler; | L2 Spools | LSF9-1; C75 DL |  |  | LSF9-1 BP; |  | 3.9GHz CBP; |  | 2" cube BCP 20u; RDT-6 Flange and ext BCP; | EZ-SSC-03, SC-14, SC-16; N2 flex lines & HW; L2-543 USC 2x; C100 girder parts; L2-060 HW; |  | EZ-SSC-03, SC-14, SC-16 20u (20F); | HPR1: OOC HPR2: L2-060; RDT-6; |  | L2-268 drop bottom flange and cage; cage (Ti) L2-543; L2-060 drop bottom flange & cage; cage L2-103; | HE-364 | L2-286, L2-536 D5; HE-349 D7/8; | J1.3-06R; |  |  |  | D1: SIC C2K/T; D2: RRR L/C4K D3: PJ1-1 warm; D4: 5C75-J-004 pull; D5: D6: RDL-2 T/W; D7: D8: | J21- MLI, HV Mag shields | J20- Tuners, Instrumentation, RF Cables J21- Insp UCM 35 |  | J07- LC MC line, instrumentation flanges, Close side port J19- LC Ins Vac |  | J11- Disassembly PCM- HOM's
2019-09-18 | Wed | HW-Coax 2 pick-up coupler; | WG blister test; | L2-BLA; LSF9-1; |  |  | J1.3-1 HOMs; L2-125 tuner and BP; HE-351; | 2" cube 800C/3h; | 3.9GHz CBP; |  |  | L2-103 HW; L2-268 HW; TD-5 & HW; L2-543 HW; HE-351 HW; C100 girder valve; |  |  | HPR1: OOC HPR2: L2-268; L2-543; |  |  | HE-364 | L2-286, L2-536, L2-060 D5; | HE-349 D7/8; |  | HE-349 D7/8; |  | D1: SIC D2: RRR T/W; D3: PJ1-1 C2K/T/W D4: D5: D6: RDL-2 warm; D7: D8: | J21- Idle | J20- Tuners, Instrumentation, RF Cables J21- Insp/FSS UCM 35 |  | J07- LC MC line, instrumentation flanges, close VV side port J19- LC Ins Vac |  | J11- Disassembly PCM- HOM's CEBAF- CM Shuffle
2019-09-19 | Thu |  | Stress Relief HW Tube | L2-BLA |  |  | HE-351; | RDT-6 | 3.9GHz CBP; |  |  | Cleaning; |  | HE-351 setup (20F); | HPR1: OOC HPR2: L2-103; TD-5; L2-543; |  | L2-543; L2-295 Ti cage; |  | L2-268 D7/8; | L2-060, L2-286, L2 536 D5; |  |  |  | D1: SIC C2K/T; D2: RRR pull; Magnet test L; D3: PJ1-1 SC4K/T; D4: D5: D6: RDL-2 pull; D7: HE-349 L; D8: | J21- Move to WS3W | J20- Tuners, Instrumentation, RF Cables J21- Unite CS to UCM |  | J07- instrumentation flanges J19- LC Ins Vac |  | J11- Disassembly PCM- Move to WS6, Shipping Alignment CEBAF- CM Shuffle LERF- Remove WG and Cabling
2019-09-20 | Fri |  | WG blister test; | C75 DL |  |  |  |  | 3.9GHz CBP; |  | Nb samples for film crew ~9am | HE-351 2x; L2-295 USC 2x; |  | HE-351 10u (20F); | HPR1: OOC HPR2: L2-103; HE-351 (overnight); |  | L2-103; |  | L2-543 D7/8; | L2-268 D7/8; |  | L2-060, L2-286, L2 536; |  | D1: SIC D2: Magnet test C2K/T/W D3: PJ1-1 C2K/T/W D4: D5: L2-060, L2-286, L2 536 L/precool D6: D7: HE-349 C2K/T/W; D8: | J06R- Receive string | J20- Tuners, Instrumentation, RF Cables, Move to WS4 J21- Unite CS to UCM, install Cav1 tuner |  | J07- instrumentation flanges J19- LC Ins Vac |  | J11- Disassembly PCM- HOM's CEBAF- CM Shuffle LERF- Remove WG and Cabling, Slide bellows
2019-09-21 | Sat | [13 empty] | HPR2: HE-351 (overnight); |  | HE-351; | [6 empty] | D7: HE-349 C2K/T/W; D5: L2-060, L2-286, L2 536 C4K
2019-09-22 | Sun | [22 empty] | D5: L2-060, L2-286, L2 536 C2K
2019-09-23 | Mon | FRIB Samples |  | LSF9-1; |  |  | HE-349 BP; |  |  |  | 5C75-RI-003 (nitric & BCP); | L2-295 HW; L2-346, 5C75-RI-003 & parts; 3HZLG1 9-cell; BLA manifold parts & cart; ceramics; Getter pumps; CW flanges & HW; |  | 3HZLG1 9-cell setup | HPR1: OOC HPR2: L2-295; C75-RI-003; |  | L2-346 Ti cage; C75-RI-003 cage; |  | L2-103 D5; HE-351; | L2-543 D7/8; |  | L2-268; |  | Recover CM; D1: SIC C4K; D2: Mag C4K/T; D3: PJ1-1 W/SC4K; D4: C75-J-004 L; D5: L2-060, L2-286, L2 536 T/W; D6: TD-5 L; D7: D8: L2-268 L/C4K; | J06R- Receive string | J20- Tuners, Instrumentation, RF Cables J21- Align UCM |  | J07- instrumentation flanges J19- Remove Bbox Cart |  | J11- Disassembly PCM- HOM's LERF- Remove shields and Cryo lines
2019-09-24 | Tue | Cryo Pump Regen | Ceramic WT | L2 spools LSF9-1; |  |  | HE-349 tune & FF; J1.3-6R passbands; |  | 5C75-RI-003 blanks; |  | RDT-6 covers; 5C75-RI-003 blanks; | 3HZLG1 9-cell; CW flanges & HW; L2-346 USC DI; L2-346 HW; RDT-6 HW |  | 3HZLG1 9cell 40u; | HPR1: OOC HPR2: L2-295; |  | L2-295; | DQW-1 (blanks); |  | HE-351; L2-103; |  | L2-543 D7/8; |  | Ran out of LHe D1: SIC hold; D2: Mag C2K/T; D3: PJ1-1 C4K; D4: C75-J-004 hold; D5: L2-060, L2-286, L2 536 warm; D6: TD-5 hold; D7: D8: L2-268 C4K; | J06R- RF Measurements, Fit 2 phase piping | J20- Tuners, Instrumentation, RF Cables J21- Align UCM, unite UCM to CS |  | J07- instrumentation flanges, RF Waveguides J19- |  | J11- Disassembly PCM- Ship Trav CEBAF- CM Shuffle LERF- Remove shields and Cryo lines
2019-09-25 | Wed | Cryo Pump Regen RFD EBW qual parts | 1200C Clean | C75 WG L2 spools |  |  |  | 3.9 GHz 800C - 3hrs; | CBP-Install new buckets |  | EBW qual parts 15u; | DQW-2 & HW; |  | HE-349 setup; | HPR1: OOC HPR2: L2-346; RDT-6; C75-RI-003; HE-351 (overnight) |  | L2-281 cage (Ti); C75-RI-003; | DQW-2; | L2-295 D5; L2-103 replace FP; C100 girder BT; HE-351; |  |  |  |  | D1: SIC hold; D2: D3: PJ1-1 hold; D4: C75-J-004 C4K; D5: L2-060, L2-286, L2 536 pull; D6: TD-5 C/T/W; D7: D8: L2-268 C4K (pm); | J06R- Fit 2 phase piping, berry bolts | J20- Instrumentation, to WS4 J21- Unite UCM to CS |  | J07- Instrumentation flanges, RF Waveguides J19- Ready for CMTF |  | J11- Disassembly PCM- Ship Trav LERF- Remove shields and Cryo lines, prep for Beamline work
2019-09-26 | Thu | RFD EBW qual parts | 1200C Clean | EBW qual parts 15u; L2-BLA |  |  | EIC-1; | 3.9 GHz 800C - 3hrs; Samples; |  |  |  | HE-349 USC 2x; DQW-2 & parts; elbows; |  | HE-349 3u; | HPR1: OOC HPR2: DQW-2; |  | L2-346; |  | C75-RI-003; C100 girder BT; RDT-6; HE-351 | C100 girder BT; |  |  |  | Ran out of LHe D1: SIC C4K; D2: D3: PJ1-1 C2K/T; D4: C75-J-004 C4K; D5: D6: D7: D8: L2-268 C2K/T; | J06R- Fit 2 phase piping, berry bolts | J21- Unite UCM to CS, Install Cav1 tuner | J20- Instrumentation, RF Cables | J07- Instrumentation flanges J19- Ready for CMTF |  | J11- Disassembly PCM- Ship Trav LERF- Remove shields and Cryo lines, prep for Beamline work
2019-09-27 | Fri | HOM; C100 WG; C75 DL; | Inj Degas | L2-BLA; EBW Weld Sample |  |  |  | Samples part 2; | BLA BL flange x2; |  |  | L2-281 USC 2x; L2-281 parts; BLA x2; |  | 3.9 GHz 3HZLG1 setup; | HPR1: OOC HPR2: L2-346; HE-349 1 pass; 5C75-RI-003; |  | L2-281 Ti cage; | 5C75-RI-003 bottom flange; |  | C100 girder BT; RDT-6; |  |  |  | D1: SIC C4K; D2: D3: PJ1-1 W/C4K; D4: C75-J-004 C/1.8K/T/W; D5: RFD-2 L/C; D6: RDT-6 L/C/T D7: HE 351 L/C4K D8: L2-268 warm; | J06R- Fit 2 phase piping, berry bolts | J21- Unite UCM to CS, Install Cav1 tuner | J20- Instrumentation, RF Cables | J07- Instrumentation flanges J19- Ready for CMTF |  | J11- Disassembly PCM- Ship Trav LERF- Remove shields and Cryo lines, prep for Beamline work
2019-09-28 | Sat | [22 empty] | D5: RFD-2 C4K/T; D7: HE 351 C/2K/T/W
2019-09-29 | Sun | [22 empty] | D5:RFD-2 warm;
2019-09-30 | Mon | HOM; C100 WG; C75 DL; |  | C75/Cebaf Cavities; |  |  | C75/Cebaf Cavities; |  |  |  |  | 3HZLG1 3.9 GHz; Girder beam line; |  | 3HZLG1 3.9 GHz 25u; | HPR1: OOC HPR2: |  | Radcon briefing; | C100 Girder(rad); | 5C75-RI-003 L2-346 D5; |  |  |  |  | Pull U-Tube 9am; D1: SIC C2K/T; D2: RRR L/C/T/W; D3: PJ1-1 C2K/T/W; D4: C75-J-004 pull; D5: RFD-2 warm D6: D7: HE-351 warm; D8: L2-268 pull; L2-543 L/C4K; | J06R- Fit 2 phase piping, berry bolts | J21- Unite UCM to CS, Install Cav1 tuner | J20- Instrumentation, | J07- Instrumentation flanges J19- Ready for CMTF |  | J11- Disassembly PCM- Ship Trav LERF- Install wheels, Remove bellows, Stage 4 removal CM18- Pull U-tubes, remove rom CMTF
2019-10-01 | Tue | HOM; C100 WG; C75 DL; |  | C75/Cebaf Cavities; IA-003; L2-340; |  |  | C75/Cebaf Cavities; HE-349 eval (pm); |  |  |  |  | Girder beam line x2; L2-268 ext rinse & bolt holes; L2-268 HW; |  |  | HPR1: OOC HPR2: L2-268; |  | C75-J-005 flange insp.; | L2-268 bottom flange; | C100 Girder(rad); DQW-2; | L2-295, L2-103, L2-346 D5; 5C75-RI-003 leaks; |  | 5C75-RI-003; | C75-J-004 fast; L2-268 fast; | D1: SIC C2K/T; D2: RRR W/T; D3: PJ1-1 warm D4: D5: RFD-2 pull, D6: D7: HE-351 pull; D8: L2-543 C2K/W; | J06R- Weld 2 phase piping, berry bolts | J21- Unite UCM to CS, Install Cav1 tuner J11- Move to WS3E Disassembly, Rail alignment | J20- Instrumentation, RF Cables | J07- Instrumentation flanges, LPT J19- Into CMTF |  | PCM- Ship Trav LERF- Install wheels, Remove bellows, Stage 4 removal CM18- Remove from CMTF
2019-10-02 | Wed | C100 WG; C75 DL; | 1200 Cleanup; | C75/Cebaf Cavities; |  |  | C75/Cebaf Cavities; C75-J-005 Probes; |  | Table Maint. C75 blanks; BLA body flanges; |  | Nb samples; C75 blanks; | HE-349 & HW; Nb samples; C100 Girder; |  | RDT-6, RDL-02 set-up; | HPR1: OOC HPR2: HE-349; |  |  | C75-J-004 complete dis & flange inspection; | L2-268; BLA; | DQW-2; |  | L2-295, L2-103, L2-346 D5; C75-RI-003; |  | D1: SIC C4K; D2: RRR W/Pull Magnet test L/C4K; D3: PJ1-1 hold; D4: D5: L2-295, L2-103, L2-346 L/Precool; D6: D7: D8: L2-543 Pull/L/C4K;; | J06R- Weld 2 phase piping | J21- Unite UCM to CS, Install Cav1 tuner, remove lollipops J11- Move to WS3E Disassembly, Rail alignment | J20- Instrumentation, RF Cables | J07- Ins vac LC J19- Into CMTF |  | PCM- Ship Trav LERF- Install wheels, Remove bellows, Stage 4 removal CM18- Remove from CMTF
2019-10-03 | Thu | C75 DL; |  | IA-282; L2-214; |  |  | C75/Cebaf Cavities; L2-239 RFIN; L2-340, L2-214 RFIN; |  | C75 blank flange; |  | RDT-6, RDL-02 flange & outside BCP; Al sample; | C75-J-005 & parts; RDT-6, RDL-02; BLA body; Al sample; |  | RDT-6, RDL-02 20um; | HPR1: OOC HPR2: C75-J-005; SC-09; |  | HE-349; |  | C100 Girder; BLA; | DQW-2; |  | C75-RI-003; |  | D1: SIC C2K/T; D2: Magnet test, D3: PJ1-1 pull; C75-RI-003 L; D4: D5: L2-295, L2-103, L2-346 W->100K/C4K; D6: D7: D8: L2-543 C2K/T; | J06R- Weld 2 phase piping, install magnet | J21- GHRP Pipe clamps, remove lollipops, 2 phase welding J11- Waiting for lollipops | J20- Instrumentation, RF Cables | J07- LPT, Ins vac LC J18- Remove Bbox, prep 4 BL work |  | PCM- Ship Trav LERF- Remove ICR bellows from end of CM16 CM19- Prep 4 Cool down, CM Demag 1:30pm
2019-10-04 | Fri | C75 DL; |  | C75/Cebaf Cavities IA-014; L2-239; |  |  | Tune HOM's J1.3-20 |  |  |  |  | L2-214; CW beam tubes; RDTTD-01; flex hoses; C75 cavity; |  | Acid change; | HPR1: OOC HPR2: HE-349; C75-J-005 x4; |  | C75-J-005; | DQW-2; | DQW-2; | L2-268; C100 Girder; BLA; |  |  | DQW-2; | D1: SIC C2K/T; D2: Magnet test; D3: C75-RI-003 hold; D4: D5: L2-295, L2-103, L2-346 hold; D6: D7: D8: L2-543 C4K; | J06R- Weld 2 phase piping, Missing parts, install/align magnet | J21- Remove lollipops, prep magnet leads J11- Install lollipops | J20- Tune HOM's | J07- Ins vac LC J18- prep 4 BL work |  | PCM- Ship Trav LERF- Ready for move CM19- Controller out
2019-10-05 | Sat | [17 empty] | DQW-2;
2019-10-06 | Sun
2019-10-07 | Mon | BT & flange PD x4; |  | C75/Cebaf Cavities IA-008; IA-014; |  |  | scrap C50; C75-RI-006; |  |  |  | RFD BT 15u; | L2-340; CW beam tube; TE01NS-001; SC-09 parts; SC-16; pump cart valves; |  | HF Spike; EIC-1 setup; | HPR1: OOC HPR2: L2-281; |  |  |  | C75-J-005; HE-349; | C100 Girder; DQW-2; |  | L2-268; |  | D1: SIC hold D2: Magnet hold D3: C75-RI-003 C4K D4: D5: L2-295, L2-103, L2-346 C4K; D6: D7: D8: L2-543 C2K/T/W; | J06R- Weld 2 phase piping, Missing parts, align magnet | J21- prep magnet leads, heat stations J11- Install lollipops | J20- Inst check | J07- Ins vac LC J18- Beam Line work |  | PCM- Ship Trav, store on UITF LERF- Ready for move
2019-10-08 | Tue | BT & flange PD x4; RFD BT; | BLA absorbers; | C75/Cebaf Cavities; IA-016; |  |  | C20 5-cells; J1.3-20 HOMs; |  |  |  | HF Sample; | EIC-1; eight sets cold FPC hardware; |  | EIC-1 10u; | HPR1: OOC HPR2: SC-09; TE01NS-001; |  |  | BLA 0; | BLA-1; L2-214, L2-239, L2-340 D5; | HE-349; | DQW-2 |  |  | CMTF U-Tubes 3:30pm?; D1: SIC hold D2: Magnet C2.6K/T D3: C75-RI-003 C2K/T/W; D4: D5: L2-295, L2-103, L2-346 C4K; D6: D7: L2-268 L; D8: L2-543 warm; | J06R- Weld 2 phase piping, Missing parts, align magnet | J21- prep magnet leads, heat stations J11- Install lollipops, Raise UCM | J20- Install lower shields, HOM sweep | J07- Ins vac LC J18- Beam Line work |  | PCM- Ship Trav, store on UITF LERF- CM16 to Test Lab
2019-10-09 | Wed | C75 DL repair | PD samples; | C75 DL; C75/Cebaf Cavities |  |  |  |  | SC-09; |  | Nb furnace caps, Mo HW; | L2-239; BLA body; SC-09 & HW; Girder bellows; |  | HE-354 setup; | HPR1: OOC HPR2: RDT-6; L2-281; |  | N2 down (pm) 1 hr; L2-281; |  | L2-214, L2-239, L2-340 D5; TE01NS-001 TS16-005; SC-09 D7/8; | C75-J-005; BLA-1; SC-09; | DQW-2 | HE-349; |  | D1: SIC C2K/T D2: Magnet C2K/T/W; D3: C75-RI-003 pull; D4: D5: L2-295, L2-103, L2-346 C2K/T/W; D6: D7: L2-268 hold; D8: L2-543 pull; HE-349 L/C4K; | J06R- Weld 2 phase piping, Missing parts, MLI | J21- Solder magnet leads, heat stations J11- Prep UCM | J20- clearance shields, | J07- Ins vac LC J18- Beam Line work, M-mounts |  | PCM- Ready to Ship LERF- CM05 to Test Lab
2019-10-10 | Thu | C75 DL repair | BLA | C75/Cebaf Cavities; IA-008; |  |  | 5-cells (X2); J1.3-20 HOMs; |  |  |  |  | C50 end groups; |  | HE-354 60u; | HPR1: OOC HPR2: SC-09; |  |  |  | BLA manifold; L2-281 D7/8; SC-09; | L2-214, L2-239, L2-340 D5; |  | DQW-2; C75-J-005 |  | D1: SIC C4K; D2: D3: D4: C75-J-005 L; D5: L2-295, L2-103, L2-346 warm; D6: D7: L2-268 hold; D8: HE-349 C4K; | J06R- 2 phase welding | J21- Solder magnet leads, prep tuners J11- Raise UCM | J20- HOM's, Weld shields | J07- Ins vac LC J18- Beam Line work, M-mounts |  | PCM- Ready to Ship J05- Start disassembly
2019-10-11 | Fri | C75 DL repair | BLA | C75/Cebaf Cavities |  |  |  | RDT-6 w/caps; |  |  |  | HE-354 (2x); |  | HE-354 20u (20F); | HPR1: OOC HPR2: |  |  |  | BLA Manifold | L2-281; TE01NS-001; | SC-09 120C/24h; | L2-214, L2-239, L2-340; SC-09; | L2-281 fast; | *Field map D5;* CMTF pumpdown to 2K; D1: SIC D2: D3: D4: C75-J-005 L/C4K (cal level sensor) D5: L2-295, L2-103, L2-346 pull; *, DQW-2 L/C4K; D6: D7: L2-268 hold; D8: HE-349 C2K; | J06R- 2 phase welding J11- Weld 1/4" lines, RF measurements, Prep 4 cutting | J21- solder magnet leads, prep tuners | J20- Weld shields, MLI, Into VV | J07- Ins vac LC J18- Beam Line work, M-mounts |  | PCM- Ready to Ship J05- Dis Assy In progress
2019-10-12 | Sat | [6 empty] | RDT-6 w/caps; | [12 empty] | SC-09 120C/24h; |  |  | D5: DQW-2 hold; D8: HE-349 T/W;
2019-10-13 | Sun | [6 empty] | RDT-6 w/caps; | [12 empty] | SC-09 120C/24h; |  |  | D5: DQW-2 C4K; D8: HE-349 W;
2019-10-14 | Mon | filament; C75 DL; | roll BT Flux Expulsion (x4); | C75/cebaf cavities; C75-RI-006 |  |  | C75-RI-005; | RDT-6 w/caps; | BLA; |  | C50 end groups (x3); Cu samples; | RDT-6 HW; BLA-2; String HW; |  |  | HPR1: OOC HPR2: HE-354 1P; L2-281; |  | cage L2-281 drop bottom flange; cage C75-RI-005; | C75-RI-003; | BLA-1; |  |  | TE01NS-001; SC-09; |  | High shield temps; D1: SIC C2K; D2: D3: D4: C75-J-005 C4K; D5: DQW-2 C4K; D6: D7: L2-268 hold; D8: HE-349 pull; SC-09 L thermal cycles; | J06R- 2 phase welding/LC J11- Weld 1/4" lines, Remove Cold Couplers | J21- solder magnet leads, prep tuners | J20- MLI, Into VV | J07- Ins vac LC J18- Beam Line work, M-mounts |  | PCM- Ready to Ship J05- In progress, MC Line
2019-10-15 | Tue | Moly shim stock | PD samples; |  |  |  |  | RDT-6 w/caps; BT PD (x4) 1000C/3h; | 5C75-RI-005; C75 Blanks; |  | Al samples; Nb furnace covers; C75 blanks; | L2 BPM kit; 5C75-RI-005 HW; RDT-6; C50 end groups (x4); |  | 5C75-RI-006 setup; | HPR1: OOC HPR2: RDT-6; |  |  |  | RDT-6 D6; BLA-2; BLA-3; BLA-4; L2-281 D7/8; | BLA-1; |  |  |  | Re-fill CM; D1: SIC C2K; D2: D3: D4: C75-J-005 C2K; D5: DQW-2 C2K/T/W; D6: TE01NS-001 L/SC4K; D7: L2-268 hold; D8: SC-09 thermal cycles/C4K; | J06R- 2 phase LC, mli J11- Cut 2 phase | J21- solder magnet leads (parts issues), prep tuners | J20- Align CM in VV | J07- M-mounts J18- Beam Line work | NL07-Move C20 Disassy rail , Configure | PCM- Ready to Ship J05- Disassy In progress, WC's
2019-10-16 | Wed |  |  | C75/cebaf cavities L2-BLA; |  |  |  | BT PD (x4) 1000C/3h; | C75 Blanks; |  | 5C75-RI-005 & blanks; Al bars; | 5C75-RI-005 & blanks; L2 string kit; |  | 5C75-RI-006 40u; | HPR1: OOC HPR2: 5C75-RI-005 |  |  |  | L2 Gate Valve; | BLA-2; BLA-3; BLA-4; L2-281; |  |  |  | CM Pumpdown; D1: SIC C2K; D2: D3: D4: C75-J-005 T/W; D5: DQW-2 T/warm; D6: TE01NS-001 test; D7: L2-268 failed qualification; D8: SC-09 C2K/T/W; | J06R- 2 phase LC, mli, HV Mag shields J11- Cut 2 phase | J21- CS Align, solder magnet leads (parts issues), prep tuners | J20- Align CM in VV | J07- M-mounts J18- Beam Line work | NL07-Move C20 Disassy rail , Configure | PCM- Ready to Ship J05- Disassy In progress, WC's
2019-10-17 | Thu | C100 WG; BT-HC PD (x4); |  | C75/cebaf cavities; BNL lamination coil; |  |  |  | BT PD (x4) 1000C/3h; RDL-02; | C75 Blanks; |  | BT PD (x4); C75 Blanks; | MC lines, flanges, HW; FPC cold parts; Bellows; |  | 5C75-RI-006 40u | HPR1: OOC HPR2: RDL-2; |  | US valve assy; |  | L2 BPM; | BLA-2; BLA-3; BLA-4; L2 Gate Valve; |  | L2-281 HOMs; | L2-1; L2-2; L2-3; | D1: SIC C2K; D2: D3: D4: C75-J-005 warm; D5: DQW-2 warm/pull; L2-214, L2-239, L2-340 L/C4K; D6: TE01NS-001 C2K/T/W4K/T/W; D7: L2-268 troubleshoot TS air leak D8: SC-09 warm; | J06R- HV MLI and Mag shields J11- Cut 2 phase, Remove cavities | J21- CS Align | J20- Move to WS5 | J07- M-mounts, to WS6 J18- to WS6 | NL07- Configure rail components | PCM- Ready to Ship J05- Disassy In progress, WC's, to WS5
2019-10-18 | Fri | BT-HC PD (x4); |  | BNL lamination coil; L2 long spools; C50 Endgroup |  |  |  | RDL-02; |  |  | C75 Blank; | L2-1 ext rinse; L2-2 ext rinse; L2-3 ext rinse; 5C75-RI-006; L2 bellows; Gate valve; Lollipops; C50 end groups; AMV flanges; |  | 5C75-RI-006 20u; Acid change; | HPR1: OOC HPR2: 5C75-RI-005 (4p); |  | C75-RI-005 |  | L2 BPM; | BLA-3; BLA-4; |  |  | L2-4; | D1: SIC D2: D3: D4: C75-J-005 pull; D5: L2-214, L2-239, L2-340 warm -> 100K, C2K; D6: RDT-6 L/C/T; D7: L2-268 troubleshoot TS air leak D8: SC-09 warm; | J06R- HV MLI and Mag shields J11- Cut 2 phase, Remove cavities | J21- CS Align |  | J20- Move to WS5 J05- Disassy In progress, WC's | NL07- Configure rail components | PCM- Ready to Ship J07- M-mounts J18- Ship Trav J05- Disassy In progress, WC's, to WS5
2019-10-19 | Sat | [6 empty] | RDL-02; | [15 empty] | D5: L2-214, L2-239, L2-340 T/W;
2019-10-20 | Sun | [6 empty] | RDL-02;
2019-10-21 | Mon | BT-HC PD (x3); | air-fired ceramics; | BNL lamination coil; |  |  | C75-RI-006 freq & FF; | RDL-02; | L2 spools; |  |  | L2-1, 2, 3 bolt holes; L2-4, 5, 6 ext rinse; C75-RI-006; L2 lollipop parts; bellows, flanges; Feed through; EZ-SSC-03 & parts; |  | HF spike; EP maint; C75-J-004 setup; | HPR1: OOC HPR2: |  | Lollipops; | C75-J-005; | C75-RI-005 D3/4; L2 BPM; |  |  | L2-281 sensors; | L2-5; L2-6; | D1: SIC C2K/T; D2: D3: D4: D5: L2-214, L2-239, L2-340 pull; D6: D7: L2-268 troubleshoot TS air leak/C4K; D8: SC-09 pull, L2-281 L; | J06R- HV MLI and Mag shields, UCM ready J11- Cut 2 phase LLP's | J21- Move to East 4 post Tuners |  | J20- Beam line work, WC's J05- Disassy In progress, WC's | NL07- Configure rail components | PCM- Ready to Ship J07- Ship Align J18- Ship Trav
2019-10-22 | Tue | BT-HC PD (x3); C100 WG mod; | air-fired ceramics; RF Sep. PD SC (x2) ; | BNL lamination coil; | C75-J-005 |  | C75-RI-007 probe check; | C75-RI-006 450C/3h, 800C/3h; | C75-RI-007 flange insp. EZ-SSC-03 |  | Nb furnace caps; | L2-4, 5, 6 bolt holes; L2-7, 8 ext rinse; L2-211; C75-J-004 (2x); C75-RI-007; |  | C75-J-004 10u; | HPR1: OOC HPR2: RDL-02; |  | Lollipops; |  | RDL-02 D6; | C75-RI-005; L2 BPM; |  |  | L2-7; | D1: SIC C2K/T; D2: Magnet Test Nb L/C4K/T D3: D4: D5: field map/degauss; D6: D7: L2-268 C2K/T/W; D8: L2-281 C4K; | J06R- Move WS3 J11- Done | J21- Tuners |  | J20- Beam line work, WC's, weld JT's J05- Disassy In progress, WC's | NL07- Configure rail components | PCM- Ready to Ship J18- Ship Trav
2019-10-23 | Wed | C100 WG mod; | PD SC (x2) ; | L2-BLA; BNL Coil; | C75-J-005 |  |  | C75-RI-006 450C/3h, 800C/3h; |  |  | PD SC (x2) weld prep; | L2-211 ext rinse; L2- 9, 10 ext rinse; L2-7, 8 bolt holes; SC-IB & parts; |  | HE-352 setup; | HPR1: OOC HPR2: C75-J-004 (1p) (swap cage to 007); EZ-SSC-003 (4p ext spray); C75-RI-007; |  | Lollipops; Bellows conditioning; |  |  |  |  | C75-RI-005; | L2-8; | D1: SIC C2K/T; D2: Magnet Test Nb C2K/T D3: C75-RI-005 L/C4K; D4: D5: field map/degauss; D6: RDL-02 L/C/T; D7: L2-268 warm; D8: L2-281 C2K/T/W; | J06R- Unite CS to UCM | J21- Tuners |  | J20- Beam line work, WC's, weld JT's J05- Disassy In progress, WC's | NL07- Pending Paperwork | PCM- Prep for loading J18-ongoing J07- ongoing
2019-10-24 | Thu |  |  | Cu tubes (x4); BNL coils (5x); |  |  | C75-RI-006 freq & FF & probes; |  | Test blank; EIC; C75-J-005; |  |  | L2- 9, 10 bolt holes; Girder parts; |  | HE-352 60u; | HPR1: OOC HPR2: |  | mag field meas. tooling; | [6 empty] | D1: SIC C2K/T; D2: Magnet Test Nb C2K/T; D3: C75-RI-005 C2K/T/W; D4: D5: field map/degauss?; D6: RDL-02 W D7: L2-268 pull; field map/degauss; D8: L2-281 warm; | J06R- Unite CS to UCM | J21- Tuners |  | J20- Beam line work, WC's, HPT J05- Disassy In progress, WC's | NL07- Pending Paperwork | PCM- Load CM J18-ongoing J07- ongoing NL25- Set limit switches SL25- Adjust bead bags LERF- Prep/LC bellows joint
2019-10-25 | Fri |  | RF Sep. | Cu tubes (x4); |  |  |  |  | C75-J-005 BP; C75 DL; |  |  | HE-352 (2x); HE-034; |  | HE-352 20u (20F); | HPR1: OOC HPR2: RDT-06; C75-RI-007; |  | C75-RI-007; |  | SCIB; | EZSSC-03; | EZSSC-03; |  |  | D1: SIC C2K/T; D2: RRR L/C/W/T; D3: C75-RI-005 warm; D4: D5: D6: D7: D8: L2-281 pull; | J06R- Unite CS to UCM | J21- Tuners |  | J20- Beam line work, WC's, Weld JT J05- Disassy In progress, WC's | NL07- Pending Paperwork | PCM- Load CM/Ship J18-ongoing J07- ongoing NL25- Set limit switches SL25- Adjust bead bags LERF- Prep/LC bellows joint
2019-10-26 | Sat | [17 empty] | C75-RI-007 D3/4; |  | EZSSC-03;
2019-10-27 | Sun | [13 empty] | HPR2: L2-1; L2-2; | [5 empty] | EZSSC-03;
2019-10-28 | Mon | PD SC (x2); | RF Sep. | BNL Coils; L2-Spools; Cu tubes; |  |  | C75-RI-002 Freq/FF/FPC; |  | C75 DL; EIC-1; |  | Nb plate 5u and Moly HW (Jay); EIC-1; TE1NS001 nitric soak; | Heater (Jay); |  | C75-RI-006 setup; | HPR1: OOC HPR2: L2-3; L2-4; HE-352 7p/ overnight; |  |  |  | L2-1, L2-2 to rail; | SCIB; C75-RI-007; |  |  |  | D1: SIC C2K/T; D2: RRR hold; D3: C75-RI-005 hold; D4: D5: Magnetic testing D6: RDT-6 L/C/T; D7: Magnetic testing D8: Magnetic testing | J06R- Unite CS to UCM | J21- Tuners/FSS | J21- VV from BC | J20- Beam line work, WC's, Weld JT J05- Remove WC's | NL07- Begin disassy | J18-ongoing J07- Move to WS6, Ship traveler
2019-10-29 | Tue | PD SC (x2); | RF Sep. | C75-RI-002 (pm); C75 DL (3x); | PD SC (x2); |  | C75-RI-002 HOM BP and tophats; |  | EIC-1; C75 DL; |  | C75 DL & bodies; | C75-RI-006; C75-J-005; C75 DL bodies; |  | C75-RI-006 30u; | HPR1: OOC HPR2: L2-5 (543) 4p; L2-6; |  |  |  | L2-3, L2-4 to rail; |  |  | SCIB; C75-RI-007; |  | Fast Cooldown/demag CMTF; D1: SIC hold; D2: RRR pull; D3: C75-RI-005 pull; D4: D5: Magnetic testing D6: RDT-6 pull; D7: Magnetic testing D8: Magnetic testing | J06R- Weld 2 phase piping | J21- Fastener SS | J21- WS4 | J20- WC's, 2 phase LC J05- Remove WC's | NL07- Begin disassy | J18-Move to WS6, Shipping Alignment J07- Move to WS6, Ship traveler
2019-10-30 | Wed | PD SC (x2); C75 DL bodies; | RF Sep. | [5 empty] | C75 DL; EIC-1; |  | EIC-1; | C75 DL bodies; L2 Cold FPC parts; EIC-1; |  | C75-J-005 setup; | HPR1: OOC HPR2: L2-7 (214) 4p; L2-8; |  |  | C75-RI-005; | L2-5, L2-6 to rail; |  |  |  |  | D1: SIC C2K/T; D2: D3: C75-RI-007 L/C4K; D4: D5: Mag test hold; D6: D7: Magnetic test hold; D8: Mag test pull; EZSSC-03 L; | J06R- Weld 2 phase piping | J21- Fastener SS, tuners, waiting on magnet parts | J21- VV in place | J20- MC line, 2 phase LC J05- Remove WC's | NL07- Pending Paperwork | J18-Shipping Alignment J07- idle
2019-10-31 | Thu | PD SC (x2); C75 DL bodies; | RF Sep. | C75-RI002 |  |  | C75-RI-005 Freq/FF/FPC; |  |  |  |  | C75-J-005; |  | C75-J-005 50u; | HPR1: OOC HPR2: TE1NS001 |  |  |  | L2-7, L2-8 to rail; HE-034 D7/8; | HE-034; |  | HE-034; |  | D1: SIC C2K/T; D2: Magnet test L/C4K/T/W; D3: C75-RI-007 C2K/T/W; D4: D5: Mag test pull; D6: D7: Mag test pull; D8: EZSSC-03 P/check sensors/L/C4K; | J06R- Weld 2 phase piping, Cav 1 tuner | J21- waiting on magnet parts | J21- VV in place | J20- JT welding, MC line, 2 phase LC J05- Remove WC's | NL07- Pending Paperwork | J18-Shipping Alignment J07- idle
2019-11-01 | Fri | Maint | RF Sep. | Vac |  |  | C75 Window RF measurement; |  |  |  |  | Cold FPC cups & HW; L2-281 ext rinse & bolt holes; RDT-6 HW; |  | RDT-6, RDL-02, SC-09 setup; | HPR1: OOC HPR2: SC-11; L2-281; |  | C75 DL prep (x2); L2-281 bottom flange and cage; | [6 empty] | D1: SIC C2K/T; D2: Magnet test pull; D3: C75-RI-007 warm; D4: D5: D6: D7: HE-034 L/C4K; D8: EZSSC-03 thermal cycles/C4K; | J06R- Weld 2 phase piping, Cav 1 tuner | J21- Heat station magnet leads, complete tuners | J21- VV in place | J20- MC line, 2 phase leak check, RT SATURDAY J05- Remove WC's, complete BL work | NL07- Pending Paperwork | J18- on UITF J07- Tune HOM's, ship trav, ship Nov 8th LERF- LC Cryocan connection
2019-11-02 | Sat | [26 empty] | RT for CM20 7A.M.
2019-11-03 | Sun
2019-11-04 | Mon |  | HWCoax FT; | C75-RI-002; C75 DL (x2); |  |  | C75-RI-006 Freq/FF/probes; J1.3-07 HOMs; |  | C75-J-004; FPC WG flanges (x2); |  |  | RDT-6, RDL-02, SC-09; SCIB parts; L2-x137; |  | RDT-6, RDL-02, SC-09 20u (20F); | HPR1: OOC HPR2: SCIB; |  | cage L2-137; cage L2-328; |  | SC-11; SCIB D6; L2-281 D5; bag J1.3-09R | SC-11; |  |  |  | CMTF 4 Cav Run; D1: SIC C4K; D2: D3: C75-RI-007 pull; D4: D5: D6: D7: HE-034 C2K/T/W; D8: EZSSC-03 C4K; |  | J21- Verify alignment, to WS4 J06R- Weld 2 phase piping, Cav 1 tuner | J21- VV in place | J20- MC line LC, 2 phase leak check J05- Move to UITF J16- Move to WS5 | NL07- RADCON Briefing | J18- on UITF J07- Tune HOM's, ship trav
2019-11-05 | Tue | Maint | BB cleaning; | C75-RI-005; C75 RI-002; |  |  | C75-J-005 BP; | RDT-6 800C/3h, 140C/48h; | C75-J-004; C75 DL; FPC WG flanges (x1); | C75-J-002; | RFD damper parts 15u; tubes; | L2-328 and HW; L2-137 HW; Vac chamber; Mag shield tubes; Lg conflats & probes; |  | HE-349 setup; | HPR1: OOC HPR2: RDT-6; L2-137; L2-328 (overnight); |  |  | C75-RI-007; |  | SCIB; J1.3-09R; |  | SCIB; |  | CMTF 4 Cav Run; D1: SIC C2K/T; D2: D3: D4: D5: D6: D7: HE-034 warm; D8: EZSSC-03 C2K/T/W; |  | J06R- Weld 2 phase piping/LC, Cav 1 tuner | J21- RF Cables, Instrumentation, Mag end caps | J20- MC line LC, 2 phase leak check J16- Beam line work | NL07- RADCON Briefing | J07- Tune HOM's, ship trav
2019-11-06 | Wed | Maint | BLA; | C75-RI-005; C75 RI-002; |  |  | C75-RI-002; | RDT-6 800C/3h, 140C/48h; | C75 DL; C75-RI-006; |  | BT; C75 flanges; Nb samples; | FPC WG flanges (x3); PJ1-1 & HW; C75-RI-006 HW; |  | HE-349 60u; | HPR1: OOC HPR2: PJ1-1; L2-137; |  | L2-137; | HE-034; | String IP; |  | EZSSC-03 120C/24h; |  |  | D1: SIC warm; D2: Magnet Test L/C4K; D3: D4: D5: D6: SCIB SC4K D7: HE-034 pull (keep under vacuum); D8: EZSSC-03 pull; |  | J06R- Weld 2 phase piping/LC, Cav 1 tuner | J21- Instrumentation, Mag end caps | J20-RF Waveguides, Inst flanges J16- Beam line work, GHRP Bellows protector | C75-01- RADCON Briefing@ 10:30 | J07- Tune HOM's, ship trav
2019-11-07 | Thu | Cryo Pump Regen | BLA; | L2-BLA; C75-RI-002; C75-RI-005; |  |  | C75-RI-002; plasma test stand dis; J1.3-09R passbands; | RDT-6 800C/3h, 140C/48h; | C75-RI-006; |  |  | HE-349 (2x); L2-328 parts; |  | HE-349 20u (20F); | HPR1: OOC HPR2: |  | L2-328; | String rollout; | PJ1-1; SC-13 D7/8; L2-281, L2-137 D5; BLA training (x2 assemled); | SC-13; | EZSSC-03 120C/24h; | SC-13; |  | D1: SIC pull; D2: Magnet Test C2K/T; D3: D4: D5: D6: SCIB C2K/T/W; D7: D8: SC-13 L/C4K; | J09R- Receive CS | J06R- Weld 2 phase piping/LC, prep magnet leds | J21- Instrumentation, , RF Cables | J20-RF Waveguides, Inst flanges J16- Beam line work, | C75-01- Begin CM Disassembly | J07- Load CM Modify magnet intercepts
2019-11-08 | Fri | Cryo Pump Regen | BLA; TW annealing; | L2-BLA; C75 DL; C75 RI-005 |  |  | plasma test stand dis; | RDT-6 800C/3h, 140C/48h; | C75-RI-006; C75 CBP; |  |  | BLA; L2-332; SC-10; SC-15; BLA post-bake (x3); |  | HE-364 setup; | HPR1: OOC HPR2: HE-349 (1p); L2-328; |  | L2-332; | C20 flange dis; | BLA training; | PJ1-1; |  | EZSSC-03; |  | D1: D2: Magnet Test Hold D3: D4: D5: D6: D7: EZSSC-03 L/C4K; D8: SC-13 thermal cycles; | J09R- Receive CS, RF Measurements | J06R- LC 2 Phase piping, prep magnet leads, remove lollipops | J21- Instrumentation, , RF Cables, alignmnet verification | J20- Inst flanges J16- Beam line work, GHRP Bellows protector | C75-02- Begin CM Disassembly | J07- Ship CM J06R-Modify magnet intercepts
2019-11-09 | Sat | [22 empty] | D7: EZSSC-03 C2K/T/W;
2019-11-10 | Sun
2019-11-11 | Mon | Cryo Pump Regen |  | L2-BLA; C75 RI-005 C75 DL (4x); |  |  | DL window meas; C75 RI-005; J1.3-18 HOM meas; | 45mm tubes AP 600C/10h; | C75 DL; C75-RI-002; |  | C75-RI-006; Nb samples (GC) x13; AP BTs; furnace caps; | C75-RI-006; cold FPC HW & tophats; |  | HE-364 45u; | HPR1: OOC HPR2: RDT-6; L2-332; |  | cage L2-167; | EZSSC-03; SC-13; TS28-011; | L2-281, L2-137, L2-328 D5; BLA (x1); |  |  |  |  | D1: SIC L; D2: Magnet Test C4K/T; D3: D4: D5: D6: D7: EZSSC-03 pull; D8: SC-13 pull; | J09R- fit 2 phase piping, instrumentation | J06R- LC 2 Phase piping, prep magnet leads | J21- Instrumentation, RF Cables, alignment verification | J20- LC Ins Vac J16- Beam line work | C75-02-CM Disassembly | J06R-Modify magnet intercepts
2019-11-12 | Tue | maint Cryo pump replacement | maint | L2-BLA; C75 DL (4x); |  |  | C75 RI-005; plasma TS maint; J1.3-18 HOM tune; | Nb samples (GC) x13 450C/3h, 800C/3h; | C75-RI-002; C75 HOM elbows; |  | HIPEMS flanges; C75 HOMs; L2 FTs; | HIPEMS chamber and HW; L2 FPC parts; BLA kits; BLA (x6); C75-RI-006 HW; L2-167 (USC x2) & HW; L2-332 HW; |  | HE-364 35u (20F); | HPR1: OOC HPR2: C75-RI-006; L2-167; |  | L2-332; |  | SC-10 D7/8; SC-15 D7/8; BLA (x1); RDT-6; | SC-10; SC-15; |  | SC-10; SC-15; |  | D1: SIC C2K/W (leaks); D2: Magnet Test C2K/T/W; D3: D4: D5: D6: thermometer cal L/C4K/W (leaks); D7: D8: | J09R- fit 2 phase piping, instrumentation,Berry bolts, install SPQA | J06R- LC 2 Phase piping, prep magnet leads, heat intercepts | J21- Instrumentation, RF Cables, alignment verification | J20- LC Ins Vac, Move to WS6 J16- Beam line work | C75-02-CM Disassembly | J06,9,11R-Modify magnet intercepts J18- Move to WS5, Tune HOM's, Cav4 WC Investigate, ship 11-22
2019-11-13 | Wed | Cryo pump replacement | BLA | C75 RI-005; C75 Inner adapter; C75-RI-002; C75-DL |  |  | J1.3-21 HOM tune; | Nb samples (GC) x13 450C/3h, 800C/3h; | C75 DL; C75 HOM elbows; C75-RI-002; |  |  | HE-364 (2x); BLA kits; SC-12 HW; HIPEMS chamber; L2 parts; FPC valve; Wilcox valves & HW; |  | HE-364 disassemby; Maint; | HPR1: OOC HPR2: L2-332; C75-RI-006 (4P); HE-364 overnight; |  | C75-RI-006; | Lollipops L2; | HIPEMS; | L2-281, L2-137, L2-328; |  |  |  | D1: SIC pull; D2: Magnet Test hold D3: Mag scan system L; D4: D5: D6: RDT-6 L/C/T/W4K; D7: SC-15 L/thermal cycles; D8: SC-10 L/thermal cycles; | J09R- fit 2 phase piping, instrumentation,Berry bolts | J06R- prep magnet leads, CS Alignment | J21- Tune HOM's, Test fit shields | J18- Cav4 WC repair J16- Beam line work, m-mounts | C75-02-CM Disassembly, Remove flanges | J06,9,11R-Modify magnet intercepts J20- LC Ins Vac
2019-11-14 | Thu | Cryo pump replacement | BLA; | L2-BLA; C75 DL; |  |  | C75 DL windows; |  | C75-RI-005; C75-RI-002; |  |  |  | Maint. |  | HPR1: OOC HPR2: L2-167; SC-12 (4pass); |  | L2-167; | L2 lollipops; | BLAs; C75-RI-006; |  |  | L2-281, L2-137, L2-328; |  | D1: SIC L/C2K/T; D2: Magnet Test C2K/T/W; D3: Mag scan system C4K; D4: D5: L2-281, L2-137, L2-328 L/precool; D6: RDT-6 W20K/C/T; D7: SC-15 thermal cycles; D8: SC-10 thermal cycles; | J09R- fit 2 phase piping, instrumentation,Berry bolts | J06R- CS Alignment | J21- Install shields, verify HOM's | J18- Cav4 WC repair J16- Beam line work, m-mounts | C75-02-CM Disassembly, Remove flanges, machine setup | J06,9,11R-Modify magnet intercepts J20- LC Ins Vac Shipping frame back from SLAC Transport SSA Crates BC to SAB
2019-11-15 | Fri | Compressor replacement | BLA (x3) Hall D Anneal | C75-DL |  |  | C75 Windows | RDL-02 800C/3h, 140C/48h; | C75-RI-005; |  | C75-RI-002; | C75-RI-002; TS28-011 parts; L2-140; L2-BLA preclean (x3); | Maint. Acid Change out | Maint. Acid Change out | HPR1: OOC HPR2: EIC-1 RDL-02 (no bay); |  | cage L2-140; |  | L2-332, L2-167 D5; BLAs; | C75-RI-006; |  | C75-RI-006; |  | D1: SIC Hold; D2: D3: Mag scan system C4K/T/W; D4: C75-RI-006 L/C4K; D5: L2-281, L2-137, L2-328 C4K (20cm); D6: RDT-6 C2K/T/thermometry test/W; D7: SC-15 pull; D8: SC-10 pull; | J09R- fit 2 phase piping, instrumentation, Alignment | J06R- CS Alignment, Tuners | J21- MLI, into VV | J18- Cav4 WC repair J16- Beam line work, Ship Trav | C75-02-CM Disassembly, Remove flanges, machine setup | J06,9,11R-Modify magnet intercepts J20- LC Ins Vac UCM from BC
2019-11-16 | Sat | [6 empty] | RDL-02 800C/3h, 140C/48h;
2019-11-17 | Sun | [6 empty] | RDL-02 800C/3h, 140C/48h;
2019-11-18 | Mon | Compressor replacement | Frank anneal; | C75 DLs; C75-RI-002; |  |  |  | RDL-02 800C/3h, 140C/48h; | C75-RI-005; C75 DL (x2)'; |  | C75 HOM elbows; C75-RI-002 flanges; | L2-330 and parts; L2-140 parts; NS-001 parts; HB-046; C75 HOM elbows; C75-RI-002; | HWCoax2 setup; | HF Spike; | HPR1: OOC HPR2: L2-140; NS-001; |  | cage L2-330 | C75 end dish; |  | BLAs; SC-11, SC-12; |  |  |  | D1: SIC C2K/T; D2: D3: Mag scan system warm; D4: C75-RI-006 C2K/T/C1.8K/T/W; D5: L2-281, L2-137, L2-328 W/C4K; D6: RDT-6 C2K/T/W; D7: D8: | J09R- fit 2 phase piping, Alignment | J06R- Tuners, Magnet leads | J21- HOM cans, Weld process pipes, checklist | J18- Shipping Trav, Inserts, Ship 11/22 J16- Beam line work, Ship Trav | C75-02- Machine setup, Bleed up beamline | J06,9,11R-Debur magnet intercepts J20- Remove BB J09R- UCM in house, QC FSS
2019-11-19 | Tue | AP BT (x4); |  | L2-BLA; C75-RI-002; |  |  | DL windows; | HB-046 600C/10h; | C75-RI-005; |  |  | L2-308 parts; FPC parts (full set); HIPIMS bellows; C75 valves; HC x2; furnace caps; L2 HW; BLAs for ship; LSF5-1 HW; | HWCoax2 10u; | maint; | HPR1: OOC HPR2: L2-330; L2-140; |  | L2-140; HiPIMS; |  | NS-001 TS-16-005; | NS-001; |  | TS-28-006 sensor repair; |  | CMTF supply u-tube pull, CTF C3 testing; D1: SIC C4K; D2: Magnet Test L/C4K/T/W; D3: Mag scan system pull/load/C4K; D4: C75-RI-006 warm/pull; D5: L2-281, L2-137, L2-328 C2K; D6: RDT-6 pull; D7: D8: | J09R- fit 2 phase piping, Alignment | J06R- Tuners, heat station magnet leads | J21- HOM cans, lower shields, verify HOM's | J18- Shipping Trav, Ship caps, Ship 11/22 J16- Beam line work, Ship Trav | C75-02- Machine setup, beamline bled up | J20- Install GHRP flange and BNNT Cav 1 J09R- UCM in house, QC FSS, weld repair 1L26-3-Tuner repair FL02- Tuner repair all
2019-11-20 | Wed | AP BT (x4); |  | C75-RI-002; L2-BLA's; C75 HOM elbows; |  |  | C75-RI-002; | HB-046 600C/10h; | C75-RI-005; C75-J-002, C75-J-000 CBP; |  | HIPIMS; | 28 inch test stand parts RG; HIPIMS; L2-BLA (x2); RDL-02 HW; L2-308; L2-536; |  | SC-10, SC-13, SC-15 setup; | HPR1: OOC HPR2: RDL-02; HWCoax-2; L2-330; |  | L2-330; cage L2-308; HiPIMS; | L2-536 drop bottom flange; | L2-332, L2-167, L2-140 D5; RDL-02; | RDL-02; | SC-11, SC-12 120C/24h; |  |  | D1: SIC C2K/T; D2: Magnet Test C2K/T/W; D3: Mag scan system C4K/T; D4: D5: L2-281, L2-137, L2-328 HOMs/T/warm; D6: D7: D8: | J09R- Weld 2 phase piping, prep mag shields | J06R- Tuners, heat station magnet leads | J21- verify HOM's, weld shields | J18- Shipping Trav, Ship 11/22 J16- Ship Trav, m-mounts | C75-02- Remove manifolds, motors | J20- Prep for move to LERF tomorrow J09R- UCM QC FSS, weld repair
2019-11-21 | Thu | PD SC (x2); HiPIMS cathode; | L2-BLAs (x3); | L2-BLA; C75 inner adapter; C75-RI-002; |  |  | HB-046 FF and flange insp. C75-RI-002; |  | C75-RI-002; C75-J-002, C75-J-000 CBP; |  | C75-RI-005; NS-001 (nitric); AP Beam tubes (x4); Nb sheets; | LSF5-1; C75-RI-005; SC-10, SC-13, SC-15; | Maint (acid out) | SC-10, SC-13, SC-15 30u (20F); | HPR1: OOC HPR2: L2-536; L2-308; nozzle change; LSF5-1; |  |  | DQW2; | L2-330 D7/8; L2 BLA (x3); | L2-332, L2-167, L2-140 D5; |  | SC-11; SC-12; |  | D1: SIC; D2: Magnet Test 4K D3: Mag scan system D4: maint; D5: L2-281, L2-137, L2-328 warm; D6: RDL-02 L/C2K/T/W; D7: SC-11 L D8: SC-12 L | J09R- Weld/LC 2 phase piping, prep mag shields | J06R- Tuners, heat station magnet leads | J21- Weld shields,MLI | J18- Load in trailer J16- Ship Trav, m-mounts | C75-02- Remove manifolds, motors | J20- Move to LERF J09R- UCM QC FSS, weld repair
2019-11-22 | Fri |  | L2-BLAs (x3); | C75-RI-005 L2-BLA; J1.3-11 Bellows; |  |  | HB-046 FF and flange insp.; C75-RI-005; C75-RI-002; | FH3C 800C 3hrs 140C 48hrs with N2; | 5C75-RI-002 FPC; |  |  | L2 warm BL parts; L2-118 (pm); L2 FPC (x8); | Maint |  | HPR1: OOC HPR2: nozzle change, clean-up run; FH3C; L2-308; |  | L2-308; L2-118 Ti cage (pm); L2-295 to tuning; | DQW2; | LSF5-1; L2-536 D7/8; | L2-330; L2 BLA (x3); |  | L2-281, L2-137, L2-328 remove sensors; L2-332, L2-167, L2-140 sensors & HOMs; |  | CMTF U-tubes; D1: SIC; D2: Magnet Test 2K D3: Mag scan system D4: D5: L2-281, L2-137, L2-328 pull; L2-332, L2-167, L2-140 L/precool; D6: RDL-02 W D7: SC-11 thermal cycles; D8: SC-12 thermal cycles; | J09R- Weld/LC 2 phase piping, prep mag shields | J06R- Tuners, verify alignment J09R- UCM Weld Repair, Install D-Line hangers | J21- Verfiy HOM's, Weld shields,MLI | J05- On floor for WC removal J16- Ship Trav, m-mounts, Move to WS6 | C75-02- Open Tophat | J18- Ships today 10am-ish J20- LERF
2019-11-23 | Sat | [6 empty] | FH3C 800C 3hrs 140C 48hrs with N2; | [11 empty] | LSF5-1; |  |  |  | D5: L2-332, L2-167, L2-140 W/C4K;
2019-11-24 | Sun | [6 empty] | FH3C 800C 3hrs 140C 48hrs with N2; | [11 empty] | LSF5-1; |  |  |  | D5: L2-332, L2-167, L2-140 C2K/T/W;
2019-11-25 | Mon | PD SC (x2); HiPIMS cathode; |  | L2-BLA; C75 HOM loads; C75 inner adapters; |  |  |  | FH3C 800C 3hrs 140C 48hrs with N2; | C75-J-004; C75-J-005; |  | C75-RI-002; C75-J-004; PD 2cav & plugs; C75 inner adapt; FM HC; | C75-RI-002; C75-RI-005; C75-J-004; L2 FPC (x8 cont.); L2 BLA (x3); SC-10 parts; FH3C parts; | needs acid; |  | HPR1: OOC HPR2: NS-001; L2-118; (setup SC-10); |  | C75 TS28-001 | DQW2; | L2-308 D7/8; | L2-536; L2 BLA (x2) scans; |  | LSF5-1; L2-330 sensors & HOMs; |  | D1: SIC D2: D3: Mag scan system pull; D4: D5: L2-332, L2-167, L2-140 W; D6: D7: SC-11 thermal cycles; D8: SC-12 pull; L2-330 L/C4K; | J09R- LC 2 phase piping, prep mag shields | J06R- Tuners J09R- UCM Weld Repair,FSS | J21- MLI, into VV | J05- WC removal J16- Ship Trav, m-mounts, Shis Dec 6th | C75-02- Open Tophat, break 1st indium joint | J20- LERF J19- Prep to remove from CMTF
2019-11-26 | Tue | PD SC (x2); |  | C75-RI-002; L2-BLA; | L2-281; |  | L2-295 tuning in HV; | FH3C 800C 3hrs 140C 48hrs with N2; AP BT(x3), HC(x2) 800C/3h; | C75-J-005; |  | C75 HOM loads HF; | C75-J-005; C75 pair prep; C75 HOM loads; C75 TS28-001; | needs acid; |  | HPR1: OOC HPR2: (nozzle change) FH3C; (nozzle change); SC-10 (4P); |  | L2-118; C75 pair prep (mag hygiene); SC-10; |  | NS-001; FH3C; HWCoax2; | C75 valves; L2-308; HWCoax2 (fail); NS-001 (fail); |  | L2-536 sensors & HOMs; LSF5-1; HWCoax; |  | D1: SIC C2K/T; D2: D3: Mag scan system L/C4K; D4: D5: L2-332, L2-167, L2-140 warm; D6: D7: LC-11 pull; L2-536 L/C2K; D8: L2-330 C2K/T; | J09R- LC 2 phase piping, prep mag shields | J06R- Tuners J09R- UCM Weld Repair,FSS | J21- MLI, into VV | J05- WC removal J16- Ship Trav, m-mounts, Ships Dec 6th | C75-02- Open Tophat, break 1st indium joint | J20- LERF J19-Remove from CMTF
2019-11-27 | Wed | PD SC (x2); |  | C75-RI-002; L2-BLA (3); |  |  | L2-295 tuning in HV; | AP BT(x3), HC(x2) 800C/3h; | C75-RI-002 FPC; |  |  | C75 HOM elbows x 4; C75 Tooling; C75 HW; L2-281; | needs acid; |  | HPR1: OOC HPR2: L2-118; |  | C75 Prep; | L2-281 and Ti cage; | SC-10; | FH3C; |  | L2-308 sensors; TS-28-010 RA valve repair; |  | D1: SIC C2K/T; D2: D3: Mag scan system warm; D4: D5: L2-332, L2-167, L2-140 pull; D6: D7: L2-536 T/W; D8: L2-330 T/warm; | J09R- Install Mag shields, FSS | J06R- Tuners J09R- FSS, Demag | J21- Ready for alignment Dec 2 | J05- WC removal J19- Prep for BL work | C75-02- Remove tophats | J20- Idle in LERF J16- Ship Trav, tune HOM, ships Dec 6th
2019-11-28 | Thu | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2019-11-29 | Fri | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2019-11-30 | Sat
2019-12-01 | Sun
2019-12-02 | Mon | Edwards Pump rebuid 4 wks | BLAs (x3); | L2 bellows; C75 End dishes (1); |  |  |  | AP BT(x3), HC(x2) 800C/3h pull; | C75-J-002 dis-assy; |  | C75-RI-002; C75 top hats; | C75-RI-002; C75-J-002; HB-046; L2 BLAs (x3); Mircea valves x8; SC-10 HW; C75 prep; |  | RDL-02, RDT-06 setup; | HPR1: OOC HPR2: L2-281; |  |  |  | L2-118; L2-137; |  |  | L2-308 HOMs; | L2-1; | D1: SIC C2K/T; D2: D3: Mag scan system pull; D4: LSF5-1 L/C2K/T; D5: D6: FH3C L; D7: L2-536 pull; SC-12 L/thermal cycles; D8: L2-330 pull; L2-308 L/C4K; | J09R- Install Mag shields, FSS | J06R- Tuners J09R- FSS, Demag | J21- Ready for alignment Dec 2 | J05- WC removal J19- Prep for BL work | C75-02- Remove tophats | J20- Idle in LERF J16- Ship Trav, tune HOM, ships Dec 6th
2019-12-03 | Tue |  | BLAs (x3); | C75-RI-002 (1); L2 bellows; L2 BLAs; |  |  |  |  | C75-RI-002; C75 tophats; |  | C75 End dishes; RDL-02, RDT-06; | C75 End dishes; RDL-02, RDT-06; C75-J-002; L2-328; L2-140; L2-332; | HB-046 setup; | RDL-02, RDT-06 10u; | HPR1: OOC HPR2: SC-10 (4P) L2-281; |  | L2-281; |  |  | L2-118; L2-137; |  |  | L2-328; L2-140; L2-332; | D1: SIC C2K/T; D2: D3: Mag scan system L/C4K/T; D4: LSF5-1 C2K/T; D5: D6: FH3C C/T; D7: SC-12 thermal cycles/C4K; D8: L2-308 C2K/T/W; | J09R- FSS | J06R- Tuners, heat stations J09R- UCM Repair done | J21- Align CM in VV | J05- Wait 4 cantilever J19- Beam line work | C75-02- Remove waveguides, adjust wachs | J20- LERF- CM is aligned, PSS today J16- Ship Trav, ships Dec 6th, Shipping Trailer in
2019-12-04 | Wed |  |  | L2 BLA (x3); C75 HOM elbows (x 4) (1); |  |  | C75-RI-006; |  | C75 tophats; |  | C75-RI-002; C75 tophats; AMV cathodes; | C75-RI-002; HB-046; L2 BLA (x3) preclean; BLA kits (x4); C75 tophats; Test stand rods; SNS carts; | HB-046 30u; |  | HPR1: OOC HPR2: RDT-06; |  |  |  | L2-281; SC-10; |  |  | L2-118 & L2-137 sensors & HOMs; |  | D1: SIC C2K/T; D2: D3: Mag scan system warm/pull; D4: LSF5-1 C2K/T/W; D5: D6: FH3C C/T; D7: SC-12 C2K/T/W; D8: L2-308 warm | J09R- Idle | J06R- Tuners, heat stations J09R- UCM QC Alignment | J21- Align CM in VV, Move to WS5 | J05- Wait 4 cantilever, Move to WS4 J19- Beam line work | C75-02- Remove waveguides | J20- LERF- CM is aligned, Assemble cryo piping J16- Ship Trav, ships Dec 6th, Ship trailer in, Install caps
2019-12-05 | Thu |  | Nb Anneal | C75-J-005; C75-J-004; L2-bellows; JLEIC CC BT; |  |  | HB-046 probes; C75-RI-006; | RDT-06 | C75-J-005; C75-RI-002; |  | TE01NS-001 nitric; C75-RI-002; | TE01NS-001 ; C75-RI-002; L2 BLA (x3) to C/R; |  |  | HPR1: OOC HPR2: TE01NS-001 |  |  |  | L2 BLA (x3); | L2-281; SC-10; |  |  |  | D1: SIC C2K/T; D2: CPW L/C2K/T/W20K; D3: D4: LSF5-1 warm; D5: D6: FH3C warm; D7: SC-12 warm/pull; L2-137 L/C4K; D8: L2-308 pull; L2-118 L/C2K; | J09R- Idle | J06R- Tuners, heat stations J09R- UCM QC Alignment | J05- Remove from VV | J19- Beam line work, M-mounts J21- Prep for BL work/WC's/JT welding | C75-02- Remove waveguides | J20- LERF- CM is aligned, Assemble cryo piping/LC J16- Shipping caps, load into frame
2019-12-06 | Fri |  | L2-BLA (x3); | L2 Bellows; C75 Inner adapter; L2 BLA (x5); |  |  | C75-RI-007; | RDT-06 | C75-RI-002; C75-J-005; C75 inner adapter; |  | C75-RI-002; C75 inner adapter; Doglegs (x2); AMV Nb nuts; | HB-046 & HW; L2-BLAs; BLA kit & brackets; Pair1 Doglegs (x2); Pair2 Doglegs (x2); AMV HW; MS tools; |  |  | HPR1: OOC HPR2: C75-RI-005; C75-RI-002; |  | C75 end dishes; |  | L2 BLA (x3); TE01NS-001; | L2-281 Test stand; |  | L2-281; | L2-308 fast; L2-330 fast; | D1: SIC C2K/T; D2: CPW hold; D3: GC Heater Load; D4: LSF5-1 Pull/L/C4K/T; D5: D6: D7: L2-137 C2K/T/W; D8: L2-118 T/W; | J09R- Idle | J06R- Tuners, heat stations J09R- UCM QC complete | J05- grind shields | J19- Beam line work, M-mounts J21- Prep for BL work/WC's/JT welding | C75-02- Remove peripherals, Indium clean so far | J20- LERF- LC cryo piping J16- To SLAC…#13/21
2019-12-07 | Sat | [6 empty] | RDT-06
2019-12-08 | Sun | [6 empty] | RDT-06 | [6 empty] | HPR2: HB-046 (4P); |  | C75-RI-005; C75-RI-002; cage L2-330;
2019-12-09 | Mon |  | L2-BLA | L2-BLA; | C75-RI-008; |  | C75-RI-008; C75-RI-006; |  |  |  | C75-J-004; | C75-J-004; L2-330 wipe; L2-308 wipe; MC lines; |  |  | HPR1: OOC HPR2: C75-RI-005 (4P); C75-RI-002(4P); HB-046 (overnight); |  | HB-046; C75 prep; |  |  | L2 BLA (x3); TE01NS-001; SC-11; |  | SC-11; |  | D1: SIC C2K/T; D2: CPW C2K/T/W; D3: GC Heater cryo cooler test; D4: D5: D6: D7: L2-137 pull; L2-281 L/C2K; D8: L2-118 pull; water test L/T; | J09R- Idle | J06R- Tuners, heat stations J09R- UCM move to cantilever | J05- move to E. rail | J19- Beam line work, M-mounts J21- Prep for BL work/WC's/JT welding | C75-02- Remove peripherals, Indium clean so far | J20- LERF- LC cryo piping J16- To SLAC…#13/21
2019-12-10 | Tue |  | L2-BLA (x3) | L2-BLA; L2-bellows; C75-RI-008; | C75-RI-008; |  | C75-RI-006; | RGA change out; | BLA flange; C75-J-004; |  | L2-308 & L2-330 probe tips; AP Nb samples; | L2-308 & L2-330 parts; |  | C75-RI-008 setup; | HPR1: OOC HPR2: L2-330; |  | C75 prep; | clean dis L2-308, inspect three probes. Cage L2-308; | C75-RI-005; C75-RI-002; | L2 BLA (x3); |  | TE01NS-001; |  | PSS Cert AM D1: SIC C2K/T; D2: CPW pull; D3: GC Heater cryo cooler test; D4: D5: D6: TE01NS-001 L/SC4K; D7: L2-281 C2K/T/W; D8: water test T/W/pull; |  | J06- Tuners,FSS, Instrumentation, RF cables J09- UCM Alignment, move CS to WS3 | J05- Prep for BL bleed up, FSS | J19- Remove tophats, Install slam sticks, HOM sweep J21- Prep for BL work/WC's/HPT | C75-02- Continue disassy, parts for wachs | J20- LERF- Idle, running until Thursday
2019-12-11 | Wed |  | L2-BLA (x3) | C75-RI-006; L2 Bellows; |  |  | C75-RI-007; | AP samples 1000C/3h; |  |  | C75-J-004; | C75-J-004; C75 HOM elbows; C75-RI-006; BPM body; |  | C75-RI-008 75u; | HPR1: OOC HPR2: L2-308; L2-330; |  | L2-330; |  | HB-046 D5; | L2 BLAs (x3); |  |  |  | D1: SIC C2K/T; D2: D3: GC Heater cryo cooler test; D4: D5: D6: TE01NS-001 T/C2K/T/W; D7: L2-281 warm; D8:SC-11 L/C2K; |  | J05- Bleed up BL, FSS J09- Move CS to WS3, Unite to UCM | J06- FSS, Mag shields, Instrumentation, RF cables | J19- HOM sweep/Tune J21- Prep for BL work/WC's/Weld RT joint | C75-02- Continue disassy, parts for wachs | J20- LERF- Idle, running until Thursday J02- Prep for move RT CM21 Sat Dec.14th
2019-12-12 | Thu |  | L2-BLA (x3) | L2-BLA; C75-RI-007; JLEIC Cu tubes (x4); C75-RI-006; |  |  | C75-RI-006; |  |  |  | 3 HRS Scrubber Maint. (am) | C75-RI-008; BLA kits; | 3 HRS Scrubber Maint. (am) | 3 HRS Scrubber Maint. (pm); C75-RI-008 25u; | HPR1: OOC HPR2: 3 HRS Scrubber Maint.; RDT-06; L2-308; |  | L2-308; |  | L2 BLAs (x3); L2-330 D7/8; | C75-RI-005; C75-RI-002; L2-330; HB-046; L2 BLAs (x3); |  |  | L2-281 fast; | D1: SIC warm; D2: CPW L/C2K/T/W; D3: GC Heater cryo cooler test D4: D5: D6: D7: L2-281 pull; D8: SC-11 T/W; |  | J05- Bleed up BL, FSS J09- Unite to UCM | J06- Instrumentation, RF cables | J19- HOM sweep/Tune, ship trav J21- Prep for BL work/WC's/Weld RT joint | C75-02- Continue disassy, parts for wachs | J20- LERF- MLI, Shields J02- Prep for move Trailer back from SLAC-Unload
2019-12-13 | Fri |  | L2-BLA (x3) | C75-RI-007; HW Coax blank; L2-BLA (x3) |  |  | C75-RI-006; | C75-RI-008 450C/3h, 800C/3h; | C75 HOM elbows; |  |  | EIC1 hardware; |  |  | HPR1: OOC HPR2: EIC1; |  | J1.3-05 BPM HW swap; | L2-281 probes; | C75-RI-005 & C75-RI-002 D7/8; L2-308 D7/8; L2 BLAs (x3); RDT-06; | C75-RI-005 & C75-RI-002; | HB-046 120C/24h; | L2-330 HOMs & sensors; |  | D1: SIC hold; D2: CPW C2K/T/W; D3: GC Heater hold; D4: Magnetic Scanner L/C4K/T/W; D5: D6: D7: L2-330 L/C2K; D8: SC-11 warm; |  | J05- BPM Hardware replacement, FSS J09- Unite to UCM | J06- Instrumentation, RF cables | J19- Ship trav items J21- BL work/WC's/Weld RT joint | C75-02- Continue disassy, parts for wachs | J20- LERF- MLI, Shields, Ins vac bellows J02- Move to TL
2019-12-14 | Sat | [6 empty] | C75-RI-008 450C/3h, 800C/3h; | [12 empty] | HB-046 120C/24h; |  |  | D7: L2-330 T/HOM/W; | [5 empty] | RT CM21 Sat Dec.14th
2019-12-15 | Sun | [6 empty] | C75-RI-008 450C/3h, 800C/3h; | [15 empty] | D7: L2-330 warm;
2019-12-16 | Mon |  | FM Nb anneal; | JLEIC tubes; C75-RI-006; L2-BLA |  |  |  | C75-RI-008 troubleshoot; |  |  |  | L2-118 ext rinse; SC-14 & parts; MS warm L2 FPC parts; BLAs (x3) to C/R; |  |  | HPR1: OOC HPR2: |  | SC-14; |  | SC-10; EIC1 D3/4; | L2-308; |  | L2-308 HOMs and sensors; C75-RI-005 & C75-RI-002 mag & temp sensors; | L2-118 fast; | D1: SIC pull; D2: CPW hold; D3: GC heater pull; D4: Magnetic Scanner pull; D5: HB-046 L/C2K; D6: RDT-06 L/C2K/T; D7: L2-330 pull; L2-308 L/C4K; D8: SC-11 pull; C75-RI-005 & C75-RI-002 L/WDLC/pull; |  | J05- BPM pumpdown, FSS IP J09- Unite to UCM, fit 2 phase pipe | J06- FSS IP, HOM tuning Prep shields | J19- Ship trav items, ship alignment J21- BL work/MC Line RT GOOD | C75-02- Continue disassy, move cutter | J20- LERF- LC Ins vac J02- on UITF SNS HV Welding
2019-12-17 | Tue |  |  | JLEIC tubes; |  |  |  | C75-RI-008 450C/3h, 800C/3h; | C75-RI-006; C75 HOM elbows; |  | L2-118 probes; | L2-118 ext rinse; |  |  | HPR1: OOC HPR2: SC-14 (4P, ext spray); |  |  | L2-118 probe inspection; | TS28-007; | EIC1; L2 BLAs (x3); | SC-10 120C/24h; | EIC1; C75-RI-005 & C75-RI-002 leak check; |  | D1: SIC L/C2K/T; D2: CPW pull; D3: EIC1 L/SC4K; D4: D5: HB-046 T/W; D6: RDT-06 W20K/C2K/T; D7: L2-308 C2K/T/HOM/W; D8: C75-RI-005 & C75-RI-002 L |  | J05- BPM LC, FSS IP J09- Unite to UCM, fit 2 phase pipe | J06- FSS IP, HOM tuning Prep shields | J19- Ship trav items, inserts/caps J21- BL work/MC Line | C75-02- Continue disassy, move cutter | J20- LERF- LC Ins vac J02- on UITF SNS HV Welding
2019-12-18 | Wed |  |  | BNL ring lamination; L2-BLA; |  |  |  | C75-RI-008 450C/3h, 800C/3h; | C75 HOM elbows; C75-RI-006; |  | AP Nb samples; |  |  | C75-RI-008 setup; | HPR1: OOC HPR2: |  |  |  | SC-14 cart; L2 BLAs (x3); |  | SC-10 120C/24h; |  |  | D1: SIC C2K/T; D2: CPW L/C2K/T/W; D3: EIC1 SC4K/T/W; D4: D5: HB-046 warm; D6: D7: L2-308 warm D8: C75-RI-005 & C75-RI-002 WDLC/pull; |  | J05- BPM LC, FSS IP J09- Unite to UCM, fit 2 phase pipe | J06- FSS IP, HOM tuning Prep shields | J19- Ship trav items, inserts/caps J21- BL work/MC Line | C75-02- Continue disassy, move cutter | J20- LERF- LC Ins vac J02- on UITF SNS HV Welding
2019-12-19 | Thu |  |  | C75-002; JLEIC tubes (x2); L2-BLA; |  |  |  |  | C75 HOM elbows; C75-RI-006; |  |  | C75-RI-006; C75 HOM elbows; C75-RI-008; |  | C75-RI-008 30u; New HEP Install; | HPR1: OOC HPR2: |  | L2 BLAs (x3); |  |  | SC-14; L2 BLAs (x3); |  | SC-10 120C/24h; |  | D1: SIC C2K/T; D2: D3: EIC1 SC4K/T/W; D4: D5: HB-046 warm; D6: D7: L2-308 pull; TS28-007 L/thermal cycles; D8: |  | J05- BPM LC, FSS IP J09- Unite to UCM, fit 2 phase pipe | J06- FSS IP, HOM tuning Prep shields | J19- Ship trav items, inserts/caps J21- BL work/MC Line | C75-02- Continue disassy, move cutter | J20- LERF- LC Ins vac J02- on UITF SNS HV Welding
2019-12-20 | Fri |  |  | L2-BLA; BNL rings (x10); |  |  |  |  | C75 HOM elbows; C75-RI-006; |  |  |  |  | New HEP Install-3/1/20 | HPR1: OOC HPR2: |  | L2 BLAs (x3); | [6 empty] | CTF Kinney shut down (time TBD) D1: SIC D2: D3: EIC1 W; D4: D5: HB-046 pull; D6: D7: TS28-007 thermal cycles D8: |  | J05- Remove pump J09- Cav1 tuner, fit 2 phase pipe | J06- Checklist, lower shields | J21- BL work, testing cap | C75-02- Machine welds, REC open | J20- LERF- Valve off He suply J19- Ship caps
2019-12-21 | Sat
2019-12-22 | Sun
2019-12-23 | Mon
2019-12-24 | Tue
2019-12-25 | Wed
2019-12-26 | Thu
2019-12-27 | Fri
2019-12-28 | Sat
2019-12-29 | Sun
2019-12-30 | Mon
2019-12-31 | Tue
2020-01-01 | Wed
2020-01-02 | Thu |  | Injector heat treat; | L2 bellows; BNL rings (x10); |  |  |  |  | C75 HOM elbows; C75 dogleg; |  |  | BLA bag (x5); |  | New HEP Install-3/1/20 | HPR1: OOC HPR2: |  |  |  |  | L2 BLAs (x3); |  | C75 pair | HB-046 fast | D1: SIC hold; D2: D3: EIC1 hold; D4: D5: HB-046 pull; D6: D7: TS28-009 thermal cycles; D8: C75-RI-002, C75-RI-005 L/WDLC/C2K; |  | J05- FSS J09- Cav1 tuner, Weld 2 phase pipe | J06- Verify HOM's, weld shields | J21- Testing cap, Prep 4 bayonet box | C75-02- Machine welds, REC open | J20- LERF- u-tubes/cooldown tomorrow J19- Final measurements, shipping frame into TL
2020-01-03 | Fri |  | Injector heat treat; | C75-DL; L2-BLA; BNL lamination rings; | [6 empty] | C75 HOM elbows; C75 dogleg; Ceramic beads; | L2 BLA (x2); Lollipop parts; |  | New HEP Install-3/1/20 | HPR1: OOC HPR2: |  | cage HB-046 | HB-046 |  | L2 BLAs (x3); |  |  |  | D1: SIC? D2: D3: EIC1 pull; D4: D5: D6: D7: TS28-009 pull; D8: C75-RI-002, C75-RI-005 T/W (for desorp); |  | J05- FSS J09- Cav1 tuner, Weld 2 phase pipe | J06- MLI, Into VV | J21- bayonet box, prep for ion pump, weld restraint nuts | C75-02- Machine welds | J20- LERF- u-tubes/cooldown today J19- Load into frame, ships tomorrow
2020-01-04 | Sat | [22 empty] | 1.4 L/H/W
2020-01-05 | Sun
2020-01-06 | Mon |  | L2 BLA (x4); | C75-RI-006; |  | ` | C75-RI-007; |  | C75-RI-006; |  | C75 elbow; | lollipop parts; L2 string kit; L2 bellows; HB-046 parts; C75-RI-006; Girder (x2); cold FPC HW; C75 elbow; |  | New HEP Install-3/1/20 | HPR1: OOC HPR2: HB-046(2p) |  | L2 rail into CR; |  | L2 gate valve (x2); | L2 gate valve (x2); L2 FPCs (x4); L2 BLAs (x3); |  |  |  | CTF Maintenance Down; D1: D2: D3: D4: D5: D6: D7: D8: C75-RI-002, C75-RI-005 desorp; |  | J05- FSS J09- Weld 2 phase pipe | J06- Remove tooling, align | J21- bayonet box, add ion pump, weld restraint nuts | C75-02- Machine welds, open bridging areas | J19- Heading to SLAC CM02- WS6 Disassemble
2020-01-07 | Tue |  | L2 BLA (x4); | BNL EIC Rings; L2 BLAs; |  |  |  |  | C75-RI-007; |  | C75-RI-006; | L2 string prep; HB-049; |  | New HEP Install-3/1/20 | HPR1: OOC HPR2: HB-046; |  | HB-046; L2 lollipops; |  |  | L2 FPCs (x4); L2 BLAs (x3); |  |  |  | CTF Maintenance Down; D1: D2: D3: D4: D5: D6: D7: D8: C75-RI-002, C75-RI-005 warm; |  | J05- FSS J09- Weld 2 phase pipe/LC | J06- align CM in VV | J21- bayonet box/LC | C75-02- Machine welds, open bridging areas | J19- Heading to SLAC CM05- VV from BC CM02- WS6 Disassembl
2020-01-08 | Wed |  | L2 BLA (x4); | C75-Ceramics (x6); C75-RI-006; L2 BLAs; |  |  |  |  | C75-RI-007; |  |  | L2 string prep; L2-BLA x 4 to c/r; L2 Shipping Manifolds; L2 MC Vac HW; HE 9-cell parts; |  | New HEP Install-3/1/20 | HPR1: OOC HPR2: |  | BLA prep work; |  | HB-046 D5; | L2 BLAs (x3); |  |  | L2-5; L2-6; | CTF Maintenance Down; D1: D2: D3: D4: D5: D6: D7: D8: C75-RI-002, C75-RI-005 pull; |  | J05- Tune HOM's J09- Weld 2 phase pipe/LC, heat stations, magnet lead prep | J06- align CM in VV, move to WS5 | J21- Close VV, Inst flanges | C75-02- Machine welds, open bridging areas | CM02- WS6 Disassembl
2020-01-09 | Thu |  |  | L2 BLAs; C75-RI-006; |  |  |  | Ion gage replacement; HB-049 600C/10h; | C75-RI-007; |  |  | L2-5,6,7,8 ext rinse; L2 BLAs (x3) to furnace; L2 string prep; C75-RI-007; |  | New HEP Install-3/1/20 | HPR1: OOC HPR2: |  | RDT-05 mock assy; |  | L2 BLA (x3); |  |  |  | L2-7; L2-8; | CTF Maintenance Down; D1: D2: D3: D4: D5: D6: D7: D8: |  | J05- Tune HOM's J09- Weld 2 phase pipe/LC, heat stations, magnet lead prep | J06- align CM in VV, move to WS5 | J21- Close VV, Inst flanges | C75-02- Machine welds, open bridging areas | CM02- WS6 Disassembl
2020-01-10 | Fri |  | HKP feedthrough | L2 BLAs; C75 elbows; |  |  |  | HB-049 600C/10h; |  |  |  | L2 cages; L2-5,6,7,8 bolt holes; L2 string prep; |  | New HEP Install-3/1/20 | HPR1: OOC HPR2: |  | cage L2-1 through -4; |  |  | L2 BLA (x3); L2 FPCs; |  |  |  | CTF Maintenance Down; D1: SIC hold; D2: CPW pull; D3: Cryo cooler test L; D4: D5: D6: D7: D8: |  | J05- Tune HOM's J09- Weld 2 phase pipe/LC, heat stations, magnet lead prep | J06- align CM in VV, move to WS5 | J21- Close VV, Inst flanges | C75-02- Machine welds, open bridging areas | CM02- WS6 Disassembl
2020-01-11 | Sat | [6 empty] | HB-049 600C/10h;
2020-01-12 | Sun | [6 empty] | HB-049 600C/10h;
2020-01-13 | Mon |  | L2 BLAs (x3); | C75-DL; L2 BLAs; |  |  | C75-RI-007; HE-353; | HB-049; | CPB: BNL gun electrode; C75-RI-007; |  |  | RDT-05 and parts; C75-RI-007; |  | New HEP Install-3/1/20 | HPR1: OOC HPR2: |  |  |  | L2 BPM; | HB-046; L2 BLAs (x3); |  | HB-046; |  | CTF Maintenance Down; D1: SIC; D2: D3: Cryo cooler test; D4: D5: D6: D7: D8: |  | J09- Magnet heat stations, mag shields | J05- Verify HOM's, weld shields | J02- WS5 Remove WC's J06- Prep 4 beam line work, JT Welding | C75-02- Machine welds, open bridging areas, EC/CU's relocated | J21- CMTF, Ins Vac LC, Waveguides
2020-01-14 | Tue |  | L2 BLAs (x3); | C75 DL; L2-BLA; |  |  | HB-049; |  | CPB: BNL gun electrode; C75 Elbow; |  | C75-RI-007; | Superclamp parts; C75-RI-007; |  | New HEP Install-3/1/20 | HPR1: OOC HPR2: HE-353; |  | L2 Bellows stretching; L2 string magnetic hygiene; |  | L2 BPM; L2 US valve assy; |  |  |  |  | CTF Maintenance Down; D1: D2: D3: Cryo cooler test; D4: D5: D6: D7: D8: |  | J09- Magnet heat stations, mag shields | J05- Verify HOM's, weld shields | J02- WS5 Remove WC's J06- Prep 4 beam line work, JT Welding | C75-02- Machine welds, open bridging areas, EC/CU's relocated | J21- CMTF, Ins Vac LC, Waveguides
2020-01-15 | Wed |  | L2 BLAs (x3); L2 BLAs (x2)?; | C75-End dish (x2); L2-BLA; C75-RI-007; |  |  | C75-RI-001; |  | CPB: BNL gun electrode; C75 elbow; BLA; |  | C75 Elbow; half cell; Dogleg; | HE-353; Superclamp parts; L2 BLAs (x3); C75 elbow; Dogleg; FPC parts; Clamps; |  | New HEP Install-3/1/20 | HPR1: OOC HPR2: HE-353; |  | cage HB-049; HE-353; | C75CP01; |  | L2 BPM; HB-046; |  | HB-046; |  | CTF Maintenance Down; D1: D2: D3: Cryo cooler test; D4: D5: D6: D7: D8: |  | J09- Magnet heat stations, invar rods | J05- Align CM in VV | J02- Beamline work J06- GHRP cap, jumpers, JT Welding, WC's | C75-02- open bridging areas, EC/CU's relocated **REPOST CU ROOM, BEGIN GRINDING IN THE TECH SHOP** | J21- CMTF, Ins Vac LC
2020-01-16 | Thu |  | HP FT | JLEIC BT; C75-DL |  |  | C75-RI-001; |  | C75-RI-007; C75 elbow; CPB: BNL gun electrode |  | crab HC; C75-RI-007; C75 elbow; | HB-049; L2 BLA; Superclamp parts; C75-RI-007; C75 elbow; test stand parts; BLA kit; HE-353 flange; | HB-049 setup; | New HEP Install-3/1/20 | HPR1: OOC HPR2: HE-353 (4p); |  | HE-353; | C75CP01; | L2 BLA (x3); |  |  |  |  | CTF Maintenance Down; D1: D2: D3: Cryo cooler test; D4: D5: D6: D7: D8: HB-046 L/hold; |  | J09- Magnet heat stations, invar rods | J05- Align CM in VV, Move to WS5 | J02- Beamline work, Move to UITF J06- GHRP cap, jumpers, JT Welding, WC's | C75-02- open bridging areas, EC/CU's relocated | J21- CMTF, Ins Vac LC
2020-01-17 | Fri |  | 1200 Clean | Half wave coax blank; C75 end dish; |  |  | C75-RI-003; | maint | MAG-5 |  |  | Superclamp parts; HB-049; | HB-049 setup; | New HEP Install-3/1/20 | HPR1: OOC HPR2: RDT-05; |  |  | C75CP01; | L2 BLA (x3); HE-353; |  |  |  |  | CTF Maintenance Down; D1: D2: D3: Cryo cooler test; D4: D5: D6: D7: D8: HB-046 hold; |  | J09- LC ins vac; | J05- JT fit-up | J02- leak check cold coupler; J06- install WCS, high pressure test; | C75-02- open bridging areas, EC/CU's relocated | J21- CMTF, Ins Vac LC
2020-01-18 | Sat | [22 empty] | CTF Maintenance Down;
2020-01-19 | Sun | [22 empty] | CTF Maintenance Down;
2020-01-20 | Mon | [12 empty] | New HEP Install-3/1/20 | HPR1: OOC HPR2: L2-1; L2-2; |  |  |  |  | HE-353; |  |  |  | CTF Maintenance Down; D1: D2: D3: D4: D5: D6: D7: D8: HB-046 hold;
2020-01-21 | Tue |  | BLA X3 | C75-RI-007; |  |  | C75-RI-001; | maint | C75 elbow (x3); MAG-5; | FH SC; | C75 elbow (x3); | HB-049; Superclamp tooling; MS blanks; Rongli Test stand HW; HDIce tubes & blanks; C75 elbow (x3); | HB-049 30u; | New HEP Install-3/1/20 | HPR1: OOC HPR2: L2-3; L2-4; |  |  |  | L2-1; L2-2; |  |  |  |  | D1: SIC C4K/Software test/W; D2: D3: Cryo cooler test; D4: LSF5-1 L/C4K D5: D6: RDT-6 hold; D7: SC-10 L D8: HB-046 C2.1K; |  | J09- LC ins vac; | J05- Move to WS5 | J02- leak check cold coupler; J06- install WCS, high pressure test; | C75-02- open bridging areas, EC/CU's relocated | J21- CMTF, Ins Vac LC
2020-01-22 | Wed |  | BLA X3 | L2-BLA; C75 Hom loads; C75 elbow; |  |  | C75-RI-003; C75-RI-001; | maint | MAG-5; |  | Cu SOS brite cleaning; | L2 cold FPC parts; SNS HV rings (x6); MC lines & HW; JS baskets; |  | New HEP Install-3/1/20 | HPR1: OOC HPR2: L2-5; L2-6; |  |  |  | L2-3; L2-4; |  |  |  |  | CMTF cooldown; D1: SIC C2K/T; D2: Magnet test L/C4K/T; D3: Cryo cooler test; D4: LSF5-1 C2K (2) D5: D6: RDT-6 hold; D7: SC-10 C4K; (3) D8: HB-046 T/W; (1) |  | J09- Align CS to UCM | J02- Remove shields, move to WS3E | J05- WC's, HPT, JT welding J06- Install WC's, HPT, Testing cap | C75-02- Grind HV, Disassemble CU's | J21- CMTF, U-tubes 9am
2020-01-23 | Thu |  | BLA X3 Cu-Sample | C75-RI-001; C75 Hom loads; C75 elbow; RFD ceramics (x5) |  |  | C75-RI-003; | maint |  |  | MAG-5; | L2 BLA (x3) to c/rm; SNS HV rings; |  | New HEP Install-3/1/20 | HPR1: OOC HPR2: L2-7; L2-8; |  |  |  | L2-5; L2-6; |  | TS34-003 120C; |  |  | D1: SIC HOLD; D2: Magnet test HOLD; D3: Cryo cooler test; D4: LSF5-1 Warm/pull (PM); D5: D6: RDT-6 hold; D7: SC-10 C2K/T/W; D8: HB-046 warm; |  | J09- Tuners,mu shields, heat stations J02- flow hood | J02-Move to WS3 | J05- WC's, JT welding J06- Install MC Line,Testing cap | C75-02- Grind HV, Disassemble CU's | J21- CMTF, Cooldown
2020-01-24 | Fri |  | Cu SS; | C75 Doglegs; C75-End dish; |  |  |  | clean/test run |  | F4; |  | HWCoax-2; HB-049 parts; |  | New HEP Install-3/1/20 | HPR1: OOC HPR2: HB-049; HWCoax-2; |  |  | lollipops; | L2-7; L2-8; |  | TS34-003 120C; |  |  | D1: SIC C2K/T; D2: Magnet test; D3: Cryo cooler test; D4: maint; D5: D6: RDT-6 hold; D7: SC-10 warm/pull; D8: HB-046 pull; TS28-009 load; |  | J09- Tuners,Mu shields, heat stations J02- Flow hood, add turbo cart |  | J05- WC's, JT welding, Inst flanges J06- Install MC Line, Testing cap, LC 2 phase | C75-02- Grind HV, Disassemble CU's | J21- CMTF, Cooldown
2020-01-25 | Sat | [22 empty] | D8: TS28-009 C4K/W
2020-01-26 | Sun | [17 empty] | HWCoax-2;
2020-01-27 | Mon |  | Cu sample run; | L2-BLA; C75 Loads; RFD ceramics; |  |  | C75-RI-003 |  |  |  |  | L2 cold FPC parts; C75-RI-006; C75-RI-007; C75 cages; |  | New HEP Install-3/1/20 | HPR1: OOC HPR2: |  |  |  | RDT-05 superclamp; HE-353; | HE-353; HWCoax-2; |  |  |  | D1: SIC C2K/T; D2: Magnet test pull; TC L/C/T; D3: Cryo Cooler warm; D4: D5: D6: RDT-6 pull; C75 DL L/C4K/T/W; D7: SC-10 L/C4K; D8: TS28-009 thermal cycles; |  | J09- Tuners,Mu shields, heat stations J02- Add turbo cart |  | J05- JT welding, Inst flanges, MC Line J06- JT Welding, Install MC Line, Testing cap, LC 2 phase | C75-02- Grind HV, Disassemble CU's | J21- CMTF, Cooldown
2020-01-28 | Tue |  | Cu sample run; | C75-RI-001; C75 WG; C75 DL; |  |  | C75-RI-003; |  |  | F4; |  | C75 gate valves; L2 BLAs (x3); |  | New HEP Install-3/1/20 | HPR1: OOC HPR2: HB-049; |  | C75 inner adapter; HB-049; C75 end dish prep; |  | RDT-05 superclamp; | L2 BLA (x3); RDT-05 superclamp; J1.3-11R bag; HWCoax-2; |  | HE-353; |  | D1: SIC C2K/T; D2: TC pull; TC L/C/T; D3: Cryo Cooler pull; D4: D5: D6: C75 DL pull; D7: SC-10 C2K/T/W; D8: TS28-009 thermal cycles; |  | J09- Tuners,Mu shields, heat stations J02- Flow hood over Cav7, LC couplers Complete, UCM QC |  | J05- JT welding, Inst flanges, MC Line LC J06- Install MC Line, Testing cap, LC 2 phase | C75-02- Grind HV, Setup for Wach HV | J21- CMTF, Cooldown Complete
2020-01-29 | Wed |  | 1200C clean run; | C75 end dishes; C75 HOM loads; |  |  | LSF9-1; |  | C75 inner adapter; |  | Cu brite (SOS). | L2 BLA; |  | New HEP Install-3/1/20 | HPR1: OOC HPR2: 9-cell fit test (RG); |  |  |  | HB-049; C75 gate valves; | J1.3-11R; |  |  |  | D1: SIC C2K/T; D2: TC pull; D3: D4: Cryo Operator: Kushnick load; D5: D6: D7: SC-10 W/pull; HE-353 L/C4K; D8: TS28-009 thermal cycles; |  | J09- Tuners,Mu shields, heat stations J02- Flow hood over Cav7, LC couplers Complete, UCM QC |  | J05- JT welding, Inst flanges, MC Line LC J06- Install MC Line, Testing cap, LC 2 phase | C75-02- Grind HV, Setup for Wach HV | J21- CMTF, Cooldown Complete
2020-01-30 | Thu |  |  | C75 HOM loads; C75 DL; C75-RI-003; C75 inner adapter; |  |  | LSF9-1; |  | C75 inner adapter; |  | C75 end dish; C75 inner adapter; Nb sample 25u; | C75 HW; C75 DL; |  | New HEP Install-3/1/20 | HPR1: OOC HPR2: |  | C75 DL keyserts; String rollout!! |  | L2 BLA (x2); C75 gate valves; | HB-049; C75 gate valves; |  |  |  | Cryo Operator: Kushnick D1: SIC C2K/T; D2: D3: D4: RDT-5 C4K; D5: D6: D7: HE-353 C2K/T/W; D8: TS28-009 pull; HB-049 L/C4K; |  | J09- Tuners,Mu shields, heat stations J02- Flow hood over Cav7, LC couplers Complete, UCM QC |  | J05- JT welding, Inst flanges, MC Line LC J06- Install MC Line, Testing cap, LC 2 phase | C75-02- Grind HV, Setup for Wach HV | String rollout!! C75 end dish leak check; J21- CMTF, Cooldown Complete |  |  |  |  | Cryo Operator Day: David Swing: Justin
2020-01-31 | Fri |  |  | C75-RI-001; JLEIC tubes; Lamination rings; |  |  | LSF9-1; plamsa test stand spool and filter; C75-RI-008; | Tubes 900C/3h; |  |  | C75 HOM loads; | C75 inner adapter; C75 HW; |  | New HEP Install-3/1/20 | HPR1: OOC HPR2: |  | C75 gate valves; C75 strongback; C75 indium prep; C75 fastener prep; Mag field meas; |  | L2 BLA (x3); |  |  |  |  | RF Operator: Peter Owen Cryo Operator: Kushnick D1: SIC C2K/T; D2: D3: D4: RDT-5 C2K/T/W; D5: D6: D7: HE-353 W/P; D8: HB-049 C2K/T/W; |  | J09- Tuners,Mu shields, heat stations J02- Flow hood over Cav7, LC couplers Complete, UCM QC |  | J05- JT welding, Inst flanges, MC Line LC J06- Install MC Line, Testing cap, LC 2 phase | C75-02- Grind HV, Setup for Wach HV | [5 empty] | Cryo Operator Day: David Swing: Justin
2020-02-01 | Sat | [6 empty] | Tubes 900C/3h; | [21 empty] | J21- CMTF,
2020-02-02 | Sun | [6 empty] | Tubes 900C/3h; | [6 empty] | HPR2:
2020-02-03 | Mon |  | L2 BLAs (x3); | C75-RI-002; C75-RI-005; L2-BLA; |  |  | LSF9-1; | Tubes unload; | C75-J-005; |  |  | L2 CM shipping HW; C75-J-004 parts; |  | New HEP Install-3/1/20 | HPR1: OOC HPR2: C75-J-004; |  |  |  | SC-14; | L2 BLA (x3); |  |  |  | RF Operator: Christiana Cryo Operator: Kushnick CMTF Fast cooldown; D1: SIC W; D2: magnet test L; D3: D4: RDT-5 pull; D5: D6: D7: D8: HB-049 pull; | [10 empty] | Cryo Operator Day: Justin Swing: David
2020-02-04 | Tue |  | L2 BLAs (x3); | C75-RI-002; C75-RI-005; L2-BLA; |  |  | C75-RI-008; cage LSF9-1; J1.3-11R; |  | C75-J-005; |  |  | LSF9-1 parts; CEBAF girder; LSF9-1; |  | New HEP Install-3/1/20 | HPR1: OOC HPR2: C75-J-004; |  | C75-J-004; | HE-353; |  | SC-14; |  |  | L2 BLA (x3); | D1: SIC pull; D2: magnet test C4K/C2K/W; D3: D4: D5: D6: D7: D8: |  | J09- Tuners,Mu shields, heat stations J02- Flow hood over Cav7, LC couplers Complete, UCM QC |  | J05- JT welding, Inst flanges, MC Line LC J06- Install MC Line, Testing cap, LC 2 phase | C75-02- Grind HV, Setup for Wach HV | [5 empty] | Cryo Operator Day: Justin Swing: ?
2020-02-05 | Wed |  | L2 BLAs (x3); | C75-RI-002; C75-RI-005; |  |  | J1.3-11R; C75-J-005; |  | C75-RI-008; C75 elbows; |  | sample Nb 75u; C75 elbow; | L2 BLA (x3); CEBAF girder; |  | New HEP Install-3/1/20 | HPR1: OOC HPR2: nozzle change; LSF9-1; |  | C75 pair parts inspection; L2 BLA clean; |  | C75-J-004; | C75 HOM load test; |  | SC-14; |  | RF Operator: Liang Cryo Operator: Kushnick D1: D2: magnet test P/L/C4K/T/WT; D3: D4: D5: D6: D7: SC-14 L/thermal cycles; D8: |  | J09- Tuners,Mu shields, heat stations J02- Flow hood over Cav7, LC couplers Complete, UCM QC |  | J05- JT welding, Inst flanges, MC Line LC J06- Install MC Line, Testing cap, LC 2 phase | C75-02- Grind HV, Setup for Wach HV; 1/4 complete; |  |  |  | maint day; |  | Cryo Operator Day: Justin Swing: ?
2020-02-06 | Thu |  | Cu SOS; | C75-RI-005; C75 end dish; C75 HOM loads; |  |  | C75-RI-002; C75-RI-005: |  | C75-RI-008; C75-RI-002; C75 elbows; |  | TE1NS001; Nb Samples; C75 elbows; | HE-353 HW; HE-353 (2x USC, keep wet); C75 gate valves (x6); TE1NS001 parts; BLAs (x7) bag; Flanges; C75 elbows; |  | New HEP Install-3/1/20 | HPR1: OOC HPR2: LSF9-1; nozzle change; |  | LSF9-1; |  | L2 BLA (x3); | C75-J-004; |  |  |  | RF Operator: Kirk Davis; Cryo Operator: Kushnick D1: SIC L/C4K/T; D2: magnet test C2K/T/W4K/T/W; D3: D4: D5: D6: KEK-R5 L/C4K(10cm)/slow W; D7: SC-14 thermal cycles; D8: |  | J09- Tuners,Mu shields, heat stations J02- Flow hood over Cav7, LC couplers Complete, UCM QC |  | J05- JT welding, Inst flanges, MC Line LC J06- Install MC Line, Testing cap, LC 2 phase | C75-02- Grind HV, Setup for Wach HV; 2/4 complete; | [5 empty] | Cryo Operator Day: Justin Swing: ?
2020-02-07 | Fri |  | Cu SOS; | C75 HOM loads (x4); |  |  | J1.3-09 HOMs; |  | C75-RI-002; C75-RI-005; C75-RI-008; C75 elbows (x8); |  | C75-RI-002; C75-RI-008; C75 elbows; heater parts; | heater parts; C75-RI-002; C75-RI-008; C75 elbows (x10); SNS HV parts; FH Cu 1/2cells; |  | New HEP Install-3/1/20 | HPR1: OOC HPR2: clean up run; HE-353; TE1NS001; |  | C75 Gate Valves (x6) |  | LSF9-1; L2 BLA (x3); | C75 Gate Valves (x2); |  | C75-J-004 temp sensors; |  | RF Operator: Peter Owen; Cryo Operator: Kushnick D1: SIC C4K; D2: magnet test pull; D3: D4: D5: D6: D7: SC-14 thermal cycles/W; D8: C75-J-004 L/C4K; |  | J09- Tuners,Mu shields, heat stations J02- Flow hood over Cav7, LC couplers Complete, UCM QC |  | J05- JT welding, Inst flanges, MC Line LC, alignment; J06- Install MC Line, Testing cap, LC 2 phase | C75-02- Grind HV, Setup for Wach HV; 3/4 complete; | [5 empty] | Cryo Operator Day: Justin Swing: ?
2020-02-08 | Sat
2020-02-09 | Sun | [10 empty] | C75 HOM Loads; C75-RI-005; |  |  | HPR2: C75-RI-006; C75-RI-007;
2020-02-10 | Mon |  | L2 BLA (x3); | C75 HOM loads; C75-RI-002 (final insp); |  |  | J1.3-09 HOM; |  | C75-RI-005; C75-RI-008; |  | C75-RI-005; C75 elbows (x7); Nb covers; | L2 BLA HW kit; C75 HOM loads (x5); C75 HW; C75-RI-005; |  | New HEP Install-3/1/20 | HPR1: OOC HPR2: C75-RI-006 (4P); C75-RI-007 (4P); |  | C75-RI-006; C75-RI-007; |  |  | C75 Gate Valves (x2); L2 BLA (x3); LSF9-1; | SC-14 (120C/24h); |  |  | CTF Kinney Maint; CMTF Supply U-tube D1: SIC C4K; D2: RRR L/C/T; D3: D4: D5: D6: D7: D8: C75-J-004 C4K; |  | J02- Idle, waiting for decision, CC repair |  | J05- M-Mounts, HOM verification, final inst check, Close VV side port J06- LC 2 phase, Close VV, Ins Vac LC | C75-02- Remove cavity pair from HV | P1 Coming to Test Lab ~ 10 a.m.
2020-02-11 | Tue |  | L2 BLA (x3); | C75-RI-005 (final insp); C75-RI-002 (final insp); C75-RI-001; C75-RI-003; |  |  | C75-RI-001; C75-RI-003; |  |  |  | injector group Steel pipes HCl; | HW-Coax 2 & HW; |  | New HEP Install-3/1/20 | HPR1: OOC HPR2: maint; |  | HE-353; |  | C75-RI-006; C75-RI-007; |  | SC-14 (120C/24h); LSF9-1 120C/48h; |  |  | Cryo: Kushnick; RF: Powers; D1: SIC C/T; D2: RRR T/W; D3: D4: D5: D6: D7: D8: C75-J-004 hold/contamination; |  | J02- Idle, waiting for decision, CC repair |  | J05- M-Mounts, HOM verification, final inst check, Close VV side port J06- LC 2 phase, Close VV, Ins Vac LC | C75-02- Remove cavity pair from HV | SNS HV welding;
2020-02-12 | Wed |  | L2 BLA (x3); | C75-RI-005 (final insp); C75 end dishes; C75 elbows; |  |  | J1.3-09 homs; |  |  |  |  | L2 BLA (x3); |  | New HEP Install-3/1/20 | HPR1: OOC HPR2: HW COAX-2; |  | HE-353; |  | CEBAF girder; | C75-RI-006; C75-RI-007; | LSF9-1 120C/48h; |  |  | Cryo: Kushnick; RF: Liang; CMTF U-tubes D1: SIC C/T; D2: RRR warm; D3: MSF L/C4K; D4: D5: D6: D7: Thermal cycles L; D8: C75-J-004 warm 10K; | J11- Tack Ti sheets, LC 2 Phase piping | J02- Idle, Write Procedure | J09- hang lower shields, HOM verify, weld shields | J05- Move to WS6 J06- LC Ins Vac, FSS | C75-02- Remove cavity pair from HV | SNS HV welding; Remove U-tubes CMTF@ 9:30 |  |  |  |  | Cryo: David
2020-02-13 | Thu |  | inj degas; | C75 Doglegs; C75 inner adapter; C75-RI-005; |  |  |  |  | C75-RI-005; |  |  | L2 BLA parts; |  | New HEP Install-3/1/20 | HPR1: OOC HPR2: HE-353; |  |  |  | C75-RI-006; C75-RI-007; L2 BLA (x3); | C75 Gate Valves (x2); C75-RI-006; C75-RI-007; | LSF9-1 120C/48h; |  |  | Cryo: Kushnick; RF: Powers; D1: SIC C/T/W; D2: RRR W/T; D3: MSF pull; D4: D5: D6: D7: TC; D8: C75-J-004 warm; | J11- LC 2 Phase piping, MLI; | J02- Idle, Write Procedure | J09- Into VV | J05- Load into frame J06- warm FPC inst. | C75-02- Remove cavity pair from HV | SNS HV welding Remove CM21 from CMTF Shipping trailer into TL 8am |  |  |  |  | Cryo: David
2020-02-14 | Fri |  |  | C75 elbows; C75 HOM loads (x8); C75 End dish; | [6 empty] | C75-RI-005; | C75-RI-005; |  | New HEP Install-3/1/20 | HPR1: OOC HPR2: TE1NS001; |  |  |  | HW COAX-2; HE-353; L2 BLA (x3); | C75-RI-006; C75-RI-007; |  | LSF9-1 ; |  | Cryo: Kushnick; RF: Owen; D1: SIC pull; D2: RRR pull; D3: D4: D5: D6: D7: TC; D8: C75-J-004 pull/maint; | J11- LC 2 Phase piping, MLI, Mag Shields | J02- Idle, Write Procedure | J09- Align CM in VV | J05- ship to SLAC J06- Move into CMTF J21- prep for ship | C75-02- Remove cavity pair from HV | SNS HV welding |  |  |  |  | Cryo: David
2020-02-15 | Sat | [17 empty] | C75-RI-006; C75-RI-007;
2020-02-16 | Sun | [18 empty] | C75-RI-006; C75-RI-007;
2020-02-17 | Mon |  | maint | [5 empty] | C75 inner adapter; | P3 HEP; | C75 end dishes; | HB-50; MS vented bolts (x8); C75 inner adapter; |  | New HEP Install-3/1/20 P3 HEP; | HPR1: OOC HPR2: |  | C75 rail setup; C75 stack-up; C75 inner adapter; TS16-001 maint; |  | TE1NS001 | L2 BLA (x3); C75 gate valves; HE-353; |  | C75-RI-006; C75-RI-007; HE-353; |  | Cryo: Kushnick; RF: Christiana; D1: D2: D3: D4: MFS L; D5: D6: D7: TC pull; C75-RI-006 & C75-RI-007 L; D8: | J11- LC 2 Phase piping, MLI, Mag Shields | J02- Idle, Write Procedure | J09- Move to WS5 | J21- prep for ship, Prep beam line work | C75-02- Remove cavity pair from HV | SNS HV welding |  |  |  |  | Cryo: David
2020-02-18 | Tue |  | 1200C clean BB; | C75 Inner adapter; C75 Loads; |  |  |  | HB-50; |  |  | C75 inner adapter; | C75 doglegs; C75 inner adapter; |  | New HEP Install-3/1/20 | HPR1: OOC HPR2: |  | C75 end dishes; |  |  | C75 end dishes; |  |  |  | CMTF U-tubes 11am; Cryo: Kushnick; D1: D2: D3: D4: MFS C4K; D5: D6: D7: C75-RI-006 & C75-RI-007 WDLC/C4K (1); D8: LSF9-1 L/C4K (2); | J11- LC 2 Phase piping, MLI, Mag Shields | J02- Idle, Write Procedure |  | J09- WC's, JT welding J21- prep for ship, Prep beam line work | C75-02- Remove cavity pair from HV | SNS HV welding |  |  |  |  | Cryo: David
2020-02-19 | Wed |  | BB maint. | C75 Dogleg; C75 elbows; |  |  |  | HB-50; |  |  |  | C75 HOM loads; C75 Fasteners; Pump drops (x4); |  | New HEP Install-3/1/20 | HPR1: OOC HPR2: |  | cage C75-RI-002; cage C75-RI-005; |  |  | CEBAF girder; |  |  |  | Cryo: Kushnick; RF: Liang; D1: SIC L; D2: D3: HE TC L; D4: MFS W/pull; D5: D6: D7: C75-RI-006 / C75-RI-007 C2K/T/W (1); D8: LSF9-1 C2K/T (2); |  | J02- Idle, Write Procedure |  | J09- WC's, JT welding J21- prep for ship, Prep beam line work | C75-02- Remove cavity pair from HV | SNS HV welding |  |  |  |  | Cryo: David
2020-02-20 | Thu |  | BB maint. | C75-RI-008; C75 Load; |  |  |  | HB-50; |  |  | Cu weld prep; | C75-RI-002; C75-RI-005; C75 elbows; MC lines; BLA vales; |  | New HEP Install-3/1/20 | HPR1: OOC HPR2: |  | roughing pump maint.; C75 pair prep.; |  | BLA rework; |  |  |  |  | Cryo: Kushnick; RF: Powers; D1: SIC hold; D2: D3: HE TC C; D4: maint D5: D6: D7: C75-RI-006 / C75-RI-007 C2K/T/W; D8: LSF9-1 C2K/T |  | J02- Idle, Write Procedure |  | J09- WC's, JT welding J21- prep for ship, Prep beam line work | C75-02- Remove cavity pair from HV | SNS HV welding
2020-02-21 | Fri |  | BB maint. | C75-RI-001; |  |  | HB-50; |  | C75-RI-008; |  | HE rolled tubes; | BLA (x2); |  | New HEP Install-3/1/20 | HPR1: OOC HPR2: C75-RI-002 (4P); C75-RI-005 (4P); |  | C75 pair prep.; | HB-049 uncage; | L2 BLA rework; |  |  |  |  | C2 test CTF; D1: SIC C4K/T; D2: D3: Flux tubes TC C; D4: D5: D6: D7: C75-RI-006 / C75-RI-007 C2K/T/W; D8: LSF9-1 C2K/T |  | J02- Idle, Write Procedure |  | J09- WC's, JT welding J21- prep for ship, Prep beam line work | C75-02- Remove cavity pair from HV | SNS HV welding
2020-02-22 | Sat
2020-02-23 | Sun
2020-02-24 | Mon |  | BB maint. | C75-RI-001; |  |  | HB-50; |  | C75-RI-008; |  | Nb sample chamber and plates; C75-RI-008; | L2 warm FPC kit; C75-RI-008; |  | New HEP Install-3/1/20 | HPR1: OOC HPR2: |  |  |  | C75-RI-002/ C75-RI-005; | HW Coax2; TE1NS-001; |  |  |  | D1: SIC C4K; D2: D3: Flux tubes pull; D4: D5: D6: D7: C75-RI-006 / C75-RI-007 W/desorb/W; D8: LSF9-1 pull; |  | J02- Idle, Write Procedure |  | J09- WC's, JT welding J21- prep for ship, Prep beam line work | C75-02- Remove cavity pair from HV | SNS HV welding
2020-02-25 | Tue |  | BB maint. | C75 HOM loads; C75-RI-001; C75-RI-003; C75-RI-008; L2-BLA; RFD braze samples; JLEIC tubes; Lamination rings; |  |  | HB-50; |  | maint; |  |  | L2 warm FPC kit; |  | New HEP Install-3/1/20 | HPR1: OOC HPR2: |  | cage HB-50; |  | HW Coax2; | L2 BLA rework; L2 FPCs; C75-RI-002/ C75-RI-005; HW Coax2; |  | TE1NS-001; |  | Cryo: Kushnick; RF: Powers D1: SIC hold; D2: D3: Flux tubes L/TC; D4: D5: D6: TE1NS-001 L/SC4K; D7: C75-RI-006 / C75-RI-007 pull; C75-J-004 L/C4K; D8: LSF9-1 L/C4K |  | J02- Idle, Write Procedure |  | J09- WC's, JT welding J21- prep for ship, Prep beam line work | C75-02- Remove cavity pair from HV | SNS HV welding |  |  |  |  | Cryo: Dave
2020-02-26 | Wed |  | BB maint. | C75 lapping plates; C75 Doglegs; |  |  | C75-RI-001; |  |  |  |  | HB-50; RDT-05 and frame; | HB-50 setup; | New HEP Install-3/1/20 | HPR1: OOC HPR2: |  |  |  |  | C75-RI-002/ C75-RI-005 tophat install; |  |  |  | D1: SIC warm; D2: Magnet L/C4K/T/W; D3: Flux tubes TC/W; D4: D5: D6: TE1NS-001 T/C2K; D7: C75-J-004 C4K; D8: LSF9-1 C2K/test stand leaks/W; | J11- String Idle, Draft Procedure, weld tests | J02- CMA Procedure out 4 review |  | J09- MC Line,beam pipe work, HPT J21- prep for ship, beamline work | C75-02- Need strongback to continue | SNS HV welding Safety stand down
2020-02-27 | Thu |  | Witness samples; | C75-RI-008; HEP housing; | [6 empty] | C75 elbows; Witness samples; | RDT-05 and frame; HB-50; C75 HV x2; | HB-50 30u; | New HEP Install-3/1/20 | HPR1: OOC HPR2: |  |  |  |  | C75-RI-002/ C75-RI-005; CEBAF girder (x2); |  |  |  | D1: SIC pull; D2: Magnet warm; D3: Flux tubes pull; MFS L/SC4K/W; D4: Flux tubes L/TC/W; D5: D6: TE1NS-001 C2K/T/W; D7: C75-J-004 C2K/T/W; D8: LSF9-1 P/L; | J11- String Idle, Draft Procedure, weld tests | J02- CMA Procedure out 4 review |  | J09- MC Line LC,beam pipe work, HPT J21- Move to WS6, Signing party/Cake 2pm | C75-02- Need strongback to continue | SNS HV welding
2020-02-28 | Fri |  | maint | HEP flange; | [6 empty] | Flux tubes; Witness Samples; C75 blanks; | C75-RI-008 and HW; Flux tubes; Super clamps; C75 HV end groups; |  | New HEP Install-3/1/20 | HPR1: OOC HPR2: RDT-05; C75-RI-008 (4P); |  | cage C75-RI-008; | [6 empty] | D1: D2: Magnet P/L/C4K/C2K/T; D3: MFS pull; D4: Flux tubes W/P; D5: D6: TE1NS-001 W; D7: C75-J-004 warm; D8: LSF9-1 P/maint/L/C2K/T; | J11- String Idle, Draft Procedure, weld tests | J02- CMA Procedure out 4 review |  | J09- MC Line LC,beam pipe work, HPT | C75-02- Need strongback to continue J21- Tune HOM's, Shipping Trav. | SNS HV welding
2020-02-29 | Sat
2020-03-01 | Sun
2020-03-02 | Mon |  | BB maint. | C75 Elbows; C75-RI-006/C75-RI-007; |  |  | HE-349; | Flux tubes; |  |  | Nb samples chambers; | MS RA valves (x6); C75-03 CP1; HE-349 parts; |  | New HEP Install-3/1/20 | HPR1: OOC HPR2: RDT-10; |  | cage HE-349; |  | C75-RI-008; |  |  | C75-RI-002/C75-RI-005 |  | Fast Cooldown D1: SIC L D2: Magnet hold; D3: D4: D5: D5-->D8 D6: TE1NS-001 pull D7: C75-J-004 pull; C75-RI-002/C75-RI-005 L; D8: LSF9-1 C2K/T; | J11- String Idle, Draft Procedure, weld tests | J02- Remove UCM |  | J09- beam pipe work, RF Waveguides | C75-02- Need strongback C75-01- Prepare for 1st pair J21- Shipping Trav. CM21 Signing party/Cake 2pm | SNS HV welding
2020-03-03 | Tue |  | BB maint | C75-RI-006/C75-RI-007; |  |  |  | Flux tubes; |  |  | HEP Align | HE-349 (2x USC); C75 tuner plates; |  | New HEP Install-3/1/20 | HPR1: OOC HPR2: |  |  | C75-03 CP1 dis; | RDT-10; RDT-05; | C75-RI-008; RDT-10; CEBAF girder; |  |  |  | D1: SIC C4K D2: Magnet Test L/C4K/T/W; D3: D4: D5: D6: D7: C75-RI-002/C75-RI-005 WDLC/C4K; D8: LSF9-1 C2K/T/W; | J11- String Idle, weld tests, remove 2 phase piping and magnet | J02- Remove UCM |  | J09- beam pipe work, RF Waveguides, Install testing cap | C75-02- Need strongback C75-01- Prepare for 1st pair J21- Shipping Trav. | SNS HV welding
2020-03-04 | Wed |  | BB maint. | C75-RI-006/C75-RI-007; C75 Elbows; C75 Inner adapter; C75 End dishes; C75 HOM loads; C75-RI-001; C75-RI-003; JLEIC tubes; Lamination rings; |  |  | HE-364 Tune; C75-RI-008 disassy; C75-J-005 set probes; |  | C75 elbows; |  |  |  |  | New HEP Install-3/1/20 | HPR1: OOC HPR2: HE-349; |  |  | C75-03 CP1 dis; |  | C75-RI-008 failed LC; CEBAF girder #1; L2 BLA; |  | RDT-10; |  | Cryo Operator: Kushnick; RF Operator: Liang; D1: SIC C2K/T; D2: Magnet Test P/L/C4K; D3: D4: D5: D6: RDT-10 L/SC4K/T; D7: C75-RI-002/C75-RI-005 C2K/T; D8: LSF9-1 W; | J11- String Idle, weld tests, remove 2 phase piping and magnet | J02- Remove UCM |  | J09- beam pipe work, RF Waveguides, Install testing cap | C75-02- Need strongback C75-01- Prepare for 1st pair J21- Shipping Trav. | SNS HV welding Plasma Cart welding;
2020-03-05 | Thu |  | BB maint | C75-RI-006/C75-RI-007; |  |  | C75-J-005 set probes; |  | C75 elbow; C75-J-005; |  | HE-349 probe; | C75 HV headers (x4); S/S tubing; C75-J-005; C75 elbow; |  | New HEP Install-3/1/20 | HPR1: OOC HPR2: HE-349; |  | HE-349; |  |  | CEBAF girder #2; L2 BLA; |  | HE-353 sensors; |  | D1: SIC C2K/T; D2: Magnet Test C2K/T/W; D3: D4: D5: D6: RDT-10 T/C2K/T/W; D7: C75-RI-002/C75-RI-005 HOM survey/W; D8: LSF9-1 pull; HE-353 L/C4K; | J11- String Idle, weld tests, remove 2 phase piping and magnet | J02- HOLD |  | J09- beam pipe work, RF Waveguides, Install testing cap | C75-02- HOLD C75-01- Prepare for 1st pair J21- on trailer | SNS HV welding Plasma Cart welding;
2020-03-06 | Fri |  | witness run; | C75-RI-006/C75-RI-007; |  |  |  |  | C75 blanks; |  | C75 elbows; S/S tubing; | S/S tubing; C75 elbow; TE1NS-001; |  | New HEP Install-3/1/20 | HPR1: OOC HPR2: SC-10 (training); |  |  | C75-RI-008; | HE-349; |  |  |  |  | Supply U-tube removal (pm) D1: SIC C2K/T; D2: magnet test pull; D3: D4: D5: D6: RDT-10 W4K/T/W; D7: C75-RI-002/C75-RI-005 warm/desorb/warm; D8: HE-353 C2K/T/W; | J11- String Idle, weld tests, remove 2 phase piping and magnet | J02- Move to WS5 |  | J09- beam pipe work, RF Waveguides, Install testing cap | C75-02- dis pair #3 C75-01- Prepare for 1st pair J21- on trailer | SNS HV welding Plasma Cart welding;
2020-03-07 | Sat
2020-03-08 | Sun
2020-03-09 | Mon |  | witness run; | C75-RI-001 |  |  |  |  | C75 blanks; |  | C75-RI-008; C75 blanks; L2-536 FP & HOMs; | LSF9-1 car wash in cage; C75-02 CP2; LSF9-1 bottom flange/HW; C75-RI-008; L2-536 (x2) & HW; C75 HV rings; Superclamp tooling; |  | New HEP Install-3/1/20 | HPR1: OOC HPR2: TE1NS-001 |  | TS28-011 2-3/4 gasket replacement; | LSF9-1 vent and remove from TS28-011; L2-536 dis; |  | HE-349; | HE-349 120C/24h; |  |  | CMTF U-tubes, CTF C2 clean-up run (am); D1: SIC C2K/T; D2: magnet test L/C4K/T; D3: D4: D5: D6: D7: C75-RI-002/C75-RI-005 pull; SC-14 L/C4K; D8: HE-353 warm; | J11- String Idle, weld tests |  |  | J09- 2 Phase LC, Close ins vac/LC J02- Prep for CC R&R | C75-02- dis pair #3 C75-01- Prepare for 1st pair P1- Assemble End Can stands, complete grinding of bridging rings | SNS HV welding Plasma Cart welding
2020-03-10 | Tue |  | witness run; | C75-RI-003 |  |  | C75-RI-008; IA-339; |  |  | SC-10 | Uttar Nb parts; Nb sample; | Superclamp tooling; cavity pair manifold; KM cavity components; C75-02 CP2; |  | New HEP Install-3/1/20 | HPR1: OOC HPR2: LSF9-1 (3P); L2-536; | [5 empty] | HE-349 120C/24h; |  |  | D1: SIC C2K/T; D2: magnet test C2K/T; D3: D4: D5: D6: D7: SC-14 C2K/T/W; D8: HE-353 pull; C75-RI-002/C75-RI-005 L/WDLC/P; | J11- String Idle, weld tests |  |  | J09- 2 Phase LC, Close ins vac/LC J02- Prep for CC R&R | C75-02- dis pair #3 C75-01- Receive 1st pair, add fluxgates P1- Complete grinding of bridging rings J06- Remove from CMTF | SNS HV welding Plasma Cart welding
2020-03-11 | Wed |  | maint | C75 HOM loads; C75 elbow; |  |  | C75-RI-008; IA-335; |  | C75-RI-001; C75-J-005; |  | C75-J-005; C75-RI-008; | Superclamp tooling; C75-RI-008; Plasma parts; |  | New HEP Install-3/1/20 SC-10 setup; | HPR1: OOC HPR2: TE1NS-001; L2-536; |  | L2-536; |  | LSF9-1; TE1NS-001; |  |  | HE-349; |  | D1: SIC C2K/T; D2: magnet test P/L/C4K/T/W; D3: D4: D5: D6: D7: SC-14 warm; D8: heater maint; ; | J11- String Idle, weld tests |  |  | J09- Into CMTF J02- Prep for CC R&R | C75-02- dis pair #4 C75-01-Add fluxgates, demag parts P1- Complete grinding of bridging rings J06- WS6 (shipping) | SNS HV welding Plasma Cart welding
2020-03-12 | Thu |  | L2-BLAs - Repair C75 Windows Test x3 | C75-RI-003 C75 End dishes; C75 HOM loads; L2-BLAs; C75 elbows; JLEIC tubes; |  |  |  |  | C75-RI-001; |  |  | L2-gauge manifold; C75 HV; SC-10 parts; |  | New HEP Install-3/1/20 SC-10 10u; | HPR1: OOC HPR2: C75-RI-008 (4pass); |  |  |  | L2-536; | LSF9-1; TE1NS-001; C75 dogleg; |  |  |  | VTA Elect. work AM; D1: SIC C2K/T; D2: magnet test C4K/T/C2K/T/W; D3: MFSS L; D4: D5: D6: D7: SC-14 pull; C75-RI-002/C75-RI-005 L/C2K D8: HE-349 L\C4k | J11- String Idle, install tuner on test vessel |  |  | J06- WS6 to WS5, Add flow hood, install M-mounts, measure HOM's J02- Prep for CC R&R | C75-02- Idle C75-01- demag parts, Install tuners P1- Open bridging rings J09- Prep for Cool down | SNS HV welding LCLS Shipping Tailer returns Plasma Cart welding
2020-03-13 | Fri |  | L2-BLAs - Repair C75 Windows Test x3 Clean Run | C75 End-Dish C75 Elbows |  |  | C75-RI-003 |  |  | SC-10; | C75-RI-001; Brazing fixture; | C75-RI-001; |  | New HEP Install-3/1/20 | HPR1: OOC HPR2: SC-10 |  |  | C75-02 CP2; | C75-RI-008; | LSF9-1; L2-536; |  | TE1NS-001 |  | CMTF U-tubes; D1: SIC C2K/T; D2: magnet test pull; D3: MFSS C4K/T/W/SC4K/T/W; D4: D5: D6: TE1NS-001 L/SC4K/T; D7: C75-RI-002/C75-RI-005 slow warm; D8: HE-349 C4K; | J11- String Idle, exercise tuner on test vessel |  |  | J06- Beam line work, Post test, tune HOM's J02- Prep for CC R&R | C75-02- Idle C75-01- Install tuners P1- Disconnect beampipes J09- U-tubes, cool down | SNS HV welding Plasma Cart welding
2020-03-14 | Sat |  | Clean run
2020-03-15 | Sun
2020-03-16 | Mon |  | L2-BLA (x2); | C75-RI-001; C75 elbows; |  |  | C20 pair dis |  | C75-RI-003; HE Nb tubes; |  | Nb sample 10u; | RDT-05; C75 HV; |  | P3 Setup; | HPR1: OOC HPR2: |  |  |  | SC-10 D7/8; | LSF9-1; C75-RI-008; |  | L2-536; LSF9-1; |  | CMTF pump to 2K; D1: SIC D2: C75 DL D3: MFSS hold D4: D5: D6: TE1NS-001 C2K/T/W; D7: C75-RI-002/C75-RI-005 desorb/W; D8: HE-349 hold; | J11- String Idle; |  |  | J06- Beam line work, Post test, tune HOM's J02- Prep for CC R&R | C75-02- Wait on S.B. C75-01- Install tuners P1- Disconnect beampipes | SNS HV welding Plasma Cart welding
2020-03-17 | Tue |  | L2-BLA (x2); | C75 elbows; C75 HOM loads; C75-J-005 flange insp; |  |  | C75-J-005; |  | C75-RI-003; C75 elbows (x2); HE Nb tubes; |  |  | HB-046; L2 Clamps & Blanks; C75-RI-003; C75 elbows (x2); |  | P3 EP testing; | HPR1: OOC HPR2: |  | cavity pair manifold; HB tooling; | C75-RI-008; |  | SC-10 D7/8; | SC-10 120C/24h; |  |  | VTA Elect. work AM D1: SIC warm; D2: C75 DL C4K; D3: MFSS hold D4: D5: D6: TE1NS-001 warm; D7: C75-RI-002/C75-RI-005 pull, LSF9-1 L/C2K/T; D8: HE-349 C2K/T; | J11- Remove SPQA, Cold coupler heat stationing, and 2 phase piping |  |  | J06- Beam line work, Post test J02- Prep for CC R&R | C75-02- Wait on S.B. C75-01- Install tuners P1- Remove End Cans, Move CM to WS2E, retrieve tooling from Warehouse | SNS HV welding 1st one complete C75-J-005 mini-CF weld to tube; Plasma Cart welding
2020-03-18 | Wed |  | L2-BLA (x2); | C75 Doglegs; |  |  |  |  | HE Nb tubes; |  | C75-J-005; C75 elbows (x2); | C75-J-005 & parts; L2-BLA (x2); HIPIMS tubes; |  | 5 cell EP setup; | HPR1: OOC HPR2: C75-J-005 (4pass); |  | TS28-006; | C75-RI-002/C75-RI-005 prep for passout; | HB-046 TS34-003; |  | SC-10 120C/24h; |  |  | D1: SIC hold; D2: C75 DL C4K/T/W; D3: MFSS hold; D4: Flux Expulsion tubes L/Thermal Cycles; D5: D6: TE1NS-001 hold; D7: LSF9-1 W; D8: HE-349 C2K/T/W; | J11- Ready to move to CR |  |  | J06- Beam line work, Prep for shipping J02- Prep for CC R&R | C75-02- Wait on S.B., remove final CP C75-01- Install tuners P1- Retrieve tooling from Warehouse
2020-03-19 | Thu |  |  | L2 BLAs; C75 elbows; C75 HOM loads; |  |  | C20 CP2 dis |  |  |  | C75 indium (2x); C75-RI-003; | C75-RI-003; |  | 5 cell EP testing; | HPR1: OOC HPR2: |  |  |  | C75-J-005; |  |  |  |  | D1: SIC hold; D2: D3: MFSS hold (pull?); D4: Flux Expulsion tubes hold; D5: D6: TE1NS-001 pull; D7: LSF9-1 pull; L2-536 L/C4K; D8: HE-349 warm; | J11- Ready to move to CR |  |  | J06- Beam line work, Prep for shipping J02- Prep for CC R&R | C75-02- Wait on S.B., remove final CP C75-01- Install tuners P1- Retrieve tooling from Warehouse, Install tooling onto rail
2020-03-20 | Fri | leak check |  | C75-RI-003; |  |  |  |  | C75 elbows (x2); |  | C75-RI-008 (nitric); | L2 shipping manifold; C75-RI-008; C75 elbows (x2); |  | 5 cell EP testing; New HEP maint; | HPR1: OOC HPR2: |  |  | C75-J-005 (bottom flange); |  | C75-J-005 (conflat leaked); |  |  | C75-J-005; | D1: SIC hold; D2: D3: D4: Flux Expulsion tubes hold; D5: D6: D7: L2-536 C2K/T/W; D8: HE-349 hold (pull?); C75-J-005 L/C4K; | J11- Ready to move to CR |  |  | J06- Prep for shipping, move to WS6 J02- Prep for CC R&R | C75-02- Remove final CP, prep HV C75-01- Install tuners P1- Install lollipops, remove WG heat stations
2020-03-21 | Sat
2020-03-22 | Sun
2020-03-23 | Mon |  |  | C75 Doglegs; C75 end dishes; L2-BLA; C75-RI-002/C75-RI-005; C75-RI-003; | [9 empty] | New HEP Install; 9-cell alignment tests; | HPR1: OOC HPR2: C75-J-005; |  |  |  |  | L2-BLA (x2); |  |  |  | CMTF fast cooldown; D1: D2: D3: D4: D5: HB-046 C2K/T/W; D6: D7: L2-536 pull; D8: | J11- Ready to move to CR |  |  | J06- Prep for shipping, move to WS6 J02- Prep for CC R&R | C75-02- Remove final CP, prep HV C75-01- Install tuners P1- Install lollipops, remove WG heat stations
2020-03-24 | Tue | [12 empty] | New HEP Install; | HPR1: OOC HPR2: |  |  |  |  | L2-BLA RGA (x2); |  |  |  | D1: D2: D3: D4: D5: D6: D7: D8:
2020-03-25 | Wed | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-03-26 | Thu | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-03-27 | Fri | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-03-28 | Sat
2020-03-29 | Sun
2020-03-30 | Mon | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-03-31 | Tue | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-04-01 | Wed | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-04-02 | Thu | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-04-03 | Fri | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-04-04 | Sat
2020-04-05 | Sun
2020-04-06 | Mon | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-04-07 | Tue | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-04-08 | Wed | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-04-09 | Thu | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-04-10 | Fri | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-04-11 | Sat
2020-04-12 | Sun
2020-04-13 | Mon | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-04-14 | Tue | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-04-15 | Wed | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-04-16 | Thu | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-04-17 | Fri | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-04-18 | Sat
2020-04-19 | Sun
2020-04-20 | Mon | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-04-21 | Tue | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-04-22 | Wed | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-04-23 | Thu | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-04-24 | Fri | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-04-25 | Sat
2020-04-26 | Sun
2020-04-27 | Mon | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-04-28 | Tue | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-04-29 | Wed | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-04-30 | Thu | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-05-01 | Fri | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-05-02 | Sat
2020-05-03 | Sun
2020-05-04 | Mon | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-05-05 | Tue | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-05-06 | Wed | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-05-07 | Thu | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-05-08 | Fri | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-05-09 | Sat
2020-05-10 | Sun
2020-05-11 | Mon | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-05-12 | Tue | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-05-13 | Wed | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-05-14 | Thu | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-05-15 | Fri | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-05-16 | Sat
2020-05-17 | Sun
2020-05-18 | Mon | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-05-19 | Tue | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-05-20 | Wed | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-05-21 | Thu | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-05-22 | Fri | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-05-23 | Sat
2020-05-24 | Sun
2020-05-25 | Mon | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-05-26 | Tue | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-05-27 | Wed | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-05-28 | Thu | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-05-29 | Fri | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-05-30 | Sat
2020-05-31 | Sun
2020-06-01 | Mon | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-06-02 | Tue | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-06-03 | Wed | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-06-04 | Thu | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-06-05 | Fri | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-06-06 | Sat
2020-06-07 | Sun
2020-06-08 | Mon | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-06-09 | Tue | [10 empty] | Injector parts; |  | New HEP Install; | HPR1: OOC HPR2: Cleanup Run | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8: | CM11 Prep for CR | Prep UCM for reuse |  |  |  | LCLSII CM06-Shipping Alignment |  | Relocate rail from Blue Crab
2020-06-10 | Wed | [5 empty] | HE-353 BP; |  | HE samples; |  | Injector parts; | Injector parts; |  | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8: | CM-11 prep; | Prep UCM/2k plumbing |  |  | C75-01 parts prep; | LCLSII CM06-Shipping Alignment | P1 dis; weight transfer to lollipops, N95 Fit tests Prep VV for move to UITF | Install HV Tooling and Cavity on rail | RGA 1L25 WG
2020-06-11 | Thu |  |  | C75-RI-003; |  |  | HE-353 tuning; | [6 empty] | New HEP Install; | HPR1: OOC HPR2: |  | TS34-003; | [6 empty] | D1: D2: D3: D4: D5: D6: D7: D8: |  | Prep UCM/2k plumbing |  |  | C75-01 parts prep; | Pump on U-tubes, heat ex, etc. in CMTF L2-09 | P1 dis; cut shield bellows, N95 Fit tests Move VV to UITF |  | LERF heater controls updates; 1L25 decarad installation; |  | PSS updates, checkout;
2020-06-12 | Fri |  | Injector parts BB | C75-RI-003; C75-RI-002/C75-RI-005 (#1); |  |  | HE-353 cage; | Cleanup run; | HE Nb samples; |  |  | Injector parts; |  | New HEP Install; | HPR1: OOC HPR2: |  | TS34-003; locate L2-536 and move to VAA; | C75 pair 2 to CMM; |  | BLAs establish vacuum; |  |  | L2-536; | D1: D2: D3: D4: D5: D6: D7: D8: | CM11 prep | Prep UCM/2k plumbing |  |  | C75-01 parts prep; |  | P1 dis; cut shield bellows, unhang 50k shields |  | LERF heater controls updates; |  | PSS updates, checkout;
2020-06-13 | Sat |  | Injector parts BB | C75-RI-002/C75-RI-005 (#1);
2020-06-14 | Sun |  | Injector parts BB
2020-06-15 | Mon |  | Injector parts BB | C75-RI-002/C75-RI-005 (#1); |  |  |  |  | C75-RI-003; |  | C75-RI-003; | L2-536 ext rinse; hardware; |  | New HEP Install; | HPR1: OOC HPR2: | [6 empty] | D6 test stand sensor removal; |  | D1: D2: C75 DL pull; D3: D4: D5: D6: test stand pull; D7: D8: | CM11 prep | Prep UCM/2k plumbing |  |  | C75-01 parts prep; |  | P1 dis, remove SF and 50Kshields |  | LERF heater controls updates;
2020-06-16 | Tue |  | Injector parts BB | C75-RI-002/C75-RI-005 (#1); |  |  | C75-J-004; |  |  |  |  | L2-536 bolt holes; L2 CM-11 cav 8 wipe; clamps; |  | New HEP Install; | HPR1: OOC HPR2: |  | cage L2-536; | accept L2 string; | SC-09 D6; | BLA RGA scan (x1); SC-09 D6; |  |  | L2 string; | D1: D2: D3: D4: D5: D6: D7: D8: | CM11 into cleanroom | Prep UCM/2k plumbing |  |  | C75-01 parts prep; |  | P1 dis, remove SF and 50Kshields |  | 1L12 BL vacuum troubleshooting; LERF heater controls updates;
2020-06-17 | Wed |  |  | C75-RI-002/C75-RI-005 (#1); |  |  | C75-J-004; |  |  |  |  | L2 tooling; L2 clamps; |  | New HEP Install; | HPR1: OOC HPR2: L2-536 (am) |  | pre-clean FPC; | L2 string dis; | [5 empty] | D1: D2: D3: D4: D5: D6: D7: D8: |  | UCM to 4-poster; |  |  |  |  | P1 dis, remove SF and 50Kshields |  | 1L12 ion pump replacement; LERF heater controls update; |  | prepare L2 CM-09 for cooldown/test;
2020-06-18 | Thu |  |  | C75-RI-003 (#2); C75 hom loads (#3); |  |  | C75-J-004; |  |  |  |  | L2 Bellows; Injector parts; |  | Reinstall T/Cs; | HPR1: OOC HPR2: |  |  |  | L2 CM-11 cavity replacement; |  |  |  |  | D1: D2: D3: D4: D5: D6: D7: D8: | [8 empty] | 1L12 ion pump replacement; 2L12 ts;
2020-06-19 | Fri |  |  | C75-RI-003 (#2); |  |  | C75-J-004; | [6 empty] | New HEP Install; | HPR1: OOC HPR2: |  |  |  | L2 CM-11 pumpdown; HB-046 D5; | HB-046; |  | SC-09 sensors; SC-10 sensors; |  | D1: D2: D3: D4: D5: field map (<20mG); D6: SC-09 L; D7: D8:
2020-06-20 | Sat
2020-06-21 | Sun
2020-06-22 | Mon |  | BB injector electrode; | C75 Elbows(x2); |  |  | C75-RI-004; |  |  |  | HE rings; | HE rings; |  | New HEP Install; | HPR1: OOC HPR2: |  |  |  | L2 Shipping Manifold (CW); | L2-CM-11 bag test; |  |  |  | D1: D2: D3: D4: HE samples hold; D5: HB-046 L; D6: SC-09 hold; D7: D8: |  | UCM QC Fastener Spread Sheet |  |  | Demag parts Inventory W2C beam pipe parts | CM06- Prep for shipping Assemble 2 shipping manifolds in CR | Remove remaining tuners parts Begin 2 phase cutting |  |  |  | Degauss, Cooldown (David am, Justin pm);
2020-06-23 | Tue |  | BB injector electrode and flanges; | C75 elbows (x6); C75 End dishes; |  |  | C75-RI-004; |  |  |  |  | HE 353 parts; roughing hoses; |  | New HEP Install; | HPR1: OOC HPR2: |  |  |  |  | L2-CM-11 LC; |  |  |  | D1: D2: D3: D4: HE samples C4K/TC; D5: HB-046 hold; D6: SC-09 hold; D7: D8: |  | UCM QC Fastener Spread Sheet |  |  | Inventory W2C beam pipe parts Remove shield from VV for wg heat stations Test new wg hs clamp | CM06- Install shipping insert/caps, PPE required. | Remove remaining tuners parts Continue 2 phase cutting RF Testing Windows
2020-06-24 | Wed |  | BB injector electrode and flanges; | IA-339; C75 End dish; |  |  | C75-RI-004; |  | HE rings; C75 Elbows(x3); |  | Elbows(x3); | L2 blanks and vlvs; L2 string parts; Elbows(x3); |  | New HEP Install; | HPR1: OOC HPR2: |  |  |  |  | J1.3-11R; |  |  |  | D1: D2: D3: D4: HE samples TC; D5: HB-046 C4K; D6: SC-09 C2K/T/W; D7: D8: |  | UCM QC Fastener Spread Sheet |  |  | Weld shield from VV for wg heat stations | CM06- Complete shipping prep. Truck in tomorrow 8am | Continue 2 phase cutting RF Testing Windows |  | 1L12 BL vacuum troubleshooting; |  | J1.3-09 cooldown;
2020-06-25 | Thu | Cleaning chamber | BB injector electrode and flanges; | IA-335 |  |  | C75-RI-004; |  | HE rings (lot B); |  | HE rings; |  |  | New HEP Install; | HPR1: OOC HPR2: C75-J-005; |  |  |  | J1.3-11R; SC-15 D6; | SC-15 D6; |  |  |  | D1: D2: D3: D4:HE samples TC; D5: HB-046 C2.1K/T/W; D6: SC-09 pull; D7: D8: |  | UCM QC Fastener Spread Sheet |  |  | Weld shield from VV for wg heat stations | CM06- Truck in tomorrow 8am. Load CM | Continue 2 phase cutting RF Testing Windows | HRCR On-site, sns shipping frame to Aspen |  |  | J1.3-09 cooldown;
2020-06-26 | Fri | Cleaning chamber | BB injector electrode and flanges; | L2-BLA (3x); C75 End dish; |  |  | C75-RI-004 HOM BP; | [6 empty] | New HEP Install; | HPR1: OOC HPR2: |  |  |  | J1.3-11R; C75-J-005 D7/8; |  |  | SC-15 D6; |  | D1: D2: D3: D4:HE samples TC; D5: HB-046 W; D6: SC-09 pull; SC-15 L/C4K; D7: SC-10 C4K; D8: |  | UCM QC Fastener Spread Sheet |  |  | Weld shield from VV for wg heat stations | CM06- Ship to SLAC | Continue 2 phase cutting RF Testing Windows |  |  |  | J1.3-09 pumpdown/test; HPA corrective maintenance (windows test stand);
2020-06-27 | Sat |  | BB injector electrode and flanges; | [20 empty] | D6: SC-15 C2K/T/W;
2020-06-28 | Sun |  | BB injector electrode and flanges; | [20 empty] | D7: SC-10 C2K
2020-06-29 | Mon | C75 DL; |  | P1 C100 guard vacuum waveguides |  |  |  |  | C75 Inner adapter (CP#3); |  | C75 DL; SS flange; | C75 CM-01 W/C beamline parts; HE-353 (US x2); |  | New HEP Install; | HPR1: OOC HPR2: |  | cage C75-RI-001; cage C75-RI-003; |  |  | J1.3-11R bag; C75-J-005; |  |  |  | D1: D2: D3: D4: HE samples pull; D5: HB-046 pull; D6: SC-15 pull; D7: SC-10 T/W; D8: | CM11- Prep for string | UCM 008 Weld Inspection |  |  | Demag parts |  | RF Test windows LC Cold WG's String disassembly House parts |  | NL pumpdown to 2K; |  | J1.3-09 testing; Windows test stand maint.
2020-06-30 | Tue | C75 DL; | C75 Test Blank; | P1 C100 guard vacuum waveguides; C75 Inner adapter (CP#3); |  |  | vacation |  | C75 Inner adapter (CP#3); |  | C75 Inner adapter (CP#3); HE samples; | C75-RI-001; C75-RI-003; C75 strongback; |  | New HEP Install; | HPR1: OOC HPR2: HE-353; |  | demag C75 parts; | HB-046; |  | J1.3-11R rollout; C75-J-005; |  |  |  | D1: D2: D3: D4: D5: D6: D7: SC-10 warm; D8: | CM11- Receive string 2 phase pipe |  |  |  | Demag parts |  | RF Test windows LC Cold WG's House parts |  | NL pumpdown to 2K; 1L25 measurements; SL pumpdown to 2K; |  | Q0 measurements J1.3-09;
2020-07-01 | Wed | C75 DL; |  | C75 Inner adapter (CP#3); |  |  | HB-046; | Nb tubes 975C/3h; | C75 Inner adapter (CP#3); |  | C75 Inner adapter (CP#3); HE half cells; C75 end dishes; | C75 pair HW; C75 HOM loads; C75 elbows; |  | New HEP Install; HF spike; | HPR1: OOC HPR2: C75-RI-001 (4P); HE-353; |  | C75 pair parts prep; HE-353; | C75-J-005; | [5 empty] | D1: D2: D3: D4: D5: D6: D7: D8: | CM11- 2 phase pipe, Magnet install, Berry bolts cavs 7 & 8 Instrumentation |  |  |  | Demag parts, tuners |  | RF Test windows LC Cold WG's | Prep lollipops for shipment | 1L25 RF measurements; 1L13 tuner measurements on C75 cavities; |  | Q0 measurements J1.3-09;
2020-07-02 | Thu | C75 DL; |  | C75-J-004; C75 DL-144; |  |  | HB-046; | Nb tubes 975C/3h; | C75 DL-144; | EP 5cell cavity IA-012; | Electrical Work in Chem Room; C75 DL-144; | C75 pair Doglegs; C75 pair etc; C75 DL-144; |  | New HEP Install; | HPR1: OOC HPR2: C75-RI-003 (4P); |  | C75 pair parts prep; |  | HE-353; |  |  |  |  | D1: D2: D3: D4: D5: D6: D7: D8: | CM11- 2 phase pipe, Magnet install, Berry bolts cavs 7 & 8 Instrumentation |  |  |  | Demag parts, tuners | L2 shipping trailer return; | RF Test windows LC Cold WG's |  | 1L25 high power RF measurements;
2020-07-03 | Fri | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-07-04 | Sat
2020-07-05 | Sun
2020-07-06 | Mon | C75 DL |  | C75-J-004; P1 C100 guard vacuum waveguides; |  |  | HB-046; C75-RI-004 HOM BP; | HE samples 600C/10h; |  | IA-012 (EP); |  | C75 gortex gaskets; C75 DL-144; HE gaskets; |  | New HEP commissioning IA-012 5-cell; | HPR1: OOC HPR2: |  |  |  |  | HE-353; |  | SC-10 sensor removal; LSF9-1 sensors; |  | D1: D2: D3: D4: D5: D6: D7: SC-10 pull; D8: | CM11- 2 phase pipe, Berry bolts cavs 7 & 8 Instrumentation |  |  |  | Tuners, CU1 |  | RF Test windows LC Cold WG's |  | 1L25 eight cavity run; 2L03 frozen tuners; |  | Windows test stand HPA troubleshooting; LERF test system checkout L2;
2020-07-07 | Tue | C75 DL |  | C75 pair #4 elbows |  |  | HB-046; | HE samples pull; |  |  |  | HB-050 parts; clamps, blanks, gaskets; L2 shipping manifold; C75 CM-01 W/C beamline parts; |  | New HEP commissioning IA-012 5-cell; | HPR1: OOC HPR2: |  |  |  | C75-RI-001; HE-353 on test stand; | HE-353; |  |  |  | Four Cavity Runs CMTF D1: D2: D3: D4: D5: D6: D7: D8: | CM11- Fiducialize CS | Demag UCM/Invar |  | CM02-Hook up diffuser | Tuners, CU1 Remove 50k shields from VV |  | RF Test windows LC Cold WG's Clear assy rail Transport tooling to Blue Crab | HB-049; | 2L03 warmup room temp; |  | Windows test stand HPA troubleshooting; LERF test system checkout L2;
2020-07-08 | Wed | Vacation |  | C75 End dishes; |  |  | C75-J-004; |  |  | IA-012; | C75 DL; C75 elbow; |  |  | New HEP Install; SC-09 setup; | HPR1: OOC HPR2: HB-050 |  |  |  | C75-RI-001/ C75-RI-003; | HE-353; |  |  |  | Four Cavity Runs CMTF D1: D2: C75 FT thermal cycle (x3); D3: D4: D5: D6: D7: D8: LSF9-1 L/C4K (PM); | CM11- Fiducialize CS | Demag UCM/Invar |  | CM02- Leak check connections | Tuners, CU1 Remove 50k shields from VV |  | RF Test windows LC Cold WG's
2020-07-09 | Thu | C75DL, Waveguide Flange Repair |  | C75 Hom loads; C75 Elbows |  |  | P1 cavity setup; |  | C75-J-004; |  |  | L2 FPCs (x2); |  | New HEP Install; SC-09 2.5u; | HPR1: OOC HPR2: HB-050; |  | HB-050 |  | L2 FPCs (-71, -87); | C75-RI-001/ C75-RI-003; |  | HE-353; |  | D1: D2: D3: D4: D5: D6: D7: HE-353 L/C4K (PM); D8: LSF9-1 C2K/T; | CM11- LC 2 Phase, MLI, Mag shields |  |  |  | Tuners, CU1 REC Prep Mod HV's and VV's |  | RF Test windows
2020-07-10 | Fri | C100 Waveguide Flange Repair |  | C75 Doglegs; |  |  | P1 JL-004; |  |  |  | C75-J-004; | C75-J-004; |  | New HEP Install; SC-15 setup; | HPR1: OOC HPR2: |  |  |  | HB-050 D5; | C75-RI-001/ C75-RI-003; L2 FPCs (-71, -87); |  |  |  | UITF u-tubes install D1: D2: D3: D4: D5: D6: D7: HE-353 C2K/T/W (1); D8: LSF9-1 hold; | CM11- LC 2 Phase, mli, mag shields |  |  |  | Tuners, CU1 Mod components REC Prep- Cold Shock |  | RF Test windows Prep EP03 | Alignment crew HB-049 | 1L12 warm-up to RT for tuner T/S; |  | Windows test stand RF T/S;
2020-07-11 | Sat | [7 empty] | C75 DL; | [10 empty] | L2 FPCs (-71, -87);
2020-07-12 | Sun |  |  | C75 Doglegs; | [15 empty] | L2 FPCs (-71, -87);
2020-07-13 | Mon |  |  | C75-J-004; |  |  | P1 JL-005; |  |  |  | Nb3Sn HW; | C75 parts; SC-09; SC-09 parts; |  | New HEP Install; SC-15 2.5u; | HPR1: OOC HPR2: SC-09; |  |  | C75-RI-001/ C75-RI-003; |  | HB-050; |  |  |  | CMTF u-tubes removed D1: D2: D3: D4: D5: D6: D7: HE-353 pull; HB-050 L/C4K; D8: LSF9-1 C2K/T/W; | CM11- MLI, mag shields |  |  |  | Tuners, CU1 REC/SEC Prep- Cold Shock |  | RF Test windows | HB-049 into HV |  |  | pull U-tubes; LERF PSS cert;
2020-07-14 | Tue | P1/C75 Waveguide Flange Repair |  | C75 end dishes; |  |  | C75 test HW; HB-049 into HV, RF Meas; |  | C75-RI-001 debur HOM; C75-J-004; |  | C75 DL & inner adapter C75-RI-001 (HF); C75-RI-003 (HF); C75-J-004; PD crucible; | C75 parts & HW; C75-RI-001; C75-RI-003; C75 Dogleg & inner adapter; |  | Software; | HPR1: OOC HPR2: |  |  | HE-353; | SC-09 TS16-001; |  |  |  |  | D1: D2: D3: D4: D5: D6: D7: HB-050 C2K/T/W; D8: LSF9-1 warm; | CM11- MLI, mag shields |  |  | CM09- PSS Cert | Tuners, CU1 REC/SEC Prep- Cold Shock. LC Field Map Mu shields |  | RF Test windows | HB-049 Tacked/ Align next | 1L12 cooldown; |  | LERF PSS cert; CMTF PSS cert;
2020-07-15 | Wed |  |  | C75-J-004; |  |  | HB-049 into HV, RF Meas; P1 EP-003; P1 JL-007; | Nb samples 900C/3h; | HE rings; |  | PD crucible Cu; Buncher cavity; | HE-353; SC-15; |  | Software; SC-15 disassembly; IA-012 setup; | HPR1: OOC HPR2: C75-RI-001 (4P); |  |  | HE-353; |  | SC-09; |  | SC-09 sensors; LSF9-1 triangulation; |  | PSS cert AM D1: D2: D3: D4: D5: D6: D7: HB-050 warm; D8: LSF9-1 pull; | CM11- MLI,Mag shields, fluxgates |  |  | CM09- Prep for removal | Tuners, CU1 REC/SEC Prep-LC |  | RF Test windows | HB-049 Align Crew
2020-07-16 | Thu | P1/C75 Waveguide Flange Repair | Buncher cavity; | P1 waveguides; C75 HOM loads; C75 elbows |  |  | P1 JL-006; P1 JL-003; | Nb samples 900C/3h; | [5 empty] | Software; IA-012 test; | HPR1: OOC HPR2: C75-RI-003 (4P); |  | P1 EP-03 prep; | LSF9-1 remove from TS; HB-050 remove from TS; | C75-RI-001; |  |  |  |  | D1: D2: D3: D4: D5: D6: SC-09 L/C1.5K/T/W; D7: HB-050 pull; D8: | CM11- Align UCM to rail |  |  | CM09- Remove from CMTF, set flowhoods | Tuners, CU1 REC/SEC Prep-LC Field Map Mu shields |  |  | HB-49 Weld |  |  | CM09 removal;
2020-07-17 | Fri | Nb Crucible | Buncher cavity (x2); | P1 windows; P1 waveguides; C75 elbows |  |  | P1 EP-003; HB-049; blanks; |  |  |  |  | C75 valves clean and bake; Buncher cavity parts; SC-15 parts; |  | HE-353 setup; | HPR1: OOC HPR2: SC-15; |  | P1 EP-03 prep machine shop; |  | C75-RI-001/C75-RI-003; |  |  |  |  | D1: D2: D3: D4: D5: D6: SC-09 C1.5K/T/W; D7: D8: | CM11- Align UCM to WS3; |  |  | CM09- Prep for BL work, measure WC's | Tuners, CU1 REC/SEC Prep-LC Field Map Mu shields |  |  | HB-49 Weld | LEM; 1L25-8 WG processing; LERF 8-cavity Q0 measurement;
2020-07-18 | Sat
2020-07-19 | Sun
2020-07-20 | Mon | Cryo Regen | Buncher cavity (x2); | P1 windows; P1 secondary waveguides; |  |  | P1 JL-009; HB-049; blanks; |  |  |  | Nb samples (x55); | HE-353 parts; |  | HE-353 1u; | HPR1: OOC HPR2: |  | P1 EP-03 prep machine shop; L2 FPCs (-71, -87); |  | SC-15 TS16-001; | C75-RI-001/C75-RI-003 and RF measurement; |  | SC-09 remove sensors; |  | D1: D2: D3: D4: D5: D6: SC-09 pull; D7: D8: |  | CM11-Move to WS3, Unite with UCM |  | CM09- Prep for BL work, Install M-Mounts | Tuners, CU1 REC/SEC Prep-LC Field Map Mu shields |  | Evaluate Mag Shields | HB-49 Weld, RF Measurements
2020-07-21 | Tue | Cryo Regen | Buncher cavity (x2); |  |  |  | P1 JL-008; HB-049; P1 blanks; C75 pair passbands; |  |  |  | Nb3Sn crucible & sample chamber; | C75 HV (x5); |  | SOFTWARE MAINT | HPR1: OOC HPR2: |  |  |  | C75-RI-001/C75-RI-003 D7/8; | C75-RI-001/C75-RI-003 and RF measurement; SC-15; |  | SC-015 sensors; |  | power outage am 4hrs Morning to Noon Radcon Monitor Down No testing D1: D2: D3: D4: D5: D6: D7: D8: |  | CM11- Add bearing block assy's |  | CM09- Install M-Mounts, Vacuum IP swap | Tuners, CU1 REC/SEC Prep-LC Field Map Mu shields |  |  | HB-49 Weld, RF Measurements, Align Crew
2020-07-22 | Wed |  | P1 windows; | P1 window frames (x4); |  |  | P1 EP-002; |  |  |  | P1 window eyelets; | L2 BPM fasteners; L2 FPC; |  | HE-353; SC-09 setup; | HPR1: OOC HPR2: |  |  | HB-050 remove from cage, deliver to welding; SC-09 dis; |  | C75-RI-001/C75-RI-003 RF measurement; |  | C75-RI-001/C75-RI-003; |  | D1: D2: D3: D4: D5: D6: SC-15 L/C2K/T/W; D7: D8: C75-RI-001/C75-RI-003 L |  | CM11- Bearing blocks, 2 phase pipe | CM11- Prep VV | CM09- Remove testing IP | Tuners, CU1 REC/SEC Prep-LC Field Map Mu shields |  |  | HB-49 Weld, RF Measurements | J1.3-20 LERF testing 4k; CEBAF RF recovery;
2020-07-23 | Thu |  | P1 windows; | P1 window frames (x2); P1 Primary waveguides; | [7 empty] | SC-09 (x2) and parts; |  | SC-09 2.5u; | HPR1: OOC HPR2: |  |  | P1 seal ring removal; | J1.3-02 BPM fasteners; | C75 girder gate valves; |  |  |  | D1: D2: D3: D4: D5: D6: D7: D8: C75-RI-001/C75-RI-003 WDLC/C4K; |  | CM11- Bearing blocks, 2 phase pipe, Cavity 1 tuner |  | CM09- Remove testing IP/Cap CM02- Cold Coupler repair/BPM Hardware replace | Tuners, CU1 REC/SEC Prep-LC |  |  | HB-49 -Weld, RF Measurements HB50- Receive cavity, measure for shell length | J1.3-20 LERF testing; |  | PSS Cert;
2020-07-24 | Fri |  | P1; | P1 primary waveguides; P1 secondary waveguides; | [9 empty] | maint | HPR1: OOC HPR2: SC-09; |  |  | P1 seal ring removal; | J1.3-02 FPC replacement; |  |  |  |  | D1: D2: D3: D4: D5: D6: D7: D8: C75-RI-001/C75-RI-003 C2K/T; |  | CM11- 2 phase pipe, Cavity 1 tuner |  | CM09- Prep for shipping manifold install CM02- Cold Coupler repair | Tuners, CU1 REC/SEC Prep-LC Demag parts |  |  | HB50- Align Crew HB-49- RF Measurements, Alignment Crew
2020-07-25 | Sat
2020-07-26 | Sun
2020-07-27 | Mon |  | P1 window; | JL-003; |  |  | HB-049 horz. passbands; |  | He Nb ring; C75-RI-008; |  |  | C75-RI-008 parts; HB-049 ext clean; |  | maint; | HPR1: OOC HPR2: |  | C75-RI-008 inspect flanges; |  | SC-09 TS16-001; |  |  |  |  | D1: D2: D3: D4: D5: D6: D7: D8: C75-RI-001/C75-RI-003 C2K/T/W (W for desorb); |  | CM11- 2 phase pipe, GV Bracket |  | CM09-Install shipping manifold CM02- Pumpdown LC | Rework Tuners REC/SEC Prep-LC Demag parts |  |  | HB50- Measure features HB-49- Final RF Measurements
2020-07-28 | Tue |  |  | JL-009; C75 HOM loads |  |  | JL-003 prep for MS; |  | C75-RI-008; |  | AUP RFD damper samples weld prep; C75-RI-008; | C75-RI-008; |  |  | HPR1: OOC HPR2: |  | TS28-xxx mods for plasma; |  |  | SC-09; |  |  |  | D1: SIC C/T; D2: D3: B-scan C/T/W; D4: D5: D6: D7: D8: C75-RI-001/C75-RI-003 warm; |  | CM11- 2 phase pipe, Remove Lollipops |  | CM09-Install shipping manifold/LC CM02- Pumpdown LC | Rework Tuners REC/SEC Prep-LC |  |  | HB-49- to VTA QC SNS Shipping Frame
2020-07-29 | Wed | AUP RFD damper samples; |  | JL-004; | [7 empty] | HB-049 exterior; |  | New HEP Install; | HPR1: OOC HPR2: |  | TS28-xxx mods for plasma; |  | HB-049 TS34-003; |  |  | Flux expulsion tubes; SC-09; |  | D1: SIC C/T; D2: D3: B-scan warm; D4: D5: D6: SC-09 L/C2K/T/W; D7: D8: C75-RI-001/C75-RI-003 pull; |  | CM11- 2 phase pipe, thermal straps |  | CM09-Prep BL work US end, Verfiy HOM's CM02- Leak Check | Rework Tuners Modify 2nd 50k shield REC/SEC Prep-LC |  |  | QC SNS Shipping Frame Retreive tooling from warehouse
2020-07-30 | Thu |  |  | C75-RI-008; JL-005; |  |  | P1 test blanks (2 sets); |  | He S/S blanks; |  | Nb3Sn Sample chamber & HW; HE-353 prep; | P1 windows; |  | New HEP Install; | HPR1: OOC HPR2: |  | TS28-xxx mods for plasma; | golden girl pair disassembly; |  | HB-049 TS34-003; |  | C75-RI-001/C75-RI-003 leak check & remove sensors; |  | D1: SIC C/T; D2: D3: B-scan warm/pull; D4: Flux exp tubes L/10cm 4K C/T D5: HB-049 L/C4K; D6: SC-09 C/T/W; D7: D8: |  | CM11- move to E 4-poster |  | CM09-BL work US end CM02- Prep 4 move to WS2 | Modify 2nd 50k shield REC/SEC Prep-LC |  |  | Prep tooling for cleaning
2020-07-31 | Fri |  |  | P1 Jl-007; | [7 empty] | C75-RI-008; SNS tooling; |  | New HEP Install; | HPR1: OOC HPR2: C75-RI-008 4P; |  | TS28-xxx mods for plasma; | C75-RI-001/C75-RI-003 remove from TS; golden girl pair disassembly; |  |  |  | C75-RI-001/C75-RI-003 leak check; |  | D1: SIC C/T; D2: D3: B-scan L/C/T/W; D4: Flux exp tubes 10cm 4K C/T D5: HB-049 C2K/T/W; D6: SC-09 pull; D7: D8: |  | CM11- 2 phase pipe welding, prep tuners |  | CM09- Complete BL work, prep for shipping and alignment CM02- Move to WS2, move UCM from N end | Modify 2nd 50k shield REC/SEC Prep-LC |  |  | Tooling disassembled for Mock up Leak check HV heads
2020-08-01 | Sat
2020-08-02 | Sun
2020-08-03 | Mon | JLEIC; | C75 windows; | C75 Mag shields; PPU helium vessels; IA335 (C75-03); |  |  | deliver C100 to water room; |  |  |  | HW Coax; HE-353 prep; | JL-009 and HW; C100 cavity gross rinse; |  | commissioning; | HPR1: OOC HPR2: |  |  |  | C75-RI-008 D7/8; |  |  | C75-RI-001/C75-RI-003 torque; HB-049 cable check; |  | D1: SIC C/T; D2: D3: B-scan SC4K; D4: Flux exp tubes C4K; D5: HB-049 pull; D6: D7: D8: | CM02- Berry bolts, MLI, Mag shields cavs 7&8 | CM11- 2 phase pipe welding, prep tuners |  | CM09-Prep 4 shipping/alignment | Modify/Hang 2nd 50k shield REC/SEC Prep-LC |  |  | Reassemble tooling for Mock up Leak check HV heads
2020-08-04 | Tue | JLEIC; | C75 windows; | IA-335 (C75-03) C75 Mag Shields; |  |  | IA335 (C75-03) FPC Qext; |  |  |  |  | JL-009 HW; JL-004; SC-15 and HW; |  | SC-15 setup; | HPR1: OOC HPR2: |  |  | SC-15 dis outside Clnrm; |  | C75-RI-008 |  |  |  | D1: SIC hold; D2: D3: B-scan warm; D4: Flux exp tubes C4K/W; D5: D6: D7: D8: C75-RI-001/C75-RI-003 L; | CM02- Berry bolts, MLI, Mag shields cavs 7&8 | CM11- 2 phase pipe welding/LC, prep tuners CM02- Demag UCM |  | CM09-Shipping prep | Hang 2nd 50k shield REC/SEC Prep |  |  | Reassemble tooling for Mock up Leak check HV heads
2020-08-05 | Wed | JLEIC; | C75 windows; | IA-346; C75 Mag shields; |  |  | P1 cal; Cage JL-004; |  |  |  | HE-353; | HE-353; SC-15; |  | SC-15 40u; | HPR1: OOC HPR2: | [6 empty] | C75-RI-008 OSTs; |  | D1: SIC C/T; D2: D3: B-scan warm/pull (PM); D4: Flux exp tubes C4K/W; D5: HB-049 L; D6: D7: D8: C75-RI-001/C75-RI-003 C4K:(1) | CM02- Fiducialize CS | CM11- 2 phase pipe LC CM02- Demag UCM |  | CM09-Alignment | Hang 2nd 50k shield REC/SEC Prep | LCLS Shipping frame in at 2 pm-ish LC Flow Safe Valve |  | Reassemble tooling for Mock up Leak check HV heads
2020-08-06 | Thu |  | Hall D Shield anneal; | C75 Mag shields; C75 HOM loads; L2 BLAs; |  |  | HE-353 FF check (am); P1 passbands in vertical orientation; |  | HE samples; |  | P1 flanges and seal rings; | JL-004 and HW; EIC-1; Hall D parts; |  | commissioning; | HPR1: OOC HPR2: SC-15; JL-004; | [6 empty] | C75-RI-008 sensors |  | D1: SIC C/T; D2: D3: B-scan L/C4K/T/W; D4: Flux exp tubes hold; D5: HB-049 hold; D6: SC-09 L; D7: C75-RI-008 L/C4K; D8: C75-RI-001/C75-RI-003 C2K/T/W (1); | CM02- Fiducialize CS | CM11- 2 phase pipe LC, prep tuners CM02- Demag UCM |  | CM09-Alignment, install shipping caps, | REC/SEC PT |  |  | Leak check HV heads
2020-08-07 | Fri | Cu Tubes for harmonic kicker; | Hall D Shield anneal; | C75 HOM loads; PPU helium vessels; |  |  | HE-353 tuning; P1 probes; |  | HE samples; |  |  | P1 probes; BLAs; |  | commissioning; | HPR1: OOC HPR2: |  |  | GG disassembly; | SC-15; |  |  |  |  | D1: SIC C/T/W; D2: D3: B-scan pull/L hold; D4: Flux exp tubes hold; D5: HB-049 hold; D6: SC-09 hold; D7: C75-RI-008 C2K/T/C1.8K/T/W (1); D8: C75-RI-001/C75-RI-003 T/Maintain 2K; | CM02- Fiducialize CS | CM11- Heat stations, MLI CM02- Align UCM-Rail |  |  | REC/SEC PT | CM09-Complete load,ship to SLAC |  | Leak check HV heads
2020-08-08 | Sat | [22 empty] | D5: HB-049 C4K;
2020-08-09 | Sun | [22 empty] | D5: HB-049 C2K/T/W;
2020-08-10 | Mon |  | BB cleanup run; | PPU helium vessels; |  |  | P1 probes; |  | HE samples; |  |  | P1 probes; HE-353; RF Cables; |  | commissioning; | HPR1: OOC HPR2: HE-353; |  | JL-004; locate BLA HW; inspect C75-J-005; |  |  |  |  | C75-RI-008 OST removal; |  | D1: SIC C/T/W; D2: D3: B-scan C4K/T; D4: Flux exp tubes C4K/T/W; D5: HB-049 hold; D6: SC-09 C1.4K/T/W; D7: C75-RI-008 pull; D8: C75-RI-001/C75-RI-003 warm for desorb; | CM02- Prep 4 move to WS3 | CM11- Heat stations, MLI, CS Align CM02- Align UCM-Rail |  |  | REC PT |  | P1 cavity to machine shop; | Leak check HV heads
2020-08-11 | Tue | Cu Tubes for harmonic kicker; | BLAs; | IA-346 (C75-03); IA-335 (C75-03); |  |  | P1 probes; GG cavities Qext; |  | HE samples; |  | C75-J-005 flanges nitric soak; | C75-J-005; |  | commissioning; | HPR1: OOC HPR2: JL-004; HE-353; |  | HE-353; | SC-09; | [5 empty] | D1: SIC C/T/W; D2: D3: B-scan pull; D4: Flux exp tubes C4K/T/W; D5: HB-049 hold; D6: SC-09 pull; D7: D8: C75-RI-001/C75-RI-003 desorb/warm; | CM02- Move to WS3 | CM11- CS Align to UCM CM02- Unite to UCM |  |  | REC/SEC PT |  | Cavity in shop | Leak check HV heads
2020-08-12 | Wed | Cu Tubes for harmonic kicker; | BLAs; | IA-339 (C75-03); IA-354 (C75-03); |  |  | P1 probes; GG cavities Qext; |  | C75-J-005 flanges; |  |  | C75-J-005 HW; BLA parts; P1 parts; |  | disassembly; JLEIC 5C setup; | HPR1: OOC HPR2: |  |  | C75-RI-008; GG pair 4; flip HB-046; | HE-353; JL-004; SC-15; | SC-15; |  |  |  | D1: SIC C/T/W; D2: D3: D4: Flux exp tubes C4K/T/W; D5: HB-049 warm; D6: D7: D8: C75-RI-001/C75-RI-003 pumping vacuum; | CM02- Move to WS3 | CM11- CS Align to UCM CM02- Unite to UCM |  |  | REC/SEC PT |  | Cavity in shop | Leak check HV heads
2020-08-13 | Thu | Cu Tubes for harmonic kicker; | BLAs; | IA-340 (C75-03); IA-333 (C75-03); P1 waveguides; |  |  | GG cavities Qext; P1 probes; |  | HE samples; C75-J-005 flanges; |  | C75-J-005 flanges; C75-J-005 test blanks; | C75-J-005; SC-16 and parts; JL-009 (X2); |  | JLEIC 5C setup; | HPR1: OOC HPR2: |  | BLAs; | HB-049 dis for bead pull; GG pair 4; |  | HE-353; JL-004; |  | SC-15 sensors; |  | D1: SIC C/T/W; D2: D3: B-scan L/C4K/T; D4: Flux exp tubes C4K/T/W; D5: HB-049 pull; D6: SC-15 L; D7: D8: C75-RI-001/C75-RI-003 WDLC/pull for leak checking; |  | CM11- Tuners CM02- Unite to UCM |  |  | REC PT, Prep SEC Fabricate gear box brackets Weld Cu strapping 3rd shield | Truck back from SLAC, Unload | Cavity in shop | Leak check HV heads Tack backing straps/HV heads Mock up Coupler tooling
2020-08-14 | Fri | Cu Tubes for harmonic kicker; |  | IA-334 (C75-03); IA-301 (C75-03); P1 waveguides; |  |  | P1 probes; |  |  |  | C75-J-005 flanges; HE samples; | C75-J-005; HE samples; |  | JLEIC 5C setup; | HPR1: OOC HPR2: C75-J-005 (4P); |  |  | HE-353; JL-004; | BLAs; |  |  | C75-RI-001/C75-RI-003 leak checking @VSA; |  | D1: SIC C/T/W; D2: D3: B-scan L/C4K/T; D4: Flux exp tubes C4K/T/W; D5: D6: SC-15 hold; D7: D8: |  | CM11- Tuners, Magnet leads CM02- Unite to UCM, 2 phase piping |  |  | Prep SEC Fabricate gear box brackets Weld Cu strapping 3rd shield |  | Cavity in shop | Leak check HV Mock up Coupler tooling
2020-08-15 | Sat
2020-08-16 | Sun
2020-08-17 | Mon | Cu Tubes for harmonic kicker; |  | SNS HV; |  |  | HB-049 bead pull; |  | HE samples; |  | Nitric NbTi sample; |  |  | JLEIC 5C processing; | HPR1: OOC HPR2: SC-16; |  |  | HB-049 dis for bead pull; | C75-J-005 TS28-007; | BLAs; |  | C75-RI-001/C75-RI-003 leak checking @VSA; |  | D1: SIC C/T/W; D2: D3: B-scan pull; D4: Flux exp tubes C/thermal cycles/W; D5: D6: SC-15 C1.6K/T/W; D7: D8: |  | CM11- Tuners CM02- 2 phase piping, drop lollipops |  |  | SEC PT Fabricate gear box brackets Tuners CU2 |  | Cavity in shop | Mock up Coupler tooling
2020-08-18 | Tue | Cu Tubes for harmonic kicker; |  | SNS HV; P1 waveguides; |  |  | HB-049 BP; |  | JL-009; |  | JL-009 flanges; | JL-009 |  | JLEIC 5C processing; | HPR1: OOC HPR2: |  |  |  | SC-16 TS28-008 (or cart); | C75-J-005; BLAs; |  | C75-RI-001/C75-RI-003 leak checking @VSA; |  | D1: SIC C/T/W; D2: D3: B-scan L/C/T; D4: Flux exp tubes pull; D5: D6: D7: D8: C75-RI-001/C75-RI-003 L/WDLC; |  | CM11- Tuners, Alignment 4 magnet CM02- 2 phase piping, heat stations |  |  | Tuners CU2 Prep REC for rail | Move LCLS Tooling to BC | Cavity in shop, fab toling Remove BP from EC, grind | SNS Heads-tack backing rings
2020-08-19 | Wed |  | P1 windows; | P1 waveguides; SNS HV; |  |  | P1 probes; |  | HE samples; |  | AUP rings; | P1 windows; |  | maint; | HPR1: OOC HPR2: JL-009 (4P) |  |  | JL-004; | SC-16; | BLAs; C75 DL; |  | C75-J-005 sensors and OSTs; |  | D1: SIC C/T/W; D2: D3: B-scan hold; D4: D5: D6: D7: C75-J-005 L/hold D8: C75-RI-001/C75-RI-003 C2K/hold; |  | CM11- Move to WS4, Instrumentation CM02- 2 phase piping, heat stations, Cav8 tuner | CM11- Instrumentation |  | Install 3rd shield into VV, remove 4th Tuners CU2 Prep REC for rail |  | Cavity in shop, fab tooling | SNS Heads-tack backing rings Mock up- Move HB46
2020-08-20 | Thu | AUP weld test; | P1 windows; |  |  |  | P1 probes; |  | JL-004; |  | SC weld prep; | P1 parts; |  | JLEIC 5C processing; | HPR1: OOC HPR2: |  |  |  | JL-009 TS28-003; | SC-16; C75 DL; |  |  |  | CTF CB3 Warm up D1: SIC hold; D2: D3: B-scan warm; D4: D5: D6: D7: C75-J-005 hold; D8: C75-RI-001/C75-RI-003 hold; |  | CM02- 2 phase piping, heat stations, Cav8 tuner | CM11- Instrumentation, RF Cables, HV Mu caps |  | Remove/Modify 4th 50k shield Install WG clamps Tuners CU2 Prep SEC for rail |  | Cavity in shop, fab tooling | SNS Heads-tack backing rings HB50 HV being machined
2020-08-21 | Fri |  | P1 windows; | SNS HV; |  |  | P1 probes; |  | JL-004; |  | JL-004 nitric flanges; | JL-004; |  | JLEIC 5C processing; | HPR1: OOC HPR2: |  | TS28-xxx mods for plasma; |  | JL-009 TS28-003; | C75 DL; | SC-16 120C/24h; |  |  | CTF CB3 Warm up D1: SIC hold; D2: D3: B-scan pull; D4: D5: D6: D7: C75-J-005 hold; D8: C75-RI-001/C75-RI-003 warm am for desorb pm; |  | CM02- 2 phase piping, heat stations | CM11- Instrumentation, RF Cables, HV Mu caps |  | Remove/Modify 4th 50k shield Install WG clamps Tuners CU2 Prep SEC for rail | Retrieve EC tooling from Warehouse | Cavity in shop, fab tooling | HB50 HV in house
2020-08-22 | Sat
2020-08-23 | Sun
2020-08-24 | Mon | AUP weld test; | P1 windows; | L2 BLA visual (LZ); SNS HV heads; P1 WG (LZ); |  |  |  |  | C75-02 elbows; HE samples; |  | JL-004 parts; C75 samples 50u; |  |  | JLEIC 5C processing; | HPR1: OOC HPR2: JL-004 (4P); |  | TS28-006 mods for plasma; |  |  | JL-009; | SC-15 120C/24h; | SC-16 sensors; |  | D1: SIC C2K/T; D2: D3: B-scan L/SC4K/T; D4: D5: D6: D7: C75-J-005 C2K; D8: C75-RI-001/C75-RI-003 WDLC/pull; |  | CM02- 2 phase piping, heat stations, set tuners | CM11- Instrumentation, RF Cables |  | Remove/Modify 4th 50k shield Install WG clamps Tuners CU2 Prep SEC for rail |  | Cavity in shop, fab tooling | HB50 HV in house
2020-08-25 | Tue | AUP weld test; P1 windows; | P1 windows; | P1 WG (LZ); L2 BLA visual (LZ); SNS HV heads; |  |  | J1.3-011R HOMs; | C75 samples 800C/3h; | C75-02 elbows; HE samples; |  | Nb3Sn coating HW; | C75-02 elbows; JLEIC 5C; |  | JLEIC 5C teardown; | HPR1: OOC HPR2: |  | TS28-006 mods for plasma; | BLA; | JL-004 D7/8; | JL-009; C75 DL; | SC-15 120C/24h; | SC-15 sensors; |  | UITF cool/fill/pump D1: SIC C2K/T; D2: D3: B-scan C4K/T/W; D4: D5: D6: D7: C75-J-005 T/W; D8: SC-16 L; |  | CM02- 2 phase piping LC, heat stations | CM11- Instrumentation, RF Cables |  | Tuners CU2 Prep SEC for rail Clear EC tooling |  | Cavity in shop, fab tooling
2020-08-26 | Wed | AUP weld test; P1 windows; | P1 windows; |  |  |  | J1.3-011R HOMs; | C75 samples 800C/3h; | C75-02 elbows; HE samples; |  | C75-02 elbows; | C75-02 elbows; ion pump; curtains; |  | commissioning; | HPR1: OOC HPR2: |  | SNS PPU mockup prep; |  | Cleanroom Dessicant Repair. JL-004 D7/8; | C75 DL; |  |  |  | D1: SIC warm; D2: D3: B-scan C4K/T/W; D4: JL-009 L/C2K; D5: D6: D7: C75-J-005 warm; D8: SC-16 TC; |  | CM02- 2 phase piping LC, hs,mli | CM11- HOM Tuning, Instrumentation check |  | SEC Prep fit HOM Dampers | Break down LCLS 4 poster tooling Relocate transfer rail | Cavity into tooling, prep for cut
2020-08-27 | Thu |  | P1 Windows; | C75-RI-004 prep for pair assy (1); JL-006; SNS HV heads (2); |  |  | J1.3-011R HOMs (am); HE-353 flange inspection; | C75 samples 800C/3h; | C75-02 elbows; HE samples; |  | C75 samples 20u; C75-02 elbows; | C75-02 elbows; curtains; L2 HW; P1 WG test flange; |  | commissioning; | HPR1: OOC HPR2: |  |  |  | RI-001/C75-RI-003 retorque; | JL-004; C75 DL; BLAs; |  |  |  | D1: SIC pull; D2: C75-DL L; D3: B-scan pull D4: JL-009 C2K/T/W; D5: D6: SC-15 L; D7: C75-J-005 pull; Pair test stand load; D8: SC-16 TC/C2K; |  | CM02- FSS, hs Magnet leads | CM11- Lower shields |  | HOM Dampers | Relocate transfer rail | Cavity into tooling, prep for cut
2020-08-28 | Fri | P1 windows; | P1 Windows; |  |  |  | J1.3-011R HOMs final; | HE samples 600C/10h; | C75-02 elbows; HE samples; |  | C75-02 elbows; | C75-02 elbows; Cu-ceramic brazements; MC lines L2; ER ion pump and valve; |  | commissioning; | HPR1: OOC HPR2: |  | HE-353 dirty assy & LC; |  |  | RI-001/C75-RI-003 not leaking; |  |  |  | D1: SIC L/C2K/T; D2: C75-DL C4K/T/W; D3: D4: JL-009 warm; D5: D6: SC-15 C2K/T; D7: Pair test stand WDLC/pull/L; D8: SC-16 T/W; |  | CM02- FSS, hs Magnet leads | CM11- Lower shields |  | HOM Dampers | Relocate transfer rail | Cavity into tooling, prep for cut
2020-08-29 | Sat
2020-08-30 | Sun
2020-08-31 | Mon | P1 windows; | P1 Windows; | C75-RI-004 prep for pair assy (1); |  |  | HB-050; | HE samples unload; | P1 cold WG; HE samples; JL-006 flanges; |  |  | HE-353; |  | New HEP Install; | HPR1: OOC HPR2: |  | HE-353 dirty assy & LC; |  |  | BLA; |  |  |  | D1: SIC C2K (4); D2: C75-DL pull; D3: B-scan load/C4K (4); D4: JL-009 pull; HE rolled tubes L; D5: D6: SC-15 W; D7: Pair test stand WDLC/C4K (2); D8: SC-16 pull; JL-004 L/C2K (1); |  | CM02- FSS, hs Magnet leads | CM11- Lower shields, MLI, into VV |  | HOM Dampers, MLI, LC Bellows |  |  | HB50 into tank
2020-09-01 | Tue | Single Cell Repair | P1 Windows; | JL-003 post machining; |  |  | HB-050; |  | P1 cold WG; JL-006 flanges; HE samples; |  | JL-006 flanges; | JL-006; HE-353 and parts; |  | EIC-5 Setup; | HPR1: OOC HPR2: HE-353 (2P); |  | JL-007 prep for MS; | [6 empty] | D1: SIC C2K; D2: magnet test L/C4K/W; D3: B-scan W10K/C4K; D4: HE rolled tubes W; D5: D6: SC-15 hold; D7: Pair test stand C2K; D8: JL-004 T/W; |  | CM02- hs Magnet leads | CM11- into VV, add support posts, prep 4 align |  | HOM Dampers, MLI, LC Bellows |  | Machine Cavity JL-007; | HB50 into tank
2020-09-02 | Wed | Single Cell Repair | P1 Windows; | P1 window adapters (2); C75-RI-004 prep for pair assy (1); |  |  | HB-050; C75-RI-004 prep for pair assy (1); | He samples 600C/10h; | P1 cold WG; HE samples; |  | JL-006 blanks; | JL-006 parts; |  | EIC-5 run; | HPR1: OOC HPR2: JL-006 (4P); |  | HE-353; cage JL-006; | JL-009; BLA; | BLA prep; | P1 WG flange; |  |  |  | D1: SIC C2K; D2: magnet test pull; D3: D4: HE rolled tubes pull; D5: D6: SC-15 C2K/T/W; D7: pair test stand warm for desorb; D8: JL-004 pull; |  | CM02- Install heater, Prep for CS alignment | CM11- Alignment CM in VV |  | MLI, LC Bellows, mag sheilding; | Move LCLS Tooling onto UITF HTB in house | Machine Cavity JL-007; | HB50 into tank
2020-09-03 | Thu | Single Cell Repair | P1 Windows; | C75 new loads (before braze); P1 WG (LZ); |  |  | C75-RI-004 prep for pair assy (1); | He samples 600C/10h; | HE samples; |  | TE1NS-001 nitric flanges & BCP internals 20u; | BLA parts; TE1NS-001; |  | EIC-5 run; | HPR1: OOC HPR2: HE-353 (2P); |  |  |  | JL-006 D3/4; BLA; |  |  |  |  | D1: SIC W; D2: D3: B-scan pull; D4: HE rolled tubes L/TC; D5: D6: SC-15 pull; D7: pair test stand DESORB/W; D8: |  | CM02-Prep for CS alignment, Instrumentation | CM11- Alignment CM in VV |  | MLI, LC Bellows, mag sheilding; | HTB measurements | Machine Cavity JL-007; | HB50 into tank
2020-09-04 | Fri | Vacation | P1 Windows; | P1 WG (LZ); |  |  |  | He samples pull; | C75-RI-004 prep for pair assy; HE samples; |  | C75-RI-004 prep for pair assy; |  |  |  | HPR1: OOC HPR2: |  |  |  | JL-006 D3/4; HE-353 TS28-004; | P1 WG flange; BLA; |  |  |  | D1: SIC pull; D2: magnet test L/C4K; D3: D4: HE rolled tubes TC; D5: D6: D7: pair test stand pull; D8: |  | CM02-Instrumentation | CM11- Alignment CM in VV, Move to WS5 |  | HOM Dampers, MLI, LC Bellows | HTB close up/store | Machine Cavity JL-007; | HB50 into tank
2020-09-05 | Sat
2020-09-06 | Sun
2020-09-07 | Mon | [12 empty] | New HEP Install; | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-09-08 | Tue | Vacation | P1 windows; | P1 WG (LZ); SNS Hv heads (1); C75-RI-004 prep for pair assy; |  |  | PPU01; JL-004 dis for MS; |  | C75-RI-004; |  | Twin cavity flanges nitric soak; C75 pair parts; C75-RI-004; | Twin cavity; P1 Window Parts; PPU01 ext; C75 pair parts; C75-RI-004; C75-J-005; | Twin cavity hardware 10um; | EIC-5 disassembly; | HPR1: OOC HPR2: |  | cage C75-J-004; | 5C75-J-005 for degreasing | C75-RI-001/C75-RI-003 TS28-001; | BLA; P1 WG flange; JL-006; HE-353; |  |  |  | D1: D2: magnet test pull; D3: D4: HE rolled tubes TC; D5: D6: D7: D8: |  | CM02- Align CS to UCM | CM02- Prep VV | CM11- Warm Couplers, Prep 4 BL | Mu shields, MLI, LC Bellows | Disassemble Nb3Sn 1/4 | Machine Cavity EP-002 | HB50- Move to weld fixture/ freq check
2020-09-09 | Wed | Maint. | P1 windows; | SNS Hv heads (3); P1 WG (LZ); C75-RI-004 (1); C75 DL (2); |  |  | HB-050; JL-003 probes; |  | C75-RI-004; |  | Nb3sn hardware; C75-RI-004; | C75-RI-004; C75 parts; |  | EIC-5 dis; | HPR1: OOC HPR2: |  |  |  | BLA; | BLA; C75-RI-001/C75-RI-003 TS28-001; |  | HE-353; |  | D1: D2: D3: JL-006 L/C2K (2); D4: HE rolled tubes pull/L/TC; D5: D6: D7: HE-353 L/C4K (3); D8: |  | CM02- Align CS to UCM |  | CM11- Warm Couplers, Add BL spool/testing cap, peripherals | Mu shields, MLI, LC Bellows | Disassemble Nb3Sn 1/4 | Machine Cavity- JL005 | HB50- Weld
2020-09-10 | Thu | Single Cell Repair | P1 windows; | SNS Hv heads (3); P1 WG (LZ); C75 DL (2); |  |  |  | 5C75-J-005 800C/3h; |  |  |  | C75 loads; |  | EIC-5 dis; | HPR1: OOC HPR2: |  |  |  | PPU01 TS34-003; P1 WG; | BLA; PPU01; |  | C75-RI-001/C75-RI-003 leak troubleshooting; |  | D1: D2: Magnet test L/C4K; D3: JL-006 T/W; D4: HE rolled tubes TC/W; D5: PPU01 L; D6: D7: HE-353 C2K (1); D8: C75-RI-001/C75-RI-003 L/WDLC/C2K (2); |  | CM02- Align CS to UCM |  | CM11- Warm Couplers, Add BL spool/testing cap, peripherals | Mu shields, MLI, LC Bellows | Disassemble Nb3Sn 1/4 | Machine Cavity- JL004 | HB50- Weld
2020-09-11 | Fri | Vacation | P1 windows; | SNS Hv heads (1); P1 WG; AD out Fri; C75 End Dishes (1); |  |  |  | 5C75-J-005 pull; |  |  |  | EIC-5; C75-RI-004; C75 tooling; |  | EIC-5 dis; | HPR1: OOC HPR2: |  | C75 pair tooling & mag field checks; |  |  | BLA RGA analysis; P1 WG; |  |  |  | D1: D2: Magnet test?; D3: JL-006 warm; D4: HE rolled tubes warm/pull; D5: PPU01 C4K; D6: D7: HE-353 hold; D8: C75-RI-001/C75-RI-003 W/DESORB/W; D8-->D5 |  | CM02- Heat stations, MU hv caps |  | CM11- Warm Couplers, Add BL spool/testing cap, peripherals | Mu shields, MLI | Disassemble Nb3Sn 1/4 | JL004 machining complete Welding return pipe assy, then HV | HB50- Weld CM Assy tooling from warehouse, clean
2020-09-12 | Sat |  |  | SNS Hv heads;
2020-09-13 | Sun |  |  | SNS Hv heads; | [19 empty] | D5: PPU01 C2.1K
2020-09-14 | Mon | Single Cell Repair |  | JL-007 post machining (LZ); C75-Doglegs (203, 120); SNS Hv heads; C75 End Dishes (1); |  |  | MAG-5 FF; |  | C75 Dogleg (120); HE samples; |  | C75 End Dishes; C75 Dogleg (120); | C75 End Dishes; C75 Dogleg (120); HEP parts; |  | New HEP Install; | HPR1: OOC HPR2: |  | C75 pair prep; | JL-006 (VSA); C75-RI-001/C75-RI-003 for CMM; | [5 empty] | D1: D2: D3: JL-006 pull; B-scan test L/C4K; D4: D5: PPU01 T/W; D6: D7: HE-353 C2K/T/W; D8: C75-RI-001/C75-RI-003 pull; |  | CM02- FSS, Heat stations, instrumentation |  | CM11- Warm Couplers, Testing cap/GHRP caps, peripherals | Mu shields, MLI | Disassemble Nb3Sn 1/4 | JL008 machine shop Welding return pipe assys/HV's Fab 2 Phase Tee's | HB50- Weld CM Assy tooling from warehouse, clean
2020-09-15 | Tue | Single Cell Repair |  | C75 inner adapter; |  |  | MAG-5 FF; HB-050; | Nb Samples x24 900C/10h; | C75 inner adapter; |  | C75 inner adapter; | C75 inner adapter; ion pump; C75 dogleg (203); L2 FPC header; |  | HF spike; | HPR1: OOC HPR2: C75-J-004 4P |  | C75 gate valves and end dishes; Dirty IP test; KEK-R5 leak test outside CR; | [6 empty] | D1: SIC L/C2K/T; D2: magnet test L/C4K; D3: B-scan test C4K/T/W; D4: D5: PPU01 warm; D6: D7: HE-353 warm; D8: |  | CM02- FSS, Heat stations, instrumentation |  | CM11- Warm Couplers, Testing cap/GHRP caps, peripherals | Mu shields, Prep for tuning | Disassemble Nb3Sn 1/4 | JL009 machine shop Welding return pipe assys/HV's Fab 2 Phase Tee's Turn over JL003 | HB50- Weld RF Measurements CM Assy tooling, clean
2020-09-16 | Wed | Single Cell Repair | P1 Windows; | JL-007 post machining; JL-003 post weld (#1); P1 cold waveguides (#2); C75-RI-001/C75-RI-003 (PM); |  |  | JL-003; | Nb Samples x24 900C/10h; | C75 Dogleg; |  | C75 Dogleg; | C75 inner adapter; HE-349 and parts; C75 Doglegs; SNS rail x2; |  | L2-234 install and test new end plates; | HPR1: OOC HPR2: HE-349; |  | plasma test stand (C100-XY); dirty IP test; | HE-349 bottom flange; | C75-J-004; | PPU01 RGA scans; C75-RI-001/C75-RI-003 roll out; |  |  |  | D1: SIC C2K/T; D2: magnet test hold; D3: B-scan test pull; D4: D5: PPU01 pull; D6: D7: HE-353 pull; D8: |  | CM02- FSS, Heat stations, instrumentation |  | CM11- Testing cap, MC lIne | CU1- Cavity tuning, reset fluxgates | Disassemble Nb3Sn 1/4 | JL006 machine shop Welding return pipe assys/HV's | HB50- Weld Alignment Crew, RF CM Assy tooling, clean
2020-09-17 | Thu | Single Cell Repair RF Separator set up | Cleanup run BB; | C75 elbows; C75 HOMs; C75-RI-001/C75-RI-003 (PM); |  |  | HB-050; | Nb Samples x24 900C/10h; | JL-003; HE samples; |  | JL-003 flanges & blanks; | JL-003 x2; JL-003 parts; SNS rail x2; Girder BPM; HD ICE SS; Ceramic samples; |  | New HEP Install; | HPR1: OOC HPR2: C75-RI-004 4P; |  | TS28-001 maint; TS28-003 maint; TS28-008 maint; | PPU01; | C75-J-004; HE-349 D7; |  |  |  |  | D1: SIC C2K/T; D2: magnet test hold; D3: D4: D5: D6: D7: D8: |  | CM02- instrumentation |  | CM11- RF WG's, MC lIne, Weld JT's | CU1- Prep for HV |  | Welding return pipe assys/HV's Next Cav JL007 | HB50- Freq Measurement CM Assy tooling, clean Dummy CM Arrives
2020-09-18 | Fri | RF Separator set up | BLA absorber load; | HE FTs; C75 HOMs; P1 windows (x7); C75-RI-001/C75-RI-003 (PM); |  |  | JL-007; |  | Dev. samples; |  | HE rings x3; | P1 windows; HB-50 (ext); C75 headers; |  | New HEP Install; | HPR1: OOC HPR2: JL-003 (4p) |  | cage JL-003 (chem rm); plasma test stand (C100-XY); |  | C75-RI-004/C75-J-004; | HE-349; |  |  |  | D1: SIC C2K/T/W; D2: magnet test hold; D3: B-scan L/C4K; D4: D5: D6: D7: D8: |  | CM02- Align Crew, move to WS4 |  | CM11- MC lIne LC, Weld JT's RT this Saturday 7am | CU1- Prep for HV |  | Welding return pipe assys/HV's JL007 Weld, LC, Turnover | Rework CM Assy tooling
2020-09-19 | Sat |  |  | C75-RI-001/C75-RI-003 | [23 empty] | RT LCLSII CM11
2020-09-20 | Sun |  |  | SNS He vessel heads FP end;
2020-09-21 | Mon | Single Cell Repair; RF Separator set up; | Girder pump drop parts; | JL-007 (1); C75-RI-001/C75-RI-003 (PM) SNS He vessel heads FP end; |  |  | PPU-03; |  | JL-007; Dev. samples; |  |  | Pump drops (x5); BLA absorber; IP & valve; C100-02; P1 HV plugs; |  | L2-234 setup/run; | HPR1: OOC HPR2: |  |  |  | HB-050 D5; JL-003 D3/4; | C75-RI-004/C75-J-004 leaks; HB-050 D5; |  | HE-349; |  | D1: SIC warm; D2: magnet test C4K; D3: B-scan C4K; D4: D5: HB-050 L; D6: D7: HE-349 L/C4K; D8: |  |  | CM02- Install RF cables | CM11- RF WG's, Bayonet Box | CU1/2- Instrumentation, torque |  | Welding return pipe assys/HV's JL004 Weld, LC, | Rework CM Assy tooling Dummy CM in today | SAD begins;
2020-09-22 | Tue | P1 windows; | P1 Windows; | C75 elbows (1); C75-RI-001/C75-RI-003 (PM); |  |  | PPU-02; |  | JL-007; Dev. samples; |  | JL-007 nitric flanges; JL-007 S/S parts; RF sep. end plates x3; SC weld prep; | PPU-01 and parts; JL-007 x2 and parts; RF sep. Cu x2; L2-234; |  | L2-234 dis; | HPR1: OOC HPR2: |  |  |  |  | JL-003; C75-RI-004/C75-J-004; |  |  |  | D1: SIC hold; D2: magnet test C2K/W; D3: B-scan pull; D4: D5: HB-050 C4K (2); D6: D7: HE-349 C2K/T/W (1); D8: |  |  | CM02- Install RF cables, FSS | CM11- Set warm couplers, MLI | CU1/2- Instrumentation, torque | LERF- Prep CM20 for move | Welding return pipe assys/HV's JL004 LC, Turnover JL005 Next |  | 4K warmup
2020-09-23 | Wed | P1 windows; | P1 Windows; | SNS He vessel heads; P1 windows (x14); P1 cold waveguides (LZ); | C75-Pair3 Trvlrs (PM) |  | C75 pair 3; JL-004; |  | Dev. samples; |  |  | MDC valves; BPM; L2 cold coupler parts; |  |  | HPR1: OOC HPR2: JL-007 (4P); |  | cage JL-007 (chem AM); |  | L2 BLA; | C75-RI-004/C75-J-004; |  |  |  | D1: SIC pull; D2: magnet test pull; D3: D4: D5: HB-050 C2K/test/warm; D6: D7: HE-349 warm; D8: |  |  | CM02- Install RF cables, Test fit lower shields | CM11- Bayonet Box Install/LC | CU1/2- Instrumentation, torque Receive CP3 | LERF- Prep CM20 for move | Welding return pipe assys/HV's JL009 Weld
2020-09-24 | Thu | P1 windows; |  | JL-004 (AM) P1 windows (x14); P1 cold waveguides (LZ); | SNS He vessel heads (Trvlrs); |  | J1.3-02 HOMs; |  | Dev. samples; |  | Nb3Sn HW; | IA-012; Cu gaskets; VAT HW; CEBAF BPM (x2); |  |  | HPR1: OOC HPR2: PPU-01 (2P); |  | blow-thru test setup (AP); |  | JL-007 D7/8; | L2 BLA; C75-RI-004/C75-J-004 heat and leak test; |  |  |  | D1: D2: TC L/C2K D3: maint D4: JL-003 L/C4K/W/maint; D5: HB-050 warm; D6: D7: HE-349 pull; B-scan load/C; D8: |  |  | CM02- Tune HOM's | CM11- Bayonet Box LC | CU1/2- Instrumentation, torque CU3- Install fluxgates | LERF- Prep CM20 for move | Welding return pipe assys/HV's JL009-LC/Turn over JL005-Weld
2020-09-25 | Fri | P1 windows; |  | P1 windows (9+5); P1 cold waveguides CMM; AD-Out | P1 cold waveguides (LZ); |  | J1.3-02 HOMS; |  | Dev. samples; | [5 empty] | HPR1: OOC HPR2: PPU-01 (2P); |  | PPU-01 D7/8; |  |  | JL-007; C75-RI-004/C75-J-004 heat and leak test; |  |  |  | D1: D2: TC T/W; D3: maint; D4: JL-003 maint; D5: HB-050 pull; D6: D7: B-scan C10K/W; D8: |  |  | CM02- Instrumentation checks, HOM Verification | CM11- Close VV, Instrumentation | CU1/2- Instrumentation-IP, torque CU3- Prep 4 tuners | LERF- Prep CM20, move into position | Welding return pipe assys/HV's JL005-LC Turn over | Modify SF Tooling
2020-09-26 | Sat |  |  | PPU-02; CMM Programming |  |  |  |  | JL-004;
2020-09-27 | Sun
2020-09-28 | Mon |  |  | JL-009 (1); P1 windows (9+5) (2); | P1 cold Waveguides (LZ); |  | EP-002 cal; JL-009 post weld; |  | Dev samples; |  | JL-004; | JL-004 (x2); TE1NS-001; |  |  | HPR1: OOC HPR2: TE1NS-001; |  |  |  | PPU-01 D7/8; | C75-RI-004/C75-J-004; JL-007; |  |  |  | D1: D2: TC pull; magnet test L/C4K/T; D3: maint, JL-003 L; D4: JL-003 pull, maint; D5: D6: D7: B-scan pull; JL-007 L/C4K; D8: |  |  | CM02- Instrumentation checks | CM11- Close VV, LC ins vac | CU1/2- Instrumentation-IP, torque CU3- Prep 4 tuners | LERF- Move CM20 to Test Lab | Welding return pipe assys/HV's JL006-Weld | Modify SF Tooling
2020-09-29 | Tue | RF Separator |  | P1 windows (9+5); PPU-02; PPU-03; C75 elbows; TBD C100 HOM FTs (~20); TBD SNS MagShield (2x7) TBD IA-012 straightening (TBD); | P1 cold waveguides (LZ); |  | JL-005 post-weld; J-1.3-02 HOMs; |  | Dev samples; |  | JL-004 blanks; Nb target; | HE-349; JL-004 blanks; |  |  | HPR1: OOC HPR2: Clean Room Work (Filters/Duct) |  | Clean Room Work (Filters/Duct); PPU String mock-up; | C75-RI-004/C75-J-004; | Clean Room Work (Filters/Duct); TE1NS-001 D6; | PPU-01; | PPU-01 120C/24h; |  |  | D1: SIC L/C2K; D2: magnet test C2K/T D3: JL-003 L/C4K; D4: maint; D5: D6: D7: JL-007 C2K/T/W; D8: B-scan L/C4K; |  |  | CM02- HOM Verification, weld lower shields | CM11- LC ins vac, Into CMTF | CU1/2- torque, Install remaining Mu shields CU3- Install tuners | Crate LCLSII Ins Vac Bellows | Welding return pipe assys/HV's JL006-turn-over JL008- Weld | Modify SF Tooling
2020-09-30 | Wed | RF Separator |  | JL-005; |  |  | C75-J-005 FF; | [7 empty] | HPR1: OOC HPR2: Clean Room Work (Filters/Duct) JL-004 (4P); |  | Clean Room Work (Filter/Duct); PPU String mock-up; | HE-349 prep for HPR; C75-RI-004/C75-J-004; | Clean Room Work (Filters/Duct) | TE1NS-001; | PPU-01 120C/24h; | TE1NS-001; |  | D1: SIC C2K; D2: D3: JL-003 C2K/T/W; D4: maint; D5: D6: D7: JL-007 warm; D8: B-scan C4K; |  |  | CM02- weld lower shields, Into VV | CM11- LC ins vac, align CM20- Move to WS5 | CU1- Set tuners, prep 4 HV CU2- Remain Mu shields CU3- Install tuners | Crate LCLSII Ins Vac Bellows | Welding return pipe assys/HV's JL008- Weld | Modify SF Tooling
2020-10-01 | Thu | High Q0 single cell repair; | [9 empty] | HE-349 parts; |  | C75-J-005 setup; | HPR1: OOC HPR2: HE-349 (2P); |  |  | C75-RI-004/C75-J-004; | JL-004 D?; PPU-02 D7/8; |  |  | HE Rolled tubes |  | D1: SIC C2K; D2: D3: JL-003 warm; D4: HE rolled tubes L/TC; D5: D6: TE1NS-001 L/SC4K/T D7: JL-007 pull; PPU-01 L/C4K; D8: B-scan C4K;
2020-10-02 | Fri | maint. |  | JL-006; | [7 empty] | C75-J-005; |  | C75-J-005 25u; | HPR1: OOC HPR2: |  |  |  | HE-349; | PPU-02; | PPU-02 120C/24h; |  |  | D1: SIC C2K; D2: D3: JL-003 pull; D4: HE rolled tubes TC; D5: D6: TE1NS-001 C2K/T/W; D7: PPU-01 C2K/T/W; D8: B-scan C4K;
2020-10-03 | Sat | [19 empty] | PPU-02 120C/24h;
2020-10-04 | Sun
2020-10-05 | Mon | maint. | [6 empty] | C75-J-005 flanges?; | [5 empty] | HPR1: OOC HPR2: |  |  |  |  | HE-349; |  |  |  | D1: SIC C2K?; D2: D3: D4: D5: D6: D7: PPU-01 pull; PPU-02 L/C4K; D8: B-scan pull; HE-349 L/C4K;
2020-10-06 | Tue |  |  | JL-008; | [10 empty] | HPR1: OOC HPR2: | [8 empty] | CMTF U-tubes D1: D2: D3: D4: D5: D6: D7: D8:
2020-10-07 | Wed | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-10-08 | Thu |  |  | EP-002; | [10 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-10-09 | Fri | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-10-10 | Sat
2020-10-11 | Sun
2020-10-12 | Mon | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-10-13 | Tue | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-10-14 | Wed | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-10-15 | Thu | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-10-16 | Fri | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-10-17 | Sat
2020-10-18 | Sun
2020-10-19 | Mon | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-10-20 | Tue | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-10-21 | Wed | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-10-22 | Thu | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-10-23 | Fri | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-10-24 | Sat
2020-10-25 | Sun
2020-10-26 | Mon | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-10-27 | Tue | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-10-28 | Wed | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-10-29 | Thu | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-10-30 | Fri | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-10-31 | Sat
2020-11-01 | Sun
2020-11-02 | Mon | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-11-03 | Tue | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-11-04 | Wed | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-11-05 | Thu | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-11-06 | Fri | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-11-07 | Sat
2020-11-08 | Sun
2020-11-09 | Mon | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-11-10 | Tue | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-11-11 | Wed | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-11-12 | Thu | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-11-13 | Fri | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-11-14 | Sat
2020-11-15 | Sun
2020-11-16 | Mon | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-11-17 | Tue | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-11-18 | Wed | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-11-19 | Thu | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:
2020-11-20 | Fri | [13 empty] | HPR1: OOC HPR2: | [8 empty] | D1: D2: D3: D4: D5: D6: D7: D8:

## Priorities (hidden)
Project/Activity | SRF Owner | Priority 1, 2, or 3 | Description / Explanation | Project Account Code
C75 refurbishment | K. Macha | 1 | Refurbishment of a C20 cryomodule for CEBAF.
LCLSII production | K. Davis | 1 | 21 cryomodules for SLAC | L2CCPT
LCLSII R&D | Ari | 1 | material suitability for production
NB3Sn | G. Eremeev | 1
SIC | G. Eremeev | 2
RRR | A-M Valente-Feliciano | 2
SNS MB-002 | S. Williams | 2 |  | SNSCV3, (SNSCV2)
DQW2 | Naeem | 3
RFD | HyeKyoung | 3
EIC1, EIC5 | Marhauser | 1
LCLSII HE | Reece | 2
CERN1, CERN5 | Marhauser | 2
ILC Cost Reduction | Reece | 2
High Q0 R&D | Pashupati
Twin | HyeKyoung | 3

## Stands (hidden)
Test Stand Tracking
| Serial # |  | TS28-001 | TS28-002 | TS28-003 | TS28-004 | TS28-005 | TS28-006 | TS28-007 | TS16-007 | TS28-008 | TS28-009 | TS28-010 | TS28-011
| Date |  | 7 cell | ILC/ Thermometry stand Slow Pump-down Throttle | (7 cell use) D-3 or D-4 | (7 cell use) D-3 or D-4 Future Nb3Sn Test Stand | Laser light stand, Currently (D-5 Adapter ring installed) | ILC/ Slow Pump-down Throttle | ILC Stand | Anne-Marie Stand w/ 28" dewar adapter ring installed | 7 cell Future Ball Lightning Test Stand | 7 cell Future Crab Cavity Test Stand | 7 cell | ILC Thermometry
Mon | 2011-01-31
Tue | 2011-02-01
Wed | 2011-02-02 |  | C100-1H | 9 cell seamless | 1500 MHz | C100-2H | GiGi | PKU-2 | C100-8 | MT | MT | MT | MT
Thu | 2011-02-03 |  | C100-1H | 9 cell seamless | 1500 MHz | C100-2H | GiGi | PKU-2 | C100-9 | CC-B1 | C100-17H | C100-13H
Fri | 2011-02-04 |  | C100-1H | 9 cell seamless | 1500 MHz | C100-2H | GiGi | PKU-2 | C100-10 | CC-B1 | C100-17H | C100-13H
Sat | 2011-02-05 |  |  | 9 cell seamless | 1500 MHz | C100-2H | GiGi | PKU-2 | C100-11 | CC-B1 | C100-17H | C100-13H
Sun | 2011-02-06 |  | TS28-003: 1500 MHz; TS28-004: C100-19H; TS28-005: GiGi; TS28-006: PKU-2; TS16-007: CC-B1; TS28-008: C100-17H; TS28-009: C100-13H
Mon | 2011-02-07 |  | TS28-003: 1500 MHz; TS28-004: C100-19H; TS28-005: GiGi; TS28-006: PKU-2; TS16-007: CC-B1; TS28-008: C100-17H; TS28-009: C100-13H
Tue | 2011-02-08 |  | TS28-003: 1500 MHz; TS28-004: C100-19H; TS28-005: GiGi; TS28-006: PKU-2; TS16-007: CC-B1; TS28-008: C100-17H; TS28-009: C100-13H
Wed | 2011-02-09 |  | TS28-003: 1500 MHz; TS28-004: C100-19H; TS28-005: GiGi; TS28-006: PKU-2; TS16-007: CC-B1; TS28-008: C100-17H; TS28-009: C100-13H
Thu | 2011-02-10 |  | TS28-003: 1500 MHz; TS28-004: C100-19H; TS28-005: GiGi; TS28-006: PKU-2; TS16-007: CC-B1; TS28-008: C100-17H; TS28-009: C100-13H
Fri | 2011-02-11 |  | TS28-003: 1500 MHz; TS28-004: C100-19H; TS28-005: GiGi
Sat | 2011-02-12 |  | TS28-001: C100-18H; TS28-003: 1500 MHz; TS28-004: C100-19H; TS28-005: GiGi
Sun | 2011-02-13 |  | TS28-001: C100-18H; TS28-003: 1500 MHz; TS28-004: C100-19H; TS28-005: GiGi
Mon | 2011-02-14 |  | TS28-001: C100-18H; TS28-003: 1500 MHz; TS28-004: C100-19H; TS28-005: GiGi
Tue | 2011-02-15 |  | TS28-001: C100-18H; TS28-003: 1500 MHz; TS28-004: C100-19H; TS28-005: GiGi
Wed | 2011-02-16 |  | TS28-001: C100-18H; TS28-003: C100-17H; TS28-004: C100-19H; TS28-005: GiGi; TS28-008: C100-20H
Thu | 2011-02-17 |  | TS28-001: C100-18H; TS28-003: C100-17H; TS28-004: C100-19H; TS28-005: GiGi; TS28-008: C100-20H
Fri | 2011-02-18 |  | TS28-001: C100-18H; TS28-003: C100-17H; TS28-004: C100-19H; TS28-005: GiGi; TS28-007: DESY-9cell; TS28-008: C100-20H
Sat | 2011-02-19 |  | TS28-001: C100-18H; TS28-003: C100-17H; TS28-005: GiGi; TS28-007: DESY-9cell; TS28-008: C100-20H
Sun | 2011-02-20 |  | TS28-001: C100-18H; TS28-003: C100-17H; TS28-005: GiGi; TS28-007: DESY-9cell; TS28-008: C100-20H
Mon | 2011-02-21 |  | TS28-001: C100-18H; TS28-003: C100-17H; TS28-005: GiGi; TS28-007: DESY-9cell; TS28-008: C100-20H
Tue | 2011-02-22 |  | TS28-003: C100-17H; TS28-005: GiGi; TS28-007: DESY-9cell; TS28-008: C100-20H
Wed | 2011-02-23 |  | TS28-003: C100-17H; TS28-004: C100-21H; TS28-005: GiGi; TS28-007: DESY-9cell
Thu | 2011-02-24 |  | TS28-004: C100-21H; TS28-005: GiGi; TS28-007: DESY-9cell
Fri | 2011-02-25 |  | TS28-004: C100-21H; TS28-005: GiGi
Sat | 2011-02-26 |  | TS28-004: C100-21H
Sun | 2011-02-27 |  | TS28-004: C100-21H
Mon | 2011-02-28 |  | TS28-004: C100-21H
Sun | 2011-07-24
Mon | 2011-07-25
Tue | 2011-07-26
Wed | 2011-07-27
Thu | 2011-07-28
Fri | 2011-07-29
Sat | 2011-07-30
Sun | 2011-07-31
Mon | 2011-08-01
Tue | 2011-08-02
Wed | 2011-08-03 | Wed | TS28-001: C100-41; TS28-002: RI-23; TS28-004: TE1AES001; TS28-005: LASER; TS28-006: NR1; TS16-007: BEP-1; TS28-009: C100-39
Thu | 2011-08-04 | Thu | C100-41 | RI-23 |  | TE1AES001 | LASER | NR1 |  | BEP-1 | J100-2 | C100-39
Fri | 2011-08-05 | Fri | C100-41 | RI-23 | 650-A | TE1AES001 | LASER | NR1 |  | Fansteel | J100-2 | C100-39
Sat | 2011-08-06 | Sat | C100-41 |  | 650-A | TE1AES001 | LASER | NR1 |  | Fansteel | J100-2 | C100-39
Sun | 2011-08-07 | Sun | TS28-001: C100-41; TS28-003: 650-A; TS28-004: TE1AES001; TS28-005: LASER; TS28-006: NR1; TS28-008: J100-2; TS28-009: C100-39
Mon | 2011-08-08 | Mon | C100-41 |  | 650-A | TE1AES001 | LASER | NR1 |  |  | J100-2 | C100-39 | C100-43H
Tue | 2011-08-09 | Tue | TS28-001: C100-42H; TS28-003: 650-A; TS28-005: LASER; TS28-006: NR1; TS28-008: J100-2; TS28-009: C100-39; TS28-010: C100-43H
Wed | 2011-08-10 | Wed | TS28-001: C100-42H; TS28-003: 650-A; TS28-005: LASER; TS28-006: NR1; TS28-008: J100-2; TS28-009: C100-39; TS28-010: C100-43H
Thu | 2011-08-11 | Thu | TS28-001: C100-42H; TS28-005: LASER; TS28-008: J100-2; TS28-009: C100-44H; TS28-010: C100-43H
Fri | 2011-08-12 | Fri | TS28-001: C100-42H; TS28-004: C100-40H; TS28-005: LASER; TS28-008: J100-2; TS28-009: C100-44H; TS28-010: C100-43H
Sat | 2011-08-13 | Sat | TS28-001: C100-42H; TS28-004: C100-40H; TS28-009: C100-44H; TS28-010: C100-43H
Sun | 2011-08-14 | Sun | TS28-001: C100-42H; TS28-004: C100-40H; TS28-009: C100-44H; TS28-010: C100-43H
Mon | 2011-08-15 | Mon | TS28-001: C100-42H; TS28-004: C100-40H; TS28-009: C100-44H; TS28-010: C100-43H
Tue | 2011-08-16 | Tue | TS28-001: C100-42H; TS28-004: C100-40H; TS28-008: C100-45H; TS28-009: C100-44H
Wed | 2011-08-17 | Wed | TS28-001: C100-42H; TS28-004: C100-40H; TS28-008: C100-45H; TS28-009: C100-44H
Thu | 2011-08-18 | Thu | TS28-004: C100-40H; TS28-008: C100-45H; TS28-010: C100-46H
Fri | 2011-08-19 | Fri | TS28-004: C100-40H; TS28-008: C100-45H; TS28-010: C100-46H
Sat | 2011-08-20 | Sat | TS28-008: C100-45H; TS28-010: C100-46H
Sun | 2011-08-21 | Sun | TS28-008: C100-45H; TS28-010: C100-46H
Mon | 2011-08-22 | Mon | TS28-001: C100-39H; TS28-008: C100-45H; TS28-010: C100-46H
Tue | 2011-08-23 | Tue | TS28-001: C100-39H; TS28-008: C100-45H; TS28-010: C100-46H
Wed | 2011-08-24 | Wed | TS28-001: C100-39H; TS28-006: MHI-8; TS28-008: C100-45H; TS28-010: C100-46H
Thu | 2011-08-25 | Thu | TS28-001: C100-39H; TS28-006: MHI-8; TS28-009: C100-8H; TS28-010: C100-46H
Fri | 2011-08-26 | Fri | TS28-001: C100-39H; TS28-006: MHI-8; TS28-009: C100-8H
Sat | 2011-08-27 | Sat | TS28-001: C100-39H; TS28-006: MHI-8; TS28-009: C100-8H
Sun | 2011-08-28 | Sun | TS28-001: C100-39H; TS28-006: MHI-8; TS28-009: C100-8H
Mon | 2011-08-29 | Mon | TS28-001: C100-39H; TS28-006: MHI-8; TS28-009: C100-8H
Tue | 2011-08-30 | Tue | TS28-006: MHI-8; TS28-009: C100-8H
Wed | 2011-08-31 | Wed | TS28-006: MHI-8; TS28-009: C100-8H
Thu | 2011-09-01 | Thu | TS28-006: MHI-8
Fri | 2011-09-02 | Fri | bar: TS28-006 to TS16-007
Sat | 2011-09-03 | Sat | bar: TS28-006 to TS16-007
Sun | 2011-09-04 | Sun | bar: TS28-006 to TS16-007
Mon | 2011-09-05 | Mon | bar: TS28-006 to TS16-007
Tue | 2011-09-06 | Tue | bar: TS28-006 to TS16-007
Wed | 2011-09-07 | Wed | bar: TS28-006 to TS16-007
Thu | 2011-09-08 | Thu | bar: TS28-006 to TS16-007
Fri | 2011-09-09 | Fri | bar: TS28-006 to TS16-007
Sat | 2011-09-10 | Sat | bar: TS28-006 to TS16-007
Sun | 2011-09-11 | Sun | bar: TS28-006 to TS16-007
Mon | 2011-09-12 | Mon | bar: TS28-006 to TS16-007
Tue | 2011-09-13 | Tue | bar: TS28-006 to TS16-007

## L2 Cavity Status (hidden)
String ID | Cavity 1 | Cavity 2 | Cavity 3 | Cavity 4 | Cavity 5 | Cavity 6 | Cavity 7 | Cavity 8 | Material | Cavity ID | Location | Type | Status | Performance | Path Forward | Column1
J1.3-5 | L2-048 | L2-057 | L2-072 | L2-061 | L2-062 | L2-079 | L2-075 | L2-080 |  | L2-201 | Jlab | Production | field emitted, rinsed, field emitted | Q0(16) = 2.2e10 | undefined
J1.3-6 | L2-053 | L2-056 | L2-087 | L2-059 | L2-060 | L2-089 | L2-088 | L2-094 |  | L2-202 | Jlab | Production | Possible defect in end cell(s) | quenching at 14.9 MV/m | undefined
J1.3-7 | L2-264 | L2-090 | L2-112 | L2-082 | L2-123 | L2-124 | L2-271 | L2-273 |  | L2-208 | Jlab | Production | field emitted, low Q0 | Flat Q0 2e10 | undefined
J1.3-8 | L2-289 | L2-113 | L2-099 | L2-106 | L2-102 | L2-130 | L2-122 | L2-270 |  | L2-225 | Llab | Production | rinsed retested, field emitted again | FE onset 17 MV/m, Q0 rollover | undefined
J1.3-9 | L2-133 | L2-279 | L2-131 | L2-118 | L2-281 | L2-097 | L2-295 | L2-125 |  | L2-210 | Jlab | Production | awaiting rise, retest | FE onset 12 MV/m, Q0(16) = 2.3e10 | undefined
J1.3-10 | L2-297 | L2-327 | L2-138 | L2-310 | L2-276 | L2-288 | L2-306 | L2-134 |  | L2-024 | Jlab | Production | scratched iris, | FE onset 6 MV/m | undefined
J1.3-11 | L2-135 | L2-328 | L2-332 | L2-330 | L2-308 | L2-140 | L2-137 | L2-167 |  | L2-048 | Jlab | Production | Jlab qualified after re-rinse |  | String 5
J1.3-12 | L2-152 | L2-153 | L2-156 | L2-278 | L2-165 | L2-166 | L2-155 | L2-254 |  | L2-057 | Jlab | Production | Desy Qualified |  | String 5
J1.3-13 | L2-253 | L2-144 | L2-304 | L2-314 | L2-243 | L2-255 | L2-319 | L2-157 |  | L2-061 | Jlab | Production | Desy Qualified |  | String 5
J1.3-14 | L2-315 | L2-322 | L2-168 | L2-252 | L2-169 | L2-325 | L2-247 | L2-251 |  | L2-062 | Jlab | Production | Desy Qualified |  | String 5
J1.3-15 | L2-245 | L2-261 | L2-151 | L2-305 | L2-025 | L2-056 | L2-059 | L2-272 | NX-900 | L2-072 | Jlab | Production | Jlab qualified |  | String 5
J1.3-16 | L2-506 | L2-505 | L2-509 | L2-218 | L2-219 | L2-515 | L2-170 | L2-224 |  | L2-073 | Jlab | Production | incoming completed, bad HOMs? PICs removed | untested | undefined
J1.3-17 | L2-518 | L2-520 | L2-522 | L2-523 | L2-208 | L2-504 | L2-542 | L2-514 | NX-900 | L2-075 | Jlab | Production | Jlab qualified |  | String 5
J1.3-18 | L2-531 | L2-532 | L2-094 | L2-538 | L2-539 | L2-541 | L2-073 | L2-077 | NX-900 | L2-079 | Jlab | Production | Jlab qualfied |  | String 5
J1.3-19 | L2-345 | L2-086 | L2-078 | L2-089 | L2-085 | L2-087 | L2-344 | L2-064 | NX-900 | L2-080 | Jlab | Production | Jlab qualified |  | String 5
J1.3-20 | L2-074 | L2-159 | L2-088 | L2-160 | L2-146 | L2-105 | L2-104 | L2-109 | NX-900 | L2-082 | Jlab | Production | cleanroom | Clean to 24MV, Q0(16) = 2.5e10 | String 7
J1.3-21 | [8 empty] | NX-900 | L2-083 | Jlab | Production | Low Q0 in D7, PICs removed | 18700000000 | undefined
J1.3-06R | [8 empty] | TD | L2-053 | Jlab | Production | Desy Qualified, D5 | 24 MV/m; Qo(16MV/m)=3.2e10, FE onset 9.5MV/m, 1R/hr at 16.5MV/m | String 6; rinse, VTRF, rinse VTRF
J1.3-09R | [8 empty] | TD | L2-056 | Jlab | Production | Desy Qualified, cleanroom | 24 MV/m; Qo(16MV/m)=3.3e10, 3.1e10, quench 23.3 MV/m | String 6; rinse, VTRF, Qualified
[9 empty] | TD | L2-059 | Jlab | Production | Desy Qualified, D5 qualified 6/29 | 22.6 MV/m; Qo(16MV/m)=3e10, Q0(16) 3.5e10, quench 23.5MV/m | String 6; rinse, VTRF, qualified
[9 empty] | TD | L2-060 | Jlab | Production | Desy Qualified, D5 | 23 MV/m; Qo(16MV/m)=3.1e10, Q0(16) 3.0e10, quench at 18.5MV/m with FE spikes, possibly MP | String 6; rinse, VTRF, rinse VTRF
[9 empty] | NX-900 | L2-063 | Jlab | Production | Low Q0 in D7; PICs removed | 20.4 MV/m; Q0(16MV/m)= 2.1e10 | undefined
[9 empty] | NX-900 | L2-087 | Jlab | Production | DESY tested, received | Q0(16)=2.4e10; Emax=19.5 MV/m | undefined
String Candidates | [8 empty] | NX-900 | L2-088 | Jlab | Production | DESY tested, received | Q0(16)=2.5e10; Emax=23.3 MV/m | undefined
L2-060* | L2-118** | L2-295** | L2-543 |  | L2-201 | L2-536 |  |  | NX-900 | L2-089 | Jlab | Production | DESY tested, received | Q0(16)=2.4e10; Emax= 21.6 MV/m | undefined
L2-053* | L2-120 | L2-333 |  |  | L2-209 | L2-268 |  |  | NX-900 | L2-090 | Jlab | Production | Jlab qualified after retest (failed Q0 at DESY) | Q0(16)=2.8e10; Emax=24.0 MV/m | String 7
L2-083 | L2-125** | L2-334 |  |  | L2-210 | L2-063 |  |  | NX-900 | L2-084 | FNAL | Production | Shipped to FNAL 6/7 |  | N/A
L2-097** | L2-133** | L2-337 |  |  | L2-211 | L2-299 |  |  | NX-900 | L2-092 | FNAL | Production | Shipped to FNAL 6/7 |  | N/A
L2-103 | L2-147 | L2-338 |  |  | L2-502 | L2-242 |  |  | TD | L2-094 | Jlab | Production | qualified 6/16. Failed (FE) 7/2 in D8 | Initial FE 9.4MV/m. 2nd 4un FE 14MV/m. | String 6; rinse, VTRF. Full dis, rinse, VTRF, Qualified-->String 18;
| L2-279** | L2-341 |  |  | L2-508 | L2-220 |  |  | NX-900 | L2-104 | Jlab | Production | Jlab tested, failed | Q0(16)=2.2e10; Emax=24.0 MV/m | undefined
L2-115 … | L2-281** | L2-342 |  |  |  | L2-227 |  |  | TD | L2-262 | FNAL | Production | at Jlab, to be shipped from Jlab to FNAL |  | N/A
L2-116 | L2-286 | L2-343 |  |  | L2-526 | L2-346?
* string 6 | [8 empty] | TD | L2-263 | FNAL | Production | at Jlab, to be shipped from Jlab to FNAL |  | N/A
**String 9 | [8 empty] | TD | L2-264 | Jlab | Production | qualified 7/14 | Q0(16)=3.5e10, Emax=24.0 MV/m | String 7
[9 empty] | TD | L2-265 | Jlab | Production | Optical Inspection | Quenching at 15.2 MV/m | Optical inspection cell 5 cat-eye…
[9 empty] | NX-C | L2-229 | Jlab | bare R&D | in cleanroom | 24 MV/m; Q0(16) = 3.3e10 | He Vessel welding?
[9 empty] | TD | L2-244 | Jlab | bare R&D | in cleanroom | Q0(16) = 3.4E10, admin limited to 24 MV/m | He Vessel welding?
[9 empty] | NX-B | L2-209 | Jlab | Production | failed VTRF | Q0(16) = 2e10, quenching at 17.8 MV/m | undefined
[9 empty] | NX-B | L2-211 | Jlab | Production | failed VTRF | Q0(16) below 2e10, quenching at 19 MV/m | rework
[9 empty] | NX-900 | L2-109 | Jlab | Production | in cleanroom | Q0(16)=2.4e10; Emax = 24 MV/m | FPC flange staining USE AS IS, undefined
[9 empty] | NX-900 | L2-112 | Jlab | Production | qualified | Q0(16)= 2.6e10; Emax = 24 MV/m; FE on 18 MV/m | String 7
[9 empty] | TD | L2-268 | Jlab | Production | in cleanroom | Q0(16)~ 2.6e10; Quenching at 17.3 MV/m, FE free | Retest D7 due to magnetic fields
[9 empty] | TD | L2-271 | Jlab | Production | in cleanroom | Q0(16) = 3.2e10; Emax = 24 MV/m; no FE | String 7
[9 empty] | TD | L2-272 | Jlab | Production | in cleanroom. D7 qualified 7/3 | Q0(16) = 4e10; Emax = 24 MV/m; FE onset 16 MV/m, Q0(16) ~ 3.1e10, FE on 18 MV/m, FE on 22 MV/m. Q0(16) 2.7e10, Emax 29.4 MV/m, no FE. | full dis, rinse, VTRF D7/8; full dis, rinse, VTRF D7/8; full dis, rinse, VTRF D7/8; String 15
[9 empty] | TD | L2-273 | Jlab | Production | in cleanroom | Q0(16) = 3.3e10; Emax = 24 MV/m; FE on 19.5 MV/m | String 7
[9 empty] | NX-B950 | L2-099 | Jlab | Production | cleanroom | Q0(16) = 3.3e10; quench 18.8 MV/m; no FE | string 8
[9 empty] | NX-B950 | L2-101 | Jlab | Production | incoming completed | untested; received 89% field flat | tuning, HPR, assy, VTRF D7/8
[9 empty] | NX-B950 | L2-102 | Jlab | Production | cleanroom | Q0(16)~4e10, quench limited 21.2 MV/m, FE free, | incoming RF inspection, 2xrinse, VTRF D7/8 string 8
[9 empty] | TD | L2-260 | Jlab | Production |  | Quenching 15.2 MV/m | optical inspection
[9 empty] | TD | L2-261 | Jlab | Production | in cleanroom | Q0 3.1E10, admin limit @24, FE onset @ 21.2; quench 32.7MV/m. No FE. Q0(16)3.05e10 | full dis, rinse, leaky FP; VTRF D5; Qualified
[9 empty] | NX-900 | L2-097 | Jlab | Production | cleanroom | Q0(16)~2.8e10, quench 20.2 MV/m, FE free | string 9
[9 empty] | NX-900 | L2-113 | Jlab | Production | cleanroom | Q0(16)~2.e10, quench limited 22.3MV/m , FE free | string 9
[9 empty] | NX-900 | L2-118 | Jlab | Production | cleanroom | Q0(16)~2.6e10, admin limited 24 MV/m, FE free | rinse, VTRF D7/8 string 9
[9 empty] | NX-900 | L2-116 | Jlab | Production | D5 bellows test | Q0(16)~2.7e10, admin limited 24 MV/m , FE free | rinse, VTRF
[9 empty] | NX-900 | L2-122 | Jlab | Production | cleanroom | Q0(16)~2.5e10, admin limited 24 MV/m , FE free | string 8
[9 empty] | TD | L2-123 | Jlab | Production | cleanroom | Q0(16)~2.7e10, quench limited 21.5MV/m , FE free | string 7
[9 empty] | TD | L2-124 | Jlab | Production | cleanroom | Q0(16)~3.5e10, admin limited 24 MV/m , FE free | string 7
[9 empty] | NX-B950 | L2-106 | Jlab | Production | cleanroom | Q0(16)~4.1e10, , quench limited 20.2 MV/m, FE free | incoming insp, VTRF D5, string 9
[9 empty] | TD | L2-125 | Jlab | production | cleanroom | Q0(16)~2.5e10, admin limited 24 MV/m , FE free | incoming insp, VTRF D5, string 9
[9 empty] | NX-C975 | L2-128 | Jlab | production | cleanroom | Q0(16)~3.3e10, quench limited 17.8 MV/m, FE free | incoming insp, VTRF D7/8, optical inspection
[10 empty] | L2-234 | Jlab | R&D bare 9-cell | shipping/receiving | untested | beadpull, assy, vtrf
[10 empty] | L2-238 | Jlab | R&D bare 9-cell | VAA, on TS28-006 | Q0(16)~2.8e10, quench 21.7MV/m , FE on 11MV/m | beadpull, assy, vtrf, full dis, rinse, VTRF D7/8
[9 empty] | TD | L2-270 | Jlab | Production | cleanroom | Q0(16)~3.3e10, admin limited 24 MV/m, FE free | string 8
[9 empty] | TD | L2-278 | Jlab | Production | cleanroom | Q0(16)~3.6e10, quench limited 28 MV/m, FE free; D5 Quench at 25.2MV/m. No FE. Q0(16)2.4e10 | Bellows rinse test D5, Full disassembly, rinse VTRF D7/8, dented HOM, VTRF D5; VTRF D7/8, string 9
[9 empty] | NX-900 | L2-279 | Jlab | Production | cleanroom | Q0(16)~2.6e10, admin limited 24 MV/m, FE free | string 9
[9 empty] | NX-900 | L2-281 | Jlab | Production | cleanroom | Q0(16)~2.7e10, admin limited 24 MV/m, FE free | VTRF D7/8, String 9
[9 empty] | NX-C975 | L2-130 | Jlab | Production | cleanroom | Q0(16)~3.1e10, quench 20.5 MV/m, FE free | String 9
[9 empty] | NX-C975 | L2-131 | Jlab | Production | cleanroom | Q0(16)~2.9e10, quench 21.6 MV/m, FE free | String 9, damaged bellows
[9 empty] | NX-C975 | L2-133 | Jlab | Production | cleanroom | Q0(16)~3.9e10, quench 21.2 MV/m, FE free | String 9
[9 empty] | NX-A | L2-284 | Jlab | Production | cleanroom | Q0(15)~2.5e10, quench 15 MV/m, FE free | vent, beadpull, full dis, rinse, VTRF D7/8, visual insp
[8 empty] | ? | NX-A | L2-286 | Jlab | Production | cleanroom | Q0(16)~2.8e10, admin limited 24 MV/m, FE free, bellows test; FE on 7.5MV/m; | Bellows rinse test D5, Full disassembly, rinse VTRF D5; full dis, rinse, VTRF D7/8;
[9 empty] | NX-A | L2-288 | Jlab | Production | cleanroom | Q0(16)~3.2e10, admin limited 24 MV/m, FE free | incoming insp, VTRF D7/8, rinse, VTRF D7/8, rinse, VTRF D7/8, string 10
[8 empty] | EZ PICs | TD-950 | L2-276 | Jlab | Production | cleanroom | Q0(16)~3.4e10, admin limited 24 MV/m, FE free | incoming insp, leaky burst disk, VTRF D7/8 , rinse, VTRF D7/8,
[8 empty] | EZ PICs | NX-B | L2-297 | Jlab | Production | cleanroom | Q0(16)~3.6e10, admin limited 24 MV/m, FE free | incoming insp, VTRF D7/8;string 10
[8 empty] | EZ PICs | NX-B | L2-295 | Jlab | Production | cleanroom | Q0(16)~3.1e10, admin limited 24 MV/m; FE free | incoming insp, VTRF D7/8; string 9
[8 empty] | EZ PICs | NX-B | L2-299 | Jlab | Production | cleanroom | FE onset 4 MV/m; Q0(16)~2.3e10, FE onset 23 MV/m, Quench 23 MV/m; | incoming insp, new FP, rinse, VTRF D7/8, degrease, rinse, VTRF D7/8; undefined
[8 empty] | incentive | NX-A | L2-304 | Jlab | Production | cleanroom | FE onset 4 MV/m, FE onset 8 MV/m, Q0(16)~2.7e10, FE free, quench 23.1 MV/m | incoming insp, new FP, rinse, VTRF D7/8, sample, degrease, rinse, VTRF D7/8, rerinse, VTRF D7/8; Qualfied
[8 empty] | incentive | NX-A | L2-305 | Jlab | Production | cleanroom | D5 Q0(16) 2.7e10, Quench 24.5 MV/m, FE on 22 MV/m, Q2 1.5e12, FE ON 6.5 MV/m; quench 26.9MV/m. No FE. Q0(16)3.3e10, HOMs & FP high; Q0(16)~2.8e10, no FE, Quench 24.2 MV/m | incoming insp, VTRF D5, VTRF D7/8, rinse, VTRF D5, rinse, VTRF, rinse, VTRF D5, replace FP & HOM FTs, VTRF; Qualified;
[8 empty] | incentive | NX-A | L2-306 | Jlab | Production | cleanroom | D5 Q0(16) 3.0e10. No FE. Admin limit at 24MV/m. | incoming insp, VTRF D5, string 10
[8 empty] | incentive | NX-A | L2-308 | Jlab | Production | cleanroom | D7 Q0(16) 2.9e10, no FE, quench 25 MV/m | incoming insp, VTRF D5, rinse, VTRF D7/8, string 11
[9 empty] | TD | L2-134 | Jlab | Production | cleanroom | Q0(16) 3.1e10, FE free, quench 23.5 MV/m | incoming insp, VTRF D7/8, string 10
[9 empty] | TD | L2-135 | Jlab | Production | cleanroom | Q0(16)~3.6e10, FE free, quench 19.8 MV/m | incoming insp, VTRF D7/8, string 11
[9 empty] | TD | L2-137 | Jlab | Production | cleanroom | Q0(16)~3.5e10, quench limited 24.5 MV/m, FE free | incoming insp, VTRF D7/8, rinse, VTRF D7/8
[9 empty] | TD | L2-138 | Jlab | Production | cleanroom | Q0(16) 3.1e10, FE free, quench 23.5 MV/m | incoming insp, VTRF D7/8, string 10
[8 empty] | incentive | NX-A | L2-293 | Jlab | Production | cleanroom | Quenching at 13.6 MV/m | incoming insp, VTRF D5, optical inspection
[8 empty] | incentive | A & EG B | L2-310 | Jlab | Production | cleanroom | Q0(16) 2.6e10, FE free, quench 22.4 MV/m | incoming insp, VTRF D7/8, string 10
[8 empty] | incentive | A/B | L2-314 | Jlab | Production | cleanroom | Q0(16)~2.5e10, FE onset 11.5 MV/m, Q0(16)~3.4e10, FE free, quench 21.5 MVm | incoming insp, VTRF D5, full dis, rinse, VTRF D7/8, qualified
[8 empty] | incentive | TD | L2-327 | Jlab | Production | cleanroom | Q0(16)~2.8e10, FE free, quench 25.5 MV/m | incoming insp, VTRF D5, string 10
[9 empty] | TD | L2-328 | Jlab | Production | cleanroom | Q0(16)~3.2e10, quench 23.7 MV/m, FE free | incoming insp, VTRF D5, string 11
[9 empty] | NX?950 | L2-330 | Jlab | Production | cleanroom | Q0(16)~3.3e10, quench 23.4 MV/m, FE free | incoming insp, VTRF D5, string 11
[9 empty] | NX-A/B950 | L2-331 | Jlab | Production | cleanroom | Q0(16)~1.8e10, quench 30.6 MV/m, FE onset 28 MV/m | incoming insp, VTRF D5, undefined
[9 empty] | TD/NX950 | L2-332 | Jlab | Production | cleanroom | Q0(16)~2.7e10, quench 23.4 MV/m, FE free | incoming insp, VTRF D7/8, string 11
[9 empty] | NX-900 | L2-115 | Jlab | Production | cleanroom | FE onset 2 MV/m | incoming insp, VTRF D7/8, undefined
[9 empty] | TD | L2-140 | Jlab | Production | cleanroom | Q0(16)~2.5e10, quench 28.0 MV/m, FE free | incoming insp, VTRF D5, fpc flange stains, string 11,
[9 empty] | TD | L2-144 | Jlab | Production | cleanroom | Q0(16)~2.9e10, quench 25.4 MV/m, FE free | incoming insp, VTRF D5, FE, rinse, VTRF, qualified
[9 empty] | rework | L2-145 | Jlab | Production | cleanroom | Q0(16)~1.7e10, quench 23 MV/m, FE free | incoming insp, VTRF D5, undefined
[9 empty] | rework | L2-146 | Jlab | Production | VAA | Quench 18 MV/m. No FE. | incoming insp, VTRF, undefined
[9 empty] | rework | L2-147 | Jlab | Production | D5 | untested | incoming insp, VTRF
[9 empty] | rework | L2-148 | Jlab | Production |  | untested | incoming insp, VTRF
[9 empty] | rework | L2-149 | Jlab | Production |  | untested | incoming insp, VTRF
[9 empty] | TD | L2-152 | Jlab | Production | cleanroom | Q0(16) 3.1e10, FE free, quench 24.5 MV/m | incoming insp, VTRF D7/8, string 12
[9 empty] | TD | L2-153 | Jlab | Production | cleanroom | Q0(16) 3.2e10. Quenched at 20 MV/m. No FE | incoming insp, VTRF D7/8, string 12
[9 empty] | TD | L2-155 | Jlab | Production | cleanroom | Q0(16) 3.3e10, quench 22.3 MV/m, No FE | incoming insp, VTRF D7/8, string 12
[9 empty] | TD | L2-156 | Jlab | Production | cleanroom | Q0(16)~2.7e10, quench 23.5 MV/m, no FE | incoming insp, VTRF D7/8, string 12
[9 empty] | TD | L2-165 | Jlab | Production | cleanroom | Quench ~ 25.5MV/m. No FE. Q0(16)3.5e10 | incoming insp, VTRF D7/8, string 12
[9 empty] | TD | L2-166 | Jlab | Production | cleanroom | Quench ~ 27MV/m. No FE. Q0(16)2.7e10 | incoming insp, VTRF D7/8, String 12
[9 empty] | TD | L2-167 | Jlab | Production | cleanroom | Q0(16) 2.80e10, quench at 23.9MV/m. No FE | incoming insp, VTRF D5, String 11
[8 empty] | Rincentive | TD | L2-253 | Jlab | Production | cleanroom | Q0(16) 3.2e10, no FE, Quench 22.8 MV/m | incoming insp, VTRF D7/8, full dis, new FP, rinse, VTRF D5, Qualified
[8 empty] | Rincentive | TD | L2-315 | Jlab | Production | cleanroom | Q0(16) 2.9e10, quench at 21.2MV/m. No FE. Cold leak, Q2 6e10 Q0(16) 2.9E10, quench 20.3, no FE | incoming insp, VTRF D5, full dis, CMM, new FP, rinse, VTRF D7/8; Qualified
[8 empty] | Rincentive | TD | L2-321 | Jlab | Production | cleanroom | Q0(12) 2.5e10, quench 12 MV/m, FE free | incoming insp, VTRF D7/8, inspection, measure FP
[8 empty] | Rincentive | TD | L2-325 | Jlab | Production | cleanroom | Q0(16) 2.3e10, quench at 21MV/m. No FE, Q0(16)~3.4e10, quench 22.1 MV/m, no FE | incoming insp, VTRF D5, VTRF D7/8, qualified
[8 empty] | Rincentive | TD | L2-250 | Jlab | Production | cleanroom | Q0(12)=2.7e10, quench at 14.5 MV/m; no FE | incoming insp, VTRF D7/8, bad input cable, VTRF D7/8, inspection
[8 empty] | Rincentive | TD | L2-252 | Jlab | Production | cleanroom | Q0(16)~2.6e10, quench limited 19.5 MV/m; no FE, Q2 5e10; FE onset 7 MV/m, Q2 1e12; Q0(16)~3.9e10, Quench 19 MV, FE free | incoming insp, VTRF D7/8, new FP, rinse, VTRF D7/8, rinse, VTRF D7/8, qualified;
[8 empty] | Rincentive | TD | L2-254 | Jlab | Production | cleanroom | Q0(16)~2.7e10, quench limited 20.5 MV/m; no FE | incoming insp, VTRF D7/8, String 12
[8 empty] | Rincentive | TD | L2-319 | Jlab | Production | cleanroom | Q0(16)~3.0e10, quench limited 20.8 MV/m, no FE, Q2 5e10; 3.3e10, 21.5 MV/m, 9.8e11 | incoming insp, VTRF D5, full dis, new FP, rinse, VTRF D7/8; qualfied
[9 empty] | TD | L2-242 | Jlab | Production | cleanroom | Q0(16)~3.1e10, quench limited 17 MV/m; no FE | incoming insp, VTRF D5, undefined
[9 empty] | TD | L2-243 | Jlab | Production | cleanroom | Q0(16)~2.9e10, quench limited 23.5 MV/m; no FE | incoming insp, VTRF D5, qualified
[9 empty] | TD | L2-255 | Jlab | Production | cleanroom | Q0(16)~3.2e10, quench limited 23.3 MV/m; no FE | incoming insp, VTRF D5, qualified
[9 empty] | TD | L2-322 | Jlab | Production | cleanroom | Q0(16)~2.76e10, quench limited 18.9 MV/m; no FE, Q2=3.14e11 | incoming insp, VTRF D5, qualified as per project
[9 empty] | TD | L2-151 | Jlab | Production | cleanroom | Q0(16)~3.61e10, FE onset@18 MV/m then @8MV/m, Q2=4.12e11, FE onset 16 MV/m, Q0(16)~3.1e10, FE free, quench 23.5 MV/m | incoming insp, VTRF D5, full dis, rinse, VTRF D7/8; full dis, rinse, VTRF D7/8; qualified
[9 empty] | TD | L2-157 | Jlab | Production | cleanroom | Q0(16)~3.2e10, quench limited 21.2 MV/m; no FE, Q2=2.4e11 | incoming insp, VTRF D5, qualified
[9 empty] | TD | L2-168 | Jlab | Production | cleanroom | Q0(16)~3.1e10, mode mix limited 23.5 MV/m, no FE | incoming insp, VTRF D5, qualified
[9 empty] | TD | L2-169 | Jlab | Production | cleanroom | Q0(16)~3.0e10, quench 23.2 MV/m, no FE | incoming insp, VTRF D5, retest D5, Qualified
[9 empty] | TD | L2-245 | Jlab | Production | cleanroom | Q0(16)~2.8e10, quench 21.6 MV/m, no FE, Q2 9.5e10; Q0(16)~2.9e10, quench 21.7 MVm; | incoming insp, VTRF D5, swap FP, VTRF D7/8; Qualified
[9 empty] | TD | L2-246 | Jlab | Production | cleanroom | Q0(15)~2.9, quench 15.2 MV/m, no FE | incoming insp, VTRF D5, undefined
[9 empty] | TD | L2-247 | Jlab | Production | cleanroom | Q0(16)~2.8e10, quench 21.0 MV/m, no FE | incoming insp, VTRF D5, qualified
[9 empty] | TD | L2-251 | Jlab | Production | cleanroom | Q0(16)~3.2e10, quench 19.2 MV/m, no FE | incoming insp, VTRF D5, qualified
[9 empty] | TD | L2-025 | Jlab | Production | cleanroom | Q0(16)~4.1e10, quench 24.0 MV/m, no FE | incoming insp, VTRF D5, qualified
[9 empty] | NX-C | L2-201 | Jlab | Production | cleanroom VSA TS34-002 | Q0(16)~3.5e10. Quench 16.2 MV/m. No FE. | incoming insp, VTRF D5, Vent. Set aside
[9 empty] | NX-B | L2-209 | Jlab | Production | cleanroom VSA TS34-002 | Q0(16)~2.7e10. Quench 17.6 MV/m. No FE. | incoming insp, VTRF D5. Vent. Set aside
[9 empty] | NX-B | L2-210 | Jlab | Production | incoming insp. Cleanroom. TS34-002 D5 | Q0(16)~2.6e10. Quench 17.7 MV/m. No FE. | incoming insp, VTRF D5. Vent. Set aside
[9 empty] | NX-B | L2-211 | Jlab | Production | incoming insp TS34-002 D5, cleanroom | Q0(15.2)~3e10. Quench at 15.5MV/m. No FE. | incoming insp, VTRF D5 VTRF D5. 5u EP, VTRF D8, Remove PICS, Use as is
[9 empty] | TD | L2-521 | JLab | R&D bare 9-cell | cleanroom D7, cleanroom | 5mG: Q0(16)~3.7e10. Quench 21.5MV/m. FE processed away. 20mG: Q0(16)~2.8e10. Quench 20.2 MV/m. No FE. | incoming RF; VTRF D7
[9 empty] | TD | L2-527 | JLab | R&D bare 9-cell | D8 | 20mG: Q0(16)~2.45e10. Quench 23.8 MV/m. No FE. 5mG: Q0(16)~2.8e10. Quench 24MV/m. No FE. | incoming RF; VTRF D7/8
[9 empty] | NX-B | L2-206 | Jlab | production | incoming insp TS28-008 D7/8, cleanroom | Q0(13.5)~3.2e10. Quench 13.5MV/m. No FE. | VTRF D7/8 , Remove PICS, Set aside
[9 empty] | NX-B | L2-207 | Jlab | production | incoming insp TS34-002 D5, cleanroom | Q0(14.7)~3.3e10. Quench 14.8MV/m. No FE | VTRF D5. Set aside
[9 empty] | NX-B | L2-208 | Jlab | production | TS34-001 in D5; cleanroom; | Q0(16)~2.5e10. Quench 17.5MV/m. No FE; Q0(16)~2.9e10. Quench 20.5MV/m. No FE | VTRF D5. 5u EP, VTRF, string 17
[9 empty] | NX-C | L2-212 | Jlab | production | TS34-001 in D5; | Q0(14.3)~2.4e10. Quench 14.5MV/m. No FE. | VTRF D5. 5u EP, VTRF
[9 empty] | TD | L2-502 | Jlab | production | shipping damage? D5 TS34-001, cleanroom | Quench 18 MV/m. No FE. | incoming insp, VTRF D5. Optical inspection?
[9 empty] | TD | L2-503 | Jlab | production | shipping damage? D5 TS34-001, cleanroom | Quench 13.4 MV/m. No FE. | incoming insp, VTRF D5. VTRF with HOM blanks, all passbands;
[9 empty] | TD | L2-505 | Jlab | production | D5 TS34-001 cleanroom | Q0(16)~3.9e10. Quench 23.6 MV/m. No FE. | incoming insp, VTRF D5. Qualified.
[9 empty] | TD | L2-506 | Jlab | production | D8 TS28-008, cleanroom | Q0(16)~3.4e10. Quench 25.3 MV/m. No FE. | incoming insp, VTRF D8. Qualified.
[9 empty] | TD | L2-508 | Jlab | production | TS28-010 VSA | Q0(16)~3.9e10. Quench 19MV/m. No FE. (questionable cable connection) Q0(16)~3.6e10. Quench 17.8MV/m. No FE. | incoming insp, VTRF D5. Go back to D7/8, Need HOM survey, re-test to confirm performance. Set aside
[9 empty] | TD | L2-509 | Jlab | production | cleanroom TS34-002 VSA, cleanroom | Q0(16)~4.5e10. Quench 19.5MV/m. No FE. | incoming insp, VTRF D5. Qualified.
[9 empty] | TD | L2-217 | Jlab | production | incoming insp, TS34-001 in D5; cleanroom | Q0(15.4)~2.7e10. Quench 15.3MV/m. No FE. | VTRF D5. Set aside.
[9 empty] | TD | L2-218 | Jlab | production | incoming insp, VSA TS28, cleanroom | Q0(16)~2.5e10, Quench 24.1 MV/m, no FE | VTRF D7, Qualified
[9 empty] | TD | L2-219 | Jlab | production | incoming insp, D8, cleanroom | Q0(16)~2.8e10, Quench 24.0 MV/m, no FE | VTRF D7/8; Qualified
[9 empty] | TD | L2-220 | Jlab | production | incoming insp, VSA TS34, | Q0(16)~2.8e10, Quench 17.5 MV/m, no FE | VTRFT D5; undefined
[9 empty] | TD | L2-515 | Jlab | production | incoming insp, D7, cleanroom | Q0(16)~3.0e10, quench 24.3 MV/m, no FE | VTRF D8, Qualified
[9 empty] | TD | L2-520 | Jlab | production | incoming insp, VSA TS34, | Q0(16)~3.4e10, quench 24.0 MV/m, no FE | VTRFT D5; Qualified
[9 empty] | TD | L2-518 | Jlab | production | incoming insp, VSA TS34, | Q0(16)~3.0e10, quench 25.3 MV/m, no FE | VTRFT D5; Qualified
[9 empty] | TD | L2-170 | Jlab | production | incoming insp, D8, | Q0(16)~3.0e10, quench 25.5 MV/m, no FE | incoming insp, VTRF D8, Qualified
[9 empty] | TD | L2-024.1 | Jlab | pre-qual bare 9-cell | incoming insp, D7, cleanroom, tuning room |  | incoming insp, VTRF D7, passed, ship to Zanon
[9 empty] | NX-A | L2-213 | Jlab | production | incoming insp, D7, cleanroom | Q0(16)~3.1e10, quench 14.5 MV/m, no FE | incoming insp., VTRF D7/8, undefined
[9 empty] | TD | L2-224 | Jlab | production | incoming insp, D5, cleanroom | Q0(16)~2.9e10, quench 23.8 MV/m, no FE | incoming insp, VTRF D5, qualified
[9 empty] | NX-B | L2-227 | Jlab | production | incoming insp, D8, cleanroom | Q0(16)~4.2e+10, quench 18.1 MV/m, no FE | incoming insp, VTRF D7/8; undefined
[9 empty] | NX-B | L2-228 | Jlab | production | incoming insp, D5, cleanroom | Q0(16)~3.0e+10, quench 16.2 MV/m, no FE | incoming insp, VTRF D5, undefined
[9 empty] | NX-B | L2-231 | Jlab | production | incoming insp, D5, cleanroom | Q0(15)~2.3e10, quench 15.2 MV/m, no FE | incoming insp, VTRF D5, undefined
[9 empty] | TD | L2-522 | Jlab | production | incoming insp, D5, cleanroom | Q0(16)~3.8e10, quench 24.3 MV/m, no FE | incoming insp, VTRF D5; qualified
[9 empty] | TD | L2-523 | Jlab | production | incoming insp D5, cleanroom | Q0(16)~3.9e10, quench 25.2 MV/m, no FE | incoming insp, VTRF D5; qualified
[9 empty] | TD | L2-542 | Jlab | production | incoming insp, D5 | HOMB~1e9 | incoming insp, VTRF D5; tune HOM, retest VTRF
[9 empty] | TD | L2-543 | Jlab | production | cleanroom | Q0(16)~3.8e10, quench 25.0 MV/m, FE on 11 MV/m; M-parameter NCR | incoming insp, VTRF D7/8; VTRF D7/8; HPR; VTRF D7/8;
[9 empty] | TD | L2-504 | Jlab | production | incoming insp; D5, cleanroom | Q0(16)~3.9e10, quench 23.1 MV/m, no FE; | string 17
[9 empty] | TD | L2-526 | Jlab | production | incoming insp; D5, cleanroom | Q0(16)~3.4e10, quench 17.9 MV/m, no FE; undefined | incoming insp, VTRF D5, undefined
[9 empty] | TD | L2-531 | Jlab | production | incoming insp; D5, cleanroom | Q0(16)~3.4e10, quench 23.1 MV/m, no FE; qualified
[9 empty] | TD | L2-532 | Jlab | production | incoming insp; D5, cleanroom | Q0(16)~2.5e10, quench 25.3 MV/m, no FE; qualified
[9 empty] | TD | L2-514 | Jlab | Production | incoming insp; D5, cleanroom | Q0(16)~2.9e10, quench 22.6 MV/m, no FE; qualified | incoming insp, VTRF
[9 empty] | TD | L2-536 | Jlab | Production | incoming insp; D5, VSA | Q0(16)~3.1e10, quench 25.5 MV/m, FE onset 16 MV/m | incoming insp, VTRF, rinse, retest
[9 empty] | TD | L2-538 | Jlab | Production | incoming insp; D5, VSA | Q0(16)~3.2e10, quench 24.5 MV/m, no FE, qualified | incoming insp, VTRF
[9 empty] | TD | L2-539 | Jlab | Production | incoming insp; D5, VSA | Q0(16)~3.0e10, quench 25.0 MV/m, no FE, qualified | incoming insp, VTRF
[9 empty] | TD | L2-541 | Jlab | Production | incoming insp; D5, cleanroom | Q0(16)~2.9e10, quench 28.0 MV/m, no FE, qualified | incoming insp, VTRF
[9 empty] | TD | L2-064 | Jlab | Production | incoming insp; D5 | Q0(16): 3.5e10, Quench at 20.5 MV/m, no FE | incoming insp, VTRF
[9 empty] | TD | L2-074 | Jlab | Production | incoming insp; D5 | Q0(16): 2.8e10; Quench at 21 MV/m, no FE | incoming insp, VTRF
[9 empty] | TD | L2-145 | Jlab | Production | incoming insp; D5 | Quench at 14.5 MV/m | incoming insp, VTRF
[9 empty] | TD | L2-146 | Jlab | Production | incoming insp; | Quench 18.5 MV/m, Q0(16)~3.5e10, no FE, | incoming insp, VTRF, undefined; string 20
[10 empty] | L2-073 | Jlab | Production | incoming insp; D5, cleanroom | Q0(16)~3.4e10, quench 22.0 MV/m, no FE, qualified
[10 empty] | L2-077 | Jlab | Production | incoming insp; D5, cleanroom | Q0(16)~3.1e10, quench 26.0 MV/m, no FE, qualified
[10 empty] | L2-078 | Jlab | Production | incoming insp; | 078 passed, quench 25.9MV, no FE,
[10 empty] | L2-086 | Jlab | Production | incoming insp; | 086 qualified. Q0(16)~3.5e10, FE free
[10 empty] | L2-343 | Jlab | Production | incoming insp;
[10 empty] | L2-344 | Jlab | Production | incoming insp; D5, cleanroom | Q0(16)~4e10, quench limited 19.2 MV/m, FE free, | Qualified
[10 empty] | L2-346 | Jlab | Production | incoming insp; beadpull;
[10 empty] | L2-345 | Jlab | Production |  | L2-345 quenching at 19.6MV, Q0(16)~3.7e10, no radiation
[10 empty] | L2-089 | Jlab | Production | incoming insp; D5, VSA | Q0(16)~3.4e10, quench 24.1 MV/m, no FE, qualified;
[10 empty] | L2-105 | Jlab | Production | incoming insp; D5, VSA | Q0(16)~2.6e10, quench 24.9, FE onset 15.4 MV/m; Q0(16)~3.6e10, Quench 22.3MV/m, no FE. | HPR, VTRF, Qualified
[10 empty] | L2-085 | Jlab | Production | incoming insp; D5, VSA | Q0(16)~3e10, quench 27.6 MV/m, no FE, qualified;
[10 empty] | L2-347 | Jlab | Production | incoming insp; D5, cleanroom | Q0(16)~3.2e10, quench limited 17.3 MV/m, FE free, | undefined; string 20
[9 empty] | 3 | L2-348 | Jlab | Production | incoming insp; D8, cleanroom | Q0(16)~3.8e10, quench 16.8 MV/m, FE free | undefined
[9 empty] | 1 | L2-159 | Jlab | Production | incoming insp | Q0(16): 3.2e10, Quench at 23 MV/m, no FE | Qualified
[9 empty] | 1 | L2-160 | Jlab | Production | incoming insp | Q(16): 2.7e10, Quench at 19.5 MV/m, no FE | Qualified
[9 empty] | 2 | L2-063 | Jlab | Production | incoming insp | Q0(16): 2.6e10, Quench at 18.2 MV/m, no FE | undefined
[9 empty] | 2 | L2-083 | Jlab | Production | incoming insp | Q0(16): 2.9e10, Final quench at 22 MV/m, FE 0.5 R/hr | rinse, VTRF
[9 empty] | 2 | L2-103 | Jlab | Production | incoming insp
[9 empty] | 2 | L2-115 | Jlab | Production | incoming insp, D5 | Q0(16)~3.1e10 FE on 12 MV/m, rad limited 20 MV/m
[10 empty] | L2-087 | Jlab | Production | incoming insp; D5, cleanroom | Q0(16)~3.2e10, quench limited 24 MV/m, FE free, | Qualified
[9 empty] | 2 | L2-088 | Jlab | Production | received, incoming insp | Q(16): 3.1e10, Quench at 23.5 MV/m, no FE | Qualified
[9 empty] | 2 | L2-109 | Jlab | Production | received, incoming insp, D5 | Q0(16)~2.4e10, quench 22.8 MV/m, no FE | String 20
[9 empty] | 2 | L2-104 | Jlab | Production | received, incoming insp, D5 | Q0(16)~2.4e10, quench 21 MV/m, no FE | String 20
[9 empty] | 2 | L2-120 | Jlab | Production | received, incoming insp, D5
[9 empty] | 2 | L2-116 | Jlab | Production | received, incoming insp, D5
[9 empty] | 3 | L2-333 | Jlab | Production | received, incoming insp
[9 empty] | 3 | L2-334 | Jlab | Production | received, incoming insp
[9 empty] | 3 | L2-337 | Jlab | Production | received
[9 empty] | 3 | L2-338 | Jlab | Production | received
[9 empty] | 3 | L2-341 | Jlab | production | received
[9 empty] | 3 | L2-342 | Jlab | production | received
[9 empty] | 3 | L2-295 | Jlab | production | received
[9 empty] | 3N60 | HE-353 | Jlab | R&D bare 9-cell | VAA | quench 17 MV/m
[9 empty] | 3N60 | HE-352 | Jlab | R&D bare 9-cell | VAA | Q0(15) ~3.2e10, no FE, quench 15.9 MV/m
[9 empty] | 2N0 | HE-364 | Jlab | R&D bare 9-cell | VAA | Q0(16) 3.2e10, FE onset 18.8MV/m, quench 22.5
[9 empty] | 2N0 | HE-349 | Jlab | R&D bare 9-cell | warming
[9 empty] | 3N60 | HE-354 | Jlab | R&D bare 9-cell
[9 empty] | 3N60 | HE-351 | Jlab | R&D bare 9-cell

## Milestones
Week of | Work Days | C75-01 | C75-02 | P1 | SNS PPU | LCLS2 | LCLS HE | CEBAF Support | Maint | CTF Loads
2020-08-17 | 5 | [8 empty] | VTA, UITF
2020-08-24 | 5 | 3rd pair leak check; |  | Cavities & WG | HV shells & heads inspect; String mockup prep; HB-050 HV welding; | BLAs; J1.3-011 HOM; tuning; | HE-353 dis/insp; SC-16 VTRF; SC-15 VTRF; |  | Clnrm maint 26/27 | VTA, UITF
2020-08-31 | 5 | 3rd pair dis, prep |  | post machining cavity insp/test; VTRF; | First cavity arrives; | BLAs; | HE-353 assy; |  | HEP new endgroup; Wed cranes maint. | VTA, UITF
2020-09-07 | 4 | 3rd pair desorb; |  | post machining cavity insp/test; VTRF; | PPU-01 incoming inspection | BLAs; | HE-353 assy; |  |  | VTA, UITF
2020-09-14 | 5 | 4th pair assy; |  | Post welding cavity inspection; | PPU-01 VTRF; HB-050 VTRF; PPU-02, -03 arrive; | BLAs; | HE-353 VTRF; |  | modifications | VTA, UITF
2020-09-21 | 5 | 3rd pair CMM |  | Post welding cavity inspection; Qual test VTRF; | HB-050 VTRF; | BLAs (x2); BLA returns from SLAC (x3); | HE-349 VTRF; | CEBAF girder prep; | HEP in production; SAD | VTA, UITF
2020-09-28 | 5 | 4th pair test; 3rd pair turnover; | Cavities arrive; | VTRF; | PPU-01 re-VTRF; String mockup | J1.3-011 into CMTF; J1.3-020 prep for ship; | HE-351 arrives under vaccum VTRF; SC-11 arrives under vacuum VTRF; | CEBAF girder prep; LINAC warm-up and U-tubes; | SAD | VTA, UITF; Clnrm filters;
2020-10-05 | 5 | 4th pair CMM; 4th pair turnover; |  | VTRF; | Tank PPU-01; PPU-04, 05 arrive; PPU-02 bare VTRF; BL bellows (2+4); | J1.3-002 to WS-5; J1.3-011 CD CMTF; |  |  | SAD | VTA, CMTF?
2020-10-12 | 5 |  |  | VTRF; | Tank PPU-01; PPU-03 bare VTRF; |  |  | New VAT valves cleaning (x25); | SAD | VTA, CMTF?
2020-10-19 | 5 |  |  | VTRF; | Tank PPU-02; PPU-06, 07 arrive; PPU-04 bare VTRF; PPU-01 tanked VTRF; | J1.3-020 ships; | Rolled tubes for FE; Single cells (ready to test) (x6); |  | SAD | VTA, CMTF?
2020-10-26 | 5 |  |  | String Assy | Tank PPU-02; PPU-05 bare VTRF; PPU-02 tanked VTRF; |  |  | girder removal and disassembly; | SAD | VTA, CMTF?
2020-11-02 | 5 |  |  | String Assy | String 1 assy prep; |  |  | girder rework; | SAD | VTA, CMTF?
2020-11-09 | 5 |  |  | String Assy |  | J1.3-002 ships; |  | girder rework; | SAD | VTA, CMTF?
2020-11-16 | 5 | [6 empty] | girder rework; | SAD | VTA, CMTF?
2020-11-23 | 3 | [7 empty] | SAD | VTA, CMTF?
2020-11-30 | 5 | [7 empty] | SAD | VTA, CMTF?
2020-12-07 | 5 | [7 empty] | SAD | VTA, UITF
2020-12-14 | 5 | [7 empty] | SAD | VTA, UITF
2020-12-21 | 2 | [7 empty] | SAD | VTA, UITF
2020-12-28 | 0 | [7 empty] | SAD | VTA, UITF
2021-01-04 | 5 | [7 empty] | SAD | VTA, UITF
2021-01-11 | 5 | [7 empty] | SAD | VTA, UITF
2021-01-18 | 5 |  |  |  | String 1 complete; |  |  |  | SAD | VTA, UITF
2021-01-25 | 5 | [7 empty] | SAD | VTA, UITF
2021-02-01 | 5 | [7 empty] | SAD | VTA, UITF
2021-02-08 | 5 | [7 empty] | SAD | VTA, UITF
2021-02-15 | 5 | [7 empty] | SAD | VTA, UITF
2021-02-22 | 5 | [7 empty] | SAD | VTA, UITF
2021-03-01 | 5 | [7 empty] | SAD | VTA, UITF
2021-03-08 | 5 | [7 empty] | SAD | VTA, UITF
2021-03-15 | 5 | [7 empty] | SAD | VTA, UITF
2021-03-22 | 5 | [7 empty] | SAD | VTA, UITF
2021-03-29 | 5 | [7 empty] | SAD | VTA, UITF
2021-04-05 | 5 | [7 empty] | SAD | VTA, UITF
2021-04-12 | 5 |  | All cavities qualified; | [5 empty] | SAD | VTA, UITF
2021-04-19 | 5 | [7 empty] | SAD | VTA, UITF
2021-04-26 | 5 | [7 empty] | SAD | VTA, UITF

## R&D Medcon 5
X
Approved by AS (date) | Priority | Research Program | Funding source (Project) | PI names | Persons involved | Solo person activities | Distancing no issue | Requires non-cleanroom tech support | Requires additional cleanroom garb | Requires cleanroom tech support | Requires occasional COVID-PPE
2020-07-06 | 1 | SRF thin film research - Phase 1 - no cleanroom wk, no COVID-PPE, single-person activities, incld. 1 authorized W&M student | ARDTHF ECA-AM ARDNB3 | AMVF, UP | AMVF, RB, UP | X | X | X
2020-07-06 | 1 | Complete vertical test of LSF9-1 with second sound sensors, waiting since March - US-Japan | ATUJ03 | RG | RG | X | X | X |  | dismount allowed
2020-07-06 | 1 | ODU graduate student Nb3Sn R&D sputter process R&D | ECA-GE CAVNB3 | CR | NS | X | X
2020-07-14 | 2 | LDRD Cavity production needs for OCD1 | LD2005 | FM | FM | X | X
2020-07-14 | 2 | Magnetic field mapping of SRF cavities - VTA | NSF/ ARDPRJ | GC | IP | X | X | X
2020-07-14 | 2 | Window ceramic bench measureents - RF lab | ARDPRJ | JG | JG | X | X
2020-07-14 | 2 | 2.45 GHz magnetron measureemnt - test Lab mezzanine | ADMAG | HW | HW | X | X
2020-07-21 | 3 | Nb3Sn cavity pair work for Quarter CM - non cleanroom wk | ECA-GE | Macha | SRF Ops | X | X | X
2020-07-31 | 3 | Harmonic kicker fabrication EBW tests | FOA | HW | HW, GP, SSO, ebw (Jim F.) | X | X | X
2020-07-31 | 3 | JLEIC crab cavity ebw tests | ODU | HP | HP, ebw (Jim F.) | X | X | X
2020-07-31 | 3 | Flux pinning strength as a function of Nb metallurgical history - cavity fab. | ARDQ0 | PD | PD | X | X | X
2020-07-31 | 3 | N-doping sample research | ECA-AP | AP | AP, HT, RM, JS | X | X | X
2020-07-31 | 3 | Fab new US-Japan LSF 9-cell cavities (2) | ATUJ04 | RG | RG, SW, shop | X | X | X
2020-07-31 | 3 | Half wave coax fabrication | ODU | HP | HP, ebw (Jim F.) | X | X | X
| 3 | 915 MHz magnetron turn on in LERF lab 1 | MAGRFS | HW | HW, KJ, safety | 2 people | X
| 4 | Nb3Sn cavity pair work for Quarter CM - Includes pair assembly | ECA-GE | Macha | SRF Ops |  |  | X | X | X | X
| 4 | Nitrogen "infusion" research - cavity chemistry, furnace, VTA | ARDQ0 RDFNAL | CR | PD | X | X | X | X
| 4 | SBIR support - superclamp for clean assembly - expires 9/30 | HYPC&T | CR | GB, ops techs | X | X | X
| 4 | Flux pinning strength as a function of Nb metallurgical history - student work - incld. VTA work | ARDQ0 | PD | PD | X | X | X | X | X
| 4 | SRF thin film research - Phase 2- cleanroom work required, cavity testing, no COVID-19 PPE | ARDTHF ECA-AM ARDNB3 | AMVF, UP | AMVF, RB, UP | X | X | X | X | X
| 5 | Misc. other R&D work that requires cleanroom use for cavity prep - students, WFO, LDRD, etc. | ARDPRM CAVNB3 misc. | CR, HT, FM,NS, ... | FM, HT, NS, ... | X | X | X | X | X
| 6 | Nb3Sn Quarter CM assembly | ECA-GE | Macha | SRF Ops |  |  | X | X | X | X

## L2 Strings Completed (hidden)
Andrew's List
String ID | Cavity 1 | Cavity 2 | Cavity 3 | Cavity 4 | Cavity 5 | Cavity 6 | Cavity 7 | Cavity 8 | CAV0026 | 21.1 | 37274701400 | TD | 900 | FNAL
J1.3-5 | L2-048 | L2-057 | L2-072 | L2-061 | L2-062 | L2-079 | L2-075 | L2-080 | CAV0040 | 23 | 33024085600 | TD | 900 | FNAL
J1.3-6 | L2-053 | L2-056 | L2-087 | L2-059 | L2-060 | L2-089 | L2-088 | L2-094 | CAV0066 | 13.7 | Quench Before | NX | 975 | FNAL
J1.3-7 | L2-264 | L2-090 | L2-112 | L2-082 | L2-123 | L2-124 | L2-271 | L2-273 | CAV0097 | 20.1 | 29702454700 | NX | 900 | JLab | From J9
J1.3-8 | L2-289 | L2-113 | L2-099 | L2-106 | L2-102 | L2-130 | L2-122 | L2-270 | CAV0103 | 25.8677 | 17708468820 | NX | 950 | JLab
J1.3-9 | L2-133 | L2-279 | L2-131 | L2-118 | L2-281 | L2-097 | L2-295 | L2-125 | CAV0114 | 15 | Quench Before | NX | 900 | FNAL
J1.3-10 | L2-297 | L2-327 | L2-138 | L2-310 | L2-276 | L2-288 | L2-306 | L2-134 | CAV0118 | 24.1 | 25652437800 | NX | 900 | JLab | From J9
J1.3-11 | L2-135 | L2-328 | L2-332 | L2-330 | L2-308 | L2-140 | L2-137 | L2-167 | CAV0119 | 16.5 | 25609133500 | NX | 900 | FNAL
J1.3-12 | L2-152 | L2-153 | L2-156 | L2-278 | L2-165 | L2-166 | L2-155 | L2-254 | CAV0125 | 24.1 | 24500000000 | TD | 900 | JLab | From J9
J1.3-13 | L2-253 | L2-144 | L2-304 | L2-314 | L2-243 | L2-255 | L2-319 | L2-157 | CAV0128 | 19.2 | 33803510200 | NX | 975 | JLab
J1.3-14 | L2-315 | L2-322 | L2-168 | L2-252 | L2-169 | L2-325 | L2-247 | L2-251 | CAV0132 | 16.8 | 39702302400 | NX | 975 | FNAL
J1.3-15 | L2-245 | L2-261 | L2-151 | L2-305 | L2-025 | L2-056 | L2-059 | L2-272 | CAV0133 | 21.3 | 38873924400 | NX | 975 | JLab | From J9
J1.3-16 | L2-506 | L2-505 | L2-509 | L2-218 | L2-219 | L2-515 | L2-170 | L2-224 | CAV0145 | 14.5 | Quench Before | NX | 950 | JLab
J1.3-17 | L2-518 | L2-520 | L2-522 | L2-523 | L2-208 | L2-504 | L2-542 | L2-514 | CAV0147 | 13.2677 | Quench Before | NX | 900 | JLab
J1.3-18 | L2-531 | L2-532 | L2-094 | L2-538 | L2-539 | L2-541 | L2-073 | L2-077 | CAV0149 | 16.6602 | 32855220300 | NX | 950 | FNAL
J1.3-19 | L2-345 | L2-086 | L2-078 | L2-089 | L2-085 | L2-087 | L2-344 | L2-064 | CAV0503 | 13.37 | Quench Before | TD | 900 | JLab
J1.3-20 | L2-074 | L2-159 | L2-088 | L2-160 | L2-146 | L2-105 | L2-104 | L2-109 | CAV0508 | 17.5 | 35787279860 | TD | 900 | JLab
J1.3-21 | L2-083 | L2-116 | L2-120 | L2-333 | L2-334 | L2-338 | L2-341 | L2-065 | CAV0536 | Needs Re-rinse |  |  |  | JLab
J1.3-06R | L2-068 | L2-115 | L2-343 | L2-347 | L2-502 | L2-220 | L2-053 | L2-279
J1.3-09R | L2-063 | L2-060 | L2-286 | L2-346 | L2-543 | L2-211 | L2-348 | L2-214 | Liang's list
J1.3-11R | L2-328 | L2-332 | L2-167 | L2-140 | L2-268 | L2-308 | L2-137 | L2-330 | L2-242, 17.2 MV/m, Q0(16) 3.1e10, no FE.
L2-128, 17.8 MV/m, Q0(16) 3.4e10, no FE.
L2-109, 22.4 MV/m, Q0(16) 2.4e10, no FE.
L2-210, 17.7 MV/m, Q0(16) 2.6e10, no FE.

## L2 String Candidates (hidden)
Rank | Material | Group | Vendor | Cavity ID | Location | Type | Status | Performance | Path Forward | Column1
? | TD! |  | Zanon | L2-348 | Jlab | Production | incoming insp; D8, cleanroom | Q0(16)~3.8e10, quench 16.8 MV/m, FE free | undefined
? | TD! |  | Zanon | L2-347 | Jlab | Production | incoming insp; D5, cleanroom | Q0(16)~3.2e10, quench limited 17.3 MV/m, FE free, | undefined; string alternate?
? | NX-A/B950 |  | Zanon | L2-331 | Jlab | Production | cleanroom | Q0(16)~1.8e10, quench 30.6 MV/m, FE onset 28 MV/m | incoming insp, VTRF D5, undefined
0 | TD |  | RI | L2-250 | Jlab | Production | cleanroom | Q0(12)=2.7e10, quench at 14.5 MV/m; no FE | incoming insp, VTRF D7/8, bad input cable, VTRF D7/8, inspection
0 | TD |  | RI | L2-145 | Jlab | Production | incoming insp; D5, | Quench at 14.5 MV/m | incoming insp, VTRF, undefined
1 | TD | CM06/FE | RI | L2-053 | Jlab | Production | Desy Qualified, D5, Cleanroom | 24 MV/m; Qo(16MV/m)=3.2e10, FE onset 9.5MV/m; Quench 22MV, Q0(16)~2.5e10, no FE; | String 6; rinse, VTRF, rinse VTRF; qualified
1 | TD | CM06 | RI | L2-060 | Jlab | Production | Desy Qualified, D5, Cleanroom | 23 MV/m; Qo(16MV/m)=3.1e10, Q0(16) 3.3e10,, Quench 21, | String 6; rinse, VTRF, rinse VTRF qualified
? | TD | tested | Zanon | L2-268 | Jlab | Production | Cleanroom | Q0(16)~ 2.6e10; Quenching at 17.3 MV/m, FE free | Retest D8 due to magnetic fields, string alternate?
1 | NX-A | CM09 | RI | L2-097 | Jlab | Production |  | Q0(16)~2.8e10, quench 20.2 MV/m, FE free | string 9, rinse VTRF
1 | NX-A | CM09 | RI | L2-118 | Jlab | Production |  | Q0(16)~2.6e10, admin limited 24 MV/m, FE free | rinse, VTRF D7/8 string 9, rinse VTRF
1 | TD | CM09 | RI | L2-125 | Jlab | production |  | Q0(16)~2.5e10, admin limited 24 MV/m , FE free | incoming insp, VTRF D5, string 9, rinse VTRF
1 | NX-A | CM09 | Zanon | L2-279 | Jlab | Production |  | Q0(16)~2.6e10, admin limited 24 MV/m, FE free, quench 19.1 MV/m, Fe onset 17.5; Quench 19.8MV, no FE | string 9, CMM, HPR, VTRF, D7/8, HPR, VTRF D7/8, qualified
1 | NX-A | CM09 | Zanon | L2-281 | Jlab | Production |  | Q0(16)~2.7e10, admin limited 24 MV/m, FE free; FE onset 3 MV/m, Q0~1e10 | VTRF D7/8, String 9, rinse, VTRF; inspection
1 | NX-C975 | CM09 | RI | L2-133 | Jlab | Production |  | Q0(16)~3.9e10, quench 21.2 MV/m, FE free | String 9, unable to recover FF; --> Bluecrab
1 | NX-A | tested | Zanon | L2-286 | Jlab | Production | Cleanroom | Q0(16)~2.8e10, admin limited 24 MV/m, FE free, bellows test; FE on 7.5MV/m; FE onset 20MV/m; Q0(16)~2.3, quench 26.6 MV; | Bellows rinse test D5, Full disassembly, rinse VTRF D5; , rinse, VTRF D7/8;, alternate
? | NX-B | tested | Zanon | L2-299 | Jlab | Production |  | FE onset 4 MV/m; Q0(16)~2.3e10, FE onset 23 MV/m, Quench 23 MV/m; | incoming insp, new FP, rinse, VTRF D7/8, degrease, rinse, VTRF D7/8; undefined
1 | NX-A | NX-900 | RI | L2-147 | Jlab | Production | cleanroom | Quench at 12.5 MV/m | incoming insp, VTRF, reject
? | TD | tested | Zanon | L2-242 | Jlab | Production |  | Q0(16)~3.1e10, quench limited 17 MV/m; no FE | incoming insp, VTRF D5, undefined
4 | NX-C | tested | Zanon | L2-201 | Jlab | Production | cleanroom | Q0(16)~3.5e10. Quench 16.2 MV/m. No FE. | incoming insp, VTRF D5, Vent. Set aside
4 | NX-B | tested | Zanon | L2-209 | Jlab | Production | cleanroom | Q0(16)~2.7e10. Quench 17.6 MV/m. No FE. | incoming insp, VTRF D5. Vent. Set aside
4 | NX-B | tested | Zanon | L2-210 | Jlab | Production | incoming insp. Cleanroom. | Q0(16)~2.6e10. Quench 17.7 MV/m. No FE. | incoming insp, VTRF D5. Vent. Set aside
? | NX-B | tested | Zanon | L2-211 | Jlab | Production | incoming insp TS34-002 D5, | Q0(15.2)~3e10. Quench at 15.5MV/m. No FE; Q0(16)~3.9e10, Quench 17.5MV/m, no FE | incoming insp, VTRF D5 VTRF D5. 5u EP, VTRF D8, Remove PICS, Use as is
? | TD | tested | RI | L2-502 | Jlab | production | shipping damage? D5 TS34-001, Cleanroom | Q0(16)~4e10, Quench 18 MV/m. No FE. | incoming insp, VTRF D5. String alternate?
? | TD | tested | Zanon | L2-220 | Jlab | production | incoming insp, Cleanroom | Q0(16)~2.8e10, Quench 17.5 MV/m, no FE | VTRFT D5; string alternate?
1 | TD | tested | RI | L2-543 | Jlab | production |  | Q0(16)~3.8e10, quench 25.0 MV/m, FE on 11 MV/m; M-parameter NCR | incoming insp, VTRF D7/8; VTRF D7/8; HPR; VTRF D7/8; Qualified CM9R
1 | TD | tested | RI | L2-536 | Jlab | Production | incoming insp; D5, cleanroom | Q0(16)~3.1e10, quench 25.5 MV/m, FE onset 16 MV/m; FE onset 6 MV/m, FE onset 20 MV/m; | incoming insp, VTRF, rinse, retest, rinse retest; rinse retest;
3 | TD | New Zanon | Zanon | L2-343 | Jlab | Production | incoming insp; Cleanroom | Q0(16)~4.2e10, Quench 19.5 MV/m, no FE | qualfied
4 | TD | New Zanon | Zanon | L2-346 | Jlab | Production | incoming insp; beadpull; | Q0(16) 3.2e10, quench 19MV/m, no FE | alternate
2,? | NX-B | NX-900 | RI | L2-063 | Jlab | Production | incoming insp, VTRF, Cleanroom | Q0(16): 2.6e10, Quench at 18.2 MV/m, no FE | string alternate
2, 1 | NX-B | NX-900 | RI | L2-083 | Jlab | Production | incoming insp | Q0(16): 2.9e10, Final quench at 22 MV/m, FE 0.5 R/hr; Q0(16)~3.4e10, quench 21.5MV/m, no FE | rinse, VTRF, qualified
1 | NX-A | NX-900 | RI | L2-103 | Jlab | Production | incoming insp, leak, cleanroom | Q0(16)~1.8e10, quench 25.9 MV/m, FE free; | VTRF D5; ?
2, 1 | NX-A | NX-900 | RI | L2-115 | Jlab | Production | incoming insp, D5; cleanroom | Q0(16)~3.1e10 FE on 12 MV/m, rad limited 20 MV/m, Q0(16)~3.4e10, quench 24.5MV, no FE | rinse, VTRF, qualified
1 | NX-A | NX-900 | RI | L2-120 | Jlab | Production | received, incoming insp, D5 | Q0(16)~2.5e10, quench 22.7 MV/m, FE free | qualified
1 | NX-A | NX-900 | RI | L2-116 | Jlab | Production | received, incoming insp, D5, | Q(0)16~2.8e10, quench 26.1 MV/m, FE free | qualified
3 | TD | New Zanon | Zanon | L2-333 | Jlab | Production | received, incoming insp, D5 | Q0(16)~3.3e10, quench 18.9 MV/m, FE free | qualified
3 | TD | New Zanon | Zanon | L2-334 | Jlab | Production | received, incoming insp, D5 | Q0(16)~3.8e10, quench 19.2 MV/m, FE free | qualified
3 | TD | New Zanon | Zanon | L2-337 | Jlab | Production | received, incoming insp, D5, cleanroom | Q0(14)~3.4e10, quench 14.5 MV/m, FE free | vent, set aside
3 | TD | New Zanon | Zanon | L2-338 | Jlab | Production | received, incoming insp, D5 | Q0(16)~3.9e10, quench 21.5 MV/m, FE free | qualified
3 | TD | New Zanon | Zanon | L2-341 | Jlab | production | received, incoming insp, D5 | Q0(16)~4.1e10, quench 18 MV/m, FE free | qualfied, accepted by Dan Gonella
3 | TD | New Zanon | Zanon | L2-342 | Jlab | production | received, incoming insp, D5 cleanroom | Quench 15.4 MV/m, FE free | vent, set aside
1 | NX-B | CM09 | Zanon | L2-295 | Jlab | production | no longer FF, tuned in HV | Q0(16) 2.2e10, quench 22.7 MV/m, suspect FF | tuning, VTRF, ?
1 | NX-900R |  | RI | L2-065 | RI | production | received, incoming insp, D5 | Q0(16)~3.1e10, quench 23.2 MV/m, FE free | qualified
1 | NX-900R |  | RI | L2-068 | RI | production | received, incoming insp, D5 | Q0(16)~2.4e10, quench 21.5 MV/m, FE free | string alternate
CM-11 |  |  |  | L2-135 | Jlab | Production | CM-11 | Q0(16)~3.6e10, FE free, quench 19.8 MV/m | damaged bellows
CM-11 |  |  |  | L2-328 | Jlab | Production | CM-11 | Q0(16)~3.2e10, quench 23.7 MV/m, FE free; Q0(16)~2.5e10, Quench 21.8MV/m, FE free; | Qualified for 11R
CM-11 |  |  |  | L2-332 | Jlab | Production | CM-11 | Q0(16)~2.7e10, quench 23.4 MV/m, FE free; Q0)16)~2.5+I93e+10, Quench 22.2 MV/m, FE free; | Qualified for 11R
CM-11 |  |  |  | L2-330 | Jlab | Production | CM-11 | Q0(16)~3.3e10, quench 23.4 MV/m, FE free; Q0(16~34e10, Quench 20.9 MV/m, FE free | Qualified for 11R
CM-11 |  |  |  | L2-308 | Jlab | Production | CM-11 | D7 Q0(16) 2.9e10, no FE, quench 25 MV/m
CM-11 |  |  |  | L2-140 | Jlab | Production | CM-11 | Q0(16)~2.5e10, quench 28.0 MV/m, FE free; Q0(16)~3e10, quench 24 MV/m; FE free; | Qualified for 11R
CM-11 |  |  |  | L2-137 | Jlab | Production | CM-11 | Q0(16)~3.5e10, quench limited 24.5 MV/m, FE free
CM-11 |  |  |  | L2-167 | Jlab | Production | CM-11 | Q0(16) 2.80e10, quench at 23.9MV/m. No FE; Q0(16)~3e10, quench 25.6 MV/m, FE free | Qualified for 11R
|  |  |  | L2-340 | Jlab | from FNAL? |  | Q0(16)~3.5e10, quench15.7 MV/m, no FE; | ?
|  |  |  | L2-239 | Jlab | from FNAL? |  | Q0(16)~2.4e10, quench 16.5, no FE; | ?
| 3N60 | HE-353 | Jlab | R&D bare 9-cell | VAA | quench 17 MV/m
| 3N60 | HE-352 | Jlab | R&D bare 9-cell | VAA | Q0(15) ~3.2e10, no FE, quench 15.9 MV/m
| 2N0 | HE-364 | Jlab | R&D bare 9-cell | VAA | Q0(16) 3.2e10, FE onset 18.8MV/m, quench 22.5
| 2N0 | HE-349 | Jlab | R&D bare 9-cell
| 3N60 | HE-354 | Jlab | R&D bare 9-cell
| 3N60 | HE-351 | Jlab | R&D bare 9-cell

## L2 Countdown List (hidden)
L2-097 | J1.3-9
L2-103 | ?
L2-118 | J1.3-9
L2-125 | J1.3-9
L2-201 |  | Q0(16)~3.5e10. Quench 16.2 MV/m. No FE.
L2-209 |  | Q0(16)~2.7e10. Quench 17.6 MV/m. No FE.
L2-210 |  | Q0(16)~2.6e10. Quench 17.7 MV/m. No FE.
L2-242 |  | Q0(16)~3.1e10, quench limited 17 MV/m; no FE
L2-281 | J1.3-9
L2-295 | J1.3-9
L2-299 |  | Q0(16)~2.3e10, FE onset 23 MV/m, Quench 23 MV/m;
L2-536 |  | Q0(16)~3.1e10, quench 25.5 MV/m, FE onset 16 MV/m; FE onset 6 MV/m, FE onset 20 MV/m; FE onset 5MV/m

## L2 Cavity Retest Req
Initial state notes | from vendor or jlab re-rinse | venting | dissasembly | cleaning | prep | cleaning | cleaning | cleaning | cleaning | HPR/Assembly | notes
| FE above 10MVm | fast bleedup | remove all but 4 bolts on the bottom flange | on CVT - external cleaning in water room | in cleanroom remove bottom flange assembly, disassembly flange assembly and send parts out for cleaning |  | right before HPR rinse/wipe bottom flange |  |  | standard final assembly
| FE below 10MVm | fast bleedup | removal all hardware, disassembly flange assembly and send parts out for cleaning | on CVT - external precleaning - tape, grease ext. with solvents | cage cavity - use USC safe titanium brackets they are marked. Unmarked anodized aluminum brackes can't be used. Blank of return Tee | ultrasonic in >1% Liquinox - moving every 5 mintes - cavity fully open | internal/external rinse vertically in cage | Ultrasonic in DI water in new large USC moving every 5 mintes | final external rinse vertically in cage - dry in ISO 6 if nessisary, but leave wet until HPR is prefered | standard 2 HPR assembly | I would prefer the first HPR to be a 12-14hr overnight
| From CM6/ cavites vented outside cleanroom | venting | dissasembly | cleaning | prep | cleaning | cleaning | cleaning | cleaning | HPR/Assembly | notes
The cavity inlet from rebuild cavites must have the inlet welded shut before they enter the water room. The cavity return tee must be check for burn and sharp edges beforeentery into the water room. | NA | NA | removal all hardware, disassembly flange assembly and send parts for cleaning | on CVT - external precleaning - tape, grease ext. with solvents | cage cavity - use USC safe titanium brackets they are marked. Unmarked anodized aluminum brackes can't be used. Blank of return Tee | ultrasonic in >1% Liquinox - moving every 5 mintes - cavity fully open | internal/external rinse vertically in cage | Ultrasonic in DI water in new large USC moving every 5 mintes | final external rinse vertically in cage - dry in ISO 6 if nessisary, but leave wet until HPR is prefered | standard 2 HPR assembly | I would prefer the first HPR to be a 12-14hr overnight

## CEBAF- C75, P70, C100R
String ID | Cavity 1 | Cavity 2 | Cavity 3 | Cavity 4 | Cavity 5 | Cavity 6 | Cavity 7 | Cavity 8
C75-01
C75-02
C75-03
C75-04
P70
C100-01
C100-02

## CEBAF C75 Cavity Candidates
Cavity ID | Location | Status | Performance | Path Forward | Column1
5C75-J-004 | Cav ASSY |  | failed VTRF | ?
5C75-J-005 | Cav ASSY | VTRF
5C75-RI-001 | Cav ASSY | C7501, CPR0x | failed desorbtion test | leak check, retighten, ?
5C75-RI-002 | CM ASSY | C7501, CPR02 | accepted
5C75-RI-003 | Cav ASSY | C7501, CPR0x | failed desorbtion test | leak check, retighten, ?
5C75-RI-004
5C75-RI-005 | CM ASSY | C7501, CPR02 | accepted
5C75-RI-006 | CM ASSY | C7501, CPR01 | accepted
5C75-RI-007 | CM ASSY | C7501, CPR01 | accepted
5C75-RI-008
5C75-RI-NBSN1
5C75-RI-009
5C75-RI-010
5C75-RI-011
5C75-RI-012
5C75-RI-013
5C75-RI-014
5C75-RI-015
5C75-RI-016

## CEBAF P1 Cavity Candidates
Rank | Material | Group | Vendor | Cavity ID | Location | Type | Status | Performance | Path Forward | Column1
|  |  |  | JL-005 |  | P1-7 Cell
|  |  |  | JL-007 |  | P1-7 Cell | MS complete, ready for CMM
|  |  |  | JL-006 |  | P1-7 Cell
|  |  |  | JL-003 |  | P1-7 Cell | MS complete, CMM complete, ready for saddle weld
|  |  |  | EP-002 |  | P1-7 Cell
|  |  |  | JL-004 |  | P1-7 Cell | Pre-MS tested, ready for MS | Quench 11 MV/m, Q0~7e9
|  |  |  | JL-009 |  | P1-7 Cell | Pre-MS tested, ready for MS | Quench 13.8 MV/m, Q0~6e9
|  |  |  | JL-008 |  | P1-7 Cell
|  |  |  | EP-003 |  | P1-7 Cell
Note on G2: 7 Cell Cornell style
Note on G3: 7 Cell Cornell style
Note on G4: 7 Cell Cornell style
Note on G5: 7 Cell Cornell style
Note on G6: 7 Cell Cornell style
Note on G7: 7 Cell Cornell style
Note on G8: 7 Cell Cornell style
Note on G9: 7 Cell Cornell style

## SNSPPU String
String ID | Cavity 1 | Cavity 2 | Cavity 3 | Cavity 4

## SNSPPU Cavity Candidates
Rank | Material | Group | Vendor | Cavity ID | Location | Type | Status | Performance | Path Forward | Column1
|  |  | RI | PPU-01 |  |  | cavities arrive at JLAB starting in Sept
|  |  | RI | PPU-02
|  |  | RI | PPU-03
|  |  | RI | PPU-04
|  |  | RI | PPU-05
|  |  | RI | PPU-06
|  |  | RI | PPU-07
|  |  | RI | PPU-08
|  |  | RI | PPU-09
|  |  | RI | PPU-10
|  |  | RI | PPU-11
|  |  | RI | PPU-12
|  |  | RI | PPU-13
|  |  | RI | PPU-14
|  |  | RI | PPU-15
|  |  | RI | PPU-16
|  |  | RI | PPU-17
|  |  | RI | PPU-18
|  |  | RI | PPU-19
|  |  | RI | PPU-20
|  |  | RI | PPU-21
|  |  | RI | PPU-22
|  |  | RI | PPU-23
|  |  | RI | PPU-24
|  |  | RI | PPU-25
|  |  | RI | PPU-26
|  |  | RI | PPU-27
|  |  | RI | PPU-28
|  |  | RI | PPU-29
|  |  | RI | PPU-30
|  |  | RI | PPU-31
|  |  | RI | PPU-32

## C100 Cavity Status
String ID | Cavity 1 | Cavity 2 | Cavity 3 | Cavity 4 | Cavity 5 | Cavity 6 | Cavity 7 | Cavity 8 | C100 ID | Cavity ID | R/L | FF % | Status | Performance | Path Forward | Column1
C100-6R | L | L | L | 51 | R | R | R | 43 | spare | RI-027 | R |  | qualified | 24 MV/m (admin), no FE;
[9 empty] | spare | RI-009 |  |  | needs tuning, needs HV welding
[9 empty] | spare | RI-016 |  |  | needs tuning in HV
[9 empty] | C100-6 | RI-039 | R | 92.9 | qualified | 29 MV/m, FE onset 29 MV/m
[9 empty] | C100-6 | RI-051 | L | 94.3 | qualified | 29 MV/m, FE onset 21.5 MV/m
[9 empty] | C100-6 | RI-053 | L | 91 | qualified | 26 MV/m, FE free;
[9 empty] | C100-6 | RI-056 | L | 92.7 | qualified | 24 MV/m, FE free;
[9 empty] | C100-6 | RI-043 | R | 97.5 | qualified | 28 MV/m (quench), FE onset 21 MV/m, 24 MV/m (admin), FE onset 21.5 MV/m,
|  | String Candidates | [6 empty] | C100-6 | RI-049 | R | 91 | input probe fell off, had long rinse w/FPC, qualified | 24 MV/m (admin), no FE;
[9 empty] | C100-6 | RI-047 | R | 88.7 | needs rinse, retest | FE onset 8 MV/m, final FE onset 8 MV/m
|  | RI-009 | [6 empty] | C100-6 | RI-055 | L | 91.7 | input probe fell off, had long rinse w/FPC, rinse, retest, qualified | FE onset 9 MV/m; 24 MV/m, FE free;
RI-016
RI-047