## Sheet1
H-HOM Feedthrough
| Traveler Name | Traveler ID | Abbreviation | Author | Reviewer 1 | Reviewer 2 | Drawing Number | Status | Required Online | No. of Parts | CMM | JLab CMM | Current Location | Not Written
Unique | H-HOM Feedthrough 25ohm Rod | AUP-INSP-HHOMFT-FTHMRD | FTHMRD | Matthew Weaks | Naeem Huque |  | JL0089755 | Ready to Submit | 2020-10-16 | 4 | No | No | JLab Inventory | Ready to Submit
| H-HOM Feedthrough Brazing Assembly | AUP-ASSY-HHOMFT-BRZAS | BRZAS | Matthew Weaks | Naeem Huque | Scott Williams | JL0089751 | Ready to Submit | 2020-10-31 | 3 | Yes | No | Assembly | Draft Folder
| H-HOM Feedthrough Assembly | AUP-ASSY-HHOMFT-HFTASY | HFTASY | Matthew Weaks | Naeem Huque | Abam O'Brien | JL0093243 | Ready to Submit | 2020-10-31 | 3 | Yes | Yes | Assembly | Awaiting Approval
Online
H-HOM Field Antenna
| Traveler Name | Traveler ID |  | Author | Reviewer 1 | Reviewer 2 | Drawing Number | Status | Required Online | No. of Parts | CMM | JLab CMM | Current Location
Unique | Field Antenna 25ohm Hook | AUP-INSP-FANT-FA25SN | FA25SN | Matthew Weaks | Naeem Huque |  | JL0090341 | Ready to Submit | 2020-10-16 | 3 | No | No | JLab Inventory
| Feedthrough Pince Cable 25ohm | AUP-INSP-FANT-FAPINC | FAPINC | Matthew Weaks | Naeem Huque |  | JL0090344 | Ready to Submit | 2020-10-16 | 3 | No | No | JLab Inventory
| Feedthrough Cable Connector | AUP-INSP-FANT-CABL | CABL | Matthew Weaks | Naeem Huque |  | JL0090343 | Ready to Submit | 2020-10-23 | 3 | Yes | No | Assembly
| Field Antenna 25ohm | AUP-ASSY-FANT-FAASY | FAASY | Matthew Weaks | Naeem Huque | Adam O'Brien | JL0090340 | Ready to Submit | 2020-10-31 | 3 | Yes | Yes | Assembly
V-HOM Coupler
| Traveler Name | Traveler ID |  | Author | Reviewer 1 | Reviewer 2 | Drawing Number | Status | Required Online | No. of Parts | CMM | JLab CMM | Current Location
Unique | V-HOM Couple 25ohm Hook | AUP-INSP-VHOM-VH25SN | VH25SN | Matthew Weaks | Naeem Huque |  | JL0090122 | Ready to Submit | 2020-10-16 | 3 | No | No | JLab Inventory
| V-HOM Couple 25ohm | AUP-ASSY-VHOM-VCASSY | VCASSY | Matthew Weaks | Naeem Huque | Adam O'Brien | JL0089940 | Ready to Submit | 2020-10-31 | 3 | Yes | Yes | Assembly
H-HOM Damper
| Traveler Name | Traveler ID |  | Author | Reviewer 1 | Reviewer 2 | Drawing Number | Status | Required Online | No. of Parts | CMM | JLab CMM | Current Location
Unique | HOM Niobium Hook | AUP-INSP-DAMP-HOOK | HOOK | Matthew Weaks | Naeem Huque |  | JL0086021 | Draft Folder | 2020-10-12 | 3 | Yes | Yes | JLab Machine Shop
| HOM Tee | AUP-INSP-DAMP-TEE | TEE | Matthew Weaks | Naeem Huque |  | JL0083868 | Draft Folder | 2020-10-12 | 3 | Yes | Yes | JLab Machine Shop
| Niobium Can Lid | AUP-INSP-DAMP-NBLID | NBLID | Matthew Weaks | Naeem Huque |  | JL0086010 | Ready to Submit | 2020-10-16 | 3 | Yes | Yes | JLab Inventory
| Niobium Can Lid Final Machining | AUP-INSP-DAMP-LDMCH | LDMCH | Matthew Weaks | Naeem Huque |  | JL0088326 | Ready to Submit | 2020-10-31 | 3 | Yes | Yes | Assembly
| Outer Can Lid | AUP-INSP-DAMP-OCLID | OCLID | Matthew Weaks | Naeem Huque |  | JL0088271 | Ready to Submit | 2020-10-16 | 3 | No | No | JLab Inventory
| Niobium Lid Brazing Assembly | AUP-ASSY-DAMP-NLASSY | NLASSY | Matthew Weaks | Naeem Huque | Scott Williams | JL0088238 | Ready to Submit | 2020-10-31 | 3 | Yes | Yes | Assembly
| Niobium Can Lid Machining Assembly | AUP-ASSY-DAMP-CLASSY | CLASSY | Matthew Weaks | Naeem Huque |  | JL0088600 | Ready to Submit | 2020-10-31 | 3 | Yes | Yes | Assembly
| H-HOM Inner Tube | AUP-INSP-DAMP-ITUBE | ITUBE | Matthew Weaks | Naeem Huque |  | JL0086026 | Draft Folder | 2020-10-08 | 3 | Yes | Yes | JLab Machine Shop
| H-HOM Flange DN100 | AUP-INSP-DAMP-DN100 | DN100 | Matthew Weaks | Naeem Huque |  | JL0086025 | Ready to Submit | 2020-10-16 | 3 | No | No | JLab Inventory
| DN100 Braze Assembly | AUP-ASSY-DAMP-FLGWLD | FLGWLD | Matthew Weaks | Naeem Huque | Scott Williams | JL0088274 | Ready to Submit | 2020-10-31 | 3 | Yes | Yes | Assembly
| DN100 Machining | AUP-ASSY-DAMP-FLMCH | FLMCH | Matthew Weaks | Naeem Huque |  | JL0088272 | Ready to Submit | 2020-10-31 | 3 | Yes | Yes | Assembly
| Hook and Tee Weldment | AUP-ASSY-DAMP-HKTEE | HKTEE | Matthew Weaks | Naeem Huque | Adam O'Brien | JL0088266 | Ready to Submit | 2020-10-31 | 3 | Yes | Yes | Assembly
| Inner Can Assembly | AUP-ASSY-DAMP-INCAN | INCAN | Matthew Weaks | Naeem Huque | Adam O'Brien | JL0088602 | Ready to Submit | 2020-10-31 | 3 | Yes | Yes | Assembly
| HOM H External Pipe | AUP-INSP-DAMP-EXPIPE | EXPIPE | Matthew Weaks | Naeem Huque |  | JL0086009 | Ready to Submit | 2020-10-16 | 3 | No | No | JLab Inventory
| Outlet Tube | AUP-INSP-DAMP-OTUBE | OTUBE | Matthew Weaks | Naeem Huque |  | JL0088598 | Ready to Submit | 2020-10-31 | 3 | No | No | Vendor
| Outer Tube Assembly | AUP-ASSY-DAMP-TBASSY | TBASSY | Matthew Weaks | Naeem Huque | Adam O'Brien | JL0088268 | Ready to Submit | 2020-10-31 | 3 | Yes | No | Assembly
| AUP RFD H-HOM Damper | AUP-ASSY-DAMP-FASSY | FASSY | Matthew Weaks | Naeem Huque | Adam O'Brien | JL0086007 | Ready to Submit | 2020-10-31 | 3 | Yes | Yes | Assembly
Common Travelers
| Traveler Name | Traveler ID |  | Author | Reviewer 1 | Reviewer 2 | Drawing Number | Status | Required Online | No. of Parts | CMM | JLab CMM | Current Location
| Pince Feedthrough | AUP-INSP-CMN-FTPCSN | FTPCSN | Matthew Weaks | Naeem Huque |  | JL0101223 | Ready to Submit | 2020-10-31 | 3 | No | No | Vendor
| Copper Ring | AUP-INSP-CMN-CURING | CURING | Matthew Weaks | Naeem Huque |  | JL0089865 | Online | 2020-09-20 | 13 | No | No | JLab Inventory
| Feedthrough 25ohm Rod | AUP-INSP-CMN-FTROD | FTROD | Matthew Weaks | Naeem Huque |  | JL0090118 | Online | 2020-09-20 | 11 | No | No | JLab Inventory
| Custom DN40 Flange | AUP-INSP-CMN-DN40 | DN40 | Matthew Weaks | Naeem Huque |  | JL0089760 | Ready to Submit | 2020-10-16 | 12 | No | No | JLab Inventory
| Ceramic D40d14 | AUP-INSP-CMN-DSCCRM | DSCCRM | Matthew Weaks | Naeem Huque |  | LHCACFHC0206 | Online | 2020-09-20 | 17 | Yes | Yes | JLab Inventory
| Flange Brazing Assembly | AUP-ASSY-CMN-FLBRZ | FLBRZ | Matthew Weaks | Naeem Huque | Scott Williams | JL0092614 | Draft Folder | 2020-10-08 | 9 | Yes | Yes | Assembly
| Feedthrough 25ohm Brazing Assembly | AUP-ASSY-CMN-BRZAS | BRZAS | Matthew Weaks | Naeem Huque | Scott Williams | JL0090121 | Ready to Submit | 2020-10-31 | 6 | Yes | Yes | Assembly