## CMM Plan & Forecast
Ready to Inspect Filter (TBD) | Project Name | Inspection Charge Code | Contact /SOTR | WCA or Sub Assembly | Traveler Name | Traveler Names/Availablity G= available, Y/B/P = not available as of 06Oct2020 | Part No. | Part Name | Serial No.s | Priority Project (vs. CEBAF) | Priority within Project | Date when Parts & Traveler in CMM | Days waiting to start | Qty Required | First Article (Man Hrs) | Planned Duration (Man-Hrs) | Type (CMM) | Type (Visual & Other) | Anticpated delivery date first lot | Actual Delivery date first lot | Planned Start Date | Finish | Qty delivered to JLAB Sep2020 | Complete or Qualified | Qty remaining to Inspect | Complete | WBS-Cost Point | WBS Name | P6- WBS Path | P6- Activity ID | P6-Activity Name | Comments
| P1 |  | Tony Reilly |  | String ASSY Wk of Nov16th |  |  |  |  | 1 | [8 empty] | 2020-05-07 |  |  | 2021-05-07 | [5 empty] | P1 Assembly & Test
|  | P1001Q | Gigi/Tiffany | Cavity Preparation | Helium Vessel Weldment Assembly Inspection | P1-INSP-HELV |  |  | EP-002 | 1 |  |  |  | 1 |  |  | CMM | [5 empty] | 1 |  | 1
|  | P1001Q | Gigi/Tiffany | Cavity Preparation | Helium Vessel Weldment Assembly Inspection | P1-INSP-HELV |  |  | EP-003 | 1 |  |  |  | 1 |  |  | CMM | [5 empty] | 1 |  | 1
|  | P1001Q | Gigi/Tiffany | Cavity Preparation | Helium Vessel Weldment Assembly Inspection | P1-INSP-HELV |  |  | JL006 | 1 |  |  |  | 1 |  |  | CMM | [5 empty] | 1 |  | 1
|  | P1001Q | Gigi/Tiffany | Cavity Preparation | Helium Vessel Weldment Assembly Inspection | P1-INSP-HELV |  |  | JL009 | 1 |  |  |  | 1 |  |  | CMM | [5 empty] | 1 |  | 1
|  | P1001Q | Scott | Component Preparation | Inspection Primary waveguide (COLD) | P1-INSP-WGD |  |  |  | 1 | [6 empty] | CMM | Visual | [6 empty] | 0
|  | C1010Q | Scott | Component Prepreation | Inspection Secondary Waveguide (WARM) & Leak Check | P1-INSP-GVWG |  |  |  | 1 | [6 empty] | CMM | Visual | [6 empty] | 0
|  | P1001Q | Scott | Component Prepreation | Inspection Brazement Adapter Assembly | P1-INSP-ADPT |  |  |  | 1 | [6 empty] | CMM | Visual | [6 empty] | 0
|  | C1010Q | Scott | Component Prepreation | Inspection RF Window Welded Assembly | C100R-INSP-WIN-R1 |  |  |  | 1 | [6 empty] | CMM | Visual | [6 empty] | 0
|  | C1010Q | Scott | Component Prepreation | Inspection Double Sided Rectangular Flange | C100R-INSP-DSRF |  |  |  | 1 | medium |  |  | 4 |  |  | CMM | Visual |  | 2020-10-08 |  |  | 4 |  | 4 | [6 empty] | 08Oct2020 returned to CMM from Inventory w/SN ,insp first4 only (per Scott use xxxxx- 87 thru 102 )
|  | P1001Q | Scott | Component Prepreation | Inspection Modified Window | P1-INSR |  |  |  | 1 | High |  |  | 4 |  |  | CMM | Visual |  | 2020-10-09 |  |  | 4 |  | 4 | [6 empty] | 09Oct2020 delivered to CMM - full inspection (first parts in this lot)
|  | P1001Q | Scott | Component Prepreation | Waveguide and window weldment modification | P1-WELD-WIN-ASSY |  |  |  | 1 | [6 empty] | CMM | Visual | [6 empty] | 0
String Assembly
0
| C75-01 |  | Tony Reilly | [6 empty] | 2 | [8 empty] | 2018-02-14 |  |  | 2021-04-09 |  |  | 0 |  |  | C75-01 Assembly & test
|  | C7501Q | Gigi Ciovati | Cavity | C75 Cavity Optical Inspection | C75-CAV-INSP-OPTK |  |  |  | 2 |  |  |  | 8 | [10 empty] | 8
|  | C7501Q | Mitchell/Macha | Cavity | C75 Cavity Flange Component inspection | C75-INSP-FLG-COMP |  |  |  | 2 | [14 empty] | 0
|  | C7501Q | Scott Williams | Component Preparation | Cebaf Cryomodule Dogleg Assembly Inspection | C75-CPR-INSP-DGLG |  |  |  | 2 | [14 empty] | 0
|  | C7501Q | Scott Williams | Component Preparation | Dogleg Waveguide Cavity Flange Inspection | C75-CPR-INSP-DLCF |  |  |  | 2 | [14 empty] | 0
|  | C7501Q | Scott Williams | Component Preparation | Dogleg Waveguide Window Flange Inspection | C75-CPR-INSP-DLWF |  |  |  | 2 | [14 empty] | 0
|  | C7501Q | Scott Williams | Component Preparation | Dogleg Window Waveguide Section | C75-CPR-INSP-DLWS-R2 |  |  |  | 2 | [14 empty] | 0 | [6 empty] | C75-CPR-INSP-DLWS (Scott)Traveler rev approved by Aaron on 15Oct2020
|  | C7501Q | Mitchell/Macha | Component Preparation | Cryomodule End Dish and Bellows Assembly Dimensional Inspection | C75-CPR-INSP-ENDD |  |  |  | 2 | [14 empty] | 0
|  | C7501Q | Jiquan Guo | Component Preparation | HOM Elbow Assembly Dimensional Inspection | C75-CPR-INSP-HOME |  |  |  | 2 | [14 empty] | 0
|  | C7501Q | Jiquan Guo | Component Preparation | HOM Load Assembly Inspection | C75-CPR-INSP-HOML |  |  |  | 2 | [14 empty] | 0
|  | C7501Q | Gigi Ciovati | Component Preparation | Inner Adapter Dimensional Inspection | C75-CPR-INSP-INAD |  |  |  | 2 | [14 empty] | 0
|  | C7501Q | Scott Williams | Component Preparation | Cryomodule Dogleg Window Ceramic Inspection | C75-CPR-INSP-WNCR |  |  |  | 2 | [14 empty] | 0
|  | C7501Q | Scott Williams | Component Preparation | Cryomodule Dogleg Window Eyelet Inspection | C75-CPR-INSP-WNEY |  |  |  | 2 | [14 empty] | 0
|  | C7501Q | Gigi Ciovati | Component Preparation | 5-Cell Cavity Dimensional Inspection | C75-CAV-INSP | JL0059982-RevA, JL0031321 - RevE | C75 Cavity |  | 2 | [14 empty] | 0
|  | C7501Q | Gigi Ciovati | Component Preparation | C75 Cavity Pair Inspection | C75-CPR-INSP |  |  |  | 2 | [14 empty] | 0
|  | C7501Q | Gigi Ciovati | Component Preparation | Waveguide Extension Inspection | C75-CU-INSP-WGDX |  |  |  | 2 | [14 empty] | 0
|  | C7501Q | Gigi Ciovati | Component Preparation | Warm Window Assembly Dimensional Inspection | C75-CU-INSP-WIN |  |  |  | 2 | [14 empty] | 0
|  | C7501Q | Gigi Ciovati | Component Preparation | Warm Window Inspection | C75-CU-INSP-WINW |  |  |  | 2 | [14 empty] | 0
|  | C7501Q | Gary Cheng | Component Preparation | Inspection of C75 Cryomodule Cavity Magnetic Shield Assembly | C75-CM-INSP-CMAG |  |  |  | 2 | [14 empty] | 0
[10 empty] | 2 | [14 empty] | 0
[10 empty] | 2 | [14 empty] | 0
| C7502 |  | Tony Reilly | [6 empty] | 2 | Priority -1 | [7 empty] | 2020-03-01 |  |  | 2021-06-30 |  |  | 0 |  |  | C75-02 Assemble & Test
|  | C7502Q | Jiquan Guo | Component Preparation | HOM Elbow Assembly Dimensional Inspection | C75-CPR-INSP-HOME |  |  |  | 2 | [9 empty] | 2020-08-30 |  |  | 16 |  | 0 | [6 empty] | Will be needed for the next C75 (not urgent)
|  | C7502Q | Scott Williams | Component Preparation | Dogleg Waveguide Cavity Flange Inspection | C75-CPR-INSP-DLCF |  |  |  | 2 | [9 empty] | 2020-10-03 |  |  | 10 |  | 0 | [6 empty] | 03Oct2020- For Dog Legs , 10 delvered to CMM, when done go to EBW
|  | C7502Q | Scott Williams | Component Preparation | Dogleg Waveguide Window Flange Inspection | C75-CPR-INSP-DLWF |  |  |  | 2 | [9 empty] | 2020-10-03 |  |  | 10 |  | 0 | [6 empty] | 03Oct2020- For Dog Legs , 10 delvered to CMM, when done go to EBW
|  | C7502Q | Scott Williams | Component Preparation | Dogleg Window Waveguide Section | C75-CPR-INSP-DLWS |  |  |  | 2 | [9 empty] | 2020-10-03 |  |  | 10 |  | 0 | [6 empty] | 03Oct2020- For Dog Legs , 10 delvered to CMM, when done go to EBW
[10 empty] | 2 | [14 empty] | 0
| C7503 |  | Tony Reilly | [6 empty] | 2 | Priority -1 | [7 empty] | 2020-01-31 |  |  | 2022-01-20 |  |  | 0 |  |  | C75-03 Assemble & Test
|  | C7503Q | Gigi | Cavity | New Cavities from RI |  |  |  |  | 2 |  |  |  | 8 |  |  |  |  | 2020-11-06 |  |  |  | 0 |  | 8 | [6 empty] | Delivery expected 3rd week of October 2020
[10 empty] | 2 | [14 empty] | 0
| C100R |  | Tony Reilly | [7 empty] | Priority -1 | [7 empty] | TBD |  |  | TBD |  |  | 0 |  |  | C75-03 Assemble & Test
|  | C1010Q | HK Park | Component Preparation | Cavity HOM Feedthru Receiving Inspection | C100R-CAV-INSP-HMFT | JL0070606 | C100 REPLACEMENT HOM FEED THRU | [5 empty] | 20 | [8 empty] | 0 |  | 20 | [6 empty] | Spares - to go into inventory for next C100R per HK Park PO # is 19-D0236-0
0
| SNSPPU | N/A | Ed Daly |  | see below |  |  |  |  | 3 | after P1/C75 | [7 empty] | 2019-11-26 |  |  | 2022-11-10 |  |  | 0 |  | 1.21.02.002.003.005 | SNSPPU Cryomodule (7 CMs )
0
|  | Charge | SOTR |  | PPU- Cavity | Traveler |  |  |  |  | 1 |  |  | 32 | [10 empty] | 32 |  |  |  | 1.02.03.14.03 | 102031403000 | Perform Mechanical Inspection of CM-01 Cavity #1
|  | PUCSAP | P. Dhakal | Cavity | Cavity Visual & CMM Inspection | SNSPPU-CAV-INSP-CAV | 104211800-M8U-8200-A001 | CAVITY ASSEMBLY | PPU-01 |  | 3 |  |  | 1 |  |  |  |  | 2020-09-01 | at JLAB |  |  | 1 |  | 1 |  | 1.21.02.002.003.015.02 | Cleanroom String Ass Proc |  |  |  | PPU-001 to 008 need to be reworked tuner attachment then rechecked
|  | PUCSAP | P. Dhakal | Cavity | Cavity Visual & CMM Inspection | SNSPPU-CAV-INSP-CAV | 104211800-M8U-8200-A001 | CAVITY ASSEMBLY | PPU-02 |  | 1 |  |  | 1 |  |  |  |  | 2020-09-01 | at JLAB |  |  | 1 |  | 1 |  | 1.21.02.002.003.015.02 | Cleanroom String Ass Proc |  |  |  | PPU-001 to 008 need to be reworked tuner attachment then rechecked
|  | PUCSAP | P. Dhakal | Cavity | Cavity Visual & CMM Inspection | SNSPPU-CAV-INSP-CAV | 104211800-M8U-8200-A001 | CAVITY ASSEMBLY | PPU-03 |  | 2 |  |  | 1 |  |  |  |  | 2020-09-01 | at JLAB |  |  | 1 |  | 1 |  | 1.21.02.002.003.015.02 | Cleanroom String Ass Proc |  |  |  | PPU-001 to 008 need to be reworked tuner attachment then rechecked
|  | PUCSAP | P. Dhakal | Cavity | Cavity Visual & CMM Inspection | SNSPPU-CAV-INSP-CAV | 104211800-M8U-8200-A001 | CAVITY ASSEMBLY | PPU-04 |  | 4 |  |  | 1 |  |  |  |  | 2020-10-08 | at JLAB |  |  | 1 |  | 1 |  | 1.21.02.002.003.015.02 | Cleanroom String Ass Proc |  |  |  | PPU-001 to 008 need to be reworked tuner attachment then rechecked
|  | PUCSAP | P. Dhakal | Cavity | Cavity Visual & CMM Inspection | SNSPPU-CAV-INSP-CAV | 104211800-M8U-8200-A001 | CAVITY ASSEMBLY | PPU-05 |  | 5 |  |  | 1 |  |  |  |  | 2020-10-08 | at JLAB |  |  | 1 |  | 1 |  | 1.21.02.002.003.015.02 | Cleanroom String Ass Proc |  |  |  | PPU-001 to 008 need to be reworked tuner attachment then rechecked
|  | PUCSAP | P. Dhakal | Cavity | Cavity Visual & CMM Inspection | SNSPPU-CAV-INSP-CAV | 104211800-M8U-8200-A001 |  | PPU-06 |  | 6 | [7 empty] | 2020-10-22 | [5 empty] | 0 |  | 1.21.02.002.003.015.02 | Cleanroom String Ass Proc |  |  |  | PPU-001 to 008 need to be reworked tuner attachment then rechecked
|  | PUCSAP | P. Dhakal | Cavity | Cavity Visual & CMM Inspection | SNSPPU-CAV-INSP-CAV | 104211800-M8U-8200-A001 |  | PPU-07 |  | 7 | [7 empty] | 2020-10-22 | [5 empty] | 0 |  | 1.21.02.002.003.015.02 | Cleanroom String Ass Proc |  |  |  | PPU-001 to 008 need to be reworked tuner attachment then rechecked
|  | PUCSAP | P. Dhakal | Cavity | Cavity Visual & CMM Inspection | SNSPPU-CAV-INSP-CAV | 104211800-M8U-8200-A001 |  | PPU-08 |  | 8 | [7 empty] | 2020-11-02 | [5 empty] | 0 |  | 1.21.02.002.003.015.02 | Cleanroom String Ass Proc |  |  |  | PPU-001 to 008 need to be reworked tuner attachment then rechecked
|  | PUCSAP | P. Dhakal | Cavity | Cavity Visual & CMM Inspection | SNSPPU-CAV-INSP-CAV | 104211800-M8U-8200-A001 |  | PPU-09 |  | 9 | [7 empty] | 2020-11-02 | [5 empty] | 0 |  | 1.21.02.002.003.015.02 | Cleanroom String Ass Proc
|  | PUCSAP | P. Dhakal | Cavity | Cavity Visual & CMM Inspection | SNSPPU-CAV-INSP-CAV | 104211800-M8U-8200-A001 |  | PPU-10 | [15 empty] | 0 |  | 1.21.02.002.003.015.02 | Cleanroom String Ass Proc
|  | PUCSAP | P. Dhakal | Cavity | Cavity Visual & CMM Inspection | SNSPPU-CAV-INSP-CAV | 104211800-M8U-8200-A001 |  | PPU-11 | [15 empty] | 0 |  | 1.21.02.002.003.015.02 | Cleanroom String Ass Proc
|  | PUCSAP | P. Dhakal | Cavity | Cavity Visual & CMM Inspection | SNSPPU-CAV-INSP-CAV | 104211800-M8U-8200-A001 |  | PPU-12 | [15 empty] | 0 |  | 1.21.02.002.003.015.02 | Cleanroom String Ass Proc
|  | PUCSAP | P. Dhakal | Cavity | Cavity Visual & CMM Inspection | SNSPPU-CAV-INSP-CAV | 104211800-M8U-8200-A001 |  | PPU-13 | [15 empty] | 0 |  | 1.21.02.002.003.015.02 | Cleanroom String Ass Proc
|  | PUCSAP | P. Dhakal | Cavity | Cavity Visual & CMM Inspection | SNSPPU-CAV-INSP-CAV | 104211800-M8U-8200-A001 |  | PPU-14 | [15 empty] | 0 |  | 1.21.02.002.003.015.02 | Cleanroom String Ass Proc
|  | PUCSAP | P. Dhakal | Cavity | Cavity Visual & CMM Inspection | SNSPPU-CAV-INSP-CAV | 104211800-M8U-8200-A001 |  | PPU-15 | [15 empty] | 0 |  | 1.21.02.002.003.015.02 | Cleanroom String Ass Proc
|  | PUCSAP | P. Dhakal | Cavity | Cavity Visual & CMM Inspection | SNSPPU-CAV-INSP-CAV | 104211800-M8U-8200-A001 |  | PPU-16 | [15 empty] | 0 |  | 1.21.02.002.003.015.02 | Cleanroom String Ass Proc
|  | PUCSAP | P. Dhakal | Cavity | Cavity Visual & CMM Inspection | SNSPPU-CAV-INSP-CAV | 104211800-M8U-8200-A001 |  | PPU-17 | [15 empty] | 0 |  | 1.21.02.002.003.015.02 | Cleanroom String Ass Proc
|  | PUCSAP | P. Dhakal | Cavity | Cavity Visual & CMM Inspection | SNSPPU-CAV-INSP-CAV | 104211800-M8U-8200-A001 |  | PPU-18 | [15 empty] | 0 |  | 1.21.02.002.003.015.02 | Cleanroom String Ass Proc
|  | PUCSAP | P. Dhakal | Cavity | Cavity Visual & CMM Inspection | SNSPPU-CAV-INSP-CAV | 104211800-M8U-8200-A001 |  | PPU-19 | [15 empty] | 0 |  | 1.21.02.002.003.015.02 | Cleanroom String Ass Proc
|  | PUCSAP | P. Dhakal | Cavity | Cavity Visual & CMM Inspection | SNSPPU-CAV-INSP-CAV | 104211800-M8U-8200-A001 |  | PPU-20 | [15 empty] | 0 |  | 1.21.02.002.003.015.02 | Cleanroom String Ass Proc
|  | PUCSAP | P. Dhakal | Cavity | Cavity Visual & CMM Inspection | SNSPPU-CAV-INSP-CAV | 104211800-M8U-8200-A001 |  | PPU-21 | [15 empty] | 0 |  | 1.21.02.002.003.015.02 | Cleanroom String Ass Proc
|  | PUCSAP | P. Dhakal | Cavity | Cavity Visual & CMM Inspection | SNSPPU-CAV-INSP-CAV | 104211800-M8U-8200-A001 |  | PPU-23 | [15 empty] | 0 |  | 1.21.02.002.003.015.02 | Cleanroom String Ass Proc
|  | PUCSAP | P. Dhakal | Cavity | Cavity Visual & CMM Inspection | SNSPPU-CAV-INSP-CAV | 104211800-M8U-8200-A001 |  | PPU-24 | [15 empty] | 0 |  | 1.21.02.002.003.015.02 | Cleanroom String Ass Proc
|  | PUCSAP | P. Dhakal | Cavity | Cavity Visual & CMM Inspection | SNSPPU-CAV-INSP-CAV | 104211800-M8U-8200-A001 |  | PPU-25 | [15 empty] | 0 |  | 1.21.02.002.003.015.02 | Cleanroom String Ass Proc
|  | PUCSAP | P. Dhakal | Cavity | Cavity Visual & CMM Inspection | SNSPPU-CAV-INSP-CAV | 104211800-M8U-8200-A001 |  | PPU-26 | [15 empty] | 0 |  | 1.21.02.002.003.015.02 | Cleanroom String Ass Proc
|  | PUCSAP | P. Dhakal | Cavity | Cavity Visual & CMM Inspection | SNSPPU-CAV-INSP-CAV | 104211800-M8U-8200-A001 |  | PPU-27 | [15 empty] | 0 |  | 1.21.02.002.003.015.02 | Cleanroom String Ass Proc
|  | PUCSAP | P. Dhakal | Cavity | Cavity Visual & CMM Inspection | SNSPPU-CAV-INSP-CAV | 104211800-M8U-8200-A001 |  | PPU-28 | [15 empty] | 0 |  | 1.21.02.002.003.015.02 | Cleanroom String Ass Proc
|  | PUCSAP | P. Dhakal | Cavity | Cavity Visual & CMM Inspection | SNSPPU-CAV-INSP-CAV | 104211800-M8U-8200-A001 |  | PPU-29 | [15 empty] | 0 |  | 1.21.02.002.003.015.02 | Cleanroom String Ass Proc
|  | PUCSAP | P. Dhakal | Cavity | Cavity Visual & CMM Inspection | SNSPPU-CAV-INSP-CAV | 104211800-M8U-8200-A001 |  | PPU-30 | [15 empty] | 0 |  | 1.21.02.002.003.015.02 | Cleanroom String Ass Proc
|  | PUCSAP | P. Dhakal | Cavity | Cavity Visual & CMM Inspection | SNSPPU-CAV-INSP-CAV | 104211800-M8U-8200-A001 |  | PPU-31 | [15 empty] | 0 |  | 1.21.02.002.003.015.02 | Cleanroom String Ass Proc
|  | PUCSAP | P. Dhakal | Cavity | Cavity Visual & CMM Inspection | SNSPPU-CAV-INSP-CAV | 104211800-M8U-8200-A001 |  | PPU-32 | [15 empty] | 0 |  | 1.21.02.002.003.015.02 | Cleanroom String Ass Proc
0
[5 empty] | Helium Vessel Mechanical & Visual Inspections | [5 empty] | 2 | [7 empty] | 2020-04-13 | [5 empty] | 0
|  | PUHVPR | K. Wilson | Helium Vessel Mechanical & Visual Inspections | Helium Vessel Shell Inspection | SNSPPU-INSP-HES | 104211700-M8U-8200-A020 | HELIUM VESSEL - SHELL WELDMENT | [5 empty] | 28 |  |  | CMM |  | 2020-06-18 |  |  |  | 10 | 4 | 24 |  | 1.21.02.002.003.003.03 |  |  |  |  | 08Oct2020: 10 of 30 rec'd per KW , traveler to be updated with sampling plan (1:5) , or if we don’t get update add Katherines email to all SNs not inspected
|  | PUHVPR | K. Wilson | Helium Vessel Mechanical & Visual Inspections | Helium Vessel Probe End Inspection | SNSPPU-INSP-HEHDP | 104211700-M8U-8200-A025 | PROBE END HEAD WELDMENT | [5 empty] | 28 |  |  | CMM |  | 2020-06-18 |  |  |  | 10 | 4 | 24 |  | 1.21.02.002.003.003.03 |  |  |  |  | same as HE Vessel
|  | PUHVPR | K. Wilson | Helium Vessel Mechanical & Visual Inspections | Helium Vessel FPC End Inspection | SNSPPU-INSP-HEHDF | 104211700-M8U-8200-A023 | FPC END HEAD WELDMENT | [5 empty] | 28 |  |  | CMM |  | 2020-05-15 |  |  |  | 10 | 4 | 24 |  | 1.21.02.002.003.003.03 |  |  |  |  | same as HE Vessel
0
[5 empty] | Cavity String PPU Bellows | [5 empty] | 4 |  |  | 21 | [10 empty] | 21 |  |  |  | 1.02.03.14.03 | 102031403000 | Perform Mechanical Inspection of CM-01 Cavity #1 | each cavity string has three beamline bellows, one return warm to cold bellows, and one supply warm to cold bellows.
|  | PUHVPR | K. Wilson | Cavity String PPU Bellows | Beamline Bellows Visual Inspection (3 per string) | SNSPPU-INSP-BLBP | 104211500-M8U-8200-A029 | BELLOWS ASSEMBLY |  |  | need Jan/01 |  |  | 21 | [5 empty] | 2020-10-07 |  |  | 24 |  | 21 |  | 1.21.02.002.003.015.02 | Cleanroom String Ass Proc |  |  |  | 2 delivered 07Oct2020, traveler in process
|  | PUHVPR | K. Wilson | Cavity String PPU Bellows | Supply Warm to Cold Bellows Visual Inspection (1 per string) | SNSPPU-INSP-SUBP | 104210300-M8U-8200-A103 | SUPPLY WARM - COLD BEAMPIPE WELDMENT |  |  | need Jan/01 |  |  | 14 | [5 empty] | 2020-10-07 |  |  | 8 |  | 14 |  | 1.21.02.002.003.015.02 | Cleanroom String Ass Proc |  |  |  | 2 delivered 07Oct2020, traveler in process
|  | PUHVPR | K. Wilson | Cavity String PPU Bellows | Return Warm to Cold Bellows Visual Inspection (1 per string) | SNSPPU-INSP-RTBP | 104210300-M8U-8200-A205 | RETURN WARM - COLD BEAMPIPE WELDMENT |  |  | need Jan/01 |  |  | 14 | [5 empty] | 2020-10-07 |  |  | 8 |  | 14 |  | 1.21.02.002.003.015.02 | Cleanroom String Ass Proc |  |  |  | 2 delivered 07Oct2020, traveler in process
0
[5 empty] | Cryomodule Tuner Mechanical & Visual Inspections | [5 empty] | 8 |  |  | 28 | [8 empty] | 28 |  | 28
|  | PUTNPR | N. Huque | Cryomodule Tuner Mechanical & Visual Inspections | Tuner Assembly Visual & CMM Inspection | SNSPPU-CM-INSP-TUNC | 104211400-M8U-8200-A001 | SNS TUNER FRAME ASSEMBLY KIT | [14 empty] | 29 |  | 0 |  | 1.21.02.002.003.004.03 | Tuner Procurement | 1.02.03.04.02 | 102030402351 | Inspect Tuner Frames Lot #1 | 03Oct2020, all Tuner parts rec'd in July- Qty & need date ??
|  | PUTNPR | N. Huque | Cryomodule Tuner Mechanical & Visual Inspections | Tuner Harmonic Drives Batch Inspection | SNSPPU-CM-INSP-HMDR | HDC-014-100-2A SP | HARMONIC DRIVE | [10 empty] | 2020-08-01 |  |  |  | 29 |  | 0 |  | 1.21.02.002.003.004.03 | Tuner Procurement | 1.02.03.04.02 | 102030402270 | Inspect Tuner Harmonic Drives | 03Oct2020, all Tuner parts rec'd in July- Qty & need date ??
|  | PUTNPR | N. Huque | Cryomodule Tuner Mechanical & Visual Inspections | Tuner Motor Batch Inspection | SNSPPU-CM-INSP-SM | [18 empty] | 0 |  | 1.21.02.002.003.004.03 | Tuner Procurement | 1.02.03.04.02 | 102030402070 | Inspect Tuner Motors | 03Oct2020, all Tuner parts rec'd in July- Qty & need date ??
|  | PUTNPR | G. Cheng | Cryomodule Tuner Mechanical & Visual Inspections | Helium Outlet Bellows & Con Bellows Inspection | SNSPPU-CM-INSP | 104211500-M8U-8200-A026 | SNS-PPU CAVITY STRING CON BELLOWS 3.50 ID X 7.91 |  |  | 7 | [11 empty] | 9 |  | 0 |  | 1.21.02.002.003.004.03 | Tuner Procurement
|  | PUTNPR | G. Cheng | Cryomodule Tuner Mechanical & Visual Inspections | Equalizer Flex Hose Inspection | SNSPPU-CM-INSP-EQFH | [18 empty] | 0 |  | 1.21.02.002.003.004.03 | Tuner Procurement
|  | PUTNPR | G. Cheng | Cryomodule Tuner Mechanical & Visual Inspections | Cold Mass Return Piping Inspection | SNSPPU-CM-INSP-RPIPE | [18 empty] | 0 |  | 1.21.02.002.003.004.03 | Tuner Procurement
|  | PUTNPR | G. Cheng | Cryomodule Tuner Mechanical & Visual Inspections | Cold Mass Supply Piping Inspection | SNSPPU-CM-INSP-SPIPE | [18 empty] | 0 |  | 1.21.02.002.003.004.03 | Tuner Procurement
|  | PUTNPR | G. Cheng | Cryomodule Tuner Mechanical & Visual Inspections | Cold Mass Guard Vacuum Piping Assy Inspection | SNSPPU-CM-INSP-GVPA | [18 empty] | 0 |  | 1.21.02.002.003.004.03 | Tuner Procurement
|  | PUTNPR | G. Cheng | Cryomodule Tuner Mechanical & Visual Inspections | Cold Mass Misc. Components Inspection | SNSPPU-CM-INSP-CMMC | [18 empty] | 0 |  | 1.21.02.002.003.004.03 | Tuner Procurement
|  | PUTNPR | G. Cheng | Cryomodule Tuner Mechanical & Visual Inspections | 8 Pin Cryogenic Feedthru Inspection | SNSPPU-INSP-FT08P | [12 empty] | 2020-04-22 | [5 empty] | 0 |  | 1.21.02.002.003.004.03 | Tuner Procurement
0
|  | PUTSMP | K. Wilson | Cryomodule Tuner Mechanical & Visual Inspections | Therm Shield & MLI Proc | ??? | [18 empty] | 0 |  | 1.21.02.002.003.005.02 | Therm Shield & MLI Proc
0
[5 empty] | Cold Mass | [19 empty] | 0
|  | PUCMP | G. Cheng | Cold Mass | Helium Outlet Bellows and Con Bellows Weld Inspection | SNSPPU-CWI-HOBCB | 104211500-M8U-8200-017 (2pc) 104211500-MBU-8200-A026 (1Pc) | [6 empty] | 7 | [8 empty] | 7 |  | 7 | [6 empty] | 7 Kits + spares (each has 3 components A026 (1 pc) and A017 (2Pc)
[5 empty] | Space Frame & Thermal Shield | [8 empty] | 7 |  |  |  |  | 2020-07-06 |  |  |  | 1 |  | 7 |  |  |  | 1.02.03.14.03 | 102031403000 | Perform Mechanical Inspection of CM-01 Cavity #1
|  | PUSTSP | M. Marchlik | Cryomodule | Space Frame Inspection | SNSPPU-CM-INSP-SFR | [18 empty] | 0 |  | 1.21.02.002.003.017.02 | Spacefrm Therm ShieldProc |  |  |  | Space frame expected 9/25 (LATE)
|  | PUSTSP | M. Marchlik | Cryomodule | Thermal Station Inspection | SNSPPU-INSP-THRMST | [18 empty] | 0 |  | 1.21.02.002.003.017.02 | Spacefrm Therm ShieldProc
|  | PUSTSP | M. Marchlik | Cryomodule | Thermal Shield Inspection | SNSPPU-INSP-THRM | [18 empty] | 0 |  | 1.21.02.002.003.017.02 | Spacefrm Therm ShieldProc
0
[5 empty] | Cryomodule | [19 empty] | 0
|  | PUVVLP | M. Marchlik | Cryomodule | Vacuum Vessel Inspection | SNSPPU-CM-INSP-VV | [7 empty] | 7 | [10 empty] | 7 |  | 1.21.02.002.003.007.02 | Vacuum Vessel Proc |  |  |  | Cav. Vessel expected 15Dec 2020
|  | PUSECP | G. Cheng | Cryomodule | Supply End Can Inspection | SNSPPU-CM-INSP-SENC | [7 empty] | 7 | [10 empty] | 7 |  | 1.21.02.002.003.008.02 | Supply End Can Proc |  |  |  | End cans expected November 2020
|  | PUREPR | G. Cheng | Cryomodule | Return End Can Inspection | SNSPPU-CM-INSP-RENC | [7 empty] | 7 | [10 empty] | 7 |  | 1.21.02.002.003.009.03 | Return End Can Proc |  |  |  | End cans expected November 2020
|  | PUINSP | ??? | Cryomodule | Instrumentation Proc | ??? | [18 empty] | 0 |  | 1.21.02.002.003.010.02 | Instrumentation Proc
|  | PUTOLP | M. Marchlik | Cryomodule | Tophat Inspection | SNSPPU-CM-INSP-TPHT | 104110000-A262-1 | SNS PPU CM FPC TOPHATS | [5 empty] | 28 |  |  |  |  | 2020-04-24 | 2020-04-24 |  |  | 28 |  | 28 |  | 1.21.02.002.003.011.02 | Tooling Proc
|  | PUTOLP | M. Marchlik | Cryomodule | Tophat Bellow Inspection | SNSPPU-CM-INSP-TPHTB | 104211600-A051 |  |  |  | 6 |  |  | 30 |  |  |  |  | 2020-08-06 | 2020-08-06 |  |  | 30 |  | 30 | [6 empty] | Per Matt - Top Hat Bellows are higher prioirty than top hats The Tophat Bellows (104211600-A051) were inventoried 8/6/2020, there are 30 of them.
|  | PUMSPR | G. Cheng | Cryomodule | Outer Magnetic Shield Visual Inspecton | SNSPPU-INSP-OMAG | 104211000-M8U-8200-A001 | OUTER MAGNETIC SHIELD ASSY |  |  | 3 |  |  | 7 |  |  |  |  | 2020-09-24 | 2020-09-24 |  |  | 7 |  | 7 |  | 1.21.02.002.003.013.03 | Magnetic Shielding Proc |  |  |  | Blue Crab Scheduled to start 14Oct2020-28Oct2020
|  | PUMSPR | G. Cheng | Cryomodule | Inner Magnetic Shield Visual Inspecton | SNSPPU-INSP-IMAG | 104211200-M8U-8200-A001 | INNER MAGNETIC SHIELD ASSY |  |  | 3 |  |  | 7 |  |  |  |  | 2020-09-24 | 2020-09-24 |  |  | 7 |  | 7 |  | 1.21.02.002.003.013.03 | Magnetic Shielding Proc |  |  |  | Blue Crab Scheduled to start 14Oct2020-28Oct2020
|  | PUCMP | K. Wilson | Cryomodule | Cold Mass Assembly Proc | [19 empty] | 0 |  | 1.21.02.002.003.016.02 | Cold Mass Assembly Proc
0
|  | PUFCAP | K. Wilson | Cryomodule | Final CM Assembly Proc | [19 empty] | 0 |  | 1.21.02.002.003.018.02 | Final CM Assembly Proc
0
| LCLS-II |  | Naeem Huque | [21 empty] | 0 |  | 1.17 | LCLS-II Cryomodule
|  | L2CP17 | HyeKyoung Park |  | LCLSII HOM BLA incoming inspection, testing and storage | L2PRD-CAV-INSP-BLA | [18 empty] | 0 |  |  | BLAs
0
0
| HE | HECINT | Katherine Wilson | [21 empty] | 0 |  | TBD | TBD
|  | ?? | Hogan | Inspection | Helium Vessel Inspection | L2HE-INSP-CAV | [7 empty] | 80 |  |  |  |  | 2021-04-29
|  | ?? | Hogan | Inspection | Cavity RF Inspection | L2HE-TUNE-CAV-RFIN
|  |  | Huque | Inspection | Coupler (pairs) | L2HE-INSP-FPC | [12 empty] | 2021-05-28 | [12 empty] | Serial numbers from Supplier now reauired so CPI has material tracability (first 4 bellows won't have tracability - contact Mod was too late ) Prioirty is Cold Bellows (beam line) -
|  |  | Huque | Inspection | FPC Waveguide Incoming Inspection | L2HE-INSP-FPCWG
|  | HECFT2 | Park | Inspection | Cavity Field Probe Feedthru Receiving Inspection | L2HE-INSP-FPFT | GMM-9434A |  |  | 3 |  |  |  | 10 | [8 empty] | 10 |  | 10 | [6 empty] | 22Oct2020 Mike Dickey - L2HE HMFT & FPFTs awaiting SOTR Serialization
|  | HECFT2 | Park | Inspection | Cavity HOM Feedthru Receiving Inspection | L2HE-INSP-HMFT | GMM-B9433A |  |  | 3 |  |  |  | 21 | [8 empty] | 21 |  | 21 | [6 empty] | 22Oct2020 Mike Dickey - L2HE HMFT & FPFTs awaiting SOTR Serialization
|  | HEBEL1 | Wilson | Inspection | SAMPLE Bellows | no traveler
|  | HEBEL2 | Marchlik | Inspection | Cavity Beam Line Bellows PRCM | L2HE-INSP-BLBP
|  | HEBEL2 | Marchlik | Inspection | Cavity Beam Line Bellows Short | L2HE-INSP-BLBS
|  | HEBEL2 | Marchlik | Inspection | Cavity String Weldment Upstream Bellows | L2HE-INSP-BLBU | [12 empty] | 2021-04-19
|  |  | Marchlik | Inspection | String Beam Line Extension Downstream | L2HE-INSP-BLXD
|  |  | Marchlik | Inspection | String Beam Line Extension Upstream | L2HE-INSP-BLXU
|  |  |  | Inspection | 300K Current Leads CF Flange Inspection | L2HE-INSP-CFL
|  | HETUN2 |  | Inspection | End Lever Tuner Mechanical Frame Inspection | L2HE-INSP-TUNMC
|  | HETUN2 |  | Inspection | End Lever Tuner Moto | L2HE-INSP-TUNMT
|  |  | Peter Owen | Inspection | Tuner Piezo Actuatir Assembly Inspection | L2HE-INSP-TUNPZ | [12 empty] | 2021-07-19
|  | HEMAG2 | Lakshmi Latitha | Inspection | Quadrapole Magnet SPQA002 Inspection | L2HE-MAG-QUAD | [12 empty] | 2021-02-12
|  |  |  | Inspection | Bellows 2-Phase Pipe | L2HE-INSP-BP2PH
|  |  |  | Inspection | Cryomodule Cool Down Cryogenic Valve (CDV) | L2HE-INSP-CDV
|  |  |  | Inspection | Warm FPC Inspection | L2HE-INSP-FPCW
|  |  | Gary Cheng | Inspection | Receiving Inspection CM Magnetic Shield Assembly | L2HE-INSP-IMAG | [7 empty] | 10 |  |  |  |  | 2021-08-27
|  |  |  | Inspection | Receiving Inspection CM Rod Invar 2-Phase Long | L2HE-INSP-IROD2L
|  |  |  | Inspection | Receiving Inspection CM Rod Invar 2-Phase | L2HE-INSP-IROD2P
|  |  |  | Inspection | Receiving Inspection CM Assembly, JT Cryogenic Valve | L2HE-INSP-JTV
|  |  |  | Inspection | Receiving Inspection CM Assembly, JT Valve Tube Kit | L2HE-INSP-JTVTK
|  |  |  | Inspection | Receiving Inspection CM Assembly, Liquid He Level-DS | L2HE-INSP-LLDS
|  |  |  | Inspection | Receiving Inspection of CM Weldment Line Liquid Level DS | L2HE-INSP-LLNDS
|  |  |  | Inspection | Receiving Inspection CM Weldment Line Liquid Level US | L2HE-INSP-LLNUS
|  |  |  | Inspection | Receiving Inspection CM Assembly, Liquid He Level-US | L2HE-INSP-LLUS
|  |  |  | Inspection | LCLS-II Cryomodule MC Coupling Line Assembly Inspection | L2HE-INSP-MCCLA
|  |  |  | Inspection | Receiving Inspection CM Weldment 2-Phase Pipe End Cap | L2HE-INSP-PEC2P
|  |  | Gary Cheng | Inspection | Upper Cold Mass Inspection | L2HE-INSP-UCM | [7 empty] | 10 |  |  |  |  | 2021-03-23
|  |  |  | Inspection | Receiving Inspection CM Vacuum Vessel | L2HE-INSP-VV
|  | HEBPM2 | HK Park | Inspection | Beam Position Monitor (BPM) | no inspection ? | [12 empty] | 2021-02-22 | [5 empty] | 0
0
0
| SRFR&D |  | Bob Rimmer/Charlie Reece | [7 empty] | Priority - Lower than P1, C75, SNS, L2 and HE | [13 empty] | 0 |  | TBD | TBD
|  | ARDNB3 | Uttar Pudasaini |  | IA-012 straight beamline with all cells parallel (no tuning required) |  |  |  | IA-012 |  |  |  |  | 1 | [10 empty] | 1
| AUP |  | Naeem Huque |  | Travelers only where "CMM" is required | [5 empty] | Priority - Lower than P1, C75, SNS, L2 and HE | [13 empty] | 0 |  | TBD | TBD
|  | AUPHM2 | Mathew Weaks | H-HOM Feedthrough | H-HOM Feedthrough Brazing Assembly | AUP-ASSY-HHOMFT-BRZAS | JL0089751 | [6 empty] | 3 | [5 empty] | NOT IN |  |  |  |  | 3
|  | AUPHM2 | Mathew Weaks | H-HOM Feedthrough | H-HOM Feedthrough Assembly | AUP-ASSY-HHOMFT-HFTASY | JL0093243 | [6 empty] | 3 | [5 empty] | NOT IN |  |  |  |  | 3
|  | AUPHM2 | Mathew Weaks | H-HOM Field Antenna | Field Antenna 25ohm | AUP-ASSY-FANT-FAASY | JL0090340 | [6 empty] | 3 | [5 empty] | NOT IN |  |  |  |  | 3
|  | AUPHM2 | Mathew Weaks | H-HOM Field Antenna | Feedthrough Cable Connector | AUP-PREP-FANT-CNCTR-R1 | JL0090343 | [6 empty] | 3 | [5 empty] | NOT IN |  |  |  |  | 3
|  | AUPHM2 | Mathew Weaks | V-HOM Coupler | V-HOM Couple 25ohm | AUP-ASSY-VHOM-VCASSY | JL0089940 | [6 empty] | 3 | [5 empty] | NOT IN |  |  |  |  | 3
|  | AUPHM2 | Mathew Weaks | H-HOM Damper | Niobium Can Lid Machining Assembly | AUP-ASSY-DAMP-CLASSY | JL0088600 | [6 empty] | 3 | [5 empty] | NOT IN |  |  |  |  | 3
|  | AUPHM2 | Mathew Weaks | H-HOM Damper | AUP RFD H-HOM Damper | AUP-ASSY-DAMP-FASSY | JL0086007 | [6 empty] | 3 | [5 empty] | NOT IN |  |  |  |  | 3
|  | AUPHM2 | Mathew Weaks | H-HOM Damper | DN100 Braze Assembly | AUP-ASSY-DAMP-FLGWLD | JL0088274 | [6 empty] | 3 | [5 empty] | NOT IN |  |  |  |  | 3
|  | AUPHM2 | Mathew Weaks | H-HOM Damper | DN100 Machining | AUP-ASSY-DAMP-FLMCH | JL0088272 | [6 empty] | 3 | [5 empty] | NOT IN |  |  |  |  | 3
|  | AUPHM2 | Mathew Weaks | H-HOM Damper | Hook and Tee Weldment | AUP-ASSY-DAMP-HKTEE | JL0088266 | [6 empty] | 3 | [5 empty] | NOT IN |  |  |  |  | 3
|  | AUPHM2 | Mathew Weaks | H-HOM Damper | Inner Can Assembly | AUP-ASSY-DAMP-INCAN | JL0088602 | [6 empty] | 3 | [5 empty] | NOT IN |  |  |  |  | 3
|  | AUPHM2 | Mathew Weaks | H-HOM Damper | Niobium Lid Brazing Assembly | AUP-ASSY-DAMP-NLASSY | JL0088238 | [6 empty] | 3 | [5 empty] | NOT IN |  |  |  |  | 3
|  | AUPHM2 | Mathew Weaks | H-HOM Damper | Outer Tube Assembly | AUP-ASSY-DAMP-TBASSY | JL0088268 | [6 empty] | 3 | [5 empty] | NOT IN |  |  |  |  | 3
|  | AUPHM2 | Mathew Weaks | H-HOM Damper | H-HOM Inner Tube | AUP-PREP-DAMP-ITUBE-R1 | JL0086026 | [6 empty] | 3 | [5 empty] | NOT IN |  |  |  |  | 3
|  | AUPHM2 | Mathew Weaks | H-HOM Damper | Niobium Can Lid Final Machining | AUP-INSP-DAMP-LDMCH | JL0088326 | [6 empty] | 3 | [5 empty] | NOT IN |  |  |  |  | 3
|  | AUPHM2 | Mathew Weaks | H-HOM Damper | Niobium Can Lid | AUP-PREP-DAMP-NCLID-R1 | JL0086010 | [6 empty] | 3 | [5 empty] | IN (13Oct2020) |  |  |  |  | 3
|  | AUPHM2 | Mathew Weaks | H-HOM Damper | HOM Niobium Hook | AUP-INSP-DAMP-HOOK | JL0086021 | [6 empty] | 3 | [5 empty] | NOT IN |  |  |  |  | 3
|  | AUPHM2 | Mathew Weaks | H-HOM Damper | HOM Tee | AUP-INSP-DAMP-TEE | JL0083868 | [6 empty] | 3 | [5 empty] | NOT IN |  |  |  |  | 3
|  | AUPHM2 | Mathew Weaks | Common Travelers | Feedthrough 25ohm Brazing Assembly | AUP-ASSY-CMN-BRZAS | JL0090121 | [6 empty] | 6 | [5 empty] | NOT IN |  |  |  |  | 6
|  | AUPHM2 | Mathew Weaks | Common Travelers | Flange Brazing Assembly | AUP-ASSY-CMN-FLBRZ-R1 | JL0092614 | [6 empty] | 9 | [5 empty] | NOT IN |  |  |  |  | 9
|  | AUPHM2 | Mathew Weaks | Common Travelers | Ceramic D40d14 | AUP-INSP-CMN-DSCCRM | LHCACFHC0206 | [6 empty] | 17 | [5 empty] | NOT IN |  |  |  |  | 17
| SRFR&D |  | Bob Rimmer/Charlie Reece | [7 empty] | Priority - Lower than P1, C75, SNS, L2 and HE | [13 empty] | 0 |  | TBD | TBD
|  | ARDNB3 | Uttar Pudasaini |  | IA-012 straight beamline with all cells parallel (no tuning required) |  |  |  | IA-012 |  |  |  |  | 1 | [10 empty] | 1
| SRFR&D - Crymod Assy-Nb3Sn QCM (Reilly/ Macha/Grigory) |  |  |  | No traveler to be used, per K. Macha will use M Drive /CMM for QA data
|  | NB3SND | Uttar Pudasaini | Disassy-Nb3Sn QCM | N/A | N/A | o 5C75-RI-nbsn1/nbsn2 |  | 1 & 2 |  |  |  |  | 2
|  | NB3SNP | Uttar Pudasaini | CavProc&Assy-Nb3Sn QCM | N/A | N/A | [7 empty] | 1
|  | NB3SNA | Uttar Pudasaini | Crymod Assy-Nb3Sn QCM | N/A | N/A | [7 empty] | 1
|  | NB3SNQ | Uttar Pudasaini | Nb3Sn QCM QA/Insp&CMM/WCD | N/A | N/A | [7 empty] | 1
|  | NB3SNT | Uttar Pudasaini | CMTF-Test Nb3Sn QCM | N/A | N/A | [7 empty] | 1
|  | NB3SNC | Uttar Pudasaini | Install&Comm-Nb3Sn QCM | N/A | N/A | [7 empty] | 1
600
Note on G1: E. Anne McEwen: Green = Complete Blue = Draft sent for edits Purple = rec'd by Pansophy awaiting release Yelllow = not available
Note on F4: Cavity CMM Receiving Inspection, Pre/Post Weld , afterLap etc.
Note on F5: Cavity CMM Receiving Inspection, Pre/Post Weld , afterLap etc.
Note on F6: Cavity CMM Receiving Inspection, Pre/Post Weld , afterLap etc.
Note on F7: Cavity CMM Receiving Inspection, Pre/Post Weld , afterLap etc.
Note on G13: Was P1-INSP-WINM, will use General P1 Inspoection traveler instead P1- INSR (27Oct2020) From: Scott Williams <scott@jlab.org> Sent: Friday, October 9, 2020 11:43 AM To: E. Anne McEwen <mcewen@jlab.org> Subject: Re: Travelers for double sided flange and modified window Hi Anne, The P1-INSP-WINM will need work to conform to this style and configuration of a modified F100 Window that this appears to be relevant to. Not sure if the evolution of the window design is the reason for Traveler not applying to the current window design (looks like an earlier design sequence). This will have to be addressed after vacation unfortunately. Have A Good Weekend,
Note on G24: E. Anne McEwen: released in Pansophy on 29Oct2020
Note on H54: Original PN for SNS HB Cavity Top Assmebly CRM9007010-0002
Note on H55: Original PN for SNS HB Cavity Top Assmebly CRM9007010-0002
Note on H56: Original PN for SNS HB Cavity Top Assmebly CRM9007010-0002
Note on H57: Original PN for SNS HB Cavity Top Assmebly CRM9007010-0002
Note on H58: Original PN for SNS HB Cavity Top Assmebly CRM9007010-0002
Note on H59: Original PN for SNS HB Cavity Top Assmebly CRM9007010-0002
Note on H60: Original PN for SNS HB Cavity Top Assmebly CRM9007010-0002
Note on H61: Original PN for SNS HB Cavity Top Assmebly CRM9007010-0002
Note on H62: Original PN for SNS HB Cavity Top Assmebly CRM9007010-0002
Note on H63: Original PN for SNS HB Cavity Top Assmebly CRM9007010-0002
Note on H64: Original PN for SNS HB Cavity Top Assmebly CRM9007010-0002
Note on H65: Original PN for SNS HB Cavity Top Assmebly CRM9007010-0002
Note on H66: Original PN for SNS HB Cavity Top Assmebly CRM9007010-0002
Note on H67: Original PN for SNS HB Cavity Top Assmebly CRM9007010-0002
Note on H68: Original PN for SNS HB Cavity Top Assmebly CRM9007010-0002
Note on H69: Original PN for SNS HB Cavity Top Assmebly CRM9007010-0002
Note on H70: Original PN for SNS HB Cavity Top Assmebly CRM9007010-0002
Note on H71: Original PN for SNS HB Cavity Top Assmebly CRM9007010-0002
Note on H72: Original PN for SNS HB Cavity Top Assmebly CRM9007010-0002
Note on H73: Original PN for SNS HB Cavity Top Assmebly CRM9007010-0002
Note on H74: Original PN for SNS HB Cavity Top Assmebly CRM9007010-0002
Note on H75: Original PN for SNS HB Cavity Top Assmebly CRM9007010-0002
Note on H76: Original PN for SNS HB Cavity Top Assmebly CRM9007010-0002
Note on H77: Original PN for SNS HB Cavity Top Assmebly CRM9007010-0002
Note on H78: Original PN for SNS HB Cavity Top Assmebly CRM9007010-0002
Note on H79: Original PN for SNS HB Cavity Top Assmebly CRM9007010-0002
Note on H80: Original PN for SNS HB Cavity Top Assmebly CRM9007010-0002
Note on H81: Original PN for SNS HB Cavity Top Assmebly CRM9007010-0002
Note on H82: Original PN for SNS HB Cavity Top Assmebly CRM9007010-0002
Note on H83: Original PN for SNS HB Cavity Top Assmebly CRM9007010-0002
Note on H84: Original PN for SNS HB Cavity Top Assmebly CRM9007010-0002
Note on G87: Sampling Plan to be added to Traveler by KW 1 out of 5 sammpling If traveler does not get updated add email to any not inspected as "devaitation"
Note on G88: Sampling Plan to be added to Traveler by KW 1 out of 5 sammpling If traveler does not get updated add email to any not inspected as "devaitation"
Note on G89: Sampling Plan to be added to Traveler by KW 1 out of 5 sammpling If traveler does not get updated add email to any not inspected as "devaitation"
Note on O91: E. Anne McEwen: as of 27Aug2020
Note on G92: 16Oct2020, delivered to Pansophy for routing & approval
Note on G93: 16Oct2020, delivered to Pansophy for routing & approval
Note on G94: 16Oct2020, delivered to Pansophy for routing & approval
Note on F127: E. Anne McEwen: All spare and new magnetic shields need to be inspected to make sure we have 7 complete sets of inner, outer, supply extension and return extension shields, we should. But the spare magnetic shields are repaired by a vendor and there are new shields made by another vendor. So, it is complicated. I think two inspectors should team up to do the inspection because some shields can be large and heavy. Shields are crated. We don't want to drop the shields to the ground and permanently damage any of them. I estimate 3 days for two people to go through the shields and regroup them to make 7 complete sets. There will be excess shields to be packaged separately. Inspectors shall consult me before they start the inspection. I need to explain in more details about what they are expected to look for.
Note on F128: E. Anne McEwen: All spare and new magnetic shields need to be inspected to make sure we have 7 complete sets of inner, outer, supply extension and return extension shields, we should. But the spare magnetic shields are repaired by a vendor and there are new shields made by another vendor. So, it is complicated. I think two inspectors should team up to do the inspection because some shields can be large and heavy. Shields are crated. We don't want to drop the shields to the ground and permanently damage any of them. I estimate 3 days for two people to go through the shields and regroup them to make 7 complete sets. There will be excess shields to be packaged separately. Inspectors shall consult me before they start the inspection. I need to explain in more details about what they are expected to look for.
Note on C137: E. Anne McEwen: Was HEED3A Development Account code for all development work for HE
Note on K142: E. Anne McEwen: behind C75, P1 and SNSPPU
Note on K143: E. Anne McEwen: behind C75, P1 and SNSPPU
Note on G184: E. Anne McEwen: available in Pansophy 0-3Nov2020
Note on G194: E. Anne McEwen: available in Pansophy 0-3Nov2020
Note on G196: E. Anne McEwen: available in Pansophy 0-3Nov2020
Note on G198: E. Anne McEwen: available in Pansophy 0-3Nov2020
Note on G200: E. Anne McEwen: available in Pansophy 0-3Nov2020
Note on G201: E. Anne McEwen: available in Pansophy 0-3Nov2020

## Complete Inspections
Ready to Inspect | Project Name | Inspection Charge Code | Contact /SOTR | Sub Assembly | Traveler Name | Traveler Names/Availablity G= available, Y/B/P = not available as of 06Oct2020 | Part No. | Part Name | Serial No.s | Priority Total Project | Priority within Project | Date when Parts & Traveler in CMM | Days waiting to start | Qty Required | First Article (Man Hrs) | Planned Duration (Man-Hrs) | Type (CMM) | Type (Visual & Other) | Anticpated delivery date first lot | Actual Delivery date first lot | Planned Start Date | Finish | Qty delivered to JLAB Sep2020 | Complete or Qualified | Qty remaining to Inspect | Complete | WBS-Cost Point | WBS Name | P6- WBS Path | P6- Activity ID | P6-Activity Name | Comments | Project Name
| P1 |  | Tony Reilly | [30 empty] | P1 Assembly & Test
| complete | P1001Q | Gigi/Tiffany | Cavity | Helium Vessel Weldment Assembly Inspection | P1-INSP-HELV |  |  | JL005 |  |  |  |  | 1 |  |  | CMM |  | Qualified |  |  | 2020-10-08 | 1 | 1 | 0 | Complete | [5 empty] | Qualified , no further CMM work needed
| complete | P1001Q | Gigi/Tiffany | Cavity | Helium Vessel Weldment Assembly Inspection | P1-INSP-HELV |  |  | JL007 |  |  |  |  | 1 |  |  | CMM |  | Qualified |  |  | 2020-10-02 | 1 | 1 | 0 | Complete | [5 empty] | Qualified , no further CMM work needed
| complete | P1001Q | Gigi/Tiffany | Cavity Preparation | Helium Vessel Weldment Assembly Inspection | P1-INSP-HELV |  |  | JL003 |  |  |  |  | 1 |  |  | CMM | [5 empty] | 1 |  | 1 | [6 empty] | Qualified
| complete | P1001Q | Gigi/Tiffany | Cavity Preparation | Helium Vessel Weldment Assembly Inspection | P1-INSP-HELV |  |  | JL004 |  |  |  |  | 1 |  |  | CMM | [5 empty] | 1 |  | 1 | [6 empty] | Qualified
| complete | P1001Q | Gigi/Tiffany | Cavity Preparation | Helium Vessel Weldment Assembly Inspection | P1-INSP-HELV |  |  | JL008 |  |  |  |  | 1 |  |  | CMM | [5 empty] | 1 |  | 1 | [6 empty] | Qualified
| C75-01 |  | Tony Reilly | [30 empty] | C75-01 Assembly & test
| C7502 |  | Tony Reilly | [30 empty] | C75-02 Assemble & Test
| C7503 |  | Tony Reilly | [30 empty] | C75-03 Assemble & Test
| C100R |  | Tony Reilly | [30 empty] | C75-03 Assemble & Test
| SNSPPU | N/A | Ed Daly | [29 empty] | 1.21.02.002.003.005 | SNSPPU Cryomodule (7 CMs )
| LCLS-II |  | Naeem Huque | [29 empty] | 1.17 | LCLS-II Cryomodule
| LCLS-II HE |  | Katherine Wilson | [29 empty] | TBD | TBD
|  |  | Hogan |  | Receiving Inspection CM Rod Invar 2-Phase Long | L2PRD-INSP-IROD2L
|  |  | Hogan |  | Receiving Inspection CM Rod Invar 2-Phase | L2PRD-INSP-IROD2P
|  |  | Hogan |  | Receiving Inspection CM Assembly, JT Cryogenic Valve | L2PRD-INSP-JTV
|  |  | Hogan |  | Receiving Inspection CM Assembly, JT Valve Tube Kit | L2PRD-INSP-JTVTK
|  |  | Hogan |  | Receiving Inspection CM Assembly, Liquid He Level-DS | L2PRD-INSP-LLDS
|  |  | Hogan |  | Receiving Inspection of CM Weldment Line Liquid Level DS | L2PRD-INSP-LLNDS
|  |  | Hogan |  | Receiving Inspection CM Weldment Line Liquid Level US | L2PRD-INSP-LLNUS
|  |  | Hogan |  | Receiving Inspection CM Assembly, Liquid He Level-US | L2PRD-INSP-LLUS
| AUP |  | Naeem Huque | [29 empty] | TBD | TBD
| JLEIC |  | HK Park |  | JLEIC Crab Cavity Parts | [27 empty] | TBD | TBD
|  | ??? | HyeKyoung Park |  | components for JLEIC Crab Cavities | R&D Work , see email (no Traveler needed) | [25 empty] | No longer required at this time, removed from CMM room by HK Park 13Oct2020
| SRFR&D |  | Rimmer/Reece | [29 empty] | TBD | TBD
Note on G1: E. Anne McEwen: Green = Complete Blue = Draft sent for edits Purple = rec'd by Pansophy awaiting release Yelllow = not available
Note on F5: Cavity CMM Receiving Inspection, Pre/Post Weld , afterLap etc.
Note on F6: Cavity CMM Receiving Inspection, Pre/Post Weld , afterLap etc.
Note on F7: Cavity CMM Receiving Inspection, Pre/Post Weld , afterLap etc.
Note on F8: Cavity CMM Receiving Inspection, Pre/Post Weld , afterLap etc.
Note on F9: Cavity CMM Receiving Inspection, Pre/Post Weld , afterLap etc.

## Tony's Milestone Chart 17Aug20
Task Name | Duration | Start | Finish
SNS PPU (7 CM) | 745 days | Tue 11/26/19 | Thu 11/10/22
PPU Cavity Prep and Test | 478 days | Tue 11/26/19 | Wed 10/13/21
PPU Cavity String Assembly | 326 days | Thu 8/13/20 | Fri 12/3/21
PPU Cryomodule Assembly | 400 days | Fri 1/8/21 | Fri 8/12/22
PPU Cryomodule Test | 298 days | Wed 8/11/21 | Fri 10/21/22
PPU Pack and Ship | 262 days | Thu 10/21/21 | Thu 11/10/22
LCLS II HE Assembly (10 CM - JLab) | 628 days | Thu 9/30/21 | Wed 4/17/24
HE Cavity Prep and Test | 269 days | Thu 9/30/21 | Mon 10/31/22
HE Cavity String Assembly | 386 days | Mon 10/25/21 | Fri 5/19/23
HE Cryomodule Assembly | 504 days | Wed 1/5/22 | Tue 1/16/24
HE Cryomodule Test | 398 days | Tue 8/23/22 | Wed 4/3/24
HE Pack and Ship | 408 days | Tue 8/23/22 | Wed 4/17/24
CEBAF Performance Plan Cryomodules (10 C75 + 6 C100R) | 1270 days | Wed 2/14/18 | Fri 2/17/23
Disassembe a C20 (cav for C75-02, rest for C75-03) | 60 days | Wed 2/14/18 | Tue 5/8/18
C75-01 CM Assemble and Test | 812 days | Wed 2/14/18 | Fri 4/9/21
Cavity Procurement | 324 days | Wed 2/14/18 | Mon 5/13/19
Dog Leg Windows | 116 days | Mon 4/8/19 | Mon 9/16/19
Inspections and QA | 285 days | Wed 2/14/18 | Tue 3/19/19
Cavity Pair Qualification | 99 days | Mon 5/4/20 | Fri 9/18/20
Pair Qualification Completed | 0 days | Fri 9/18/20 | Fri 9/18/20
Cryounit Assembly | 90 days | Fri 8/21/20 | Fri 1/8/21
Cryo Unit Assembly Completed | 0 days | Fri 1/8/21 | Fri 1/8/21
Cryomodule Assembly | 100 days | Mon 10/5/20 | Fri 3/5/21
Cryomodule Assembly Completed | 0 days | Fri 3/5/21 | Fri 3/5/21
Acceptance Test | 25 days | Mon 3/8/21 | Fri 4/9/21
Acceptance Test Completed | 0 days | Fri 4/9/21 | Fri 4/9/21
C75-01 Install and Commission | 20 days | Mon 4/12/21 | Fri 5/7/21
C75-01 Turn Over to Accel Ops | 0 days | Fri 5/7/21 | Fri 5/7/21
Disassemble a C20 (for C75-04) | 60 days | Mon 5/10/21 | Tue 8/3/21
P1 Refurbishment | 251 days | Thu 5/7/20 | Fri 5/7/21
Disassembly | 50 days | Thu 5/7/20 | Wed 7/15/20
Crymodule Disassembly Completed | 0 days | Wed 7/15/20 | Wed 7/15/20
Cavity Prep and Test | 70 days | Thu 7/16/20 | Thu 10/22/20
Cavity Prep and Test Completed | 0 days | Thu 10/22/20 | Thu 10/22/20
String Assembly | 15 days | Fri 10/23/20 | Thu 11/12/20
String Assembly Completed | 0 days | Thu 11/12/20 | Thu 11/12/20
Space Frame Assembly | 45 days | Fri 11/13/20 | Thu 1/28/21
Space Frame Assembly Completed | 0 days | Thu 1/28/21 | Thu 1/28/21
Cryomodule Assembly | 45 days | Fri 1/29/21 | Thu 4/1/21
Cryomodule Assembly Completed | 0 days | Thu 4/1/21 | Thu 4/1/21
Cryomodule Test | 20 days | Mon 4/12/21 | Fri 5/7/21
Cryomodule Test Completed | 0 days | Fri 5/7/21 | Fri 5/7/21
Install and Commission P1 | 15 days | Mon 5/10/21 | Mon 5/31/21
P1 Turn Over to Accel Ops | 0 days | Mon 5/31/21 | Mon 5/31/21
C75-02 CM Assemble and Test | 597 days | Fri 3/1/19 | Wed 6/30/21
Cavity Procurement | 270 days | Mon 8/5/19 | Fri 8/14/20
Cavities Arrived | 0 days | Fri 8/14/20 | Fri 8/14/20
Dog Leg Windows | 391 days | Fri 3/1/19 | Fri 8/28/20
Dog Legs Completed | 0 days | Fri 8/28/20 | Fri 8/28/20
Inspections and QA | 234 days | Mon 6/8/20 | Fri 5/14/21
Cavity Pair Qualification | 135 days | Mon 8/17/20 | Mon 3/8/21
Cavity Pair Qualification Completed | 0 days | Mon 3/8/21 | Mon 3/8/21
Cryounit Assembly | 100 days | Tue 10/27/20 | Mon 3/29/21
Cryounit Assembly Completed | 0 days | Mon 3/29/21 | Mon 3/29/21
Cryomodule Assembly | 100 days | Tue 1/5/21 | Tue 5/25/21
Cryomodule Assembly Completed | 0 days | Tue 5/25/21 | Tue 5/25/21
Acceptance Test | 26 days | Wed 5/26/21 | Wed 6/30/21
Cryomodule Test Completed | 0 days | Wed 6/30/21 | Wed 6/30/21
C75-02 Install and Commission | 20 days | Mon 10/25/21 | Fri 11/19/21
C75-02 Turn Over to Accel Ops | 0 days | Fri 11/19/21 | Fri 11/19/21
Disassemble a C20 (for C75-05) | 60 days | Mon 11/22/21 | Mon 2/28/22
C75-03 CM Assembly and Test | 490 days | Fri 1/31/20 | Thu 1/20/22
Cavity Procurement | 240 days | Fri 1/31/20 | Fri 1/15/21
Cavities Arrived | 0 days | Fri 1/15/21 | Fri 1/15/21
Dog Leg Windows | 116 days | Mon 8/3/20 | Tue 1/26/21
Dog Legs Completed | 0 days | Tue 1/26/21 | Tue 1/26/21
Inspections and QA | 234 days | Wed 11/11/20 | Thu 10/21/21
Cavity Pair Qualification | 130 days | Mon 1/18/21 | Tue 7/20/21
Cavity Pair Qualification Completed | 0 days | Tue 7/20/21 | Tue 7/20/21
Cryounit Assembly | 109 days | Mon 4/19/21 | Tue 9/21/21
Cryounit Assembly Completed | 0 days | Tue 9/21/21 | Tue 9/21/21
Cryomodule Assembly | 105 days | Mon 6/28/21 | Tue 11/23/21
Cryomodule Assembly Completed | 0 days | Tue 11/23/21 | Tue 11/23/21
Acceptance Test | 26 days | Fri 12/3/21 | Thu 1/20/22
Cryomodule Test Completed | 0 days | Thu 1/20/22 | Thu 1/20/22
C75-03 Install and Commission | 20 days | Fri 1/21/22 | Thu 2/17/22
C75-03 Turn Over to Accel Ops | 0 days | Thu 2/17/22 | Thu 2/17/22
Disassemble a C20 (for C75-06) | 60 days | Fri 1/21/22 | Thu 4/14/22
C100-09R Refurbishment | 285 days | Mon 11/2/20 | Thu 1/6/22
Disassembly | 40 days | Mon 11/2/20 | Fri 1/8/21
Crymodule Disassembly Completed | 0 days | Fri 1/8/21 | Fri 1/8/21
Cavity Prep and Test | 100 days | Mon 1/11/21 | Mon 5/31/21
Cavity Prep and Test Completed | 0 days | Mon 5/31/21 | Mon 5/31/21
String Assembly | 15 days | Tue 6/1/21 | Mon 6/21/21
String Assembly Completed | 0 days | Mon 6/21/21 | Mon 6/21/21
Spafe Frame Assembly | 55 days | Tue 6/22/21 | Wed 9/8/21
Space Frame Assembly Completed | 0 days | Wed 9/8/21 | Wed 9/8/21
Cryomodule Assembly | 55 days | Thu 9/9/21 | Wed 11/24/21
Cryomodule Assembly Completed | 0 days | Wed 11/24/21 | Wed 11/24/21
Cryomodule Test | 20 days | Mon 11/29/21 | Thu 1/6/22
Cryomodule Test Completed | 0 days | Thu 1/6/22 | Thu 1/6/22
C100-09R Install & Commission | 20 days | Fri 1/7/22 | Thu 2/3/22
C100-09R Turn Over to Accel Ops | 0 days | Thu 2/3/22 | Thu 2/3/22
Pull Next C100 | 10 days | Fri 1/7/22 | Thu 1/20/22
C75-04 CM Assembly and Test | 378 days | Wed 1/27/21 | Mon 8/1/22
Cavity Procurement | 140 days | Mon 3/1/21 | Wed 9/15/21
Cavities Arrived | 0 days | Wed 9/15/21 | Wed 9/15/21
Dog Leg Windows | 116 days | Wed 1/27/21 | Fri 7/9/21
Dog Legs Completed | 0 days | Fri 7/9/21 | Fri 7/9/21
Inspections and QA | 234 days | Thu 5/6/21 | Mon 4/18/22
Cavity Pair Qualification | 120 days | Thu 9/16/21 | Thu 3/17/22
Cavity Pair Qualification Completed | 0 days | Thu 3/17/22 | Thu 3/17/22
Cryounit Assembly | 109 days | Thu 11/4/21 | Wed 4/20/22
Cryounit Assembly Completed | 0 days | Wed 4/20/22 | Wed 4/20/22
Cryomodule Assembly | 105 days | Thu 1/27/22 | Thu 6/23/22
Cryomodule Assembly Completed | 0 days | Thu 6/23/22 | Thu 6/23/22
Acceptance Test | 26 days | Fri 6/24/22 | Mon 8/1/22
Cryomodule Test Completed | 0 days | Mon 8/1/22 | Mon 8/1/22
C75-04 Install and Commission | 20 days | Wed 10/5/22 | Tue 11/1/22
C75-04 Turn Over to Accel Ops | 0 days | Tue 11/1/22 | Tue 11/1/22
Disassemble a C20 (for C75-07) | 60 days | Wed 11/2/22 | Tue 2/7/23
C75-05 CM Assembly and Test | 456 days | Wed 4/14/21 | Fri 2/17/23
Cavity Procurement | 196 days | Wed 4/14/21 | Tue 2/1/22
Cavities Arrived | 0 days | Tue 2/1/22 | Tue 2/1/22
Dog Leg Windows | 116 days | Tue 11/16/21 | Wed 5/11/22
Dgog Legs Completed | 0 days | Wed 5/11/22 | Wed 5/11/22
Inspections and QA | 234 days | Thu 3/10/22 | Fri 2/17/23
Cavity Pair Qualification | 120 days | Wed 2/2/22 | Thu 7/21/22
Cavity Pair Qualificaiton Completed | 0 days | Thu 7/21/22 | Thu 7/21/22
Cryounit Assembly | 105 days | Wed 3/23/22 | Thu 8/18/22
Cryounit Assembly Completed | 0 days | Thu 8/18/22 | Thu 8/18/22
Cryomodule Assembly | 100 days | Wed 5/25/22 | Fri 10/14/22
Cryomodule Assembly Completed | 0 days | Fri 10/14/22 | Fri 10/14/22
Acceptance Test | 26 days | Mon 10/24/22 | Wed 11/30/22
Cryomodule Test Completed | 0 days | Wed 11/30/22 | Wed 11/30/22
C75-05 Install and Commission | 20 days | Thu 12/1/22 | Mon 1/9/23
C75-05 Turn Over to Accel Ops | 0 days | Mon 1/9/23 | Mon 1/9/23
Disassemble a C20 (for C75-08) | 45 days | Thu 12/1/22 | Mon 2/13/23
C100-XR1 CM Assembly and Test | 225 days | Fri 1/21/22 | Thu 12/8/22
Disassembly | 40 days | Fri 1/21/22 | Thu 3/17/22
Cryomodule Disassembly Completed | 0 days | Thu 3/17/22 | Thu 3/17/22
Cavity Prep and Test | 45 days | Fri 3/18/22 | Thu 5/19/22
Cavity Prep and Test Completed | 0 days | Thu 5/19/22 | Thu 5/19/22
String Assembly | 15 days | Fri 5/20/22 | Fri 6/10/22
String Assembly Completed | 0 days | Fri 6/10/22 | Fri 6/10/22
Space Frame Assembly | 55 days | Mon 6/13/22 | Mon 8/29/22
Space Frame Assembly Completed | 0 days | Mon 8/29/22 | Mon 8/29/22
Cryomodule Assembly | 50 days | Tue 8/30/22 | Tue 11/8/22
Cryomodule Assembly Completed | 0 days | Tue 11/8/22 | Tue 11/8/22
Cryomodule Test | 20 days | Wed 11/9/22 | Thu 12/8/22
Cryomodule Test Completed | 0 days | Thu 12/8/22 | Thu 12/8/22
C100-XR1 Install and Commission | 25 days | Fri 12/9/22 | Tue 1/24/23
C100-XR1 Turn Over to Accel Ops | 0 days | Tue 1/24/23 | Tue 1/24/23
Disassemble C100-XX | 40 days | Fri 12/9/22 | Tue 2/14/23
C100-XR2 CM Assembly and Test | 225 days | Wed 1/5/22 | Fri 11/18/22
Disassembly | 40 days | Wed 1/5/22 | Tue 3/1/22
Disassembly Completed | 0 days | Tue 3/1/22 | Tue 3/1/22
Cavity Prep and Test | 45 days | Wed 3/2/22 | Tue 5/3/22
Cavity Prep and Test Completed | 0 days | Tue 5/3/22 | Tue 5/3/22
String Assembly | 15 days | Wed 5/4/22 | Tue 5/24/22
String Assembly Completed | 0 days | Tue 5/24/22 | Tue 5/24/22
Space Frame Assembly | 55 days | Wed 5/25/22 | Thu 8/11/22
Space Frame Assembly Completed | 0 days | Thu 8/11/22 | Thu 8/11/22
Cryomodule Assembly | 50 days | Fri 8/12/22 | Fri 10/21/22
Cryomodule Assembly Completed | 0 days | Fri 10/21/22 | Fri 10/21/22
Cryomodule Test | 20 days | Mon 10/24/22 | Fri 11/18/22
C100-XR2 Install and Commission | 25 days | Mon 11/21/22 | Fri 1/6/23
C100-XR2 Turn Over to Accel Ops | 0 days | Fri 1/6/23 | Fri 1/6/23
Disassemble C100-XX | 40 days | Mon 11/21/22 | Fri 1/27/23

## PPU Prioirty list 20Oct2020
| Charge | SOTR | PPU- Cavity | Traveler (G= available in Pansophy) | Part No | Qty
#1 | PUCSAP | P. Dhakal | Cavity Visual & CMM Inspection | SNSPPU-CAV-INSP-CAV | 104211800-M8U-8200-A001 | 30
#2 | PUHVPR | K. Wilson | Helium Vessel Shell Inspection | SNSPPU-INSP-HES | 104211700-M8U-8200-A020 | 28
#2 | PUHVPR | K. Wilson | Helium Vessel Probe End Inspection | SNSPPU-INSP-HEHDP | 104211700-M8U-8200-A025 | 28
#2 | PUHVPR | K. Wilson | Helium Vessel FPC End Inspection | SNSPPU-INSP-HEHDF | 104211700-M8U-8200-A023 | 28
#3 | PUMSPR | G. Cheng | Outer Magnetic Shield Visual Inspecton | SNSPPU-INSP-OMAG | 104211000-M8U-8200-A001 | 7
#3 | PUMSPR | G. Cheng | Inner Magnetic Shield Visual Inspecton | SNSPPU-INSP-IMAG | 104211200-M8U-8200-A001 | 7
#4 | PUCSAP | K. Wilson | Beamline Bellows Visual Inspection | SNSPPU-CST-INSP-BLBP | 104211500-M8U-8200-A029 | 21
#4 | PUCSAP | K. Wilson | Supply Warm to Cold Bellows Visual Inspection | SNSPPU-CST-INSP- | 104210300-M8U-8200-A103 | 14
#4 | PUCSAP | K. Wilson | Return Warm to Cold Bellows Visual Inspection | SNSPPU-CST-INSP | 104210300-M8U-8200-A205 | 14
#5 | PUTNPR | N. Huque | Tuner Assembly Visual & CMM Inspection | SNSPPU-CM-INSP-TUNC | 104211400-M8U-8200-A001 | ?
Note on F3: Original PN for SNS HB Cavity Top Assmebly CRM9007010-0002
Note on E5: Sampling Plan to be added to Traveler by KW 1 out of 5 sammpling If traveler does not get updated add email to any not inspected as "devaitation"
Note on E6: Sampling Plan to be added to Traveler by KW 1 out of 5 sammpling If traveler does not get updated add email to any not inspected as "devaitation"
Note on E7: Sampling Plan to be added to Traveler by KW 1 out of 5 sammpling If traveler does not get updated add email to any not inspected as "devaitation"
Note on D9: E. Anne McEwen: All spare and new magnetic shields need to be inspected to make sure we have 7 complete sets of inner, outer, supply extension and return extension shields, we should. But the spare magnetic shields are repaired by a vendor and there are new shields made by another vendor. So, it is complicated. I think two inspectors should team up to do the inspection because some shields can be large and heavy. Shields are crated. We don't want to drop the shields to the ground and permanently damage any of them. I estimate 3 days for two people to go through the shields and regroup them to make 7 complete sets. There will be excess shields to be packaged separately. Inspectors shall consult me before they start the inspection. I need to explain in more details about what they are expected to look for.
Note on D10: E. Anne McEwen: All spare and new magnetic shields need to be inspected to make sure we have 7 complete sets of inner, outer, supply extension and return extension shields, we should. But the spare magnetic shields are repaired by a vendor and there are new shields made by another vendor. So, it is complicated. I think two inspectors should team up to do the inspection because some shields can be large and heavy. Shields are crated. We don't want to drop the shields to the ground and permanently damage any of them. I estimate 3 days for two people to go through the shields and regroup them to make 7 complete sets. There will be excess shields to be packaged separately. Inspectors shall consult me before they start the inspection. I need to explain in more details about what they are expected to look for.
Note on E12: 16Oct2020, delivered to Pansophy for routing & approval
Note on E13: 16Oct2020, delivered to Pansophy for routing & approval
Note on E14: 16Oct2020, delivered to Pansophy for routing & approval

## Inventory Insp not needed
The following parts appear in PRIMeS indication "HOLD INSPECTION PENDING" , however are not normally inspected (no traveler or mechanical inspection)
For SNSPPU
-Ion pump support tooling
-Surge tank piping
-Corrugated hose assy
-Button cover plate A
-Button cover plate B
-Harmonic drive
-6 inch gate valve

## Cavity Serial Numbers
C75 Serial Numbers
JLAB | 5C75-J-004
JLAB | 5C75-J-005
RI | 5C75-RI-001
RI | 5C75-RI-002
RI | 5C75-RI-003
RI | 5C75-RI-004
RI | 5C75-RI-005
RI | 5C75-RI-006
RI | 5C75-RI-007
RI | 5C75-RI-008
RI | 5C75-RI-NBSN1
RI | 5C75-RI-009
RI | 5C75-RI-010
RI | 5C75-RI-011
RI | 5C75-RI-012
RI | 5C75-RI-013
RI | 5C75-RI-014
RI | 5C75-RI-015
RI | 5C75-RI-016
P1 Cavity Serial Numbers
EP-002
EP-003
JL-003
JL-004
JL-005
JL-006
JL-007
JL-008
JL-009
SNSPPU Cavities
RI | PPU-01
RI | PPU-02
RI | PPU-03
RI | PPU-04
RI | PPU-05
RI | PPU-06
RI | PPU-07
RI | PPU-08
RI | PPU-09
RI | PPU-10
RI | PPU-11
RI | PPU-12
RI | PPU-13
RI | PPU-14
RI | PPU-15
RI | PPU-16
RI | PPU-17
RI | PPU-18
RI | PPU-19
RI | PPU-20
RI | PPU-21
RI | PPU-22
RI | PPU-23
RI | PPU-24
RI | PPU-25
RI | PPU-26
RI | PPU-27
RI | PPU-28
RI | PPU-29
RI | PPU-30
RI | PPU-31
RI | PPU-32

## 2016Jun17 Brian's Schedule
Project/Component | Charge Code | Priority | Quanitity | Duration(Man-hrs) | Total Time(man-hrs) | Anticipated Delivery | Planned Start Date | Start | Finish
Green = Deliverd to Jlab
US-LARP DQW |  | 3
Cavity 01 Assembly |  | 3 | 1 | 24 | 24 | 2016-10-01
Cavity 01 Parts |  | 3 | 1 | 24 | 24 | 2016-10-01
Cavity 02 Assembly |  | 3 | 1 | 24 | 24 | 2016-10-01
Cavity 02 Parts |  | 3 | 1 | 24 | 24 | 2016-10-01
US-LARP RFD |  | 3
Cavity 01 Assembly |  | 3 | 1 | 24 | 24 | 2016-10-01
Cavity 01 Parts |  | 3 | 1 | 24 | 24 | 2016-05-09 |  | 2016-05-09 | 2016-05-13
Cavity 02 Assembly |  | 3 | 1 | 24 | 24 | 2016-10-01
Cavity 02 Parts |  | 3 | 1 | 24 | 24 | 2016-05-09 |  | 2016-05-09 | 2016-05-13
C75 Cavities |  | 1
Cavity 00 Post EBW |  | 1 | 1 | 1 | 1 |  |  | 2016-06-13 | 2016-06-13
Cavity 00 After Lap |  | 1 | 1 | 4 | 4 | 2016-06-15
Cavity 01 Post EBW |  | 1 | 1 | 1 | 1 | 2016-07-15
Cavity 01 After Lap |  | 1 | 1 | 4 | 4 | 2016-07-15
Cavity 02 Post EBW |  | 1 | 1 | 1 | 1 | 2016-07-15
Cavity 02 After Lap |  | 1 | 1 | 4 | 4 | 2016-07-15
Cavity 03 Post EBW |  | 1 | 1 | 1 | 1 | 2016-07-15
Cavity 03 After Lap |  | 1 | 1 | 4 | 4 | 2016-07-15
Cavity 01/02 Pair Prep |  | 1 | 13 | 80 | 1040 | 2016-12-15
QCM
Instrumentation flange |  | 1 | 1 | 8 | 8 |  | 2016-06-20
End Can Bridge |  | 1 | 2 | 4 | 8 |  | 2016-06-27
Cryomodule Stands |  | 1 | 1 | 4 | 4
Return EC rupture disk |  | 1 | 1 | 4 | 4
LCLS2 Prototype CMM |  |  |  |  | 0
8 Tuner(mech) Assemblies |  | 2 | 8 | 1 | 8 |  | 2016-07-01
CM Vacuum Vessel |  | 2 | 1 | 40 | 40 |  |  | 2016-06-08 | 2016-06-14
Cryomodule Stands |  | 2 | 2 | 4 | 8 | 2016-05-02
FPC Warm Parts |  | 2 | 8 | 40 | 320
JT Valves |  | 2 | 2 | 4 | 8
Shipping Frames |  | 2 | 1 | 8 | 8
Coupler pumping lines/vac equip. |  | 2 | 1 | 16 | 16 | 2016-05-02
LCLS2 Production CMM |  |  |  |  | 0
FPC Warm Parts |  | 2 | 17 | 5 | 85
2 phase bellows |  | 2 | 19 | 0.5 | 9.5
BPM feedthrus |  | 2 | 70 | 2 | 140
Cavities |  | 2 | 132 | 4 | 528
Cavities - Lot 1 |  | 2 | 4 | 6 | 24 | 2016-07-16
Cavities - Lot 2 |  | 2 | 4 | 6 | 24 | 2016-08-01
Cavities - Lot 3 |  | 2 | 4 | 6 | 24
Cavities - Lot 4 |  | 2 | 4 | 6 | 24
Cavities - Lot 5 |  | 2 | 4 | 6 | 24
Cavities - Lot 6 |  | 2 | 4 | 6 | 24
Cavities - Lot 7 |  | 2 | 4 | 6 | 24
Cavities - Lot 8 |  | 2 | 4 | 6 | 24
Cavities - Lot 9 |  | 2 | 4 | 6 | 24
Cavities - Lot 10 |  | 2 | 4 | 6 | 24
Cavities - Lot 11 |  | 2 | 4 | 6 | 24
Cavities - Lot 12 |  | 2 | 4 | 6 | 24
Cavities - Lot 13 |  | 2 | 4 | 6 | 24
Cavities - Lot 14 |  | 2 | 4 | 6 | 24
Cavities - Lot 15 |  | 2 | 4 | 6 | 24
Cavities - Lot 16 |  | 2 | 4 | 6 | 24
Cavities - Lot 17 |  | 2 | 4 | 6 | 24
Cavities - Lot 18 |  | 2 | 4 | 6 | 24
Cavities - Lot 19 |  | 2 | 4 | 6 | 24
Cavities - Lot 20 |  | 2 | 4 | 6 | 24
Cavities - Lot 21 |  | 2 | 4 | 6 | 24
Cavities - Lot 22 |  | 2 | 4 | 6 | 24
Cavities - Lot 23 |  | 2 | 4 | 6 | 24
Cavities - Lot 24 |  | 2 | 4 | 6 | 24
Cavities - Lot 25 |  | 2 | 4 | 6 | 24
Cavities - Lot 26 |  | 2 | 4 | 6 | 24
Cavities - Lot 27 |  | 2 | 4 | 6 | 24
Cavities - Lot 28 |  | 2 | 4 | 6 | 24
Cavities - Lot 29 |  | 2 | 4 | 6 | 24
Cavities - Lot 30 |  | 2 | 4 | 6 | 24
Cavities - Lot 31 |  | 2 | 4 | 6 | 24
Cavities - Lot 32 |  | 2 | 4 | 6 | 24
Cavities - Lot 33 |  | 2 | 4 | 6 | 24
Cold Mass 1 parts |  | 2 | 17 | 24 | 408
Cold mass II parts |  | 2 | 17 | 24 | 408
Field Probes |  | 2 | 302 | 2 | 604
HOM Probes |  | 2 | 460 | 2 | 920
JT Valves |  | 2 | 36 | 4 | 144
Saddles |  | 2 | 36 | 4 | 144
Shipping Frames |  | 2 | 17 | 8 | 136
Upper cold mass parts |  | 2 | 17 | 24 | 408
Vacuum Vessels 01 |  | 2 | 1 | 24 | 24 | 2016-07-13
Vacuum Vessels 02 |  | 2 | 1 | 24 | 24
Vacuum Vessels 03 |  | 2 | 1 | 24 | 24
Vacuum Vessels 04 |  | 2 | 1 | 24 | 24
Vacuum Vessels 05 |  | 2 | 1 | 24 | 24
Vacuum Vessels 06 |  | 2 | 1 | 24 | 24
Vacuum Vessels 07 |  | 2 | 1 | 24 | 24
Vacuum Vessels 08 |  | 2 | 1 | 24 | 24
Vacuum Vessels 09 |  | 2 | 1 | 24 | 24
Vacuum Vessels 10 |  | 2 | 1 | 24 | 24
Vacuum Vessels 11 |  | 2 | 1 | 24 | 24
Vacuum Vessels 12 |  | 2 | 1 | 24 | 24
Vacuum Vessels 13 |  | 2 | 1 | 24 | 24
Vacuum Vessels 14 |  | 2 | 1 | 24 | 24
Vacuum Vessels 15 |  | 2 | 1 | 24 | 24
Vacuum Vessels 16 |  | 2 | 1 | 24 | 24
Vacuum Vessels 17 |  | 2 | 1 | 24 | 24
Vacuum Vessels 18 |  | 2 | 1 | 24 | 24
Bellows - un-plated Lot 0 |  | 2 | 35 | 2 | 70 |  |  | 2016-05-16 | 2016-05-26
Bellows - Plated Lot 0 |  | 2 | 35 | 2 | 70 | 2016-06-01
Bellows - Plated Lot 1 |  | 2 | 8 | 2 | 16
Bellows - Plated Lot 2 |  | 2 | 8 | 2 | 16
Bellows - Plated Lot 3 |  | 2 | 8 | 2 | 16
Bellows - Plated Lot 4 |  | 2 | 8 | 2 | 16
Bellows - Plated Lot 5 |  | 2 | 8 | 2 | 16
Bellows - Plated Lot 6 |  | 2 | 8 | 2 | 16
Bellows - Plated Lot 7 |  | 2 | 8 | 2 | 16
Bellows - Plated Lot 8 |  | 2 | 8 | 2 | 16
Bellows - Plated Lot 9 |  | 2 | 8 | 2 | 16
Bellows - Plated Lot 10 |  | 2 | 8 | 2 | 16
Bellows - Plated Lot 11 |  | 2 | 8 | 2 | 16
Bellows - Plated Lot 12 |  | 2 | 8 | 2 | 16
Bellows - Plated Lot 13 |  | 2 | 8 | 2 | 16
Bellows - Plated Lot 14 |  | 2 | 8 | 2 | 16
Bellows - Plated Lot 15 |  | 2 | 8 | 2 | 16
Bellows - Plated Lot 16 |  | 2 | 8 | 2 | 16
Bellows - Plated Lot 17 |  | 2 | 8 | 2 | 16
Bellows - Plated Lot 18 |  | 2 | 8 | 2 | 16
Spools un-plated Lot 0 |  | 2 | 15 | 2 | 30 |  |  | 2016-04-21 | 2016-05-04
Spools - Plated Lot 0 |  | 2 | 15 | 2 | 30 | 2016-06-01
Spools - Plated Lot 1 |  | 2 | 2 | 2 | 4
Spools - Plated Lot 2 |  | 2 | 2 | 2 | 4
Spools - Plated Lot 3 |  | 2 | 2 | 2 | 4
Spools - Plated Lot 4 |  | 2 | 2 | 2 | 4
Spools - Plated Lot 5 |  | 2 | 2 | 2 | 4
Spools - Plated Lot 6 |  | 2 | 2 | 2 | 4
Spools - Plated Lot 7 |  | 2 | 2 | 2 | 4
Spools - Plated Lot 8 |  | 2 | 2 | 2 | 4
Spools - Plated Lot 9 |  | 2 | 2 | 2 | 4
Spools - Plated Lot 10 |  | 2 | 2 | 2 | 4
Spools - Plated Lot 11 |  | 2 | 2 | 2 | 4
Spools - Plated Lot 12 |  | 2 | 2 | 2 | 4
Spools - Plated Lot 13 |  | 2 | 2 | 2 | 4
Spools - Plated Lot 14 |  | 2 | 2 | 2 | 4
Spools - Plated Lot 15 |  | 2 | 2 | 2 | 4
Spools - Plated Lot 16 |  | 2 | 2 | 2 | 4
Spools - Plated Lot 17 |  | 2 | 2 | 2 | 4
Spools - Plated Lot 18 |  | 2 | 2 | 2 | 4
Tuners - Lot 1 |  | 2 | 8 | 2 | 16 | 2016-07-22
Tuners - Lot 2 |  | 2 | 8 | 2 | 16 | 2016-08-22
Tuners - Lot 3 |  | 2 | 8 | 2 | 16 | 2016-09-22
Tuners - Lot 4 |  | 2 | 8 | 2 | 16 | 2016-10-22
Tuners - Lot 5 |  | 2 | 8 | 2 | 16 | 2016-11-22
Tuners - Lot 6 |  | 2 | 8 | 2 | 16 | 2016-12-22
Tuners - Lot 7 |  | 2 | 8 | 2 | 16 | 2017-01-22
Tuners - Lot 8 |  | 2 | 8 | 2 | 16 | 2017-02-22
Tuners - Lot 9 |  | 2 | 8 | 2 | 16 | 2017-03-22
Tuners - Lot 10 |  | 2 | 8 | 2 | 16 | 2017-04-22
Tuners - Lot 11 |  | 2 | 8 | 2 | 16 | 2017-05-22
Tuners - Lot 12 |  | 2 | 8 | 2 | 16 | 2017-06-22
Tuners - Lot 13 |  | 2 | 8 | 2 | 16 | 2017-07-22
Tuners - Lot 14 |  | 2 | 8 | 2 | 16 | 2017-08-22
Tuners - Lot 15 |  | 2 | 8 | 2 | 16 | 2017-09-22
Tuners - Lot 16 |  | 2 | 8 | 2 | 16 | 2017-10-22
Tuners - Lot 17 |  | 2 | 8 | 2 | 16 | 2017-11-22
Tuners - Lot 18 |  | 2 | 8 | 2 | 16 | 2017-12-22
7690.5

## SNSPPU ChargeCodes 07Aug2020 (hidden)
Project | Project Name | Abbrv | Proj Manager Name | Allow Charges Fl | TC Project Flag | Prime Contract | Organization | Organization Abbrv | Project Start Date | Project End Date
000001.21.02.002.003 | Jefferson Lab Scope |  | DALY, EDWARD F | N | N |  | 1.DO.005.0001.01 | SNSPPU | 2018-08-24 |  | From: Ed Daly
000001.21.02.002.003.001 | Project Management |  | DALY, EDWARD F | N | N |  | 1.DO.005.0001.01 | SNSPPU | 2018-08-24 |  | Sent: Thursday, August 6, 2020 7:25 PM
000001.21.02.002.003.001.01 | Design Management | PUPMAN | DALY, EDWARD F | N | N | YN1901000ORNL4400000615 | 1.DO.005.0001.01 | SNSPPU | 2018-08-24 |  | To: E. Anne McEwen <mcewen@jlab.org>; John Fischer <fischer@jlab.org>; Kirk Davis <kdavis@jlab.org>; Philip Denny <denny@jlab.org>; Larry King <king@jlab.org>
000001.21.02.002.003.001.02 | Design Project Controls | PUPCON | DALY, EDWARD F | N | N | YN1901000ORNL4400000615 | 1.DO.005.0001.01 | SNSPPU | 2018-08-24 |  | Cc: Tony Reilly <areilly@jlab.org>; Lisa Loewus <lloewus@jlab.org>; Katherine Wilson <kwilson@jlab.org>; Mark Wiseman <wiseman@jlab.org>; Kurt Macha <macha@jlab.org>; James Henry <jhenry@jlab.org>
000001.21.02.002.003.001.03 | Design Procurement Suppor | PUPROC | DALY, EDWARD F | N | N | TBD | 1.DO.005.0001.01 | SNSPPU |  |  | Subject: Inspection Labor - Charge Codes
000001.21.02.002.003.001.04 | Design Integration and QA | PUPIQA | DALY, EDWARD F | N | N | YN1901000ORNL4400000615 | 1.DO.005.0001.01 | SNSPPU | 2018-11-01
000001.21.02.002.003.001.05 | Management | PUPMGT | DALY, EDWARD F | Y | T | YN1901000ORNL4400000615-003 | 1.DO.005.0001.01 | SNSPPU | 2019-10-01 |  | Dear All,
000001.21.02.002.003.001.06 | Project Controls | PUPCNT | DALY, EDWARD F | Y | T | YN1901000ORNL4400000615-003 | 1.DO.005.0001.01 | SNSPPU | 2019-10-01 |  | You can find the attached spreadsheet with the full list of charge codes for PPU. The updated list is found here as well - M:\SNS_PPU\PMO\Project Listings & Charge Codes
000001.21.02.002.003.001.07 | Procurement Support | PUPRCM | DALY, EDWARD F | Y | T | YN1901000ORNL4400000615-003 | 1.DO.005.0001.01 | SNSPPU | 2019-10-01
000001.21.02.002.003.001.08 | Integration and QA | PUINQA | DALY, EDWARD F | Y | T | YN1901000ORNL4400000615-003 | 1.DO.005.0001.01 | SNSPPU | 2019-10-01 |  | The cheat sheet is below -
000001.21.02.002.003.002 | Cavity & FPC Support |  | WILSON, KATHERINE M | N | N |  | 1.DO.005.0001.01 | SNSPPU | 2018-08-24
000001.21.02.002.003.002.01 | Cavity Design Support | PUCVDS | WISEMAN, MARK A | N | N | YN1901000ORNL4400000615 | 1.DO.005.0001.01 | SNSPPU | 2018-08-24 |  | Inspection (BLUE) - Charge codes for inspection are part of the procurement effort so they typically have "proc" in the project name.
000001.21.02.002.003.002.02 | Cavity Proc Support | PUCVPS | WILSON, KATHERINE M | N | N | YN1901000ORNL4400000615 | 1.DO.005.0001.01 | SNSPPU | 2018-08-24
000001.21.02.002.003.002.03 | FPC Design Support | PUFPDS | WISEMAN, MARK A | N | N | YN1901000ORNL4400000615 | 1.DO.005.0001.01 | SNSPPU | 2018-08-24 |  | Labor for Cavity Test, String and CM assembly (YELLOW)
000001.21.02.002.003.002.04 | FPC Proc Support | PUFPPS | WILSON, KATHERINE M | N | N | YN1901000ORNL4400000615 | 1.DO.005.0001.01 | SNSPPU | 2018-08-24
000001.21.02.002.003.003 | Helium Vessel |  | WILSON, KATHERINE M | N | N |  | 1.DO.005.0001.01 | SNSPPU | 2018-08-24 |  | Sustaining Engineering and Design (ORANGE) - used by Scientists, Engineers, Designers and Technicians when revising models, drawings, travelers, procedures and other work planning control documents based on feedback from production.
000001.21.02.002.003.003.01 | Helium Vessel Design | PUHEVD | WISEMAN, MARK A | N | N | YN1901000ORNL4400000615 | 1.DO.005.0001.01 | SNSPPU | 2018-08-24
000001.21.02.002.003.003.02 | Helium Vessel Proc-NA | PUHEVP | WILSON, KATHERINE M | N | N | YN1901000ORNL4400000615 | 1.DO.005.0001.01 | SNSPPU | 2019-03-07
000001.21.02.002.003.003.03 | Helium Vessel Proc | PUHVPR | WILSON, KATHERINE M | Y | T | YN1901000ORNL4400000615-002 | 1.DO.005.0001.01 | SNSPPU | 2019-10-01
000001.21.02.002.003.004 | Tuner |  | WILSON, KATHERINE M | N | N |  | 1.DO.005.0001.01 | SNSPPU | 2018-08-24
000001.21.02.002.003.004.01 | Tuner Design | PUTUND | WISEMAN, MARK A | N | N | YN1901000ORNL4400000615 | 1.DO.005.0001.01 | SNSPPU | 2018-08-24
000001.21.02.002.003.004.02 | Tuner Procurement-NA | PUTUNP | WILSON, KATHERINE M | N | N | YN1901000ORNL4400000615 | 1.DO.005.0001.01 | SNSPPU | 2019-08-16
000001.21.02.002.003.004.03 | Tuner Procurement | PUTNPR | WILSON, KATHERINE M | Y | T | YN1901000ORNL4400000615-002 | 1.DO.005.0001.01 | SNSPPU | 2019-10-01
000001.21.02.002.003.005 | Thermal Shield & MLI |  | WILSON, KATHERINE M | N | N |  | 1.DO.005.0001.01 | SNSPPU | 2018-08-24
000001.21.02.002.003.005.01 | Therm Shield & MLI Design | PUTSMD | WISEMAN, MARK A | N | N | YN1901000ORNL4400000615 | 1.DO.005.0001.01 | SNSPPU | 2018-08-24
000001.21.02.002.003.005.02 | Therm Shield & MLI Proc | PUTSMP | WILSON, KATHERINE M | Y | T | YN1901000ORNL4400000615-002 | 1.DO.005.0001.01 | SNSPPU | 2019-10-01
000001.21.02.002.003.006 | Spaceframe |  | WILSON, KATHERINE M | N | N |  | 1.DO.005.0001.01 | SNSPPU | 2018-08-24
000001.21.02.002.003.006.01 | Spaceframe Design | PUSPFD | WISEMAN, MARK A | N | N | YN1901000ORNL4400000615 | 1.DO.005.0001.01 | SNSPPU | 2018-08-24
000001.21.02.002.003.006.02 | Spaceframe Proc | PUSPFP | WILSON, KATHERINE M | Y | T | YN1901000ORNL4400000615-002 | 1.DO.005.0001.01 | SNSPPU | 2019-10-01
000001.21.02.002.003.007 | Vacuum Vessel |  | WILSON, KATHERINE M | N | N |  | 1.DO.005.0001.01 | SNSPPU | 2018-08-24
000001.21.02.002.003.007.01 | Vacuum Vessel Design | PUVVLD | WISEMAN, MARK A | N | N | YN1901000ORNL4400000615 | 1.DO.005.0001.01 | SNSPPU | 2018-08-24
000001.21.02.002.003.007.02 | Vacuum Vessel Proc | PUVVLP | WILSON, KATHERINE M | Y | T | YN1901000ORNL4400000615-002 | 1.DO.005.0001.01 | SNSPPU | 2019-10-01
000001.21.02.002.003.008 | Supply End Can |  | WILSON, KATHERINE M | N | N |  | 1.DO.005.0001.01 | SNSPPU | 2018-08-24
000001.21.02.002.003.008.01 | Supply End Can Design | PUSECD | WISEMAN, MARK A | N | N | YN1901000ORNL4400000615 | 1.DO.005.0001.01 | SNSPPU | 2018-08-24
000001.21.02.002.003.008.02 | Supply End Can Proc | PUSECP | WILSON, KATHERINE M | Y | T | YN1901000ORNL4400000615-002 | 1.DO.005.0001.01 | SNSPPU | 2019-10-01
000001.21.02.002.003.009 | Return End Can |  | WILSON, KATHERINE M | N | N |  | 1.DO.005.0001.01 | SNSPPU | 2018-08-24
000001.21.02.002.003.009.01 | Return End Can Design | PURECD | WISEMAN, MARK A | N | N | YN1901000ORNL4400000615 | 1.DO.005.0001.01 | SNSPPU | 2018-08-24
000001.21.02.002.003.009.02 | Return End Can Proc - NA | PURECP | WILSON, KATHERINE M | N | N | YN1901000ORNL4400000615 | 1.DO.005.0001.01 | SNSPPU | 2019-03-07
000001.21.02.002.003.009.03 | Return End Can Proc | PUREPR | WILSON, KATHERINE M | Y | T | YN1901000ORNL4400000615-002 | 1.DO.005.0001.01 | SNSPPU | 2019-10-01
000001.21.02.002.003.010 | Instrumentation |  | WILSON, KATHERINE M | N | N |  | 1.DO.005.0001.01 | SNSPPU | 2018-08-24
000001.21.02.002.003.010.01 | Instrumentation Design | PUINSD | WISEMAN, MARK A | N | N | YN1901000ORNL4400000615 | 1.DO.005.0001.01 | SNSPPU | 2018-08-24
000001.21.02.002.003.010.02 | Instrumentation Proc | PUINSP | WILSON, KATHERINE M | Y | T | YN1901000ORNL4400000615-002 | 1.DO.005.0001.01 | SNSPPU | 2019-10-01
000001.21.02.002.003.011 | Tooling |  | WILSON, KATHERINE M | N | N |  | 1.DO.005.0001.01 | SNSPPU | 2018-08-24
000001.21.02.002.003.011.01 | Tooling Design | PUTOLD | WISEMAN, MARK A | N | N | YN1901000ORNL4400000615 | 1.DO.005.0001.01 | SNSPPU | 2018-08-24
000001.21.02.002.003.011.02 | Tooling Proc | PUTOLP | WILSON, KATHERINE M | Y | T | YN1901000ORNL4400000615-002 | 1.DO.005.0001.01 | SNSPPU | 2019-10-01
000001.21.02.002.003.012 | Stands |  | WILSON, KATHERINE M | N | N |  | 1.DO.005.0001.01 | SNSPPU | 2018-08-24
000001.21.02.002.003.012.01 | Stands Design | PUSTND | WISEMAN, MARK A | N | T | YN1901000ORNL4400000615 | 1.DO.005.0001.01 | SNSPPU | 2018-08-24
000001.21.02.002.003.012.02 | Stands Proc | PUSTNP | WILSON, KATHERINE M | N | N | TBD | 1.DO.005.0001.01 | SNSPPU
000001.21.02.002.003.013 | Magnetic Shielding |  | WILSON, KATHERINE M | N | N |  | 1.DO.005.0001.01 | SNSPPU | 2018-09-17
000001.21.02.002.003.013.01 | Magnetic Shielding Design | PUMASD | WISEMAN, MARK A | N | N | YN1901000ORNL4400000615 | 1.DO.005.0001.01 | SNSPPU | 2018-09-17
000001.21.02.002.003.013.02 | Magnetic ShieldingProc-NA | PUMASP | WILSON, KATHERINE M | N | N | YN1901000ORNL4400000615 | 1.DO.005.0001.01 | SNSPPU | 2019-08-16
000001.21.02.002.003.013.03 | Magnetic Shielding Proc | PUMSPR | WILSON, KATHERINE M | Y | T | YN1901000ORNL4400000615-002 | 1.DO.005.0001.01 | SNSPPU | 2019-10-01
000001.21.02.002.003.014 | Cavity Prep & Test |  | WILSON, KATHERINE M | N | N |  | 1.DO.005.0001.01 | SNSPPU | 2018-09-17
000001.21.02.002.003.014.01 | Cavity Prep & Test Design | PUCPTD | WISEMAN, MARK A | N | N | YN1901000ORNL4400000615 | 1.DO.005.0001.01 | SNSPPU | 2018-09-17
000001.21.02.002.003.014.02 | Cavity Prep & Test Proc | PUCPTP | WILSON, KATHERINE M | N | N | YN1901000ORNL4400000615-002 | 1.DO.005.0001.01 | SNSPPU | 2019-10-01
000001.21.02.002.003.014.03 | Cavity Prep & Testing | PUCPAT | WILSON, KATHERINE M | Y | T | YN1901000ORNL4400000615-003 | 1.DO.005.0001.01 | SNSPPU | 2019-11-25
000001.21.02.002.003.015 | Cleanroom String Assembly |  | WILSON, KATHERINE M | N | N |  | 1.DO.005.0001.01 | SNSPPU | 2018-09-17
000001.21.02.002.003.015.01 | Cleanroom String Ass Des | PUCSAD | WISEMAN, MARK A | N | N | YN1901000ORNL4400000615 | 1.DO.005.0001.01 | SNSPPU | 2018-09-17
000001.21.02.002.003.015.02 | Cleanroom String Ass Proc | PUCSAP | WILSON, KATHERINE M | Y | T | YN1901000ORNL4400000615-002 | 1.DO.005.0001.01 | SNSPPU | 2019-10-01
000001.21.02.002.003.015.03 | Cleanroom String Assembly | PUCSAS | WILSON, KATHERINE M | Y | T | YN1901000ORNL4400000615-003 | 1.DO.005.0001.01 | SNSPPU | 2020-08-03
000001.21.02.002.003.016 | Cold Mass Assembly |  | WILSON, KATHERINE M | N | N |  | 1.DO.005.0001.01 | SNSPPU | 2018-09-17
000001.21.02.002.003.016.01 | Cold Mass Assembly Design | PUCMD | WISEMAN, MARK A | N | N | YN1901000ORNL4400000615 | 1.DO.005.0001.01 | SNSPPU | 2018-09-17
000001.21.02.002.003.016.02 | Cold Mass Assembly Proc | PUCMP | WILSON, KATHERINE M | Y | T | YN1901000ORNL4400000615-002 | 1.DO.005.0001.01 | SNSPPU | 2019-10-01
000001.21.02.002.003.016.03 | Cold Mass Assembly | PUCMA | WILSON, KATHERINE M | Y | T | YN1901000ORNL4400000615-003 | 1.DO.005.0001.01 | SNSPPU | 2020-08-03
000001.21.02.002.003.017 | Spacefrm Therm Shield Ass |  | WILSON, KATHERINE M | N | N |  | 1.DO.005.0001.01 | SNSPPU | 2018-09-17
000001.21.02.002.003.017.01 | Spacefrm Therm Shield Des | PUSTSD | WISEMAN, MARK A | N | N | YN1901000ORNL4400000615 | 1.DO.005.0001.01 | SNSPPU | 2018-09-17
000001.21.02.002.003.017.02 | Spacefrm Therm ShieldProc | PUSTSP | WILSON, KATHERINE M | N | N | YN1901000ORNL4400000615-002 | 1.DO.005.0001.01 | SNSPPU | 2019-10-01
000001.21.02.002.003.017.03 | Spacefrm Therm Shield Ass | PUSTSA | WILSON, KATHERINE M | Y | T | YN1901000ORNL4400000615-003 | 1.DO.005.0001.01 | SNSPPU | 2020-05-06
000001.21.02.002.003.018 | Final Cryomodule Assembly |  | WILSON, KATHERINE M | N | N |  | 1.DO.005.0001.01 | SNSPPU | 2018-09-17
000001.21.02.002.003.018.01 | Final CM Assembly Design | PUFCAD | WISEMAN, MARK A | N | N | YN1901000ORNL4400000615 | 1.DO.005.0001.01 | SNSPPU | 2018-09-17
000001.21.02.002.003.018.02 | Final CM Assembly Proc | PUFCAP | WILSON, KATHERINE M | Y | T | YN1901000ORNL4400000615-002 | 1.DO.005.0001.01 | SNSPPU | 2019-10-01
000001.21.02.002.003.018.03 | Final CM Assembly | PUFCMA | WILSON, KATHERINE M | Y | T | YN1901000ORNL4400000615-003 | 1.DO.005.0001.01 | SNSPPU | 2020-08-03
000001.21.02.002.003.019 | Shipping |  | WILSON, KATHERINE M | N | N |  | 1.DO.005.0001.01 | SNSPPU | 2018-09-17
000001.21.02.002.003.019.01 | Shipping Design | PUSHPD | WISEMAN, MARK A | N | N | YN1901000ORNL4400000615 | 1.DO.005.0001.01 | SNSPPU | 2018-09-17
000001.21.02.002.003.019.02 | Prepare CM for Shipment | PUPCMS | WILSON, KATHERINE M | Y | T | YN1901000ORNL4400000615-003 | 1.DO.005.0001.01 | SNSPPU | 2020-02-11
000001.21.02.002.003.019.03 | Ship CM | PUSHCM | REILLY, ANTHONY V | N | N | TBD | 1.DO.005.0001.01 | SNSPPU

## SNSPPU P6 Insp. Sch 06Aug2020 (hidden)
NOTE: - only ~ half of these "Inspections" are for CMM
WBS Path | Activity ID | Activity Name | Start | Forecast Finish July Month End | BL Project Finish | Forecast Finish June Month End | Total Float | Physical % Complete
1.02.03.05.02 | 102030502220 | Inspect MLI First Article | 2020-08-03 | 2020-08-03 | 2020-07-22 | 2020-07-21 | 153 | 0%
1.02.03.14.03 | 102031403000 | Perform Mechanical Inspection of CM-01 Cavity #1 | 2020-08-11 | 2020-08-13 | 2020-08-13 | 2020-08-13 | 0 | 0%
1.02.03.18.02 | 102031802195 | Inspect Surge Tank | 2020-08-10 | 2020-08-14 | 2020-01-15 | 2020-08-07 | 194 | 0% | Traveler ??
1.02.03.19.02 | 102031902195 | Inspect Dummy Cryomodule | 2020-08-17 | 2020-08-17 | 2020-08-12 | 2020-11-05 | 160 | 0% | Traveler ??
1.02.03.14.03 | 102031403000A10 | Perform Mechanical Inspection of CM-01 Cavity #2 | 2020-08-14 | 2020-08-18 | 2020-08-18 | 2020-08-18 | 7 | 0%
1.02.03.03.02 | 102030302070 | Inspect Helium Vessels Lot #1 | 2020-08-17 | 2020-08-21 | 2020-05-28 | 2020-08-21 | 4 | 0%
1.02.03.14.03 | 102031403000A20 | Perform Mechanical Inspection of CM-01 Cavity #3 | 2020-08-19 | 2020-08-21 | 2020-08-21 | 2020-08-21 | 14 | 0%
1.02.03.03.02 | 1020303020721 | Inspect Helium Vessels Lot #2 | 2020-08-18 | 2020-08-24 | 2020-06-19 | 2020-07-21 | 92 | 0%
1.02.03.13.02 | 1020313020225 | Inspect Magnetic Shielding Existing Parts and Modification | 2020-08-11 | 2020-08-24 | 2020-02-13 | 2020-09-21 | 138 | 0%
1.02.03.14.03 | 102031403000A30 | Perform Mechanical Inspection of CM-01 Cavity #4 | 2020-08-24 | 2020-08-26 | 2020-08-26 | 2020-08-26 | 21 | 0%
1.02.03.16.02 | 102031602170 | Inspect Cold Mass Assembly Machined Parts | 2020-08-21 | 2020-08-27 | 2020-07-23 | 2020-08-27 | 85 | 0% | Traveler ??
1.02.03.11.02 | 102031102040 | Inspect Modified Misc.Clean Room Tooling | 2020-08-31 | 2020-08-31 | 2020-06-03 | 2020-09-25 | 43 | 0% | Traveler ??
1.02.03.03.02 | 102030302074925 | Inspect Helium Vessels Lot #4 | 2020-08-26 | 2020-09-01 | 2020-09-08 | 2020-09-01 | 199 | 0%
1.02.03.18.02 | 102031802440 | Inspect Coupler Return Piping | 2020-09-10 | 2020-09-16 | 2020-07-20 | 2020-07-29 | 172 | 0% | Traveler ??
1.02.03.18.02 | 102031802315 | Inspect Tophats | 2020-08-03 | 2020-09-17 | 2020-04-09 | 2020-09-17 | 171 | 0%
1.02.03.03.02 | 1020303020724 | Inspect Helium Vessels Lot #3 | 2020-09-15 | 2020-09-21 | 2020-07-20 | 2020-08-18 | 111 | 0% | Traveler ??
1.02.03.11.02 | 102031102215 | Inspect Warm to Cold Beam Tube Support | 2020-08-03 | 2020-09-30 | 2020-05-15 | 2020-09-15 | 22 | 0% | Traveler ??
1.02.03.11.02 | 102031102260 | Inspect CR Pump Drop Support | 2020-08-03 | 2020-09-30 | 2020-05-12 | 2020-09-15 | 22 | 0% | Traveler ??
1.02.03.11.02 | 102031102350 | Inspect FPC Installation tooling | 2020-08-03 | 2020-09-30 | 2020-06-15 | 2020-09-15 | 22 | 0% | Traveler ??
1.02.03.11.02 | 102031102395 | Inspect CR Bellows installation and support tooling | 2020-08-03 | 2020-09-30 | 2020-06-09 | 2020-09-15 | 22 | 0% | Traveler ??
1.02.03.15.02 | 102031502190 | Inspect Supply and Return Warm to Cold Beamline Weldments | 2020-09-02 | 2020-09-30 | 2020-05-28 | 2020-09-30 | 20 | 0% | Traveler ??
1.02.03.15.02 | 102031502255 | Inspect Warm to Cold Beamline Bellows Restraints | 01-Apr-20 A | 2020-09-30 | 2020-05-29 | 2020-07-31 | 22 | 10% | Traveler ??
1.02.03.16.02 | 102031602060 | Inspect Helium Outlet and CON Bellows and Corrugated Hose Assemblies | 2020-08-03 | 2020-09-30 | 2020-05-14 | 2020-08-05 | 62 | 0%
1.02.03.03.02 | 102030302074940 | Inspect Helium Vessels Lot #5 | 2020-09-25 | 2020-10-01 | 2020-10-07 | 2020-10-01 | 218 | 0%
1.02.03.17.03 | 102031703125 | Vendor Effort for Inspecting the Thermal Shield Assemblies | 2020-08-07 | 2020-10-01 | 2020-10-01 |  | 109 | 0%
1.02.03.05.02 | 102030502150 | Inspect Thermal Shields | 2020-08-03 | 2020-10-02 | 2020-07-28 | 2020-10-02 | 110 | 0%
1.02.03.05.02 | 102030502170 | Inspect Additional 50K Support Assemblies | 2020-08-03 | 2020-10-02 | 2020-07-28 | 2020-07-28 | 110 | 0%
1.02.03.15.02 | 102031502125 | Inspect Gate valves VAT 482XX | 2020-08-03 | 2020-10-07 | 2020-02-24 | 2020-10-07 | 297 | 0%
1.02.03.18.02 | 102031802495 | Inspect Supply Warm Beamtube Assembly | 2020-10-02 | 2020-10-08 | 2020-08-10 | 2020-08-20 | 155 | 0%
1.02.03.18.02 | 102031802525 | Inspect Return Warm Beamtube Assembly | 2020-10-02 | 2020-10-08 | 2020-08-10 | 2020-08-20 | 155 | 0%
1.02.03.07.02 | 102030702070 | Inspect Vacuum Vessel #1 | 2020-10-01 | 2020-10-09 | 2020-10-12 | 2020-10-12 | 154 | 0%
1.02.03.03.02 | 102030302074955 | Inspect Helium Vessels Lot #6 | 2020-10-07 | 2020-10-13 | 2020-10-19 | 2020-10-13 | 250 | 0%
1.02.03.15.02 | 102031502060 | Inspect Beamline Bellows | 2020-09-17 | 2020-10-16 | 2020-03-11 | 2020-08-31 | 10 | 0%
1.02.03.11.02 | 102031102085 | Inspect End Can Support | 2020-08-03 | 2020-10-30 | 2020-07-24 | 2020-09-01 | 140 | 0%
1.02.03.11.02 | 102031102130 | Inspect Misc. Tooling Required for Cryomodule builds | 2020-08-04 | 2020-10-30 | 2020-07-23 | 2020-07-06 | 140 | 0%
1.02.03.14.03 | 102031403025 | Perform Mechanical Inspection of CM-02 Cavities | 2020-10-19 | 2020-10-30 | 2020-10-30 | 2020-10-30 | 44 | 0%
1.02.03.10.02 | 102031002115 | Inspect Feed Thru Flange Weldment | 2020-08-03 | 2020-11-02 | 2020-05-29 | 2020-08-03 | 139 | 0%
1.02.03.13.02 | 102031302060 | Inspect Magnetic Shielding | 2020-08-12 | 2020-11-02 | 2020-06-17 | 2020-08-07 | 39 | 0%
1.02.03.04.02 | 102030402070 | Inspect Tuner Motors | 2020-08-03 | 2020-11-03 | 2020-05-18 | 2020-07-17 | 38 | 0%
1.02.03.04.02 | 102030402270 | Inspect Tuner Harmonic Drives | 2020-08-26 | 2020-11-03 | 2020-06-15 | 2020-08-17 | 38 | 0%
1.02.03.04.02 | 102030402351 | Inspect Tuner Frames Lot #1 | 2020-08-03 | 2020-11-03 | 2020-03-23 | 2020-08-03 | 38 | 0%
1.02.03.15.02 | 102031502425 | Inspect SoftShut Valves (Line 1 - 5 valves) | 2020-10-29 | 2020-11-04 | 2020-10-07 | 2020-11-04 | 136 | 0%
1.02.03.07.02 | 102030702085 | Inspect Vacuum Vessel #2 | 2020-11-02 | 2020-11-10 | 2020-11-11 | 2020-11-11 | 192 | 0%
1.02.03.06.02 | 102030602070 | Inspect Spaceframe | 2020-09-14 | 2020-11-13 | 2020-08-20 | 2020-08-03 | 80 | 0%
1.02.03.16.02 | 102031602140 | Inspect Large FPC/Tophat Bellows | 2020-08-07 | 2020-11-13 | 2020-06-03 | 2020-08-05 | 30 | 0%
1.02.03.14.03 | 102031403050 | Perform Mechanical Inspection of CM-03 Cavities | 2020-11-09 | 2020-11-20 | 2020-11-20 | 2020-11-20 | 68 | 0%
1.02.03.18.02 | 102031802235 | Inspect Flange NW250 + feedthrough flange weld | 2020-11-17 | 2020-11-23 | 2020-01-15 | 2020-11-23 | 123 | 0%
1.02.03.18.02 | 102031802130 | Inspect Flange Blank Assy. | 2020-11-18 | 2020-12-03 | 2020-03-05 | 2020-10-30 | 118 | 0%
1.02.03.07.02 | 102030702100 | Inspect Vacuum Vessel #3 | 2020-12-01 | 2020-12-09 | 2020-12-10 | 2020-12-10 | 213 | 0%
1.02.03.15.02 | 102031502429 | Inspect SoftShut Valves (Line 2 - 8 valves) | 2020-12-03 | 2020-12-09 | 2020-11-09 | 2020-12-09 | 213 | 0%
1.02.03.18.02 | 102031802060 | Inspect Gate valve MDC 303006-133 | 2020-11-24 | 2020-12-09 | 2020-05-14 | 2020-11-05 | 114 | 0%
1.02.03.14.03 | 102031403075 | Perform Mechanical Inspection of CM-04 Cavities | 2020-11-30 | 2020-12-11 | 2020-12-11 | 2020-12-11 | 91 | 0%
1.02.03.05.02 | 102030502235 | Inspect MLI Remainder of MLI | 2020-12-14 | 2020-12-18 | 2020-12-21 | 2020-12-18 | 126 | 0%
1.02.03.18.02 | 102031802275 | Inspect Pressure Relief Plates and Rupture Disks | 2020-08-03 | 2020-12-23 | 2020-02-24 | 2020-07-08 | 104 | 0%
1.02.03.04.02 | 102030402362 | Inspect Tuner Frames Lot #2 | 2020-08-03 | 2021-01-05 | 2020-05-13 | 2020-08-03 | 197 | 0%
1.02.03.04.02 | 102030402370 | Inspect Tuner Frames Lot #3 | 2020-08-03 | 2021-01-05 | 2020-07-09 | 2020-08-03 | 162 | 0%
1.02.03.04.02 | 102030402390 | Inspect Tuner Frames Lot #4 | 2020-08-03 | 2021-01-05 | 2020-08-18 | 2020-08-03 | 202 | 0%
1.02.03.14.03 | 102031403100 | Perform Mechanical Inspection of CM-05 Cavities | 2020-12-14 | 2021-01-05 | 2021-01-05 | 2021-01-05 | 120 | 0%
1.02.03.07.02 | 102030702115 | Inspect Vacuum Vessel #4 | 2021-01-04 | 2021-01-12 | 2021-01-13 | 2021-01-13 | 231 | 0%
1.02.03.14.03 | 102031403125 | Perform Mechanical Inspection of CM-06 Cavities | 2021-01-06 | 2021-01-20 | 2021-01-20 | 2021-01-20 | 150 | 0%
1.02.03.08.02 | 102030802070 | Inspect Supply End Cans | 2020-11-24 | 2021-01-22 | 2021-01-22 | 2021-01-22 | 90 | 0%
1.02.03.09.02 | 102030902070 | Inspect Return End Cans | 2020-11-24 | 2021-01-26 | 2021-01-25 | 2021-01-25 | 88 | 0%
1.02.03.14.03 | 102031403150 | Perform Mechanical Inspection of CM-07 Cavities | 2021-01-21 | 2021-02-03 | 2021-02-03 | 2021-02-03 | 180 | 0%
1.02.03.07.02 | 102030702130 | Inspect Vacuum Vessel #5 | 2021-02-04 | 2021-02-12 | 2021-02-15 | 2021-02-15 | 249 | 0%
1.02.03.10.02 | 102031002085 | Inspect Vaccuum Feedthroughs Instrumentation | 2020-08-03 | 2021-03-01 | 2020-03-25 | 2020-10-02 | 64 | 0%
1.02.03.07.02 | 102030702145 | Inspect Vacuum Vessel #6 | 2021-03-03 | 2021-03-11 | 2021-03-12 | 2021-03-12 | 270 | 0%
1.02.03.07.02 | 102030702160 | Inspect Vacuum Vessel #7 | 2021-03-26 | 2021-04-05 | 2021-04-06 | 2021-04-06 | 293 | 0%

## P1 Schedule 13Aug2020 (hidden)
From: Tony Reilly <areilly@jlab.org>
Sent: Thursday, August 13, 2020 12:02 PM
To: John Fischer <fischer@jlab.org>; Ed Daly <edaly@jlab.org>; Michael Drury <drury@jlab.org>; Kirk Davis <kdavis@jlab.org>; E. Anne McEwen <mcewen@jlab.org>; Michael Drury <drury@jlab.org>; Kurt Macha <macha@jlab.org>; Tiffany Ganey <ganey@jlab.org>; Valerie Bookwalter <bookwalt@jlab.org>; Scott Williams <scott@jlab.org>; Danny Forehand <forehand@jlab.org>; Liang Zhao <lzhao@jlab.org>; Ashley Anderson Mitchell <ashleya@jlab.org>; James Henry <jhenry@jlab.org>; George DeKerlegand <georged@jlab.org>
Subject: Draft high level schedule for P1
All,
Below is the draft schedule for P1. It's a tight schedule, not much room for delays. The schedule already reflects a late delivery to CEBAF.
Thanks,
Tony
Task Name | Duration | Start | Finish
P1 Refurbishment | 251 days | Thu 5/7/20 | Fri 5/7/21
Disassembly | 50 days | Thu 5/7/20 | Wed 7/15/20
Crymodule Disassembly Completed | 0 days | Wed 7/15/20 | Wed 7/15/20
Cavity Prep and Test | 70 days | Thu 7/16/20 | Thu 10/22/20
Cavity Prep and Test Completed | 0 days | Thu 10/22/20 | Thu 10/22/20
String Assembly | 15 days | Fri 10/23/20 | Thu 11/12/20
String Assembly Completed | 0 days | Thu 11/12/20 | Thu 11/12/20
Space Frame Assembly | 45 days | Fri 11/13/20 | Thu 1/28/21
Space Frame Assembly Completed | 0 days | Thu 1/28/21 | Thu 1/28/21
Cryomodule Assembly | 45 days | Fri 1/29/21 | Thu 4/1/21
Cryomodule Assembly Completed | 0 days | Thu 4/1/21 | Thu 4/1/21
Cryomodule Test | 20 days | Mon 4/12/21 | Fri 5/7/21
Cryomodule Test Completed | 0 days | Fri 5/7/21 | Fri 5/7/21
Install and Commission P1 | 15 days | Mon 5/10/21 | Mon 5/31/21
P1 Turn Over to Accel Ops | 0 days | Mon 5/31/21 | Mon 5/31/21

## P1 Inventory Fischer Aug2020
P1 Cavity Serial Numbers |  | P1 Waveguide Conversion to F100 Style
JL-005 |  | Parts Inventory, Location, and Inspection notes
JL-007
JL-006
JL-003
EP-002
JL-004
JL-009
JL-008
EP-003
Part | SN's |  | Location |  | Inspection Status/Notes | Primes Disposition | NCR Link
CRM1007070-0000 Cold Waveguide (2)
I chose an arbitrary batch, more in the | F034887/14 |  | INV Area |  |  | Hold-Inspection Pending
Inventory area. See attached Primes | F034887/11 |  | INV Area |  |  | Hold-Inspection Pending
sheet | F034887/18 |  | INV Area |  |  | Hold-Inspection Pending
| F034887/06 |  | INV Area |  |  | Hold-Inspection Pending
| F034887/02 |  | INV Area |  |  | Hold-Inspection Pending
| F034887/19 |  | INV Area |  |  | Hold-Inspection Pending
| F034887/08 |  | INV Area |  |  | Hold-Inspection Pending
Total 7
CRM1207070-0000 Cold Waveguide (6)
11 Others in Inventory area-Rejected tag | F063952/02 |  | CG Rad Cabinet -TLA | RAM Tag-6171 | Cavity end flange machined, small step left | No Info- NCR 18/325 D3-18
for various reasons | F067764/05 |  | CG Rad Cabinet -TLA | RAM Tag-6169 | Cavity end flange machined, small step left | No Info- NCR 323 D3-7/9
| F061584/04 |  | CG Rad Cabinet -TLA | RAM Tag-6170 | Cavity end flange machined, small step left | No Info- NCR-137 D3-6/11
| F067764/15 |  | CG Rad Cabinet -TLA | RAM Tag-6234 | Cavity end flange machined, small step left | No Info- NCR 322 D3-3/8
| F061359/10 |  | CG Rad Cabinet -TLA | RAM Tag-6235 | Cavity end flange machined, small step left | No Info- NCR 218 D3- 5/10/19
| F356223/05 |  | INV Area |  |  | Hold-Inspection Pending- NCR 340/1014
| G103046/04 |  | INV Area |  |  | Use As Is
| F890195/03 |  | INV Area |  |  | Use As Is- NCR 1002 D3-13/15/20/21
| G103046/07 |  | INV Area |  | Yellow Tag- Scratches small flange | Hold- NCR 46/67
| G103046/01 |  | INV Area |  | Yellow Tag- Scratches small flange | Hold- NCR 41/71
| G096314/01 |  | INV Area |  | Yellow Tag- Need RF Testing/Cu plating | Modify- NCR 62
| G096314/12 |  | INV Area |  | Yellow Tag- Need RF Testing/Cu plating | Hold- NCR 45/65
Total 12
CRM1207075-0035 C100 RF Windows (14)
6 Empty window flanges in Inventory area | Assem 0035-202 |  | INV Area |  | F100 traveler -passed RF tests and "OK to use" | Use As Is
| Assem 0035-181 |  | INV Area |  | Flunked RF test for high max temp (200+ C) and large gradient across ceramic (10 - 15C)
| Assem 0035-191 |  | INV Area |  | F100 traveler -incomplete traveler - no RF test or notes on disposition | Hold-Inspection Pending
| Assem 0035-224 |  | INV Area |  | F100 traveler -incomplete traveler - no RF test or notes on disposition | Hold-Inspection Pending
| Assem 0035-192 |  | INV Area |  | F100 traveler -incomplete traveler - no RF test or notes on disposition | Hold-Inspection Pending
| Assem 0035-223 |  | INV Area |  | F100 traveler -incomplete traveler - no RF test or notes on disposition | Hold-Inspection Pending
| Assem 0035-095 |  | INV Area |  | Traveler states "undetermined failure at 400C- multiple cracks "
| Assem 0035-020 |  | INV Area |  | R100 traveler states "frame failed DIM INSP". No RF test
| Assem 0035-222 |  | INV Area |  | F100 traveler -incomplete traveler - no RF test or notes on disposition | Hold-Inspection Pending
| Assem 0035-221 |  | INV Area |  | F100 traveler -incomplete traveler - no RF test or notes on disposition | Hold-Inspection Pending
| Assem 0035-022 |  | INV Area |  | F100 traveler -incomplete traveler - no RF test or notes on disposition | Hold-Inspection Pending
| Assem 0035-220 |  | INV Area |  | F100 traveler -incomplete traveler - no RF test or notes on disposition | Hold-Inspection Pending
| Assem 0035-219 |  | INV Area |  | F100 traveler -incomplete traveler - no RF test or notes on disposition | Hold-Inspection Pending
Total 13
115800-1033 RF Windows (2)
| Rev- 1003 |  | INV Area |  | Need to verify Rev change and dim. | No Record INV Area
| Rev- 1009 |  | INV Area |  | Need to verify Rev change and dim. | No Record INV Area
| Rev- 1005 |  | INV Area |  | Need to verify Rev change and dim. | No Record INV Area
| Rev- 1002 |  | INV Area |  | Need to verify Rev change and dim. | No Record INV Area
| Rev- 1007 |  | INV Area |  | Need to verify Rev change and dim. | No Record INV Area
| Rev A 1013 |  | INV Area |  | Need to verify Rev change and dim. | No Record INV Area
| Rev A 1011 |  | INV Area |  | Need to verify Rev change and dim. | No Record INV Area
| Rev A 1016 |  | INV Area |  | Need to verify Rev change and dim. | No Record INV Area
Total 8
CRM1207075-0040 C100 WG Spool Left (3)
| L44 |  | Blue Crab |  | No info on part | Hold- NCR 328/339
| L51 |  | Blue Crab |  | NCR 18 -DNU | Hold- NCR 18
| L53 |  | Blue Crab |  | NCR 20- DNU | Hold- NCR 16/20/21/22/23
| L54 |  | Blue Crab |  | Yellow tag- DNU Rework ? | Hold- NCR 14/30
| L50 |  | INV Area |  | Rejected | Rejected- NCR 10
Total 5
CRM1207075-0041 C100 WG Spool Right (3)
| R24 |  | Blue Crab |  | No info on part | Hold-Inspection Pending/83
| R25 |  | Blue Crab |  | No info on part | Hold-Inspection Pending/66
| R35 |  | Blue Crab |  | Did not locate | Use As Is
| R50 |  | Blue Crab |  | Yellow tag- DNU Rework ? | Hold- NCR 12/29
| R53 |  | Blue Crab |  | NCR 28- DNU | Hold- NCR 15/28
Total 5
115800-1011 WG Spool Left (1)
| L01 |  | Blue Crab |  | Yellow Tag- Repairable or Rework | Modify, NCR 4/27
Total 1
115800-1010 WG Spool Right (1)
| R02 |  | Blue Crab |  | Accepted RFU | Use As Is NCR 7
Total 1