## Inspection Activities
WBS Path | Activity ID | Activity Name | Early Start - Parts Scheduled to Arrive | Forecast Finish Dec-20 Month End - Parts Needed | BL Project Finish | Forecast Finish Nov-20 Month End | Total Float | Physical % Complete
1.02.03.13.02 | 102031302060 | Inspect Magnetic Shielding | 29-Oct-20 A | 2021-01-04 | 2020-06-17 | 2021-01-29 | 93 | 60%
1.02.03.05.02 | 102030502235 | Inspect MLI Remainder of MLI | 2021-01-05 | 2021-01-08 | 2020-12-21 | 2020-12-18 | 183 | 0%
1.02.03.11.02 | 102031102085 | Inspect End Can Support | 14-Sep-20 A | 2021-01-15 | 2020-07-24 | 2021-01-15 | 174 | 50%
1.02.03.14.03 | 102031403050 | Perform Mechanical Inspection of CM-03 Cavities | 30-Nov-20 A | 2021-01-15 | 2020-11-20 | 2020-12-18 | 103 | 37.5%
1.02.03.11.02 | 102031102040 | Inspect Modified Misc.Clean Room Tooling | 2021-01-22 | 2021-01-22 | 2020-06-03 | 2020-12-18 | 28 | 0%
1.02.03.03.02 | 1020303020721 | Inspect Helium Vessels Lot #2 | 18-Dec-20 A | 2021-01-29 | 2020-06-19 | 2021-01-05 | 54 | 50%
1.02.03.04.02 | 102030402070 | Inspect Tuner Motors | 2021-01-04 | 2021-01-29 | 2020-05-18 | 2020-12-14 | 75 | 0%
1.02.03.16.02 | 102031602060 | Inspect Helium Outlet and CON Bellows and Corrugated Hose Assemblies | 19-Oct-20 A | 2021-01-29 | 2020-05-14 | 2020-12-23 | 75 | 70%
1.02.03.16.02 | 102031602140 | Inspect Large FPC/Tophat Bellows | 2021-01-04 | 2021-01-29 | 2020-06-03 | 2020-12-01 | 75 | 0%
1.02.03.18.02 | 102031802315 | Inspect Tophats | 2021-01-04 | 2021-01-29 | 2020-04-09 | 2021-01-05 | 165 | 0%
1.02.03.18.02 | 102031802495 | Inspect Supply Warm Beamtube Assembly | 2021-01-26 | 2021-02-01 | 2020-08-10 | 2021-01-06 | 164 | 0%
1.02.03.18.02 | 102031802525 | Inspect Return Warm Beamtube Assembly | 2021-01-26 | 2021-02-01 | 2020-08-10 | 2021-01-06 | 164 | 0%
1.02.03.14.03 | 102031403075 | Perform Mechanical Inspection of CM-04 Cavities | 18-Dec-20 A | 2021-02-04 | 2020-12-11 | 2021-01-15 | 140 | 12.5%
1.02.03.16.02 | 102031602170 | Inspect Cold Mass Assembly Machined Parts | 2021-01-12 | 2021-02-08 | 2020-07-23 | 2021-02-26 | 69 | 0%
1.02.03.15.02 | 102031502425 | Inspect SoftShut Valves (Line 1 - 5 valves) | 2021-02-03 | 2021-02-17 | 2020-10-07 | 2021-07-01 | 152 | 0%
1.02.03.14.03 | 102031403100 | Perform Mechanical Inspection of CM-05 Cavities | 2021-02-05 | 2021-02-18 | 2021-01-05 | 2021-02-01 | 169 | 0%
1.02.03.06.02 | 102030602070 | Inspect Spaceframe | 2021-02-16 | 2021-02-22 | 2020-08-20 | 2021-01-29 | 104 | 0%
1.02.03.03.02 | 1020303020724 | Inspect Helium Vessels Lot #3 | 2021-01-04 | 2021-02-26 | 2020-07-20 | 2021-01-29 | 74 | 0%
1.02.03.04.02 | 102030402351 | Inspect Tuner Frames Lot #1 | 2021-01-04 | 2021-02-26 | 2020-03-23 | 2021-01-14 | 55 | 0%
1.02.03.04.02 | 102030402362 | Inspect Tuner Frames Lot #2 | 2021-01-04 | 2021-02-26 | 2020-05-13 | 2021-01-14 | 240 | 0%
1.02.03.04.02 | 102030402370 | Inspect Tuner Frames Lot #3 | 2021-01-04 | 2021-02-26 | 2020-07-09 | 2021-01-14 | 205 | 0%
1.02.03.04.02 | 102030402390 | Inspect Tuner Frames Lot #4 | 2021-01-04 | 2021-02-26 | 2020-08-18 | 2021-01-14 | 398 | 0%
1.02.03.07.02 | 102030702070 | Inspect Vacuum Vessel #1 | 2021-02-16 | 2021-02-26 | 2020-10-12 | 2021-01-11 | 144 | 0%
1.02.03.10.02 | 102031002085 | Inspect Vaccuum Feedthroughs Instrumentation | 2021-01-04 | 2021-03-01 | 2020-03-25 | 2021-03-01 | 144 | 0%
1.02.03.14.03 | 102031403125 | Perform Mechanical Inspection of CM-06 Cavities | 2021-02-19 | 2021-03-04 | 2021-01-20 | 2021-02-15 | 352 | 0%
1.02.03.03.02 | 102030302074925 | Inspect Helium Vessels Lot #4 | 2021-01-19 | 2021-03-11 | 2020-09-08 | 2021-03-11 | 154 | 0%
1.02.03.15.02 | 102031502429 | Inspect SoftShut Valves (Line 2 - 15 valves) | 2021-03-02 | 2021-03-15 | 2020-11-09 | 2021-11-03 | 219 | 0%
1.02.03.14.03 | 102031403150 | Perform Mechanical Inspection of CM-07 Cavities | 2021-03-05 | 2021-03-18 | 2021-02-03 | 2021-03-01 | 382 | 0%
1.02.03.07.02 | 102030702085 | Inspect Vacuum Vessel #2 | 2021-03-19 | 2021-03-26 | 2020-11-11 | 2021-02-22 | 169 | 0%
1.02.03.10.02 | 102031002115 | Inspect Feed Thru Flange Weldment | 2021-01-04 | 2021-03-26 | 2020-05-29 | 2021-01-04 | 125 | 0%
1.02.03.18.02 | 102031802275 | Inspect Pressure Relief Plates and Rupture Disks | 2021-02-24 | 2021-03-26 | 2020-02-24 | 2021-01-29 | 125 | 0%
1.02.03.03.02 | 102030302074940 | Inspect Helium Vessels Lot #5 | 2021-02-18 | 2021-04-01 | 2020-10-07 | 2021-04-01 | 332 | 0%
1.02.03.07.02 | 102030702100 | Inspect Vacuum Vessel #3 | 2021-04-08 | 2021-04-16 | 2020-12-10 | 2021-03-15 | 194 | 0%
1.02.03.03.02 | 102030302074955 | Inspect Helium Vessels Lot #6 | 2021-04-05 | 2021-04-30 | 2020-10-19 | 2021-04-30 | 351 | 0%
1.02.03.07.02 | 102030702115 | Inspect Vacuum Vessel #4 | 2021-05-21 | 2021-05-27 | 2021-01-13 | 2021-04-23 | 215 | 0%
1.02.03.05.02 | 102030502220 | Inspect MLI First Article | 2021-06-02 | 2021-06-08 | 2020-07-22 | 2021-06-08 | 74 | 0%
1.02.03.08.02 | 102030802070 | Inspect Supply End Cans | 2021-05-10 | 2021-06-09 | 2021-01-22 | 2021-07-30 | 73 | 0%
1.02.03.07.02 | 102030702130 | Inspect Vacuum Vessel #5 | 2021-06-14 | 2021-06-18 | 2021-02-15 | 2021-05-14 | 240 | 0%
1.02.03.04.02 | 102030402270 | Inspect Tuner Harmonic Drives | 2021-01-04 | 2021-06-30 | 2020-06-15 | 2020-12-15 | 13 | 0%
1.02.03.07.02 | 102030702145 | Inspect Vacuum Vessel #6 | 2021-07-26 | 2021-07-30 | 2021-03-12 | 2021-06-25 | 404 | 0%
1.02.03.07.02 | 102030702160 | Inspect Vacuum Vessel #7 | 2021-08-13 | 2021-08-19 | 2021-04-06 | 2021-07-16 | 430 | 0%
1.02.03.11.02 | 102031102130 | Inspect Misc. Tooling Required for Cryomodule builds | 2021-09-09 | 2021-09-10 | 2020-07-23 | 2021-09-10 | 53 | 0%
1.02.03.09.02 | 102030902070 | Inspect Return End Cans | 2021-08-18 | 2021-09-17 | 2021-01-25 | 2021-07-30 | 3 | 0%
1.02.03.15.02 | 102031502060 | Inspect Beamline Bellows | 15-Dec-20 A | 2022-01-21 | 2020-03-11 | 2020-12-16 | 210 | 0%
1.02.03.15.02 | 102031502190 | Inspect Supply and Return Warm to Cold Beamline Weldments | 2021-01-04 | 2022-01-21 | 2020-05-28 | 2020-12-23 | 210 | 0%
1.02.03.15.02 | 102031502255 | Inspect Warm to Cold Beamline Bellows Restraints | 01-Apr-20 A | 2022-01-21 | 2020-05-29 | 2020-12-23 | 210 | 10.04%
1.02.03.09.02 | 102030902130 | Inspect Return End Can Heat Exchangers | 01-Jun-20 A | 01-Jun-20 A | 2020-05-18 | 2020-06-01 |  | 100%
1.02.03.05.02 | 102030502150 | Inspect Thermal Shields | 01-Sep-20 A | 01-Sep-20 A | 2020-07-28 | 2020-09-01 |  | 100%
1.02.03.05.02 | 102030502170 | Inspect Additional 50K Support Assemblies | 01-Sep-20 A | 01-Sep-20 A | 2020-07-28 | 2020-09-01 |  | 100%
1.02.03.10.02 | 102031002060 | Inspect Instrumentation (First Group) | 01-Apr-20 A | 02-Apr-20 A | 2020-02-12 | 2020-04-02 |  | 100%
1.02.03.14.03 | 102031403000A10 | Perform Mechanical Inspection of CM-01 Cavity #2 | 02-Oct-20 A | 02-Oct-20 A | 2020-08-18 | 2020-10-02 |  | 100%
1.02.03.15.02 | 102031502125 | Inspect Gate valves VAT 482XX | 03-Dec-20 A | 04-Dec-20 A | 2020-02-24 | 2021-01-29 |  | 100%
1.02.03.14.03 | 102031403000A30 | Perform Mechanical Inspection of CM-01 Cavity #4 | 26-Oct-20 A | 06-Nov-20 A | 2020-08-26 | 2020-11-06 |  | 100%
1.02.03.18.02 | 102031802440 | Inspect Coupler Return Piping | 07-Sep-20 A | 07-Sep-20 A | 2020-07-20 | 2020-09-07 |  | 100%
1.02.03.18.02 | 102031802235 | Inspect Flange NW250 + feedthrough flange weld | 08-Jul-20 A | 08-Jul-20 A | 2020-01-15 | 2020-07-08 |  | 100%
1.02.03.07.02 | 102030702190 | Inspect Ion Pump Support Assembly | 08-May-20 A | 08-May-20 A | 2020-07-15 | 2020-05-08 |  | 100%
1.02.03.10.02 | 102031002145 | Inspect Thermocouple Probe Procurement | 08-May-20 A | 08-May-20 A | 2020-06-08 | 2020-05-08 |  | 100%
1.02.03.14.03 | 102031403000 | Perform Mechanical Inspection of CM-01 Cavity #1 | 07-Oct-20 A | 09-Oct-20 A | 2020-08-13 | 2020-10-09 |  | 100%
1.02.03.11.02 | 102031102215 | Inspect Warm to Cold Beam Tube Support | 10-Aug-20 A | 12-Oct-20 A | 2020-05-15 | 2020-10-12 |  | 100%
1.02.03.11.02 | 102031102260 | Inspect CR Pump Drop Support | 10-Aug-20 A | 12-Oct-20 A | 2020-05-12 | 2020-10-12 |  | 100%
1.02.03.11.02 | 102031102350 | Inspect FPC Installation tooling | 10-Aug-20 A | 12-Oct-20 A | 2020-06-15 | 2020-10-12 |  | 100%
1.02.03.11.02 | 102031102395 | Inspect CR Bellows installation and support tooling | 10-Aug-20 A | 12-Oct-20 A | 2020-06-09 | 2020-10-12 |  | 100%
1.02.03.18.02 | 102031802060 | Inspect Gate valve MDC 303006-133 | 07-Dec-20 A | 14-Dec-20 A | 2020-05-14 | 2020-12-09 |  | 100%
1.02.03.19.02 | 102031902150 | Inspect Shipping Frame Springs | 14-Jul-20 A | 14-Jul-20 A | 2020-09-10 | 2020-07-14 |  | 100%
1.02.03.19.02 | 102031902235 | Inspect Shipping Test Instrumentation | 14-Jul-20 A | 14-Jul-20 A | 2020-06-16 | 2020-07-14 |  | 100%
1.02.03.03.02 | 102030302070 | Inspect Helium Vessels Lot #1 | 17-Aug-20 A | 15-Sep-20 A | 2020-05-28 | 2020-09-15 |  | 100%
1.02.03.11.02 | 102031102440 | Inspect Cavity/He Vessel welding tooling | 10-Dec-19 A | 16-Dec-19 A | 2019-12-19 | 2019-12-16 |  | 100%
1.02.03.14.03 | 102031403025 | Perform Mechanical Inspection of CM-02 Cavities | 20-Nov-20 A | 19-Dec-20 A | 2020-10-30 | 2020-12-02 |  | 100%
1.02.03.05.02 | 102030502325 | Inspect Installing Thermal Shield Assy to Space Frame Assy | 19-Jun-20 A | 19-Jun-20 A | 2020-06-09 | 2020-06-19 |  | 100%
1.02.03.18.02 | 102031802130 | Inspect Flange Blank Assy. | 20-Jul-20 A | 20-Jul-20 A | 2020-03-05 | 2020-07-20 |  | 100%
1.02.03.18.02 | 102031802195 | Inspect Surge Tank | 21-Dec-20 A | 22-Dec-20 A | 2020-01-15 | 2020-12-01 |  | 100%
1.02.03.05.02 | 102030502195 | Inspect One Additional Set of Thermal Shield Return and Supply End Assemblies MOD 2 | 19-Jun-20 A | 22-Jun-20 A | 2020-07-28 | 2020-06-22 |  | 100%
1.02.03.11.02 | 102031102485 | Inspect Spaceframe Temp Pump Drop support | 22-Jun-20 A | 25-Jun-20 A | 2020-05-28 | 2020-06-25 |  | 100%
1.02.03.14.03 | 102031403000A20 | Perform Mechanical Inspection of CM-01 Cavity #3 | 25-Sep-20 A | 25-Sep-20 A | 2020-08-21 | 2020-09-25 |  | 100%
1.02.03.15.02 | 102031502320 | Inspect VAT Right Angle Valve (Supply End) | 28-Feb-20 A | 28-Feb-20 A | 2020-04-13 | 2020-02-28 |  | 100%
1.02.03.18.02 | 102031802470 | Inspect CM Rupture Disk Spool Assemblies Requisition | 28-Jul-20 A | 28-Jul-20 A | 2020-07-13 | 2020-07-28 |  | 100%
1.02.03.13.02 | 1020313020225 | Inspect Magnetic Shielding Existing Parts and Modification | 26-Oct-20 A | 29-Oct-20 A | 2020-02-13 | 2020-10-29 |  | 100%
1.02.03.19.02 | 102031902195 | Inspect Dummy Cryomodule | 29-Sep-20 A | 29-Sep-20 A | 2020-08-12 | 2020-09-29 |  | 100%
1.02.03.15.02 | 102031502360 | Inspect Titan 40 L/s ion pump (correction: 11 L/s) | 29-Apr-20 A | 30-Apr-20 A | 2020-04-17 | 2020-04-30 |  | 100%
1.02.03.19.02 | 102031902105 | Inspect Shipping Frame Modifications | 27-Jul-20 A | 30-Jul-20 A | 2020-09-08 | 2020-07-30 |  | 100%
1.02.03.19.02 | 102031902295 | Inspect Shipping Frame Modifications | 30-Jul-20 A | 30-Jul-20 A | 2020-07-31 | 2020-07-30 |  | 100%