## Travelers (hidden)
Traveler Name | Traveler ID | AUTHOR | REVIEWER | REVIEWER | MANAGER | NCR EMAIL NAMES | Old REV_NO | REV | FINAL DONE | APRV SIGN
Receiving Travelers
Cavity
C75 Cavity recv | C75-CAV-RECV-CAV | Ciovati | Dickey |  | Macha |  | R2-0 | R1-0 | 2019-03-22
Disassembly Traveler
C75 Cavity Pair Disassembly | C75-CPR-DISA | Forehand | Davis |  | Macha |  | R4-0 | R1-0 | 2018-02-16
C75 Cryounit Disassembly | C75-CU-DISA | Fischer | Worland |  | Macha |  | R1-0 | R1-0 | 2017-08-24
C75 Disassembly Traveler | C75-CM-DISA | Fischer | Worland |  | Macha |  |  |  | 2017-08-23
Cavity Fabrication Travelers
C75 weld-prep BCP | C75-CAV-BCP-COMP | Ciovati | Follkie | Geng | Macha |  |  |  | 2018-03-16
C75 BCP half-cell | C75-CAV-CHEM-BCP-HCEL | Ciovati | Anderson | Follkie | Macha |  |  |  | 2018-01-18
C75 cavity fabrication | C75-CAV-FAB | Ciovati | Clemens | Daly | Macha |  |  |  | 2018-02-01
C75 Deep draw cell half | C75-CAV-FAB-HCEL | Ciovati | Williams |  | Macha |  |  |  | 2017-10-31
C75 Half-Cells Heat Treatment | C75-CAV-HEAT-HCEL | Ciovati | Forehand |  | Macha |  |  |  | 2018-02-08
C75 Cavity Adapter Ring Inspection (in works) | C75-CAV-INSP-ADTPR | DeKerlegand | Carpenter | Ciovati | Macha | Ciovati
C75 Inspect Dumbbells after machining | C75-CAV-INSP-DB | Dekerlegand |  | Ciovati | Macha | Ciovati |  |  | 2018-07-23
C75 FPC Beamtube Inspection | C75-CAV-INSP-FPCBT | Dekerlegand |  | Ciovati | Macha |  |  |  | 2018-04-17
C75 Inspect C20 End group after machining prep for C75 | C75-CAV-INSP-ENDG | Dekerlegand | Carpenter | Ciovati | Macha | Ciovati
C75 half-cell inspection | C75-CAV-INSP-HCEL | Dekerlegand | Carpenter | Ciovati | Macha | Ciovati |  |  | 2018-03-01
C75 Material receipt inspection - Nb Discs | C75-CAV-INSP-NB | Dekerlegand | Carpenter | Ciovati | Macha | Ciovati |  |  | 2017-12-12
C75 Material receipt inspection - Nb Ingot | C75-CAV-INSP-NBI | Cheng | Ciovati |  | Macha |  |  |  | 2017-12-12
C75 Inspection Stiffening rings | C75-CAV-INSP-SRING | Dekerlegand | Carpenter | Ciovati | Macha | Ciovati |  |  | 2018-02-23
FPC End group Dimensional Inspection | C75-CAV-INSP-FPCEG | DeKerlegand | Ciovati |  | Macha |  |  |  | 2018-09-14
C75 Dumbbell RF measurement | C75-CAV-RFIN-DB | Ciovati | Marhauser |  | Macha
C75 Half Cell RF Measurement | C75-CAV-RFIN-HCEL | Ciovati | Marhauser |  | Macha |  |  |  | 2018-03-06
C75 End Half Cell RF Measurement | C75-CAV-RFIN-EHCEL | Ciovati | Marhauser |  | Macha |  |  |  | 2018-03-06
C75 End-group RF measurement | C75-CAV-RFIN-ENDG | Ciovati | Marhauser |  | Macha
Fabrication Travelers
C75 HOM LOAD ASSEMBLY | C75-CPR-FAB-HOML | Williams | Carpenter |  | Macha
C75 Dogleg Assembly | C75-CPR-FAB-DGLG (C50) | Williams | Carpenter | Palczewski | Macha |  | R9-0 | R1-0
C75 Dogleg Ceramic/Eyelet Window Subassembly | C75-CPR-FAB-WNCR (C50) | Williams | Marhauser |  | Macha |  | R4-0 | R1-0
Electron Beam Certification | C75-EBW-CERT | Clemens | Ciovati |  | Macha |  |  |  | 2017-08-22
Inspection travelers
Cavity Pair
C75 Cavity Dimensional Inspection | C75-CPR-INSP-CAV | DeKerlegand | Carpenter |  | Macha | kdavis,forehand | R5-0 | R1-0 | 2018-04-12
C75 Cavity Pair Final Assembly Dimensional Inspection | C75-CPR-INSP-CAVPR | DeKerlegand | Carpenter | Fischer | Macha | kdavis,fischer | R3-0 | R1-0
C75 Dogleg Window Assembly Dimensional Inspection | C75-CPR-INSP-DGLG | DeKerlegand | Carpenter | Williams | Macha | kdavis,forehand | R8-0 | R1-0 | 2017-11-10
C75 Dogleg Window Cavity Flange Dimensional Inspection | C75-CPR-INSP-DLCF | DeKerlegand | Carpenter | Williams | Macha | scott | R1-0 | R1-0 | 2017-11-10
C75 Dogleg Window Flange Dimensional Inspection | C75-CPR-INSP-DLWF | DeKerlegand | Carpenter | Williams | Macha | scott | R1-0 | R1-0 | 2017-11-10
C75 Dogleg Window Waveguide Section Dimensional Inspection | C75-CPR-INSP-DLWS | DeKerlegand | Carpenter | Williams | Macha | scott | R2-0 | R1-0 | 2017-11-10
C75 End Dish and Bellows Assembly Dimensional Inspection | C75-CPR-INSP-ENDD | DeKerlegand | Carpenter |  | Macha | kdavis,forehand | R3-0 | R1-0 | 2017-11-10
C75 H. O. M. Elbow Assembly Dimensional Inspection | C75-CPR-INSP-HOME | DeKerlegand | Carpenter |  | Macha | kdavis,forehand | R5-0 | R1-0 | 2018-02-16
C75 HOM Flange Inspection | C75-CPR-INSP-HOMF | DeKerlegand | Carpenter | Williams |  | scott
C75 HOM Load Assembly Dimensional Inspection | C75-CPR-INSP-HOML | DeKerlegand | Carpenter | Williams | Macha | kdavis,forehand | R4-0 | R1-0 | 2017-11-10
C75 HOM Pedestal Inspection | C75-CPR-INSP-HOMP | DeKerlegand | Carpenter | Williams |  | scott
C75 Inner Adapter Dimensional Inspection | C75-CPR-INSP-INAD | DeKerlegand | Carpenter |  | Macha | kdavis,forehand | R4-0 | R1-0 | 2017-11-10
C75 Dogleg Window Ceramic Dimensional Inspection | C75-CPR-INSP-WNCR | DeKerlegand | Carpenter | Williams | Macha | scott | R1-0 | R1-0 | 2017-11-10
C75 Dogleg Window Eyelet Dimensional Inspection | C75-CPR-INSP-WNEY | DeKerlegand | Carpenter | Williams | Macha | scott | R1-0 | R1-0 | 2017-11-10
Cryo Unit
C75 Waveguide Extension Dimensional Inspection | C75-CU-INSP-WGDX | DeKerlegand | Carpenter | Fischer | Macha | fischer | R4-0 | R1-0 | 2017-11-15
C75 Warm Window Assembly Dimensional Inspection | C75-CU-INSP-WIN | DeKerlegand | Carpenter | Fischer | Macha | fischer | R3-0 | R1-0 | 2017-11-15
C75 Warm Window Dimensional Inspection | C75-CU-INSP-WINW | DeKerlegand | Carpenter | Fischer | Macha | fischer | n/a | R1-0 | 2017-11-15
Cryo Unit
C75 Waveguide Extension Dimensional Inspection | C75-CU-INSP-WGDX | DeKerlegand | Carpenter | Fischer | Macha | fischer | R4-0 | R1-0 | 2017-11-15
Processing Travelers
Cavity
C75 Cavity flange Initial lapping traveler | C75-CAV-ILAP | C Johnson | Follkie | Castagnola | Macha |  | n/a | R1-0
C75 Cavity flange Final lapping traveler. | C75-CAV-FLAP | C Johnson | Follkie | Castagnola | Macha |  | R1-0 | R1-0
C75 Cavity End Dish Fabrication traveler. | C75-CAV-FAB-ENDD | Williams | Ciovati | Castagnola | Macha |  | n/a | R1-0
C75 Cavity Lapping (in progress) | C75-CAV-LAP (C50) | C Johnson | Follkie | Castagnola | Macha |  | R1-0 | R1-0
C75 Chemistry BCP | C75-CAV-CHEM-BCP | Castagnola | Reilly |  | Reilly |  | R1-0 | R1-0
C75 Cavity Heat Treatment | C75-CPR-HEAT | Ciovati | Forehand |  | Macha |  | R1-0 | R1-0 | 2018-07-26
C75 Processing | C75-CAV-PROC | Bookwalter | Davis | Reece | Macha |  | R1-0 | R1-0 | 2018-01-16
C75 Half-Cells Insepection, Grinding and Polishing | C75-CAV-PROC-POL-DBEL | Ciovati | Palczewski |  | Macha |  | R1-0 |  | 2018-02-08
C75 Cavity Thickness Measurement | C75-CAV-CHEM-THK | Ciovait | Mitchell |  | Macha |  |  |  | 2019-01-25
C75 Chemistry HEP | C75-CAV-CHEM-HEP | Ciovati | Mitchell |  | Macha |  |  |  | 2019-03-19
C75 Cavity Degreasing | C75-CAV-CHEM-DEGR | Anderson | Follkie | Ciovati | Macha |  | R1-0 | R1-0 | 2018-02-21
C75 First HPR | C75-CAV-CHEM-HPR1 | Anderson | Follkie | Ciovati | Macha |  | R2-0 | R1-0 | 2018-02-21
C75 Second HPR | C75-CAV-CHEM-HPR2 | Anderson | Follkie | Ciovati | Macha |  | R2-0 | R1-0 | 2018-02-21
C75 Cavity BCP Flange Prep | C75-CAV-CHEM-BCP-FLNG
Cavity Pair
C75 Pair Component Etching and Cleaning | C75-CPR-BCP-SUBC | Castagnola | Reilly |  | Reilly |  | R1-0 | R1-0
C75 Subcomponent Cleaning | C75-CPR-CLN-SUBC | Castagnola | Reilly |  | Reilly |  | R1-0 | R1-0
C75 Cavity Pair Cleaning and Acid Etching | C75-CPR-CHEM-CPR | Anderson | Follkie | Ciovati | Reilly |  | R1-0
Cryomodule
C75 Cryomodule Cavity Magnetic Shield Assembly | C75-CM-INSP-CMAG | Cheng | DeKerlegand | Macha | Reilly |  | R2-0 | R1-0 | 2018-08-20
Assembly Travelers
Cavity
C75 Cavity Tuning | C75-CAV-TUNE | Ciovati | Forehand | Marhauser | Macha |  | R2-0 | R1-0 | 2018-07-26
Cavity Pair
C75 Pair Assembly 1st Assembly | C75-CPR-ASSY-FRST | Forehand | Dreyfuss | Palczewski | Macha |  | R2-0 | R1-0
C75 Pair Assembly 2nd Assembly | C75-CPR-ASSY-SCND | Forehand | Dreyfuss | Palczewski | Macha |  | R3-0 | R1-0
C75 Supply Side Pump Drop and Return Side Beam Pipe Assembly | C75-CPR-ASSY-BPIP | Forehand | Dreyfuss | Palczewski | Macha |  | R1-0 | R1-0
C75 Pair Assembly Completion | C75-CPR-ASSY-CMPL | Forehand | Dreyfuss | Palczewski | Macha |  | R6-0 | R1-0
C75 Dogleg Assembly | C75-CPR-ASSY-DGLG | DeKerlegand | Scott |  | Macha |  |  |  | 2018-03-28
C75 End-Dish Sub-Assembly (not in C50) | C75-CPR-ASSY-ENDD (C50) | Dreyfuss | Forehand | Palczewski | Macha |  | R3-0 | R1-0
C75 Pair Assembly-Cavity Evacuation and Leak test | C75-CPR-ASSY-EVAC | Forehand | Dreyfuss | Palczewski | Macha |  | R5-0 | R1-0 | 2018-02-16
C75 Metallized Ceramic Window Warm RF Measurements | C75-CPR-ASSY-MWNRF | Forehand | Haipeng | Marhauser | Davis |  | R1-0 | R1-0
C75Pair Assembly Strong-back Fixture Preparation | C75-CPR-ASSY-STBK | Forehand | Dreyfuss |  | Macha |  | R2-0 | R1-0
C75 Pair Assembly Stack-up | C75-CPR-ASSY-STKU | Forehand | Dreyfuss |  | Macha |  | R2-0 | R1-0 | 2018-02-16
C75 Pair Assembly Transfer to Dewar | C75-CPR-ASSY-TDWR (C50 - hold) | Forehand | Dreyfuss |  | Macha |  | R1-0 | R1-0
C75 Pair Assembly Preparation for Turnover | C75-CPR-ASSY-TOVR | Forehand | Dreyfuss |  | Macha |  | R2-0 | R1-0 | 2018-02-16
C75 Dogleg Ceramic/Eyelet Window Subassembly | C75-CPR-ASSY-WNCR | Williams | DeKerlegand |  | Macha |  | R2-0 |  | 2018-04-12
C75 Pair Assembly Transfer to Test Stand | C75-CPR-TRANS-TSTD ? | Forehand | Dreyfuss |  | Macha |  | R3-0 | R1-0
C75 parts magnetic hygiene | C75-CPR-DEMAG-COMP | Cheng |  | Ciovati | Macha
Cryo Unit
C75 Warm Window Brazed Assembly | C75-CU-BRAZ-WINW | Williams |  |  | Macha |  | R1-0 | R1-0 | 2018-08-20
C75 Helium Vessel Assembly | C75-CU-ASSY-HELV | McCrea | Worland | Fischer | Macha |  | R1-0 | R1-0
C75 Tuner Assembly, Mu metal and HOM stiffener installation | C75-CU-ASSY-TUNE-MU? | McCrea | Worland | Fischer | Macha |  | R2-0 | R1-0
C75 cryounit parts demag | C75-CU-DEMAG-COMP | Cheng | McCrea | Ciovati | Macha
C75 Vacuum Vessel Assembly | C75-CU-ASSY-VV | McCrea | Worland | Fischer | Macha |  | R1-0 | R1-0
C75Waveguide Assembly | C75-CU-ASSY-WG | McCrea | Worland | Fischer | Macha |  | R1-0 | R1-0
Cryomodule
C75 Cryomodule Assembly | C75-CM-ASSY | Campbell | Worland | Fischer | Macha |  | R1-0 | R1-0
Testing Travelers
C75 Cavity Pair VTA Test | C75-CPR-VTRF | Stribet | Davis |  | Macha |  | R2-0 | R1-0
C75 VTA Pair Coldown | C75-CPR-VTA-COOL | Kushnick | Davis |  | Macha |  |  | R1-0
C75 DogLeg VTA Test | C75-CPR-VTRF-DGLG | Forehand | Marhauser | Davis | Macha |  | R2-0 | R1-0 | 2018-02-20
C75 Cryomodule Acceptance Test | C75-CM-CMTF-ACC | Drury |  |  | Macha |  | R1-0 | R1-0
C75 Cryomodule Commissioning | C75-CM-COM-TEST | Drury |  |  | Macha |  | R1-0 | R1-0
Installation Travelers
Standard Project Travelers
C75 Detours, Deviations and Discrepancies (D3) | C75-D3 | Bookwalter |  |  |  |  | R1-0 | R1-0 | 2017-08-01
C75 Project NCR | C75-NCR | Bookwalter |  |  |  |  | R5-0 | R1-0 | 2017-08-01
Girder rework Travelers
Girder particle sample and disassembly
Girder assembly and leak test

## Master List
Document Type | Traveler Name | Traveler ID (SEPARATE BY WORKCENTERS) | Procedure(s), Name (if known) OR Yes/No | Drawing(s), Name (if known) OR Yes/No | SOP/TOSP/OSP/THA | Revision | Author | Reviewer | Project Manager | SOTR | Due | D3 ?? (USERNAME) | NCR Dispositioners (USERNAME) | NCR Informative (USERNAME) | Traveler (Holdpoint) Closer (USERNAME) | Notes
Inventory
Traveler | C75 Cavity Receiving | C75-CAV-RECV-CAV |  |  |  | R1 | G. Ciovati | M. Dickey | K. Macha |  | 2020-03-22
Traveler | Magnetic Shield Receive Traveler | C75-CAV-RECV-IMAG |  |  |  | R1 | M. Dickey | G. Cheng | K. Macha |  | 2020-05-12 |  |  |  |  | Data needs to be backfilled
Traveler | Nextor Pump for waveguide | C75-CPR-RECV-NEXTOR |  |  |  | R1 | M. Dickey | G. Ciovati | K. Macha |  | 2020-06-30
Traveler | Capacitorr Pump for BL | C75-CM-RECV-CAPTOR |  |  |  | R1 | M. Dickey | G. Ciovati | K. Macha |  | 2020-06-30
Traveler | Cavity MDC gate valve | C75-CPR-RECV-GV40 |  |  |  | R1 | M. Dickey | G. Ciovati | K. Macha |  | 2020-05-12
Disassembly
Traveler | C20 HOM End group Dimensional Inspection | C20-CAV-INSP-HOMEG |  |  |  | R1 | A. DeKerlegand | G. Ciovati | K. Macha |  | 2019-10-07
Traveler | C20 FPC End group Dimensional Inspection | C20-CAV-INSP-FPCEG |  |  |  | R2 | A. DeKerlegand | G. Ciovati | K. Macha |  | 2019-10-07
Traveler | C20 Cavity pair disassembly | C20-CPR-DISA |  |  |  | R1 | D. Forhand | K. Davis | K. Macha |  | 2020-08-20
Traveler | C20 Cryounit Disassmbly | C20-CU-DISA |  |  |  | R2 | J. Fischer | K. Worland | K. Macha | [6 empty] | R2 is Ready for approval, R1 is in use (Talk with John, is this ready?) RadCon update?
Traveler | C20 Cryomodule Disassembly | C20-CM-DISA |  |  |  | R1 | J. Fischer | K. Worland | K. Macha |  | 2019-10-21
Traveler | Cavity Pair Disasseembly | C75-CPR-DISA |  |  |  | R1 | D. Forehand | K. Davis | K. Macha |  | 2019-02-16 |  |  |  |  | Danny to revise. Belongs in C20 project. May require C75 disassembly some day
Traveler | Cryounit Disassmbly | C75-CU-DISA |  |  |  | R2 | J. Fischer | K. Worland | K. Macha |  | 2017-10-05
Traveler | Cryomodule Disassembly | C75-CM-DISA |  |  |  | R2 | J. Fischer | K. Worland | K. Macha
Traveler | Cavity Disasseembly
Cavity Fabrication
Traveler | Weld Prep BCP | C75-CAV-BCP-COMP |  |  |  | R2 | G. Ciovati | J. Follkie | K. Macha |  | 2018-03-16
Traveler | BCP of C75 Dumbbells | C75-CAV-BCP-DBEL |  |  |  | R1 | G. Giovati | A. Mitchell | K. Macha |  | 2018-07-30
Traveler | BCP Half Cell | C75-CAV-CHEM-BCP-HCEL |  |  |  | R1 | G. Ciovati | A. Mitchell | K. Macha |  | 2018-01-18
Traveler | BCP of C75 Cavity Flanges | C75-CAV-CHEM-BCP-FLNG |  |  |  | R1 | G. Ciovati | A. Mitchell | K. Macha |  | 2019-05-20
Traveler | Cavity Fabrication | C75-CAV-FAB |  |  |  | R1 | G. Ciovati | B. Clemens | K. Macha |  | 2018-02-01
Traveler | Deep Draw Cell Half | C75-CAV-FAB-HCEL |  |  |  | R3 | G. Ciovati | S. Williams | K. Macha |  | 2017-10-31
Traveler | C75 Half-Cells Heat Tratment | C75-CAV-HEAT-HCEL |  |  |  | R1 | G. Ciovati | D. Forehand | K. Macha |  | 2018-01-30
Traveler | Dumbbell Dimensional Inspection | C75-CAV-INSP-DBEL |  |  |  | R1 | A. DeKerlegand | G. Ciovati | K. Macha |  | 2018-07-23
Traveler | FPC Beamtube Inspection | C75-CAV-INSP-FPCBT |  |  |  | R1 | A. DeKerlegand | G. Ciovati | K. Macha |  | 2018-04-17
Traveler | Inspect C20 End group after machining prep for C75 | C75-CAV-INSP-FPCEG |  |  |  | R1 | A. DeKerlegand | G. Ciovati | K. Macha |  | 2018-09-14
Traveler | half-cell inspection | C75-CAV-INSP-HCEL |  |  |  | R4 | A. DeKerlegand | G. Ciovati | K. Macha |  | 2018-03-01
Traveler | Material receipt inspection - Nb Discs | C75-CAV-INSP-NB |  |  |  | R1 | A. DeKerlegand | G. Ciovati | K. Macha |  | 2017-12-12
Traveler | Material receipt inspection - Nb Ingot | C75-CAV-INSP-NBI |  |  |  | R1 | G. Cheng | G. Ciovati | K. Macha |  | 2017-12-12
Traveler | Inspection Stiffening rings | C75-CAV-INSP-SRING |  |  |  | R1 | A. DeKerlegand | G. Ciovati | K. Macha |  | 2018-02-23
Traveler | Dumbbell RF measurement | C75-CAV-RFIN-DBEL |  |  |  | R1 | G. Ciovati | F. Marhauser | K. Macha |  | 2018-02-02
Traveler | Half Cell RF Measurement | C75-CAV-RFIN-HCEL |  |  |  | R1 | G. Ciovati | F. Marhauser | K. Macha |  | 2018-03-06
Traveler | End Half Cell RF Measurement | C75-CAV-RFIN-EHCEL |  |  |  | R1 | G. Ciovati | F. Marhauser | K. Macha |  | 2018-03-06
Traveler | C75 Processing | C75-CAV-PROC |  |  |  | R2 | V. Bookwalter | K. Davis | K. Macha |  | 2018-01-16
Procedure | C75 Half-Cell and tube forming | CP-C75-CAV-FAB-HCEL |  |  |  | R1 | G. Ciovati | S. Williams | K. Macha |  | 2017-10-24
Procedure | C75 Dumb-Bell and end half cells RF inspection | CP-C75-CAV-RFIN |  |  |  | R1 | G. Ciovati | F. Marhauser | K. Macha |  | 2018-06-11
Traveler | C75 Half-Cells Insepection, Grinding and Polishing | C75-CAV-PROC-POL-DBEL |  |  |  | R2 | G. Ciovati | A. Palczewski | K. Macha |  | 2018-07-27
Component Preparation
Inspection
Traveler | C75 Cavity Optical Inspection | C75-CAV-INSP-OPTK |  |  |  | R1 | G. Ciovati | R. Geng | K. Macha |  | 2019-04-08
Traveler | C75 Cavity Flange Component inspection | C75-INSP-FLG-COMP |  |  |  | R1 | A. DeKerlegand | K. Macha | K. Macha |  | 2020-08-18
Traveler | Cebaf Cryomodule Dogleg Assembly Inspection | C75-CPR-INSP-DGLG |  |  |  | R4 | A. DeKerlegand | S.Williams | K. Macha |  | 2019-04-30 |  | forehand,gciovati,macha,scott | ashleya
Traveler | Dogleg Waveguide Cavity Flange Inspection | C75-CPR-INSP-DLCF |  |  |  | R1 | A. DeKerlegand | S.Williams | K. Macha |  | 2018-03-28 |  | scott
Traveler | Dogleg Waveguide Window Flange Inspection | C75-CPR-INSP-DLWF |  |  |  | R1 | A. DeKerlegand | S.Williams | K. Macha |  | 2019-04-05 |  | scott
Traveler | Dogleg Window Waveguide Section | C75-CPR-INSP-DLWS |  |  |  | R2 | A. DeKerlegand | S.Williams | K. Macha |  | 2020-10-15 |  | scott |  |  | Need PDF
Traveler | Cryomodule End Dish and Bellows Assembly Dimensional Inspection | C75-CPR-INSP-ENDD |  |  |  | R1 | A. DeKerlegand | G. Ciovati | K. Macha |  | 2017-10-31 |  | forehand,gciovati,macha | ashleya
Traveler | HOM Elbow Assembly Dimensional Inspection | C75-CPR-INSP-HOME |  |  |  | R1 | A. DeKerlegand | G. Ciovati | K. Macha |  | 2017-10-31 |  | forehand,gciovati,macha | ashleya
Traveler | HOM Load Assembly Inspection | C75-CPR-INSP-HOML |  |  |  | R1 | A. DeKerlegand | G. Ciovati | K. Macha |  | 2017-10-31 |  | forehand,gciovati,macha | ashleya
Traveler | Inner Adapter Dimensional Inspection | C75-CPR-INSP-INAD |  |  |  | R1 | A. Dekerlegand | G. Ciovati | K. Macha |  | 2020-04-28 |  | forehand,gciovati,macha | ashleya
Traveler | Cryomodule Dogleg Window Ceramic Inspection | C75-CPR-INSP-WNCR |  |  |  | R1 | A. Dekerlegand | G. Ciovati | K. Macha |  | 2017-11-07 |  | scott
Traveler | Cryomodule Dogleg Window Eyelet Inspection | C75-CPR-INSP-WNEY |  |  |  | R1 | A. Dekerlegand | G. Ciovati | K. Macha |  | 2017-10-31 |  | scott
Traveler | Dogleg VTA Cold Testing | C75-CPR-VTRF-DGLG |  |  |  | R2 | D. Forehand | F. Marhauser | K. Macha |  | 2018-02-19 |  | marhause |  |  | Revision required as per Frank M.
Traveler | 5-Cell Cavity Dimensional Inspection | C75-CAV-INSP |  |  |  | R5 | A. Dekerlegand | G. Ciovati | K. Macha |  | 2020-05-06
Traveler | Final inspection of new HOM load
Chemistry
Procedure | Acid Etching at the Chemical Fume Hood procedure | CP-STP-CAV-CHEM-ACID |  |  |  | R1 | A. Mitchel | J. Follkie | K. Macha |  | 2017-07-25
Traveler | C75 Cavity Thickness Measurement | C75-CAV-CHEM-THK |  |  |  | R1 | G. Ciovati | A. Mitchell | K. Macha |  | 2019-01-25
Traveler | C75 Chemistry HEP | C75-CAV-CHEM-HEP |  |  |  | R2 | G. Ciovati | A. Mitchell | K. Macha |  | 2020-10-20
Traveler | C75 Cavity Degreasing | C75-CAV-CHEM-DEGR |  |  |  | R1 | A. Mitchell | G. Ciovati | K. Macha |  | 2018-02-21
Procedure | C75 Cavity De-greasing | CP-C75-CAV-CHEM-USC |  |  |  | R1 | A. Wildeson | G. Ciovati | K. Macha |  | 2020-06-01
Traveler | C75 HPR | C75-CAV-CHEM-HPR |  |  |  | R1 | A. Mitchell | G. Ciovati | K. Macha |  | 2018-02-21
Procedure | C75 Cavity Pair HPR Procedure | CP-C75-CPR-CHEM-HPR |  |  |  | R1 | A. Mitchel | G. Ciovati | K. Macha |  | 2020-02-19
Procedure | C75 Cavity HPR Procedure | CP-C75-CAV-CHEM-HPR |  |  |  | R1 | A. Mitchel | G. Ciovati | K. Macha |  | 2020-02-01
Traveler | C75 Cavity Flange Final Lapping Traveler | C75-CAV-CHEM-FLAP |  |  |  | R1 | A. Wildeson | A. Mitchell | K. Macha |  | 2019-05-17
Procedure | C75 Cavity flange lapping procedure. | CP-C75-CAV-CHEM-FLAP |  |  |  | R1 | A. Wildeson | A. Mitchell | G. Ciovati |  | 2020-06-01
Traveler | Dog Leg Flange Lapping Traveler | C75-CAV-LAP-DGLG |  |  |  | R1 | A. Wildeson | A. Mitchell | K. Macha |  | 2019-10-30
Traveler | Field Probe Flange Lapping Traveler | C75-CAV-LAP-FPFT |  |  |  | R1 | A. Wildeson | A. Mitchell | K. Macha |  | 2019-10-30
Traveler | End Dish Flange Lapping Traveler | C75-CAV-LAP-ENDD |  |  |  | R1 | A. Wildeson | A. Mitchell | K. Macha |  | 2019-10-30
Traveler | Inner Adapter Flange Lapping Traveler | C75-CAV-LAP-INAD |  |  |  | R1 | A. Wildeson | A. Mitchell | K. Macha |  | 2019-10-30
Traveler | Warm Window Assembly Lapping Traveler | C75-CAV-LAP-WIN |  |  |  | R1 | A. Wildeson | A. Mitchell | K. Macha |  | 2019-11-06
Traveler | Warm Window Lapping Traveler | C75-CAV-LAP-WINW |  |  |  | R1 | A. Wildeson | A. Mitchell | K. Macha |  | 2019-11-06
Procedure | C75 Components flange lapping procedure. | CP-C75-CPR-LAP-COMP |  |  |  | R1 | A. Wildeson | A. Mitchell | K. Macha |  | 2020-06-01
Procedure | C75 Flange BCP Procedure | CP-C75-CAV-CHEM-BCPFL |  |  |  | R1 | A. Mitchell | G. Ciovati | K. Macha |  | 2020-08-11
Procedure | Baking in nitrogen oven | CP-STP-CAV-CHEM-BAKE |  |  |  | R1 | G. Gross | A. Mitchell | K. Macha |  | 2020-06-01 |  |  |  |  | Working on this
Procedure | C75 Field Probe Degreasing Procedure | CP-C75-CPR-DEGR-FPFT |  |  |  | R1 | G. Gross | A. Mitchell | K. Macha |  | 2020-06-01
Procedure | C75 Gate Valve Degreasing | CP-C75-CPR-DEGR-GV15 |  |  |  | R1 | G. Gross | A. Mitchell | K. Macha |  | 2020-05-04
Procedure | C75 HOM Load Degreasing Procedure | CP-C75-CPR-CHEM-DEGR-HOML |  |  |  | R1 | G. Gross | A. Mitchell | K. Macha |  | 2020-06-01
Procedure | C75 BCP Weld-prep etch | CP-C75-CAV-BCP-COMP-R1 |  |  |  | R1 | G. Ciovati | R. Geng | K. Macha |  | 2018-03-16
Procedure | Acid Etch rate measurement | CP-C75-CAV-BCP-ER |  |  |  | R1 | G. Ciovati | J. Follkie | K. Macha |  | 2017-12-08
Procedure | C75 Cavity Pair HPR Procedure | CP-C75-CPR-CHEM-HPR |  |  |  | R1 | A. Mitchel | G. Ciovati | K. Macha |  | 2020-02-19
Procedure | C75 Waveguide Extensions/ Adapter | CP-C75-CM-CHEM-CUPL |  |  |  | R1 | A. Wildeson | G. Ciovati | K. Macha |  | 2020-06-01 |  |  |  |  | Long Copper plated waveguide. Let Kurt know how you title.
Procedure | VAT 01 gate valve cleaning procedure | CP-C75-CPR-CHEM-VAT |  |  |  | R1 | A. Wildeson | G. Ciovati | K. Macha | [6 empty] | Consult John on rework of old valve or do we replace with new?
Procedure | C75 HEP procedure | CP-CAV-CHEM-HEP |  |  |  | R1 | Follkie | Reilly | K. Macha |  | 2020-10-20 |  |  |  |  | Ask Ashley if this is needed?
Procedure | C75 UHV parts cleaning procedure | CP-STP-CAV-CHEM-DEGR |  |  |  | R1 | A. Mitchel | J. Follkie | K. Macha | [6 empty] | Locate and verify good
Procedure | C75 Dogleg Chemisty & Degreasing | CP-C75-CPR-CHEM-DGLG |  |  |  | R1 | A. Mitchel | G. Ciovati | K. Macha |  | 2020-10-27
Procedure | Warm Window Degreasing | CP-C75-CPR-CHEM-WIND |  |  |  | R1 | A. Wildeson | G. Ciovati | K. Macha |  | 2020-06-01
Traveler | C75 HOM Elbow Lapping Procedure | C75-CHEM-HOME-LAP |  |  |  | R1 | A. Wildeson | G. Ciovati | K. Macha |  | 2020-09-22
Procedure | C75 End Dish acid etching Procedure | CP-C75-CHEM-ENDD |  |  |  | R2 | G. Gross | A. Mitchell | K. Macha |  | 2020-09-15
Procedure | C75 Elbow buffered chemistry polish Procedure | CP-C75-CPR-BCP-HOME |  |  |  | R1 | G. Gross | A. Mitchell | K. Macha |  | 2020-06-01 |  |  |  |  | Need pictures
Traveler | C75 Pair Components Preparation | C75-CHEM-COMP-DEGR |  |  |  | R2 | A. Mitchel | G. Ciovati | K. Macha |  | 2020-10-13
Assembly
Traveler | 5-Cell Cavity assembly for VTA test | C75-CAV-ASSY |  |  |  | R1 | C. Dreyfuss | G. Ciovati | K. Macha |  | 2020-09-28
Procedure | 5 Cell Single Cavity Assembly | CP-C75-CAV-ASSY |  |  |  | R1 | C. Dreyfuss | G. Ciovati | K. Macha |  | 2020-09-28
Traveler | C75 5-cell transfer to test stand | C75-CLNRM-CAV-TSTD |  |  |  | R1 | C. Dreyfuss | G. Ciovati | K. Macha |  | 2020-06-01
Procedure | Slow pump procedure | C75-STD-SLOW-PUMP |  |  |  | R1 | C. Dreyfuss | G. Ciovati | K. Macha
Procedure | C75 Cavity Cage Install | CP-C75-CAV-ASSY-CAGE |  |  |  | R1 | C. Dreyfuss | G. Ciovati | K. Macha |  | 2020-06-01
Traveler | Warm Cavity RF Tuning | C75-CAV-TUNE |  |  |  | R2 | G. Ciovati | D. Forehand | K. Macha |  | 2019-05-20
Procedure | RF Tuning procedure | CP-C75-CAV-TUNE | [6 empty] | K. Macha | [6 empty] | Roland to work on this procedure 80%
Traveler | Warm Window Brazed Assembly | C75-CU-BRAZ-WINW |  |  |  | R1 | S. Williams | F. Maurhauser | K. Macha |  | 2018-08-20 |  | scott
Traveler | Dogleg Assembly | C75-CPR-ASSY-DGLG |  |  |  | R2 | S. Williams | A. DeKerlegand | K. Macha |  | 2020-05-05
Procedure | C75 Parts Grinding | CP-C75-CAV-POL |  |  |  | R1 | A. Polczewski | S. Williams |  |  | 2018-01-31
Traveler | Dogleg Ceramic/Eyelet Window Subassembly | C75-CPR-ASSY-WNCR |  |  |  | R2 | S. Williams | A. DeKerlegand | K. Macha |  | 2018-04-10
Traveler | C75 Cavity Heattreat | C75-CAV-HEAT |  |  |  | R1 | G. Ciovati | D. Forehand | K. Macha |  | 2018-07-26
Traveler | C75 HOM Load Brazing/ Assy | C75-CAV-BRAZ-HOML |  |  |  | R1 | S. Williams | J. Guo | K. Macha |  | 2020-05-05
Cavity Pair
Assembly
Traveler | Pair Assembly - Cavity Evacuation and Leak Test | C75-CPR-ASSY-EVAC |  |  |  | R1 | C. Dreyfus | G. Ciovati | K. Macha |  | 2020-06-01 | forehand,macha,kdavis,gciovati | FOREHAND,kdavis,gciovati | macha
Traveler | End Dish and MDC valve sub-assembly | C75-CLNRM-ENDD-ASSY |  |  |  | R1 | C. Dreyfus | G. Ciovati | K. Macha |  | 2020-09-04
Procedure | C75 Gate valve assembly procedure | CP-C75-CPR-?? |  |  |  | R1 | C. Dreyfuss | D. Forehand | K. Macha
Procedure | C75 End dish Alignment procedure | CP-C75-CPR-ALIGN-ENDD |  |  |  | R1 | C. Dreyfuss | D. Forehand | K. Macha
Traveler | Pair Assembly | C75-CPR-ASSY-FNAL |  |  |  | R2 | C. Dreyfuss | D. Forehand | K. Macha |  | 2020-11-30 | forehand,macha,kdavis,gciovati | FOREHAND,kdavis,gciovati | macha |  | In Approval
Procedure | C75 Pair Assembly Procedure | CP-C75-CPR-ASSY |  |  |  | R1 | C. Dreyfuss | G. Ciovati | K. Macha |  | 2020-10-06 |  |  |  |  | In Review within Danny's Group
Procedure | C75 Ionized Nitrongen Component Cleaning Procedure | CP-C75-CPR-CLN-ION |  |  |  | R1 | D. Forehand | C. Dreyfuss | K. Macha |  | 2020-02-22
Procedure | C75 Indium Pressing Procedure | CP-C75-CPR-ASSY-INPP |  |  |  | R1 | C. Dreyfuss | D. Forehand | K. Macha |  | 2020-09-01
Procedure | Indium wire Cleaning | CP-C75-CPR-CLN-INWC |  |  |  | R1 | C. Dreyfuss | D. Forehand | K. Macha |  | 2020-04-27 |  |  |  |  | Possible revision to reflect assembly time after cleaning
Procedure | Cavity Pair Strongback setup procedure | CP-C75-CPR-ASSY-STBK |  |  |  | R1 | C. Dreyfuss | D. Forehand | K. Macha |  | 2020-10-20
Procedure | C75 Cavity Pair Magnetic Hygiene Procedure | CP-C75-CPR-HYG-COMP |  |  |  | R1 | G. Cheng | G. Ciovati | K. Macha |  | 2020-06-24
Procedure | C75 Inner adapter size/ prep | CP-C75-CPR-FAB-INPP |  |  |  | R1 | C. Dreyfuss | D. Forehand | K. Macha |  | 2020-10-30 |  |  |  |  | In approval, Kirk and Tony
Traveler | Pair Assembly Stack up | C75-CPR-ASSY-STKU |  |  |  | R1 | D. Forehand | G. Ciovati | K. Macha |  |  | forehand,macha,kdavis,gciovati | FOREHAND,kdavis,gciovati | macha |  | Danny wants to revise
Procedure | C75 Stackup procedure? | CP-C75-ASSY-STKP |  |  |  |  | D. Forehand | G. Ciovati | K. Macha
Traveler | Pair Warm Dewar Leak Test | C75-VTA-CPR-LEAKW |  |  |  | R1 | G. Ciovati | D. Forehand | K. Macha |  | 2020-08-25 | forehand,macha,kdavis,gciovati | FOREHAND,kdavis,gciovati | macha
Traveler | C75 cavity pair desorption leak test | C75-VTA-CPR-LEAKD |  |  |  | R1 | G. Ciovati | D. Forehand | K. Macha |  | 2020-08-25
Traveler | Pair Assembly Preparation for Turnover | C75-CPR-ASSY-TOVR |  |  |  | R1 | D. Forehand | G. Ciovati | K. Macha |  |  | forehand,macha,kdavis,gciovati | FOREHAND,kdavis,gciovati | macha |  | What's the deal here? In Pansophy but not being used.
Traveler | Pair Assembly Transfer to Test Stand | C75-CLNRM-CAV-TSTD |  |  |  | R1 | D. Forehand | G. Ciovati | K. Macha |  | 2020-10-29 | forehand,macha,kdavis,gciovati | FOREHAND,kdavis,gciovati | macha
Traveler | Leak check of C75 dogleg | C75-CPR-DGLG-LEAK |  |  |  | R1 | G. Ciovati | D. Forehand | K. Macha |  | 2020-08-25
Testing
Traveler | Cavity and Cavity Pair VTA Cooldown | C75-CPR-VTA-COOL |  |  |  | R1 | P. Kushnick | G. Ciovati | K. Macha |  | 2019-05-21 |  | kdavis,gciovati
Procedure | C75 cavity/ pair cooldown | CP-C75-VTA-COOL
Traveler | Cavities VTA RF Test | C75-CPR-VTRF |  |  |  | R3 | G. Ciovati | F. Marhauser | K. Macha |  | 2020-09-15 |  | kdavis,gciovati
Procedure | RF testing of C75 cavities in the VTA | CP-C75-CRP-VTRF |  |  |  | R1 | G. Ciovati | K. Davis | K. Macha |  | 2020-09-01
Procedure | C75 Cavity Testing Using VTA RF Test Stand | CP-STP-CAV-VTA-OPS |  |  |  | R1 | C. Wilson | G. Ciovati |  |  | 2019-07-15
Inspection
Traveler | C75 Cavity Pair Inspection | C75-CPR-INSP |  |  |  | R2 | A. DeKerlegand | G. Ciovati | K. Macha |  | 2020-04-28
Cryounit
Inspection
Traveler | Waveguide Extension Inspection | C75-CU-INSP-WGDX |  |  |  | R2 | A. DeKerlegand | J. Fischer | K. Macha |  | 2017-10-31 |  | fischer
Traveler | Warm Window Assembly Dimensional Inspection | C75-CU-INSP-WIN |  |  |  | R2 | A. DeKerlegand | J. Fischer | K. Macha |  | 2017-10-31 |  | fischer
Traveler | Warm Window Inspection | C75-CU-INSP-WINW |  |  |  | R2 | A. DeKerlegand | J. Fischer | K. Macha |  | 2017-10-31 |  | fischer
Assembly
Traveler | Tuner Assembly | C75-CMACU-TUNE-ASSY |  |  |  | R1 | J. Fischer | K. Worland | K. Macha |  | 2020-04-21
Procedure | C50 Ball Screw Drive Assembly Rebuild Procedure | CP-C75-CU-RWRK-CTUN |  |  |  | R1 | J. Fischer | L. Page | K. Macha |  | 2020-05-19
Procedure | C75 Rotary Feed Thru Rebuilding | CP-C75-CU-RWRK-RTFT |  |  |  | R1 | J. Fischer | K. Worland | K. Macha |  | 2020-05-19
Procedure | C75 Warm Tuning Procedure | CP-C75-CU-TUNE-TUNC |  |  |  | R2 | J. Fischer | G. Ciovati | K. Macha |  | 2020-10-20 |  |  |  |  | In approval
Traveler | Helium Vessel Assembly | C75-CMACU-HELV-ASSY |  |  |  | R1 | J. Fischer | K. Worland | K. Macha |  | 2020-06-01
Procedure | CEBAF CM Rotary feedthru replacement | CP-C75-CU-RWRK-FTRT |  |  |  | R1 | J. Fischer | K. Worland | K. Macha |  | 2020-04-23
Traveler | Vacuum Vessel Assembly | C75-CU-ASSY-VV |  |  |  | R1 | J. Fischer | K. Worland | K. Macha |  | 2020-07-01 |  |  |  |  | Mostly written from C50, Needs revision
Traveler | Waveguide Assembly | C75-CU-ASSY-WG |  |  |  | R1 | J. Fischer | G. Ciovati | K. Macha |  | 2020-07-01 |  |  |  |  | Mostly written from C50, Needs revision
Procedure | Cryomodule Beam Line Pumping procedure | CP-C75-CM-BPIP-PUMPSL |  |  |  | R1 | C. Wilcox | J. Fischer | K. Macha |  | 2020-05-26
Procedure | Crymodule MLI Installation Procedure | CP-C75-CM-INST-MLI |  |  |  | R1 | J. Fischer | K. Worland | K. Macha |  | 2020-06-09
Procedure | Activation of C75 FPC waveguide NEXTorr pump | CP-C75-CM-EVAC-NEG |  |  |  | R1 | G. Ciovati | J. Fischer | K. Macha |  | 2020-04-09
Procedure | Cryomodule Magnetic Hygiene Procedure | CP-C75-CM-MAG-HYG |  |  |  | R1 | G. Cheng | J. Fischer | K. Macha
Procedure | Beam line assembly procedure | [5 empty] | C. Wilcox | J. Fischer
Procedure | JT calibration procedure | CP-STP |  |  |  |  | K. Worland | J. Fischer
Traveler | Bridging bellows |  |  |  |  | R1 | C. Wilcox | J. Fischer | K. Macha | [6 empty] | Ready for approval, John where is this?
Traveler | Return end can beam pipe assembly | C75-CMA-RTBP-ASSY |  |  |  | R1 | C. Wilcox | J. Fischer | K. Macha |  | 2020-10-29
Traveler | Supply end can beam pipe assembly | C75-CMA-SUPBP-ASSY |  |  |  | R1 | C. Wilcox | J. Fischer | K. Macha | [6 empty] | Ready for approval, John where is this?
Traveler | Supply end can pump drop assembly |  |  |  |  | R1 | C. Wilcox | J. Fischer | K. Macha
Cryomodule
Inspection
Traveler | Inspection of C75 Cryomodule Cavity Magnetic Shield Assembly | C75-CM-INSP-CMAG |  |  |  | R1 | G. Cheng | A. DeKerlegand | K. Macha |  | 2018-08-24 |  | cheng,fischer
Traveler | End Can Rework | C75-CM-ASSY-ECRW |  |  |  |  | J. Fischer | K. Worland | K. Macha |  | 2020-08-01
Traveler | Cryomodule Assembly | C75-CM-ASSY |  |  |  | R1 | J. Fischer | K. Worland | K. Macha |  | 2020-08-01
Traveler | Cryomodule Acceptance Test | C75-CM-CMTF-ACTS |  |  |  |  | M. Drury |  | K. Macha |  | 2020-09-01
Other
Traveler | Weld Qualification Record | C75-EBW-CERT |  |  |  | R1 | W. Clemens | G. Ciovati | K. Macha |  | 2017-08-22
|  | C75-CM-ACTS-PREP |  |  |  |  | M. Drury | A. |  |  |  | drury | drury,shabalin | macha,gciovati
C75-CM-ACTS
[12 empty] | fischer,gciovati,cheng | fischer,worland,jjcamp,macha | areilly,cheng
| Rework Procedures that may not apply? | [10 empty] | fischer,gciovati,cheng | fischer,worland,jjcamp,macha | areilly,cheng
Procedure | C50 End Dish Backing Flange Replacement | CP-C75-CRP-RPB |  |  |  | R1 | Forehand | Dreyfuss |  |  |  | fischer,gciovati,cheng | fischer,worland,jjcamp,macha | areilly,cheng
Procedure | C50 Cavity Pair End Dish Replacement Procedure | CP-C75-CRP-RPE |  |  |  | R1 | Forehand | Dreyfuss |  |  |  | fischer,gciovati,cheng | fischer,worland,jjcamp,macha | areilly,cheng
Procedure | C50 Field Probe Replacement for Assembled Cavity Pairs | CP-C75-CRP-RPF |  |  |  | R1 | Forehand | Dreyfuss
Procedure | C50 Gate Valve Replacement for Assembled Cavity Pairs | CP-C75-CRP-RPV |  |  |  | R1 | Forehand | Dreyfuss |  |  |  | fischer,gciovati,cheng | fischer,worland,jjcamp,macha | areilly,cheng

## TravChart
| Due/mo | Done/mo | Open (Cumulative) | Completed (Cumulative)
2017-08-17 | 0 | 0 | 0 | 0
2017-09-17 | 0 | 0 | 0 | 0
2017-10-17 | 0 | 0 | 0 | 0
2017-11-17 | 0 | 0 | 0 | 0
2017-12-17 | 0 | 0 | 0 | 0
2018-01-17 | 0 | 0 | 0 | 0
2018-02-17 | 0 | 0 | 0 | 0
2018-03-17 | 0 | 0 | 0 | 0
0

## Procedures
Procedure Title | Procedure ID | Assigned Author | Technical Reviewer | REV | Date for Draft Doc. | Approval/ PDF Upload Date | Draft uploaded to DS / signed | Final uploaded to DS / released | Comments:
Chemistry
C75 BCP Acid Etching at the Chemical Fume Hood procedure | CP-C75-BCP | T. Harris | A. Mitchel | R1-0 |  |  |  |  | Not seen in Docushare
C75 Cavity De-greasing | CP-C75-CAV-DEGR | T. Harris | A. Mitchel | R1-0 |  |  |  |  | Not seen in Docushare
C75 Cavity HPR Procedure | CP-C75-CAV-HPR | A. Mitchel | G. Ciovati | R1-0 |  |  |  | 2020-02-19
C75 Cavity flange lapping procedure. | CP-C75-CAV-LAP | A. Wildeson | A. Mitchel | R1-0 |  |  |  | 2020-05-05
C75 Cavity Flange Etching Procedure | CP-C75-CHEM-FLG | T. Harris | A. Mitchel | R1-0 |  |  |  |  | Not seen in Docushare
C75 HOM Load and Gate Valve Baking Procedure | CP-C75-CPR-BAKE-COMP | T. Harris | A. Mitchel | R1-0 |  |  |  |  | Not seen in Docushare
C75 Field Probe Degreasing Procedure | CP-C75-CPR-DEGR-FPFT | A. Mitchel | A. Mitchel | R1-0 |  |  |  |  | Not seen in Docushare
C75 Gate Valve Degreasing | CP-C75-CPR-DEGR-GTVC | T. Harris | A. Mitchel | R1-0 |  |  |  |  | Not seen in Docushare
C75 HOM Load Degreasing Procedure | CP-C75-CPR-DEGR-HOM | T. Harris | A. Mitchel | R1-0 |  |  |  |  | Not seen in Docushare
C75 Components flange lapping procedure. | CP-C75-CPR-LAP-COMP | A. Wildeson | A. Mitchel | R1-0 |  |  |  | 2020-05-05 | Not seen in Docushare
C75 BCP Weld-prep etch | CP-C75-CAV-BCP-COMP-R1 | G. Ciovati | R. Geng | R1-0 |  |  |  | 2018-03-16
Acid Etch rate measurement | CP-C75-CAV-BCP-ER | G. Ciovati | J. Follkie | R1-0 |  |  |  | 2017-12-08
C75 Cavity Pair HPR Procedure | CP-C75-CPR-CHEM-HPR | A. Mitchel | G. Ciovati | R1-0 |  |  |  | 2020-02-19
C75 Parts Grinding | CP-C75-CAV-POL | A. Polczewski | S. Williams | R1-0 |  |  |  | 2018-01-31
CR Assembly
C75 Ionized Nitrongen Component Cleaning Procedure | CP-C75-CPR-CLN-COMP | C. Dreyfuss | D. Forehand | [5 empty] | IN PROGRESS - AWAITING APPROVAL
Ionized Nitrogen Parts Cleaning | CP-C75-CST-ION-CLN | D. Forehand | G. Ciovati | R1-0 |  |  |  |  | Is this needed or are we using the one above?
C75 Indium Pressing Procedure | CP-C75-CPR-FAB-INPP | C. Dreyfuss | D. Forehand | R1-0 |  |  |  |  | IN PROGRESS - AWAITING APPROVAL
C75 Indium Wire Cleaning Procedure | CP-C75-CPR-CLN-INWC | C. Dreyfuss | D. Forehand | R1-0 |  |  |  |  | IN PROGRESS - AWAITING APPROVAL
C75 End dish Sub-assembly procedure | CP-C75-CPR-ALIGN-ENDD | C. Dreyfuss | D. Forehand | R1-0 |  |  |  | 2020-04-21 | IN PROGRESS - AWAITING APPROVAL
C75 End dish Sub-assembly procedure | CP-C75-CPR-?? | C. Dreyfuss | D. Forehand | R1-0 |  |  |  | 2020-04-21
C75 Gate valve assembly procedure | CP-C75-CPR-?? | C. Dreyfuss | D. Forehand |  |  |  |  | 2020-04-21
C75 Strongback tooling setup | CP-C75-CPR-??
C75 FPC and FP Qext Calibration | CP-C75-CAV-TUNE-QEXT | D. Forehand | H. Wang
C75 Cage setup procedure | CP-C75-CHEM-CAGE | C. Dreyfuss | D. Forehand | R1-0 |  |  |  | 2020-04-28 | Close
C75 End dish surface repair/ prep |  |  |  | R1-0
C75 Inner adapter size/ prep
C75 Stackup procedure?
C75 Half-Cell and tube forming | CP-C75-CAV-FAB-HCEL | G. Ciovati | S. Williams | R1-0 |  |  |  | 2017-10-24
C75 Dumb-Bell and end half cells RF inspection | CP-C75-CAV-RFIN | G. Ciovati | F. Marhauser | R2-0 |  |  |  | 2018-06-11
C75 Cavity Pair Magnetic Hygiene Procedure | CP-C75-CPR-??? | G. Cheng | G. Ciovati |  |  |  |  | 2020-04-21
C75 Cav Tune
VTA RF
C75 Cavity Pair Vertical Test Procedure | CP-C75-CRP-VTRF | C. Wilson | G. Ciovati | R1-0 |  |  |  |  | Follow-up with who owns and when
C75 cavity/ pair cooldown?
C75 Cavity Testing Using VTA RF Test Stand | CP-STP-CAV-VTA-OPS | C. Wilson | G. Ciovati | R2-0 |  |  |  | 2019-07-15
Cryomodule assembly
C50 Ball Screw Drive Assembly Rebuild Procedure | CP-C75-CU-RWRK-CTUN | J. Fischer | K Macha | R1-0 |  |  |  | 2020-04-23 | IN PROGRESS - AWAITING APPROVAL
C75 Rotary Feed Thru Rebuilding | CP-C75-CU-RWRK-FTFT | J. Fischer | K Macha | R1-0 |  |  |  | 2020-04-23 | IN PROGRESS - AWAITING APPROVAL
C75 Warm Tuning Procedure | CP-C75-CU-TUNE-TUNC | J. Fischer | G. Ciovati | R1-0 |  |  |  | 2020-04-29
C75 HEP procedure | CP-C75-HEP-CAV | Follkie | Reilly | R1-0 |  |  |  |  | Not seen in Docushare Move to Chem
C75 UHV parts cleaning procedure | CP-C75-UHVC | Castagnola | Reilly | R1-0 |  |  |  |  | Not seen in Docushare Move to Chem
CEBAF CM Rotary feedthru replacement | CP-CEBA-REPL-RTFT | J. Fischer | K. Worland | R1-0
SLOW PUMP-DOWN CAVITY EVACUATION PROCEDURE | CP-STP-CM-EVAC | C. Wilcox | J. Fischer | R1-0 |  |  |  | 2020-05-05
Crymodule MLI Installation Procedure | CP-C75-CM-MLI-INST | J. Fischer | K. Worland | R1-0 |  |  |  | 2020-05-05
Waveguide Neg pump start up | CP-C75-CM-NEG-STRT | G. Ciovati | J. Fischer | R1-0 |  |  |  | 2020-05-05
Cryomodule Magnetic Hygiene Procedure | CP-C75-CM-MAG-HYG | G. Cheng | J. Fischer | R1-0
Clean and assembly of warm waveguide | [8 empty] | Parts need cleaning procedure
VAT 01 gate valve cleaning procedure | [8 empty] | C75 brand new valves, blow down only in CR
Rework Procedures that may not apply?
C50 End Dish Backing Flange Replacement | CP-C75-CRP-RPB | Forehand | Dreyfuss | R1-0
C50 Cavity Pair End Dish Replacement Procedure | CP-C75-CRP-RPE | Forehand | Dreyfuss | R1-0
C50 Field Probe Replacement for Assembled Cavity Pairs | CP-C75-CRP-RPF | Forehand | Dreyfuss | R1-0
C50 Gate Valve Replacement for Assembled Cavity Pairs | CP-C75-CRP-RPV | Forehand | Dreyfuss | R1-0

## ProcChart
| Due/mo | Done/mo | Open (Cumulative) | Completed (Cumulative)
2017-08-17 | 0 | 0 | 0 | 0
2017-09-17 | 0 | 0 | 0 | 0
2017-10-17 | 0 | 0 | 0 | 0
2017-11-17 | 0 | 0 | 0 | 0
2017-12-17 | 0 | 0 | 0 | 0
2018-01-17 | 0 | 0 | 0 | 0
2018-02-17 | 0 | 0 | 0 | 0
2018-03-17 | 0 | 0 | 0 | 0

## Legacy_Procedures
Procedure Title/Hyperlink | Location in Docushare | Author | Technical Reviewer | PM or Designee | Comment
2K Desorption Leak Test | Draft Assembly Procedures - Cavity Production | Overton | Forehand | Macha
Baking Of HOM Loads | Draft Chemistry Procedures - Cavity Production | Castagnola | Reilly | Reilly
BCP Etch of Inner Adapter | Draft Chemistry Procedures - Cavity Production | Castagnola | Reilly | Reilly
BCP of HOM Elbow | Draft Chemistry Procedures - Cavity Production | Castagnola | Reilly | Reilly
C 50 Component Lapping LM 36 | Draft Assembly Procedures - Cavity Production | Daniels | Castagnola | Reilly
C50 5 cell first assembly | C50 included procedures | Forehand | Castagnola | Macha
C50 5 cell second assembly | C50 included procedures | Forehand | Castagnola | Macha
C50 Ball Scew Drive Rebuild Procedure | Cryomodule Refurbishment - C50 CM # 1-10 only | McCrea | Worland | Fischer
C50 Cavity Evacuation Procedure | C50 included procedures | Forehand | Castagnola | Macha
C50 Cavity Pair Assembly Fixture/Assembly Procedure | Cryomodule Refurbishment - C50 CM # 1-10 only, | Carpenter | Williams | Macha
C50 Cavity Straightening Procedure | Procedures | Carpenter | Williams | Reilly
C50 Cavity Tuning Procedure - unwritten ? | Procedure Drafts | Forehand | Haipeng | Davis | Incorporated in Traveler
C50 COMPONENT LAPPING PROCEDURE - duplicate ? | Draft Assembly SOPs - Cavity Production | Daniels | Castagnola | Reilly
C50 Component Lapping Procedure Manual method | Draft Chemistry Procedures - Cavity Production | Daniels | Castagnola | Reilly
C50 Component Lapping Procedure Manual method - duplicate ? | Draft Chemistry Procedures - Cavity Production | Daniels | Castagnola | Reilly
C50 End Dish Backing Flange Replacement for Assembled Cavity Pairs | Approved Assembly Procedures - Cavity Production | Macha | Dreyfuss | Forehand
C50 End Dish Replacement Procedure for Assembled Cavity Pairs | Approved Assembly Procedures - Cavity Production | Macha | Dreyfuss | Forehand
C50 Field Probe Replacement for Assembled Cavity Pairs | Draft Assembly Procedures - Cavity Production | Dreyfuss | Macha | Castagnola
C50 Field Probe Replacement Procedure for Assembled Cavity Pairs | Approved Assembly Procedures - Cavity Production | Macha | Dreyfuss | Forehand
C-50 five cell cavity removal from the HPR cabinet | Draft Chemistry Procedures - Cavity Production | Castagnola | Harris | Reilly
C50 Gate Valve Replacement for Assembled Cavity Pairs | Approved Assembly Procedures - Cavity Production | Macha | Dreyfuss | Forehand
C-50 Hardware | Draft Chemistry Procedures - Cavity Production | Castagnola | Reilly | Macha
C50 Qext Calibration Procedure(draft) | Procedure Drafts | Forehand | Haipeng | Davis
C50 Warm Tuning Procedure | Cryomodule Refurbishment - C50 CM # 1-10 only | McCrea | Worland | Fischer
C50_Cavity_Heat_Treatment_Procedure | Draft RF Procedures - Cavity Production | Forehand | Reilly | Reilly
CAVPR-5CELL-CAGE-ALGN-R1-0 | Draft Chemistry Procedures - Cavity Production | Castagnola | Reilly | Carpenter
CAVPR-5CELL-CHEM-R1-0 | Draft Chemistry Procedures - Cavity Production | Castagnola | Reilly | Reilly
CAVPR-5CELL-DEGR-R1-0 | Draft Chemistry Procedures - Cavity Production | Castagnola | Reilly | Reilly
CAVPR-5CELL-FLNG-INSP-R1-0 | Draft Chemistry Procedures - Cavity Production | Castagnola | Reilly | Reilly
CAVPR-5CELL-HPR1-R1-0 | Draft Chemistry Procedures - Cavity Production | Castagnola | Reilly | Reilly
CAVPR-5CELL-HPR2-R1-0 | Draft Chemistry Procedures - Cavity Production | Castagnola | Reilly | Reilly
CAVPR-5CELL-VTRF-R1-0 | Draft RF Procedures - Cavity Production | Stirbet | Reece | Davis
CAVPR-CPAIR-ASSY-R1-0 | Draft Assembly Procedures - Cavity Production | Forehand | Castagnola | Macha
CAVPR-CPAIR-CHEM-R1-0 | Draft Chemistry Procedures - Cavity Production | Castagnola | Reilly | Reilly
CAVPR-CPAIR-CHEM-R1-0 | Draft Chemistry Procedures - Cavity Production | Castagnola | Reilly | Reilly
CAVPR-CPAIR-DEGR-R1-0 | Draft Chemistry Procedures - Cavity Production | Castagnola | Reilly | Reilly
CAVPR-CPAIR-SUBC-CHEM-R1-0 | Draft Chemistry Procedures - Cavity Production | Castagnola | Reilly | Reilly
CAVPR-CPAIR-SUBC-CLN-R1-0 | Draft Chemistry Procedures - Cavity Production | Castagnola | Reilly | Reilly
CAVPR-SCREF-HDW-CLN-R1-0 | Draft Chemistry Procedures - Cavity Production | Castagnola | Reilly | Reilly
Cleaning and Transporting alignment fixture for cleanroom | Draft Assembly Procedures - Cavity Production | Forehand | Castagnola | Reilly
CP-C50-DGLG-VTRF | Draft RF Procedures - Cavity Production | Forehand | Haipeng | Davis
CP-C50-DGLG-WARM-RFCAL | Draft RF Procedures - Cavity Production | Forehand | Haipeng | Davis
CP-C50-DGLG-WARM-RFTST | Draft RF Procedures - Cavity Production | Forehand | Haipeng | Davis
CP-CEBAF-C50-RWRK-RFTU.docx | Final Procedures | McCrea | Worland | Fischer
Degreasing Burst Disk | Draft Chemistry Procedures - Cavity Production | Castagnola | Reilly | Reilly
Degreasing Ceramic Windows | Draft Chemistry Procedures - Cavity Production | Castagnola | Reilly | Reilly
Degreasing Field Probes | Draft Chemistry Procedures - Cavity Production | Castagnola | Reilly | Reilly
Degreasing of Cavity | Draft Chemistry Procedures - Cavity Production | Castagnola | Reilly | Reilly
Degreasing of Seals | Draft Chemistry Procedures - Cavity Production | Castagnola | Reilly | Reilly
Dogleg Performance Characterization | Dog Leg Windows | Forehand | Haipeng | Davis | Not a procedure
End Dish Etching | Draft Chemistry Procedures - Cavity Production | Castagnola | Reilly | Reilly
Garment cleaning return invoice | Draft Chemistry Procedures - Cavity Production | Castagnola |  |  | Not a procedure
Lapping Niobium Flanges | Draft Chemistry Procedures - Cavity Production | Daniels | Castagnola | Reilly
Pressing Niobium eyelets for C50 Doglegs | Procedures | Williams | Castagnola | Reilly
Procedure for Preparing Niobium Flanges for Assembly of C50 Cavity Pairs | Cavity Pair Preparation - Before Assembly | Daniels | Castagnola | Reilly
Second HPR 5-cell | Draft Chemistry Procedures - Cavity Production | Castagnola | Reilly | Reilly | Seems duplicate to CAVPR-5CELL-HPR2-R1-0
Waveguide Pressing Procedure | Waveguide Pressing Procedure for C-50 Doglegs | Williams