## C75 EG
| Issue | Proposed Action | responsibility | Date initiated | Date complete
C20 | No formal procedure for SN configuration to use, or what to do when the cavity has new end groups (example C75-04) | Two choices - either add to Traveler or create a Procedure If adding to Traveler need to confirm SN for end groups (EG-RI-XXX or EG-CEBAF-XXX or EG-New, where XXX is the cavity number) (or if this does not work create a procedure ? | Aaron
| End Group SN are being recorded in C20 not being transferred to C75 | Need to find way to transfer SN from C20 to C75 ? | Pansophy ?
| No record in shipping documents for End Group SN shipped to RI (is only in emails) | Propose to add copy of list from email to shipping documents ? | SOTR/ Shipping /Inventory ?
C75-01 | Check with RI to see if they track End Group SNs | Ask RI if they have a list of which end groups went on which cavities ADDENDUM: 22Feb2021, RI responded , do not track end group SN (not in contract) | Gigi | 2021-02-17 | 2021-02-22
| SN of End Groups not required in Inspection Travelers - cavities already in Cryo units, no longer available, Gigi said he has a list of SN | Gigi said he has a list of all end groups for C75-01 (We just don't know which cavities they went on) To satisfy Pressure vessel code, if Gigi provides the complete list of SN for C75-01, the list could be up loaded in all Cavity inspection travelers for C75-01 (Cavity Inspection travelers need to be re-opened) | Gigi/Pansophy/Aaron | 2021-02-17
C75-02 | SN not available in dropdowns at the time of inspection, however photos were taken of all SN and up loaded to the traveler - therefore we have a record in the traveler | Decision needed : Pressure vessel code requirement was satisfied with photos of SN However for consistency would be better to reopen the travelers and enter all SNs ?? | SOTR/Project | 2021-02-17
|  | Pansophy to delete unused SN, | Pansophy | 2021-02-17 | 2021-02-18
|  | Pansophy to check for inconsistencies in remaining SNs (preferred would have been to correct the SN to EG-IA-XXX, however this may not be possible ) | Pansophy | 2021-02-17
|  | Assuming remaining SN are checked and are OK, then reopen C75-02 Cav Insp Travelers | Pansophy
|  | Assuming Travelers are reopened update SN Entries to match photos , add a comment to clarify where SN in drop down is unclear | Aaron
C75-03 | End Groups inspected using C20 Travelers and end groups have been shipped to RI - is all needed information available in the drop downs ? | is all needed information from C20 available in the drop downs for C75 ? | Pansophy ?
C75-04 | Will use new cavities with new End groups made by RI | add to drop down SNs Example "New-EG" ? for the case where there is a new End Group , otherwise it would appear to have been missed | Pansophy

## Other internal SN Issues
| Issue | Proposed Action | responsibility | Date initiated | Date complete
Other Topics | Inventory vs Pansophy responsibilities ? | TBD
| Other C20 part SN ( elbows, end dishes etc. ?) | TBD
| New SN for HE R&D Cavities ? | TBD