## TRAVELERS
| Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | Author | Reviewer | Reviewer | Project Manager | SOTR | NCR Informative | NCR Dispositioners | D3 Emails | Procedure(s), Name (if known) | Drawing(s), Name (if known) | Acronym from INV | Notes | Status | Section
Cavity Preparation
Inspection
| Helium Vessel Inspection | L2HE-INSP-CAV |  | 2021-08-01 |  |  |  | Hogan | [6 empty] | CAV
| Cavity RF Inspection | L2HE-TUNE-CAV-RFIN |  | 2021-08-01 |  |  |  | Hogan | [6 empty] | CAV | Cavities arrive in Aug2021 per KW
| Chemistry | [16 empty] | SS
| Processing | [16 empty] | SS
| Cavity Heat Treatment & Nitrogen Doping | L2HE-CAV-ASSY-HEAT | [5 empty] | Hogan
| Cavity HOM Measurements and Tuning | L2HE-CAV-HOM-TUNE |  | 2021-08-01 |  |  |  | Hogan
| Assembly | [16 empty] | SS
| Cavity 1st Assembly | L2HE-CAV-ASSY-FRST |  | 2021-08-01 | Forehand | Davis |  | Hogan
| Cavity 2nd Assembly | L2HE-CAV-ASSY-SCND |  | 2021-08-01 | Forehand | Palczewski |  | Hogan
| Cavity Evacuation & Leak Test | L2HE-CAV-ASSY-LEAK |  | 2021-08-01 | Forehand | Palczewski |  | Hogan
| Transfer of L2PRD 9-cell cavities to Test Stands | L2HE-CLNRM-CAV-TSTD |  | 2021-08-01 | Forehand | Davis |  | Hogan
| Transfer of L2PRD 9-cell cavities to Test Stands for Dewar 5 | L2HE-CLNRM-CAV-TSTD-D5 |  | 2021-08-01 | Forehand | Davis |  | Hogan
| Testing | [16 empty] | SS
| Cavity Cooldown | L2HE-VTA-CAV-COOL |  | 2021-09-01 | Kent? | Ari |  | Hogan
| Cavity Production VTA HOM Survey | L2HE-VTA-CAV-HOM |  | 2021-08-01 | Stirbet | Ari |  | Hogan
| Cavity VTA Test | L2HE-CAV-VTRF |  | 2021-08-01 | Davis or Kent? | Ari |  | Hogan
| Component Prepreation | [16 empty] | SH
| Inspection | [16 empty] | SS
| FPC WARM PART | L2HE-INSP-FPCW |  | 2021-03-31 | Huque |  |  | Hogan | [5 empty] | 341081, P96394 | FPCW
| FPC COLD PART | L2HE-INSP-FPCC |  | 2021-03-31 | [9 empty] | 341082, P96406 | FPCC
CP | FPC Waveguide Inventory | L2HE-INV-FPCWG | R1 |  | Dickey | Barnes |  | Wilson |  | Wislon | Huque,Fischer | Huque,Fisher |  |  |  |  | CP
CP | FPC Waveguide Incoming Inspection | L2HE-INSP-FPCWG | R1 | 2021-10-15 | Huque | Stirbet |  | Hogan | Huque | [5 empty] | FPCWG |  | CP
CP | Cavity Field Probe Feedthru Receiving Inspection | L2HE-INSP-FPFT | R1 | 2020-10-16 | Park | DeKerlegand | N/A | Wilson | Park | Ari, Reece | Park, Wilson | Park, Wilson | No | GMM-9434A |  |  | CP
CP | Cavity HOM Feedthru Receiving Inspection | L2HE-INSP-HMFT | R1 | 2020-10-16 | Park | DeKerlegand | N/A | Wilson | Park | Ari, Reece | Park, Wilson | Park, Wilson | No | GMM-9433A |  |  | CP
| Cavity Beam Line Bellows PRCM | L2HE-INSP-BLBP |  | 2021-08-15 | Marchlik | DeKerlegand | Zhao | Hogan | Marchlik
| Cavity Beam Line Bellows Short | L2HE-INSP-BLBS |  | 2021-08-15 | Marchlik | DeKerlegand | Zhao | Hogan | Marchlik
| Cavity String Weldment Upstream Bellows | L2HE-INSP-BLBU |  | 2021-08-15 | Marchlik | DeKerlegand | Zhao | Hogan | Marchlik
| String Beam Line Extension Downstream | L2HE-INSP-BLXD |  | 2021-08-15 | Marchlik | DeKerlegand | Zhao | Hogan | Marchlik
15 | 300K Current Leads CF Flange Inspection | L2HE-INSP-CFL |  | 2021-03-01 | Lakshmi | King | Morrone | Hogan
| End Lever Tuner Mechanical Frame Inspection | L2HE-INSP-TUNMC |  | 2021-04-01 | Powen | DeKerlegand | Huque | Hogan | Powen | kwilson | Powen, Huque, georged | Powen, Huque, Wilson |  | F10132292-B, F10138922-A
| End Lever Tuner Motor | L2HE-INSP-TUNMT |  | 2021-04-01 | King | Powen | Huque | Hogan | Powen | huque,kwilson | Powen, King | Powen, Huque, Wilson |  |  |  | Will be a batch traveler
15 | Tuner Piezo Actuator Assembly Inspection | L2HE-INSP-TUNPZ |  | 2021-03-05 | King | Powen | Huque | Hogan | Powen | huque,kwilson | Powen, King | Powen, Huque, Wilson |  |  |  | Will be a batch traveler
| Quadrapole Magnet SPQA002 Inspection | L2HE-MAG-QUAD |  | 2021-04-15 | Lakshmi | King | Morrone | Hogan | Lakshmi |  | Lakshmi, Wilson | Lakshmi, Wilson
| Cryomodule Cool Down Cryogenic Valve (CDV) | L2HE-INSP-CDV |  | 2021-04-12 | Kent | Fischer | McEwen | Hogan | Kent | Katherine, Hogan | Kent, Wilson | Kent, Fischer
15 | Receiving Inspection CM Magnetic Shield Assembly | L2HE-INSP-IMAG | R1 | 2021-03-01 | Gary | DeKerlegand | Fischer | Hogan | Gary | Katherine, Hogan | Gary, Fischer | Gary, Fischer |  | F10048652
15 | Receiving Inspection CM Rod Invar 2-Phase Long | L2HE-INSP-IROD2L |  | 2021-03-01 | O'Brien |  |  | Hogan
15 | Receiving Inspection CM Rod Invar 2-Phase | L2HE-INSP-IROD2P |  | 2021-03-01 | Gary |  |  | Hogan
| Receiving Inspection CM Assembly, JT Cryogenic Valve | L2HE-INSP-JTV |  | 2021-04-12 | Kent | Fischer | McEwen | Hogan | Kent | Katherine, Hogan | Kent, Wilson | Kent, Fischer
| Receiving Inspection CM Assembly, JT Valve Tube Kit | L2HE-INSP-JTVTK |  | 2021-04-12 | Kent | Fischer | McEwen | Hogan | Kent | Katherine, Hogan | Kent, Wilson | Kent, Fischer
30 | Upper Cold Mass Inspection | L2HE-INSP-UCM | R1 | 2021-03-15 | Gary | DeKerlegand | N/A | Hogan | Gary | Katherine, Hogan | Gary, Fischer | Gary, Fischer |  | F10009954
30 | Upper Cold Mass Weld Inspection | L2HE-CWI-UCM | R1 | 2021-03-15 | Gary | Jenord | Fischer | Hogan | Gary | Katherine, Hogan | Gary, Fischer | Gary, Fischer |  | F10009954
30 | Upper Cold Mass CMA Inspection | L2HE-CMA-INSP-UCM | R1 | 2021-03-15 | Gary | Fischer | N/A | Hogan | Gary | Katherine, Hogan | Gary, Fischer | Gary, Fischer |  | F10009954
30 | Receiving Inspection CM Vacuum Vessel | L2HE-INSP-VV | R1 | 2021-03-15 | Gary | DeKerlegand | N/A | Hogan | Gary | Katherine, Hogan | Gary, Fischer | Gary, Fischer |  | F10026609
30 | Receiving CMA Inspection CM Vacuum Vessel | L2HE-CMA-INSP-VV | R1 | 2021-03-15 | Gary | Fischer | N/A | Hogan | Gary | Katherine, Hogan | Gary, Fischer | Gary, Fischer |  | F10026609
| Chemistry | [16 empty] | SS
| Cavity Cleaning / UltraSonic Cleaning | L2HE-CHEM-COMP-USC |  | 2021-08-01 | Mitchell | Wildeson | Palczewski | Hogan |  | ashleya | hogan,ari | ashleya,ari,hogan,kdavis,forehand
| First HPR | L2HE-CHEM-COMP-HPRN |  | 2021-08-01 | Mitchell | Wildeson | Palczewski | Hogan |  | ashleya | hogan,ari | ashleya,ari,hogan,kdavis,forehand
| Components Cleaning | L2HE-CHEM-COMP-DEGR |  | 2021-08-01 | Mitchell | Wildeson | Palczewski | Hogan |  | ashleya | hogan,ari | ashleya,ari,hogan,kdavis,forehand
| Laping | L2HE-CHEM-COMP-LAP |  | 2021-08-01 | Wildeson | Mitchell | Palczewski | Hogan |  | ashleya | hogan,ari | ashleya,ari,hogan,kdavis,forehand
| Weld Inspection | [16 empty] | SS
| Leak Checks | [16 empty] | SS
CP | Cavity Field Probe Feedthru Receiving Inspection | L2HE-CMA-FPFT-LEAK | R1 | 2020-10-21 | Park | Wilcox | N/A | Wilson | Park | Ari, Reece | Park, Wilson | Park, Wilson | Leak check spec 11141-S-0029 | GMM-9434A |  |  | CP
CP | Cavity HOM Feedthru Receiving Inspection | L2HE-CMA-HMFT-LEAK | R1 | 2020-10-21 | Park | Wilcox | N/A | Wilson | Park | Ari, Reece | Park, Wilson | Park, Wilson | Leak check spec 11141-S-0029 | GMM-9433A |  |  | CP
| Cavity Beam Line Bellows PRCM Leak Test | L2HE-CMA-BLBP-LEAK | R1 | 2021-08-15 | Marchlik | WIlcox | N/A | Wilson | Marchlik | Ari, Reece | Marchlik, Wilson | Marchlik, Wilson | Leak check spec 11141-S-0029 | F10041075
| Cavity Beam Line Bellows Short | L2HE-CMA-BLBS-LEAK | R1 | 2021-08-15 | Marchlik | WIlcox | N/A | Wilson | Marchlik | Ari, Reece | Marchlik, Wilson | Marchlik, Wilson | Leak check spec 11141-S-0029 | F10023437
| Cavity String Weldment Upstream Bellows | L2HE-CMA-BLBU-LEAK | R1 | 2021-08-15 | Marchlik | WIlcox | N/A | Wilson | Marchlik | Ari, Reece | Marchlik, Wilson | Marchlik, Wilson | Leak check spec 11141-S-0029 | F10075494
| String Beam Line Extension Downstream | L2HE-CMA-BLXD-LEAK | R1 | 2021-08-15 | Marchlik | WIlcox | N/A | Wilson | Marchlik | Ari, Reece | Marchlik, Wilson | Marchlik, Wilson | Leak check spec 11141-S-0029 | F10052775
| Cold Shock | [16 empty] | SS
CP | Cavity Field Probe Feedthru Receiving Inspection | L2HE-VTA-FPFT-CSHK | R1 | 2020-10-22 | Park | Forehand | Kent | Wilson | Park | Ari, Reece | Park, Wilson | Park, Wilson | No | GMM-9434A |  |  | CP
CP | Cavity HOM Feedthru Receiving Inspection | L2HE-VTA-HMFT-CSHK | R1 | 2020-10-23 | Park | Forehand | Kent | Wilson | Park | Ari, Reece | Park, Wilson | Park, Wilson | No | GMM-9433A |  |  | CP
| Cavity String | [16 empty] | SH
| Assembly | [16 empty] | SS
| Cavity String Assembly | L2HE-CST-ASSY |  | 2021-09-01 | Forehand |  |  | Hogan
| BPM Magnet sub-assembly | L2HE-CST-ASSY-BPM |  | 2021-09-01 | Forehand |  |  | Hogan
| String Pump down, leak test and transfer to phase 1 | L2HE-CST-ASSY-LEAK |  | 2021-09-01 | Forehand |  |  | Hogan
| Cavity String Gate Valve Leak Test | L2HE-CST-LEAK-AMGV |  | 2021-09-01 | Forehand |  |  | Hogan
| Chemistry | [16 empty] | SS
| Cryomodule | [16 empty] | SH
| Inspection | [16 empty] | SS
| Cryomodule Assembly | [16 empty] | SS
| CM Assembly First | L2HE-CMA-FRST |  | 2021-11-01 | Fischer | Worland |  | Hogan
| CM Assembly Second | L2HE-CMA-SCND |  | 2021-11-01 | Fischer | Worland |  | Hogan
| CM Assembly Final | L2HE-CMA-FNAL |  | 2021-11-01 | Fischer | Worland |  | Hogan
| Cryomodule Vacuum Vessel Assembly | L2HE-CMA-VV |  | 2021-11-01 | Fischer | Worland |  | Hogan
| FPC Warm Installation | L2HE-CMA-FPCW |  | 2021-11-01 | Huque |  |  | Hogan
| Cryomodule Rework Traveler | L2HE-CMA-REW |  | 2021-11-01 | Fischer |  |  | Hogan
| Cryomodule Prep and Shipping to SLAC | L2HE-CMA-SHIP |  | 2021-11-01 | Martin | Fischer |  | Hogan
| Cryomodule Retrofit Traveler | L2HE-CMA-RFIT |  | 2021-11-01 | Fischer |  |  | Hogan
| FPCW AC Diassemble/Removal | L2HE-CMA-FPCW-DISA |  | 2021-11-01 | Huque |  |  | Hogan
| Processing | [16 empty] | SS
| Production Cryomodule Demagnetization | L2HE-DMAG-CM |  | 2022-07-01 | Cheng | Fischer |  | Hogan | Cheng | Wilson, Hogan | Fischer, Cheng | Fischer, Cheng
| Upper Cold Mass Magnetic Hygiene Control | L2HE-DMAG-UCM |  | 2022-01-03 | Cheng | Fischer |  | Hogan | Cheng | Wilson, Hogan | Fischer, Cheng | Fischer, Cheng
| Cryomodule Testing | [16 empty] | SS
| Cryomodule Installation & Commisioning | [16 empty] | SS
| Cryomodule Acceptance Test | L2HE-CM-ACTS |  |  | Drury |  |  | Hogan
| Cryomodule Acceptance Test - Install and Cooldown | L2HE-CM-ACTS-PREP |  |  | Drury |  |  | Hogan
| Cryomodule Acceptance Test | L2HE-CM-CMTF-LPRF |  |  | Drury |  |  | Hogan
| Cryomodule Acceptance Test | L2HE-CM-CMTF-HPRF |  |  | Drury |  |  | Hogan
| Standard Project Travelers | [16 empty] | SH
CP | D3 Report | L2HE-D3 | R2 | [13 empty] | CP
CP | Cavity Non-conformance Report | L2HE-NCR | R11 | [13 empty] | CP
CP | Inspection Summary Report | L2HE-INSR | R1 | [13 empty] | CP
Color Legend |  | Count | Percent
CP | Complete (CP) | 11 | 15.28%
NR | New Revision Out for Approval (NR) | 0 | 0%
OA | Out for Approval (OA) | 0 | 0%
30 | Due in 30 Days | 5 | 6.944%
15 | Due in 15 Days | 5 | 6.944%
OD | Overdue | 0 | 0%
| Remaining | 51 | 70.83%
| Total Traveler IDs | 72

## INVENTORY TRAVELERS
Traveler Name | Traveler ID (SEPARATE BY WORKCENTERS) | Questions / Comments | Necessary Documentation | Author | Reviewer | Project Manager | SOTR | Date | D3 ?? (USERNAME) | NCR Dispositioners (USERNAME) | NCR Informative (USERNAME) | Notes

## PROCEDURES
PROCEDURE TITLE | PROCEDURE ID | REVISION | Author | Reviewer | Proj Lead | Due | Approved | CURRENT FILE LOCATION
Safety Procedures
Incoming inspection Procedures
Chemistry/ Cleaning Procedures
Cavity Procedures
String Production Procedures
Cryomodule Production Procedures
Cryomodule Testing Procedures
Cryomodule Shipping Procedures

## TRAVELERSold (hidden)
Traveler Name | Traveler ID (SEPARATE BY WORKCENTERS) | Procedure(s), Name (if known) OR Yes/No | Drawing(s), Name (if known) OR Yes/No | SOP/TOSP/OSP/THA | Revision | Author | Reviewer | Project Manager | SOTR | Due | D3 ?? (USERNAME) | NCR Dispositioners (USERNAME) | NCR Informative (USERNAME) | Traveler (Holdpoint) Closer (USERNAME) | Notes
Receiving Travelers
Cavity
Helium Vessel Receiving Traveler | SNSPPU-CAV-RECV-HELV |  |  |  | R1
Cavity String
Bellows Receiving Traveler | SNSPPU-CST-RECV-(bellows) |  |  |  | R1
Gate Valves Receiving Traveler | SNSPPU-CST-RECV-(gate valve) |  |  |  | R1
FPC Receiving Traveler | SNSPPU-CST-RECV-FPC |  |  |  | R1
Cryomodule
Diode CXCU Inventory Traveler | SNSPPU-CM-RECV-DCXCU |  |  |  | R1 | M. Dickey | C. Barnes | E. Daly | P. Owen | 2020-01-02 |  | powen,king,edaly,kwilson,mdickey,areilly
Disassembly Travelers
Cavity
Cavity String
Cryomodule
Leak Check Travelers
Cavity
Cavity String
Bellows Leak Check Traveler | SNSPPU-CST-LEAK-(bellows) |  |  |  | R1
Gate Valves Leak Check Traveler | SNSPPU-CST-LEAK-(gate valves) |  |  |  | R1
FPC Leak Check Traveler | SNSPPU-CST-LEAK-FPC |  |  |  | R1
Cryomodule
Inspection Travelers
Cavity
Visual and CMM Inspection of Cavity | SNSPPU-CAV-INSP-CAV |  | 104211800-M8U-8200-A00X |  | R1 |  |  |  | K. Wilson | 2020-02-01
Visual/CMM Inspection of Helium Vessel | SNSPPU-CAV-INSP-HELV | TI CLEANING | 104211700-M8U-8200-A026 |  | R1 |  |  |  | K. Wilson | 2020-02-01
Receiving Inspection Cavity RF | SNSPPU-CAV-RFIN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
TUNER FRAME / STEPPER MOTORS / HARMONIC DRIVE |  | SS CLEANING
Cavity String
Receiving Inspection Bellows | SNSPPU-CST-INSP-(bellows) |  |  |  | R1 |  |  |  | K. Wilson | 2020-05-01
SNS FPC Visual Inspection | SNSPPU-CST-INSP-FPC |  | 104211600-M8U-8200-A00X |  | R1 |  |  |  | K. Wilson | 2019-12-01
Cryomodule
Space Frame Visual and Dimensional Inspection | SNSPPU-CM-INSP-SFR | SS CLEANING | 104210900-M8U-8200-A001 |  | R1 |  |  |  | M. Marchlik | 2020-10-01
Vacuum Vessel Visual Inspection | SNSPPU-CM-INSP-VV | LEAK CHECK; SS CLEANING | 104210800-M8U-8200-A001 |  | R1 |  |  |  | M. Marchlik | 2020-07-01
SNS Return End Can Visual/CMM Inspection | SNSPPU-CM-INSP-RENC |  | 104210700-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-11-01
SNS Supply End Can Visual/CMM Inspection | SNSPPU-CM-INSP-SENC |  | 104210600-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-06-01
SNS Outer Magnetic Shield Visual Inspection | SNSPPU-CM-INSP-OMAG |  | 104211000-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-05-01
SNS Inner Magnetic Shield Visual Inspection | SNSPPU-CM-INSP-IMAG |  | 104211200-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-05-01
SNS Thermal Shield Visual/CMM Inspection | SNSPPU-CM-INSP-THRM | HIGH SENSITIVITY LEAK CHECK | 104211100-M8U-8200-A002 104211100-M8U-8200-A014 104211100-M8U-8200-A025 |  | R1 |  |  |  | M. Marchlik | 2020-08-01
Chemistry Travelers
Cavity
Cavity High Pressure Rinse (New HPR) Traveler | SNSPPU-CAV-CHEM-HPRN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Components Cleaning Traveler | SNSPPU-CAV-CHEM-CLN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Ultra Sonic Clean Traveler | SNSPPU-CAV-CHEM-USC |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
CMM Workcenter ?
IS there a cav RFIN traveler?
Furnace Workcenter ? | changed CHEM to PROC
Bakeout before RF processing | SNSPPU-CAV-PROC-BAKE |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Cavity Heat Treatment | SNSPPU-CAV-PROC-HEAT |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Processing Travelers
Cavity
Cavity RF Tuning | SNSPPU-CAV-TUNE |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
IS there a cav RFIN traveler? |  |  |  |  | R1
Cavity String
Cryomodule
RF Processing (FPC RF Processing) | SNSPPU-CM-CST-FPC-HPRF |  |  |  | R1 |  |  |  | K. Wilson
Assembly Travelers
Cavity
SNS Helium Vessel Installation Traveler | SNSPPU-CAV-ASSY-HELV |  | 104211700-M8U-8200-A026 |  | R1 |  |  |  |  | 2020-02-01
High Beta Cavity Assembly for VTA testing | SNSPPU-CAV-ASSY (look at old SNS) |  | 104211800-M8U-8200-A00X |  | R1 |  |  |  |  | 2020-02-01
transfer to test stand
Cavity String
SNS High Beta Cavity String Traveler | SNSPPU-CST-ASSY |  |  |  | R1 |  |  |  |  | 2020-07-01
Cryomodule
Cryomodule Assembly | SNSPPU-CM-ASSY |  |  |  | R1 |  |  |  | M. Marchlik | 2020-12-01
Cold Mass Assembly | SNSPPU-CM-ASSY-CMAS |  |  |  | R1 |  |  |  |  | 2020-08-01
Cryomodule Thermal Shield-Spaceframe Assembly Traveler | SNSPPU-CM-ASSY-THRM |  | 104211100-M8U-8200-A002 104211100-M8U-8200-A014 104211100-M8U-8200-A025 |  | R1 |  |  |  | M. Marchlik
SNS High Beta Cryomodule Vacuum Vessel-End Can Assembly Traveler | SNSPPU-CM-ASSY-VV |  | 104210800-M8U-8200-A001 |  | R1
cm assy ship (rf, instrumentation)
Testing Travelers
Vertical Cavity Testing | SNSPPU-CAV-VTRF |  |  |  | R1 |  |  |  |  | 2020-04-01
Cavity VTA Cooldown | SNSPPU-CAV-VTA-COOL |  |  |  | R1 |  |  |  |  | 2020-02-01
Installation/Shipping Travelers
SNS Cryomodule Shipping | SNSPPU-CM-ASSY-SHIP |  |  |  | R1 |  |  |  |  | 2020-05-01
Standard Project Travelers
Detours, Deviations and Discrepancies (D3) | SNSPPU-D3 |  |  |  | R2 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A
Inspection Summary Report | SNSPPU-INSR |  |  |  | R1 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A
Inspection Nonconformance Report | SNSPPU-NCR |  |  |  | R10 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A