## STRAW DOG
ER5C (C20, C50R, C75) STRAW DOG
STEPS | CONVERSION TO ER5C PROCESSES | TIMEFRAME ESTIMATE | COMMENTS
1 | Copy SNs from C20/C50R to C75 | 2021-05-14
2 | Start Using C75 for all CHEM, INSP, INV, FURN, TUNE, FAB, PROC and VTA | 2021-05-14
3 | Stop Using C50R for everything EXCEPT: DISA and ASSY | 2021-05-14
4 | Stop Using C20 for everything EXCEPT: DISA | 2021-05-14
5 | RESET Traveler Sequence Numbers (This will account for combining projects) | 2021-05-14
6 | Copy All APPROVED Travelers to ER5C project area (RENAMED) | 2021-05-31
7 | Set Traveler Sequence Numbers as appropriate | 2021-05-31
8 | STOP work in C20 project to transfer data… | 2021-06-14 | Start Date Dependent on Student Help
9 | Copy Data from C20 to ER5C (Travelers, NCRs, D3s)
10 | Restart C20 work in NEW ER5C project area
11 | STOP work in 50R project to transfer data… | 2021-06-28
12 | Copy Data from C50R to ER5C (Travelers, NCRs, D3s)
13 | Restart C50R work in NEW ER5C project area
14 | STOP work in C75 project to transfer data… | 2021-07-12
15 | Copy Data from C75 to ER5C (Travelers, NCRs, D3s)
16 | Restart C75 work in NEW ER5C project area
17 | CLOSE Projects C20, C50R and C75 | 2021-07-26
18 | All work proceeds in ER5C project area

## CONVERSION PLAN
C20 TRAV_ID | C20 TRAV_SEQ_NUM | C75 TRAV_ID | C75 TRAV_SEQ_NUM | C50R TRAV_ID | C50R TRAV_SEQ_NUM | ER5C TRAV_ID | ER5C TRAV_ID C50R | COMMENTS | TOTAL SEQ_NUM | RESET SEQ_NUM
|  | C75-CHEM-CAV-CBP | 4 |  |  | ER5C-CHEM-CAV-CBP |  |  | 4 | NONE
|  | C75-CHEM-CAV-DEGR | 161 | C50R-CAV-DEGR | 10 | ER5C-CHEM-CAV-DEGR |  |  | 171 | 200
|  | C75-CHEM-CAV-FLAP | 50 | C50R-CAV-FLAP | 11 | ER5C-CHEM-CAV-FLAP |  |  | 61 | 100
|  | C75-CAV-CHEM-HEP | 41 | C50R-CAV-HEP | 10 | ER5C-CHEM-CAV-HEP |  |  | 51 | 100
|  | C75-CAV-CHEM-HPR | 97 | C50R-CAV-HPR1 | 10 | ER5C-CHEM-CAV-HPR |  |  | 107 | 200
|  |  |  | C50R-CAV-HPR2 | 9 |  |  |  | 9
|  | C75-CAV-CHEM-THK | 42 |  |  | ER5C-CHEM-CAV-THK |  |  | 42 | NONE
|  | C75-CHEM-COMP-BCP | 87 |  |  | ER5C-CHEM-COMP-BCP |  |  | 87 | 300
|  | C75-CHEM-DBEL-BCP | 12 | [5 empty] | 12
|  | C75-CHEM-FLNG-BCP | 56 | [5 empty] | 56
|  | C75-CHEM-HCEL-BCP | 37 | [5 empty] | 37
|  | C75-CHEM-COMP-DEGR | 154 |  |  | ER5C-CHEM-COMP-DEGR |  |  | 154 | NONE
|  | C75-CAV-LAP-DGLG | 20 | C50R-CAV-LAP-DGLG | 21 | ER5C-CHEM-COMP-LAP |  |  | 41 | 100
|  | C75-CAV-LAP-ENDD | 0 | C50R-CAV-LAP-ENDD | 4 |  |  |  | 4
|  | C75-CAV-LAP-FPFT | 2 | C50R-CAV-LAP-FPFT | 0 |  |  |  | 2
|  | C75-CAV-LAP-INAD | 5 | C50R-CAV-LAP-INAD | 4 |  |  |  | 9
|  | C75-CAV-LAP-WIN | 0 | C50R-CAV-LAP-WIN | 0 |  |  |  | 0
|  | C75-CAV-LAP-WINW | 0 | C50R-CAV-LAP-WINW | 1 |  |  |  | 1
|  | C75-CHEM-HOME-LAP | 0 | C50R-CAV-LAP-HOME | 16 |  |  |  | 16
|  |  |  | C50R-CAV-LAP-LOAD | 0 |  |  |  | 0
|  |  |  | C50R-CAV-LAP-WGDX | 0 |  |  |  | 0
|  |  |  | C50R-CAV-ILAP | 13 |  |  |  | 13
|  | C75-CMA-BPIP-ASSY | 0 | C50R-CST-ASSY-BPIP | 0 | ER5C-CLNRM-BPIP-ASSY-C75 | ER5C-CLNRM-BPIP-ASSY-C50R | NEEDED? | 0 | NONE
|  | C75-CLNRM-CAV-ASSY | 9 |  |  | ER5C-CLNRM-CAV-ASSY-C75 |  |  | 9 | NONE
|  | C75-CLNRM-CAV-TSTD | 11 |  |  | ER5C-CLNRM-CAV-TSTD |  |  | 11 | NONE
|  |  |  | C50R-CPR-ASSY-FRST | 36 | ER5C-CLNRM-CPR-ASSY1-C75 | ER5C-CLNRM-CPR-ASSY1-C50R |  | 36 | NONE
|  |  |  | C50R-CPR-ASSY-SCND | 33 | ER5C-CLNRM-CPR-ASSY2-C75 | ER5C-CLNRM-CPR-ASSY2-C50R |  | 33 | NONE
|  | C75-CPR-ASSY-FNAL | 9 | C50R-CPR-ASSY-CMPL | 18 | ER5C-CLNRM-CPR-ASSYF-C75 | ER5C-CLNRM-CPR-ASSYF-C50R |  | 27 | NONE
C20-CPR-DISA | 2 | C75-CPR-DISA | 2 | C50R-CPR-DISA | 17 | ER5C-CLNRM-CPR-DISA-C75 | ER5C-CLNRM-CPR-DISA-C50R |  | 21 | NONE
|  |  |  | C50R-CPR-ASSY-STBK | 13 | ER5C-CLNRM-CPR-STBK |  |  | 13 | NONE
|  | C75-CPR-ASSY-STKU | 8 | C50R-CPR-ASSY-STKU | 18 | ER5C-CLNRM-CPR-STKU |  |  | 26 | 100
|  | C75-CPR-ASSY-TDWR | 8 | C50R-CPR-ASSY-TDWR | 18 | ER5C-CLNRM-CPR-TDWR |  |  | 26 | 100
|  | C75-CPR-ASSY-TOVR | 4 | C50R-CPR-ASSY-TOVR | 11 | ER5C-CLNRM-CPR-TOVR |  |  | 15 | 100
|  | C75-CPR-ASSY-TSTD | 5 | C50R-CPR-ASSY-TSTD | 14 | ER5C-CLNRM-CPR-TSTD |  |  | 19 | 100
|  | C75-CPR-ASSY-DGLG | 32 | C50R-CPR-ASSY-DGLG | 29 | ER5C-CLNRM-DGLG-ASSY-C75 | ER5C-CLNRM-DGLG-ASSY-C50R |  | 61 | NONE
|  | C75-CPR-DGLG-LEAK | 2 |  |  | ER5C-CLNRM-DGLG-LEAK |  |  | 2 | NONE
|  | C75-CLNRM-ENDD-ASSY | 7 | C50R-CLNRM-ASSY-ENDD | 0 | ER5C-CLNRM-ENDD-ASSY-C75 | ER5C-CLNRM-ENDD-ASSY-C50R |  | 7 | NONE
|  | C75-CPR-ASSY-EVAC | 9 | C50R-CPR-ASSY-EVAC | 17 | ER5C-CLNRM-EVAC-ASSY-C75 | ER5C-CLNRM-EVAC-ASSY-C50R |  | 26 | NONE
|  | C75-CPR-ASSY-WNCR | 23 | C50R-CPR-ASSY-WNCR | 1 | ER5C-CLNRM-WNCR-ASSY-C75 | ER5C-CLNRM-WNCR-ASSY-C50R |  | 24 | NONE
|  |  |  | C50R-CM-ASSY | 3 | ER5C-CMA-CM-ASSY-C75 | ER5C-CMA-CM-ASSY-C50R |  | 3 | NONE
C20-CM-DISA | 1 | C75-CM-DISA | 1 | C50R-CM-DISA | 2 | ER5C-CMA-CM-DISA-C75 | ER5C-CMA-CM-DISA-C50R |  | 4 | NONE
C20-CU-DISA | 4 |  |  | C50R-CU-DISA | 16 | ER5C-CMACU-CU-DISA-C75 | ER5C-CMACU-CU-DISA-C50R |  | 20 | NONE
|  | C75-CMACU-HELV-ASSY | 4 | C50R-CU-ASSY-HELV | 8 | ER5C-CMACU-HELV-ASSY-C75 | ER5C-CMACU-HELV-ASSY-C50R |  | 12 | NONE
|  |  |  | C50R-CU-ASSYF-HELV | 4 |  |  |  | 4 | OBS
|  | C75-CMACU-TUNE-ASSY | 4 | C50R-CU-ASSY-TUNE | 9 | ER5C-CMACU-TUNW-ASSY-C75 | ER5C-CMACU-TUNW-ASSY-C50R | TUNWSN?? | 13 | NONE
|  |  |  | C50R-CU-ASSYF-TUNE | 4 |  |  |  | 4 | OBS
|  | C75-CMACU-VV-ASSY | 4 | C50R-CU-ASSY-VV | 8 | ER5C-CMACU-VV-ASSY-C75 | ER5C-CMACU-VV-ASSY-C50R |  | 12 | NONE
|  |  |  | C50R-CU-ASSYF-VV | 4 |  |  |  | 4 | OBS
|  | C75-CMACU-WGD-ASSY | 4 | C50R-CU-ASSY-WG | 8 | ER5C-CMACU-WGD-ASSY-C75 | ER5C-CMACU-WGD-ASSY-C50R |  | 12 | NONE
|  |  |  | C50R-CU-ASSYF-WG | 4 |  |  |  | 4 | OBS
|  | C75-CMA-RTBP-ASSY | 0 |  |  | ER5C-CMA-RTBP-ASSY |  | NEEDED? | 0 | NONE
|  | C75-CMTF-CM-ACTS | 1 | C50R-CM-CMTF-ACTS | 3 | ER5C-CMTF-CM-ACTS-C75 | ER5C-CMTF-CM-ACTS-C50R |  | 4 | NONE
|  |  |  | C50R-CM-CMTF-DCOM | 0 | ER5C-CMTF-CM-DCOM | ER5C-CMTF-CM-DCOM-C50R |  | 0 | NONE
|  | C75-D3 | 62 | C50R-D3 | 49 | ER5C-D3 |  |  | 111 | 300
|  | C75-EBW-CERT | 0 |  |  | ER5C-EBW-CERT |  | NEEDED? | 0 | NONE
|  | C75-CAV-FAB | 6 |  |  | ER5C-FAB-CAV |  |  | 6 | NONE
|  |  |  | C50R-CAV-FAB-ENDD | 8 | ER5C-FAB-ENDD |  |  | 8 | NONE
|  | C75-CAV-FAB-HCEL | 30 |  |  | ER5C-FAB-HCEL |  |  | 30 | NONE
|  | C75-FURN-HOML-BRAZ | 0 |  |  | ER5C-FURN-HOML-BRAZ |  | NEEDED? | 0 | NONE
|  | C75-CU-BRAZ-WINW | 49 | C50R-CU-BRAZ-WINW | 190 | ER5C-FURN-WINW-BRAZ |  |  | 239 | 300
|  | C75-CAV-HEAT | 20 |  |  | ER5C-FURN-CAV-HEAT |  |  | 20 | NONE
|  | C75-CAV-HEAT-HCEL | 2 |  |  | ER5C-FURN-HCEL-HEAT |  |  | 2 | NONE
|  | C75-CAV-INSP | 63 |  |  | ER5C-INSP-CAV |  |  | 63 | NONE
|  | C75-CPR-INSP | 4 | C50R-CPR-INSP-CAV | 35 | ER5C-INSP-CAV |  |  | 39 | 100
|  |  |  | C50R-CPR-INSP-CAVPR | 13 | ER5C-INSP-CPR |  |  | 13 | 100
|  | C75-CAV-INSP-DBEL | 8 |  |  | ER5C-INSP-DBEL |  |  | 8 | 100
|  | C75-CPR-INSP-DGLG | 37 | C50R-CPR-INSP-DGLG | 33 | ER5C-INSP-DGLG |  |  | 70 | 100
|  | C75-CPR-INSP-DLCF | 15 | C50R-CPR-INSP-DLCF | 19 | ER5C-INSP-DLCF |  |  | 34 | 100
|  | C75-CPR-INSP-DLWF | 14 | C50R-CPR-INSP-DLWF | 20 | ER5C-INSP-DLWF |  |  | 34 | 100
|  | C75-CPR-INSP-DLWS | 20 | C50R-CPR-INSP-DLWS | 9 | ER5C-INSP-DLWS |  |  | 29 | 100
|  | C75-CPR-INSP-ENDD | 11 | C50R-CPR-INSP-ENDD | 26 | ER5C-INSP-ENDD |  |  | 37 | 100
|  | C75-INSP-FLG-COMP | 0 |  |  | ER5C-INSP-FLG |  | NEEDED? | 0 | NONE
|  | C75-CAV-INSP-FPCBT | 4 |  |  | ER5C-INSP-FPCBT |  |  | 4 | NONE
C20-CAV-INSP-FPCEG | 26 | C75-CAV-INSP-FPCEG | 2 |  |  | ER5C-INSP-FPCEG |  |  | 28 | NONE
|  | C75-CAV-INSP-HCEL | 25 |  |  | ER5C-INSP-HCEL |  |  | 25 | NONE
|  | C75-CPR-INSP-HOME | 57 | C50R-CPR-INSP-HOME | 37 | ER5C-INSP-HOME |  |  | 94 | 100
C20-CAV-INSP-HOMEG | 23 |  | 0 |  | 0 | ER5C-INSP-HOMEG |  |  | 23 | NONE
|  | C75-CM-INSP-IMAG | 17 |  |  | ER5C-INSP-IMAG |  |  | 17 | NONE
|  | C75-CPR-INSP-INAD | 15 | C50R-CPR-INSP-INAD | 25 | ER5C-INSP-INAD |  |  | 40 | 100
|  | C75-CPR-INSP-HOML | 67 | C50R-CPR-INSP-LOAD | 59 | ER5C-INSP-LOAD |  |  | 126 | 200
|  | C75-CAV-INSP-NB | 34 |  |  | ER5C-INSP-NB |  |  | 34 | NONE
|  | C75-CAV-INSP-NBI | 8 |  |  | ER5C-INSP-NBI |  |  | 8 | NONE
|  | C75-CAV-INSP-OPTK | 33 |  |  | ER5C-INSP-OPTK |  |  | 33 | NONE
|  | C75-CAV-INSP-SRING | 16 |  |  | ER5C-INSP-SRING |  |  | 16 | NONE
|  | C75-CU-INSP-WGDX | 8 | C50R-CU-INSP-WGDX | 22 | ER5C-INSP-WGDX |  |  | 30 | 100
|  | C75-CU-INSP-WIN | 8 | C50R-CU-INSP-WIN | 14 | ER5C-INSP-WIN |  |  | 22 | 100
|  | C75-CU-INSP-WINW | 8 | C50R-CU-INSP-WINW | 24 | ER5C-INSP-WINW |  |  | 32 | 100
|  | C75-CPR-INSP-WNCR | 0 | C50R-CPR-INSP-WNCR | 25 | ER5C-INSP-WNCR |  |  | 25 | 100
|  | C75-CPR-INSP-WNEY | 0 | C50R-CPR-INSP-WNEY | 1 | ER5C-INSP-WNEY |  |  | 1 | NONE
|  | C75-CM-RECV-CAPTOR | 0 |  |  | ER5C-INV-CAPTOR |  | NEEDED? | 0 | NONE
|  | C75-CAV-RECV-CAV | 19 |  |  | ER5C-INV-CAV |  |  | 19 | NONE
|  | C75-CPR-RECV-GV40 | 0 |  |  | ER5C-INV-GV40 |  | NEEDED? | 0 | NONE
|  | C75-CAV-RECV-IMAG | 0 |  |  | ER5C-INV-IMAG |  | NEEDED? | 0 | NONE
|  | C75-CPR-RECV-NEXTOR | 0 |  |  | ER5C-INV-NEXTOR |  | NEEDED? | 0 | NONE
|  | C75-INSR | 0 | C50R-INSR | 8 | ER5C-INSR |  |  | 8 | NONE
|  | C75-NCR | 285 | C50R-NCR | 187 | ER5C-NCR |  |  | 472 | 600
|  | C75-CAV-PROC | 35 |  |  | ER5C-PROC-CAV |  |  | 35 | NONE
|  | C75-CAV-PROC-POL-DBEL | 23 |  |  | ER5C-PROC-DBEL-POL |  | ? | 23 | NONE
|  | C75-CAV-TUNE | 89 | C50R-CAV-TUNE | 29 | ER5C-TUNE-CAV |  |  | 118 | 200
|  | C75-CAV-RFIN-DBEL | 8 |  |  | ER5C-TUNE-DBEL-RFIN |  |  | 8 | NONE
|  | C75-CAV-RFIN-EHCEL | 2 |  |  | ER5C-TUNE-EHCEL-RFIN |  |  | 2 | NONE
|  | C75-CAV-RFIN-HCEL | 0 |  |  | ER5C-TUNE-HCEL-RFIN |  | NEEDED? | 0 | NONE
|  | C75-CPR-VTA-COOL | 30 | C50R-CAV-VTA-COOL | 10 | ER5C-VTA-CAV-COOL-C75 | ER5C-VTA-CAV-COOL-C50R |  | 40 | 100
|  | C75-CPR-VTRF | 47 | C50R-CPR-VTRF | 37 | ER5C-VTA-CAV-VTRF-C75 | ER5C-VTA-CAV-VTRF-C50R |  | 84 | 100
|  | C75-VTA-CPR-LEAKD | 1 |  |  | ER5C-VTA-CPR-LEAKD |  |  | 1 | NONE
|  | C75-VTA-CPR-LEAKW | 4 |  |  | ER5C-VTA-CPR-LEAKW |  |  | 4 | NONE
|  | C75-CPR-VTRF-DGLG | 22 | C50R-CPR-VTRF-DGLG | 30 | ER5C-VTA-DGLG-VTRF |  |  | 52 | 100

## C20
TRAV_ID | TRAV_SEQ_NUM | HOLD_POINT | MOD_USER | MOD_DATE | TRAV_REV | OBS
C20-CAV-INSP-FPCEG | 26 | 0 | JFMOORE | 2021-04-08 | R2
C20-CAV-INSP-HOMEG | 23 | 0 | JFMOORE | 2021-04-12 | R1
C20-CM-DISA | 1 | 1 | LPAGE | 2019-12-06 | R1
C20-CPR-DISA | 2 | 0 | OVERTONR | 2020-08-19 | R1
C20-CU-DISA | 4 | 1 | adapps | 2020-05-13 | R1
C20-D3 | 0 | 0 | adapps | 2020-07-07 | R2
C20-INSR | 0 | 0 | adapps | 2020-07-07 | R1
C20-NCR | 0 | 0 | megan | 2020-07-07 | R11

## C50R
TRAV_ID | TRAV_SEQ_NUM | HOLD_POINT | MOD_USER | MOD_DATE | TRAV_REV | OBS
C50R-CAV-DEGR | 10 | 0 | FOLLKIEJ | 2016-01-20 | R1
C50R-CAV-FAB-ENDD | 8 | 0 | CARPENTE | 2013-10-29 | R1
C50R-CAV-FLAP | 11 | 0 | DANIELS | 2013-10-10 | R1
C50R-CAV-HEP | 10 | 0 | FOLLKIEJ | 2013-09-30 | R1
C50R-CAV-HPR1 | 10 | 0 | FIEDLER | 2021-04-27 | R1
C50R-CAV-HPR2 | 9 | 0 | ASHLEYA | 2021-04-27 | R1
C50R-CAV-ILAP | 13 | 0 | WILDESON | 2021-04-20 | R1
C50R-CAV-LAP-DGLG | 21 | 0 | DANIELS | 2013-09-24 | R1
C50R-CAV-LAP-ENDD | 4 | 0 | CARPENTE | 2015-12-18 | R1
C50R-CAV-LAP-FPFT | 0 | 0 | adapps | 2013-04-29 | R1
C50R-CAV-LAP-HOME | 16 | 0 | DANIELS | 2013-09-12 | R1
C50R-CAV-LAP-INAD | 4 | 0 | TMHARRIS | 2021-04-27 | R2
C50R-CAV-LAP-LOAD | 0 | 0 | adapps | 2013-04-26 | R1
C50R-CAV-LAP-WGDX | 0 | 0 | adapps | 2013-04-29 | R1
C50R-CAV-LAP-WIN | 0 | 0 | adapps | 2013-04-29 | R1
C50R-CAV-LAP-WINW | 1 | 0 | PROSPER | 2021-02-19 | R1
C50R-CAV-TUNE | 29 | 0 | OVERTONR | 2021-04-20 | R1
C50R-CAV-VTA-COOL | 10 | 0 | KUSHNICK | 2017-02-13 | R1
C50R-CLNRM-ASSY-ENDD | 0 | 0 | adapps | 2021-05-04 | R1
C50R-CM-ASSY | 3 | 0 | FHUMPHRY | 2017-06-01 | R1
C50R-CM-CMTF-ACTS | 3 | 1 | BOOKWALT | 2017-11-16 | R1
C50R-CM-CMTF-DCOM | 0 | 0 | adapps | 2015-06-11 | R1
C50R-CM-DISA | 2 | 1 | FISCHER | 2021-04-15 | R2
C50R-CPR-ASSY-CMPL | 18 | 0 | DREYFUSS | 2021-04-28 | R1
C50R-CPR-ASSY-DGLG | 29 | 0 | FOLLKIEJ | 2019-10-04 | R2
C50R-CPR-ASSY-EVAC | 17 | 0 | DREYFUSS | 2017-04-05 | R1
C50R-CPR-ASSY-FRST | 36 | 0 | DREYFUSS | 2017-04-04 | R1
C50R-CPR-ASSY-SCND | 33 | 0 | DREYFUSS | 2017-04-05 | R1
C50R-CPR-ASSY-STBK | 13 | 0 | FOREHAND | 2017-03-20 | R1
C50R-CPR-ASSY-STKU | 18 | 0 | FOREHAND | 2021-04-28 | R1
C50R-CPR-ASSY-TDWR | 18 | 0 | FOREHAND | 2020-01-06 | R3
C50R-CPR-ASSY-TOVR | 11 | 0 | DREYFUSS | 2017-02-03 | R1
C50R-CPR-ASSY-TSTD | 14 | 0 | FOREHAND | 2017-04-10 | R1
C50R-CPR-ASSY-WNCR | 1 | 0 | SCOTT | 2018-04-23 | R1
C50R-CPR-DISA | 17 | 0 | TASHAWN | 2021-04-21 | R3
C50R-CPR-INSP-CAV | 35 | 0 | MOSBY | 2021-05-04 | R2
C50R-CPR-INSP-CAVPR | 13 | 0 | GEORGED | 2017-05-15 | R1
C50R-CPR-INSP-DGLG | 33 | 0 | GEORGED | 2021-04-23 | R3
C50R-CPR-INSP-DLCF | 19 | 0 | GEORGED | 2017-10-10 | R1
C50R-CPR-INSP-DLWF | 20 | 0 | GEORGED | 2017-10-17 | R1
C50R-CPR-INSP-DLWS | 9 | 0 | GEORGED | 2013-07-03 | R1
C50R-CPR-INSP-ENDD | 26 | 0 | GEORGED | 2021-04-23 | R1
C50R-CPR-INSP-HOME | 37 | 0 | JFMOORE | 2021-05-04 | R2
C50R-CPR-INSP-INAD | 25 | 0 | JFMOORE | 2021-04-16 | R1
C50R-CPR-INSP-LOAD | 59 | 0 | GEORGED | 2017-02-22 | R2
C50R-CPR-INSP-WNCR | 25 | 0 | GEORGED | 2016-07-22 | R1
C50R-CPR-INSP-WNEY | 1 | 0 | BOOKWALT | 2013-04-09 | R1
C50R-CPR-VTRF | 37 | 1 | GRENOBLE | 2017-04-26 | R1
C50R-CPR-VTRF-DGLG | 30 | 0 | JTKENT | 2021-04-28 | R1
C50R-CST-ASSY-BPIP | 0 | 0 | adapps | 2013-09-19 | R1
C50R-CU-ASSY-HELV | 8 | 0 | MCCREA | 2017-06-15 | R1
C50R-CU-ASSY-TUNE | 9 | 0 | MCCREA | 2017-06-15 | R1
C50R-CU-ASSY-VV | 8 | 1 | MCCREA | 2017-07-05 | R1
C50R-CU-ASSY-WG | 8 | 0 | MCCREA | 2017-06-26 | R1
C50R-CU-ASSYF-HELV | 4 | 0 | MCCREA | 2016-06-11 | R1
C50R-CU-ASSYF-TUNE | 4 | 0 | adapps | 2016-06-23 | R3
C50R-CU-ASSYF-VV | 4 | 1 | MCCREA | 2016-06-22 | R1
C50R-CU-ASSYF-WG | 4 | 0 | MCCREA | 2016-06-22 | R1
C50R-CU-BRAZ-WINW | 190 | 0 | SCOTT | 2018-07-02 | R3
C50R-CU-DISA | 16 | 1 | FISCHER | 2021-04-15 | R2
C50R-CU-INSP-WGDX | 22 | 0 | GEORGED | 2017-04-12 | R1
C50R-CU-INSP-WIN | 14 | 0 | GEORGED | 2017-04-12 | R1
C50R-CU-INSP-WINW | 24 | 0 | JOGLE | 2017-05-12 | R1
C50R-D3 | 49 | 0 | FOREHAND | 2021-04-05 | R2
C50R-INSR | 8 | 0 | JOGLE | 2017-07-19 | R1
C50R-NCR | 187 | 0 | JFMOORE | 2021-04-29 | R11

## C75
TRAV_ID | TRAV_SEQ_NUM | HOLD_POINT | MOD_USER | MOD_DATE | TRAV_REV | OBS
C75-CAV-CHEM-HEP | 41 | 0 | WILDESON | 2021-05-04 | R2
C75-CAV-CHEM-HPR | 97 | 0 | ASHLEYA | 2021-04-23 | R1
C75-CAV-CHEM-THK | 42 | 0 | FIEDLER | 2021-05-04 | R1
C75-CAV-FAB | 6 | 0 | GCIOVATI | 2021-04-27 | R1
C75-CAV-FAB-HCEL | 30 | 0 | GCIOVATI | 2021-04-30 | R3
C75-CAV-HEAT | 20 | 0 | OVERTONR | 2021-05-04 | R1
C75-CAV-HEAT-HCEL | 2 | 0 | OVERTONR | 2018-02-27 | R1
C75-CAV-INSP | 63 | 0 | adapps | 2021-02-26 | R6
C75-CAV-INSP-DBEL | 8 | 0 | GEORGED | 2018-08-08 | R1
C75-CAV-INSP-FPCBT | 4 | 0 | GEORGED | 2018-05-18 | R1
C75-CAV-INSP-FPCEG | 2 | 0 | GEORGED | 2018-09-19 | R1
C75-CAV-INSP-HCEL | 25 | 0 | adapps | 2018-11-26 | R4
C75-CAV-INSP-NB | 34 | 0 | GCIOVATI | 2020-07-22 | R1
C75-CAV-INSP-NBI | 8 | 0 | GCIOVATI | 2020-03-05 | R1
C75-CAV-INSP-OPTK | 33 | 0 | GCIOVATI | 2021-04-16 | R1
C75-CAV-INSP-SRING | 16 | 0 | GEORGED | 2018-04-18 | R1
C75-CAV-LAP-DGLG | 20 | 0 | DIMYTRI | 2021-04-12 | R1
C75-CAV-LAP-ENDD | 0 | 0 | adapps | 2019-11-12 | R1
C75-CAV-LAP-FPFT | 2 | 0 | DREYFUSS | 2019-12-02 | R1
C75-CAV-LAP-INAD | 5 | 0 | WILDESON | 2020-11-30 | R1
C75-CAV-LAP-WIN | 0 | 0 | adapps | 2019-11-12 | R1
C75-CAV-LAP-WINW | 0 | 0 | adapps | 2019-11-12 | R1
C75-CAV-PROC | 35 | 0 | GCIOVATI | 2021-04-23 | R2
C75-CAV-PROC-POL-DBEL | 23 | 0 | SCOTT | 2018-09-18 | R2
C75-CAV-RECV-CAV | 19 | 0 | CBARNES | 2020-11-13 | R1
C75-CAV-RECV-IMAG | 0 | 0 | adapps | 2020-05-18 | R1
C75-CAV-RFIN-DBEL | 8 | 0 | GCIOVATI | 2018-08-09 | R1
C75-CAV-RFIN-EHCEL | 2 | 0 | GCIOVATI | 2018-07-27 | R1
C75-CAV-RFIN-HCEL | 0 | 0 | adapps | 2018-06-22 | R1
C75-CAV-TUNE | 89 | 0 | adapps | 2021-04-23 | R4
C75-CHEM-CAV-CBP | 4 | 0 | GROSE | 2021-05-05 | R1
C75-CHEM-CAV-DEGR | 161 | 0 | WILDESON | 2021-05-05 | R2
C75-CHEM-CAV-FLAP | 50 | 0 | DIMYTRI | 2021-04-09 | R1
C75-CHEM-COMP-BCP | 87 | 0 | TMHARRIS | 2021-04-28 | R2
C75-CHEM-COMP-DEGR | 154 | 0 | TMHARRIS | 2021-04-13 | R2
C75-CHEM-DBEL-BCP | 12 | 0 | MEGAN | 2021-03-18 | R1
C75-CHEM-FLNG-BCP | 56 | 0 | ASHLEYA | 2021-04-09 | R1
C75-CHEM-HCEL-BCP | 37 | 0 | TMHARRIS | 2021-04-28 | R1
C75-CHEM-HOME-LAP | 0 | 0 | adapps | 2020-10-05 | R1
C75-CLNRM-CAV-ASSY | 9 | 0 | FIRTH | 2021-04-14 | R1
C75-CLNRM-CAV-TSTD | 11 | 0 | DREYFUSS | 2021-04-20 | R1
C75-CLNRM-ENDD-ASSY | 7 | 0 | DREYFUSS | 2020-12-02 | R1
C75-CM-DISA | 1 | 1 | adapps | 2017-10-30 | R2
C75-CM-INSP-IMAG | 17 | 1 | GEORGED | 2020-08-07 | R1
C75-CM-RECV-CAPTOR | 0 | 0 | adapps | 2020-06-30 | R1
C75-CMA-BPIP-ASSY | 0 | 0 | adapps | 2021-02-22 | R1
C75-CMA-RTBP-ASSY | 0 | 0 | adapps | 2020-11-02 | R1
C75-CMACU-HELV-ASSY | 4 | 1 | FISCHER | 2021-02-12 | R1
C75-CMACU-TUNE-ASSY | 4 | 0 | FISCHER | 2021-01-14 | R1
C75-CMACU-VV-ASSY | 4 | 1 | FISCHER | 2021-02-22 | R1
C75-CMACU-WGD-ASSY | 4 | 0 | FISCHER | 2021-03-23 | R1
C75-CMTF-CM-ACTS | 1 | 0 | DRURY | 2021-04-12 | R1
C75-CPR-ASSY-DGLG | 32 | 0 | SCOTT | 2021-03-19 | R2
C75-CPR-ASSY-EVAC | 9 | 0 | DREYFUSS | 2020-12-08 | R1
C75-CPR-ASSY-FNAL | 9 | 0 | adapps | 2021-04-13 | R3
C75-CPR-ASSY-STKU | 8 | 0 | DREYFUSS | 2020-12-02 | R1
C75-CPR-ASSY-TDWR | 8 | 0 | TASHAWN | 2020-10-12 | R1
C75-CPR-ASSY-TOVR | 4 | 0 | DREYFUSS | 2021-01-04 | R1
C75-CPR-ASSY-TSTD | 5 | 0 | JJORDAN | 2021-04-01 | R1
C75-CPR-ASSY-WNCR | 23 | 0 | adapps | 2019-04-05 | R2
C75-CPR-DGLG-LEAK | 2 | 0 | PROSPER | 2020-09-08 | R1
C75-CPR-DISA | 2 | 0 | OVERTONR | 2020-08-12 | R1
C75-CPR-INSP | 4 | 0 | GEORGED | 2021-01-12 | R2
C75-CPR-INSP-DGLG | 37 | 0 | GEORGED | 2021-03-16 | R5
C75-CPR-INSP-DLCF | 15 | 0 | MOSBY | 2020-10-30 | R1
C75-CPR-INSP-DLWF | 14 | 0 | MOSBY | 2020-11-03 | R1
C75-CPR-INSP-DLWS | 20 | 0 | MOSBY | 2020-10-30 | R2
C75-CPR-INSP-ENDD | 11 | 0 | MOSBY | 2020-10-23 | R1
C75-CPR-INSP-HOME | 57 | 0 | JFMOORE | 2021-05-04 | R1
C75-CPR-INSP-HOML | 67 | 0 | LZHAO | 2021-04-16 | R2
C75-CPR-INSP-INAD | 15 | 0 | JFMOORE | 2021-04-16 | R1
C75-CPR-INSP-WNCR | 0 | 0 | adapps | 2017-11-10 | R1
C75-CPR-INSP-WNEY | 0 | 0 | adapps | 2017-11-10 | R1
C75-CPR-RECV-GV40 | 0 | 0 | adapps | 2020-06-02 | R1
C75-CPR-RECV-NEXTOR | 0 | 0 | adapps | 2020-06-30 | R1
C75-CPR-VTA-COOL | 30 | 0 | JTKENT | 2021-04-26 | R1
C75-CPR-VTRF | 47 | 0 | adapps | 2021-04-30 | R4
C75-CPR-VTRF-DGLG | 22 | 0 | JTKENT | 2021-05-04 | R1
C75-CU-BRAZ-WINW | 49 | 0 | MEGAN | 2018-09-18 | R1
C75-CU-INSP-WGDX | 8 | 0 | JOGLE | 2018-03-15 | R2
C75-CU-INSP-WIN | 8 | 0 | JOGLE | 2018-04-25 | R2
C75-CU-INSP-WINW | 8 | 0 | JOGLE | 2018-03-12 | R2
C75-D3 | 62 | 0 | DREYFUSS | 2021-04-15 | R2
C75-EBW-CERT | 0 | 1 | adapps | 2017-08-22 | R1
C75-FURN-HOML-BRAZ | 0 | 0 | adapps | 2021-03-18 | R1
C75-INSP-FLG-COMP | 0 | 0 | adapps | 2020-08-28 | R1
C75-INSR | 0 | 0 | adapps | 2020-07-07 | R1
C75-NCR | 285 | 0 | GEORGED | 2021-04-28 | R11
C75-VTA-CPR-LEAKD | 1 | 0 | OVERTONR | 2020-12-21 | R1
C75-VTA-CPR-LEAKW | 4 | 0 | PDOYLE | 2020-12-17 | R1

## CHEM
C75 TRAV_ID | C75 TRAV_SEQ_NUM | C50R TRAV_ID | C50R TRAV_SEQ_NUM | ER5C TRAV_ID | COMMENTS | TOTAL SEQ_NUM | RESET SEQ_NUM
C75-CHEM-CAV-CBP | 4 |  |  | ER5C-CHEM-CAV-CBP |  | 4 | NONE
C75-CHEM-CAV-DEGR | 161 | C50R-CAV-DEGR | 10 | ER5C-CHEM-CAV-DEGR |  | 171 | 200
C75-CHEM-CAV-FLAP | 50 | C50R-CAV-FLAP | 11 | ER5C-CHEM-CAV-FLAP |  | 61 | 100
C75-CAV-CHEM-HEP | 41 | C50R-CAV-HEP | 10 | ER5C-CHEM-CAV-HEP |  | 51 | 100
C75-CAV-CHEM-HPR | 97 | C50R-CAV-HPR1 | 10 | ER5C-CHEM-CAV-HPR |  | 107 | 200
|  | C50R-CAV-HPR2 | 9 |  |  | 9
C75-CAV-CHEM-THK | 42 |  |  | ER5C-CHEM-CAV-THK |  | 42 | NONE
C75-CHEM-COMP-BCP | 87 |  |  | ER5C-CHEM-COMP-BCP |  | 87 | 300
C75-CHEM-DBEL-BCP | 12 |  |  |  |  | 12
C75-CHEM-FLNG-BCP | 56 |  |  |  |  | 56
C75-CHEM-HCEL-BCP | 37 |  |  |  |  | 37
C75-CHEM-COMP-DEGR | 154 |  |  | ER5C-CHEM-COMP-DEGR |  | 154 | NONE
C75-CAV-LAP-DGLG | 20 | C50R-CAV-LAP-DGLG | 21 | ER5C-CHEM-COMP-LAP |  | 41 | 100
C75-CAV-LAP-ENDD | 0 | C50R-CAV-LAP-ENDD | 4 |  |  | 4
C75-CAV-LAP-FPFT | 2 | C50R-CAV-LAP-FPFT | 0 |  |  | 2
C75-CAV-LAP-INAD | 5 | C50R-CAV-LAP-INAD | 4 |  |  | 9
C75-CAV-LAP-WIN | 0 | C50R-CAV-LAP-WIN | 0 |  |  | 0
C75-CAV-LAP-WINW | 0 | C50R-CAV-LAP-WINW | 1 |  |  | 1
C75-CHEM-HOME-LAP | 0 | C50R-CAV-LAP-HOME | 16 |  |  | 16
|  | C50R-CAV-LAP-LOAD | 0 |  |  | 0
|  | C50R-CAV-LAP-WGDX | 0 |  |  | 0
|  | C50R-CAV-ILAP | 13 |  |  | 13
C75-CAV-PROC-POL-DBEL | 23 |  |  | ER5C-PROC-DBEL-POL | ? | 23 | NONE

## CLNRM_FURN_TUNE
C20 TRAV_ID | C20 TRAV_SEQ_NUM | C75 TRAV_ID | C75 TRAV_SEQ_NUM | C50R TRAV_ID | C50R TRAV_SEQ_NUM | ER5C TRAV_ID | ER5C TRAV_ID C50R | ER5C TRAV_ID C20 | COMMENTS | TOTAL SEQ_NUM | RESET SEQ_NUM
|  | C75-CMA-BPIP-ASSY | 0 | C50R-CST-ASSY-BPIP | 0 | ER5C-CLNRM-BPIP-ASSY-C75 | ER5C-CLNRM-BPIP-ASSY-C50R |  | NEEDED? | 0 | NONE
|  | C75-CLNRM-CAV-ASSY | 9 |  |  | ER5C-CLNRM-CAV-ASSY-C75 |  |  |  | 9 | NONE
|  | C75-CLNRM-CAV-TSTD | 11 |  |  | ER5C-CLNRM-CAV-TSTD |  |  |  | 11 | NONE
|  |  |  | C50R-CPR-ASSY-FRST | 36 | ER5C-CLNRM-CPR-ASSY1-C75 | ER5C-CLNRM-CPR-ASSY1-C50R |  |  | 36 | NONE
|  |  |  | C50R-CPR-ASSY-SCND | 33 | ER5C-CLNRM-CPR-ASSY2-C75 | ER5C-CLNRM-CPR-ASSY2-C50R |  |  | 33 | NONE
|  | C75-CPR-ASSY-FNAL | 9 | C50R-CPR-ASSY-CMPL | 18 | ER5C-CLNRM-CPR-ASSYF-C75 | ER5C-CLNRM-CPR-ASSYF-C50R |  |  | 27 | NONE
C20-CPR-DISA | 2 | C75-CPR-DISA | 2 | C50R-CPR-DISA | 17 | ER5C-CLNRM-CPR-DISA-C75 | ER5C-CLNRM-CPR-DISA-C50R | ER5C-CLNRM-CPR-DISA-C20 |  | 21 | NONE
|  |  |  | C50R-CPR-ASSY-STBK | 13 | ER5C-CLNRM-CPR-STBK |  |  |  | 13 | NONE
|  | C75-CPR-ASSY-STKU | 8 | C50R-CPR-ASSY-STKU | 18 | ER5C-CLNRM-CPR-STKU |  |  |  | 26 | 100
|  | C75-CPR-ASSY-TDWR | 8 | C50R-CPR-ASSY-TDWR | 18 | ER5C-CLNRM-CPR-TDWR |  |  |  | 26 | 100
|  | C75-CPR-ASSY-TOVR | 4 | C50R-CPR-ASSY-TOVR | 11 | ER5C-CLNRM-CPR-TOVR |  |  |  | 15 | 100
|  | C75-CPR-ASSY-TSTD | 5 | C50R-CPR-ASSY-TSTD | 14 | ER5C-CLNRM-CPR-TSTD |  |  |  | 19 | 100
|  | C75-CPR-ASSY-DGLG | 32 | C50R-CPR-ASSY-DGLG | 29 | ER5C-CLNRM-DGLG-ASSY-C75 | ER5C-CLNRM-DGLG-ASSY-C50R |  |  | 61 | NONE
|  | C75-CPR-DGLG-LEAK | 2 |  |  | ER5C-CLNRM-DGLG-LEAK |  |  |  | 2 | NONE
|  | C75-CLNRM-ENDD-ASSY | 7 | C50R-CLNRM-ASSY-ENDD | 0 | ER5C-CLNRM-ENDD-ASSY-C75 | ER5C-CLNRM-ENDD-ASSY-C50R |  |  | 7 | NONE
|  | C75-CPR-ASSY-EVAC | 9 | C50R-CPR-ASSY-EVAC | 17 | ER5C-CLNRM-EVAC-ASSY-C75 | ER5C-CLNRM-EVAC-ASSY-C50R |  |  | 26 | NONE
|  | C75-CPR-ASSY-WNCR | 23 | C50R-CPR-ASSY-WNCR | 1 | ER5C-CLNRM-WNCR-ASSY-C75 | ER5C-CLNRM-WNCR-ASSY-C50R |  |  | 24 | NONE
|  | C75-CAV-HEAT | 20 |  |  | ER5C-FURN-CAV-HEAT |  |  |  | 20 | NONE
|  | C75-CAV-HEAT-HCEL | 2 |  |  | ER5C-FURN-HCEL-HEAT |  |  |  | 2 | NONE
|  | C75-CAV-TUNE | 89 | C50R-CAV-TUNE | 29 | ER5C-TUNE-CAV |  |  |  | 118 | 200
|  | C75-CAV-RFIN-DBEL | 8 |  |  | ER5C-TUNE-DBEL-RFIN |  |  |  | 8 | NONE
|  | C75-CAV-RFIN-EHCEL | 2 |  |  | ER5C-TUNE-EHCEL-RFIN |  |  |  | 2 | NONE
|  | C75-CAV-RFIN-HCEL | 0 |  |  | ER5C-TUNE-HCEL-RFIN |  |  | NEEDED? | 0 | NONE

## CMA_CMACU
C20 TRAV_ID | C20 TRAV_SEQ_NUM | C75 TRAV_ID | C75 TRAV_SEQ_NUM | C50R TRAV_ID | C50R TRAV_SEQ_NUM | ER5C TRAV_ID | ER5C TRAV_ID C50R | ER5C TRAV_ID C20 | COMMENTS | TOTAL SEQ_NUM | RESET SEQ_NUM
|  |  |  | C50R-CM-ASSY | 3 | ER5C-CMA-CM-ASSY-C75 | ER5C-CMA-CM-ASSY-C50R |  |  | 3 | NONE
C20-CM-DISA | 1 | C75-CM-DISA | 1 | C50R-CM-DISA | 2 | ER5C-CMA-CM-DISA-C75 | ER5C-CMA-CM-DISA-C50R | ER5C-CMA-CM-DISA-C20 |  | 4 | NONE
|  | C75-CMA-RTBP-ASSY | 0 |  |  | ER5C-CMA-RTBP-ASSY |  |  | NEEDED? | 0 | NONE
C20-CU-DISA | 4 |  | 0 | C50R-CU-DISA | 16 | ER5C-CMACU-CU-DISA-C75 | ER5C-CMACU-CU-DISA-C50R | ER5C-CMACU-CU-DISA-C20 |  | 20 | NONE
|  | C75-CMACU-HELV-ASSY | 4 | C50R-CU-ASSY-HELV | 8 | ER5C-CMACU-HELV-ASSY-C75 | ER5C-CMACU-HELV-ASSY-C50R |  |  | 12 | NONE
|  |  |  | C50R-CU-ASSYF-HELV | 4 |  |  |  |  | 4 | OBS
|  | C75-CMACU-TUNE-ASSY | 4 | C50R-CU-ASSY-TUNE | 9 | ER5C-CMACU-TUNW-ASSY-C75 | ER5C-CMACU-TUNW-ASSY-C50R |  | TUNWSN?? | 13 | NONE
|  |  |  | C50R-CU-ASSYF-TUNE | 4 |  |  |  |  | 4 | OBS
|  | C75-CMACU-VV-ASSY | 4 | C50R-CU-ASSY-VV | 8 | ER5C-CMACU-VV-ASSY-C75 | ER5C-CMACU-VV-ASSY-C50R |  |  | 12 | NONE
|  |  |  | C50R-CU-ASSYF-VV | 4 |  |  |  |  | 4 | OBS
|  | C75-CMACU-WGD-ASSY | 4 | C50R-CU-ASSY-WG | 8 | ER5C-CMACU-WGD-ASSY-C75 | ER5C-CMACU-WGD-ASSY-C50R |  |  | 12 | NONE
|  |  |  | C50R-CU-ASSYF-WG | 4 |  |  |  |  | 4 | OBS

## CMTF
C75 TRAV_ID | C75 TRAV_SEQ_NUM | C50R TRAV_ID | C50R TRAV_SEQ_NUM | ER5C TRAV_ID | ER5C TRAV_ID C50R | COMMENTS | TOTAL SEQ_NUM | RESET SEQ_NUM
C75-CMTF-CM-ACTS | 1 | C50R-CM-CMTF-ACTS | 3 | ER5C-CMTF-CM-ACTS-C75 | ER5C-CMTF-CM-ACTS-C50R |  | 4 | NONE
|  | C50R-CM-CMTF-DCOM | 0 | ER5C-CMTF-CM-DCOM | ER5C-CMTF-CM-DCOM-C50R |  | 0 | NONE

## INSP
C20 TRAV_ID | C20 TRAV_SEQ_NUM | C75 TRAV_ID | C75 TRAV_SEQ_NUM | C50R TRAV_ID | C50R TRAV_SEQ_NUM | ER5C TRAV_ID | COMMENTS | TOTAL SEQ_NUM | RESET SEQ_NUM
|  | C75-CAV-INSP | 63 |  | 0 | ER5C-INSP-CAV |  | 63 | NONE
|  | C75-CPR-INSP | 4 | C50R-CPR-INSP-CAV | 35 | ER5C-INSP-CAV |  | 39 | 100
|  |  |  | C50R-CPR-INSP-CAVPR | 13 | ER5C-INSP-CPR |  | 13 | 100
|  | C75-CAV-INSP-DBEL | 8 |  | 0 | ER5C-INSP-DBEL |  | 8 | 100
|  | C75-CPR-INSP-DGLG | 37 | C50R-CPR-INSP-DGLG | 33 | ER5C-INSP-DGLG |  | 70 | 100
|  | C75-CPR-INSP-DLCF | 15 | C50R-CPR-INSP-DLCF | 19 | ER5C-INSP-DLCF |  | 34 | 100
|  | C75-CPR-INSP-DLWF | 14 | C50R-CPR-INSP-DLWF | 20 | ER5C-INSP-DLWF |  | 34 | 100
|  | C75-CPR-INSP-DLWS | 20 | C50R-CPR-INSP-DLWS | 9 | ER5C-INSP-DLWS |  | 29 | 100
|  | C75-CPR-INSP-ENDD | 11 | C50R-CPR-INSP-ENDD | 26 | ER5C-INSP-ENDD |  | 37 | 100
|  | C75-INSP-FLG-COMP | 0 |  | 0 | ER5C-INSP-FLG | NEEDED? | 0 | NONE
|  | C75-CAV-INSP-FPCBT | 4 |  | 0 | ER5C-INSP-FPCBT |  | 4 | NONE
C20-CAV-INSP-FPCEG | 26 | C75-CAV-INSP-FPCEG | 2 |  | 0 | ER5C-INSP-FPCEG |  | 28 | NONE
|  | C75-CAV-INSP-HCEL | 25 |  | 0 | ER5C-INSP-HCEL |  | 25 | NONE
|  | C75-CPR-INSP-HOME | 57 | C50R-CPR-INSP-HOME | 37 | ER5C-INSP-HOME |  | 94 | 100
C20-CAV-INSP-HOMEG | 23 |  | 0 |  | 0 | ER5C-INSP-HOMEG |  | 23
|  | C75-CM-INSP-IMAG | 17 |  | 0 | ER5C-INSP-IMAG |  | 17 | NONE
|  | C75-CPR-INSP-INAD | 15 | C50R-CPR-INSP-INAD | 25 | ER5C-INSP-INAD |  | 40 | 100
|  | C75-CPR-INSP-HOML | 67 | C50R-CPR-INSP-LOAD | 59 | ER5C-INSP-LOAD |  | 126 | 200
|  | C75-CAV-INSP-NB | 34 |  | 0 | ER5C-INSP-NB |  | 34 | NONE
|  | C75-CAV-INSP-NBI | 8 |  | 0 | ER5C-INSP-NBI |  | 8 | NONE
|  | C75-CAV-INSP-OPTK | 33 |  | 0 | ER5C-INSP-OPTK |  | 33 | NONE
|  | C75-CAV-INSP-SRING | 16 |  | 0 | ER5C-INSP-SRING |  | 16 | NONE
|  | C75-CU-INSP-WGDX | 8 | C50R-CU-INSP-WGDX | 22 | ER5C-INSP-WGDX |  | 30 | 100
|  | C75-CU-INSP-WIN | 8 | C50R-CU-INSP-WIN | 14 | ER5C-INSP-WIN |  | 22 | 100
|  | C75-CU-INSP-WINW | 8 | C50R-CU-INSP-WINW | 24 | ER5C-INSP-WINW |  | 32 | 100
|  | C75-CPR-INSP-WNCR | 0 | C50R-CPR-INSP-WNCR | 25 | ER5C-INSP-WNCR |  | 25 | 100
|  | C75-CPR-INSP-WNEY | 0 | C50R-CPR-INSP-WNEY | 1 | ER5C-INSP-WNEY |  | 1 | NONE

## INV_GENERAL
C75 TRAV_ID | C75 TRAV_SEQ_NUM | C50R TRAV_ID | C50R TRAV_SEQ_NUM | ER5C TRAV_ID | COMMENTS | TOTAL SEQ_NUM | RESET SEQ_NUM
C75-CM-RECV-CAPTOR | 0 |  |  | ER5C-INV-CAPTOR | NEEDED? | 0 | NONE
C75-CAV-RECV-CAV | 19 |  |  | ER5C-INV-CAV |  | 19 | NONE
C75-CPR-RECV-GV40 | 0 |  |  | ER5C-INV-GV40 | NEEDED? | 0 | NONE
C75-CAV-RECV-IMAG | 0 |  |  | ER5C-INV-IMAG | NEEDED? | 0 | NONE
C75-CPR-RECV-NEXTOR | 0 |  |  | ER5C-INV-NEXTOR | NEEDED? | 0 | NONE
C75-INSR | 0 | C50R-INSR | 8 | ER5C-INSR |  | 8 | NONE
C75-NCR | 285 | C50R-NCR | 187 | ER5C-NCR |  | 472 | 600
C75-CAV-PROC | 35 |  |  | ER5C-PROC-CAV |  | 35 | NONE
C75-CAV-PROC-POL-DBEL | 23 |  |  | ER5C-PROC-DBEL-POL | ? | 23 | NONE

## VTA
C75 TRAV_ID | C75 TRAV_SEQ_NUM | C50R TRAV_ID | C50R TRAV_SEQ_NUM | ER5C TRAV_ID | ER5C TRAV_ID C50R | COMMENTS | TOTAL SEQ_NUM | RESET SEQ_NUM
C75-CPR-VTA-COOL | 30 | C50R-CAV-VTA-COOL | 10 | ER5C-VTA-CAV-COOL-C75 | ER5C-VTA-CAV-COOL-C50R |  | 40 | 100
C75-CPR-VTRF | 47 | C50R-CPR-VTRF | 37 | ER5C-VTA-CAV-VTRF-C75 | ER5C-VTA-CAV-VTRF-C50R |  | 84 | 100
C75-VTA-CPR-LEAKD | 1 |  |  | ER5C-VTA-CPR-LEAKD |  |  | 1 | NONE
C75-VTA-CPR-LEAKW | 4 |  |  | ER5C-VTA-CPR-LEAKW |  |  | 4 | NONE
C75-CPR-VTRF-DGLG | 22 | C50R-CPR-VTRF-DGLG | 30 | ER5C-VTA-DGLG-VTRF |  |  | 52 | 100