## TRAVELERS
| Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | Author | Reviewer | Reviewer | Project Manager | SOTR | NCR Informative | NCR Dispositioners | D3 Emails | Procedure(s), Name (if known) | Drawing(s), Name (if known) | Acronym from INV | Notes | Status | Section
Cavity Preparation
| Processing | [16 empty] | SS
CP | Cavity High Pressure Rinse | L2HE-CHEM-CAV-HPR | R1 | [11 empty] | CAV |  | CP
OD | Cavity Heat Treatment & Nitrogen Doping | L2HE-FURN-CAV-HEAT | R1 | 2021-05-01 | D. FOREHAND |  |  | K. WILSON
OD | Cavity HOM Measurements and Tuning | L2HE-TUNE-HOM | R1 | 2021-05-01 | D. FOREHAND | R. OVERTON |  | K. WILSON
CP | Cavity RF Inspection | L2HE-TUNE-CAV-RFIN | R1 | 2021-05-01 |  |  |  | Hogan | [6 empty] | CAV | Cavities arrive in Aug2021 per KW | CP
| Assembly | [16 empty] | SS
OD | Cavity 1st Assembly | L2HE-CLNRM-CAV-ASSY1 | R1 | 2021-05-01 | D. FOREHAND | C. DREYFUSS |  | K. WILSON
OD | Cavity 2nd Assembly | L2HE-CLNRM-CAV-ASSY2 | R1 | 2021-05-01 | D. FOREHAND | C. DREYFUSS |  | K. WILSON
OD | Cavity Evacuation & Leak Test | L2HE-CLNRM-CAV-LEAK | R1 | 2021-05-01 | D. FOREHAND | C. DREYFUSS |  | K. WILSON
OD | Transfer of L2PRD 9-cell cavities to Test Stands | L2HE-CLNRM-CAV-TSTD | R1 | 2021-05-01 | D. FOREHAND | C. DREYFUSS |  | K. WILSON
OD | Transfer of L2PRD 9-cell cavities to Test Stands for Dewar 5 | L2HE-CLNRM-CAV-TSTD5 | R1 | 2021-05-01 | D. FOREHAND | C. DREYFUSS |  | K. WILSON
| Testing | [16 empty] | SS
CP | Cavity Cooldown | L2HE-VTA-CAV-COOL | R1 | 2021-05-01 | JT. KENT | J. VENNEKATE |  | K. WILSON |  | hogan,kwilson | hogan,kwilson | hogan,kwilson,kdavis,jtkent |  |  |  |  | CP
OD | Cavity Production VTA HOM Survey | L2HE-VTA-CAV-HOM | R1 | 2021-05-01 | M. STIRBET | J. VENNEKATE |  | K. WILSON
CP | Cavity VTA Test | L2HE-VTA-CAV-VTRF | R1 | 2021-05-01 | JT. KENT | J. VENNEKATE |  | K. WILSON | [8 empty] | CP
OA | Production Cavity Vertical Testing Procedure | L2HE-PR-VTA-CAV-VTRF | R1 | 2021-05-01 | C. WILSON | K. DAVIS |  | K. WILSON | [8 empty] | OA
| Component Prepreation | [16 empty] | SH
| Inspection | [16 empty] | SS
CP | Cavity Inspection | L2HE-INSP-CAV | R1 | 2021-08-01 | K. WILSON |  |  | Hogan | [6 empty] | CAV |  | CP
OD | Cavity Inventory | L2HE-INV-CAV | R1 | 2021-05-01 | K. WILSON
OD | FPC WARM PART | L2HE-INSP-FPCW | R1 | 2021-03-31 | N. HUQUE |  |  | Hogan | [5 empty] | 341081, P96394 | FPCW
OD | FPC WARM PART Inventory | L2HE-INV-FPCW | R1 | 2021-05-01 | N. HUQUE
OD | FPC COLD PART | L2HE-INSP-FPCC | R1 | 2021-03-31 | N. HUQUE | [8 empty] | 341082, P96406 | FPCC
OD | FPC COLD PART Inventory | L2HE-INV-FPCC | R1 | 2021-05-01 | N. HUQUE
CP | FPC Waveguide Incoming Inspection | L2HE-INSP-FPCWG | R1 | 2021-10-15 | Huque | Stirbet |  | Hogan | Huque | [5 empty] | FPCWG |  | CP
CP | FPC Waveguide Inventory | L2HE-INV-FPCWG | R1 | 2021-05-01 | Dickey | Barnes |  | Wilson |  | Wislon | Huque,Fischer | Huque,Fisher |  |  |  |  | CP
CP | Cavity Field Probe Feedthru Receiving Inspection | L2HE-INSP-FPFT | R1 | 2020-10-16 | Liang | DeKerlegand | N/A | Wilson | Park | Ari, Reece | Park, Wilson | Park, Wilson | No | GMM-9434A |  |  | CP
OD | Cavity Field Probe Feedthru Inventory | L2HE-INV-FPFT | R1 | 2021-05-01
CP | Cavity HOM Feedthru Receiving Inspection | L2HE-INSP-HMFT | R1 | 2020-10-16 | Liang | DeKerlegand | N/A | Wilson | Park | Ari, Reece | Park, Wilson | Park, Wilson | No | GMM-9433A |  |  | CP
OD | Cavity HOM Feedthru Receiving Inventory | L2HE-INV-HMFT | R1 | 2021-05-01
OD | Cavity Beam Line Bellows PRCM | L2HE-INSP-BLBP | R1 | 2021-05-01 | Marchlik | DeKerlegand | Zhao | Hogan | Marchlik
OD | Cavity Beam Line Bellows PRCM Inventory | L2HE-INV-BLBP | R1 | 2021-05-01
OD | Cavity Beam Line Bellows Short | L2HE-INSP-BLBS | R1 | 2021-05-01 | Marchlik | DeKerlegand | Zhao | Hogan | Marchlik
OD | Cavity Beam Line Bellows Short Inventory | L2HE-INV-BLBS | R1 | 2021-05-01
OD | Cavity String Weldment Upstream Bellows | L2HE-INSP-BLBU | R1 | 2021-05-01 | Marchlik | DeKerlegand | Zhao | Hogan | Marchlik
OD | Cavity String Weldment Upstream Bellows Inventory | L2HE-INV-BLBU | R1 | 2021-05-01
OD | String Beam Line Extension Downstream | L2HE-INSP-BLXD | R1 | 2021-05-01 | Marchlik | DeKerlegand | Zhao | Hogan | Marchlik
OD | String Beam Line Extension Downstream Inventory | L2HE-INV-BLXD | R1 | 2021-05-01
CP | 300K Current Leads CF Flange Inspection | L2HE-INSP-CFL | R1 | 2021-04-01 | Lakshmi | King | Morrone | Hogan | Lakshmi | hogan,kwilson | lalitha,king | lalitha,king,fisher,morrone |  |  |  |  | CP
15 | End Lever Tuner Mechanical Frame Inspection | L2HE-INSP-TUNC | R1 | 2021-05-14 | Powen | DeKerlegand | Huque | Hogan | Powen | kwilson | Powen, Huque, georged | Powen, Huque, Wilson |  | F10132292-B, F10138922-A
15 | End Lever Tuner Mechanical Frame Inventory | L2HE-INV-TUNC | R1 | 2021-05-14
CP | End Lever Tuner Motor | L2HE-INSP-SM | R1 | 2021-04-01 | King | Powen | Huque | Hogan | Powen | huque,kwilson | Powen, King | Powen, Huque, Wilson |  |  |  | Will be a batch traveler | CP
OD | End Lever Tuner Motor Inspection | L2HE-INV-SM | R1 | 2021-05-01
CP | Tuner Piezo Actuator Assembly Inspection | L2HE-INSP-PIEZO | R1 | 2021-03-05 | King | Powen | Huque | Hogan | Powen | huque,kwilson | Powen, King | Powen, Huque, Wilson |  |  |  | Will be a batch traveler | CP
CP | Tuner Piezo Actuator Inventory | L2HE-INV-TUNPZ | R1 | 2021-05-01 | M. Dickey | C. Barnes |  | John Hogan | Peter Owen | mdickey,Hogan,areilly | powen | Hogan,powen,areilly |  |  |  |  | CP
30 | Quadrapole Magnet Inspection | L2HE-INSP-QUAD | R1 | 2021-05-28 | Lakshmi | King | Morrone | Hogan | Lakshmi |  | Lakshmi, Wilson | Lakshmi, Wilson
OD | Quadrapole Magnet Inventory | L2HE-INV-QUAD | R1 | 2021-05-01
OD | Cryomodule Cool Down Cryogenic Valve (CDV) | L2HE-INSP-CDV | R1 | 2021-04-12 | Kent | Fischer | McEwen | Hogan | Kent | Katherine, Hogan | Kent, Wilson | Kent, Fischer
15 | Receiving Inspection CM Magnetic Shield Assembly | L2HE-INSP-IMAG | R1 | 2021-05-14 | Gary | DeKerlegand | Fischer | Hogan | Gary | Katherine, Hogan | Gary, Fischer | Gary, Fischer |  | F10048652
15 | CM Magnetic Shield Assembly Inventory | L2HE-INV-IMAG | R1 | 2021-05-14
OD | Receiving Inspection CM Rod Invar 2-Phase Long | L2HE-INSP-IROD2L | R1 | 2021-05-01 | O'Brien |  |  | Hogan
OD | CM Rod Invar 2-Phase Long Inventory | L2HE-INV-IROD2L | R1 | 2021-05-01
OD | Receiving Inspection CM Rod Invar 2-Phase | L2HE-INSP-IROD2P | R1 | 2021-05-01 | O'Brien |  |  | Hogan
OD | CM Rod Invar 2-Phase Inventory | L2HE-INV-IROD2P | R1 | 2021-05-01
OD | Receiving Inspection CM Assembly, JT Cryogenic Valve | L2HE-INSP-JTV | R1 | 2021-04-12 | Kent | Fischer | McEwen | Hogan | Kent | Katherine, Hogan | Kent, Wilson | Kent, Fischer
OD | Receiving Inspection CM Assembly, JT Valve Tube Kit | L2HE-INSP-JTVTK | R1 | 2021-04-12 | Kent | Fischer | McEwen | Hogan | Kent | Katherine, Hogan | Kent, Wilson | Kent, Fischer
OD | CM Assembly, JT Valve Tube Kit Inventory | L2HE-INV-JTVTK | R1 | 2021-04-12
15 | Upper Cold Mass CMA Inspection | L2HE-CMA-UCM-INSP | R1 | 2021-05-18 | Gary | Fischer | N/A | Hogan | Gary | Katherine, Hogan | Gary, Fischer | Gary, Fischer |  | F10009954
15 | Upper Cold Mass CMA Inventory | L2HE-INV-UCM | R1 | 2021-05-18
15 | CM Vacuum Vessel Inventory | L2HE-INV-VV | R1 | 2021-05-18
CP | All Metal Gate Valve Inventory | L2HE-INV-AMGV | R1 | 2021-05-01 | Dickey | Barnes |  | Hogan | Savransky | Mdicky,Hogan | Kwilson,Dsavr | [5 empty] | CP
| Chemistry | [16 empty] | SS
OD | Cavity Cleaning / UltraSonic Cleaning | L2HE-CHEM-COMP-USC | R1 | 2021-05-01 | Mitchell | Wildeson | Palczewski | Hogan |  | ashleya | hogan,ari | ashleya,ari,hogan,kdavis,forehand
OD | First HPR | L2HE-CHEM-COMP-HPRN | R1 | 2021-05-01 | Mitchell | Wildeson | Palczewski | Hogan |  | ashleya | hogan,ari | ashleya,ari,hogan,kdavis,forehand
OD | Components Cleaning | L2HE-CHEM-COMP-DEGR | R1 | 2021-05-01 | Mitchell | Wildeson | Palczewski | Hogan |  | ashleya | hogan,ari | ashleya,ari,hogan,kdavis,forehand
OD | Laping | L2HE-CHEM-COMP-LAP | R1 | 2021-05-01 | Wildeson | Mitchell | Palczewski | Hogan |  | ashleya | hogan,ari | ashleya,ari,hogan,kdavis,forehand
| Weld Inspection | [16 empty] | SS
15 | Upper Cold Mass Weld Inspection? | L2HE-CWI-UCM | R1 | 2021-05-18 | Jenord | Gary | Fischer | Hogan | Gary | Katherine, Hogan | Gary, Fischer | Gary, Fischer |  | F10009954
| Leak Checks | [16 empty] | SS
CP | Cavity Field Probe Feedthru Receiving Inspection | L2HE-CMA-FPFT-LEAK | R1 | 2020-10-21 | Park | Wilcox | N/A | Wilson | Park | Ari, Reece | Park, Wilson | Park, Wilson | Leak check spec 11141-S-0029 | GMM-9434A |  |  | CP
CP | Cavity HOM Feedthru Receiving Inspection | L2HE-CMA-HMFT-LEAK | R1 | 2020-10-21 | Park | Wilcox | N/A | Wilson | Park | Ari, Reece | Park, Wilson | Park, Wilson | Leak check spec 11141-S-0029 | GMM-9433A |  |  | CP
| Cavity Beam Line Bellows PRCM Leak Test | L2HE-CMA-BLBP-LEAK | R1 | 2021-08-15 | Marchlik | WIlcox | N/A | Wilson | Marchlik | Ari, Reece | Marchlik, Wilson | Marchlik, Wilson | Leak check spec 11141-S-0029 | F10041075
| Cavity Beam Line Bellows Short | L2HE-CMA-BLBS-LEAK | R1 | 2021-08-15 | Marchlik | WIlcox | N/A | Wilson | Marchlik | Ari, Reece | Marchlik, Wilson | Marchlik, Wilson | Leak check spec 11141-S-0029 | F10023437
| Cavity String Weldment Upstream Bellows | L2HE-CMA-BLBU-LEAK | R1 | 2021-08-15 | Marchlik | WIlcox | N/A | Wilson | Marchlik | Ari, Reece | Marchlik, Wilson | Marchlik, Wilson | Leak check spec 11141-S-0029 | F10075494
| String Beam Line Extension Downstream | L2HE-CMA-BLXD-LEAK | R1 | 2021-08-15 | Marchlik | WIlcox | N/A | Wilson | Marchlik | Ari, Reece | Marchlik, Wilson | Marchlik, Wilson | Leak check spec 11141-S-0029 | F10052775
15 | Receiving CMA Inspection CM Vacuum Vessel | L2HE-CMA-VV-INSP | R1 | 2021-05-18 | Gary | Fischer | N/A | Hogan | Gary | Katherine, Hogan | Gary, Fischer | Gary, Fischer |  | F10026609
| Cold Shock | [16 empty] | SS
CP | Cavity Field Probe Feedthru Receiving Inspection | L2HE-VTA-FPFT-CSHK | R1 | 2020-10-22 | Park | Forehand | Kent | Wilson | Park | Ari, Reece | Park, Wilson | Park, Wilson | No | GMM-9434A |  |  | CP
CP | Cavity HOM Feedthru Receiving Inspection | L2HE-VTA-HMFT-CSHK | R1 | 2020-10-23 | Park | Forehand | Kent | Wilson | Park | Ari, Reece | Park, Wilson | Park, Wilson | No | GMM-9433A |  |  | CP
| Cavity String | [16 empty] | SH
| Assembly | [16 empty] | SS
| Cavity String Assembly | L2HE-CST-ASSY | R1 | 2021-09-01 | Forehand |  |  | Hogan
| BPM Magnet sub-assembly | L2HE-CST-ASSY-BPM | R1 | 2021-09-01 | Forehand |  |  | Hogan
| String Pump down, leak test and transfer to phase 1 | L2HE-CST-ASSY-LEAK | R1 | 2021-09-01 | Forehand |  |  | Hogan
| Cavity String Gate Valve Leak Test | L2HE-CST-LEAK-AMGV | R1 | 2021-09-01 | Forehand |  |  | Hogan
| Cryomodule | [16 empty] | SH
| Cryomodule Assembly | [16 empty] | SS
| CM Assembly First | L2HE-CMA-FRST | R1 | 2021-11-01 | Fischer | Worland |  | Hogan
| CM Assembly Second | L2HE-CMA-SCND | R1 | 2021-11-01 | Fischer | Worland |  | Hogan
| CM Assembly Final | L2HE-CMA-FNAL | R1 | 2021-11-01 | Fischer | Worland |  | Hogan
| Cryomodule Vacuum Vessel Assembly | L2HE-CMA-VV | R1 | 2021-11-01 | Fischer | Worland |  | Hogan
| FPC Warm Installation | L2HE-CMA-FPCW | R1 | 2021-11-01 | Huque |  |  | Hogan
| Cryomodule Rework Traveler | L2HE-CMA-REW | R1 | 2021-11-01 | Fischer |  |  | Hogan
| Cryomodule Prep and Shipping to SLAC | L2HE-CMA-SHIP | R1 | 2021-11-01 | Martin | Fischer |  | Hogan
| Cryomodule Retrofit Traveler | L2HE-CMA-RFIT | R1 | 2021-11-01 | Fischer |  |  | Hogan
| FPCW AC Diassemble/Removal | L2HE-CMA-FPCW-DISA | R1 | 2021-11-01 | Huque |  |  | Hogan
| Processing | [16 empty] | SS
| Production Cryomodule Demagnetization | L2HE-CMA-CM-DMAG | R1 | 2021-07-31 | Cheng | Fischer |  | Hogan | Cheng | Wilson, Hogan | Fischer, Cheng | Fischer, Cheng
| Upper Cold Mass Magnetic Hygiene Control | L2HE-CMA-UCM-DMAG | R1 | 2021-07-31 | Cheng | Fischer |  | Hogan | Cheng | Wilson, Hogan | Fischer, Cheng | Fischer, Cheng
| Cryomodule Testing | [16 empty] | SS
| Cryomodule Acceptance Test LERF | L2HE-LERF-CM-ACTS | R1 | 2021-07-31 | Drury |  |  | Hogan
| Standard Project Travelers | [16 empty] | SH
CP | D3 Report | L2HE-D3 | R2 | [13 empty] | CP
CP | Cavity Non-conformance Report | L2HE-NCR | R11 | [13 empty] | CP
CP | Inspection Summary Report | L2HE-INSR | R1 | [13 empty] | CP
Color Legend |  | Count | Percent
CP | Complete (CP) | 21 | 23.6%
NR | New Revision Out for Approval (NR) | 0 | 0%
OA | Out for Approval (OA) | 1 | 1.124%
30 | Due in 30 Days | 1 | 1.124%
15 | Due in 15 Days | 9 | 10.11%
OD | Overdue | 37 | 41.57%
| Remaining | 20 | 22.47%
| Total Traveler IDs | 89

## TECH REPS
System | JLab | EXPECTED 1ST DELIVERY? | VENDOR DOCUMENTATION | FNAL | SLAC
Dressed Cavities | John Vannekate/ Charlie Reece |  |  | Mattia Checchin / Chuck Grimm | Dan Gonnella
Feedthroughs | Liang |  |  | Mattia Checchin / Chuck Grimm | Dan Gonnella
Couplers | Naeem Huque |  |  | Ken Premo | Jeff Tice
(Nikolay Solyak – SME)
Cavity String Bellows and Spools | Matt Marchlik |  |  | Ken Premo / Andrei Lunin | Maniscalco
Cavity String Hardware and Seals | Mike Dickey |  |  | Damon Bice | Maniscalco
Magnet | Lakshmi Lalitha |  |  | John Amann | Tommy Hiatt
BPM | HyeKyoung Park |  |  | Andrei Lunin | Tommy Hiatt
Gate Valves | David Savransky |  |  | Damon Bice | Tommy Hiatt
2-Phase Pipe Components | Adam O’Brien |  |  | Chuck Grimm | Tommy Hiatt
End Lever Tuner | Peter Owen |  |  | Yuriy Pischalnikov | Maniscalco
Magnetic Shielding | Gary Cheng |  |  | Saravan Chandrasekaran / Yi Xie | Maniscalco
Cold Mass and Components | Gary Cheng |  |  | Ken Premo | Dan Gonnella
Vacuum Vessel and Components | Gary Cheng |  |  | Ken Premo | Dan Gonnella
Instrumentation | Larry King |  |  | Fred Lewis | Maniscalco
Cryogenic Valves | Justin Kent |  |  | Greg Johnson | Tommy Hiatt
Vacuum Equipment | Adam O’Brien |  |  | Ken Premo | Tommy Hiatt

## TIFFANY
Below is my understanding of the status of all the travelers we need in place now for the refurbishment cavities currently working towards a VTRF (CAV040, 295, and 331). The Pansophy team has the official tracking on the status of all the L2HE travelers and procedures so they can provide a better / corrected status update if needed.
Process Step | L2HE Traveler ID | Based on Traveler | L2HE Traveler Status | Comments
RF Inspection | L2HE-TUNE-CAV-RFIN |  | Issued | for as-received from vendor; use D3 for refurbishment cavities
CMM | L2HE-INSP-CAV |  | Issued | for as-received from vendor; use D3 for refurbishment cavities
Dual USC (Liquinox + DI) | L2HE-CHEM-CAV-USC | C100R-CAV-CHEM-USC | Draft needed based on C100R
2-pass HPR | L2HE-CHEM-CAV-HPR | C100R-CAV-CHEM-HPR | Draft needed based on C100R
First Assembly (FP, FPC, HOM) | L2HE-CLNRM-CAV-FRST | L2PRD-CAV-ASSY-FRST | Draft needed based on L2PRD
Second Assy | L2HE-CLNRM-CAV-SCND | L2PRD-CAV-ASSY-SCND | Draft needed based on L2PRD
Transfer to Test Stand | L2HE-CLNRM-CAV-TSTD and L2HE-CLNRM-CAV-TSTD-D5 | L2PRD-CAV-TRANS-TSTD and L2PRD-CAV-TRANS-TSTD-D5 | Draft needed based on L2PRD
Cooldown to 2K (including sensor install and checkout) | L2HE-VTA-CAV-COOL | L2PRD-CAV-VTA-COOL | Justin has draft; needs to be uploaded to DocuShare | L2PRD parameters need to be updated for L2HE
VTRF | L2HE-VTA-CAV-VTRF | L2PRD-CAV-VTRF | In Approvals | L2PRD parameters need to be updated for L2HE
HOM Survey | L2HE-VTA-CAV-HOM | L2PRD-CAV-VTA-HOM | Draft needed based on L2PRD
· Italicized L2HE Traveler IDs are traveler that do not currently exist and are my best guess at what the ID needs to be based on the current naming convention guidance.
Tiffany Ganey

## DELIVERIES
Component | FNAL | JLAB | SLAC | QTY | SOTR | Date for First Lot at JLAB
Niobium (Prototype) - existing cavities | NA | [5 empty] | L2HE-INV-*
Niobium (Production) | X | [5 empty] | AMGV
Cavities (Prototype) - existing cavities | NA |  |  |  | Ari Palczewski |  | FPCWG
Helium Vessels (Prototype) | X |  |  |  | Ari Palczewski |  | PIEZO
Cavities w/Helium Vessels -VTS Ready (Production) |  | X |  | 80 | Ari Palczewski | 2021-04-29
Cavity Feedthroughs |  | X |  |  | Ari Palczewski | 2020-11-02
Cavity Flanges & Assoc. Hardware/Seals (VTS & HTS compatible) |  | X |  |  |  |  | SNs From PRIMeS
Fundamental Power Coupler (FPC) |  |  | X |  |  | 2021-05-28 | AMGV*
Cavity String Interconnecting Bellows |  | X |  |  | Matt Marchlick | 2021-04-19 | AV15
Cavity String Assembly Hardware & Seals | X |  |  |  | Mike Dickey |  | C12P
SC Magnet Assembly | X |  |  |  | Lakshmi Latitha | 2021-02-12 | CAV
Beam Position Monitor (BPM) | X |  |  |  | HyeKyoung Park | 2021-02-22 | CDV
Gate Valves |  | X |  |  | David Savransky | 2021-04-09 | CFL
Beamline Vac. Monitoring Manifold & Gauge | X | [5 empty] | FPCWG*
Two-phase Pipe Bellows | X |  |  |  | Gary Cheng ? |  | FPFT
Tuner, actuator, piezos (Prototype) | X |  |  |  | Peter Owen | 2021-07-19 | FT06P
Tuner , actuator, piezos (Production) |  | X |  |  | Peter Owen |  | HMFT
Magnetic Shielding | X |  |  | 10 | Gary Cheng | 2021-08-27 | IP75SD
GRHP Sub-assembly | X | [5 empty] | JTV
Vacuum Vessel | X |  |  | 10 | Gary Cheng | 2021-03-23 | TSCPLR
Coupler Pumping Lines & Pumps (ion+TSP) + vacuum gauges | X | [5 empty] | TSHMSM
Instrumentation | X |  |  |  | Larry King
Liquid Level Probes & JT Valve | X
Beamline Interconnect Parts including Aluminum Heat Shields | X
HOM Absorber |  | X |  |  |  | 2021-01-12
Shipping Frames & End Caps + Shock Log Devices |  | X
X = Lead Lab (to be confrimed)
BLAs (will JLAB be required to inspect & Process these ? ) |  |  |  |  | ??? | 2021-04-28
Cyrogenic Valves |  |  |  |  | Naeem Huque
Vacuum Equipment |  |  |  |  | Gary Cheng
JT & Cool Down Valves |  |  |  |  | ?? | 2021-04-20

## MILESTONES
Major Processes for HE | Start date
Cavity Prep & Test | 2020-11-17
String Assembly | 2021-07-27
CM Assembly | 2021-05-15
Testing | 2022-05-17

## TRAVELERSold (hidden)
Traveler Name | Traveler ID (SEPARATE BY WORKCENTERS) | Procedure(s), Name (if known) OR Yes/No | Drawing(s), Name (if known) OR Yes/No | SOP/TOSP/OSP/THA | Revision | Author | Reviewer | Project Manager | SOTR | Due | D3 ?? (USERNAME) | NCR Dispositioners (USERNAME) | NCR Informative (USERNAME) | Traveler (Holdpoint) Closer (USERNAME) | Notes
Receiving Travelers
Cavity
Helium Vessel Receiving Traveler | SNSPPU-CAV-RECV-HELV |  |  |  | R1
Cavity String
Bellows Receiving Traveler | SNSPPU-CST-RECV-(bellows) |  |  |  | R1
Gate Valves Receiving Traveler | SNSPPU-CST-RECV-(gate valve) |  |  |  | R1
FPC Receiving Traveler | SNSPPU-CST-RECV-FPC |  |  |  | R1
Cryomodule
Diode CXCU Inventory Traveler | SNSPPU-CM-RECV-DCXCU |  |  |  | R1 | M. Dickey | C. Barnes | E. Daly | P. Owen | 2020-01-02 |  | powen,king,edaly,kwilson,mdickey,areilly
Disassembly Travelers
Cavity
Cavity String
Cryomodule
Leak Check Travelers
Cavity
Cavity String
Bellows Leak Check Traveler | SNSPPU-CST-LEAK-(bellows) |  |  |  | R1
Gate Valves Leak Check Traveler | SNSPPU-CST-LEAK-(gate valves) |  |  |  | R1
FPC Leak Check Traveler | SNSPPU-CST-LEAK-FPC |  |  |  | R1
Cryomodule
Inspection Travelers
Cavity
Visual and CMM Inspection of Cavity | SNSPPU-CAV-INSP-CAV |  | 104211800-M8U-8200-A00X |  | R1 |  |  |  | K. Wilson | 2020-02-01
Visual/CMM Inspection of Helium Vessel | SNSPPU-CAV-INSP-HELV | TI CLEANING | 104211700-M8U-8200-A026 |  | R1 |  |  |  | K. Wilson | 2020-02-01
Receiving Inspection Cavity RF | SNSPPU-CAV-RFIN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
TUNER FRAME / STEPPER MOTORS / HARMONIC DRIVE |  | SS CLEANING
Cavity String
Receiving Inspection Bellows | SNSPPU-CST-INSP-(bellows) |  |  |  | R1 |  |  |  | K. Wilson | 2020-05-01
SNS FPC Visual Inspection | SNSPPU-CST-INSP-FPC |  | 104211600-M8U-8200-A00X |  | R1 |  |  |  | K. Wilson | 2019-12-01
Cryomodule
Space Frame Visual and Dimensional Inspection | SNSPPU-CM-INSP-SFR | SS CLEANING | 104210900-M8U-8200-A001 |  | R1 |  |  |  | M. Marchlik | 2020-10-01
Vacuum Vessel Visual Inspection | SNSPPU-CM-INSP-VV | LEAK CHECK; SS CLEANING | 104210800-M8U-8200-A001 |  | R1 |  |  |  | M. Marchlik | 2020-07-01
SNS Return End Can Visual/CMM Inspection | SNSPPU-CM-INSP-RENC |  | 104210700-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-11-01
SNS Supply End Can Visual/CMM Inspection | SNSPPU-CM-INSP-SENC |  | 104210600-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-06-01
SNS Outer Magnetic Shield Visual Inspection | SNSPPU-CM-INSP-OMAG |  | 104211000-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-05-01
SNS Inner Magnetic Shield Visual Inspection | SNSPPU-CM-INSP-IMAG |  | 104211200-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-05-01
SNS Thermal Shield Visual/CMM Inspection | SNSPPU-CM-INSP-THRM | HIGH SENSITIVITY LEAK CHECK | 104211100-M8U-8200-A002 104211100-M8U-8200-A014 104211100-M8U-8200-A025 |  | R1 |  |  |  | M. Marchlik | 2020-08-01
Chemistry Travelers
Cavity
Cavity High Pressure Rinse (New HPR) Traveler | SNSPPU-CAV-CHEM-HPRN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Components Cleaning Traveler | SNSPPU-CAV-CHEM-CLN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Ultra Sonic Clean Traveler | SNSPPU-CAV-CHEM-USC |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
CMM Workcenter ?
IS there a cav RFIN traveler?
Furnace Workcenter ? | changed CHEM to PROC
Bakeout before RF processing | SNSPPU-CAV-PROC-BAKE |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Cavity Heat Treatment | SNSPPU-CAV-PROC-HEAT |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Processing Travelers
Cavity
Cavity RF Tuning | SNSPPU-CAV-TUNE |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
IS there a cav RFIN traveler? |  |  |  |  | R1
Cavity String
Cryomodule
RF Processing (FPC RF Processing) | SNSPPU-CM-CST-FPC-HPRF |  |  |  | R1 |  |  |  | K. Wilson
Assembly Travelers
Cavity
SNS Helium Vessel Installation Traveler | SNSPPU-CAV-ASSY-HELV |  | 104211700-M8U-8200-A026 |  | R1 |  |  |  |  | 2020-02-01
High Beta Cavity Assembly for VTA testing | SNSPPU-CAV-ASSY (look at old SNS) |  | 104211800-M8U-8200-A00X |  | R1 |  |  |  |  | 2020-02-01
transfer to test stand
Cavity String
SNS High Beta Cavity String Traveler | SNSPPU-CST-ASSY |  |  |  | R1 |  |  |  |  | 2020-07-01
Cryomodule
Cryomodule Assembly | SNSPPU-CM-ASSY |  |  |  | R1 |  |  |  | M. Marchlik | 2020-12-01
Cold Mass Assembly | SNSPPU-CM-ASSY-CMAS |  |  |  | R1 |  |  |  |  | 2020-08-01
Cryomodule Thermal Shield-Spaceframe Assembly Traveler | SNSPPU-CM-ASSY-THRM |  | 104211100-M8U-8200-A002 104211100-M8U-8200-A014 104211100-M8U-8200-A025 |  | R1 |  |  |  | M. Marchlik
SNS High Beta Cryomodule Vacuum Vessel-End Can Assembly Traveler | SNSPPU-CM-ASSY-VV |  | 104210800-M8U-8200-A001 |  | R1
cm assy ship (rf, instrumentation)
Testing Travelers
Vertical Cavity Testing | SNSPPU-CAV-VTRF |  |  |  | R1 |  |  |  |  | 2020-04-01
Cavity VTA Cooldown | SNSPPU-CAV-VTA-COOL |  |  |  | R1 |  |  |  |  | 2020-02-01
Installation/Shipping Travelers
SNS Cryomodule Shipping | SNSPPU-CM-ASSY-SHIP |  |  |  | R1 |  |  |  |  | 2020-05-01
Standard Project Travelers
Detours, Deviations and Discrepancies (D3) | SNSPPU-D3 |  |  |  | R2 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A
Inspection Summary Report | SNSPPU-INSR |  |  |  | R1 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A
Inspection Nonconformance Report | SNSPPU-NCR |  |  |  | R10 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A