## TRAVELERS
| Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | Author | Reviewer | Reviewer | Project Manager | SOTR | NCR Informative | NCR Dispositioners | D3 Emails | Procedure(s), Name (if known) | Drawing(s), Name (if known) | Acronym from INV | Notes | Status | Section
Disassembly Travelers
Cavity
CP | Cavity Disassembly | C100R-CAV-DISA | R1 | 2018-11-28 | Dreyfuss | Forehand |  | Davis |  | forehand,areilly,kdavis,marhause | [6 empty] | CP
CP | Cavity Disassembly | C100R-CAV-DISA | R2 | 2018-11-28 | Dreyfuss | Forehand |  | Davis |  | forehand,areilly,kdavis,marhause | [6 empty] | CP
CP | Cavity Disassembly | C100R-CAV-DISA | R3 | 2018-11-28 | Dreyfuss | Forehand |  | Davis |  | forehand,areilly,kdavis,marhause | [6 empty] | CP
| Cavity String | [16 empty] | SS
OD | Cavity String Disassembly | C100R-CST-DISA | R1 | 2020-08-01 | Forehand | Dreyfuss |  | Davis
| Cryomodule | [16 empty] | SS
CP | C100R Disassembly Traveler | C100R-CM-DISA | R1 | 2018-09-24 | Fischer | Reilly | Legg | Hamlette |  | areilly,rlegg,fischer | [6 empty] | CP
CP | C100R Disassembly Traveler | C100R-CM-DISA | R2 |  | Fisher | Worland | Hamlette | Reilly | [8 empty] | CP
| Cavity Preparation | [16 empty] | SH
| Inspection | [16 empty] | SS
CP | Cavity CMM Receiving Inspectopn | C100R-CAV-INSP | R1 | 2018-11-30 | DeKerlegand | Marhauser |  | Reilly |  | ari,fischer,kdavis | [6 empty] | CP
CP | Cavity HOM Feedthru Receiving Inspection | C100R-CAV-INSP-HMFT | R1 | 2018-11-06 | HKPARK | [11 empty] | CP
CP | Cavity RF Inspection Receiving Inspection | C100R-CAV-INSP-HMFT | R2 | 2019-01-23 | HKPARK | [11 empty] | CP
CP | Cavity RF Inspection Receiving Inspection | C100R-CAV-INSP-HMFT | R3 | 2021-03-24 | HKPARK | [11 empty] | CP
CP | Cavity RF Inspection Receiving Inspection | C100R-CAV-RFIN | R1 | 2018-12-05 | Overton | Marhauser |  | Davis |  | forehand,areilly | [6 empty] | CP
OD | Window Leak Check | C100R-CAV-LEAK-WIN | R1 | 2021-05-01
CP | Secondary Waveguide Inspection (knife edge and sealing surface) | C100R-CAV-INSP-GVWG | R1 | 2019-01-15 | DeKerlegand | Davis | Fischer |  |  | kdavis,fischer,geroged | [6 empty] | CP
CP | C100R HOM Feedthru Receiving Inspection | C100R-VTA-HMFT-CSHK | R1 | 2021-03-29 | HyeKyoung Park | Danny Forehand | Justin Kent | Tony Reilly |  | lzhao | hkpark | Hkpark,lzhao,areilly |  |  |  |  | CP
CP | C100R leak check inspection traveler | C100R-CMA-HMFT-LEAK | R1 | 2021-03-29 | HyeKyoung Park | Chris Wilcox |  | Tony Reilly |  | lzhao | Hkpark | hpark,lzhao,areilly |  |  |  |  | CP
| Chemistry | [16 empty] | SS
CP | C100R Cavity Degreasing | C100R-CAV-CHEM-USC | R1 | 2019-01-08 | Fiedler | Mitchell |  | Davis |  | ashleya,kdavis,ari | [6 empty] | CP
CP | C100R Cavity HPR | C100R-CAV-CHEM-HPR | R1 | 2019-01-08 | Fiedler | Mitchell |  | Davis |  | ashleya,kdavis,ari | [6 empty] | CP
CP | C100R Cavity Flange Lapping | C100R-CAV-LAP | R1 | 2018-11-29 | Wildeson | Mitchell |  | Davis |  | ashleya,areilly | [6 empty] | CP
CP | C100R Cavity Flange Lapping | C100R-CAV-LAP | R2 | 2018-11-29 | Wildeson | Mitchell |  | Davis |  | ashleya,areilly | [6 empty] | CP
| Assembly | [16 empty] | SS
CP | C100R Cavity Assembly | C100R-CAV-ASSY | R1 | 2018-11-06 | Forehand | Dreyfuss |  | Davis | [8 empty] | CP
CP | C100R Cavity Assembly | C100R-CAV-ASSY | R2 | 2018-11-06 | Forehand | Dreyfuss |  | Davis | [8 empty] | CP
CP | C100R Cavity Tuning | C100R-CAV-TUNE | R1 | 2018-11-06 | Overton | Forehand |  | Davis |  | forehand,areilly | [6 empty] | CP
CP | C100R Helium Vessel Installation | C100R-CAV-ASSY-HELV | R2 | 2018-11-29 | Fischer | Legg | Worland | Reilly |  | fischer,marhause,areilly | [6 empty] | CP
CP | C100R Helium Vessel Installation Traveler | C100R-CAV-INST-HELV | R1 | 2018-11-29 | Fischer | Legg | Worland | Reilly |  | fischer,marhause,areilly | [6 empty] | CP
| Testing | [16 empty] | SS
OD | VTA HOM | C100R-CAV-VTA-HOM | R1 | 2021-05-01
CP | C100R Cavity VTA Test | C100R-CAV-VTRF | R1 | 2018-11-06 | Stirbet | C.Willson |  | Davis |  | stirbet,kdavis,areilly | [6 empty] | CP
| Component Preparation | [16 empty] | SH
| Inspection | [16 empty] | SS
CP | C100R Double Sided Rectangular Flange Inspection | C100R-CAV-INSP-DSRF | R1 | 2020-10-30 | S. WILLIAMS | [11 empty] | CP
CP | Secondary Waveguide Inspection (knife edge and sealing surface) | C100R-CAV-INSP-GVWG | R2 | 2019-01-15 | DeKerlegand | Davis | Fischer |  |  | kdavis,fischer,geroged | [6 empty] | CP
CP | Primary waveguide Inspection | C100R-CAV-INSP-WGD | R1 | 2019-01-16 | Williams | DeKerlegand |  | Davis |  | kdavis,ari | [6 empty] | CP
CP | Rework - 12 GeV Upgrade Waveguides | C100R-CAV-RWRK-WGD | R1 | 2019-02-19 | DeKerlegand |  |  | Davis |  | kdavis,ari | [6 empty] | CP
CP | Recycled Waveguide Inspection - 12 GeV Upgrade Waveguides | C100R-CAV-INSP-WGD-RCYC | R1 | 2019-01-25 | Williams | DeKerlegand |  | Davis |  | kdavis,ari | [6 empty] | CP
CP | Window Flange Inspection | C100R-INSP-WIN | R1 | 2020-09-23 | Williams | DeKerlegand |  | Davis |  | kdavis,ari | [6 empty] | CP
CP | C100R Brazement Adapter Assembly Receiving Inspection | C100R-INSP-ADPT | R1 | 2020-09-03 | Williams | DeKerlegand |  | Davis |  | kdavis,ari | [6 empty] | CP
CP | C100R Window Recycled Visual Inspection | C100R-CAV-INSP-WIN-RCYC | R1 | 2019-01-16 | Williams | DeKerlegand |  | Davis |  | kdavis,ari | [6 empty] | CP
| Chemistry | [16 empty] | SS
| Secondary waveguide cleaning | C100R-CAV-GVWG-CLN
CP | C100R Component Cleaning | C100R-CAV-CHEM-COMP | R1 | 2018-12-04 | Fiedler | Mitchell |  | Davis |  | ashleya,kdavis,ari | [6 empty] | CP
15 | C100R Cavity Component Cleaning | C100R-CST-CLN-COMP | R1 | 2021-05-15 | Wildeson | Mitchell |  | Davis
| Weld Inspection | [16 empty] | SS
CP | Waveguide and window Weldement Modification | C100R-WELD-WIN-ASSY | R1 | 2021-02-05 | Macha | Williams |  | Reilly |  | georged,lzhao | scott,edaly,forehand,areilly | scott,macha,areilly |  |  |  |  | CP
| Leak Checks | [16 empty] | SS
| Cavity String | [16 empty] | SH
| Inspection | [16 empty] | SS
| Chemistry | [16 empty] | SS
| Assembly | [16 empty] | SS
CP | C100R Cavity String Assembly | C100R-CST-ASSY | R1 | 2019-01-21 | Forehand | [11 empty] | CP
CP | C100R Cavity String Leak Test | C100R-CST-ASSY-LEAK | R1 | [13 empty] | CP
CP | C100R Waveguide Sub-Assembly & Leak Test | C100R-CST-ASSY-WGD | R1 | 2019-01-21 | Forehand | [11 empty] | CP
| Cryomodule | [16 empty] | SH
| Inspection | [16 empty] | SS
OD | C100R Cold Electrical Feedthru Receiving Inspection (C100) | C100R-CM-INSP-ELFT | R1 | 2018-11-06 | Fischer | King |  | Reilly |  | fischer,king,areilly
| Cryomodule Assembly | [16 empty] | SS
CP | C100R Cryomodule Final Assembly | C100R-CM-ASSY | R1 | 2019-02-11 | Fischer | [11 empty] | CP
CP | C100R Cold Mass Assembly | C100R-CM-ASSY-COLD | R1 | 2019-02-11 | Fischer | [11 empty] | CP
CP | C100R Thermal Shield and Space Frame Assembly | C100R-CM-ASSY-SFR | R1 | 2019-02-11 | Fischer | [11 empty] | CP
CP | C100R Vacuum Vessel and End Can Assembly | C100R-CM-ASSY-VV | R1 | 2019-02-11 | Fischer | [11 empty] | CP
| C100R Cryomodule Beampipe Assembly | C100R-CM-ASSY-BPIP | R1 | 2021-06-30 | Fischer
30 | C100R Cryomodule Final Assembly | C100R-CM-ASSY | R2 | 2021-06-01 | Fischer | Worland | Hamlette | Reilly
30 | C100R Cold Mass Assembly | C100R-CM-ASSY-COLD | R2 | 2021-06-01 | Fischer | Worland | Hamlette | Reilly
30 | C100R Thermal Shield and Space Frame Assembly | C100R-CM-ASSY-SFR | R2 | 2021-06-01 | Fischer | Worland | Hamlette | Reilly
30 | C100R Vacuum Vessel and End Can Assembly | C100R-CM-ASSY-VV | R2 | 2021-06-01 | Fischer | Worland | Hamlette | Reilly
30 | C100R Cryomodule Beampipe Assembly | C100R-CM-ASSY-BPIP | R2 | 2021-06-01 | Fischer | Worland | Hamlette | Reilly
| Cryomodule Testing | [16 empty] | SS
CP | C100R Cryomodule Acceptance Test | C100R-CM-ACTS | R1 | 2019-10-28 | Drury | [11 empty] | CP
CP | C100R Cryomodule Commissioning | C100R-CM-COMM | R1 | 2019-10-25 | Drury | [11 empty] | CP
| Cryomodule Installation & Commisioning | [16 empty] | SS
| C100R Cryomodule Tunnel Installation | C100R-CM-INST |  | 2021-10-01
| C100 Travelers NOT in C100R | [16 empty] | SH
OD | C100 Cavity Assembly, Evacuation, and Leak Test | C100-CAV-ASSY2 | R3 | 2011-05-13 | Steve Castagnola
OD | C100 Cavity Bake-out | C100-CAV-BAKE | R2 | 2011-05-16 | Kurt Macha
OD | C100 BCP | C100-CAV-CHEM | R1 | 2010-04-19 | Teena Harris
OD | C100 Cavity Degrease | C100-CAV-DEGR | R3 | 2011-04-15 | James Davenport
OD | 7 Cell Cavity Electropolish with Cavity Cooling System | C100-CAV-EPOL | R2 | 2011-04-15 | James Davenport
OD | C100 Cavity Heat Treatment | C100-CAV-HEAT | R1 | 2010-05-24 | D. Forehand
OD | C100-CAV-INSP-ASSY-WIN | C100-CAV-INSP-ASSY-WIN | R3 | 2011-08-25 | HyeKyoung Park
OD | C100 Cold Tuner Receiving Inspection | C100-CAV-INSP-CTUN | R1 | 2010-02-15 | J. Matalevich
OD | C100 Cold Tuner Expanded Inspection | C100-CAV-INSP-CTUN2 | R1 | 2010-02-25 | J. Matalevich
OD | C100 Double Sided Rectangular Flange Receiving Inspection Traveler | C100-CAV-INSP-FLNG | R2 | 2011-02-03 | HyeKyoung Park
OD | C100 Field Probe Feedthrough Inspection Traveler | C100-CAV-INSP-FPF | R1 | 2010-07-06 | Kurt Macha
OD | C100 Guard Vacuum Waveguide Flange Receiving Inspection Traveler | C100-CAV-INSP-GVWF | R2 | 2010-09-01 | Katherine Wilson
OD | 12GeV Upgrade Cryomodule Cryogenic Circuit Components | C100-CAV-INSP-HEHD | R2 | 2010-06-01 | Gary Cheng
OD | C100 Cavity HOM Feedthru Receiving Inspection | C100-CAV-INSP-HMFT | R6 | 2011-08-25 | HyeKyoung Park
OD | 12GeV Upgrade Cryomodule Inner Magnetic Shield | C100-CAV-INSP-IMAG | R1 | 2010-07-19 | Gary Cheng
OD | 12GeV Upgrade Cryomodule 50K Thermal Shield Components | C100-CAV-INSP-THRM | R1 | 2010-02-24 | Karl Smith
OD | 12GeV Upgrade Cryomodule Vacuum Vessel | C100-CAV-INSP-VV | R2 | 2010-06-24 | Gary Cheng
OD | C100 Cavity CMM Post-tuning Inspection | C100-CAV-INSP2 | R3 | 2010-09-29 | Brian Carpenter
OD | C100 Top Hat Flange Lapping | C100-CAV-LAP-THAT | R1 | 2011-03-14 | Isiah Daniels
OD | C100 (CEBAF 12 GeV cryomodule upgrade) Cavity VTA Cooldown | C100-CAV-VTA-COOL | R1 | 2011-05-02 | T. Bass
OD | C100 Coaxial Cables Assembly and Qualification | C100-CM-ASSY-COAX | R1 | 2013-09-05 | L. King
OD | C100 Helium Vessel Removal Traveler | C100-CM-DIS-HELV | R1 | 2009-12-10 | John Fischer
OD | C100 Cryomodule Acceptance Test - High Power Testing | C100-CM-HPRF-ACTS | R1 | 2011-06-22 | M. Drury
OD | 10 PIN DOUBLE ENDED CONNECTOR, used as vacuum vessel electrical feedthrough | C100-CM-INSP-10FT | R1 | 2010-12-10 | John Fischer
OD | 19 PIN CONNECTOR, used as vacuum vessel electrical feedthrough | C100-CM-INSP-19FT | R1 | 2010-12-10 | John Fischer
OD | 32 PIN CONNECTOR, used as vacuum vessel electrical feedthrough | C100-CM-INSP-32FT | R1 | 2010-12-10 | John Fischer
OD | C100 Si Diodes Receiving Inspection | C100-CM-INSP-DIO | R1 | 2011-02-23 | M. Stirbet
OD | 12GeV 8 pin Cryogenic Feedthrus | C100-CM-INSP-ELFT | R2 | 2018-05-03 | John Fischer
OD | 12GeV Upgrade Cryomodule Cryogenic Circuit Components | C100-CM-INSP-HEHD | R2 | 2010-06-01 | Gary Cheng
OD | 12GeV Upgrade Cryomodule Helium Vessel | C100-CM-INSP-HELV | R2 | 2010-04-20 | Gary Cheng
OD | 12GeV Upgrade Cryomodule Helium Vessel Head Assemblies | C100-CM-INSP-HVHD | R1 | 2010-10-19 | Gary Cheng
OD | 12GeV Upgrade Cryomodule Inner Magnetic Shield | C100-CM-INSP-IMAG | R3 | 2011-01-13 | Gary Cheng
OD | Receiving Inspection - Instrumentation Feedthrough Flange | C100-CM-INSP-INFF | R1 | 2010-11-01 | Joshua Feingold
OD | 12GeV- ¿N-TYPE VacuumVessel Feedthrus | C100-CM-INSP-NTFT | R1 | 2010-12-14 | John Fischer
OD | 12GeV Upgrade Cryomodule Outer Magnetic Shield | C100-CM-INSP-OMAG | R2 | 2011-05-10 | Gary Cheng
OD | 12GeV Upgrade Cryomodule Secondary Outer Magnetic Shield | C100-CM-INSP-OMAGS | R1 | 2011-04-27 | Gary Cheng
OD | C100 End Cans | C100-CM-INSP-RENC | R1 | 2010-09-09 | Brian Carpenter
OD | C100 Return Beam Pipe Receiving Inspection | C100-CM-INSP-RTBP | R1 | 2010-12-15 | J. Matalevich
OD | C100 Supply End Cans | C100-CM-INSP-SENC | R1 | 2010-09-27 | Brian Carpenter
OD | C100 Supply Beam Pipe Receiving Inspection | C100-CM-INSP-SUBP | R1 | 2010-12-15 | J. Matalevich
OD | 12 GeV Waveguide Sweeps | C100-CM-INSP-SWEEP | R1 | 2011-02-22 | Katherine Wilson
OD | 12GeV Upgrade Cryomodule 50K Thermal Shield Components | C100-CM-INSP-THRM | R2 | 2010-08-26 | Karl Smith
OD | 12 GeV Tophats (Double) | C100-CM-INSP-TPHTD | R1 | 2011-02-14 | Katherine Wilson
OD | 12 GeV Tophats (Single) | C100-CM-INSP-TPHTS | R1 | 2011-01-31 | Katherine Wilson
OD | 12GeV Sapphire Viewport | C100-CM-INSP-VPFT | R1 | 2010-12-06 | John Fischer
OD | 12GeV Upgrade Cryomodule Vacuum Vessel | C100-CM-INSP-VV | R3 | 2010-03-26 | Gary Cheng
OD | 12 GeV Waveguide Supports | C100-CM-INSP-WSPT | R1 | 2011-01-31 | Katherine Wilson
OD | C100 Warm Tuner Receiving Inspection | C100-CM-INSP-WTUN | R1 | 2010-08-15 | J. Matalevich
OD | C100 CRYOMODULE TUNNEL INSTALLATION | C100-CM-INST | R1 | 2010-07-21 | Frank Humphry
OD | C100 Supply and return beam pipe assemblies | C100-CST-ASSY-BPIP | R1 | 2011-04-25 | Kurt Macha
OD | C100 Waveguide sub-assembly and leak test traveler | C100-CST-ASSY-WGD | R1 | 2010-06-06 | Kurt Macha
OD | C100 cavity string component cleaning | C100-CST-CLN-COMP | R1 | 2010-08-25 | James Davenport
| Standard Project Travelers | [16 empty] | SH
CP | C100R Non-Conformance Report | C100R-NCR | R11 |  | V. Bookwalter | A. McEwen |  | A. Reilly | [8 empty] | CP
CP | C100R Detours, Deviations and Discrepencies | C100R-D3 | R2 |  | V. Bookwalter | A. McEwen |  | A. Reilly | [8 empty] | CP
CP | C100R Inspection Summary Report | C100R-INSR | R1 |  | A. DeKerlegand | A. McEwen |  | A. Reilly | [8 empty] | CP
Color Legend |  | Count | Percent
CP | Complete (CP) | 43 | 39.81%
NR | New Revision Out for Approval (NR) | 0 | 0%
OA | Out for Approval (OA) | 0 | 0%
30 | Due in 30 Days | 5 | 4.63%
15 | Due in 15 Days | 1 | 0.9259%
OD | Overdue | 56 | 51.85%
| Remaining | 3 | 2.778%
| Total Traveler IDs | 108

## C100R
TRAV_ID | TRAV_REVISION | TRAV_DATE | TRAV_AUTHOR | SIGNER1 | SIGNER2 | SIGNER3 | SIGNER4 | TRAV_TITLE | TRAV_MAX_PAGE | SERIALID
C100R-CAV-ASSY | R2 | 2018-11-06 | Alex Wildeson | Danny Forehand | Kirk Davis | Anthony Reilly |  | C100R Cavity Assembly | 1 | CAVSN
C100R-CAV-ASSY-HELV | R1 | 2019-01-09 | J. Fischer | J. Fischer | B. Legg | A. Reilly | K. Worland | C100R Helium Vessel Installation Traveler | 4 | CAVSN
C100R-CAV-CHEM-COMP | R1 | 2019-02-05 | A. Anderson Mitchell | A. Anderson Mitchell | K. Davis | A. Reilly |  | C100 components cleaning | 1 | HMFTSN
C100R-CAV-CHEM-HPR | R1 | 2018-12-04 | Ashley Mitchell | A. Mitchell | K. Davis | A. Palczewski |  | Standard Traveler for Cavity High Pressure Rinse Processing | 1 | CAVSN
C100R-CAV-CHEM-USC | R1 | 2018-12-04 | Ashley Mitchell | A. Mitchell | K. Davis | A. Palczewski |  | C100R Cavity Degrease | 1 | CAVSN
C100R-CAV-DISA | R3 | 2018-11-28 | A. Wildeson | A. Wildeson | D. Forehand | K. Davis |  | C-100R Cavity Disassembly | 1 | CAVSN
C100R-CAV-INSP | R1 | 2018-11-30 | A. DeKerlegand | A. DeKerlegand | Frank Marhauser | A. Reilly |  | Receiving inspection for C100R Cavities | 4 | CAVSN
C100R-CAV-INSP-DSRF | R1 | 2020-09-30 | Scott Williams | S. Williams | A. DeKerlegand | A. Reilly |  | C100R Double Sided Rectangular Flange Receiving Inspection Traveler | 3 | DSRFSN
C100R-CAV-INSP-HMFT | R3 | 2021-03-24 | HyeKyoung Park | HyeKyoung Park | Liang Zhao | Tony Reilly |  | C100R Cavity HOM Feedthru Receiving Inspection | 3 | HMFTSN
C100R-CAV-INSP-WGD | R1 | 2019-01-16 | S. Williams | S. Williams | Ari | K Davis |  | Receiving Inspection - 12 GeV Upgrade Waveguides | 5 | WGDSN
C100R-CAV-INSP-WGD-RCYC | R1 | 2019-01-25 | S. Williams | S. Williams | A. Palczewski | K. Davis |  | Recycled Waveguide Inspection - 12 GeV Upgrade Waveguides | 3 | WGDSN
C100R-CAV-INSP-WIN-RCYC | R1 | 2019-01-16 | S. Williams | S. Williams | K. Davis | A. Reilly |  | C100RWindow Recycled Visual Inspection | 1 | WINSN
C100R-CAV-INST-HELV | R1 | 2018-11-29 | J. Fischer | J. Fischer | F. Marhauser | A. Reilly |  | C100R Helium Vessel Installation Traveler | 4 | CAVSN
C100R-CAV-LAP | R2 | 2018-11-29 | C. Johnson | C. Johnson | A. Mitchell | A. Reilly |  | C100R Cavity Flange Lapping | 2 | CAVSN
C100R-CAV-RFIN | R1 | 2018-12-05 | A. Wildeson | A. Wildeson | F. Marhauser | D. Forehand |  | C100R Cavity RF Incoming Inspection Traveler | 1 | CAVSN
C100R-CAV-RWRK-WGD | R1 | 2019-02-21 | G. DeKerlegand | G. DeKerlegand | K. Davis | A. Reilly |  | Rework - 12 GeV Upgrade Waveguides | 1 | WGDSN
C100R-CAV-TUNE | R1 | 2018-11-06 | D. Forehand | D. Forehand | K. Davis | A. Reilly |  | C100R Cavity Tuning Traveler | 5 | CAVSN
C100R-CAV-VTRF | R1 | 2018-11-06 | M. Stirbet | M. Stirbet | K. Davis | A. Reilly |  | C100R (CEBAF 12 GeV Cryomodule Upgrade) Vertical cavity Testing | 4 | CAVSN
C100R-CM-ACTS | R1 | 2019-10-28 | M. Drury | M. Drury | A. Solopova | A. Reilly |  | C100R Cryomodule Acceptance Test ¿ Cryocycle | 10 | CMSN
C100R-CM-ASSY | R1 | 2020-01-22 | J. Fischer | J. Fischer | K. Worland | T. Reilly |  | C100R Cryomodule Final Assembly Traveler | 3 | CMSN
C100R-CM-ASSY-COLD | R1 | 2019-02-25 | John Fischer | John Fischer | Robert Legg | Tony Reilly | Dave Hamlette | C100R COLD MASS ASSEMBLY | 6 | CMSN
C100R-CM-ASSY-SFR | R1 | 2019-03-04 | John Fischer | John Fischer | Robert Legg | Tony Reilly | Dave Hamlette | C100R Thermal Shield and Spaceframe Assembly | 4 | CMSN
C100R-CM-ASSY-VV | R1 | 2019-03-05 | John Fischer | John Fischer | Tony Reilly | Dave Hamlette |  | C100R Vacuum Vessel and End Can Assembly | 4 | CMSN
C100R-CM-COMM | R1 | 2019-10-25 | M. Drury | M. Drury | A. Solopova | A. Reilly |  | C100R Cryomodule Commissioning | 25 | CMSN
C100R-CM-DISA | R2 | 2020-09-17 | John Fischer | John Fischer | Tony Reilly | Ken Worland | Dave Hamlette | C100 Disassembly Traveler | 14 | CMSN
C100R-CM-INSP-GVWG | R2 | 2019-01-15 | A. DeKerlegand | A. DeKerlegand | K. Davis | J. Fischer |  | 12 GeV Guard Vacuum Waveguide | 5 | GVWGSN
C100R-CMA-HMFT-LEAK | R1 | 2021-03-29 | HyeKyoung Park | HyeKyoung Park | Chris Wilcox | Tony Reilly |  | C100R leak check inspection traveler | 1 | HMFTSN
C100R-CST-ASSY | R1 | 2019-02-01 | D. Forehand | D. Forehand | K. Davis | T. Reilly |  | C100R Cavity String Assdembly Traveler | 11 | CSTSN
C100R-CST-ASSY-LEAK | R1 | 2019-02-27 | Danny Forehand | Danny Forehand | Kirk Davis | Tony Reilly |  | C100R Cavity string leak test | 3 | CMSN
C100R-CST-ASSY-WGD | R1 | 2019-02-07 | D. Forehand | D. Forehand | D. Forehand | D. Forehand |  | C100R Waveguide sub-assembly and leak test traveler | 1 | WGDSN
C100R-D3 | R2 | 2019-08-14 | M. McDonald | M. McDonald | V. Bookwalter | A. McEwen |  | Detours, Deviations and Discrepancies (D3) | 1 | SN
C100R-INSP-ADPT | R1 | 2020-09-03 | Scott Williams | S. Williams | K. Macha | A. Reilly |  | C100R Brazement Adapter Assembly Receiving Inspection Traveler | 5 | WBASN
C100R-INSP-WIN | R1 | 2020-09-23 | S. Williams | S. Williams | K. Macha | A. Reilly |  | Window Flange Inspection | 2 | WINSN
C100R-INSR | R1 | 2016-03-21 | G. DeKerlegand | G. DeKerlegand | A. McEwen | A. Reilly |  | Inspection Summary Report | 1 | CMSN
C100R-NCR | R11 | 2018-02-26 | M. McDonald | M. McDonald | V. Bookwalter | A. McEwen | M. Dickey | Non-Conformance Report for Multiple Reworks | 4 | SN
C100R-VTA-HMFT-CSHK | R1 | 2021-03-29 | HyeKyoung Park | HyeKyoung Park | Danny Forehand | Justin Kent | Tony Reilly | C100R HOM Feedthru Receiving Inspection | 1 | HMFTSN
C100R-WELD-WIN-ASSY | R1 | 2021-02-05 | Kurt Macha | Kurt Macha | Scott Williams | Tony Reilly |  | Waveguide and window weldment modification | 3 | WINSN

## C100
Traveler Id | Rev No | Traveler Name | Author | Date
C100-CAV-ASSY | R1 | C100 Cavity Assembly | Steve Castagnola | 07-Jun-2010
C100-CAV-ASSY | R2 | C100 Cavity Assembly | Steve Castagnola | 13-May-2011
C100-CAV-ASSY | R3 | C100 Cavity Assembly | Steve Castagnola | 31-May-2011
C100-CAV-ASSY2 | R1 | C100 Cavity Assembly, Evacuation, and Leak Test | Steve Castagnola | 08-Jun-2010
C100-CAV-ASSY2 | R2 | C100 Cavity Assembly, Evacuation, and Leak Test | Steve Castagnola | 03-May-2011
C100-CAV-ASSY2 | R3 | C100 Cavity Assembly, Evacuation, and Leak Test | Steve Castagnola | 13-May-2011
C100-CAV-BAKE | R1 | C100 Cavity Bake-out | Kurt Macha | 12-Jun-2010
C100-CAV-BAKE | R2 | C100 Cavity Bake-out | Kurt Macha | 16-May-2011
C100-CAV-CHEM | R1 | C100 BCP | Teena Harris | 19-Apr-2010
C100-CAV-D3 | R1 | D3s for CAVITY processing | V. Bookwalter | 15-Jan-2010
C100-CAV-DEGR | R1 | C100 Cavity Degrease | Dia Williams | 19-Apr-2010
C100-CAV-DEGR | R2 | C100 Cavity Degrease | James Davenport | 06-Dec-2010
C100-CAV-DEGR | R3 | C100 Cavity Degrease | James Davenport | 15-Apr-2011
C100-CAV-EPOL | R1 | 7 Cell Cavity Electropolish with Cavity Cooling System | James H. Davenport II | 19-Apr-2010
C100-CAV-EPOL | R2 | 7 Cell Cavity Electropolish with Cavity Cooling System | James Davenport | 15-Apr-2011
C100-CAV-HEAT | R1 | C100 Cavity Heat Treatment | D. Forehand | 24-May-2010
C100-CAV-HPR | R1 | HPR C100 Cavities | Sarah Tipton | 19-May-2010
C100-CAV-HPR | R2 | HPR C100 Cavities | James Davenport | 15-Apr-2011
C100-CAV-INSP | R1 | Receiving inspection for C100 Cavities | Brian Carpenter | 20-Apr-2010
C100-CAV-INSP | R2 | Receiving inspection for C100 Cavities | Brian Carpenter | 20-Apr-2010
C100-CAV-INSP | R3 | Receiving inspection for C100 Cavities | Brian Carpenter | 20-Apr-2010
C100-CAV-INSP-ADPT | R1 | C100 Brazement Adapter Assembly Receiving Inspection Traveler | HyeKyoung Park | 27-Jul-2010
C100-CAV-INSP-ADPT | R2 | C100 Brazement Adapter Assembly Receiving Inspection Traveler | HyeKyoung Park | 24-Sep-2010
C100-CAV-INSP-ADPT | R3 | C100 Brazement Adapter Assembly Receiving Inspection Traveler | HyeKyoung Park | 03-Mar-2010
C100-CAV-INSP-ADPT | R4 | C100 Brazement Adapter Assembly Receiving Inspection Traveler | HyeKyoung Park | 25-Aug-2011
C100-CAV-INSP-ASSY-WIN | R1 | C100-CAV-INSP-ASSY-WIN | HyeKyoung Park | 24-Sep-2010
C100-CAV-INSP-ASSY-WIN | R2 | C100-CAV-INSP-ASSY-WIN | HyeKyoung Park | 16-Nov-2010
C100-CAV-INSP-ASSY-WIN | R3 | C100-CAV-INSP-ASSY-WIN | HyeKyoung Park | 25-Aug-2011
C100-CAV-INSP-CTUN | R1 | C100 Cold Tuner Receiving Inspection | J. Matalevich | 15-Feb-2010
C100-CAV-INSP-CTUN2 | R1 | C100 Cold Tuner Expanded Inspection | J. Matalevich | 25-Feb-2010
C100-CAV-INSP-FLNG | R1 | C100 Double Sided Rectangular Flange Receiving Inspection Traveler | HyeKyoung Park | 29-Jul-2010
C100-CAV-INSP-FLNG | R2 | C100 Double Sided Rectangular Flange Receiving Inspection Traveler | HyeKyoung Park | 03-Feb-2011
C100-CAV-INSP-FPF | R1 | C100 Field Probe Feedthrough Inspection Traveler | Kurt Macha | 06-Jul-2010
C100-CAV-INSP-GVWF | R1 | C100 Guard Vacuum Waveguide Flange Receiving Inspection Traveler | Katherine Wilson | 01-Sep-2010
C100-CAV-INSP-GVWF | R2 | C100 Guard Vacuum Waveguide Flange Receiving Inspection Traveler | Katherine Wilson | 01-Sep-2010
C100-CAV-INSP-HEHD | R1 | Receiving Inspection of 12GeV Upgrade Cryomodule Cryogenic Circuit Components | Gary Cheng | 27-Jan-2010
C100-CAV-INSP-HEHD | R2 | Receiving Inspection of 12GeV Upgrade Cryomodule Cryogenic Circuit Components | Gary Cheng | 01-Jun-2010
C100-CAV-INSP-HELV | R1 | Receiving Inspection of 12GeV Upgrade Cryomodule Helium Vessel | Gary Cheng | 20-Apr-2010
C100-CAV-INSP-HMFT | R1 | C100 Cavity HOM Feedthru Receiving Inspection | HyeKyoung Park | 27-Jul-2010
C100-CAV-INSP-HMFT | R2 | C100 Cavity HOM Feedthru Receiving Inspection | HyeKyoung Park | 17-Aug-2010
C100-CAV-INSP-HMFT | R3 | C100 Cavity HOM Feedthru Receiving Inspection | HyeKyoung Park | 09-Sep-2010
C100-CAV-INSP-HMFT | R4 | C100 Cavity HOM Feedthru Receiving Inspection | HyeKyoung Park | 20-Apr-2011
C100-CAV-INSP-HMFT | R5 | C100 Cavity HOM Feedthru Receiving Inspection | HyeKyoung Park | 09-Jun-2011
C100-CAV-INSP-HMFT | R6 | C100 Cavity HOM Feedthru Receiving Inspection | HyeKyoung Park | 25-Aug-2011
C100-CAV-INSP-IMAG | R1 | Receiving Inspection of 12GeV Upgrade Cryomodule Inner Magnetic Shield | Gary Cheng | 19-Jul-2010
C100-CAV-INSP-THRM | R1 | Receiving Inspection of 12GeV Upgrade Cryomodule 50K Thermal Shield Components | Karl Smith | 24-Feb-2010
C100-CAV-INSP-VV | R1 | Receiving Inspection of 12GeV Upgrade Cryomodule Vacuum Vessel | Gary Cheng | 26-Mar-2010
C100-CAV-INSP-VV | R2 | Receiving Inspection of 12GeV Upgrade Cryomodule Vacuum Vessel | Gary Cheng | 24-Jun-2010
C100-CAV-INSP-WGD | R1 | Receiving Inspection ¿ 12 GeV Upgrade Waveguides | Katherine Wilson | 21-Jun-2009
C100-CAV-INSP-WGD | R2 | Receiving Inspection ¿ 12 GeV Upgrade Waveguides | Katherine Wilson | 21-Jun-2009
C100-CAV-INSP-WGD | R3 | Receiving Inspection ¿ 12 GeV Upgrade Waveguides | Katherine Wilson | 21-Jan-2010
C100-CAV-INSP-WGD | R4 | Receiving Inspection - 12 GeV Upgrade Waveguides | Katherine Wilson | 01-Jun-2010
C100-CAV-INSP-WGD | R5 | Receiving Inspection - 12 GeV Upgrade Waveguides | Katherine Wilson | 01-Jun-2010
C100-CAV-INSP-WGD | R6 | Receiving Inspection - 12 GeV Upgrade Waveguides | Katherine Wilson | 15-Mar-2011
C100-CAV-INSP2 | R1 | C100 Cavity CMM Post-tuning Inspection | Brian Carpenter | 07-Jun-2010
C100-CAV-INSP2 | R2 | C100 Cavity CMM Post-tuning Inspection | Brian Carpenter | 29-Sep-2010
C100-CAV-INSP2 | R3 | C100 Cavity CMM Post-tuning Inspection | Brian Carpenter | 29-Sep-2010
C100-CAV-INST-HELV | R1 | C100 HELIUM VESSEL INSTALLATION TRAVELER | John Fischer | 24-Aug-2010
C100-CAV-INST-HELV | R2 | C100 Helium Vessel Installation Traveler | John Fischer | 24-Aug-2010
C100-CAV-LAP | R1 | C100 Cavity Flange Lapping | Isiah Daniels | 27-Oct-2010
C100-CAV-LAP | R2 | C100 Cavity Flange Lapping | Isiah Daniels | 19-Nov-2010
C100-CAV-LAP-THAT | R1 | C100 Top Hat Flange Lapping | Isiah Daniels | 14-Mar-2011
C100-CAV-NCR | R1 | JLAB Non-Conformance Report | V. Bookwalter | 15-Jan-2010
C100-CAV-NCR | R5 | JLAB Non-Conformance Report | V. Bookwalter | 15-Jan-2010
C100-CAV-NCR | R6 | NCRs for CAVITY processing | V. Bookwalter | 30-Apr-2010
C100-CAV-NCR | R7 | Non-Conformance Report | V. Bookwalter | 07-Sep-2011
C100-CAV-RFIN | R1 | C100 Cavity RF Incoming Inspection Traveler | D. Forehand | 23-Aug-2010
C100-CAV-RFIN | R2 | C100 Cavity RF Incoming Inspection Traveler | D. Forehand | 22-Nov-2010
C100-CAV-RWRK-WGD | R1 | Rework ¿ 12 GeV Upgrade Waveguides | Katherine Wilson | 31-Jan-2011
C100-CAV-RWRK-WGD | R2 | Rework - 12 GeV Upgrade Waveguides | Katherine Wilson
C100-CAV-RWRK-WGD | R3 | Rework - 12 GeV Upgrade Waveguides | Katherine Wilson | 14-Feb-2011
C100-CAV-RWRK-WGD | R4 | Rework - 12 GeV Upgrade Waveguides | Katherine Wilson | 14-Feb-2011
C100-CAV-THKN | R1 | C100 (CEBAF 12 GeV cryomodule upgrade) Cavity wall US thickness measurements | M. Stirbet | 26-Apr-2010
C100-CAV-TUNE | R1 | C100 Cavity Tuning Traveler | D. Forehand | 11-Oct-2010
C100-CAV-TUNE | R2 | C100 Cavity Tuning Traveler | D. Forehand | 17-Nov-2010
C100-CAV-TUNE | R3 | C100 Cavity Tuning Traveler | D. Forehand | 02-Dec-2010
C100-CAV-TUNE | R4 | C100 Cavity Tuning Traveler | D. Forehand | 28-Mar-2011
C100-CAV-VTA-COOL | R1 | C100 (CEBAF 12 GeV cryomodule upgrade) Cavity VTA Cooldown | T. Bass | 02-May-2011
C100-CAV-VTRF | R1 | C100 (CEBAF 12 GeV Cryomodule Upgrade) Vertical Cavity Testing | M. Stirbet | 12-Apr-2010
C100-CAV-VTRF | R2 | C100 (CEBAF 12 GeV cryomodule upgrade) Vertical Cavity Testing | M. Stirbet | 28-Jun-2010
C100-CAV-VTRF | R3 | C100 (CEBAF 12 GeV cryomodule upgrade) Vertical cavity Testing | M. Stirbet | 18-Jan-2011
C100-CAV-VTRF | R4 | C100 (CEBAF 12 GeV Cryomodule Upgrade) Vertical cavity Testing | M. Stirbet | 15-Nov-2011
C100-CM-ASSY | R1 | C100 Cryomodule Final Assembly Traveler | John Fischer | 10-May-2011
C100-CM-ASSY-COAX | R1 | C100 Coaxial Cables Assembly and Qualification | L. King | 05-Sep-2013
C100-CM-ASSY-COLD | R1 | C100 COLD MASS ASSEMBLY | John Fischer | 22-Sep-2010
C100-CM-ASSY-COLD | R2 | C100 COLD MASS ASSEMBLY | John Fischer | 22-Sep-2010
C100-CM-ASSY-COLD | R3 | C100 COLD MASS ASSEMBLY | John Fischer | 03-Jan-2011
C100-CM-ASSY-COLD | R4 | C100 COLD MASS ASSEMBLY | John Fischer | 03-Oct-2011
C100-CM-ASSY-SFR | R1 | C100 Thermal Shield and Spaceframe Assembly | John Fischer | 23-Feb-2011
C100-CM-ASSY-VV | R1 | C100 Vacuum Vessel and End Can Assembly | John Fischer | 10-May-2011
C100-CM-COMM | R1 | C100 Cryomodule Commissioning | Michael Drury | 29-Dec-2012
C100-CM-CRYO-ACTS | R1 | C100 Cryomodule Acceptance Test - Cryocycle | M. Drury | 21-Jun-2011
C100-CM-DIS-HELV | R1 | C100 Helium Vessel Removal Traveler | John Fischer | 10-Dec-2009
C100-CM-HPRF-ACTS | R1 | C100 Cryomodule Acceptance Test - High Power Testing | M. Drury | 22-Jun-2011
C100-CM-INSP-10FT | R1 | Receiving Inspection for 10 PIN DOUBLE ENDED CONNECTOR, used as vacuum vessel electrical feedthrough for C100 cryomodule. | John Fischer | 10-Dec-2010
C100-CM-INSP-19FT | R1 | Receiving Inspection for 19 PIN CONNECTOR, used as vacuum vessel electrical feedthrough for C100 cryomodule. | John Fischer | 10-Dec-2010
C100-CM-INSP-32FT | R1 | Receiving Inspection for 32 PIN CONNECTOR, used as vacuum vessel electrical feedthrough for C100 cryomodule. | John Fischer | 10-Dec-2010
C100-CM-INSP-CTUN | R1 | C100 Cold Tuner Receiving Inspection | J. Matalevich | 15-Feb-2010
C100-CM-INSP-CTUN2 | R1 | C100 Cold Tuner Expanded Inspection | J. Matalevich
C100-CM-INSP-DIO | R1 | C100 Si Diodes Receiving Inspection | M. Stirbet | 23-Feb-2011
C100-CM-INSP-ELFT | R1 | Receiving Inspection for 12GeV 8 pin Cryogenic Feedthrus | John Fischer | 06-Sep-2010
C100-CM-INSP-ELFT | R2 | Receiving Inspection for 12GeV 8 pin Cryogenic Feedthrus | John Fischer | 03-May-2018
C100-CM-INSP-GVWF | R1 | C100 Guard Vacuum Waveguide Flange Receiving Inspection Traveler | Katherine Wilson | 01-Sep-2010
C100-CM-INSP-GVWF | R2 | C100 Guard Vacuum Waveguide Flange Receiving Inspection Traveler | Katherine Wilson | 01-Sep-2010
C100-CM-INSP-GVWG | R1 | 12 GeV Guard Vacuum Waveguide | Katherine Wilson | 15-Feb-2011
C100-CM-INSP-HEHD | R1 | Receiving Inspection of 12GeV Upgrade Cryomodule Cryogenic Circuit Components | Gary Cheng | 27-Jan-2010
C100-CM-INSP-HEHD | R2 | Receiving Inspection of 12GeV Upgrade Cryomodule Cryogenic Circuit Components | Gary Cheng | 01-Jun-2010
C100-CM-INSP-HELV | R1 | Receiving Inspection of 12GeV Upgrade Cryomodule Helium Vessel | Gary Cheng | 20-Apr-2010
C100-CM-INSP-HELV | R2 | Receiving Inspection of 12GeV Upgrade Cryomodule Helium Vessel | Gary Cheng | 20-Apr-2010
C100-CM-INSP-HVHD | R1 | Receiving Inspection of 12GeV Upgrade Cryomodule Helium Vessel Head Assemblies | Gary Cheng | 19-Oct-2010
C100-CM-INSP-IMAG | R1 | Receiving Inspection of 12GeV Upgrade Cryomodule Inner Magnetic Shield | Gary Cheng | 19-Jul-2010
C100-CM-INSP-IMAG | R2 | Receiving Inspection of 12GeV Upgrade Cryomodule Inner Magnetic Shield | Gary Cheng | 19-Oct-2010
C100-CM-INSP-IMAG | R3 | Receiving Inspection of 12GeV Upgrade Cryomodule Inner Magnetic Shield | Gary Cheng | 13-Jan-2011
C100-CM-INSP-INFF | R1 | Receiving Inspection - Instrumentation Feedthrough Flange | Joshua Feingold | 01-Nov-2010
C100-CM-INSP-NTFT | R1 | Receiving Inspection for 12GeV- ¿N-TYPE VacuumVessel Feedthrus | John Fischer | 14-Dec-2010
C100-CM-INSP-OMAG | R1 | Receiving Inspection of 12GeV Upgrade Cryomodule Outer Magnetic Shield | Gary Cheng | 13-Sep-2010
C100-CM-INSP-OMAG | R2 | Receiving Inspection of 12GeV Upgrade Cryomodule Outer Magnetic Shield | Gary Cheng | 10-May-2011
C100-CM-INSP-OMAGS | R1 | Receiving Inspection of 12GeV Upgrade Cryomodule Secondary Outer Magnetic Shield | Gary Cheng | 27-Apr-2011
C100-CM-INSP-RENC | R1 | Receiving Inspection for C100 End Cans | Brian Carpenter | 09-Sep-2010
C100-CM-INSP-RTBP | R1 | C100 Return Beam Pipe Receiving Inspection | J. Matalevich | 15-Dec-2010
C100-CM-INSP-SENC | R1 | Receiving Inspection for C100 Supply End Cans | Brian Carpenter | 27-Sep-2010
C100-CM-INSP-SFR | R1 | C100 Space Frame Receiving Inspection | J. Matalevich | 15-May-2010
C100-CM-INSP-SUBP | R1 | C100 Supply Beam Pipe Receiving Inspection | J. Matalevich | 15-Dec-2010
C100-CM-INSP-SWEEP | R1 | 12 GeV Waveguide Sweeps | Katherine Wilson | 22-Feb-2011
C100-CM-INSP-THRM | R1 | Receiving Inspection of 12GeV Upgrade Cryomodule 50K Thermal Shield Components | Karl Smith | 24-Feb-2010
C100-CM-INSP-THRM | R2 | Receiving Inspection of 12GeV Upgrade Cryomodule 50K Thermal Shield Components | Karl Smith | 26-Aug-2010
C100-CM-INSP-TPHTD | R1 | 12 GeV Tophats (Double) | Katherine Wilson | 14-Feb-2011
C100-CM-INSP-TPHTS | R1 | 12 GeV Tophats (Single) | Katherine Wilson | 31-Jan-2011
C100-CM-INSP-VPFT | R1 | Receiving Inspection for 12GeV Sapphire Viewport | John Fischer | 06-Dec-2010
C100-CM-INSP-VV | R1 | Receiving Inspection of 12GeV Upgrade Cryomodule Vacuum Vessel | Gary Cheng | 26-Mar-2010
C100-CM-INSP-VV | R2 | Receiving Inspection of 12GeV Upgrade Cryomodule Vacuum Vessel | Gary Cheng | 24-Jun-2010
C100-CM-INSP-VV | R3 | Receiving Inspection of 12GeV Upgrade Cryomodule Vacuum Vessel | Gary Cheng | 26-Mar-2010
C100-CM-INSP-WSPT | R1 | 12 GeV Waveguide Supports | Katherine Wilson | 31-Jan-2011
C100-CM-INSP-WTUN | R1 | C100 Warm Tuner Receiving Inspection | J. Matalevich | 15-Aug-2010
C100-CM-INST | R1 | C100 CRYOMODULE TUNNEL INSTALLATION | Frank Humphry | 21-Jul-2010
C100-CM-LPRF-ACTS | R1 | C100 Cryomodule Acceptance Test ¿ Low Power RF Measurements | M. Drury | 22-Jun-2011
C100-CST-ASSY-ASO1 | R1 | C100 cavity string assembly traveler | Kurt Macha | 29-Jun-2010
C100-CST-ASSY-ASO1 | R2 | C100 cavity string assembly traveler | Kurt Macha | 11-Feb-2011
C100-CST-ASSY-BPIP | R1 | C100 Supply and return beam pipe assemblies | Kurt Macha | 25-Apr-2011
C100-CST-ASSY-WGD | R1 | C100 Waveguide sub-assembly and leak test traveler | Kurt Macha | 06-Jun-2010
C100-CST-CLN-COMP | R1 | C100 cavity string component cleaning | James Davenport | 25-Aug-2010
C100-CST-CLN-STTL | R1 | C100 cavity string tooling cleaning | James Davenport | 25-Aug-2010
C100-D3 | R1 | D3s for Cryomodule Processing (NOT cavity) | V. Bookwalter | 15-Jan-2010
C100-INSR | R1 | Inspection Summary Report | Brian Carpenter | 04-Mar-2005
C100-NCR | R1 | JLAB Non-Conformance Report | V. Bookwalter | 15-Jan-2010
C100-NCR | R10 | Non-Conformance Report for Multiple Reworks | BOOKWALT | 26-Feb-2018
C100-NCR | R5 | JLAB Non-Conformance Report | V. Bookwalter | 15-Jan-2010
C100-NCR | R6 | NCRs for Cryomodule Processing (NOT cavity) | V. Bookwalter | 15-Jan-2010
C100-NCR | R7 | Non-Conformance Report | V. Bookwalter | 07-Sep-2011
C100-NCR | R8 | Non-Conformance Report | V. Bookwalter | 16-Jun-2014
C100-NCR | R9 | Non-Conformance Report | V. Bookwalter | 21-Sep-2015

## INVENTORY TRAVELERS
Traveler Name | Traveler ID (SEPARATE BY WORKCENTERS) | Questions / Comments | Necessary Documentation | Author | Reviewer | Project Manager | SOTR | Date | D3 ?? (USERNAME) | NCR Dispositioners (USERNAME) | NCR Informative (USERNAME) | Notes

## PROCEDURES
PROCEDURE TITLE | PROCEDURE ID | REVISION | Author | Reviewer | Proj Lead | Due | Approved | CURRENT FILE LOCATION
Safety Procedures
Incoming inspection Procedures
Chemistry/ Cleaning Procedures
Cavity Procedures
String Production Procedures
Cryomodule Production Procedures
Cryomodule Testing Procedures
Cryomodule Shipping Procedures

## TRAVELERSold (hidden)
Traveler Name | Traveler ID (SEPARATE BY WORKCENTERS) | Procedure(s), Name (if known) OR Yes/No | Drawing(s), Name (if known) OR Yes/No | SOP/TOSP/OSP/THA | Revision | Author | Reviewer | Project Manager | SOTR | Due | D3 ?? (USERNAME) | NCR Dispositioners (USERNAME) | NCR Informative (USERNAME) | Traveler (Holdpoint) Closer (USERNAME) | Notes
Receiving Travelers
Cavity
Helium Vessel Receiving Traveler | SNSPPU-CAV-RECV-HELV |  |  |  | R1
Cavity String
Bellows Receiving Traveler | SNSPPU-CST-RECV-(bellows) |  |  |  | R1
Gate Valves Receiving Traveler | SNSPPU-CST-RECV-(gate valve) |  |  |  | R1
FPC Receiving Traveler | SNSPPU-CST-RECV-FPC |  |  |  | R1
Cryomodule
Diode CXCU Inventory Traveler | SNSPPU-CM-RECV-DCXCU |  |  |  | R1 | M. Dickey | C. Barnes | E. Daly | P. Owen | 2020-01-02 |  | powen,king,edaly,kwilson,mdickey,areilly
Disassembly Travelers
Cavity
Cavity String
Cryomodule
Leak Check Travelers
Cavity
Cavity String
Bellows Leak Check Traveler | SNSPPU-CST-LEAK-(bellows) |  |  |  | R1
Gate Valves Leak Check Traveler | SNSPPU-CST-LEAK-(gate valves) |  |  |  | R1
FPC Leak Check Traveler | SNSPPU-CST-LEAK-FPC |  |  |  | R1
Cryomodule
Inspection Travelers
Cavity
Visual and CMM Inspection of Cavity | SNSPPU-CAV-INSP-CAV |  | 104211800-M8U-8200-A00X |  | R1 |  |  |  | K. Wilson | 2020-02-01
Visual/CMM Inspection of Helium Vessel | SNSPPU-CAV-INSP-HELV | TI CLEANING | 104211700-M8U-8200-A026 |  | R1 |  |  |  | K. Wilson | 2020-02-01
Receiving Inspection Cavity RF | SNSPPU-CAV-RFIN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
TUNER FRAME / STEPPER MOTORS / HARMONIC DRIVE |  | SS CLEANING
Cavity String
Receiving Inspection Bellows | SNSPPU-CST-INSP-(bellows) |  |  |  | R1 |  |  |  | K. Wilson | 2020-05-01
SNS FPC Visual Inspection | SNSPPU-CST-INSP-FPC |  | 104211600-M8U-8200-A00X |  | R1 |  |  |  | K. Wilson | 2019-12-01
Cryomodule
Space Frame Visual and Dimensional Inspection | SNSPPU-CM-INSP-SFR | SS CLEANING | 104210900-M8U-8200-A001 |  | R1 |  |  |  | M. Marchlik | 2020-10-01
Vacuum Vessel Visual Inspection | SNSPPU-CM-INSP-VV | LEAK CHECK; SS CLEANING | 104210800-M8U-8200-A001 |  | R1 |  |  |  | M. Marchlik | 2020-07-01
SNS Return End Can Visual/CMM Inspection | SNSPPU-CM-INSP-RENC |  | 104210700-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-11-01
SNS Supply End Can Visual/CMM Inspection | SNSPPU-CM-INSP-SENC |  | 104210600-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-06-01
SNS Outer Magnetic Shield Visual Inspection | SNSPPU-CM-INSP-OMAG |  | 104211000-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-05-01
SNS Inner Magnetic Shield Visual Inspection | SNSPPU-CM-INSP-IMAG |  | 104211200-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-05-01
SNS Thermal Shield Visual/CMM Inspection | SNSPPU-CM-INSP-THRM | HIGH SENSITIVITY LEAK CHECK | 104211100-M8U-8200-A002 104211100-M8U-8200-A014 104211100-M8U-8200-A025 |  | R1 |  |  |  | M. Marchlik | 2020-08-01
Chemistry Travelers
Cavity
Cavity High Pressure Rinse (New HPR) Traveler | SNSPPU-CAV-CHEM-HPRN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Components Cleaning Traveler | SNSPPU-CAV-CHEM-CLN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Ultra Sonic Clean Traveler | SNSPPU-CAV-CHEM-USC |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
CMM Workcenter ?
IS there a cav RFIN traveler?
Furnace Workcenter ? | changed CHEM to PROC
Bakeout before RF processing | SNSPPU-CAV-PROC-BAKE |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Cavity Heat Treatment | SNSPPU-CAV-PROC-HEAT |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Processing Travelers
Cavity
Cavity RF Tuning | SNSPPU-CAV-TUNE |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
IS there a cav RFIN traveler? |  |  |  |  | R1
Cavity String
Cryomodule
RF Processing (FPC RF Processing) | SNSPPU-CM-CST-FPC-HPRF |  |  |  | R1 |  |  |  | K. Wilson
Assembly Travelers
Cavity
SNS Helium Vessel Installation Traveler | SNSPPU-CAV-ASSY-HELV |  | 104211700-M8U-8200-A026 |  | R1 |  |  |  |  | 2020-02-01
High Beta Cavity Assembly for VTA testing | SNSPPU-CAV-ASSY (look at old SNS) |  | 104211800-M8U-8200-A00X |  | R1 |  |  |  |  | 2020-02-01
transfer to test stand
Cavity String
SNS High Beta Cavity String Traveler | SNSPPU-CST-ASSY |  |  |  | R1 |  |  |  |  | 2020-07-01
Cryomodule
Cryomodule Assembly | SNSPPU-CM-ASSY |  |  |  | R1 |  |  |  | M. Marchlik | 2020-12-01
Cold Mass Assembly | SNSPPU-CM-ASSY-CMAS |  |  |  | R1 |  |  |  |  | 2020-08-01
Cryomodule Thermal Shield-Spaceframe Assembly Traveler | SNSPPU-CM-ASSY-THRM |  | 104211100-M8U-8200-A002 104211100-M8U-8200-A014 104211100-M8U-8200-A025 |  | R1 |  |  |  | M. Marchlik
SNS High Beta Cryomodule Vacuum Vessel-End Can Assembly Traveler | SNSPPU-CM-ASSY-VV |  | 104210800-M8U-8200-A001 |  | R1
cm assy ship (rf, instrumentation)
Testing Travelers
Vertical Cavity Testing | SNSPPU-CAV-VTRF |  |  |  | R1 |  |  |  |  | 2020-04-01
Cavity VTA Cooldown | SNSPPU-CAV-VTA-COOL |  |  |  | R1 |  |  |  |  | 2020-02-01
Installation/Shipping Travelers
SNS Cryomodule Shipping | SNSPPU-CM-ASSY-SHIP |  |  |  | R1 |  |  |  |  | 2020-05-01
Standard Project Travelers
Detours, Deviations and Discrepancies (D3) | SNSPPU-D3 |  |  |  | R2 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A
Inspection Summary Report | SNSPPU-INSR |  |  |  | R1 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A
Inspection Nonconformance Report | SNSPPU-NCR |  |  |  | R10 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A