## TRAVELERS (2)
Issue(s) / Question(s) | Header 1 | Header 2 |  | Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | Author | Reviewer | Reviewer | Project Manager | SOTR | NCR Informative | NCR Dispositioners | D3 Emails | Procedure(s), Name (if known) | Drawing(s), Name (if known) | Acronym from INV | Notes | Status | Section
Need NCR and D3 names | Disassembly Travelers | Cavity | CP | Cavity Disassembly | C100R-CAV-DISA | R3 | 2018-11-28 | Dreyfuss | Forehand |  | Davis |  | forehand,areilly,kdavis,marhause | [6 empty] | CP
Need NCR and D3 names | Disassembly Travelers | Cavity String | CP | Cavity String Disassembly |  |  | 2020-08-01 | Forehand | Dreyfuss |  | Davis | [8 empty] | CP
Can be removed from list since R2 is issued | Disassembly Travelers | Cryomodule | CP | C100R Disassembly Traveler | C100R-CM-DISA | R1 | 2018-09-24 | Fischer | Reilly | Legg | Hamlette |  | areilly,rlegg,fischer | [6 empty] | CP
R2 is in Pansophy; Need NCR and D3 names | Disassembly Travelers | Cryomodule |  | C100R Disassembly Traveler | C100R-CM-DISA | R2 |  | Fisher | Worland | Hamlette | Reilly
Needs revision; Needs NCR and D3 names | Cavity Preparation | Inspection | CP | Cavity CMM Receiving Inspectopn | C100R-CAV-INSP | R1 | 2018-11-30 | DeKerlegand | Marhauser |  | Reilly |  | ari,fischer,kdavis | [6 empty] | CP
Needs NCR and D3 names; Is this a duplicate of C100R-VTA-HMFT-CSHK? | Cavity Preparation | Inspection | CP | Cavity HOM Feedthru Receiving Inspection | C100R-CAV-INSP-HMFT | R3 | 2018-11-06 | Park | Davis |  | Reilly |  | hkpark | [6 empty] | CP
Needs NCR and D3 names | Cavity Preparation | Inspection | CP | Cavity RF Inspection Receiving Inspection | C100R-CAV-RFIN | R1 | 2018-12-05 | Overton | Marhauser |  | Davis |  | forehand,areilly | [6 empty] | CP
Not in Pansophy; Is this traveler needed? | Cavity Preparation | Inspection |  | Window Leak Check | C100R-CAV-LEAK-WIN
Not in Pansophy | Cavity Preparation | Inspection | CP | Secondary Waveguide Inspection (knife edge and sealing surface) | C100R-CAV-INSP-GVWG | R2 | 2019-01-15 | DeKerlegand | Davis | Fischer |  |  | kdavis,fischer,geroged | [6 empty] | CP
Needs NCR and D3 names | Cavity Preparation | Inspection | CP | Primary waveguide Inspection | C100R-CAV-INSP-WGD | R1 | 2019-01-16 | Williams | DeKerlegand |  | Davis |  | kdavis,ari | [6 empty] | CP
Needs NCR and D3 names | Cavity Preparation | Inspection | CP | Recycled Waveguide Inspection - 12 GeV Upgrade Waveguides | C100R-CAV-INSP-WGD-RCYC | R1 | 2019-01-25 | Williams | DeKerlegand |  | Davis |  | kdavis,ari | [6 empty] | CP
Needs NCR and D3 names; Is this a duplicate of C100R-CAV-INSP-HMFT? | Cavity Preparation | Inspection | CP | C100R HOM Feedthru Receiving Inspection | C100R-VTA-HMFT-CSHK | R1 |  | HyeKyoung Park | Danny Forehand | Justin Kent | Tony Reilly |  | lzhao | hkpark | Hkpark,lzhao,areilly |  |  |  |  | CP
Needs NCR and D3 names; Traveler not yet used | Cavity Preparation | Inspection | CP | C100R leak check inspection traveler | C100R-CMA-HMFT-LEAK-R1 | R1 |  | HyeKyoung Park | Chris Wilcox |  | Tony Reilly |  | lzhao | Hkpark | hpark,lzhao,areilly |  |  |  |  | CP
Needs NCR and D3 names | Cavity Preparation | Chemistry | CP | C100R Cavity Degreasing | C100R-CAV-CHEM-USC | R1 | 2019-01-08 | Fiedler | Mitchell |  | Davis |  | ashleya,kdavis,ari | [6 empty] | CP
Needs NCR and D3 names | Cavity Preparation | Chemistry | CP | C100R Cavity HPR | C100R-CAV-CHEM-HPR | R1 | 2019-01-08 | Fiedler | Mitchell |  | Davis |  | ashleya,kdavis,ari | [6 empty] | CP
Needs NCR and D3 names | Cavity Preparation | Chemistry | CP | C100R Cavity Flange Lapping | C100R-CAV-LAP | R2 | 2018-11-29 | Wildeson | Mitchell |  | Davis |  | ashleya,areilly | [6 empty] | CP
Needs NCR and D3 names; wrong name? | Cavity Preparation | Chemistry | 15 | C100R Cavity Component Cleaning | C100R-CST-CLN-COMP |  | 2021-05-15 | Wildeson | Mitchell |  | Davis
In Pansophy but not master list; Needs NCR and D3 names | Cavity Preparation | Chemistry |  | C100R Cavity Component Cleaning | C100-CAV-CHEM-COMP
Needs NCR and D3 names | Cavity Preparation | Assembly | CP | C100R Cavity Assembly | C100R-CAV-ASSY | R2 | 2018-11-06 | Forehand | Dreyfuss |  | Davis | [8 empty] | CP
Needs NCR and D3 names | Cavity Preparation | Assembly | CP | C100R Cavity Tuning | C100R-CAV-TUNE | R1 | 2018-11-06 | Overton | Forehand |  | Davis |  | forehand,areilly | [6 empty] | CP
Is this traveler needed? | Cavity Preparation | Testing |  | VTA HOM | C100R-CAV-VTA-HOM
Needs NCR and D3 names | Cavity Preparation | Testing | CP | C100R Cavity VTA Test | C100R-CAV-VTRF | R1 | 2018-11-06 | Stirbet | C.Willson |  | Davis |  | stirbet,kdavis,areilly | [6 empty] | CP
In Pansophy but not master list; Needs NCR and D3 names | Component Preparation | Inspection |  | C100R Double Sided Rectangular Flang Receiving Inspection Traveler | C100R-CAV-INSP-DSRF
In Pansophy but not master list; Needs NCR and D3 names | Component Preparation | Inspection |  | C100R Window Recycled Visual Inspection | C100R-CAV-INSP-WIN-RCYC
In Pansophy but not master list; Needs NCR and D3 names | Component Preparation | Inspection |  | Rework - 12GeV Upgrade Waveguides | C100R-CAV-RWRK-WGD
In Pansophy but not master list; Needs NCR and D3 names | Component Preparation | Inspection |  | C100R Brazement Adapter Assembly Receiving Inspection | C100R-INSP-ADPT
In Pansophy but not master list; needs NCR and D3 names; no data in traveler | Component Preparation | Inspection |  | Window Flange Inspection | C100R-INSP-WIN
Not in Pansophy | Component Preparation | Chemistry |  | Secondary waveguide cleaning | C100R-CAV-GVWG-CLN
Traveler not yet used | Component Preparation | Weld Inspection | CP | Waveguide and window Weldement Modification | C100R-WELD-WIN-ASSY | R1 | 2021-02-05 | Macha | Williams |  | Reilly |  | georged,lzhao | scott,edaly,forehand,areilly | scott,macha,areilly |  |  |  |  | CP
Needs NCR and D3 names | Component Preparation | Assembly | CP | C100R Helium Vessel Installation | C100R-CAV-ASSY-HELV | R2 | 2018-11-29 | Fischer | Legg | Worland | Reilly |  | fischer,marhause,areilly | [6 empty] | CP
Is this traveler needed? | Cavity String | Inspection | #VALUE! | Valve INSP |  |  | Hold 2020
Not in Pansophy; replaced by CST-ASSY and CST-ASSY-LEAK? | Cavity String | Assembly | CP | C100R Cavity Assembly & Leak Test | C100R-CST-ASSY-AS01 | R1 | 2019-01-21 | Forehand | [11 empty] | CP
In Pansophy but not in master list; Needs NCR and D3 names | Cavity String | Assembly |  | C100R Cavity String Assembly Traveler | C100R-CST-ASSY
Needs NCR and D3 names | Cavity String | Assembly | CP | C100R Waveguide Sub-Assembly & Leak Test | C100R-CST-ASSY-WGD | R1 | 2019-01-21 | Forehand | [11 empty] | CP
In Pansophy but not in master list; Needs NCR and D3 names | Cavity String | Assembly |  | C100R Cavity string leak test | C100R-CST-ASSY-LEAK
Not in Pansophy | Cryomodule | Inspection | CP | C100R Cold Electrical Feedthru Receiving Inspection | C100R-CM-INSP-ELFT | R1 | 2018-11-06 | Fischer | King |  | Reilly |  | fischer,king,areilly | [6 empty] | CP
In Pansophy but not in master list; Needs NCR and D3 names | Cryomodule | Inspection |  | C100R GeV Guard Vacuum Waveguide | C100R-CM-INSP-GVWG
Needs NCR and D3 names | Cryomodule | Cryomodule Assembly | CP | C100R Cryomodule Final Assembly | C100R-CM-ASSY | R1 | 2019-02-11 | Fischer | [11 empty] | CP
Needs NCR and D3 names | Cryomodule | Cryomodule Assembly | CP | C100R Cold Mass Assembly | C100R-CM-ASSY-COLD | R1 | 2019-02-11 | Fischer | [11 empty] | CP
Needs NCR and D3 names | Cryomodule | Cryomodule Assembly | CP | C100R Thermal Shield and Space Frame Assembly | C100R-CM-ASSY-SFR | R1 | 2019-02-11 | Fischer | [11 empty] | CP
Needs NCR and D3 names | Cryomodule | Cryomodule Assembly | CP | C100R Vacuum Vessel and End Can Assembly | C100R-CM-ASSY-VV | R1 | 2019-02-11 | Fischer | [11 empty] | CP
Not in Pansophy | Cryomodule | Cryomodule Assembly |  | C100R Cryomodule Beampipe Assembly | C100R-CM-ASSY-BPIP | R1 | 2021-06-30 | Fischer
| Cryomodule | Cryomodule Assembly | 30 | C100R Cryomodule Final Assembly | C100R-CM-ASSY | R2 | 2021-06-01 | Fischer | Worland | Hamlette | Reilly
| Cryomodule | Cryomodule Assembly | 30 | C100R Cold Mass Assembly | C100R-CM-ASSY-COLD | R2 | 2021-06-01 | Fischer | Worland | Hamlette | Reilly
| Cryomodule | Cryomodule Assembly | 30 | C100R Thermal Shield and Space Frame Assembly | C100R-CM-ASSY-SFR | R2 | 2021-06-01 | Fischer | Worland | Hamlette | Reilly
| Cryomodule | Cryomodule Assembly | 30 | C100R Vacuum Vessel and End Can Assembly | C100R-CM-ASSY-VV | R2 | 2021-06-01 | Fischer | Worland | Hamlette | Reilly
| Cryomodule | Cryomodule Assembly | 30 | C100R Cryomodule Beampipe Assembly | C100R-CM-ASSY-BPIP | R2 | 2021-06-01 | Fischer | Worland | Hamlette | Reilly
Not in Pansophy | Cryomodule | Cryomodule Testing |  | C100R Cryomodule Acceptance Test | C100R-CM-ACTS-CRYO |  | 2021-10-01 | Drury
Not in Pansophy | Cryomodule | Cryomodule Testing |  | C100R Cryomodule Acceptance Test | C100R-CM-ACTS-LPRF |  | 2021-10-01 | Drury
Not in Pansophy | Cryomodule | Cryomodule Testing |  | C100R Cryomodule Acceptance Test | C100R-CM-ACTS-HPRF |  | 2021-10-01 | Drury
Needs NCR and D3 names | Cryomodule | Cryomodule Testing |  | C100R Cryomodule Commissioning | C100R-CM-COMM |  | 2021-10-01 | Drury
In Pansophy but not in master list; Needs NCR and D3 names | Cryomodule | Cryomodule Testing |  | C100R Cryomodule Acceptance Test | C100R-CM-ACTS
Not in Pansophy | Cryomodule | Cryomodule Installation & Commisioning |  | C100R Cryomodule Tunnel Installation | C100R-CM-INST |  | 2021-10-01
| Standard Project Travelers |  | CP | C100R Non-Conformance Report | C100R-NCR | R11 |  | V. Bookwalter | A. McEwen |  | A. Reilly | [8 empty] | CP
| Standard Project Travelers |  | CP | C100R Detours, Deviations and Discrepencies | C100R-D3 | R2 |  | V. Bookwalter | A. McEwen |  | A. Reilly | [8 empty] | CP
| Standard Project Travelers |  | CP | C100R Inspection Summary Report | C100R-INSR | R1 |  | A. DeKerlegand | A. McEwen |  | A. Reilly | [8 empty] | CP
Note on E5: Tiffany Ganey: Missing due date; R2 is in Pansophy
Note on E6: Tiffany Ganey: Not being used; need revision to tell user to only use this traveler for new cavities, all refurbishment inspections are captured in C100R-CAV-LAP
Note on F9: Tiffany Ganey: Not in Pansophy
Note on F10: Tiffany Ganey: Not in Pansophy
Note on E14: Tiffany Ganey: This traveler has not been used yet;
Note on F18: Tiffany Ganey: Should this be C100R-CAV-CHEM-COMP (C100R-CST-CLN-COMP is not in Pansophy)
Note on E19: Tiffany Ganey: In Pansophy, but not in master list
Note on F19: Tiffany Ganey: In Pansophy, but not in master list
Note on F22: Tiffany Ganey: Not in Pansophy
Note on E24: Tiffany Ganey: In Pansophy but not master list
Note on E25: Tiffany Ganey: In Pansophy, but not in master list
Note on E26: Tiffany Ganey: In Pansophy, but not in master list
Note on E27: Tiffany Ganey: In Pansophy, but not in master list
Note on E28: Tiffany Ganey: In Pansophy, but not in master list; No data in this traveler
Note on F29: Tiffany Ganey: Not in Pansophy
Note on E30: Tiffany Ganey: This traveler has not been used yet
Note on F33: Tiffany Ganey: Not in Pansophy
Note on E34: Tiffany Ganey: In Pansophy, but not in master list
Note on E36: Tiffany Ganey: In Pansophy, but not in master list
Note on F37: Tiffany Ganey: Not in Pansophy
Note on E38: Tiffany Ganey: In Pansophy, but not in master list
Note on F43: Tiffany Ganey: Not in Pansophy
Note on F49: Tiffany Ganey: Not in Pansophy
Note on F50: Tiffany Ganey: Not in Pansophy
Note on F51: Tiffany Ganey: Not in Pansophy
Note on F52: Tiffany Ganey: R1 currently in Pansophy
Note on E53: Tiffany Ganey: In Pansophy, but not in master list
Note on F54: Tiffany Ganey: Not in Pansophy

## TRAVELERS
Issue(s) / Question(s) |  | Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | Author | Reviewer | Reviewer | Project Manager | SOTR | NCR Informative | NCR Dispositioners | D3 Emails | Procedure(s), Name (if known) | Drawing(s), Name (if known) | Acronym from INV | Notes | Status | Section
Disassembly Travelers
Cavity
Need NCR and D3 names | CP | Cavity Disassembly | C100R-CAV-DISA | R3 | 2018-11-28 | Dreyfuss | Forehand |  | Davis |  | forehand,areilly,kdavis,marhause | [6 empty] | CP
|  | Cavity String | [16 empty] | SS
Need NCR and D3 names | CP | Cavity String Disassembly |  |  | 2020-08-01 | Forehand | Dreyfuss |  | Davis | [8 empty] | CP
|  | Cryomodule | [16 empty] | SS
Can be removed from list since R2 is issued | CP | C100R Disassembly Traveler | C100R-CM-DISA | R1 | 2018-09-24 | Fischer | Reilly | Legg | Hamlette |  | areilly,rlegg,fischer | [6 empty] | CP
R2 is in Pansophy; Need NCR and D3 names |  | C100R Disassembly Traveler | C100R-CM-DISA | R2 |  | Fisher | Worland | Hamlette | Reilly
|  | Cavity Preparation | [16 empty] | SH
|  | Inspection | [16 empty] | SS
Needs revision; Needs NCR and D3 names | CP | Cavity CMM Receiving Inspectopn | C100R-CAV-INSP | R1 | 2018-11-30 | DeKerlegand | Marhauser |  | Reilly |  | ari,fischer,kdavis | [6 empty] | CP
Needs NCR and D3 names; Is this a duplicate of C100R-VTA-HMFT-CSHK? | CP | Cavity HOM Feedthru Receiving Inspection | C100R-CAV-INSP-HMFT | R3 | 2018-11-06 | Park | Davis |  | Reilly |  | hkpark | [6 empty] | CP
Needs NCR and D3 names | CP | Cavity RF Inspection Receiving Inspection | C100R-CAV-RFIN | R1 | 2018-12-05 | Overton | Marhauser |  | Davis |  | forehand,areilly | [6 empty] | CP
Not in Pansophy; Is this traveler needed? |  | Window Leak Check | C100R-CAV-LEAK-WIN
Not in Pansophy | CP | Secondary Waveguide Inspection (knife edge and sealing surface) | C100R-CAV-INSP-GVWG | R2 | 2019-01-15 | DeKerlegand | Davis | Fischer |  |  | kdavis,fischer,geroged | [6 empty] | CP
Needs NCR and D3 names | CP | Primary waveguide Inspection | C100R-CAV-INSP-WGD | R1 | 2019-01-16 | Williams | DeKerlegand |  | Davis |  | kdavis,ari | [6 empty] | CP
Needs NCR and D3 names | CP | Recycled Waveguide Inspection - 12 GeV Upgrade Waveguides | C100R-CAV-INSP-WGD-RCYC | R1 | 2019-01-25 | Williams | DeKerlegand |  | Davis |  | kdavis,ari | [6 empty] | CP
Needs NCR and D3 names; Is this a duplicate of C100R-CAV-INSP-HMFT? | CP | C100R HOM Feedthru Receiving Inspection | C100R-VTA-HMFT-CSHK | R1 |  | HyeKyoung Park | Danny Forehand | Justin Kent | Tony Reilly |  | lzhao | hkpark | Hkpark,lzhao,areilly |  |  |  |  | CP
Needs NCR and D3 names; Traveler not yet used | CP | C100R leak check inspection traveler | C100R-CMA-HMFT-LEAK-R1 | R1 |  | HyeKyoung Park | Chris Wilcox |  | Tony Reilly |  | lzhao | Hkpark | hpark,lzhao,areilly |  |  |  |  | CP
|  | Chemistry | [16 empty] | SS
Needs NCR and D3 names | CP | C100R Cavity Degreasing | C100R-CAV-CHEM-USC | R1 | 2019-01-08 | Fiedler | Mitchell |  | Davis |  | ashleya,kdavis,ari | [6 empty] | CP
Needs NCR and D3 names | CP | C100R Cavity HPR | C100R-CAV-CHEM-HPR | R1 | 2019-01-08 | Fiedler | Mitchell |  | Davis |  | ashleya,kdavis,ari | [6 empty] | CP
Needs NCR and D3 names | CP | C100R Cavity Flange Lapping | C100R-CAV-LAP | R2 | 2018-11-29 | Wildeson | Mitchell |  | Davis |  | ashleya,areilly | [6 empty] | CP
Needs NCR and D3 names; wrong name? | 15 | C100R Cavity Component Cleaning | C100R-CST-CLN-COMP |  | 2021-05-15 | Wildeson | Mitchell |  | Davis
In Pansophy but not master list; Needs NCR and D3 names |  | C100R Cavity Component Cleaning | C100-CAV-CHEM-COMP
|  | Assembly | [16 empty] | SS
Needs NCR and D3 names | CP | C100R Cavity Assembly | C100R-CAV-ASSY | R2 | 2018-11-06 | Forehand | Dreyfuss |  | Davis | [8 empty] | CP
Needs NCR and D3 names | CP | C100R Cavity Tuning | C100R-CAV-TUNE | R1 | 2018-11-06 | Overton | Forehand |  | Davis |  | forehand,areilly | [6 empty] | CP
|  | Testing | [16 empty] | SS
Is this traveler needed? |  | VTA HOM | C100R-CAV-VTA-HOM
Needs NCR and D3 names | CP | C100R Cavity VTA Test | C100R-CAV-VTRF | R1 | 2018-11-06 | Stirbet | C.Willson |  | Davis |  | stirbet,kdavis,areilly | [6 empty] | CP
|  | Component Preparation | [16 empty] | SH
|  | Inspection | [16 empty] | SS
In Pansophy but not master list; Needs NCR and D3 names |  | C100R Double Sided Rectangular Flang Receiving Inspection Traveler | C100R-CAV-INSP-DSRF
In Pansophy but not master list; Needs NCR and D3 names |  | C100R Window Recycled Visual Inspection | C100R-CAV-INSP-WIN-RCYC
In Pansophy but not master list; Needs NCR and D3 names |  | Rework - 12GeV Upgrade Waveguides | C100R-CAV-RWRK-WGD
In Pansophy but not master list; Needs NCR and D3 names |  | C100R Brazement Adapter Assembly Receiving Inspection | C100R-INSP-ADPT
In Pansophy but not master list; needs NCR and D3 names; no data in traveler |  | Window Flange Inspection | C100R-INSP-WIN
|  | Chemistry | [16 empty] | SS
Not in Pansophy |  | Secondary waveguide cleaning | C100R-CAV-GVWG-CLN
|  | Weld Inspection | [16 empty] | SS
Traveler not yet used | CP | Waveguide and window Weldement Modification | C100R-WELD-WIN-ASSY | R1 | 2021-02-05 | Macha | Williams |  | Reilly |  | georged,lzhao | scott,edaly,forehand,areilly | scott,macha,areilly |  |  |  |  | CP
|  | Leak Checks | [16 empty] | SS
|  | Assembly | [16 empty] | SS
Needs NCR and D3 names | CP | C100R Helium Vessel Installation | C100R-CAV-ASSY-HELV | R2 | 2018-11-29 | Fischer | Legg | Worland | Reilly |  | fischer,marhause,areilly | [6 empty] | CP
|  | Cavity String | [16 empty] | SH
|  | Inspection | [16 empty] | SS
Is this traveler needed? | #VALUE! | Valve INSP |  |  | Hold 2020
|  | Chemistry | [16 empty] | SS
|  | Assembly | [16 empty] | SS
Not in Pansophy; replaced by CST-ASSY and CST-ASSY-LEAK? | CP | C100R Cavity Assembly & Leak Test | C100R-CST-ASSY-AS01 | R1 | 2019-01-21 | Forehand | [11 empty] | CP
In Pansophy but not in master list; Needs NCR and D3 names |  | C100R Cavity String Assembly Traveler | C100R-CST-ASSY
Needs NCR and D3 names | CP | C100R Waveguide Sub-Assembly & Leak Test | C100R-CST-ASSY-WGD | R1 | 2019-01-21 | Forehand | [11 empty] | CP
In Pansophy but not in master list; Needs NCR and D3 names |  | C100R Cavity string leak test | C100R-CST-ASSY-LEAK
|  | Cryomodule | [16 empty] | SH
|  | Inspection | [16 empty] | SS
Not in Pansophy | CP | C100R Cold Electrical Feedthru Receiving Inspection | C100R-CM-INSP-ELFT | R1 | 2018-11-06 | Fischer | King |  | Reilly |  | fischer,king,areilly | [6 empty] | CP
In Pansophy but not in master list; Needs NCR and D3 names |  | C100R GeV Guard Vacuum Waveguide | C100R-CM-INSP-GVWG
|  | Cryomodule Assembly | [16 empty] | SS
Needs NCR and D3 names | CP | C100R Cryomodule Final Assembly | C100R-CM-ASSY | R1 | 2019-02-11 | Fischer | [11 empty] | CP
Needs NCR and D3 names | CP | C100R Cold Mass Assembly | C100R-CM-ASSY-COLD | R1 | 2019-02-11 | Fischer | [11 empty] | CP
Needs NCR and D3 names | CP | C100R Thermal Shield and Space Frame Assembly | C100R-CM-ASSY-SFR | R1 | 2019-02-11 | Fischer | [11 empty] | CP
Needs NCR and D3 names | CP | C100R Vacuum Vessel and End Can Assembly | C100R-CM-ASSY-VV | R1 | 2019-02-11 | Fischer | [11 empty] | CP
Not in Pansophy |  | C100R Cryomodule Beampipe Assembly | C100R-CM-ASSY-BPIP | R1 | 2021-06-30 | Fischer
| 30 | C100R Cryomodule Final Assembly | C100R-CM-ASSY | R2 | 2021-06-01 | Fischer | Worland | Hamlette | Reilly
| 30 | C100R Cold Mass Assembly | C100R-CM-ASSY-COLD | R2 | 2021-06-01 | Fischer | Worland | Hamlette | Reilly
| 30 | C100R Thermal Shield and Space Frame Assembly | C100R-CM-ASSY-SFR | R2 | 2021-06-01 | Fischer | Worland | Hamlette | Reilly
| 30 | C100R Vacuum Vessel and End Can Assembly | C100R-CM-ASSY-VV | R2 | 2021-06-01 | Fischer | Worland | Hamlette | Reilly
| 30 | C100R Cryomodule Beampipe Assembly | C100R-CM-ASSY-BPIP | R2 | 2021-06-01 | Fischer | Worland | Hamlette | Reilly
|  | Cryomodule Testing | [16 empty] | SS
Not in Pansophy |  | C100R Cryomodule Acceptance Test | C100R-CM-ACTS-CRYO |  | 2021-10-01 | Drury
Not in Pansophy |  | C100R Cryomodule Acceptance Test | C100R-CM-ACTS-LPRF |  | 2021-10-01 | Drury
Not in Pansophy |  | C100R Cryomodule Acceptance Test | C100R-CM-ACTS-HPRF |  | 2021-10-01 | Drury
Needs NCR and D3 names |  | C100R Cryomodule Commissioning | C100R-CM-COMM |  | 2021-10-01 | Drury
In Pansophy but not in master list; Needs NCR and D3 names |  | C100R Cryomodule Acceptance Test | C100R-CM-ACTS
|  | Cryomodule Installation & Commisioning | [16 empty] | SS
Not in Pansophy |  | C100R Cryomodule Tunnel Installation | C100R-CM-INST |  | 2021-10-01
|  | Standard Project Travelers | [16 empty] | SH
| CP | C100R Non-Conformance Report | C100R-NCR | R11 |  | V. Bookwalter | A. McEwen |  | A. Reilly | [8 empty] | CP
| CP | C100R Detours, Deviations and Discrepencies | C100R-D3 | R2 |  | V. Bookwalter | A. McEwen |  | A. Reilly | [8 empty] | CP
| CP | C100R Inspection Summary Report | C100R-INSR | R1 |  | A. DeKerlegand | A. McEwen |  | A. Reilly | [8 empty] | CP
| Color Legend |  | Count | Percent
| CP | Complete (CP) | 29 | 53.7%
| NR | New Revision Out for Approval (NR) | 0 | 0%
| OA | Out for Approval (OA) | 0 | 0%
| 30 | Due in 30 Days | 5 | 9.259%
| 15 | Due in 15 Days | 1 | 1.852%
| OD | Overdue | 0 | 0%
|  | Remaining | 19 | 35.19%
|  | Total Traveler IDs | 54
Note on C9: Tiffany Ganey: Missing due date; R2 is in Pansophy
Note on C13: Tiffany Ganey: Not being used; need revision to tell user to only use this traveler for new cavities, all refurbishment inspections are captured in C100R-CAV-LAP
Note on D16: Tiffany Ganey: Not in Pansophy
Note on D17: Tiffany Ganey: Not in Pansophy
Note on C21: Tiffany Ganey: This traveler has not been used yet;
Note on D27: Tiffany Ganey: Should this be C100R-CAV-CHEM-COMP (C100R-CST-CLN-COMP is not in Pansophy)
Note on C29: Tiffany Ganey: In Pansophy, but not in master list
Note on D29: Tiffany Ganey: In Pansophy, but not in master list
Note on D37: Tiffany Ganey: Not in Pansophy
Note on C43: Tiffany Ganey: In Pansophy but not master list
Note on C44: Tiffany Ganey: In Pansophy, but not in master list
Note on C45: Tiffany Ganey: In Pansophy, but not in master list
Note on C46: Tiffany Ganey: In Pansophy, but not in master list
Note on C47: Tiffany Ganey: In Pansophy, but not in master list; No data in this traveler
Note on D49: Tiffany Ganey: Not in Pansophy
Note on C53: Tiffany Ganey: This traveler has not been used yet
Note on D76: Tiffany Ganey: Not in Pansophy
Note on C77: Tiffany Ganey: In Pansophy, but not in master list
Note on C79: Tiffany Ganey: In Pansophy, but not in master list
Note on D82: Tiffany Ganey: Not in Pansophy
Note on C84: Tiffany Ganey: In Pansophy, but not in master list
Note on D93: Tiffany Ganey: Not in Pansophy
Note on D101: Tiffany Ganey: Not in Pansophy
Note on D102: Tiffany Ganey: Not in Pansophy
Note on D103: Tiffany Ganey: Not in Pansophy
Note on D104: Tiffany Ganey: R1 currently in Pansophy
Note on C105: Tiffany Ganey: In Pansophy, but not in master list
Note on D107: Tiffany Ganey: Not in Pansophy

## INVENTORY TRAVELERS
Traveler Name | Traveler ID (SEPARATE BY WORKCENTERS) | Questions / Comments | Necessary Documentation | Author | Reviewer | Project Manager | SOTR | Date | D3 ?? (USERNAME) | NCR Dispositioners (USERNAME) | NCR Informative (USERNAME) | Notes

## PROCEDURES
PROCEDURE TITLE | PROCEDURE ID | REVISION | Author | Reviewer | Proj Lead | Due | Approved | CURRENT FILE LOCATION
Safety Procedures
Incoming inspection Procedures
Chemistry/ Cleaning Procedures
Cavity Procedures
String Production Procedures
Cryomodule Production Procedures
Cryomodule Testing Procedures
Cryomodule Shipping Procedures

## TRAVELERSold (hidden)
Traveler Name | Traveler ID (SEPARATE BY WORKCENTERS) | Procedure(s), Name (if known) OR Yes/No | Drawing(s), Name (if known) OR Yes/No | SOP/TOSP/OSP/THA | Revision | Author | Reviewer | Project Manager | SOTR | Due | D3 ?? (USERNAME) | NCR Dispositioners (USERNAME) | NCR Informative (USERNAME) | Traveler (Holdpoint) Closer (USERNAME) | Notes
Receiving Travelers
Cavity
Helium Vessel Receiving Traveler | SNSPPU-CAV-RECV-HELV |  |  |  | R1
Cavity String
Bellows Receiving Traveler | SNSPPU-CST-RECV-(bellows) |  |  |  | R1
Gate Valves Receiving Traveler | SNSPPU-CST-RECV-(gate valve) |  |  |  | R1
FPC Receiving Traveler | SNSPPU-CST-RECV-FPC |  |  |  | R1
Cryomodule
Diode CXCU Inventory Traveler | SNSPPU-CM-RECV-DCXCU |  |  |  | R1 | M. Dickey | C. Barnes | E. Daly | P. Owen | 2020-01-02 |  | powen,king,edaly,kwilson,mdickey,areilly
Disassembly Travelers
Cavity
Cavity String
Cryomodule
Leak Check Travelers
Cavity
Cavity String
Bellows Leak Check Traveler | SNSPPU-CST-LEAK-(bellows) |  |  |  | R1
Gate Valves Leak Check Traveler | SNSPPU-CST-LEAK-(gate valves) |  |  |  | R1
FPC Leak Check Traveler | SNSPPU-CST-LEAK-FPC |  |  |  | R1
Cryomodule
Inspection Travelers
Cavity
Visual and CMM Inspection of Cavity | SNSPPU-CAV-INSP-CAV |  | 104211800-M8U-8200-A00X |  | R1 |  |  |  | K. Wilson | 2020-02-01
Visual/CMM Inspection of Helium Vessel | SNSPPU-CAV-INSP-HELV | TI CLEANING | 104211700-M8U-8200-A026 |  | R1 |  |  |  | K. Wilson | 2020-02-01
Receiving Inspection Cavity RF | SNSPPU-CAV-RFIN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
TUNER FRAME / STEPPER MOTORS / HARMONIC DRIVE |  | SS CLEANING
Cavity String
Receiving Inspection Bellows | SNSPPU-CST-INSP-(bellows) |  |  |  | R1 |  |  |  | K. Wilson | 2020-05-01
SNS FPC Visual Inspection | SNSPPU-CST-INSP-FPC |  | 104211600-M8U-8200-A00X |  | R1 |  |  |  | K. Wilson | 2019-12-01
Cryomodule
Space Frame Visual and Dimensional Inspection | SNSPPU-CM-INSP-SFR | SS CLEANING | 104210900-M8U-8200-A001 |  | R1 |  |  |  | M. Marchlik | 2020-10-01
Vacuum Vessel Visual Inspection | SNSPPU-CM-INSP-VV | LEAK CHECK; SS CLEANING | 104210800-M8U-8200-A001 |  | R1 |  |  |  | M. Marchlik | 2020-07-01
SNS Return End Can Visual/CMM Inspection | SNSPPU-CM-INSP-RENC |  | 104210700-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-11-01
SNS Supply End Can Visual/CMM Inspection | SNSPPU-CM-INSP-SENC |  | 104210600-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-06-01
SNS Outer Magnetic Shield Visual Inspection | SNSPPU-CM-INSP-OMAG |  | 104211000-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-05-01
SNS Inner Magnetic Shield Visual Inspection | SNSPPU-CM-INSP-IMAG |  | 104211200-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-05-01
SNS Thermal Shield Visual/CMM Inspection | SNSPPU-CM-INSP-THRM | HIGH SENSITIVITY LEAK CHECK | 104211100-M8U-8200-A002 104211100-M8U-8200-A014 104211100-M8U-8200-A025 |  | R1 |  |  |  | M. Marchlik | 2020-08-01
Chemistry Travelers
Cavity
Cavity High Pressure Rinse (New HPR) Traveler | SNSPPU-CAV-CHEM-HPRN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Components Cleaning Traveler | SNSPPU-CAV-CHEM-CLN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Ultra Sonic Clean Traveler | SNSPPU-CAV-CHEM-USC |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
CMM Workcenter ?
IS there a cav RFIN traveler?
Furnace Workcenter ? | changed CHEM to PROC
Bakeout before RF processing | SNSPPU-CAV-PROC-BAKE |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Cavity Heat Treatment | SNSPPU-CAV-PROC-HEAT |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Processing Travelers
Cavity
Cavity RF Tuning | SNSPPU-CAV-TUNE |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
IS there a cav RFIN traveler? |  |  |  |  | R1
Cavity String
Cryomodule
RF Processing (FPC RF Processing) | SNSPPU-CM-CST-FPC-HPRF |  |  |  | R1 |  |  |  | K. Wilson
Assembly Travelers
Cavity
SNS Helium Vessel Installation Traveler | SNSPPU-CAV-ASSY-HELV |  | 104211700-M8U-8200-A026 |  | R1 |  |  |  |  | 2020-02-01
High Beta Cavity Assembly for VTA testing | SNSPPU-CAV-ASSY (look at old SNS) |  | 104211800-M8U-8200-A00X |  | R1 |  |  |  |  | 2020-02-01
transfer to test stand
Cavity String
SNS High Beta Cavity String Traveler | SNSPPU-CST-ASSY |  |  |  | R1 |  |  |  |  | 2020-07-01
Cryomodule
Cryomodule Assembly | SNSPPU-CM-ASSY |  |  |  | R1 |  |  |  | M. Marchlik | 2020-12-01
Cold Mass Assembly | SNSPPU-CM-ASSY-CMAS |  |  |  | R1 |  |  |  |  | 2020-08-01
Cryomodule Thermal Shield-Spaceframe Assembly Traveler | SNSPPU-CM-ASSY-THRM |  | 104211100-M8U-8200-A002 104211100-M8U-8200-A014 104211100-M8U-8200-A025 |  | R1 |  |  |  | M. Marchlik
SNS High Beta Cryomodule Vacuum Vessel-End Can Assembly Traveler | SNSPPU-CM-ASSY-VV |  | 104210800-M8U-8200-A001 |  | R1
cm assy ship (rf, instrumentation)
Testing Travelers
Vertical Cavity Testing | SNSPPU-CAV-VTRF |  |  |  | R1 |  |  |  |  | 2020-04-01
Cavity VTA Cooldown | SNSPPU-CAV-VTA-COOL |  |  |  | R1 |  |  |  |  | 2020-02-01
Installation/Shipping Travelers
SNS Cryomodule Shipping | SNSPPU-CM-ASSY-SHIP |  |  |  | R1 |  |  |  |  | 2020-05-01
Standard Project Travelers
Detours, Deviations and Discrepancies (D3) | SNSPPU-D3 |  |  |  | R2 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A
Inspection Summary Report | SNSPPU-INSR |  |  |  | R1 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A
Inspection Nonconformance Report | SNSPPU-NCR |  |  |  | R10 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A