## TRAVELERS
| Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | Author | Reviewer | Reviewer | Project Manager | SOTR | NCR Informative | NCR Dispositioners | D3 Emails | Procedure(s), Name (if known) | Drawing(s), Name (if known) | Acronym from INV | Notes | Status | Section
Cavity
Cavity
CP | Cavity Visual & CMM Inspection | SNSPPU-INSP-CAV | R2 | 2020-05-01 | P. Dhakal | K. Wilson/K. Macha | G. DeKerlegand | E. Daly | P. Dhakal | [7 empty] | CP
CP | Cavity Incoming RF Inspection | SNSPPU-TUNE-CAV-RFIN |  | 2020-05-01 | P. Dhakal | D. Forehand | K. Davis | E. Daly | P. Dhakal | [7 empty] | CP
CP | Cavity Assembly to Test Stand | SNSPPU-CLNRM-CAV-TSTD |  | 2020-05-01 | P. Dhakal | D. Forehand | K. Davis | E. Daly | P. Dhakal | [7 empty] | CP
CP | Cavity Baking at 120℃ | SNSPPU-FURN-CAV-BAKE |  | 2020-05-01 | P. Dhakal | D. Forehand | K. Davis | E. Daly | P. Dhakal | [7 empty] | CP
CP | Cavity Vertical RF Testing (R2) | SNSPPU-VTRF-CAV | R3 | 2019-12-16 | K. Davis | P. Dhakal | C. Reece | E. Daly | P. Dhakal |  |  |  | VTA RF Testing Procedure, Excel Spreafsheet for VTRF Measurements |  |  |  | CP
CP | SNS PPU Tuner Stepper Motor Inspection Traveler | SNSPPU-ELEC-SM-CHK | R1 |  | L. King | P. Owen |  | N. Huque |  | king,powen,edaly | huque | king,powen,edaly,Huque,areilly |  |  |  |  | CP
CP | SNSPPU HB Cavity First Assembly | SNSPPU-CLNRM-CAV-ASSY1 | R1 |  | D. Forehand | C. Dreyfuss | P. Dhkal | E. Daly |  | forehand,dreyfuss | kdavis,daly,dhakal | forehand,kdavis,dreyfuss, dhakal |  |  |  |  | CP
CP | SNSPPU HB Cavity Second Assembly | SNSPPU-CLNRM-CAV-ASSY2 | R1 | [6 empty] | forehand,dreyfuss | kdavis,daly,dhakal | forehand,kdavis,dreyfuss, dhakal |  |  |  |  | CP
| Helium Vessel | [16 empty] | SS
CP | Helium Vessel Shell Inspection | SNSPPU-INSP-HES |  | 2020-07-13 | K. Wilson | G. DeKerlegand | K. Macha | E. Daly | K. Wilson | [7 empty] | CP
CP | Helium Vessel Probe End Inspection | SNSPPU-INSP-HEHDP | R3 | 2020-08-12 | K. Wilson | G. DeKerlegand | K. Macha | E. Daly | K. Wilson | [7 empty] | CP
CP | Helium Vessel FPC End Inspection | SNSPPU-INSP-HEHDF | R2 | 2020-08-13 | K. Wilson | G. DeKerlegand | K. Macha | E. Daly | K. Wilson | [7 empty] | CP
CP | Helium Vessel Shell Weld Inspection | SNSPPU-CWI-HES |  |  | K. Wilson | J. Alston |  | E. Daly | K. Wilson | [7 empty] | CP
CP | Helium Vessel Probe End Weld Inspection | SNSPPU-CWI-HEHDP |  |  | K. Wilson | J. Alston |  | E. Daly | K. Wilson | [7 empty] | CP
CP | Helium Vessel FPC End Weld Inspection | SNSPPU-CWI-HEHDF |  | 2020-09-30 | K. Wilson | J. Alston |  | E. Daly | K. Wilson | [7 empty] | CP
CP | Helium Vessel Assembly | SNSPPU-CMA-HELV-ASSY | R4 | 2020-03-18 | K. Macha | K. Worland | K. Wilson | E. Daly | K. Macha |  |  |  | CP-SNSPPU-CAV-ASSY-HELV, Calculate Shell Length | Helium Vessel w/ Liquid Level Probes, Helium Vessel w/o Liquid Levl Probes, Helium Vessel Assembly |  |  | CP
CP | Backtech Helium Vessel Lift Procedure | CP-SNSPPU-CAV-ASSY-LFT | R1 |  | K. Macha | A. Mitchell |  | E. Daly | [8 empty] | CP
| Chemistry | [16 empty] | SS
CP | Cavity HPR | SNSPPU-CHEM-CAV-HPR |  | 2020-05-01 | A. Mitchell | D. Forehand | K. Davis | E. Daly | K. Wilson | [7 empty] | CP
OA | Cavity HPR Procedure | CP-SNSPPU-CHEM-CAV-HPR | R1 |  | A. Wildeson | A. Mitchell |  | N. Huque | [8 empty] | OA
CP | FPC Cleaning | SNSPPU-CHEM-FPC-DEGR-R1 |  |  | M. Stirbet | D. Forehand | A. Mitchel | E. Daly | [8 empty] | CP
| Cavity Degreasing | SNSPPU-CAV-DEGR | R1 | 2021-06-15 | A. Mitchell | A. Wildeson | N. Huque
| Cavity Degreasing Procedure | SNSPPU-PR-CAV-DEGR | R1 | 2021-06-15 | A. Mitchell | A. Wildeson | N. Huque
| FPC | [16 empty] | SS
CP | FPC Visual Inspection | SNSPPU-INSP-FPC |  | 2021-01-04 | M. Stirbet | D. Forehand | K. Davis | E. Daly | [7 empty] | Visual | CP
| Cryomodule | [16 empty] | SH
| Cold Mass | [16 empty] | SS
CP | Tuner Assembly Visual & CMM Inspection | SNSPPU-INSP-TUNC | R1 | 2020-04-15 | N. Huque | M. Wisemn | A. DeKerlegand | E. Daly | N. Huque |  |  |  |  | 10411400-M8U-8200-A001, CMM-104211400-M8U-8200-A035, CMM-104211400-M8U-8200-A050, CMM-104211400-M8U-8200-A002, JL0093052, SNS-PPU Cavity Tuner Assembly Spares |  |  | CP
| Cavity Tuner Installation Procedure | SNSPPU-PR-CMA-TUNC-INST | R1 | [13 empty] | CP
CP | Equalizer Flex Hose Weld Inspection | SNSPPU-CWI-EQFH | R2 | 2020-10-12 | G. Cheng | M. Wiseman | G. DeKerlegand | E. Daly | G. Cheng | [7 empty] | CP
CP | Cold Mass Assembly He Outlet Bellows and Con Bellows Inspection | SNSPPU-INSP-HOBCB |  |  | G. Cheng | M. Wiseman | G. DeKerlegand | E. Daly | [5 empty] | 104211500-M8U-8200-A017, 104211500-M8U-8200-A026, SRF Serialization PR-P-007, 11141S0034 Stainless Steel Cleaning Procedure |  |  | CP
CP | Helium Outlet Bellows and Con Bellows Weld Inspection | SNSPPU-CWI-HOBCB |  | 2020-10-12 | G. Cheng | M. Wiseman | G. DeKerlegand | E. Daly | G. Cheng | [7 empty] | CP
CP | RF Cable for FP Cryo Cycle/Coldshock Test | SNSPPU-VTA-FPFCA-CHSK |  | 2021-03-08 | P. Owen | L. King | K. Davis | E. Daly | P. Owen | [7 empty] | CP
CP | 8 Pin Cryogenic Feethru Electrical Check | SNSPPU-ELEC-FT08P-CHK |  | 2020-08-04 | P. Owen | L. King | M. Morrone |  | P. Owen | [7 empty] | CP
CP | 8 Pin Cryogenic Feedthru VTA Cold Shock | SNSPPU-VTA-CSHK-FT08P |  | 2020-08-04 | P. Owen | L. King | T. Goodman |  | P. Owen | [7 empty] | CP
CP | 8 Pin Cryogenic Feethru Leak Check | SNSPPU-CMA-FT08P-LEAK |  | 2020-07-14 | P. Owen | C. Wilcox |  |  | P. Owen | [7 empty] | CP
CP | 8 Pin Cryogenic Feedthru Inspection | SNSPPU-INSP-FT08P |  | 2020-07-29 | P. Owen | L. King | G. DeKerlegand |  | P. Owen | [7 empty] | CP
CP | 8 Pin Cryogenic Feedthru Inventory | SNSPPU-INV-FT08P |  |  | M. Dickey | C. Barnes |  | E. Daly | P. Owen | [7 empty] | CP
CP | Cold Mass Assembly | SNSPPU-CMA-CMASS-ASSY |  | 2021-03-01 | G. Cheng | J. Fischer | M. Wiseman |  | M. Wiseman | [7 empty] | CP
CP | Cryomodule Return End Can Receiving Weld Inspection | SNSPPU-CWI-REC | R1 |  | G. Cheng | J. Alston | M. Wiseman | E. Daly | [5 empty] | Return End Can Top Assy 104210700-M8U-8200-A001, 104210700-M8U-8200-1001-SOW |  |  | CP
CP | Supply End Can Inspection | SNSPPU-INSP-SEC | R3 | 2021-05-10 | G. Cheng | L. King | J.Fischer | E. Daly | G. Cheng | [7 empty] | CP
CP | Supply End Can Receiving Inspection | SNSPPU-CMA-SEC-INSP | R3 |  | G. Cheng | L. King | J.Fischer | E. Daly | G. Cheng | [7 empty] | CP
CP | Return End Can Inspection | SNSPPU-INSP-REC | R1 | 2021-04-16 | G. Cheng | L. King | J.Fischer | E. Daly | G. Cheng | [7 empty] | CP
CP | Return End Can Receiving Inspection | SNSPPU-CMA-REC-INSP | R1 |  | G. Cheng | L. King | J.Fischer | E. Daly | G. Cheng | [7 empty] | CP
| Space Frame and Shielding | [16 empty] | SS
CP | Space Frame Inspection | SNSPPU-INSP-SFR |  | 2020-07-21 | M. Marchlik | J. Fischer | G. DeKerlegand | E. Daly | M. Marchlik | [7 empty] | CP
CP | Feed Through Flange Weldment Inspection | SNSPPU-INSP-INFF | R1 | 1/4/2021? | M. Marchlik | K. Wilson | L. King | E. Daly | M. Marchlik |  |  |  |  | 104210100-M8U-8200-A002 Feed Thru Flange Weldment |  |  | CP
CP | Feed Through Flange Weldment Leak Check | SNSPPU-CMA-INFF-LEAK | R1 | 2020-05-05 | M. Marchlik | K. Wilson | G. DeKerlegand | E. Daly | M. Marchlik |  |  |  |  | 104210100-M8U-8200-A002 Feed Thru Flange Weldment |  |  | CP
CP | Thermal Station Inspection | SNSPPU-INSP-THRMST | R1 | 2020-07-20 | M. Marchlik | K. Wilson | G. DeKerlegand | E. Daly | M. Marchlik |  |  |  |  | 104210200-M8U-8200-A044 Thermal Station Final Assembly, 10421200-M8U-8200-A045 |  |  | CP
CP | Thermal Station Leak Check | SNSPPU-CMA-THRMST-LEAK | R1 | 2020-06-03 | M. Marchlik | K. Wilson | C. Wilcox | E. Daly | M. Marchlik | [7 empty] | CP
CP | Thermal Shield Inspection | SNSPPU-INSP-THRM | R1 | 2020-06-19 | M. Marchlik | K. Wilson | G. DeKerlegand | E. Daly | M. Marchlik | [7 empty] | CP
CP | Thermal Shield Leak Check | SNSPPU-CMA-THRM-LEAK | R1 | 2020-05-19 | M. Marchlik | K. Wilson | C. Wilcox | E. Daly | M. Marchlik | [7 empty] | CP
CP | Outer Magnetic Shield Visual Inspecton | SNSPPU-INSP-OMAG | R1 | 2020-08-13 | G. Cheng | G. DeKerlegand | M. Wiseman | E. Daly | G. Cheng | [7 empty] | CP
CP | Inner Magnetic Shield Visual Inspecton | SNSPPU-INSP-IMAG | R1 | 2020-08-13 | G. Cheng | G. DeKerlegand | M. Wiseman | E. Daly | G. Cheng | [7 empty] | CP
CP | MLI Installation - Procedure |  |  | 2020-05-05 | Fischer |  |  |  | M. Marchlik | [6 empty] | CP-C75-CM-INST-MLI | CP
| Vacuum Vessel | [16 empty] | SS
CP | Vacuum Vessel Inspection | SNSPPU-CMA-VV-INSP | R1 | 2021-02-16 | M. Marchlik | J. Fischer | G. DeKerlegand | E. Daly | M. Marchlik | [7 empty] | CP
CP | Vacuum Vessel Leak Check | SNSPPU-CMA-VV-LEAK | R1 | 2021-02-16 | M. Marchlik | J. Fischer | K. Worland | E. Daly | M. Marchlik | [7 empty] | CP
CP | Tophat Inspection | SNSPPU-INSP-TPHT | R1 | 2021-01-04 | M. Marchlik | K. Wilson | G. DeKerlegand | E. Daly | M. Marchlik | [7 empty] | CP
CP | Tophat Leak Test | SNSPPU-CMA-LEAK-TPHT | R1 | 2020-04-03 | M. Marchlik | K. Wilson | J. Fischer | E. Daly | M. Marchlik | [7 empty] | CP
CP | Tophat Bellow Inspection | SNSPPU-INSP-TPHTB | R1 | 2021-01-04 | M. Marchlik | K. Wilson | G. DeKerlegand | E. Daly | M. Marchlik | [7 empty] | CP
CP | Tophat Bellow Leak Test | SNSPPU-CMA-LEAK-TPHTB | R1 | 2020-03-17 | M. Marchlik | K. Wilson | J. Fischer | E. Daly | M. Marchlik | [7 empty] | CP
CP | Parallel Plate Relief Valves Inspection | SNSPPU-INSP-PRPA | R1 | 2020-03-20 | M. Marchlik | K. Wilson | J. Fischer | E. Daly | M. Marchlik |  |  |  |  | 104210800-M8U-8200-A025 PRESSURE RELIEF PLATE ASSY, 104210800-M8U-8200-A026 RELIEF PLATE FLANGE, 104100000-M8U-8200-A520 PRESSURE RELIEF PLATE |  |  | CP
CP | Parallel Plate Relief Valves Leak Test | SNSPPU-CMA-LEAK-PRPA | R1 | 2020-03-20 | M. Marchlik | K. Wilson | J. Fischer | E. Daly | M. Marchlik |  |  |  |  | 104210800-M8U-8200-A025 PRESSURE RELIEF PLATE ASSY |  |  | CP
CP | Cryomodule Supply End Can Receiving Weld Inspection | SNSPPU-CWI-SEC | R1 |  | G. Cheng | M. Wiseman | J. Alston | E. Daly | G. Cheng | [7 empty] | CP
| Cryomodule | [16 empty] | SS
OD | Space Frame and Thermal Shield Assembly | SNSPPU-CM-ASSY-SFTS |  | 2021-05-31 | M. Marchlik | J. Fischer | M. Wiseman | E. Daly | M. Marchlik
OD | Final Cryomodule Assembly | SNSPPU-CM-ASSY |  | 2021-06-01 | M. Marchlik | J. Fischer | M. Wiseman | E. Daly | M. Marchlik
OD | Cryomodule Shipping | SNSPPU-CM-ASSY-SHIP |  | 2021-06-01 | N. Huque | J. Fischer | M. Wiseman | E. Daly | N. Huque
| Cavity String | [16 empty] | SH
| Inspection | [16 empty] | SS
CP | Beamline Bellows Visual Inspection | SNSPPU-INSP-BLBP | R2 | 2020-04-01 | K. Wilson | K. Davis | G. DeKerlegand | E. Daly | K. Wilson | [7 empty] | CP
CP | Supply Warm to Cold Bellows Visual Inspection | SNSPPU-INSP-SUBP | R3 | 2020-07-15 | K. Wilson | K. Davis | G. DeKerlegand | E. Daly | K. Wilson | [7 empty] | CP
CP | Return Warm to Cold Bellows Visual Inspection | SNSPPU-INSP-RTBP | R2 | 2021-01-04 | K. Wilson | K. Davis | G. DeKerlegand | E. Daly | K. Wilson | [7 empty] | CP
CP | Beamline Bellows Visual Inspection | SNSPPU-CWI-BLBP |  | 2020-07-15 | K. Wilson | K. Davis | G. DeKerlegand | E. Daly | K. Wilson | [7 empty] | CP
CP | Supply Warm to Cold Bellows Visual Inspection | SNSPPU-CWI-SUBP |  | 2020-07-15 | K. Wilson | K. Davis | G. DeKerlegand | E. Daly | K. Wilson | [7 empty] | CP
CP | Return Warm to Cold Bellows Visual Inspection | SNSPPU-CWI-RTBP |  | 2020-07-15 | K. Wilson | K. Davis | G. DeKerlegand | E. Daly | K. Wilson | [7 empty] | CP
CP | All Metal Gate Valve Leak Check | SNSPPU-CMA-AMGV-LEAK |  | 2020-08-04 | K. Macha | D. Forehand | K. Davis | E. Daly | K. Wilson | [7 empty] | CP
CP | Cavity String Assembly | SNSPPU-CLNRM-CST-ASSY | R1 | 2021-02-16 | K. Macha | D. Forehand | K. Davis | E. Daly | K. Macha | [7 empty] | CP
CP | Ionized Nitrogen Parts cleaning | CP-SNSPPU-CLNRM-CST-ION | R1 |  | D. Forehand | K. Davis |  | E. Daly | [8 empty] | CP
CP | SNSPPU Cavity String Leak Test | SNSPPU-CLNRM-CST-LEAK | R1 | 2021-03-19 | D. Forehand | K. Macha | N. Huque | E. Daly |  | edaly | forehand,huque | Areilly,edaly,huque |  |  |  |  | CP
| Chemistry | [16 empty] | SS
| Components | [16 empty] | SS
CP | SNSPPU Coupler installation onto the cavity Procedure | CP-SNSPPU-CLNRM-CPLR-INST | R1 |  | K. Macha | D. Forehand |  | E. Daly | [8 empty] | CP
| Standard Project Travelers | [16 empty] | SH
CP | Detours, Deviations and Discrepancies (D3) | SNSPPU-D3 | R2 | [13 empty] | CP
CP | Inspection Summary Report | SNSPPU-INSR | R1 | [13 empty] | CP
CP | Inspection Nonconformance Report | SNSPPU-NCR | R11 | [13 empty] | CP
Color Legend |  | Count | Percent
CP | Complete (CP) | 68 | 91.89%
NR | New Revision Out for Approval (NR) | 0 | 0%
OA | Out for Approval (OA) | 1 | 1.351%
30 | Due in 30 Days | 0 | 0%
15 | Due in 15 Days | 0 | 0%
OD | Overdue | 3 | 4.054%
| Remaining | 2 | 2.703%
| Total Traveler IDs | 74

## INVENTORY TRAVELERS
Traveler Name | Traveler ID (SEPARATE BY WORKCENTERS) | Questions / Comments | Necessary Documentation | Author | Reviewer | Project Manager | SOTR | Date | D3 ?? (USERNAME) | NCR Dispositioners (USERNAME) | NCR Informative (USERNAME) | Notes

## PROCEDURES
PROCEDURE TITLE | PROCEDURE ID | REVISION | Author | Reviewer | Proj Lead | Due | Approved | CURRENT FILE LOCATION
Safety Procedures
Incoming inspection Procedures
Chemistry/ Cleaning Procedures
Cavity Procedures
String Production Procedures
Cryomodule Production Procedures
Cryomodule Testing Procedures
Cryomodule Shipping Procedures

## TRAVELERSold (hidden)
Traveler Name | Traveler ID (SEPARATE BY WORKCENTERS) | Procedure(s), Name (if known) OR Yes/No | Drawing(s), Name (if known) OR Yes/No | SOP/TOSP/OSP/THA | Revision | Author | Reviewer | Project Manager | SOTR | Due | D3 ?? (USERNAME) | NCR Dispositioners (USERNAME) | NCR Informative (USERNAME) | Traveler (Holdpoint) Closer (USERNAME) | Notes
Receiving Travelers
Cavity
Helium Vessel Receiving Traveler | SNSPPU-CAV-RECV-HELV |  |  |  | R1
Cavity String
Bellows Receiving Traveler | SNSPPU-CST-RECV-(bellows) |  |  |  | R1
Gate Valves Receiving Traveler | SNSPPU-CST-RECV-(gate valve) |  |  |  | R1
FPC Receiving Traveler | SNSPPU-CST-RECV-FPC |  |  |  | R1
Cryomodule
Diode CXCU Inventory Traveler | SNSPPU-CM-RECV-DCXCU |  |  |  | R1 | M. Dickey | C. Barnes | E. Daly | P. Owen | 2020-01-02 |  | powen,king,edaly,kwilson,mdickey,areilly
Disassembly Travelers
Cavity
Cavity String
Cryomodule
Leak Check Travelers
Cavity
Cavity String
Bellows Leak Check Traveler | SNSPPU-CST-LEAK-(bellows) |  |  |  | R1
Gate Valves Leak Check Traveler | SNSPPU-CST-LEAK-(gate valves) |  |  |  | R1
FPC Leak Check Traveler | SNSPPU-CST-LEAK-FPC |  |  |  | R1
Cryomodule
Inspection Travelers
Cavity
Visual and CMM Inspection of Cavity | SNSPPU-CAV-INSP-CAV |  | 104211800-M8U-8200-A00X |  | R1 |  |  |  | K. Wilson | 2020-02-01
Visual/CMM Inspection of Helium Vessel | SNSPPU-CAV-INSP-HELV | TI CLEANING | 104211700-M8U-8200-A026 |  | R1 |  |  |  | K. Wilson | 2020-02-01
Receiving Inspection Cavity RF | SNSPPU-CAV-RFIN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
TUNER FRAME / STEPPER MOTORS / HARMONIC DRIVE |  | SS CLEANING
Cavity String
Receiving Inspection Bellows | SNSPPU-CST-INSP-(bellows) |  |  |  | R1 |  |  |  | K. Wilson | 2020-05-01
SNS FPC Visual Inspection | SNSPPU-CST-INSP-FPC |  | 104211600-M8U-8200-A00X |  | R1 |  |  |  | K. Wilson | 2019-12-01
Cryomodule
Space Frame Visual and Dimensional Inspection | SNSPPU-CM-INSP-SFR | SS CLEANING | 104210900-M8U-8200-A001 |  | R1 |  |  |  | M. Marchlik | 2020-10-01
Vacuum Vessel Visual Inspection | SNSPPU-CM-INSP-VV | LEAK CHECK; SS CLEANING | 104210800-M8U-8200-A001 |  | R1 |  |  |  | M. Marchlik | 2020-07-01
SNS Return End Can Visual/CMM Inspection | SNSPPU-CM-INSP-RENC |  | 104210700-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-11-01
SNS Supply End Can Visual/CMM Inspection | SNSPPU-CM-INSP-SENC |  | 104210600-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-06-01
SNS Outer Magnetic Shield Visual Inspection | SNSPPU-CM-INSP-OMAG |  | 104211000-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-05-01
SNS Inner Magnetic Shield Visual Inspection | SNSPPU-CM-INSP-IMAG |  | 104211200-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-05-01
SNS Thermal Shield Visual/CMM Inspection | SNSPPU-CM-INSP-THRM | HIGH SENSITIVITY LEAK CHECK | 104211100-M8U-8200-A002 104211100-M8U-8200-A014 104211100-M8U-8200-A025 |  | R1 |  |  |  | M. Marchlik | 2020-08-01
Chemistry Travelers
Cavity
Cavity High Pressure Rinse (New HPR) Traveler | SNSPPU-CAV-CHEM-HPRN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Components Cleaning Traveler | SNSPPU-CAV-CHEM-CLN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Ultra Sonic Clean Traveler | SNSPPU-CAV-CHEM-USC |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
CMM Workcenter ?
IS there a cav RFIN traveler?
Furnace Workcenter ? | changed CHEM to PROC
Bakeout before RF processing | SNSPPU-CAV-PROC-BAKE |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Cavity Heat Treatment | SNSPPU-CAV-PROC-HEAT |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Processing Travelers
Cavity
Cavity RF Tuning | SNSPPU-CAV-TUNE |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
IS there a cav RFIN traveler? |  |  |  |  | R1
Cavity String
Cryomodule
RF Processing (FPC RF Processing) | SNSPPU-CM-CST-FPC-HPRF |  |  |  | R1 |  |  |  | K. Wilson
Assembly Travelers
Cavity
SNS Helium Vessel Installation Traveler | SNSPPU-CAV-ASSY-HELV |  | 104211700-M8U-8200-A026 |  | R1 |  |  |  |  | 2020-02-01
High Beta Cavity Assembly for VTA testing | SNSPPU-CAV-ASSY (look at old SNS) |  | 104211800-M8U-8200-A00X |  | R1 |  |  |  |  | 2020-02-01
transfer to test stand
Cavity String
SNS High Beta Cavity String Traveler | SNSPPU-CST-ASSY |  |  |  | R1 |  |  |  |  | 2020-07-01
Cryomodule
Cryomodule Assembly | SNSPPU-CM-ASSY |  |  |  | R1 |  |  |  | M. Marchlik | 2020-12-01
Cold Mass Assembly | SNSPPU-CM-ASSY-CMAS |  |  |  | R1 |  |  |  |  | 2020-08-01
Cryomodule Thermal Shield-Spaceframe Assembly Traveler | SNSPPU-CM-ASSY-THRM |  | 104211100-M8U-8200-A002 104211100-M8U-8200-A014 104211100-M8U-8200-A025 |  | R1 |  |  |  | M. Marchlik
SNS High Beta Cryomodule Vacuum Vessel-End Can Assembly Traveler | SNSPPU-CM-ASSY-VV |  | 104210800-M8U-8200-A001 |  | R1
cm assy ship (rf, instrumentation)
Testing Travelers
Vertical Cavity Testing | SNSPPU-CAV-VTRF |  |  |  | R1 |  |  |  |  | 2020-04-01
Cavity VTA Cooldown | SNSPPU-CAV-VTA-COOL |  |  |  | R1 |  |  |  |  | 2020-02-01
Installation/Shipping Travelers
SNS Cryomodule Shipping | SNSPPU-CM-ASSY-SHIP |  |  |  | R1 |  |  |  |  | 2020-05-01
Standard Project Travelers
Detours, Deviations and Discrepancies (D3) | SNSPPU-D3 |  |  |  | R2 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A
Inspection Summary Report | SNSPPU-INSR |  |  |  | R1 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A
Inspection Nonconformance Report | SNSPPU-NCR |  |  |  | R10 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A