## FY21 Roadmap
PANSOPHY ROADMAP |  |  | START MONTH |  | 2021-01-01
FY21 | Qtr 2 |  |  | Qtr 3 |  |  | Qtr 4 |  |  | Qtr 1
| 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01
MILESTONES
Quality
Core Development
Traveler System
Project Tools
Production Tools
Communication / Documentation
Data Mining
Data Assimilation
R&D
Q2 Review
Q3 Review
Q4 Review
Q1 Review
QMS
VTA Use
FE Onset
Calibration
Compentency
CF2020
Data Security
Project Travelers / Procedures / Vendor Data
ASSY Part Verification
KPIs/ACLs
User Guides
SRF Webpage
Training Classes
Travelerization Upgrade (High School Students)
SAMTRAXS (Students)
VB
VB
MM
VB
MM
Key Security
Login Security
SQL Security
TPQM
Part Status/Trace
Status Boards
Traveler Completion
Data Completion
Closure Completion
Help System
Training Slides
AS
AS
MD
SAMTRAXS (3 Students)
CM Drilldowns
MM
Login Security
Status Boards
Travelerization Upgrade Completion
VB
ER5C (C20/C50R/C75)
C20/C50R/C75 TRAVELERS
C100R TRAVELERS
WMGRDR TRAVELERS
SNSPPU TRAVELERS
L2HE TRAVELERS
AUP TRAVELERS
P1 TRAVELERS
STP/SRFRD TRAVELERS
PROJECT PORTAL
Calibration
Report Fixes
GRID / GRAPH UPGRADE
TRAM/PRAM
Training Slides
MM
VB
MM
MM
VB
AS
WHO?
WHO?
MM
MM
VB
VB
Extra Time Needed to train and monitor
AS
<MM>
<VB>
<MD>
MM
VB
ISO Major NonConformance

## FY22 Roadmap
PANSOPHY ROADMAP |  |  | START MONTH |  | 2022-01-01
FY22 | Qtr 2 |  |  | Qtr 3 |  |  | Qtr 4 |  |  | Qtr 1
| 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01
MILESTONES
Quality
Core Development
Traveler System
Project Tools
Production Tools
Communication / Documentation
Data Mining
Data Assimilation
R&D
Q2 Review
Q3 Review
Q4 Review
Q1 Review
QMS (Reports?)
CF2021
CMTF
VTA
VTA Cooldowns
VTA Schedule
Programmer Guides
User Guides
SRF Webpage
Communication system
Training Classes
SAMTRAXS (Student?)
VB
VB
MM
MM
Workcenter Timelines
Drawing Cfg
AS
Data Security
Login Security
SQL Security
Project Travelers / Procedures / Vendor Data
CM Drilldowns
ER5C (C20/C50R/C75)
C100R TRAVELERS
WMGRDR TRAVELERS
SNSPPU TRAVELERS
L2HE TRAVELERS
AUP TRAVELERS
STP/SRFRD TRAVELERS
Compentency
VTA Use
FE Onset
GRID / GRAPH UPGRADE
KPIs/ACLs
Process Flow
Part Status/Trace
ASSY Part Verification
Traveler Completion
Data Completion
Closure Completion
PROJECT PORTAL
AS
VB
MD
WHO?
WHO?
WHO?
WHO?
VB
VB
VB
VB
VB
MM
MM
MM
VB
Extra Time Needed to train and monitor

## TeamSched
| MON |  |  |  |  | TUE |  |  |  |  | WED |  |  |  |  | THU |  |  |  |  | FRI
EST | VALERIE | MEGAN | ALLEN | AN | MIKE | VALERIE | MEGAN | ALLEN | AN | MIKE | VALERIE | MEGAN | ALLEN | AN | MIKE | VALERIE | MEGAN | ALLEN | AN | MIKE | VALERIE | MEGAN | ALLEN | AN | MIKE | PDT
7:00 | [25 empty] | 4:00
7:30 | [25 empty] | 4:30
8:00 | [25 empty] | 5:00
8:30 | [25 empty] | 5:30
9:00 | [25 empty] | 6:00
9:30 | [25 empty] | 6:30
10:00 | [25 empty] | 7:00
10:30 | [25 empty] | 7:30
11:00 | [25 empty] | 8:00
11:30 | [25 empty] | 8:30
12:00 | [25 empty] | 9:00
12:30 | [25 empty] | 9:30
13:00 | [25 empty] | 10:00
13:30 | [25 empty] | 10:30
14:00 | [25 empty] | 11:00
14:30 | [25 empty] | 11:30
15:00 | [25 empty] | 12:00
15:30 | [25 empty] | 12:30
16:00 | [25 empty] | 13:00
16:30 | [25 empty] | 13:30
17:00 | [25 empty] | 14:00
17:30 | [25 empty] | 14:30
18:00 | [25 empty] | 15:00
18:30 | [25 empty] | 15:30
19:00 | [25 empty] | 16:00
19:30 | [25 empty] | 16:30
20:00 | [25 empty] | 17:00
20:30 | [25 empty] | 17:30
21:00 | [25 empty] | 18:00
21:30 | [25 empty] | 18:30
22:00 | [25 empty] | 19:00
22:30 | [25 empty] | 19:30
23:00 | [25 empty] | 20:00
Pansophy Team Meeting
Typical Lunch Hour
Typical Lunch Hour
Typical Lunch Hour
Typical Lunch Hour
Typical Lunch Hour
Note: Megan is off every other Fri
SamTraxs II Meeting
C75/C50R Project Meeting
C100/P1 Project Meeting
SNSPPU Project Meeting
SRFPJS Bi-Weekly Meeting
Anne Bi-Weekly Meeting
L2HE Project Meeting
L2HE WCD Meeting

## FY21
|  |  | VALERIE | MEGAN | ALLEN | MIKE | ALL | HS Student | CCI Students
|  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
| TASKS | STAT | FY21 |  |  |  | FY22 |  |  |  | FY23 |  |  |  | FY24
|  |  | OCT-DEC | JAN-MAR | APR-JUN | JUL-SEP | OCT-DEC | JAN-MAR | APR-JUN | JUL-SEP | OCT-DEC | JAN-MAR | APR-JUN | JUL-SEP | OCT-DEC
SERVERS | MAINTENANCE / UPGRADES
| CF Security Patches / server reboots (MIS/CC) | ONGOING
Database Server (New)
Upgrade to CF2021
SECURITY
Add KEY security to all pages (CK SECURITY LOCKOUT OF Anne and S. Smith)
Upgrade KEY security mechanism
Upgrade PANSOPHY Log In mechanism
Secure storage locations for Data; outside Web tree
TRAVELERS | AUTOMATION / MAINTENANCE / UPGRADES
Master Traveler/Procedure Acronyms
SN Acronyms (update database & automate)
VTA Dictionary ( create help files)
CMTF Dictionary (create help files)
Modernize Uploaded File Retrieval
User choice email (new) adlib select
email D3's
change template to use UserNames
Automated Traveler Converter ( get working)
auto HTML cleanup
Electronically signed word docs
CLOSED PROJECT CONFIGURATION
SIGNED TRAVELERS/PROCEDURES SCANNED INTO D.S.
TRAVELER "REQUIRED FIELDS" HIGHLIGHTED
PETE HAS 200 FEEDTHRU TRAVELERS TO MODIFY, NO GROUP EDIT MODE
PROJECTS | TRAVELERS / REPORTS
| C50R | DONE
C100R
C100R ERROR ON CAV PERF REPORT
C100 - OPEN TRAVS CLOSE AND MOVE TO C100R
C100-CM-INSP-ELFT
C100-CAV-TUNE #107 MOVE TO C100R
| C75 | ON HOLD
C75-INSR ADD TO PROJECT
C75 DRILLDOWN
CRYO - CHL
SNS-PPU
PROPAGANDA SLIDES FOR MAMMOSSER
LCLS-II
MODIFY CM STATUS BOARD
TIMELINES FOR CM ASSY (LEGG)
AUTOMATE DATA FOR SLAC REPORT (ANNA'S READY)
CAVITY HOLDPOINT STATUS BOARD BROKE WHEN 2 TRAVS LISTED
CMTF AUTOMATED DATA UPLOAD (DRURY)
NB3SN
DATA PUT IN C50R BY OGLE NEEDS MOVED
| SRFRD ( R&D SMALL PROJECTS AREA) | ONGOING
| STP (for other Chemistry & Cavity processing) | ONGOING
COMMS | DOCUMENTATION / TRAINING / HELP FILES
| SRFPJS Team Administrative (meetings/reports) | ONGOING
| User Assistance/Help Docs/User questions | ONGOING
| Project/QA Reports emailed weekly | ONGOING
News & Noteworthy updates on Pansophy screens/logins (slide show)
UPDATE PANSOPHY HELP PAGES (FASTHELP)
| UPDATE PANSOPHY TRAINING SLIDES | ONGOING
| DocuShare Maintenance / Support | ONGOING
Favorites area for Pansophy Users
D3 automated monthly Report
SRF WEB PAGE
| PERIODIC PANSOPHY TRAINING SESSIONS | ONGOING
DATA MINING
Automate TPQM
CMTF Canned Report
UDQ saved for users
Change status boards to GRID Format
List of NCRs by CMSN
CAV Comparison (Graphs?)
ASSIMILATION
CMTF xcel processing spreadsheet (Chris' Java Program)
CMTF traveler instantiation automation
VTA traveler instantiation automation
VTA SPEADSHEET TWEAKS (TPOWERS)
C50 CMTF AUTO DATA MACRO (2/18/18) (MCEWEN)
C50 ACTS SUMMARY SHEET (9/6/18)
SAMTRAXS | REVAMP PROJECT
OTHER | OTHER
KYOTO CAMERA USEAGE LOG
WAND CAMERA USEAGE LOG
CLEAN ROOM APP
LEARN CFBUILDER
LEARN TO BUILD APPS (UNITY)
LEARN COLDBOX
NCR linked back to Originating Traveler
Web Usage reports (by user, by date, by area, by project)
Electronically Signed PDF Procedures/Travelers
Linked comment boxes
Menu Editor

## TeamList
ALLEN SAMUELS
REDO TRAINING SLIDES
UPDATE FASTHELP
TRANSFER TRAVELER WORK FULLY FROM MEGAN TO ALLEN
CONTINUE TRAVELER WORK FOR ALL PROJECTS
GO THROUGHT OFFICIAL HTML COURSE TO GET CERTIFIED.
MEGAN MCDONALD
TPQM (TRAMs/PRAMs)
DEVELOP PROJECT AREA IN PANSOPHY
NEW MULTI-FILE UPLOAD TO REPLACE FLASH VERSION
SEE IF THIS CAN BE IMPLEMENTED INTO THE TRAVELERS
USER LISTS IN PANSOPHY (REMOVE PEOPLE THAT ARE NO LONGER HERE BUT STILL KEEP THEIR NAME IN THE DB)
BUSY/BREAK PROJECT - CONVERT TRAVELERS THAT ARE ALREADY IN THE SYSTEM TO THE CURRENT NAMING CONVENTION
PROCEDURALIZE "PANSOPHY REQUESTS OF PROJECTS" TO MAKE IT A STANDARD DOCUMENT
REQUIRED FIELDS IN D3 AND NCR - MAKE AN EVENT POPUP VS HAVING TO SUBMIT THE PAGE, GET ERROR AND LOSE DATA
MIKE DICKEY
DATA MINING
DEPRECATED FEATURES
NEW NAMING CONVENTION
NEW WORK CENTER AREAS
SECURITY
LOGIN
SECURITY KEYS
LOCKOUT ALL USERS
AREA CONTROL OF USERS
PRIMeS
USER PAGES (ENTRY FORMS)
VALERIE BOOKWALTER
AN NGUYEN
ENQIAN ZHENG
COLE MATHES

## Concerns
2020-09-22
Pansophy Team Concerns
1. Projects (Travelers/Procedures)
a. Authors' responsible for uploading drafts to DocuShare and pulling from drafts when making edits or new revisions
b. Meetings - Travelers are left to the end often rushed or not discussed at all
c. Expectations on turnaround time are unrealistic
d. Priorities are not always certain/expressed (we realize they change daily, sometimes hourly) - we receive emails out of order from what travelers actually need processed first.
2. Projects (Vendor Data)
a. RI (SNSPPU) - no response to questions asked over 1 month ago, yet constantly asking if Megan is done yet.
b. Couplers (SNSPPU) - data is emailed directly to bookwalt rather than being uploaded to SharePoint Drive; no traveler yet to attach data to; expectation of us doing this?
3. Projects (Components and Serial Numbers)
a. Components are not always going through inventory, which is where Serial Numbers are added to the database for Traveler usage.
b. Leaving components in old project areas is difficult for the system to track or have available in new project areas
c. Acronyms are being randomly generated
4. Projects (Process Flow)
a. C75 (Gigi) has a process flow for cavities, we didn't know, nor does it appear that traveler users know, therefore parts may not be advancing as expected.
b. No process flow for other components - this could be added to travelers
c. AUP/P1 travelers are all together rather than separated by WCA to handle process flow - is this a standard convention we want to continue? Should we drop separating? Which projects can use? Large projects (production environment) separate travelers by WCA?
5. Projects (SOWs & SQUAPs)
a. What is being promised to customers for reports, data transfer, NCR reporting, access
6. WCA
a. Definition and Justification still needed
b. Decision on usage still needed
7. Communications (1 HS Student until May/June 2021)
a. SRF Website started by CC
i. Who should be invovled in designing requirements
ii. What is most important to do first
b. Pansophy Front Page
i. Video Viewer for VTRF results
ii. QA Board Stats
iii. Other SRFOPS announcements?
c. Pansophy HelpFast to be updated (priority?)
d. Pansophy Training to be updated (priority?)
8. Competency Training
a. R1 of Traveler released and is to be tested SNSPPU
b. Already been put on notice that changes will be coming
c. Expectation of timeframe? Thought this was FY21
9. Calibration Tool
a. Announced in SRF QA meeting that I would have this completed by Sept 2020.
b. Larry King still has not informed me of changes needed
c. Suggested use of Aaron's list for test case
d. Thought this was FY21
10. R&D SamTraxs Support (2 College Students until Dec 18, 2020)
a. What priority should this be given?
b. Is there support from SRFOPS?
11. QA Board Metrics
a. No Metrics have been identified
b. Anger over current reports - what needs to change
c. Monthly emails of Op/Cl are not helpful - what do they want instead?
d. Numbers between reports don't match - what priority is this compared to other work?

## P-Priorities
AREA | PROJECT
QA | DOCS/RECORDS | 1
QA | CALIBRATION | 3
QA | TRAINING | 2
CORE | SECURITY | 1
CORE | GRAPHS/GRIDS | 2
CORE | NEW DB SERVER | 3
CORE | REPORTS/INTEGRITY | 2 | INVOLVES WCAs
PROJECT TOOLS | STATUS BOARDS
PROJECT TOOLS | KPI SETUP
PROJECT TOOLS | TRAMs/PRAMs
PROJECT TOOLS | DRILLDOWNS
PROJECT TOOLS | CM DELIVERY DATA
TRAVELERS | L2PRD | 1 | DATES | ENDS DEC 20
TRAVELERS | SNSPPU | 1 | STR STARTS OCT | ENDS 22 | PULL FROM ED'S SLIDE
TRAVELERS | C75-1 | 1 | PAIRS NOW | INSTALL FALL 20
TRAVELERS | C75-2 | 1 |  | INSTALL DEC 21
TRAVELERS | C75-3 | 1 |  | INSTALL JAN 22
TRAVELERS | C75-3&4 | 1 |  | INSTALL JAN 23
TRAVELERS | P1 | 1 | CAVITIES NOW | INSTALL SPR 21 PLASMA TRAV
TRAVELERS | C100R-10 | 1 | EST SPR 21 | INSTALL SUM 22
TRAVELERS | AUP | 1
TRAVELERS | SRFRD | 1 | DEPENDS ON JH
TRAVELERS | L2HE | 1 | COMPs JAN 21
PRODUCTION TOOLS | TRAVELER PRECHECK | 4
PRODUCTION TOOLS | AUTOMATE CONVERSION | 4
R&D | SAMTRAXS
R&D | EDX
COMMS | WEBSITE
COMMS | TRAINING
COMMS | HELP SYSTEM

## QMS-QAISRF
PROCESS | OWNER | NOTES | OWNER PROCEDURE DUE | FINAL DUE | TOOL DUE
DOCS | JACOB | WRITES HIS OWN | FY20/Q4
RECORDS | BOOKWALTER | NEED PROCEDURES & TOOL / HELP WITH EDITING | FY20/Q4 |  | FY21/Q4
CALIBRATION | KING | NEEDS PROCEDURE & TOOL / HELP WITH EDITING | FY20/Q4 |  | FY21/Q4
COMPETENCE | FISCHER | NEEDS PROCEDURE & TOOL | FY20/Q4 |  | FY21/Q4
LEADERSHIP | TONY | NEEDS PROCEDURES & KPIs | FY20/Q4 |  | FY21/Q4
ORG KNOWLEDGE | MACHA | SELF WRITE | FY20/Q4 |  | FY21/Q4
INVENTORY | PHIL | ? CAN PHIL COMPLETE WHAT JH STARTED | TBD
SUPPLIERS | NAEEM | CAN HE WRITE HIS OWN? | TBD
QUALITY | JACOB | WRITES HIS OWN | FY20/Q4
NCRS/CARS | ? | ? | FY21
OPERATIONS | KDAVIS |  | FY21
PROJECT MGMT | EDALY |  | FY21
CONT IMPROVEMENT | JACOB |  | FY21
INTERNAL AUDIT | JACOB |  | FY21
MGMT REVIEW |  |  | FY20/Q4
JH NEEDS TO ASK FOR HELP (CONTRACTOR)

## Task List
Priority Things | NEW IDEAS
New Database Machine testing (Renewal due April 1st)! | traveler selection more options for searching
Update license for SQLXL | USER CANNED REPORTS - make easier to create
Quick Things | Batch Traveler Closing - more slection options
Bring Monitor Home - property pass/loan | Batch Traveler Closing - ensuring data is complete
Danny's group M:drive access: Firth, Jordan, Smarks, Pdoyle, tashawn | Batch Traveler Closing - is closer valid
Fischer has not yet filled out C100R-CM-DISA | 4. Projects (Process Flow)
Does VPN map DSDrive? | 11. QA Board Metrics
SNSPPU-INV-FPCWG? | a. No Metrics have been identified
Send Jacob the new naming convention of traveler/procedures; he has PROJ-PR-SYS-WKS-COMP; PROJ-TR-SYS-WKS-COMP | b. Anger over current reports - what needs to change
Discussions to Have | c. Monthly emails of Op/Cl are not helpful - what do they want instead?
Anne's comments on use of Comments rather than making Rev changes | d. Numbers between reports don't match - what priority is this compared to other work?
Does Anne have our back when it comes to travelers/revisions/time? | CM Locations update request (Ed/Tony) - New Project?
Why do authors have such a problem? Katherine, Danny, Fischer? | ISO COMPLIANCE - OTHER GROUPS NEED TO UNDERSTAND (SRFOPS INS/OUTS)
Can edits be delegated to reviewers? Admin (Carolyn)?
Are people using DSDrive? | PROBLEMS
Get a "Tuesday Tidbits" going with Kirk Davis | SQL INJECTION / URL USEAGE
Communications with people at the lab | TRAVELER OPEN/CLOSE - MAJOR NON-CONFORMANCE
Camera/Microphones for floor/home computers | NCR OP/CL BY ENGR - NEEDS FIXED
Use of Microsoft Teams by people at lab | NCR OP/CL DOES NOT EXPORT (LINKS ARE PART OF QUERY)
CM Locations update request (Ed/Tony) - New Project? | GRIDS - LINKS NOT WORKING CORRECTLY (LINKS ARE PART OF QUERY)
Space for Allen | DATA MINING
Aaron's second port is not working | DEPRECATED FEATURES
Laptop has small screen; can he hook up to larger screen? | NEW NAMING CONVENTION
Need Monitor for his computer for future work | NEW WORK CENTER AREAS
Brainstorm fix to a problem: | PRIMeS
Gigi has Danny filling out 2 travelers for every cavity assembly; The ASSY and the FAB travelers. | USER PAGES (ENTRY FORMS) - TRAINING / REQUIRED USE OF
Can something automatic be put into place? | SCANNERS AND/OR PHONE APP
Can Gigi be satisfied with a status board? | STATUS ONLY (EX. PART INFORMATION/NCRS)
How to track cavity processing (when in pseudo-research)? | INTERACTION (EX. PART MOVING)
Survey WCA breakdown travelers | NEW MULTI-FILE UPLOAD TO REPLACE FLASH VERSION
Paper traveler/checklist with part
Moving of Inventory from one project to another - how to trace? | Projects (Components and Serial Numbers)
P2020 Upgrades still required | a. Components are not always going through inventory, which is where Serial Numbers are added to the database for Traveler usage.
Check out TOAST UI Chart (from MDD) | b. Leaving components in old project areas is difficult for the system to track or have available in new project areas
SamTraxs II | c. Acronyms are being randomly generated (User Request Page)
One Note Notebook | d. Modify Serialzation Procedure modification (Phil?)
Map Next Steps | e. Naeem - Vendor Process Owner
Send schedule out | f. MLP Projects vs CEBAF Projects
Mike - examples CFC grouping | NCRs/D3s - not getting correct information for auto-fill
Mike - example combined sequel statement
Travelerization | TRAV_ID is drop-down menus only
How is username gotten for cfg file? | Traveler Template Updates
Cole - github access | Tuesday Tidbit (especially for authors)
Cole - M:drive access to pansophydev
Setup OneNote for programmers guide/documentation from Cole
Megan - stepwise testing/error checking
PRAMs/TRAMs
Brainstorming
Straw dog
Time frame
Project Master Lists
Tracking of travelers/procedures in progress
Create Checklists for Updating all Mater Listings
Pansophy Training
Create a priority for Allen's work on training slides
Order of Training
Dates?
New Employee Orientation on Pansophy/DocuShare
Setup Training Sessions
Security in Pansophy
Internal vs External PR Slide
Map out phases
Phase 1 by Feb 15th
Lock down now
P3
Setup OneNote Notebook
Setup a focus group for Pansophy (Tiffany, Sarah, Earl, John Firth,…)
Problems/Errors
Problem: macro enabled traveler doesn't email properly
Need to be more aware of Project Milestones
NCRs/D3s - not getting correct information for auto-fill
Megan - help with RI HLDPT 3
Projects
Status Boards and Canned Reports
SNSPPU Status Boards (Naeem)
L2HE Status Boards
C100R Status Boards
C75 Status Boards
C50R Status Boards
Traffic Light for SNSPPU cavity String (Naeem)
WMGRDR -
Tiffany Questions / New Updates
Tiffany has old data from C50/C100 CMs. Needs a place to store
Create traveler from Ari's list
New rev of LabVIEW procedure
SRFRD
Sarah need helps with Kicker work
EIC - new project on the horizon RFD cavities like USLARP project
BNNT
Renaming Project areas: C75 & SNSPPU (setup timeframe)
New Project Area
Establish Project Area
Map out data mining to move
ISO and SRF QMS
· ISO certification by Dec '21
· Full audits/reviews by Sep '22
· Follow up with Stuart planned for Jun/Jul '21
Records Management by Mar '21
How to help process owners with writing?
Does a link in DocuShare allow different permissions to be set on the link vs the directory?
Quality Board
Proposed New NCR graph (J. Harris)
Records Management
Complete Program Description
Start Procedure
Validate records spreadsheet
Calibration Work (L. King)
Update fields
Correct errors
Clear our old data
Enter Aaron's data
Testing by Feb 19th
Competency Work (J. Fischer)
Check on traveler usage
Next steps?