## C100R-NCR
DESCRIBECOMMENT | DESCRIBEDATE | DESCRIBESTAFF | DISPOSITION | FINALDATE | FINALDISPOSITION | FINALENGINEER | PARTDESCRIPTION | RESPONDINGDATE | RESPONDINGENGINEER | REWORKDATE | REWORKSTAFF | SN | TRAVELERID | TRAVELERREVISION | TRAVSEQNUMBER | TRAV_CLOSE_DATE | TRAV_COMPLETE | NCR_COMPLETE | NCR_OPEN_DATE | NCR_REVISION | NCR_SEQ_NUM
r | 2018-12-07 18:52 | JOGLE | Use As Is | [empty string] | [empty string] | [empty string] | C100R O39 HV Assy | 2019-10-31 16:15 | FISCHER | [empty string] | [empty string] | C100-RI-039 | C100R-CAV-ASSY-HELV | R1 | 2 | 2019-10-31 16:16 | y | y | 2018-12-07 18:55 | R10 | 1
See attachment for dimensional non-conforming. | 2018-12-07 20:58 | JOGLE | Hold/Modify | 2019-01-16 10:27 | Use As Is | ARI | C100R O55 HV Assy | 2018-12-14 10:17 | ARI | [empty string] | [empty string] | C100-RI-055 | C100R-CAV-ASSY-HELV | R1 | 3 | 2019-01-16 10:28 | y | y | 2018-12-07 21:01 | R10 | 2
Dimensional non-conforming.See attachment for dimensional inspection results. | 2018-12-11 22:48 | JOGLE | Use As Is | [empty string] | [empty string] | [empty string] | C100 053 HV ASSY | 2018-12-14 10:16 | ARI | [empty string] | [empty string] | C100-RI-053 | C100R-CAV-ASSY-HELV | R1 | 4 | 2018-12-14 10:18 | y | y | 2018-12-11 22:49 | R10 | 3
Dimension out of tolerance. Please see attached. | 2018-12-12 15:49 | GEORGED | Use As Is | [empty string] | [empty string] | [empty string] | [empty string] | 2018-12-12 16:22 | KDAVIS | [empty string] | [empty string] | C100-RI-051 | C100R-CAV-ASSY-HELV | R1 | 5 | 2018-12-12 16:23 | y | y | 2018-12-12 15:50 | R10 | 4
Minor dimensional non-conforming. See Attachment for details. | 2018-12-14 21:18 | JOGLE | Hold/Modify | 2019-01-16 14:12 | Use As Is | ARI | C100R O49 HV Assy | 2019-01-14 12:48 | ARI | [empty string] | [empty string] | C100-RI-049 | C100R-CAV-ASSY-HELV | R1 | 6 | 2019-01-16 14:12 | y | y | 2018-12-14 21:21 | R10 | 5
Dimensional non conforming. See attachment for detailed dimensional report. | 2018-12-17 21:42 | JOGLE | Proceed to next WorkCenter | 2019-10-31 16:17 | Use As Is | FISCHER | C100R O43 HV Assy | 2019-01-02 11:59 | KDAVIS | [empty string] | [empty string] | C100-RI-043 | C100R-CAV-ASSY-HELV | R1 | 7 | 2019-10-31 16:18 | y | y | 2018-12-17 21:44 | R10 | 6
Dimensional non conforming.See attachment for dimensional inspection report. | 2018-12-18 20:10 | JOGLE | Use As Is | [empty string] | [empty string] | [empty string] | C100R O47 HV Assy | 2018-12-19 09:43 | KDAVIS | [empty string] | [empty string] | C100-RI-047 | C100R-CAV-ASSY-HELV | R1 | 8 | 2018-12-19 09:43 | y | y | 2018-12-18 20:12 | R10 | 8
Lock frequency was 1496.7079 MHz, slightly out of spec which is 1496.400-1496.700 MHz | 2018-12-20 11:20 | LZHAO | Use As Is | [empty string] | [empty string] | [empty string] | [empty string] | 2019-01-16 14:09 | ARI | [empty string] | [empty string] | C100-RI-039 | C100R-CAV-VTRF | R1 | 3 | 2019-01-16 14:10 | y | y | 2018-12-20 11:21 | R10 | 9
FE Onset at 11 MV/m | 2018-12-21 09:49 | POWEN | Hold/Re-measure | 2019-01-16 10:48 | Use As Is | ARI | [empty string] | 2019-01-16 10:42 | ARI | [empty string] | [empty string] | C100-RI-056 | C100R-CAV-VTRF | R1 | 4 | 2019-01-16 10:49 | y | y | 2018-12-21 09:50 | R10 | 10
Field probe Q is slightly low at 7.55e11 range 0.8 to 1.8e12. | 2019-01-09 14:30 | POWERS | Use As Is | [empty string] | [empty string] | [empty string] | [empty string] | 2019-01-16 10:42 | ARI | [empty string] | [empty string] | C100-RI-051 | C100R-CAV-VTRF | R1 | 6 | 2019-01-16 10:42 | y | y | 2019-01-09 14:31 | R10 | 11
Cavity Field flatness at 87% FPC Body Qext 3.09E7 | 2019-01-15 10:15 | OVERTONR | Hold/Re-measure | 2019-01-16 10:30 | Use As Is | ARI | [empty string] | 2019-01-16 10:28 | ARI | [empty string] | [empty string] | C100-RI-047 | C100R-CAV-RFIN | R1 | 8 | 2019-01-16 10:30 | y | y | 2019-01-15 10:21 | R10 | 12
FE onset 8 MV/m | 2019-01-28 09:46 | POWEN | Hold/Modify | 2019-10-29 10:47 | Reject | KDAVIS | [empty string] | 2019-10-29 10:43 | KDAVIS | [empty string] | [empty string] | C100-RI-047 | C100R-CAV-VTRF | R1 | 11 | 2019-10-29 10:51 | y | y | 2019-01-28 09:47 | R10 | 13
Knife edge damaged on 2.75" conflat flange. Please see attached picture of damage. | 2019-01-31 11:47 | GEORGED | Hold/Modify | 2019-10-31 16:20 | Use As Is | FISCHER | [empty string] | 2019-02-04 15:08 | FISCHER | [empty string] | [empty string] | L16 | C100R-CM-INSP-GVWG | R2 | 2 | 2019-10-31 16:21 | y | y | 2019-01-31 11:49 | R10 | 14
FE onset at 8 MV/m after activation at 17 MV/m | 2019-02-08 12:31 | POWEN | Reject | [empty string] | [empty string] | [empty string] | [empty string] | 2019-10-29 10:48 | KDAVIS | [empty string] | [empty string] | C100R | C100R-CAV-VTRF | R1 | 15 | 2019-10-29 10:51 | y | y | 2019-02-08 12:32 | R10 | 15
Threaded end flange inside body has stains. | 2021-04-20 12:30 | JFMOORE | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | R23 | C100R-CM-INSP-GVWG | R2 | 35 | [empty string] | n | n | 2021-04-20 12:31 | R11 | 27
Thru flange end copper is not continuous around the face. Threaded end flange inside body has stains. | 2021-04-20 13:00 | JFMOORE | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | R42 | C100R-CM-INSP-GVWG | R2 | 36 | [empty string] | n | n | 2021-04-20 13:03 | R11 | 28
Threaded end flange inside body has stains. Thru flange copper is not uniform on the face. | 2021-04-20 13:54 | JFMOORE | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | R32 | C100R-CM-INSP-GVWG | R2 | 38 | [empty string] | n | n | 2021-04-20 13:56 | R11 | 29
Thru flange end has scratches on face outside of seal area. | 2021-04-21 10:29 | JFMOORE | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | L19 | C100R-CM-INSP-GVWG | R2 | 39 | [empty string] | n | n | 2021-04-21 10:31 | R11 | 30
Threaded end flange inside body has stains. | 2021-04-21 10:32 | JFMOORE | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | L19 | C100R-CM-INSP-GVWG | R2 | 39 | [empty string] | n | n | 2021-04-21 10:34 | R11 | 31
Thru flange end copper on face is not continuous. | 2021-04-21 10:59 | JFMOORE | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | L37 | C100R-CM-INSP-GVWG | R2 | 40 | [empty string] | n | n | 2021-04-21 11:01 | R11 | 32
Thru end flange inside body has stains. | 2021-04-21 11:02 | JFMOORE | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | L37 | C100R-CM-INSP-GVWG | R2 | 40 | [empty string] | n | n | 2021-04-21 11:04 | R11 | 33
Threaded end flange inside body has stains. 2.75 O.D CF flange has discoloration. 1.33 O.D mini half nipple non-rotatable flange near threaded flange end has discoloration. | 2021-04-21 11:57 | JFMOORE | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | L07 | C100R-CM-INSP-GVWG | R2 | 41 | [empty string] | n | n | 2021-04-21 12:04 | R11 | 34
Threaded end flange inside body has stains. Thru end flange inside body has stains. | 2021-04-21 13:05 | JFMOORE | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | L33 | C100R-CM-INSP-GVWG | R2 | 42 | [empty string] | n | n | 2021-04-21 13:07 | R11 | 35
Thru flange end inside body has stains. Threaded flange inside body has stains | 2021-04-21 13:27 | JFMOORE | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | R27 | C100R-CM-INSP-GVWG | R2 | 43 | [empty string] | n | n | 2021-04-21 13:30 | R11 | 36
Large Flange o-ring groove has deep ding on bottom surface. See picture attached | 2021-04-30 07:58 | JFMOORE | Use As Is | [empty string] | [empty string] | [empty string] | [empty string] | 2021-05-20 11:35 | KDAVIS | [empty string] | [empty string] | F061584-02 | C100R-CAV-INSP-WGD-RCYC | R1 | 9 | 2021-05-20 11:35 | y | y | 2021-04-30 08:01 | R11 | 37
Large Flange o-ring groove has ding on bottom surface. | 2021-04-30 09:34 | JFMOORE | Use As Is | [empty string] | [empty string] | [empty string] | [empty string] | 2021-05-20 11:35 | KDAVIS | [empty string] | [empty string] | F063951-01 | C100R-CAV-INSP-WGD-RCYC | R1 | 10 | 2021-05-20 11:36 | y | y | 2021-04-30 09:36 | R11 | 38
Discoloration around weld on copper plate both sides on copper plate. Discoloration on inside body on small flange edge. | 2021-04-30 11:13 | JFMOORE | Use As Is | [empty string] | [empty string] | [empty string] | [empty string] | 2021-05-20 11:38 | KDAVIS | [empty string] | [empty string] | F892523/02 | C100R-CAV-INSP-WGD-RCYC | R1 | 11 | 2021-05-20 11:38 | y | y | 2021-04-30 11:18 | R11 | 39
Holes out of location and oversized holes. See report. | 2021-05-03 14:22 | MOSBY | [empty string] | [empty string] | [empty string] | [empty string] | UNKN | [empty string] | [empty string] | [empty string] | [empty string] | L33 | C100R-CM-INSP-GVWG | R2 | 42 | [empty string] | n | n | 2021-05-03 14:23 | R11 | 40
Waveguide small flange flatness out of tolerance. Measured .005" Out of tolerance .002" | 2021-05-04 14:05 | GEORGED | Hold/Re-measure | 2021-05-27 14:03 | Use As Is | KDAVIS | [empty string] | 2021-05-20 11:40 | KDAVIS | [empty string] | [empty string] | F892523/02 | C100R-CAV-INSP-WGD-RCYC | R1 | 11 | 2021-05-27 14:03 | y | y | 2021-05-04 14:06 | R11 | 41
Visual:Fail. Full gasket imprint on FPC flange. | 2021-05-05 15:53 | MOSBY | Hold/Modify | 2021-05-07 12:01 | Use As Is | ASHLEYA | [empty string] | 2021-05-05 16:17 | ASHLEYA | [empty string] | [empty string] | C100-RI-070 | C100R-CAV-LAP | R2 | 10 | 2021-05-07 12:02 | y | y | 2021-05-05 15:55 | R11 | 43
Fingerprints present inside part on copper plating. Pictures attached of copper surface. | 2021-05-06 13:54 | GEORGED | Use As Is | [empty string] | [empty string] | [empty string] | [empty string] | 2021-05-27 14:03 | KDAVIS | [empty string] | [empty string] | F063952-04 | C100R-CAV-INSP-WGD-RCYC | R1 | 17 | 2021-05-27 14:04 | y | y | 2021-05-06 13:56 | R11 | 44
Cavity produced neutron field emission during VTA tests, FE onset 15.5 MV/m | 2021-05-22 19:46 | POWEN | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | C100-RI-070 | C100R-CAV-VTRF | R1 | 19 | [empty string] | n | n | 2021-05-22 19:47 | R11 | 45
Cavity Q0 is low, 5e9 | 2021-05-22 20:18 | POWEN | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | C100-RI-073 | C100R-CAV-VTRF | R1 | 20 | [empty string] | n | n | 2021-05-22 20:19 | R11 | 46
Q0 of cavity is low, 5e+9 at 20MV/m | 2021-05-22 20:24 | POWEN | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | C100-RI-073 | C100R-CAV-VTRF | R1 | 20 | [empty string] | n | n | 2021-05-22 20:25 | R11 | 47
Qext2 is low, 1.19e+11 | 2021-05-22 20:26 | POWEN | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | C100-RI-068 | C100R-CAV-VTRF | R1 | 21 | [empty string] | n | n | 2021-05-22 20:27 | R11 | 48
Q0 well below spec, 3.71e+9 | 2021-05-22 20:55 | POWEN | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | C100-RI-068 | C100R-CAV-VTRF | R1 | 21 | [empty string] | n | n | 2021-05-22 20:55 | R11 | 49
Final FE Onset 11 MV/m | 2021-05-22 20:55 | POWEN | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | C100-RI-068 | C100R-CAV-VTRF | R1 | 21 | [empty string] | n | n | 2021-05-22 20:56 | R11 | 50
Q0 is low, 5.59e+9 at 20 MV/m | 2021-05-22 21:10 | POWEN | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | C100-RI-070 | C100R-CAV-VTRF | R1 | 22 | [empty string] | n | n | 2021-05-22 21:11 | R11 | 51
Cavity power limited at 8.6 MV/m (100W) Appeared extremely undercoupled. | 2021-06-10 17:29 | GRENOBLE | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | C100-RI-076 | C100R-CAV-VTRF | R1 | 27 | [empty string] | n | n | 2021-06-10 17:31 | R11 | 52
Input cable heating prevented full cavity test | 2021-06-10 17:51 | GRENOBLE | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | C100-RI-077 | C100R-CAV-VTRF | R1 | 26 | [empty string] | n | n | 2021-06-10 17:52 | R11 | 53
Lock frequency 1496.7138 MHz, out of spec which is 1496.4-1496.7 MHz | 2021-06-17 13:44 | LZHAO | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | C100-RI-074 | C100R-CAV-VTRF | R1 | 29 | [empty string] | n | n | 2021-06-17 13:46 | R11 | 54
Lock frequency 1496.7043 MHz, slightly out of spec 1496.4-1496.7 MHz. | 2021-06-17 13:47 | LZHAO | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | C100-RI-077 | C100R-CAV-VTRF | R1 | 30 | [empty string] | n | n | 2021-06-17 13:49 | R11 | 55
KLORENZ -9.23 Hz/MVm2, out of spec which is -4.0~-6.0 | 2021-06-17 13:49 | LZHAO | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | C100-RI-077 | C100R-CAV-VTRF | R1 | 30 | [empty string] | n | n | 2021-06-17 13:50 | R11 | 56
KLORENZ -6.47, out of spec which is -4.0~-6.0 | 2021-06-17 13:51 | LZHAO | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | C100-RI-076 | C100R-CAV-VTRF | R1 | 31 | [empty string] | n | n | 2021-06-17 13:52 | R11 | 57
Low Q0, Qext1 out of spec, Emax 16.7 out of spec | 2021-06-17 13:58 | LZHAO | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | C100-RI-074 | C100R-CAV-VTRF | R1 | 29 | [empty string] | n | n | 2021-06-17 14:00 | R11 | 58
Low Q0, Emax 10 MV/m out of spec | 2021-06-17 14:01 | LZHAO | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | C100-RI-077 | C100R-CAV-VTRF | R1 | 30 | [empty string] | n | n | 2021-06-17 14:02 | R11 | 59
Low Q0, Emax 7.65 out of spec | 2021-06-17 14:03 | LZHAO | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | C100-RI-076 | C100R-CAV-VTRF | R1 | 31 | [empty string] | n | n | 2021-06-17 14:04 | R11 | 60
Lock Frequency slightly over specification. Specification 1496.700 MHz Lock Frequency 1496.710 MHz | 2021-06-29 11:43 | GRENOBLE | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | C100-RI-074 | C100R-CAV-VTRF | R1 | 33 | [empty string] | n | n | 2021-06-29 11:45 | R11 | 61
Onset of FE 9.2 MV/m. FE Limit 16 MV/m. | 2021-06-29 18:21 | GRENOBLE | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | C100-RI-074 | C100R-CAV-VTRF | R1 | 33 | [empty string] | n | n | 2021-06-29 18:22 | R11 | 62
Cavity is FE limited to 16.8 MV/m with 1R/hour and FE loading | 2021-07-05 19:53 | KDAVIS | Hold/Modify | [empty string] | [empty string] | [empty string] | [empty string] | 2021-07-05 19:56 | KDAVIS | [empty string] | [empty string] | C100-RI-077 | C100R-CAV-VTRF | R1 | 34 | [empty string] | y | n | 2021-07-05 19:57 | R11 | 63
Low Q with strong Q-slope. Cavity only made 10.7 MV/m | 2021-07-14 10:35 | POWERS | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | C100-RI-076 | C100R-CAV-VTRF | R1 | 36 | [empty string] | n | n | 2021-07-14 10:36 | R11 | 64
Low field FE onset at 5.5 MV/m after something blew up. Prior to that FE onset was about 9 MV/m. | 2021-07-14 12:02 | POWERS | [empty string] | [empty string] | [empty string] | [empty string] | CAVITY ASSEMBLY | [empty string] | [empty string] | [empty string] | [empty string] | C100-RI-080 | C100R-CAV-VTRF | R1 | 37 | [empty string] | n | n | 2021-07-14 12:03 | R11 | 65
Lorentz coefficient was -6.9 which was outside of the range of -4 to -6. | 2021-07-14 12:17 | POWERS | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | C100-RI-074 | C100R-CAV-VTRF | R1 | 38 | [empty string] | n | n | 2021-07-14 12:18 | R11 | 66
Cavity had early FE onset at 13 MV/m | 2021-07-14 12:18 | POWERS | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | C100-RI-074 | C100R-CAV-VTRF | R1 | 38 | [empty string] | n | n | 2021-07-14 12:19 | R11 | 67
CMM inspection "As Found" performed on C100-RI-074 cavity. OOT conditions. See attached report. | 2021-07-22 13:57 | MOSBY | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | RI074 | C100R-CAV-ASSY-HELV | R1 | 11 | [empty string] | n | n | 2021-07-22 14:00 | R11 | 68
FE onset at 12.65 MV/m | 2021-07-27 12:03 | POWERS | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | C100-077 | C100R-CAV-VTRF | R1 | 39 | [empty string] | n | n | 2021-07-27 12:05 | R11 | 69
Cavity Quench at 15 MV/m | 2021-07-28 15:27 | POWEN | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | C100-RI-076 | C100R-CAV-VTRF | R1 | 40 | [empty string] | n | n | 2021-07-28 15:28 | R11 | 70
Qe1 and Qe2 out of specified range during VTRF test | 2021-08-08 15:29 | POWEN | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | C100-RI-026 | C100R-CAV-VTRF | R1 | 41 | [empty string] | n | n | 2021-08-08 15:30 | R11 | 71
VTRF limited by field emission admin limit to 14 MV/m | 2021-08-08 15:30 | POWEN | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | C100-RI-026 | C100R-CAV-VTRF | R1 | 41 | [empty string] | n | n | 2021-08-08 15:31 | R11 | 72
Cavity quench with FE at 18.5 MV/m | 2021-08-08 17:53 | POWEN | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | C100-RI-080 | C100R-CAV-VTRF | R1 | 43 | [empty string] | n | n | 2021-08-08 17:54 | R11 | 73
The cavity quenched at 14.2 MV/m. | 2021-08-12 10:59 | LZHAO | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | C100-RI-076 | C100R-CAV-VTRF | R1 | 44 | [empty string] | n | n | 2021-08-12 11:01 | R11 | 74
Q1 measured 7.08e9. Specification 0.8-1.2e10 | 2021-08-17 12:09 | GRENOBLE | [empty string] | [empty string] | [empty string] | [empty string] | cavity | [empty string] | [empty string] | [empty string] | [empty string] | C100_RI_026 | C100R-CAV-VTRF | R1 | 46 | [empty string] | n | n | 2021-08-17 12:11 | R11 | 75
Copper plating deteriorated in two areas inside waveguide. Please see attached picture. | 2021-08-19 14:09 | GEORGED | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | [empty string] | F061359-07 | C100R-CAV-INSP-WGD-RCYC | R1 | 19 | [empty string] | y | n | 2021-08-19 14:10 | R11 | 76
Damage/Dings on knife edge seal. Picture attached. | 2021-08-20 13:06 | GEORGED | Use As Is | [empty string] | [empty string] | [empty string] | [empty string] | 2021-08-24 07:01 | SCOTT | [empty string] | [empty string] | F063952-04 | C100R-CAV-INSP-WGD-RCYC | R1 | 24 | 2021-08-24 07:02 | y | y | 2021-08-20 13:07 | R11 | 77
Foreign material/staining present on ceramic window flange. Please see attached. | 2021-08-20 13:11 | GEORGED | Use As Is | [empty string] | [empty string] | [empty string] | [empty string] | 2021-08-24 06:59 | SCOTT | [empty string] | [empty string] | F063952-04 | C100R-CAV-INSP-WGD-RCYC | R1 | 24 | 2021-08-24 07:01 | y | y | 2021-08-20 13:12 | R11 | 78
Damage/dings on knife edge. Pictures attached. | 2021-08-20 15:32 | GEORGED | Use As Is | [empty string] | [empty string] | [empty string] | [empty string] | 2021-08-24 06:52 | SCOTT | [empty string] | [empty string] | F061584-02 | C100R-CAV-INSP-WGD-RCYC | R1 | 18 | 2021-08-24 06:57 | y | y | 2021-08-20 15:33 | R11 | 79