## Slide 1: SNPPU Name
Color Legend |  | Count | Percent
CP | Complete (CP) | 72 | 93.51%
NR | New Revision Out for Approval (NR) | 1 | 1.30%
OA | Out for Approval (OA) | 1 | 1.30%
30 | Due in 30 Days | 0 | 0.00%
15 | Due in 15 Days | 0 | 0.00%
OD | Overdue | 2 | 2.60%
 | Remaining | 2 | 2.60%
 | Total Traveler IDs | 77 | 
Out for Approval/New Revision
SNSPPU-PR-CHEM-CAV-DEGR-R1
SNSPPU-INSP-TPHTB-R2
Approaching Overdue
NONE
Overdue
SNSPPU-CM-ASSY-R1
SNSPPU-CHEM-CAV-DEGR-R1
Please Submit any changes or questions to pansophy@jlab.org
Note:
Project Masterlist can be found in the project docushare folder
Traveler Acronym list can be found in Pansophy, under the User Tools > Traveler Tools drop downs

## Slide 2: SNSPPU Traveler Listing
Overdue |  |  |  |  | 
Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author
Cavity Degreasing | SNSPPU-CHEM-CAV-DEGR | R1 | 6/15/21 | 7/23/21 | A. Mitchell
Final Cryomodule Assembly | SNSPPU-CM-ASSY | R1 | 7/22/21 | 10/1/21 | J. Fischer
Out for Approval |  |  |  |  | 
Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author
Cavity Degreasing Procedure | SNSPPU-PR-CHEM-CAV-DEGR | R1 | 6/15/21 | 7/23/21 | A. Mitchell
Tophat Bellow Inspection | SNSPPU-INSP-TPHTB | R2 | 1/4/21 | ? | M. Marchlik