## Slide 1: P1
Color Legend |  | Count | Percent
CP | Complete (CP) | 40 | 97.56%
NR | New Revision Out for Approval (NR) | 0 | 0.00%
OA | Out for Approval (OA) | 1 | 2.44%
30 | Due in 30 Days | 0 | 0.00%
15 | Due in 15 Days | 0 | 0.00%
OD | Overdue | 0 | 0.00%
 | Remaining | 0 | 0.00%
 | Total Traveler IDs | 41 | 
Out for Approval/New Revision
P1-ACC-CM-COMM-R1
Approaching Overdue
NONE
Overdue
NONE
Please Submit any changes or questions to pansophy@jlab.org
Note:
Project Masterlist can be found in the project docushare folder
Traveler Acronym list can be found in Pansophy, under the User Tools > Traveler Tools drop downs

## Slide 2: P1 Traveler Listing
Overdue |  |  |  |  | 
Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author
Cryomodule Commissioning | P1-ACC-CM-COMM | R1 | 6/1/21 |  | M.DRURY

## Slide 3: C100R
Color Legend |  | Count | Percent
CP | Complete (CP) | 32 | 71.11%
NR | New Revision Out for Approval (NR) | 0 | 0.00%
OA | Out for Approval (OA) | 0 | 0.00%
30 | Due in 30 Days | 0 | 0.00%
15 | Due in 15 Days | 7 | 15.56%
OD | Overdue | 1 | 2.22%
 | Remaining | 5 | 11.11%
 | Total Traveler IDs | 45 | 
Out for Approval/New Revision
NONE
Approaching Overdue
C100R-CAV-GVWG-CLN
C100R-CM-ASSY-BPIP
C100R-CM-ASSY
C100R-CM-ASSY-COLD
C100R-CM-ASSY-SFR
C100R-CM-ASSY-VV
C100R-CM-ASSY-BPIP
Overdue
C100R-CST-CLN-COMP
Please Submit any changes or questions to pansophy@jlab.org
Note:
Project Masterlist can be found in the project docushare folder
Traveler Acronym list can be found in Pansophy, under the User Tools > Traveler Tools drop downs

## Slide 4: C100R Traveler Listing
Overdue |  |  |  |  | 
Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author
C100R Cavity Component Cleaning | C100R-CST-CLN-COMP |  | 7/1/21 | ? | R. Fielder
Approaching Overdue |  |  |  |  | 
Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author
C100R Cryomodule Beampipe Assembly | C100R-CM-ASSY-BPIP | R1 | 9/1/21 | ? | Fischer
C100R Cryomodule Final Assembly | C100R-CM-ASSY | R2 | 9/1/21 | ? | Fischer
C100R Cold Mass Assembly | C100R-CM-ASSY-COLD | R2 | 9/1/21 | ? | Fischer
C100R Thermal Shield and Space Frame Assembly | C100R-CM-ASSY-SFR | R2 | 9/1/21 | ? | Fischer
C100R Vacuum Vessel and End Can Assembly | C100R-CM-ASSY-VV | R2 | 9/1/21 | ? | Fischer
C100R Cryomodule Beampipe Assembly | C100R-CM-ASSY-BPIP | R2 | 9/1/21 | ? | Fischer
Secondary waveguide cleaning | C100R-CAV-GVWG-CLN |  | 9/1/21 | ? | ?