## Slide 1: PROJ Name
Color Legend |  | Count | Percent
CP | Complete (CP) | 73 | 62.93%
NR | New Revision Out for Approval (NR) | 1 | 0.86%
OA | Out for Approval (OA) | 6 | 5.17%
30 | Due in 30 Days | 0 | 0.00%
15 | Due in 15 Days | 2 | 1.72%
OD | Overdue | 6 | 5.17%
 | Remaining | 29 | 25.00%
 | Total Traveler IDs | 116 | 
Out for Approval/New Revision
L2HE-CHEM-CAV-HPR-R2
L2HE-PR-VTA-CAV-VTRF-R1
L2HE-INV-IROD2L-R1*
L2HE-INSP-JTVTK-R1
L2HE-INSP-TUNC-R1**
L2HE-INSP-TUNCX-R1**
L2HE-CHEM-COMP-DEGR-R1
Approaching Overdue
L2HE-CLNRM-CAV-LEAK-R1
L2HE-LERF-CM-ACTS-R1
Overdue
L2HE-CHEM-CAV-LAP-R1
L2HE-INV-IROD2P-R1*
L2HE-INSP-QUAD-R1
L2HE-INV-CERNOX-R1
L2HE-CHEM-COMP-LAP-R1
L2HE-LERF-CM-DMAG-R1
Please Submit any changes or questions to pansophy@jlab.org
Note:
Project Masterlist can be found in the project docushare folder
Traveler Acronym list can be found in Pansophy, under the User Tools > Traveler Tools drop downs
*L2HE-INV-IROD2L and IROD2P are on hold until we know for certain they are needed. If you know either way, please let us at pansophy know.
**L2HE-INSP-TUNC and TUNCX are approved and will be uploaded to pansophy.

## Slide 2: PROJ Traveler Listing
Overdue |  |  |  |  | 
Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author
Laping | L2HE-CHEM-CAV-LAP | R1 | 7/15/21 | ? | Wildeson
Receiving Inspection CM Rod Invar 2-Phase | L2HE-INV-IROD2P | R1 | 8/1/21 | ? | O'Brien
Quadrapole Magnet Inspection | L2HE-INSP-QUAD | R1 | 8/30/21 | ? | Lakshmi
LCLS-II HE Cernox Inventory Traveler | L2HE-INV-CERNOX | R1 | 8/15/21 | 10/1/21 | M. Dickey
Laping | L2HE-CHEM-COMP-LAP | R1 | 8/15/21 | 11/1/21 | Wildeson
Production Cryomodule Demagnetization | L2HE-LERF-CM-DMAG | R1 | 8/31/21 | ? | Cheng
Out for Approval |  |  |  |  | 
Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author
Cavity High Pressure Rinse | L2HE-CHEM-CAV-HPR | R2 | ? | ? | A. Wildeson
Production Cavity Vertical Testing Procedure | L2HE-PR-VTA-CAV-VTRF | R1 | 5/21/21 | ? | C. WILSON
Receiving Inspection CM Rod Invar 2-Phase Long | L2HE-INV-IROD2L | R1 | 8/1/21 | ? | O'Brien
Receiving Inspection CM Assembly, JT Valve Tube Kit | L2HE-INSP-JTVTK | R1 | 8/1/21 | ? | Kent
End Lever Tuner Mechanical Frame Inspection | L2HE-INSP-TUNC | R1 | 7/14/21 | 8/15/21 | Powen
End Lever Tuner Extended Mechanical Frame Inspection Traveler | L2HE-INSP-TUNCX | R1 | 7/14/21 | 8/15/21 | P Owen
Components Cleaning | L2HE-CHEM-COMP-DEGR | R1 | 7/1/21 | ? | Mitchell
Approaching Overdue |  |  |  |  | 
Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author
Cavity Evacuation & Leak Test | L2HE-CLNRM-CAV-LEAK | R1 | 9/1/21 | 10/1/21 | D. FOREHAND
Cryomodule Acceptance Test LERF | L2HE-LERF-CM-ACTS | R1 | 9/1/21 | ? | Drury