## Slide 1: C50R
Color Legend |  | Count | Percent
CP | Complete (CP) | 81 | 96.43%
NR | New Revision Out for Approval (NR) | 0 | 0.00%
OA | Out for Approval (OA) | 0 | 0.00%
30 | Due in 30 Days | 0 | 0.00%
15 | Due in 15 Days | 0 | 0.00%
OD | Overdue | 3 | 3.57%
 | Remaining | 0 | 0.00%
 | Total Traveler IDs | 84 | 
Out for Approval/New Revision
None
Approaching Overdue
None
Overdue
C50R-CPR-BCP-SUBC-R1
C50R-CPR-CLN-SUBC-R1
C50R-CPR-CHEM-CPR-R1
Please Submit any changes or questions to pansophy@jlab.org
Note:
Project Masterlist can be found in the project docushare folder
Traveler Acronym list can be found in Pansophy, under the User Tools > Traveler Tools drop downs

## Slide 2: C50R Traveler Listing
Overdue |  |  |  |  | 
Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author
C50R Pair Component Etching and Cleaning | C50R-CPR-BCP-SUBC | R1 | 8/1/21 | ? | A. Mitchell
C50R Subcomponent Cleaning | C50R-CPR-CLN-SUBC | R1 | 8/1/21 | ? | A. Mitchell
C50R Cavity Pair Cleaning and Acid Etching | C50R-CPR-CHEM-CPR | R1 | 8/1/21 | ? | A. Mitchell

## Slide 3: C75
Color Legend |  | Count | Percent
CP | Complete (CP) | 130 | 92.20%
NR | New Revision Out for Approval (NR) | 1 | 0.71%
OA | Out for Approval (OA) | 0 | 0.00%
30 | Due in 30 Days | 0 | 0.00%
15 | Due in 15 Days | 0 | 0.00%
OD | Overdue | 9 | 6.38%
 | Remaining | 2 | 1.42%
 | Total Traveler IDs | 141 | 
Out for Approval/New Revision
C75-FURN-HOML-BRAZ-R2
Approaching Overdue
NONE
Overdue
STP-PR-CAV-CHEM-BAKE-R1
C75-PR-CAV-CHEM-HEP-R1
“Beam line assembly procedure”
“JT calibration procedure”
C75-PR-CMA-BRBP-R1
C75-CMA-SUPBP-ASSY-R1
C75-CMA-BPIP-ASSY-R1
C75-CM-ASSY-ECRW-R1
C75-CM-ASSY-R1
Please Submit any changes or questions to pansophy@jlab.org
Note:
Project Masterlist can be found in the project docushare folder
Traveler Acronym list can be found in Pansophy, under the User Tools > Traveler Tools drop downs

## Slide 4: C75 Traveler Listing
Out For Approval |  |  |  |  | 
Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author
C75 HOM Load Brazing/ Assy | C75-FURN-HOML-BRAZ | R2 | 5/5/20 |  | S. Williams
Overdue |  |  |  |  | 
Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author
Baking in nitrogen oven | CP-STP-CAV-CHEM-BAKE | R1 | 8/27/21 |  | A. Mitchell
C75 HEP procedure | CP-CAV-CHEM-HEP | R1 | 8/27/21 |  | A. Mitchell
Beam line assembly procedure | ? |  | 8/15/21 |  | C. Wilcox
JT calibration procedure | CP-STP |  | 8/15/21 |  | K. Worland
Bridging bellows | CP-C75-CMA-BRBP | R1 | 8/15/21 |  | C. Wilcox
Supply end can beam pipe assembly | C75-CMA-SUPBP-ASSY | R1 | 8/15/21 |  | C. Wilcox
Supply end can pump drop assembly | ? | R1 | 8/15/21 |  | C. Wilcox
End Can Rework | C75-CM-ASSY-ECRW |  | 8/15/21 |  | J. Fischer
Cryomodule Assembly | C75-CM-ASSY | R1 | 8/15/21 |  | J. Fischer