## Sheet1
NCR SEQNUM | NCR REV | NCR OPEN DATE | NCR CLOSE DATE | PART DESCRIPTION | DESCRIBE COMMENT | DESCRIBE STAFF | DESCRIBE DATE | NCR CLOSED | RESPONDING ENGINEER | RESPONDING DATE | DISPOSITION | TRAV SEQNUM | TRAVELER ID | SERIAL NUMBER | TRAV REV | TRAV CLOSED | REWORK STAFF | FINAL ENGINEER | FINAL DATE | FINAL DISPOSITION | REWORK DATE
1 | R11 | 2021-03-09 13:44 | 2021-03-16 14:24 |  | Waveguide coupler flange (Dwg # SA-375-600-90) has multiple scratches present on flange. Please see attached. Multiple scratched areas checked w/profilometer. The worst area found was Rz (peak to valley) measured 294 u inch and RA (surface finish) measured 49 u inch. | GEORGED | 2021-03-09 13:40 | y | HUQUE | 2021-03-16 14:24 | Return To Vendor | 1 | L2HE-INSP-FPCWG | 004 | R1 | y
2 | R11 | 2021-05-04 14:39 |  | SINGLE CELL LCLS-II CAVITY | Q0(20.8) is 2.4e10, slightly lower than spec which is 2.5e10 | LZHAO | 2021-05-04 14:37 | n |  |  |  | 1 | L2HE-VTA-CAV-VTRF | 0331 | R1 | y
3 | R11 | 2021-05-05 10:37 |  | UNKN | Cavity did not pass due to FE up to 1R/hr. | GRENOBLE | 2021-05-05 10:35 | n |  |  |  | 2 | L2HE-VTA-CAV-VTRF | R009 | R1 | y
4 | R11 | 2021-05-18 12:04 | 2021-08-10 14:02 | UNKN | Cavity frequency was low at 1299.975 MHz | POWERS | 2021-05-18 12:03 | y | HANNESV | 2021-08-10 14:01 | Hold/Re-measure | 3 | L2HE-VTA-CAV-VTRF | 0040 | R1 | y |  | HANNESV | 2021-08-10 14:02 | Reject
5 | R11 | 2021-05-18 12:12 | 2021-08-10 13:59 | UNKN | Operator error except for two decay measurements the test was done at the 8pi/9 mode. For those measurements, Qo=2.9e10, Qfpc=1.94e10,Qfp=3.4e11 E = 2.9 MV/m | POWERS | 2021-05-18 12:08 | y | HANNESV | 2021-08-10 13:58 | Reject | 3 | L2HE-VTA-CAV-VTRF | 0040 | R1 | y
7 | R11 | 2021-05-19 12:19 | 2021-08-17 15:31 | PICKUP FEEDTHROUGH | Probe has stain | JFMOORE | 2021-05-19 12:18 | y | LZHAO | 2021-08-17 15:17 | Hold/Modify | 73 | L2HE-INSP-FPFT | 2061 | R1 | n |  | LZHAO | 2021-08-17 15:29 | Use As Is
8 | R11 | 2021-05-19 12:55 | 2021-08-17 15:34 |  | Scratches down outside diameter. | JFMOORE | 2021-05-19 12:53 | y | LZHAO | 2021-08-17 15:32 | Use As Is | 74 | L2HE-INSP-FPFT | 2062 | R1 | n
9 | R11 | 2021-05-25 06:45 | 2021-06-25 16:17 |  | HEH2134 has multiple dings down Antenna. | JFMOORE | 2021-05-25 06:38 | y | LZHAO | 2021-06-25 16:10 | Use As Is | 158 | L2HE-INSP-HMFT | 2134 | R1 | n
10 | R11 | 2021-05-25 08:27 | 2021-07-28 15:05 |  | HEH2143 probe antenna has metallic foreign material on face. | JFMOORE | 2021-05-25 08:25 | y | LZHAO | 2021-06-25 16:20 | Hold/Modify | 167 | L2HE-INSP-HMFT | 2143 | R1 | n |  | LZHAO | 2021-07-28 15:04 | Use As Is
11 | R11 | 2021-05-26 10:28 | 2021-08-10 14:01 | LCLS-II PRODUCTION CAVITY ASSEMBLY | Qext2 is 2.9200e+11, out of spec which is 0.75-2.5 e12. | LZHAO | 2021-05-26 10:26 | y | HANNESV | 2021-08-10 14:00 | Use As Is | 4 | L2HE-VTA-CAV-VTRF | R009 | R1 | y
12 | R11 | 2021-05-26 10:33 | 2021-08-10 13:58 |  | QextHOMb is 1.11e+11, out of spec which is >=2.7e11. Also, PHOMB at 21MVm was 3.52 W, out of spec which is ? 1.7 W | LZHAO | 2021-05-26 10:30 | y | HANNESV | 2021-08-10 13:57 | Hold/Re-measure | 4 | L2HE-VTA-CAV-VTRF | HE-R009 | R1 | y |  | HANNESV | 2021-08-10 13:57 | Use As Is
13 | R11 | 2021-05-27 11:28 | 2021-06-25 16:40 |  | Probe has multiple dings down along stem. | JFMOORE | 2021-05-27 11:26 | y | LZHAO | 2021-06-25 16:39 | Use As Is | 90 | L2HE-INSP-FPFT | 2078 | R1 | n
14 | R11 | 2021-05-27 12:42 | 2021-08-17 15:42 |  | Surface seal area has small imperfection. | JFMOORE | 2021-05-27 12:39 | y | LZHAO | 2021-06-25 16:41 | Hold/Modify | 94 | L2HE-INSP-FPFT | 2082 | R1 | n |  | LZHAO | 2021-08-17 15:41 | Use As Is
15 | R11 | 2021-05-27 13:05 | 2021-08-17 15:45 |  | Probe has gouge on O.D | JFMOORE | 2021-05-27 13:04 | y | LZHAO | 2021-08-17 15:44 | Use As Is | 95 | L2HE-INSP-FPFT | 2083 | R1 | n
16 | R11 | 2021-05-27 13:51 | 2021-06-25 16:46 |  | Probe O.D all the way around has rough finish. | JFMOORE | 2021-05-27 13:49 | y | LZHAO | 2021-06-25 16:46 | Use As Is | 97 | L2HE-INSP-FPFT | 2085 | R1 | n
17 | R11 | 2021-06-02 11:52 |  | PICKUP FEEDTHROUGH | Probe has line of rough imperfections. | JFMOORE | 2021-06-02 11:46 | n |  |  |  | 155 | L2HE-INSP-FPFT | 2143 | R1 | n
18 | R11 | 2021-06-02 13:39 |  |  | Seal surface area has rough finish. | JFMOORE | 2021-06-02 13:38 | n |  |  |  | 163 | L2HE-INSP-FPFT | 2151 | R1 | n
19 | R11 | 2021-06-03 07:39 | 2021-06-25 16:54 |  | Probe has rough finish | JFMOORE | 2021-06-03 07:38 | y | LZHAO | 2021-06-25 16:54 | Use As Is | 169 | L2HE-INSP-FPFT | 2157 | R1 | n
20 | R11 | 2021-06-03 07:57 | 2021-06-25 16:56 |  | Probe has rough finish | JFMOORE | 2021-06-03 07:56 | y | LZHAO | 2021-06-25 16:55 | Use As Is | 170 | L2HE-INSP-FPFT | 2158 | R1 | n
21 | R11 | 2021-06-03 09:06 |  |  | Seal surface area has rough finish. Probe 6mm radius has rough finish. | JFMOORE | 2021-06-03 09:04 | n |  |  |  | 259 | L2HE-INSP-HMFT | 2235 | R1 | n
22 | R11 | 2021-06-03 10:26 |  | HOM FEEDTHROUGH | Seal surface area is not smooth. Probe radius has rough finish. | JFMOORE | 2021-06-03 10:24 | n |  |  |  | 262 | L2HE-INSP-HMFT | 2238 | R1 | n
23 | R11 | 2021-06-04 13:07 |  | LCLS-II PRODUCTION CAVITY ASSEMBLY | Visual inspection of cavity bellows on SN CAV-284 found (3) minor dents in between bellow convolutions. See pictures in attach box. | JFMOORE | 2021-06-04 13:03 | n |  |  |  | 7 | L2HE-INSP-CAV | 0284 | R1 | y
24 | R11 | 2021-06-08 13:31 |  |  | Flange seal surface to probe tip distance measured 29.50 mm, slightly out of spec which is 29.51-29.61 mm. | LZHAO | 2021-06-08 13:28 | n | LZHAO | 2021-06-25 16:06 | Hold/Re-measure | 73 | L2HE-INSP-HMFT | 2049 | R1 | n
26 | R11 | 2021-06-15 11:24 |  |  | Probe is loose. | JFMOORE | 2021-06-15 11:23 | n |  |  |  | 60 | L2HE-INSP-FPFT | 2048 | R1 | n
27 | R11 | 2021-06-18 10:33 |  | PICKUP FEEDTHROUGH | Seal surface finish is not smooth | JFMOORE | 2021-06-18 10:32 | n |  |  |  | 150 | L2HE-INSP-FPFT | 2138 | R1 | n
28 | R11 | 2021-06-24 14:38 | 2021-06-25 19:09 | LCLS-II PRODUCTION CAVITY ASSEMBLY | Visual inspection of bellow convolutions found (2) small dents in bottom of convolution. | JFMOORE | 2021-06-24 14:36 | y | HANNESV | 2021-06-25 14:19 | Use As Is | 11 | L2HE-INSP-CAV | 0145 | R1 | y |  | HANNESV | 2021-06-25 19:08 | Use As Is
29 | R11 | 2021-06-24 15:06 | 2021-06-25 19:08 | LCLS-II PRODUCTION CAVITY ASSEMBLY | Visual inspection of bellow convolution only,found (1) small dent on bottom of bellow convolution. | JFMOORE | 2021-06-24 15:04 | y | HANNESV | 2021-06-25 14:20 | Use As Is | 13 | L2HE-INSP-CAV | 0118 | R1 | y
30 | R11 | 2021-07-06 11:26 | 2021-08-11 22:30 | UNKN | found small ding in bellows of CPI-001 coupler | DREYFUSS | 2021-07-06 11:24 | y | HUQUE | 2021-08-11 22:30 | Return To Vendor | 1 | L2HE-CLNRM-FPCC-INSP | CPI-FPCC-HE-001 | R1 | y
31 | R12 | 2021-07-07 10:08 | 2021-07-07 11:59 | LCLS-II PRODUCTION CAVITY ASSEMBLY | Testing Only! | BOOKWALT | 2021-07-07 10:07 | y | BOOKWALT | 2021-07-07 10:07 | Hold/Modify | 16 | L2HE-INSP-CAV | 0342 | R1 | y |  | KWILSON | 2021-07-07 11:59 | Conforming
32 | R12 | 2021-07-12 14:36 | 2021-08-10 15:31 | LCLS-II UPPER COLD MASS ASSEMBLY | Drawing part # F10074420 Vertical support lines twisted. Please see attached. | GEORGED | 2021-07-12 14:34 | y |  |  |  | 1 | L2HE-CMA-UCM-INSP | RFCHE-UC-002 | R1 | y |  | CHENG | 2021-08-10 15:30 | Use As Is
33 | R12 | 2021-07-13 07:47 | 2021-08-10 15:34 | LCLS-II UPPER COLD MASS ASSEMBLY | Copper clamp indium foil applied to wrong half. | GEORGED | 2021-07-13 07:47 | y | CHENG | 2021-08-10 10:55 | Hold/Modify | 1 | L2HE-CMA-UCM-INSP | RFCHE-UC-002 | R1 | y |  | CHENG | 2021-08-10 15:34 | Conforming
34 | R12 | 2021-07-13 07:48 | 2021-08-10 15:36 | LCLS-II UPPER COLD MASS ASSEMBLY | Cavity hangar has sharp edges. | GEORGED | 2021-07-13 07:48 | y | CHENG | 2021-08-10 15:34 | Hold/Modify | 1 | L2HE-CMA-UCM-INSP | RFCHE-UC-002 | R1 | y |  | CHENG | 2021-08-10 15:35 | Conforming
35 | R12 | 2021-07-13 08:21 | 2021-08-10 15:43 | LCLS-II UPPER COLD MASS ASSEMBLY | During the inspection, we came across bolts that had suspicious head markings.We had M16 and 1/4-20 hardware that had "vvv" on the head instead of "THE". The proper authorities were notified. | JJCAMP | 2021-07-13 08:08 | y |  |  |  | 1 | L2HE-CMA-UCM-INSP | RFCHE-UC-002 | R1 | y |  | CHENG | 2021-08-10 15:40 | Use As Is
36 | R12 | 2021-07-13 11:04 | 2021-08-11 13:13 | VESSEL LCLS-II AFTER MACHING WELDMENT | The fillet weld located on weld#C1 have been reduced in size via some machining operation. The welds are not complaint with the drawing, specifications or the welding code. It is my intention to reject the fillet weld portion of this flange weld joint that also includes a CJP groove weld. However, I found the groove weld portion of this same flange weld joint to be in compliance. | JALSTON | 2021-07-13 11:02 | y |  |  |  | 1 | L2HE-CWI-VV | RFCHE-VV-002 | R1 | y |  | CHENG | 2021-08-11 13:11 | Use As Is
37 | R12 | 2021-07-13 11:20 |  | LCLS-II PRODUCTION CAVITY ASSEMBLY | Cavity quench at 21.8 MV/m | POWEN | 2021-07-13 11:18 | n | HANNESV | 2021-07-14 17:42 | Hold/Re-measure | 8 | L2HE-VTA-CAV-VTRF | 0331 | R1 | y
38 | R12 | 2021-07-31 08:17 | 2021-07-31 15:12 | LCLS-II PRODUCTION CAVITY ASSEMBLY | FE onset 5.5 MV/m, FE loading and 1R/hr at 14 MV/m | KDAVIS | 2021-07-31 08:16 | y | HANNESV | 2021-07-31 15:10 | Hold/Re-measure | 9 | L2HE-VTA-CAV-VTRF | HE-331 | R1 | y |  | HANNESV | 2021-07-31 15:11 | Reject
39 | R12 | 2021-08-02 11:18 | 2021-08-10 15:23 | FPC WARM PART | Found scratch on copper plating of DN40 flange | MMURPHY | 2021-06-22 | y |  |  |  | 1 | L2HE-CMA-FPCW-INSP | CPI-FPCW-HE-001 | R1 | n |  | HUQUE | 2021-08-10 15:22 | Return To Vendor
40 | R12 | 2021-08-02 11:29 | 2021-08-13 13:49 | FPC WARM PART | Found scratch on copper plating of DN40 flange | MMURPHY | 2021-06-23 | y |  |  |  | 2 | L2HE-CMA-FPCW-INSP | CPI-FPCW-HE-002 | R1 | n |  | HUQUE | 2021-08-13 13:49 | Return To Vendor
41 | R12 | 2021-08-02 11:33 | 2021-08-13 13:50 | FPC WARM PART | Found scratches on copper plating of DN40 flange | MMURPHY | 2021-07-06 | y |  |  |  | 3 | L2HE-CMA-FPCW-INSP | CPI-FPCW-HE-007 | R1 | n |  | HUQUE | 2021-08-13 13:49 | Return To Vendor
42 | R12 | 2021-08-02 11:41 | 2021-08-13 13:51 | FPC WARM PART | Found scratch on copper plating of DN40 flange | MMURPHY | 2021-07-19 | y |  |  |  | 5 | L2HE-CMA-FPCW-INSP | CPI-FPCW-HE-005 | R1 | n |  | HUQUE | 2021-08-13 13:51 | Return To Vendor
43 | R12 | 2021-08-02 13:52 | 2021-08-13 13:52 | FPC WARM PART | Push rod bellows distorted and slightly twisted. Push rod was difficult to remove and reinstall. The M6 antenna vented bolt was loose | MMURPHY | 2021-07-19 | y |  |  |  | 6 | L2HE-CMA-FPCW-INSP | CPI-FPCW-HE-006 | R1 | n |  | HUQUE | 2021-08-13 13:51 | Return To Vendor
44 | R12 | 2021-08-02 14:00 | 2021-08-13 13:52 | FPC WARM PART | Face if DN100 flange scratched, small scratch on outer conductor copper plating. | MMURPHY | 2021-07-20 | y |  |  |  | 7 | L2HE-CMA-FPCW-INSP | CPI-FPCW-HE-009 | R1 | n |  | HUQUE | 2021-08-13 13:52 | Use As Is
45 | R12 | 2021-08-02 14:07 | 2021-08-13 13:48 | FPC WARM PART | Push rod bellows very bent and twisted, some convolutions were pinched. Push rod was not engaged. | MMURPHY | 2021-07-20 | y |  |  |  | 8 | L2HE-CMA-FPCW-INSP | CPI-FPCW-HE-010 | R1 | n |  | HUQUE | 2021-08-13 11:22 | Return To Vendor
46 | R12 | 2021-08-02 14:10 | 2021-08-13 13:52 | FPC WARM PART | RF contact area of inner conductor copper was pitted and copper plating had defects | MMURPHY | 2021-07-20 | y |  |  |  | 8 | L2HE-CMA-FPCW-INSP | CPI-FPCW-HE-010 | R1 | n |  | HUQUE | 2021-08-13 13:52 | Return To Vendor
47 | R12 | 2021-08-10 11:12 |  | MAGNETIC SHIELD CAVITY ASSEMBLY | Part I.D.# F10048728 Rev.A Shield, LCLS-11 2nd layer center section A. has minor ding about 5/16 diameter and .010 deep. Part I.D.# F10048731 Shield, LCLS-11 2nd layer coupler side A. Has (2) sets of imperfections (1)is about 6" long the 2nd is about 4" long ." | [8 empty] | RFCHE-MS-028
48 | R12 | 2021-08-10 13:08 |  | MAGNETIC SHIELD CAVITY ASSEMBLY | Part I.D.# F10048728 Rev.A Shield, LCLS-11 2nd layer center section A. Has light ding 3/8 diameter and .010 deep. Part I.D.# F10048731 Rev.A Shield,LCLS-11 2nd layer coupler side A. Has 6" long imperfection. marked in red." | [8 empty] | RFCHE-MS-026
49 | R12 | 2021-08-10 13:51 |  | HOM FEEDTHROUGH | Flange seal surface to probe tip is 29.5 mm, slightly out of spec which is 29.51-29.61 mm | LZHAO | 2021-08-10 13:50 | n | LZHAO | 2021-08-17 16:50 | Hold/Re-measure | 186 | L2HE-INSP-HMFT | 2161 | R1 | n
50 | R12 | 2021-08-12 13:32 | 2021-08-31 13:32 | MAGNETIC SHIELD CAVITY ASSEMBLY | Damage noted during visual inspection. Part ID#s F10048802 & F10048803 has a cut through the MAG Cavity turner end. See attached photos. Normal shield shown. | MOSBY | 2021-08-12 13:11 | y |  |  |  | 32 | L2HE-INSP-IMAG | RFCHE-MS-046 | R1 | n |  | CHENG | 2021-08-31 13:31 | Conforming
51 | R12 | 2021-08-13 10:08 | 2021-08-13 13:47 | FPC WARM PART | One of the RF spring had come undone from itself | MMURPHY | 2021-07-20 | y |  |  |  | 8 | L2HE-CMA-FPCW-INSP | CPI-FPCW-HE-010 | R1 | n |  | HUQUE | 2021-08-13 13:46 | Return To Vendor
52 | R12 | 2021-08-13 10:12 | 2021-08-31 10:22 | FPC WARM PART | Kapton sleeve missing covering the ceramic. | MMURPHY | 2021-07-19 | y | HUQUE | 2021-08-13 13:45 | Hold/Modify | 5 | L2HE-CMA-FPCW-INSP | CPI-FPCW-HE-005 | R1 | n |  | HUQUE | 2021-08-31 10:21 | Return To Vendor
53 | R12 | 2021-08-13 10:12 | 2021-08-31 10:22 | FPC WARM PART | Kapton sleeve missing covering the ceramic. | MMURPHY | 2021-07-19 | y | HUQUE | 2021-08-13 13:45 | Hold/Modify | 6 | L2HE-CMA-FPCW-INSP | CPI-FPCW-HE-006 | R1 | n |  | HUQUE | 2021-08-31 10:22 | Return To Vendor
54 | R12 | 2021-08-13 10:14 | 2021-08-31 10:22 | FPC WARM PART | Kapton sleeve missing covering ceramic. | MMURPHY | 2021-07-20 | y | HUQUE | 2021-08-13 13:45 | Hold/Modify | 7 | L2HE-CMA-FPCW-INSP | CPI-FPCW-HE-009 | R1 | n |  | HUQUE | 2021-08-31 10:22 | Return To Vendor
55 | R12 | 2021-08-13 10:16 | 2021-08-31 10:23 | FPC WARM PART | Kapton sleeve missing covering the ceramic. | MMURPHY | 2021-07-20 | y | HUQUE | 2021-08-13 10:35 | Hold/Modify | 8 | L2HE-CMA-FPCW-INSP | CPI-FPCW-HE-010 | R1 | n |  | HUQUE | 2021-08-31 10:22 | Return To Vendor
56 | R12 | 2021-08-19 19:38 | 2021-08-20 11:06 | LCLS-II PRODUCTION CAVITY ASSEMBLY | The lock frequency was below specification. It was 1299.966 MHz. | GRENOBLE | 2021-08-19 19:37 | y |  |  |  | 10 | L2HE-VTA-CAV-VTRF | HE-040 | R1 | y |  | HANNESV | 2021-08-20 11:05 | Reject
57 | R12 | 2021-08-27 11:53 |  | VESSEL LCLS-II AFTER MACHING WELDMENT | Paint present inside of groove of flange and on face of flanges. Drawing number from picture identifies flange. Please see attached. | GEORGED | 2021-08-27 11:49 | n |  |  |  | 2 | L2HE-CMA-VV-INSP | RFCHE -VV-004 | R1 | n
58 | R12 | 2021-08-27 11:59 |  | VESSEL LCLS-II AFTER MACHING WELDMENT | Scratches and pitting present on multiple flanges. Please see attached pictures. Drawing number from pictures identify flange with issue. | GEORGED | 2021-08-27 11:56 | n |  |  |  | 2 | L2HE-CMA-VV-INSP | RFCHE -VV-004 | R1 | n
59 | R12 | 2021-09-02 19:25 |  | LCLS-II PRODUCTION CAVITY ASSEMBLY | Cavity lock frequency 50 kHz below target range | POWEN | 2021-09-02 19:24 | n |  |  |  | 12 | L2HE-VTA-CAV-VTRF | HE-295 | R1 | n
60 | R12 | 2021-09-02 19:27 |  | LCLS-II PRODUCTION CAVITY ASSEMBLY | Qext 1 slightly above allowable range, Qext2 slightly below allowable range (per Traveler criteria) | POWEN | 2021-09-02 19:25 | n |  |  |  | 12 | L2HE-VTA-CAV-VTRF | HE-295 | R1 | n