## Slide 1: L2HE
Color Legend |  | Count | Percent
CP | Complete (CP) | 78 | 67.24%
NR | New Revision Out for Approval (NR) | 0 | 0.00%
OA | Out for Approval (OA) | 2 | 1.72%
30 | Due in 30 Days | 1 | 0.86%
15 | Due in 15 Days | 0 | 0.00%
OD | Overdue | 6 | 5.17%
 | Remaining | 29 | 25.00%
 | Total Traveler IDs | 116 | 
Out for Approval/New Revision
L2HE-INV-IROD2L-R1
L2HE-INSP-JTVTK-R1
Approaching Overdue
L2HE-INSP-QUAD-R1
Overdue
L2HE-CHEM-CAV-LAP-R1
L2HE-CLNRM-CAV-LEAK-R1
L2HE-INV-IROD2P-R1
L2HE-INV-CERNOX-R1
L2HE-LERF-CM-DMAG-R1
L2HE-LERF-CM-ACTS-R1
Please Submit any changes or questions to pansophy@jlab.org
Note:
Project Masterlist can be found in the project docushare folder
Traveler Acronym list can be found in Pansophy, under the User Tools > Traveler Tools drop downs

## Slide 2
Out for Approval |  |  |  |  |  |  |  | 
Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author | Reviewer | Reviewer | Proj Manager
Receiving Inspection CM Rod Invar 2-Phase Long | L2HE-INV-IROD2L | R1 | 8/1/21 |  | O'Brien |  |  | Hogan
Receiving Inspection CM Assembly, JT Valve Tube Kit | L2HE-INSP-JTVTK | R1 | 8/1/21 |  | Kent | Fischer | McEwen | Hogan
Receiving Inspection CM Rod Invar 2-Phase | L2HE-INV-IROD2P | R1 | 8/1/21 |  | O'Brien |  |  | Hogan
Overdue |  |  |  |  |  |  |  | 
Laping | L2HE-CHEM-CAV-LAP | R1 | 7/15/21 |  | Wildeson | Mitchell | T. Ganey | Hogan
Cavity Evacuation & Leak Test | L2HE-CLNRM-CAV-LEAK | R1 | 9/1/21 | 10/1/21 | D. FOREHAND | C. DREYFUSS |  | K. WILSON
LCLS-II HE Cernox Inventory Traveler | L2HE-INV-CERNOX | R1 | 8/15/21 | 10/1/21 | M. Dickey | C. Barnes | L. King | John Hogan
Production Cryomodule Demagnetization | L2HE-LERF-CM-DMAG | R1 | 8/31/21 |  | Cheng | Fischer |  | Hogan
Cryomodule Acceptance Test LERF | L2HE-LERF-CM-ACTS | R1 | 9/1/21 |  | Drury |  |  | Hogan
Receiving Inspection CM Rod Invar 2-Phase | L2HE-INV-IROD2P | R1 | 8/1/21 |  | O'Brien |  |  | Hogan
Approaching Due Date |  |  |  |  |  |  |  | 
Quadrapole Magnet Inspection | L2HE-INSP-QUAD | R1 | 9/30/21 |  | Lakshmi | King | Morrone | Hogan
L2HE Traveler Listing