## Slide 1: C100R
Color Legend |  | Count | Percent
CP | Complete (CP) | 33 | 78.57%
NR | New Revision Out for Approval (NR) | 1 | 2.38%
OA | Out for Approval (OA) | 0 | 0.00%
30 | Due in 30 Days | 0 | 0.00%
15 | Due in 15 Days | 1 | 2.38%
OD | Overdue | 8 | 19.05%
 | Remaining | 0 | 0.00%
 | Total Traveler IDs | 42 | 
Out for Approval/New Revision
C100R-CAV-VTRF-R2
Approaching Overdue
C100R-CM-INST-R1
Overdue
C100R-CST-CLN-COMP-R1
C100R-CAV-GVWG-CLN-R1
C100R-CM-ASSY-BPIP-R1
C100R-CM-ASSY-R1
C100R-CM-ASSY-COLD-R1
C100R-CM-ASSY-SFR-R1
C100R-CM-ASSY-VV-R1
C100R-CM-ASSY-BPIP-R1
Please Submit any changes or questions to pansophy@jlab.org
Note:
Project Masterlist can be found in the project docushare folder
Traveler Acronym list can be found in Pansophy, under the User Tools > Traveler Tools drop downs

## Slide 2
Out for Approval |  |  |  |  |  |  |  | 
Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author | Reviewer | Reviewer | Proj Manager
C100R Cavity VTA Test | C100R-CAV-VTRF | R2 | 11/6/18 |  | Stirbet | C.Willson |  | Davis
Overdue |  |  |  |  |  |  |  | 
C100R Cavity Component Cleaning | C100R-CST-CLN-COMP | R1 | 7/1/21 |  | R. Fielder | Mitchell |  | Davis
Secondary waveguide cleaning | C100R-CAV-GVWG-CLN | R1 | 9/1/21 |  |  |  |  | 
C100R Cryomodule Beampipe Assembly | C100R-CM-ASSY-BPIP | R1 | 9/1/21 |  | Fischer |  |  | 
C100R Cryomodule Final Assembly | C100R-CM-ASSY | R2 | 9/1/21 |  | Fischer | Worland | Hamlette | Reilly
C100R Cold Mass Assembly | C100R-CM-ASSY-COLD | R2 | 9/1/21 |  | Fischer | Worland | Hamlette | Reilly
C100R Thermal Shield and Space Frame Assembly | C100R-CM-ASSY-SFR | R2 | 9/1/21 |  | Fischer | Worland | Hamlette | Reilly
C100R Vacuum Vessel and End Can Assembly | C100R-CM-ASSY-VV | R2 | 9/1/21 |  | Fischer | Worland | Hamlette | Reilly
C100R Cryomodule Beampipe Assembly | C100R-CM-ASSY-BPIP | R2 | 9/1/21 |  | Fischer | Worland | Hamlette | Reilly
Approaching Due Date |  |  |  |  |  |  |  | 
C100R Cryomodule Tunnel Installation | C100R-CM-INST |  | 10/1/21 |  |  |  |  | 
C100R Traveler Listing