## TRAVELERS
| Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author | Reviewer | Reviewer | Project Manager | Tech Rep (SOTR) | NCR Informative | NCR Dispositioners | D3 Emails | Procedure(s), Name (if known) | Drawing(s), Name (if known) | Acronym from INV | Notes | Status | Section
Cavity Preparation
| Processing | [17 empty] | SS
CP | Cavity RF Inspection | L2HE-TUNE-CAV-RFIN | R2 | 2021-05-01 |  |  |  |  | Hogan | [6 empty] | CAV | This traveler is used to measure the cavity passband frequencies once it has arrived from the vendor. The RFIN measurements are compared to the pre-shipment vendor measurement, accounting for enviromental condition differences. If the RFIN measurments are in agreement with the vendor data, then it is assumed that the cavity was not damaged during shipment and can proceed toward VTRF. Discussions were had on whether a general spec for passband frequencies could be used instead of the vendor measurement; however, it was determined that comparision to the vendor measurements would continue to be used. No additional changes to the RFIN traveler or its calculation spreadsheet are required for the L2HE project. | CP
30 | Cavity HOM Measurements and Tuning | L2HE-TUNE-HOM | R1 | 2021-11-01 |  | D. FOREHAND | R. OVERTON |  | K. WILSON
| Chemistry | [17 empty] | SS
CP | L2HE Cavity Horizontal Electropolish | L2HE-CHEM-CAV-HEP | R1 | 2021-08-01 | 2021-08-01 | A. Mitchell | T. Ganey | T. Ganey | Hogan |  | ashleya,kwilson | hogan,vennekate,ganey | ashleya,vennekate,ganey,hogan,kdavis,forehand,kwilson |  |  |  | HEP is not anticipated for the L2HE production run; however, is available if needed for any refurbishment cavities or other situations as may be required to support the project. No changes to reference documents is required. | CP
CP | Cavity High Pressure Rinse | L2HE-CHEM-CAV-HPR | R2 |  |  | A. Wildeson | A. Mitchell | T. Ganey | Hogan |  | ashleya,kwilson | hogan,vennekate,ganey | ashleya,vennekate,ganey,hogan,kdavis,forehand,kwilson |  |  | CAV | Cavities that require reprocessing after a VTRF will receive a HPR - as was done in the L2PRD project. For L2PRD, this HPR was not captured in a traveler. For L2HE, chemistry travelers were created to capture the re-work steps for cavity vertical testing. The chemistry travelers follow standard chemistry processes and were only modified from other project travelers to reflect any 9-cell / L2HE specifics. HPR traveler does not have any references to update. | CP
OD | Laping | L2HE-CHEM-CAV-LAP | R1 | 2021-07-15 |  | Wildeson | Mitchell | T. Ganey | Hogan |  | ashleya,kwilson | hogan,vennekate,ganey | ashleya,vennekate,ganey,hogan,kdavis,forehand,kwilson |  |  |  | Cavities that require reprocessing after a VTRF will receive a HPR - as was done in the L2PRD project. For L2PRD, this HPR was not captured in a traveler. For L2HE, chemistry travelers were created to capture the re-work steps for cavity vertical testing. The chemistry travelers follow standard chemistry processes and were only modified from other project travelers to reflect any 9-cell / L2HE specifics.
CP | L2HE Cavity Ultrasonic Cleaning | L2HE-CHEM-CAV-USC | R2 |  |  | A. Wildeson | A. Mitchell | T. Ganey | Hogan |  | ashleya,kwilson | hogan,vennekate,ganey | ashleya,vennekate,ganey,hogan,kdavis,forehand,kwilson |  |  |  | Cavities that require reprocessing after a VTRF with high radiation and/or very low FE onset may receive an USC prior to HPR - as was done in the L2PRD project. For L2PRD, this USC was not captured in a traveler. For L2HE, chemistry travelers were created to capture the re-work steps for cavity vertical testing. The chemistry travelers follow standard chemistry processes and were only modified from other project travelers to reflect any 9-cell / L2HE specifics. Cavities recieved from vendor will only require external clean / wipedown prior to VTRF. Therefore the traveler was revised to include directions for if the cavity is under vacuum and a YES/NO data field. | CP
OD | L2HE Cavity Degreasing | L2HE-PR-CHEM-CAV-DEGR | R1 | 2021-09-15 | 2021-10-01 | [11 empty] | Used with the USC traveler. To include cavities under vacuum (from vendor or pre-string assy), and vented cavities requiring either USC (FE onset <10MV/m) or external clean with bolt holes (FE onset >10MV/m)
| Assembly | [17 empty] | SS
CP | Cavity 1st Assembly | L2HE-CLNRM-CAV-ASSY1 | R1 | 2021-06-01 |  | D. FOREHAND | C. DREYFUSS |  | K. WILSON | [7 empty] | This traveler will be used with refurbishment and re-processed / cleaned cavities. It is not to be used with cavities arriving directly from the vendor. Due to the different length field probe tips that were in circulation during the refurbishment work, a statement to replace the field probe with the proper length if required was added to the traveler. A Yes/No data field was also added to capture if the FP was changed. Due to the use of purge-only string assembly and the removal of HPR prior to string assemlby, it was identified that the right angle valve must be positioned correctly (in accordance with the cavity drawing package) in order to fit up with the purge system during string assembly. Instructions will be added to this traveler to ensure that the valve is installed in accordance with the drawing. | CP
CP | Cavity 2nd Assembly | L2HE-CLNRM-CAV-ASSY2 | R1 | 2021-06-01 |  | D. FOREHAND | C. DREYFUSS |  | K. WILSON | [7 empty] | This traveler will be used with refurbishment and re-processed / cleaned cavities. It is not to be used with cavities arriving directly from the vendor. No changes from L2PRD traveler | CP
OD | Cavity Evacuation & Leak Test | L2HE-CLNRM-CAV-LEAK | R1 | 2021-09-01 | 2021-10-01 | D. FOREHAND | C. DREYFUSS |  | K. WILSON | [7 empty] | Since cavity tests will frequently occur on the dewar 5 test stand and occassionally cavities are prepared for a test stand before the test stand is available, a separate traveler will be used to capture the pump down (if applicable) and leak check. Cavities from the vendor will not require the pump down as these cavities will arrive under vacuum. Cavities that were reprocessed for an additional VTRF will need to be pumped down. All cavities will recieve a leak check. This traveler aims to simplify capturing of the evacuation and leak check data by consolidating all use cases into a single traveler.
CP | Transfer of L2PRD 9-cell cavities to Test Stands | L2HE-CLNRM-CAV-TSTD | R2 | 2021-06-01 |  | D. FOREHAND | C. DREYFUSS |  | K. WILSON | [7 empty] | Several changes from the L2PRD traveler were identified and suggested. The traveler was updated to allow single cells to be captured in addition to 9-cells. The RGA scan range was updated to the current standard range used at JLab. The decision to seperate out the evacuation and leak check data into a standalone travler will require that this traveler be revised. Also the acceptable leak rate will be updated to reflect the leak rate spec provided in the cavity assembly drawings. | CP
CP | Transfer of L2PRD 9-cell cavities to Test Stands for Dewar 5 | L2HE-CLNRM-CAV-TSTD5 | R1 | 2021-06-01 |  | D. FOREHAND | C. DREYFUSS |  | K. WILSON | [7 empty] | Several changes from the L2PRD traveler were identified and suggested. The traveler was updated to allow single cells to be captured in addition to 9-cells. The decision to seperate out the evacuation and leak check data into a standalone travler will require that this traveler be revised. Also the acceptable leak rate will be updated to reflect the leak rate spec provided in the cavity assembly drawings. | CP
| Cavity 1st Assembly Procedure | L2HE-PR-CLNRM-CAV-ASSY1 | R1 | [13 empty] | CLNRM-CAV-ASSY1 traveler references this document but I have been unable to locate it to move it into the L2HE folder
| Cavity 2nd Assembly Procedure | L2HE-PR-CLNRM-CAV-ASSY2 | R1 | [13 empty] | CLNRM-CAV-ASSY2 traveler references this document but I have been unable to locate it to move it into the L2HE folder
| Cavity String Assembly Tooling Preparation | L2HE-PR-CLNRM-CST-PREP | R1 | 2021-12-01 | 2022-02-01 | [11 empty] | Needs to be revised for purge system and new rail tooling
| Testing | [17 empty] | SS
CP | Production Cavity Vertical Testing Procedure | L2HE-PR-VTA-CAV-VTRF | R1 | 2021-05-21 |  | C. WILSON | K. DAVIS |  | K. WILSON | [7 empty] | Procedure was updated to L2HE cavity vertical test specs and general VTA / RF testing instructions were updated to reflect current standard testing practices. | CP
CP | Cavity Cooldown | L2HE-VTA-CAV-COOL | R1 | 2021-05-01 |  | JT. KENT | J. VENNEKATE |  | K. WILSON |  | hogan,kwilson | hogan,kwilson | hogan,kwilson,kdavis,jtkent |  |  |  | No changes from L2PRD traveler | CP
NR | Cavity VTA Test | L2HE-VTA-CAV-VTRF | R2 | 2021-05-01 |  | JT. KENT | J. VENNEKATE |  | K. WILSON | [7 empty] | Traveler was updated to L2HE cavity vertical test specs and general VTA / RF testing instructions were updated to reflect current standard testing practices. Additional revision will be made to ensure traveler is in alignment with procedure and updated VTRF common format | NR
| Component Preparation | [17 empty] | SH
| Inspection / INVentory | [17 empty] | SS
NR | FPC COLD PART | L2HE-CLNRM-FPCC-INSP | R3 | 2021-05-24 | 2020-05-15 | N. HUQUE | [8 empty] | 341082, P96406 | FPCC |  | NR
| FPC COLD PART PROCEDURE | L2HE-PR-INSP-FPCC | R3 |  |  | N. HUQUE
CP | FPC WARM PART | L2HE-CMA-FPCW-INSP | R1 | 2021-05-24 | 2020-05-15 | N. HUQUE |  |  | Hogan | [5 empty] | 341081, P96394 | FPCW |  | CP
CP | Upper Cold Mass CMA Inspection | L2HE-CMA-UCM-INSP | R1 | 2021-05-28 |  | Gary | Fischer | N/A | Hogan | Gary | Katherine, Hogan | Gary, Fischer | Gary, Fischer |  | F10009954 |  |  | CP
CP | Receiving CMA Inspection CM Vacuum Vessel | L2HE-CMA-VV-INSP | R1 | 2021-05-28 |  | Gary | Fischer | N/A | Hogan | Gary | Katherine, Hogan | Gary, Fischer | Gary, Fischer |  | F10026609 |  |  | CP
CP | Cavity Beam Line Bellows PRCM | L2HE-INSP-BLBP | R1 | 2021-07-26 | 2021-08-01 | Marchlik | DeKerlegand | Zhao | Hogan | Reece | Hannesv, Reece | Lzhao, Wilson | Lzhao, Wilson |  |  |  |  | CP
CP | Cavity Beam Line Bellows Short | L2HE-INSP-BLBS | R1 | 2021-07-26 | 2021-08-01 | Marchlik | DeKerlegand | Zhao | Hogan | Marchlik | [7 empty] | CP
CP | Cavity String Weldment Upstream Bellows | L2HE-INSP-BLBU | R1 | 2021-07-01 | 2021-05-10 | Marchlik | DeKerlegand | Zhao | Hogan | Marchlik | [7 empty] | CP
CP | String Beam Line Extension Downstream | L2HE-INSP-BLXD | R1 | 2021-07-01 |  | Marchlik | DeKerlegand | Zhao | Hogan | Marchlik | [7 empty] | CP
CP | Cavity Inspection | L2HE-INSP-CAV | R3 | 2021-08-01 |  | K. WILSON |  |  | Hogan | [6 empty] | CAV | Revision to add instructions to visually verify the right angle valve position. Since the cavity may not be disassembled prior to string assembly and the valve position is critical for fit up with the purge system, the valve position needs to be verified during the initial inspection (and flagged with an NCR if valve position is not correct). | CP
CP | Cryomodule Cool Down Cryogenic Valve (CDV) | L2HE-INSP-CDV | R1 | 2021-05-17 |  | Kent | Fischer | McEwen | Hogan | Kent | Katherine, Hogan | Kent, Wilson | Kent, Fischer |  |  |  |  | CP
CP | 300K Current Leads CF Flange Inspection | L2HE-INSP-CFL | R1 | 2021-04-01 |  | Lakshmi | King | Morrone | Hogan | Lakshmi | hogan,kwilson | lalitha,king | lalitha,king,fisher,morrone |  |  |  |  | CP
CP | LCLS-II HE 2K Clamp Assembly Kit Inspection | L2HE-INSP-CLMP02K | R1 |  |  | Seetha-Lakshmi Lalitha | Larry King | John Fischer | John Hogan | Seetha-Lakshmi Lalitha | Kwilson,hogan | lalitha,king | lalitha,king,fischer |  |  |  |  | CP
CP | LCLS-II HE 5K Clamp Assembly Kit Inspection Traveler | L2HE-INSP-CLMP05K | R1 |  |  | Seetha-Lakshmi Lalitha | Larry King | John Fischer | John Hogan | Seetha-Lakshmi Lalitha | Kwilson,hogan | lalitha,king | lalitha,king,fischer |  |  |  |  | CP
CP | LCLS-II HE 50 K Clamp Assembly Kit Inspection Traveler | L2HE-INSP-CLMP50K | R1 |  |  | Seetha-Lakshmi Lalitha | Larry King | John Fischer | John Hogan | Seetha-Lakshmi Lalitha | Kwilson,hogan | lalitha,king | lalitha,king,fischer |  |  |  |  | CP
CP | LCLS-II HE Split-Quad Clamp Kit Inspection Traveler | L2HE-INSP-CLMPSQ | R1 |  |  | Seetha-Lakshmi Lalitha | Larry King | John Fischer | John Hogan | Seetha-Lakshmi Lalitha | Kwilson,hogan | lalitha,king | lalitha,king,fischer |  |  |  |  | CP
CP | FPC Waveguide Incoming Inspection | L2HE-INSP-FPCWG | R1 | 2021-10-15 | 2021-01-27 | Huque | Stirbet |  | Hogan | Huque | [5 empty] | FPCWG |  | CP
CP | Cavity Field Probe Feedthru Receiving Inspection | L2HE-INSP-FPFT | R1 | 2020-10-16 |  | Liang | DeKerlegand | N/A | Wilson | Liang | hannesv, Reece | lzhao, Wilson | lzhao, Wilson | No | GMM-9434A |  |  | CP
CP | Cavity HOM Feedthru Receiving Inspection | L2HE-INSP-HMFT | R1 | 2020-10-16 |  | Liang | DeKerlegand | N/A | Wilson | Liang | hannesv, Reece | lzhao, Wilson | lzhao, Wilson | No | GMM-9433A |  |  | CP
CP | Receiving Inspection CM Magnetic Shield Assembly | L2HE-INSP-IMAG | R1 | 2021-05-14 |  | Gary | DeKerlegand | Fischer | Hogan | Gary | Katherine, Hogan | Gary, Fischer | Gary, Fischer |  | F10048652 |  |  | CP
CP | Receiving Inspection CM Assembly, JT Cryogenic Valve | L2HE-INSP-JTV | R1 | 2021-05-17 |  | Kent | Fischer | McEwen | Hogan | Kent | Katherine, Hogan | Kent, Wilson | Kent, Fischer |  |  |  |  | CP
CP | Tuner Piezo Actuator Assembly Inspection | L2HE-INSP-PIEZO | R1 | 2021-03-05 | 2021-05-31 | King | Powen | Huque | Hogan | Powen | huque,kwilson | Powen, King | Powen, Huque, Wilson |  |  |  | Will be a batch traveler | CP
OD | Quadrapole Magnet Inspection | L2HE-INSP-QUAD | R1 | 2021-09-30 |  | Lakshmi | King | Morrone | Hogan | Lakshmi |  | Lakshmi, Wilson | Lakshmi, Wilson
CP | End Lever Tuner Motor | L2HE-INSP-SM | R1 | 2021-04-01 | 2021-04-30 | King | Powen | Huque | Hogan | Powen | huque,kwilson | Powen, King | Powen, Huque, Wilson |  |  |  | Will be a batch traveler | CP
CP | End Lever Tuner Mechanical Frame Inspection | L2HE-INSP-TUNC | R1 | 2021-07-14 | 2021-08-15 | Powen | DeKerlegand | Huque | Hogan | Powen | kwilson | Powen, Huque, georged | Powen, Huque, Wilson |  | F10132292-B, F10138922-A |  |  | CP
CP | End Lever Tuner Extended Mechanical Frame Inspection Traveler | L2HE-INSP-TUNCX | R1 | 2021-07-14 | 2021-08-15 | P Owen | DeKerlegand | Huque | Wilson / Hogan | [8 empty] | CP
CP | All Metal Gate Valve Inventory | L2HE-INV-AMGV | R1 | 2021-05-01 |  | Dickey | Barnes |  | Hogan | Savransky | Mdicky,Hogan | Kwilson,Dsavr | [5 empty] | CP
CP | Cavity Beam Line Bellows PRCM Inventory | L2HE-INV-BLBP | R1 | 2021-07-26 | 2021-08-01 | [12 empty] | CP
CP | Cavity Beam Line Bellows Short Inventory | L2HE-INV-BLBS | R1 | 2021-07-26 | 2021-08-01 | [12 empty] | CP
CP | Cavity String Weldment Upstream Bellows Inventory | L2HE-INV-BLBU | R1 | 2021-05-01 | 2021-05-10 | [12 empty] | CP
CP | String Beam Line Extension Downstream Inventory | L2HE-INV-BLXD | R1 | 2021-07-01 | [13 empty] | CP
CP |  | L2HE-INV-BP2PH | R1 | [14 empty] | CP
CP | Cavity Inventory | L2HE-INV-CAV | R1 | 2021-08-01 | 2020-05-15 | J. VENNEKATE | [11 empty] | CP
OD | LCLS-II HE Cernox Inventory Traveler | L2HE-INV-CERNOX | R1 | 2021-08-15 | 2021-10-01 | M. Dickey | C. Barnes | L. King | John Hogan | L. King | [6 empty] | After discussion with the Instrumentation group, it was determined that there was not need to create travelers specific to instrumention assembly/installation since any required data was captured in the cryomodule assembly travelers. The cryomodule assembly travelers reference the appropriate instrumentation procedures. The only instrumentation component that has a serial number is the cernox sensors. These sensors should be tracked through inventory. This cernox inventory traveler will be new for L2HE.
CP | FPC COLD PART Inventory | L2HE-INV-FPCC | R1 | 2021-05-24 | 2020-05-15 | N. HUQUE | M. Dickey | C. Barnes | J. Hogan | N. Huque | Dickey,Hogan,kwilson | Huque | Huque,Hogan,kwilson |  |  |  |  | CP
CP | FPC Waveguide Inventory | L2HE-INV-FPCWG | R1 | 2021-05-01 | 2021-01-27 | Dickey | Barnes |  | Wilson |  | Wislon | Huque,Fischer | Huque,Fisher |  |  |  |  | CP
CP | Cavity Field Probe Feedthru Receiving Inventory | L2HE-INV-FPFT | R1 | 2021-05-19 |  | M. Dickey | C. Barnes |  | J. Hogan | L.Zhao | hannesv, Reece | lzhao, Wilson | lzhao, Wilson |  |  |  |  | CP
CP | Cavity HOM Feedthru Receiving Inventory | L2HE-INV-HMFT | R1 | 2021-05-19 |  | M. Dickey | C. Barnes |  | J. Hogan | L.Zhao | hannesv,reece | lzhao, Wilson | lzhao, Wilson |  |  |  |  | CP
CP | CM Magnetic Shield Assembly Inventory | L2HE-INV-IMAG | R1 | 2021-05-14 |  | M. Dickey | C. Barnes |  | J. Hogan | G. Cheng | Katherine, Hogan | Gary, Fischer | Gary, Fischer |  |  |  |  | CP
OA | Receiving Inspection CM Rod Invar 2-Phase Long | L2HE-INV-IROD2L | R1 | 2021-08-01 |  | O'Brien |  |  | Hogan | [7 empty] | Waiting on FERMI for response | OA
OD | Receiving Inspection CM Rod Invar 2-Phase | L2HE-INV-IROD2P | R1 | 2021-08-01 |  | O'Brien |  |  | Hogan | [7 empty] | Waiting on FERMI for response
CP | CM Assembly, JT Valve Tube Kit Inventory | L2HE-INV-JTVTK | R1 | 2021-08-01 | [13 empty] | CP
CP |  | L2HE-INV-JTVTK | R1 | [14 empty] | CP
CP |  | L2HE-INV-LLDS | R1 | [14 empty] | CP
CP |  | L2HE-INV-LLNDS | R1 | [14 empty] | CP
CP |  | L2HE-INV-LLNUS | R1 | [14 empty] | CP
CP |  | L2HE-INV-LLUS | R1 | [14 empty] | CP
CP | Tuner Piezo Actuator Inventory | L2HE-INV-PIEZO | R1 | 2021-05-01 | 2021-05-31 | M. Dickey | C. Barnes |  | John Hogan | Peter Owen | mdickey,Hogan,areilly | powen | Hogan,powen,areilly |  |  |  |  | CP
CP | Quadrapole Magnet Inventory | L2HE-INV-QUAD | R1 | 2021-06-15 |  | Dickey | Barnes | Morrone | Hogan | Lakshmi |  | Lakshmi, Wilson | Lakshmi, Wilson |  |  |  |  | CP
CP | End Lever Tuner Mechanical Frame Inventory | L2HE-INV-TUNC | R1 | 2021-05-14 |  | M. Dickey | C. Barnes | J. Hogan | P. Owen |  | kwilson,hogan | cheng,fischer,powen | cheng,fischer |  |  |  |  | CP
CP | L2HE Extended Cold Tuner Inventory Traveler | L2HE-INV-TUNCX | R1 | 2021-05-14 |  | M. Dickey | C. Barnes |  | J. Hogan | P. Owen | kwilson,hogan | cheng,fischer,powen | cheng,fischer |  |  |  |  | CP
CP | Upper Cold Mass CMA Inventory | L2HE-INV-UCM | R1 | 2021-05-18 | [13 empty] | CP
CP | CM Vacuum Vessel Inventory | L2HE-INV-VV | R1 | 2021-05-18 | [13 empty] | CP
CP | FPC WARM PART PROCEDURE | L2HE-PR-CMA-FPCW-INSP | R1 | [14 empty] | CP
NR | Inspection Procedure for LCLS-II-HE Cold Fundamental Power Coupler | L2HE-PR-INSP-FPCC | R3 | 2021-05-24 | 2020-05-15 | [12 empty] | NR
| Chemistry | [17 empty] | SS
CP | Components Cleaning | L2HE-CHEM-COMP-DEGR | R1 | 2021-07-01 |  | Mitchell | Wildeson |  | Hogan |  | ashleya | hogan,ari | ashleya,ari,hogan,kdavis,forehand |  |  |  | Chemistry work was not captured in travelers for L2PRD. Cavity components that require cleaning will be captured in this traveler. The traveler will be based on current component cleaning travelers and standard practices. | CP
| Weld Inspection | [17 empty] | SS
CP | Upper Cold Mass Weld Inspection? | L2HE-CWI-UCM | R1 | 2021-05-28 |  | Gary | JENORD | Fischer | Hogan | Gary | Katherine, Hogan | Gary, Fischer | Gary, Fischer |  | F10009954 |  |  | CP
CP | Vacuum Vessel Receiving Weld Inspection | L2HE-CWI-VV | R1 |  |  | Gary | JENORD | Fischer | hogan |  | Kwilson, hogan | Cheng, fischer | Cheng, fischer |  |  |  |  | CP
| Leak Checks | [17 empty] | SS
CP | Cavity Beam Line Bellows PRCM Leak Test | L2HE-CMA-BLBP-LEAK | R1 | 2021-08-15 | 2021-08-01 | Marchlik | WIlcox | N/A | Wilson | Marchlik | Ari, Reece | Marchlik, Wilson | Marchlik, Wilson | Leak check spec 11141-S-0029 | F10041075 |  |  | CP
CP | Cavity Beam Line Bellows Short | L2HE-CMA-BLBS-LEAK | R1 | 2021-08-15 | 2021-08-01 | Marchlik | WIlcox | N/A | Wilson | Marchlik | Ari, Reece | Marchlik, Wilson | Marchlik, Wilson | Leak check spec 11141-S-0029 | F10023437 |  |  | CP
CP | Cavity String Weldment Upstream Bellows | L2HE-CMA-BLBU-LEAK | R1 | 2021-08-15 | 2021-05-10 | Marchlik | WIlcox | N/A | Wilson | Marchlik | Ari, Reece | Marchlik, Wilson | Marchlik, Wilson | Leak check spec 11141-S-0029 | F10075494 |  |  | CP
CP | String Beam Line Extension Downstream | L2HE-CMA-BLXD-LEAK | R1 | 2021-08-15 | 2021-08-01 | Marchlik | WIlcox | N/A | Wilson | Marchlik | Ari, Reece | Marchlik, Wilson | Marchlik, Wilson | Leak check spec 11141-S-0029 | F10052775 |  |  | CP
CP | Cavity Field Probe Feedthru Receiving Inspection | L2HE-CMA-FPFT-LEAK | R1 | 2020-10-21 |  | Park | Wilcox | N/A | Wilson | LIANG | Ari, Reece | Park, Wilson | Park, Wilson | Leak check spec 11141-S-0029 | GMM-9434A |  |  | CP
CP | Cavity HOM Feedthru Receiving Inspection | L2HE-CMA-HMFT-LEAK | R1 | 2020-10-21 |  | Park | Wilcox | N/A | Wilson | LIANG | Ari, Reece | Park, Wilson | Park, Wilson | Leak check spec 11141-S-0029 | GMM-9433A |  |  | CP
| Cavity HOM Measurements and Tuning | L2HE-CMA-HOM-TUNE | R1 | 2021-12-01 | 2022-02-01 | [11 empty] | This traveler is for use after string assembly. Traveler and procedure need to be updated to reflect new software that has been developed.
| Cavity HOM Measurements and Tuning Procedure | L2HE-PR-CMA-HOM-TUNE | R1 | 2021-12-01 | 2022-02-01 | [11 empty] | Procedure to go with L2HE-TUNE-HOM. Needs to be revised to reflect new software.
| Cold Shock | [17 empty] | SS
CP | Cavity Field Probe Feedthru Receiving Inspection | L2HE-VTA-FPFT-CSHK | R1 | 2020-10-22 |  | Park | Forehand | Kent | Wilson | Park | Ari, Reece | Park, Wilson | Park, Wilson | No | GMM-9434A |  |  | CP
CP | Cavity HOM Feedthru Receiving Inspection | L2HE-VTA-HMFT-CSHK | R1 | 2020-10-23 |  | Park | Forehand | Kent | Wilson | Park | Ari, Reece | Park, Wilson | Park, Wilson | No | GMM-9433A |  |  | CP
| Cavity String | [17 empty] | SH
| Assembly | [17 empty] | SS
| Cavity String Gate Valve Leak Test | L2HE-CLNRM-AMGV-LEAK | R1 | 2021-12-01 | 2022-02-01 | Forehand |  |  | Hogan
| BPM Magnet sub-assembly | L2HE-CLNRM-BPM-ASSY | R1 | 2021-12-01 | 2022-02-01 | Forehand |  |  | Hogan
| Cavity String Assembly (MAJOR CHANGE) | L2HE-CLNRM-CST-ASSY | R1 | 2021-12-01 |  | Forehand |  |  | Hogan | [7 empty] | Will require a major revision to include use of purge system without HPR
| String Pump down, leak test and transfer to phase 1 | L2HE-CLNRM-CST-LEAK | R1 | 2021-12-01 |  | Forehand |  |  | Hogan | [7 empty] | changes are required to support the purge system string assembly and use of Faraday Window Manifold (or alternate upstream manifold) and downstream NEG manifold
| Cavity String Gate Valve Leak Test Procedure | L2HE-PR-CLNRM-AMGV-LEAK | R1 | 2021-12-01 | 2022-02-01
| Cavity String Assembly Procedure | L2HE-PR-CLNRM-CST-ASSY | R1 | 2021-12-01 | 2022-02-01 | [11 empty] | Complete re-write of JLab L2PRD string assembly process to use purge system, without HPR, including new upstream and downstream manifolds
| Ionized Nitrogen Parts Cleaning | L2HE-PR-CLNRM-CST-IONCLN | R1 | 2021-12-01 | 2022-02-01 | [11 empty] | No significant changes from L2PRD procedure anticipated
| Upstream Gate Valve Sub-Assembly | L2HE-PR-CLNRM-GV1SA-ASSY | R1 | 2021-12-01 | 2022-02-01 | [11 empty] | Changes are required to support the purge system string assembly and use of Faraday Window Manifold (or alternate upstream manifold)
| Downstream Gate Valve Sub-Assembly | L2HE-PR-CLNRM-GV2SA-ASSY | R1 | 2021-12-01 | 2022-02-01 | [11 empty] | Changes are required to support the purge system string assembly and use of Faraday Window Manifold (or alternate upstream manifold)
| NEG Pump Manifold Assembly | L2HE-PR-CLNRM-NEG-ASSY | R1 | 2021-12-01 | 2022-02-01
| Chemistry | [17 empty] | SS
CP | Copper Plated String Components Cleaning Procedure | L2HE-PR-CHEM-CST-DEGR | R1 |  |  | Ganey | Mitchell | Fiedler | Hogan | [7 empty] | Process developed for L2PRD will be used. Combines bellow specific instructions with instructions for all copper plated string components. | CP
| Cryomodule | [17 empty] | SH
| Cryomodule Assembly | [17 empty] | SS
| CM Assembly First | L2HE-CMA-CM-ASSY1 | R1 | 2022-02-01 |  | Fischer | Worland |  | Hogan
| CM Assembly Second | L2HE-CMA-CM-ASSY2 | R1 | 2022-02-01 |  | Fischer | Worland |  | Hogan | [7 empty] | This traveler will be used with refurbishment and re-processed / cleaned cavities. It is not to be used with cavities arriving directly from the vendor. No changes from L2PRD traveler
| CM Assembly Final | L2HE-CMA-CM-ASSYF | R1 | 2022-02-01 |  | Fischer | Worland |  | Hogan
| Cryomodule Rework Traveler | L2HE-CMA-CM-REW | R1 | 2022-02-01 |  | Fischer |  |  | Hogan
| Cryomodule Retrofit Traveler | L2HE-CMA-CM-RFIT | R1 | 2022-02-01 |  | Fischer |  |  | Hogan
| Cryomodule Prep and Shipping to SLAC | L2HE-CMA-CM-SHIP | R1 | 2022-02-01 |  | Martin | Fischer |  | Hogan
| FPC Warm Installation | L2HE-CMA-FPCW-ASSY | R1 | 2022-02-01 | 2022-02-01 | Huque |  |  | Hogan
| Cryomodule Vacuum Vessel Assembly | L2HE-CMA-VV-ASSY | R1 | 2022-02-01 |  | Fischer | Worland |  | Hogan
CP | FPC WARM PART Inventory | L2HE-INV-FPCW | R1 | 2021-05-24 | 2020-05-15 |  |  |  |  | N. HUQUE | [7 empty] | CP
| Processing | [17 empty] | SS
CP | Upper Cold Mass Magnetic Hygiene Control | L2HE-CMA-UCM-DMAG | R1 | 2021-05-28 |  | Cheng | Fischer |  | Hogan | Cheng | Wilson, Hogan | Fischer, Cheng | Fischer, Cheng |  |  |  |  | CP
OD | Production Cryomodule Demagnetization | L2HE-LERF-CM-DMAG | R1 | 2021-08-31 |  | Cheng | Fischer |  | Hogan | Cheng | Wilson, Hogan | Fischer, Cheng | Fischer, Cheng
| Cryomodule Testing | [17 empty] | SS
OD | Cryomodule Acceptance Test LERF | L2HE-LERF-CM-ACTS | R1 | 2021-09-01 |  | Drury |  |  | Hogan
| Standard Project Travelers | [17 empty] | SH
CP | D3 Report | L2HE-D3 | R2 | [14 empty] | CP
CP | Cavity Non-conformance Report | L2HE-NCR | R11 | [14 empty] | CP
CP | Inspection Summary Report | L2HE-INSR | R1 | [14 empty] | CP
Color Legend |  | Count | Percent
CP | Complete (CP) | 78 | 69.64%
NR | New Revision Out for Approval (NR) | 3 | 2.679%
OA | Out for Approval (OA) | 1 | 0.8929%
30 | Due in 30 Days | 1 | 0.8929%
15 | Due in 15 Days | 0 | 0%
OD | Overdue | 8 | 7.143%
| Remaining | 24 | 21.43%
| Total Traveler IDs | 112
Note on C24: Valerie Bookwalter: APPROVED - MOVE TO PRODUCTION
Note on G24: Homer Samuels: Validate Author Name. Ganey?
Note on C27: Valerie Bookwalter: APPROVED -> MOVE TO PRODUCTION
Note on C28: Valerie Bookwalter: APPROVED BY ALL EXCEPT CHRIS D. -> MOVE TO PRODUCTION
Note on C66: Homer Samuels: Hold Still? 10/4/21 APPROVED - MOVE TO PRODUCTION
Note on C96: Homer Samuels: pull the prd and freshen up
Note on C128: Homer Samuels: pull from L2PRD

## L2HE REFS
TRAV_ID | TRAV_REVISION | LAST MOD | >3 YRS OLD | Authors | DOC TYPE | LOC AREA | DOCUMENT_TITLE | DOCUMENT_URL
L2HE-CHEM-CAV-HEP | R1 | 2017-01-12 | TRUE | Ashley Anderson |  | STP | STP Cavity degrease procedure | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-132365/CP-STP-CAV-CHEM-USC-R1.pdf
L2HE-CHEM-CAV-HEP | R1 | 2021-02-11 | FALSE | ? | VENDOR DOC |  | SPEC HEP OperatingManual8148_2020.pdf | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-219641/HEP_OperatingManual8148_2020.pdf | 03 - SRF Organizational Information Groups Cryomodule Development & Production Cavity Production Cavity Processing - Production Chemistry Group HEP Tool Listing
L2HE-CHEM-CAV-HEP | R1 |  | TRUE | Ashley Anderson | DIRECTORY |  | HEP Nb Concentration Calculator ; History | https://jlabdoc.jlab.org/docushare/dsweb/View/Collection-29772
L2HE-CHEM-CAV-HPR | R2 | 2016-08-02 | TRUE | Ashley Anderson |  | STP | CP-STP-CAV-CHEM-HPR-R2 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-125424/CP-STP-CAV-CHEM-HPR-R2.pdf
L2HE-CHEM-CAV-USC | R1 | 2020-05-14 | FALSE | Alex Wildeson |  | C75 | CP-C75-CAV-CHEM-USC-R2 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-212978/CP-C75-CAV-CHEM-USC-R1.pdf
L2HE-CHEM-CAV-USC | R2 | 2020-05-14 | FALSE | Alex Wildeson |  | C75 | CP-C75-CAV-CHEM-USC-R2 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-212978/CP-C75-CAV-CHEM-USC-R1.pdf
L2HE-CHEM-COMP-DEGR | R1 | 2017-11-13 | TRUE | Gigi Ciovati |  | C75 | CP-C75-CAV-BCP-ER | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-150777/CP-C75-CAV-BCP-ER-R1.pdf
L2HE-CHEM-COMP-DEGR | R1 | 2016-09-12 | TRUE | Jim Follkie |  | L2PRD | CP-L2PRD-CAV-CHEM-CLN-COMP | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-127640/CP-L2PRD-CAV-CHEM-CLN-COMP-R1.pdf
L2HE-CLNRM-CAV-ASSY1 | R1 | 2010-05-13 | TRUE | Steve Castagnola |  | C100 | Leak testing with an RGA procedure | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-27678/CP-C100-CAV-LKTS.pdf
L2HE-CLNRM-CAV-ASSY1 | R1 | 2016-11-03 | TRUE | Danny Forehand |  | L2PRD | Ionized Nitrogen Cleaning Procedure | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-129170/CP-L2PRD-CST-IONCLN-R1.pdf
L2HE-CLNRM-CAV-ASSY2 | R1 | 2010-05-13 | TRUE | Steve Castagnola |  | C100 | Leak testing with an RGA procedure | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-27678/CP-C100-CAV-LKTS.pdf
L2HE-CLNRM-CAV-ASSY2 | R1 | 2016-11-03 | TRUE | Danny Forehand |  | L2PRD | Ionized Nitrogen Cleaning Procedure | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-129170/CP-L2PRD-CST-IONCLN-R1.pdf
L2HE-CLNRM-FPCC-INSP | R1 | 2007-05-15 | TRUE | ? | VENDOR DOC |  | Solair 3100 Gen E Manual | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242798/Solair%203100%20Gen%20E%20Manual.pdf
L2HE-CLNRM-FPCC-INSP | R1 | 2010-05-13 | TRUE | Steve Castagnola |  | C100 | CP-C100-CAV-LKTS | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-243276/CP-C100-CAV-LKTS.pdf | 01 - SRF Projects 01 - Open 1.21.01.XXX LCLS-II HE Project - High Energy (Preb... 06 - Process Documents^Travelers (L2HE) Travelers Included Files - (L2HE) FPCs Listing
L2HE-CLNRM-FPCC-INSP | R1 | 2017-02-27 | TRUE | Kurt Macha |  | L2PRD | CP-L2PRD-CLN-PUMP | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-243275/CP-L2PRD-CLN-PUMP.docx | 01 - SRF Projects 01 - Open 1.21.01.XXX LCLS-II HE Project - High Energy (Preb... 06 - Process Documents^Travelers (L2HE) Travelers Included Files - (L2HE) FPCs Listing
L2HE-CLNRM-FPCC-INSP | R1 | 2019-02-12 | FALSE | Jeff Tice | SLAC |  | LCLSII-HE-1.2-ES-0059 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242805/LCLSII-HE-1.2-ES-0059.pdf
L2HE-CLNRM-FPCC-INSP | R1 | 2010-09-22 | TRUE | ? | DESY |  | Vacuum-005-2008 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242799/Vacuum-005-2008%20Guidelines%20for%20UHV-Components%20at%20DESY.pdf
L2HE-CLNRM-FPCC-INSP | R1 | 2017-01-23 | TRUE | Ashley Anderson |  | STP | CP-STP-CAV-CHEM-DEGR-R3 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242804/CP-STP-CAV-CHEM-DEGR-R3.pdf
L2HE-CLNRM-FPCC-INSP | R1 | 2021-05-12 | FALSE | Naeem Huque |  |  | L2HE-PR-INSP-FPCC | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-243519/L2HE-PR-INSP-FPCC-R1.pdf
L2HE-CLNRM-FPCC-INSP | R1 | 2015-10-08 | TRUE | Danny Forehand |  | L2PRO | CP-L2PRO-CST-CHEM-CLN-ION | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-243277/CP-L2PRO-CST-CHEM-CLN-ION-R1.pdf
L2HE-CLNRM-FPCC-INSP | R1 | 2018-04-11 | TRUE | Robert Legg |  | L2PRD | CP-L2PRD-CM-SLBUP-R2 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242801/CP-L2PRD-CM-SLBUP-R2.pdf
L2HE-CLNRM-FPCC-INSP | R2 | 2017-02-27 | TRUE | Kurt Macha |  | L2PRD | CP-L2PRD-CLN-PUMP | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-243275/CP-L2PRD-CLN-PUMP.docx
L2HE-CLNRM-FPCC-INSP | R2 | 2019-12-12 | FALSE | Jeff Tice | SLAC |  | LCLSII-HE-1.2-ES-0059 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242805/LCLSII-HE-1.2-ES-0059.pdf
L2HE-CLNRM-FPCC-INSP | R2 | 2010-04-13 | TRUE | Steve Castagnola |  | C100 | CP-C100-CAV-LKTS | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-243276/CP-C100-CAV-LKTS.pdf
L2HE-CLNRM-FPCC-INSP | R2 | 2010-09-22 | TRUE | U. Hahn | DESY |  | Vacuum-005-2008 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242799/Vacuum-005-2008%20Guidelines%20for%20UHV-Components%20at%20DESY.pdf
L2HE-CLNRM-FPCC-INSP | R2 | 2007-05-15 | TRUE | ? | VENDOR DOC |  | Solair 3100 Gen E Manual | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242798/Solair%203100%20Gen%20E%20Manual.pdf
L2HE-CLNRM-FPCC-INSP | R2 | 2015-10-08 | TRUE | Danny Forehand |  | L2PRO | CP-L2PRO-CST-CHEM-CLN-ION | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-243277/CP-L2PRO-CST-CHEM-CLN-ION-R1.pdf
L2HE-CLNRM-FPCC-INSP | R2 | 2018-04-11 | TRUE | Robert Legg |  | L2PRD | CP-L2PRD-CM-SLBUP-R2 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242801/CP-L2PRD-CM-SLBUP-R2.pdf
L2HE-CLNRM-FPCC-INSP | R2 | 2017-01-23 | TRUE | Ashley Anderson |  | STP | CP-STP-CAV-CHEM-DEGR-R3 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242804/CP-STP-CAV-CHEM-DEGR-R3.pdf
L2HE-CMA-BLBP-LEAK | R1 | 2019-07-30 | FALSE | Kurt Macha |  |  | 11141S0029-B | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245701/11141S0029-B%202e-10%20Leak%20Check%20Final.pdf
L2HE-CMA-BLBP-LEAK | R1 | 2015-12-10 | TRUE | G. LANGLOIS | FNAL DRAWING |  | F10041075-H (WELDMENT BELLOWS-PrCM | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245700/F10041075_H_DWG1%20PrCM%20Bellows.pdf
L2HE-CMA-BLBS-LEAK | R1 | 2014-08-06 | TRUE | G. LANGLOIS | FNAL DRAWING |  | F10023437 (WELDMENT BELLOWS-Short | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245702/F10023437_H_DWG1%20Short%20Bellows.pdf
L2HE-CMA-BLBS-LEAK | R1 | 2019-07-30 | FALSE | Kurt Macha |  |  | 11141S0029-B | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245701/11141S0029-B%202e-10%20Leak%20Check%20Final.pdf
L2HE-CMA-BLBU-LEAK | R1 | 2019-07-30 | FALSE | Kurt Macha |  |  | 11141S0029-B | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-241599/11141-S-0029.pdf
L2HE-CMA-BLBU-LEAK | R1 | 2017-03-14 | TRUE | M. KRAMP | FNAL DRAWING |  | F10075494-C (WELDMENT BELLOWS-US END | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-241595/F10075494_C_DWG1___.pdf
L2HE-CMA-BLXD-LEAK | R1 | 2016-02-15 | TRUE | M. KRAMP | FNAL DRAWING |  | F10052775 (WELDMENT EXTENSION-DS | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245703/F10052775_H_DWG1%20Spool.pdf
L2HE-CMA-BLXD-LEAK | R1 | 2019-07-30 | FALSE | Kurt Macha |  |  | 11141S0029-B | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245701/11141S0029-B%202e-10%20Leak%20Check%20Final.pdf
L2HE-CMA-FPCW-INSP | R1 | 2019-12-12 | FALSE | Jeff Tice |  |  | LCLSII-HE-1.2-ES-0059 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242805/LCLSII-HE-1.2-ES-0059.pdf
L2HE-CMA-FPCW-INSP | R1 | 2021-06-10 | FALSE | Naeem Huque |  |  | L2HE-PR-CMA -FPCW-INSP | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-244733/L2HE-PR-CMA-FPCW-INSP-R1.pdf
L2HE-CMA-FPFT-LEAK | R1 | 2019-08-19 | FALSE | A. Yokoyama | FNAL DRAWING |  | Drawing GMM-9434A | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-225208/GMM-B9434A.pdf
L2HE-CMA-HMFT-LEAK | R1 | 2019-08-19 | FALSE | A. Yokoyama | FNAL DRAWING |  | Drawing GMM-9433A | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-225207/GMM-B9433A.pdf
L2HE-CMA-UCM-DMAG | R1 | 2015-05-06 | TRUE | G. LANGLOIS | FNAL DRAWING |  | LCLS-II HE Upper Cold Mass Drawings | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242872/LCLS-II%20HE%20Upper%20Cold%20Mass%20drawings.pdf
L2HE-CMA-UCM-DMAG | R1 | 2020-05-20 | FALSE | Cheng, Gary | OSP |  | Small parts Demagnetization OSP | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242285/operational_safety_procedure_form_102532.pdf | EXPIRES 6/11/2023
L2HE-CMA-UCM-INSP | R1 | 2019-12-11 | FALSE | Ken Premo | FNAL DRAWING |  | Upper Cold Mass Specification ED0003252 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242873/ED0003252-E-SPEC.pdf
L2HE-CMA-UCM-INSP | R1 | 2015-05-06 | TRUE | G. LANGLOIS | FNAL DRAWING |  | LCLS-II HE Upper Cold Mass Drawings | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242872/LCLS-II%20HE%20Upper%20Cold%20Mass%20drawings.pdf
L2HE-CMA-UCM-INSP | R1 |  | TRUE | ? | VENDOR DOC |  | reportlistUC002 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242874/report%20listUC-002.pdf
L2HE-CMA-UCM-INSP | R1 | 2021-03-15 | FALSE | liuwei | VENDOR DOC |  | reportlistUC-002-010 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242875/report%20listUC-002-010.pdf
L2HE-CMA-VV-INSP | R1 | 2015-01-02 | TRUE | G. LANGLOIS | MSEXCEL |  | LCLS-II HE Vacuum Vessel drawings | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242984/LCLS-II%20HE%20Vacuum%20Vessel%20Drawings.pdf
L2HE-CMA-VV-INSP | R1 | 2017-02-16 | TRUE | ? | MSEXCEL |  | Vacuum Vessel_QC | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-132917/VacuumVessel_QC_Task%20List.xlsx
L2HE-CMA-VV-INSP | R1 | 2019-12-10 | FALSE | K. Premo | FNAL DRAWING |  | LCLS-II HE Vacuum Vessel Specification ED0002342 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242985/ED0002342---LCLS-II_VacVessel_SPEC.pdf
L2HE-CMA-VV-INSP | R1 |  | TRUE | ? | VENDOR DOC |  | Vendors document list | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242986/report%20listVV-002..pdf
L2HE-CWI-UCM | R1 | 2015-05-06 | TRUE | G. LANGLOIS | FNAL DRAWING |  | LCLS-II HE Upper Cold Mass Drawings | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242872/LCLS-II%20HE%20Upper%20Cold%20Mass%20drawings.pdf
L2HE-CWI-UCM | R1 | 2019-12-11 | FALSE | Ken Premo | FNAL DRAWING |  | Upper Cold Mass Specification ED0003252 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242873/ED0003252-E-SPEC.pdf
L2HE-CWI-UCM | R1 | 2014-07-15 | TRUE | M.SAWTELL | FNAL DRAWING |  | Drawings for accessible welds | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242958/UCM%20Weld%20Insp%20Drawings.pdf
L2HE-CWI-UCM | R1 |  | TRUE | ? |  |  | UCM weldmap with accessible welds circled | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242957/UCM%20Weld%20Maps%20w%20highlights%20indicate%20borescope%20videos%20to%20be%20made%20by%20WXCX%20and%20accesible%20welds%20circled_05-14-21.pdf
L2HE-CWI-VV | R1 |  | TRUE | ? |  |  | Vacuum Vessel Weldmap | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-244274/Weld%20Maps%20-%20VV%20-%2011.19.pdf
L2HE-CWI-VV | R1 | 2015-11-04 | TRUE | G. LANGLOIS | FNAL DRAWING |  | LCLS-II HE Vacuum Vessel drawings | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242984/LCLS-II%20HE%20Vacuum%20Vessel%20Drawings.pdf
L2HE-INSP-BLBP | R1 | 2015-11-06 | TRUE | G. LANGLOIS | FNAL DRAWING |  | F10041075-H (WELDMENT BELLOWS PrCM) | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245700/F10041075_H_DWG1%20PrCM%20Bellows.pdf
L2HE-INSP-BLBP | R1 | 2015-11-09 | TRUE | G. LANGLOIS | FNAL DRAWING |  | F10041076 (BELLOWS) | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245705/F10041076___DWG1.pdf
L2HE-INSP-BLBP | R1 | 2014-07-23 | TRUE | G. LANGLOIS | FNAL DRAWING |  | F10023440 (FLANGE RING) | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-241598/F10023440_B_DWG1.pdf
L2HE-INSP-BLBP | R1 | 2014-07-23 | TRUE | G. LANGLOIS | FNAL DRAWING |  | F10023439 (FLANGE ROTATABLE) | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-241597/F10023439_B_DWG1.pdf
L2HE-INSP-BLBP | R1 | 2014-07-23 | TRUE | G. LANGLOIS | FNAL DRAWING |  | F10023436 (FLANGE NR) | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245706/F10023436_B_DWG1.pdf
L2HE-INSP-BLBS | R1 | 2014-07-23 | TRUE | G. LANGLOIS | FNAL DRAWING |  | F10023440 (FLANGE RING) | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-241598/F10023440_B_DWG1.pdf
L2HE-INSP-BLBS | R1 | 2014-07-24 | TRUE | G. LANGLOIS | FNAL DRAWING |  | F10023420 (BELLOWS SHORT) | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245707/F10023420_B_DWG1.pdf
L2HE-INSP-BLBS | R1 | 2014-07-23 | TRUE | G. LANGLOIS | FNAL DRAWING |  | F10023439 (FLANGE ROTATABLE) | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-241597/F10023439_B_DWG1.pdf
L2HE-INSP-BLBS | R1 | 2014-07-23 | TRUE | G. LANGLOIS | FNAL DRAWING |  | F10023436 (FLANGE NR) | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245706/F10023436_B_DWG1.pdf
L2HE-INSP-BLBS | R1 | 2014-07-24 | TRUE | G. LANGLOIS | FNAL DRAWING |  | F10023437-H (WELDMENT BELLOWS SHORT) | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245702/F10023437_H_DWG1%20Short%20Bellows.pdf
L2HE-INSP-BLBU | R1 | 2017-03-13 | TRUE | M. KRAMP | FNAL DRAWING |  | F10075494-C (WELDMENT BELLOWS-US END) | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-241595/F10075494_C_DWG1___.pdf
L2HE-INSP-BLBU | R1 | 2014-07-23 | TRUE | G. LANGLOIS | FNAL DRAWING |  | F10023439-B (FLANGE ROTATABLE) | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-241597/F10023439_B_DWG1.pdf
L2HE-INSP-BLBU | R1 | 2014-07-23 | TRUE | G. LANGLOIS | FNAL DRAWING |  | F10023440-B (FLANGE RING) | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-241598/F10023440_B_DWG1.pdf
L2HE-INSP-BLBU | R1 | 2017-03-13 | TRUE | M. KRAMP | FNAL DRAWING |  | F10075498 (BELLOWS SHORT-US END) | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-241594/F10075498___DWG1.pdf
L2HE-INSP-BLBU | R1 | 2017-03-13 | TRUE | M. KRAMP | FNAL DRAWING |  | F10075500-B (FLANGE NR-US END) | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-241596/F10075500_B_DWG1.pdf
L2HE-INSP-BLXD | R1 | 2016-02-15 | TRUE | M. KRAMP | FNAL DRAWING |  | F10052775-H (WELDMENT EXTENSION - DS) | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245703/F10052775_H_DWG1%20Spool.pdf
L2HE-INSP-BLXD | R1 | 2014-06-06 | TRUE | G. LANGLOIS | FNAL DRAWING |  | F10009427 (TUBE LONG) | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245710/F10009427_B_DWG1.pdf
L2HE-INSP-BLXD | R1 | 2014-05-05 | TRUE | G. LANGLOIS | FNAL DRAWING |  | F10019991 (FLANGE) | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245711/F10019991_F_DWG1.pdf
L2HE-INSP-BLXD | R1 | 2016-02-15 | TRUE | M. KRAMP | FNAL DRAWING |  | F10054235 (FLANGE ROTATABLE) | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245709/F10054235___DWG1.pdf
L2HE-INSP-BLXD | R1 | 2014-06-05 | TRUE | G. LANGLOIS | FNAL DRAWING |  | F10020274 (FLANGE RING BP) | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245708/F10020274_B_DWG1.pdf
L2HE-INSP-CAV | R2 | 2014-07-01 | TRUE | M. Sawtell | FNAL DRAWING |  | Cavity Drawing Package F10023864_rev_M | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-240000/Cavity%20Drawing%20Package%20F10023864_rev_M_drawing_package.pdf
L2HE-INSP-CAV | R3 | 2014-07-01 | TRUE | M. Sawtell | FNAL DRAWING |  | Cavity Drawing Package F10023864_rev_M | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-240000/Cavity%20Drawing%20Package%20F10023864_rev_M_drawing_package.pdf
L2HE-INSP-CDV | R1 | 2020-11-13 | FALSE | ? | FNAL DRAWING |  | 226924-0010 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-243142/226924-0010.pdf
L2HE-INSP-CDV | R1 | 2017-10-18 | TRUE | P. Lambertz | FNAL DRAWING |  | F10088731 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-243144/F10088731-A-DWG1.pdf
L2HE-INSP-CDV | R1 | 2017-10-20 | TRUE | P. Lambertz | FNAL DRAWING |  | F10088841 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-243145/F10088841.pdf
L2HE-INSP-CFL | R1 | 2015-09-11 | TRUE | B. Damphousse | FNAL DRAWING |  | F10046899.pdf | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-241391/F10046899.pdf.pdf
L2HE-INSP-CFL | R1 | 2015-09-11 | TRUE | B. Damphousse | FNAL DRAWING |  | F10022642-Rev G.pdf | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-241390/F10022642-Rev%20G.pdf.pdf
L2HE-INSP-CFL | R1 | 2015-09-11 | TRUE | B. Damphousse | FNAL DRAWING |  | F10046761-Rev A.pdf | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-241392/F10046761-Rev%20A.pdf.pdf
L2HE-INSP-CLMP02K | R1 | 2015-08-17 | TRUE | M. KRAMP | FNAL DRAWING |  | F10040841-Rev G.pdf | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-244189/F10040841_Rev%20G_DWG1-SPQA%202K%20Clamp%20assembly-210505.pdf
L2HE-INSP-CLMP02K | R1 | 2015-05-13 | TRUE | M. KRAMP | FNAL DRAWING |  | F10041603-Rev D.pdf | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-244188/_6-F10041603_D_DWG1-Weldment-2K%20Clamping%20strip.pdf
L2HE-INSP-CLMP05K | R1 |  | TRUE | ? | FNAL DRAWING | PERSONAL DIR | F10045240-Rev C.pdf | file:///X:/Facilities/SRF%20Institute/01%20-%20SRF%20Projects/01%20-%20Open/1.21.01.XXX%20LCLS-II%20HE%20Project%20-%20High%20Energy%20(Preble%5eHogan)/05%20-%20Preliminary%20Drawings%20(L2HE)/F10045240-RevC.pdf
L2HE-INSP-CLMP50K | R1 | 2015-08-17 | TRUE | M. KRAMP | FNAL DRAWING |  | F10045240-Rev C.pdf | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-244213/F10045240-Rev%20C.pdf
L2HE-INSP-CLMPSQ | R1 | 2015-09-01 | TRUE | G. LANGLOIS | FNAL DRAWING |  | F10042265-Rev B.pdf | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-244230/F10042265-RevB.pdf
L2HE-INSP-CLMPSQ | R1 | 2015-09-01 | TRUE | G. LANGLOIS | FNAL DRAWING |  | F10042073-Rev B.pdf | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-244229/F10042073-RevB.pdf
L2HE-INSP-FPCWG | R1 |  | TRUE | G. Bowden | FNAL DRAWING |  | PF-490-703-62_CMM | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-235950/PF-490-703-62_CMM.pdf
L2HE-INSP-FPCWG | R1 | 2015-02-10 | TRUE | Jeff Tice | FNAL DRAWING |  | SA-375-600-90_CMM | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-235951/SA-375-600-90_CMM.pdf
L2HE-INSP-FPCWG | R1 | 2011-10-05 | TRUE | G. Bowden | FNAL DRAWING |  | PF-490-703-61_CMM | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-235949/PF-490-703-61_CMM.pdf
L2HE-INSP-FPCWG | R1 | 2017-03-16 | TRUE | K. Fant | FNAL DRAWING |  | PF-375-602-45_CMM | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-235948/PF-375-602-45_CMM.pdf
L2HE-INSP-FPCWG | R1 | 2015-02-12 | TRUE | Jeff Tice | FNAL DRAWING |  | PF-375-602-38_CMM | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-235947/PF-375-602-38_CMM.pdf
L2HE-INSP-FPCWG | R1 | 2015-03-13 | TRUE | Jeff Tice | FNAL DRAWING |  | PF-375-600-93_CMM | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-235946/PF-375-600-93_CMM.pdf
L2HE-INSP-FPCWG | R1 | 2015-03-12 | TRUE | Jeff Tice | FNAL DRAWING |  | PF-375-600-92_CMM | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-235952/PF-375-600-92_CMM.pdf
L2HE-INSP-FPCWG | R1 | 2017-03-29 | TRUE | K. Fant | FNAL DRAWING |  | SA-375-602-49 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-234671/SA-375-602-49.pdf
L2HE-INSP-FPCWG | R1 | 2015-02-10 | TRUE | Jeff Tice | FNAL DRAWING |  | SA-375-600-90 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-234670/SA-375-600-90.pdf
L2HE-INSP-FPCWG | R1 | 2011-10-05 | TRUE | G. Bowden | FNAL DRAWING |  | PF-490-703-61 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-234668/PF-490-703-61.pdf
L2HE-INSP-FPCWG | R1 | 2017-03-16 | TRUE | K. Fant | FNAL DRAWING |  | PF-375-602-45 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-234667/PF-375-602-45.pdf
L2HE-INSP-FPCWG | R1 | 2017-03-09 | TRUE | K. Fant | FNAL DRAWING |  | PF-375-602-44 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-234666/PF-375-602-44.pdf
L2HE-INSP-FPCWG | R1 | 2011-10-06 | TRUE | G. Bowden | FNAL DRAWING |  | PF-490-703-62 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-234669/PF-490-703-62.pdf
L2HE-INSP-FPCWG | R1 | 2015-02-12 | TRUE | Jeff Tice | FNAL DRAWING |  | PF-375-602-38 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-234665/PF-375-602-38.pdf
L2HE-INSP-FPCWG | R1 | 2015-03-13 | TRUE | Jeff Tice | FNAL DRAWING |  | PF-375-600-93 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-234664/PF-375-600-93.pdf
L2HE-INSP-FPCWG | R1 | 2015-03-12 | TRUE | Jeff Tice | FNAL DRAWING |  | PF-375-600-92 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-234663/PF-375-600-92.pdf
L2HE-INSP-FPCWG | R1 | 2019-05-18 | FALSE | Naeem Huque | FNAL DRAWING |  | SA-375-600-90-SOW | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-234662/SA-375-600-90-SOW.pdf
L2HE-INSP-HMFT | R1 | 2019-08-19 | FALSE | A. Yokoyama | FNAL DRAWING |  | GMM-9433A | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-225207/GMM-B9433A.pdf
L2HE-INSP-IMAG | R1 | 2016-07-27 | TRUE | G. LANGLOIS | FNAL DRAWING |  | Cavity 1 tuner end magnetic shield-1 drawings | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242287/Cavity%201%20Tuner%20End%20Mag%20Shield-1%20Drawings.pdf
L2HE-INSP-IMAG | R1 | 2020-05-20 | FALSE | Gary Cheng | OSP |  | SRF-20-102532-OSP | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242285/operational_safety_procedure_form_102532.pdf
L2HE-INSP-IMAG | R1 | 2016-02-13 | TRUE | Gary Cheng | MSEXCEL |  | Data Log | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-113580/On-axis%20mag%20field%20measurement%20data%20log.xlsx
L2HE-INSP-IMAG | R1 | 2016-01-12 | TRUE | Saravan Chandrasekaran | FNAL DRAWING |  | ED0004281 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-113579/ED0004281--Procedure%20for%20Beam%20Axis%20Measurement%20of%20the%20Magnetic%20Field%20for%20Qualification%20of%20Magnetic%20Shields-v0.pdf
L2HE-INSP-IMAG | R1 | 2015-11-24 | TRUE | G. LANGLOIS | FNAL DRAWING |  | F10048652 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242286/LCLS-II%20HE%20Magnetic%20Shield%20Drawings.pdf
L2HE-INSP-IMAG | R1 | 2016-07-27 | TRUE | G. LANGLOIS | FNAL DRAWING |  | Cavity 6 tuner end magnetic shield drawings | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242289/Cavity%206%20Tuner%20End%20Mag%20Shield%20drawings.pdf
L2HE-INSP-IMAG | R1 | 2016-07-27 | TRUE | G. LANGLOIS | FNAL DRAWING |  | Cavity 1 tuner end magnetic shield-2 drawings | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242288/Cavity%201%20Tuner%20End%20Mag%20Shield-2%20drawings.pdf
L2HE-INSP-PIEZO | R1 | 2017-08-30 | TRUE | Paul Dubiel | FNAL DRAWING |  | LCLSII HE Piezo Wiring Diagram | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-241999/LCLSII%20HE%20Piezo%20Wiring%20Diagram_3450.pdf
L2HE-INSP-SM | R1 |  | TRUE | ? | VENDOR DOC |  | Platinum RTD sensor DIN IEC 751 curve | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-241864/Pt100%20Pt103%20platinum%20RTD%20sensor%20DIN%20IEC751%20curve.pdf
L2HE-INSP-SM | R1 |  | TRUE | ? | MSEXCEL |  | Phytron stepper motor datasheet_VSS VSH.pdf | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-241846/Phytron%20stepper%20motor%20datasheet_VSS%20VSH.pdf
L2HE-INSP-SM | R1 | 2017-08-26 | TRUE | Paul Dubiel | FNAL DRAWING |  | LCLSII HE Stepper Motor Wiring Diagram | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-241847/LCLSII%20HE%20Stepper%20Motor%20Wiring%20Diagram_3456.pdf
L2HE-INSP-TUNC | R1 | 2020-10-27 | FALSE | M. KRAMP | FNAL DRAWING |  | F10147500 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245346/F10147500___DWG1.pdf
L2HE-INSP-TUNC | R1 | 2020-01-16 | FALSE | M. KRAMP | FNAL DRAWING |  | F10132292 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245330/F10132292_B_DWG1.pdf
L2HE-INSP-TUNC | R1 | 2014-05-08 | TRUE | M. Sawtell | FNAL DRAWING |  | F10008764 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245310/F10008764_E_DWG1.pdf
L2HE-INSP-TUNC | R1 | 2016-02-05 | TRUE | Saravan Chandrasekaran | FNAL DRAWING |  | ED0004463 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-123152/ED0004463-REV-A--Specification%20and%20Measurement%20Procedures%20of%20Magnetic%20Properties%20of%20Parts%20for%20LCLS%20II%20Cryomodule%20Assembly(1).doc
L2HE-INSP-TUNC | R1 | 2020-01-16 | FALSE | M. KRAMP | FNAL DRAWING |  | F10132301 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245334/F10132301___DWG1.pdf
L2HE-INSP-TUNC | R1 | 2020-10-27 | FALSE | M. KRAMP | FNAL DRAWING |  | F10147498 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245344/F10147498___DWG1.pdf
L2HE-INSP-TUNC | R1 | 2020-10-28 | FALSE | M. KRAMP | FNAL DRAWING |  | F10147497 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245343/F10147497_A_DWG1.pdf
L2HE-INSP-TUNC | R1 | 2014-05-14 | TRUE | M. Sawtell | FNAL DRAWING |  | F10007032 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245301/F10007032_C_DWG1.pdf
L2HE-INSP-TUNC | R1 | 2020-10-28 | FALSE | M. KRAMP | FNAL DRAWING |  | F10147499 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245345/F10147499_A_DWG1.pdf
L2HE-INSP-TUNCX | R1 | 2020-05-19 | FALSE | M. KRAMP | FNAL DRAWING |  | F10138922 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245336/F10138922_A_DWG1.pdf
L2HE-INSP-TUNCX | R1 | 2017-04-06 | TRUE | M. KRAMP | FNAL DRAWING |  | F10077236 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245328/F10077236_B_DWG1.pdf
L2HE-INSP-TUNCX | R1 | 2014-05-08 | TRUE | M. Sawtell | FNAL DRAWING |  | F10008764 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245310/F10008764_E_DWG1.pdf
L2HE-INSP-TUNCX | R1 | 2016-02-05 | TRUE | Saravan Chandrasekaran | FNAL DRAWING |  | ED0004463 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-123152/ED0004463-REV-A--Specification%20and%20Measurement%20Procedures%20of%20Magnetic%20Properties%20of%20Parts%20for%20LCLS%20II%20Cryomodule%20Assembly(1).doc
L2HE-INSP-TUNCX | R1 | 2020-01-16 | FALSE | M. KRAMP | FNAL DRAWING |  | F10132292 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245330/F10132292_B_DWG1.pdf
L2HE-INSP-TUNCX | R1 | 2017-06-30 | TRUE | M. KRAMP | FNAL DRAWING |  | F10077237 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245329/F10077237_B_DWG1.pdf
L2HE-INSP-TUNCX | R1 | 2020-05-19 | FALSE | M. KRAMP | FNAL DRAWING |  | F10138923 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245337/F10138923_A_DWG1.pdf
L2HE-INSP-TUNCX | R1 | 2014-05-14 | TRUE | M. Sawtell | FNAL DRAWING |  | F10007032 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245301/F10007032_C_DWG1.pdf
L2HE-INSP-TUNCX | R1 | 2020-01-16 | FALSE | M. KRAMP | FNAL DRAWING |  | F10132301 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245334/F10132301___DWG1.pdf
L2HE-VTA-CAV-COOL | R1 | 2009-03-10 | TRUE | Kirk Davis, Pete Kushnick | SOP |  | VTA SOP | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-42664/A-09-001-SOP%20Operation%20of%20the%20Test%20Lab%20VTA%20Document-21542%5B1%5D.pdf | EXPIRED 3/10/2012
L2HE-VTA-CAV-COOL | R1 | 2008-11-13 | TRUE | Pete Kushnick |  |  | VTA Cryo Procedures | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-42665/VTA%20Cryo%20Use%20Procedures%2011132008%5B1%5D.pdf
L2HE-VTA-CAV-VTRF | R1 | 2009-03-10 | TRUE | Kirk Davis, Pete Kushnick | SOP |  | VTA SOP | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-27461/A-09-001-SOP%20Operation%20of%20the%20Test%20Lab%20VTA%20Document-21542.pdf
L2HE-VTA-CAV-VTRF | R1 |  | TRUE | ? |  |  | LCLSII VTA RF Testing Procedure | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-241341/CP-L2HE-VTA-CAV-VTRF-R1.docx
L2HE-VTA-CAV-VTRF | R1 | 2017-01-07 | TRUE | Ari | MSEXCEL |  | 9-Cell Quench Analysis | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-148149/L2_xyzModeAnalysismm_dd_yyyy.xlsx
L2HE-VTA-CAV-VTRF | R1 | 2016-08-29 | TRUE | Tbass | MSEXCEL | STP | Excel spreadsheet template for VTA RF measurements | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-98189/SpreadsheetTemplate%20for%20STP-CAV-VTRF_12Nov2014.xlsm
L2HE-VTA-FPFT-CSHK | R1 | 2019-08-19 | FALSE | A. Yokoyama | FNAL DRAWING |  | Drawing GMM-9434A | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-225208/GMM-B9434A.pdf
L2HE-VTA-HMFT-CSHK | R1 | 2019-08-19 | FALSE | A. Yokoyama | FNAL DRAWING |  | Drawing GMM-9433A | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-225207/GMM-B9433A.pdf

## TRAV REFS
D.S. | PANs | Mlist | Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision |  | Validate location link | Due - 1 month prior to part arriving | First Expected date | Author | Reviewer | Reviewer | Project Manager | Tech Rep (SOTR) | NCR Informative | NCR Dispositioners | D3 Emails | Acronym from INV
|  | X | L2HE Cavity Degrease | L2HE-CHEM-CAV-DEGR | R1 |  |  | 2021-08-01 | 2021-08-01 | ASHLEYA | GANEY |  | HOGAN |  | ashleya,kwilson | hogan,vennekate,ganey | ashleya,vennekate,ganey,hogan,kdavis,forehand,kwilson
Y | Y |  | L2HE Cavity Horizontal Electropolish | L2HE-CHEM-CAV-HEP | R1 | STP Cavity degrease procedure | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-132365/CP-STP-CAV-CHEM-USC-R1.pdf | 2021-08-01 | 2021-08-01 | ASHLEYA | GANEY |  | HOGAN |  | ashleya,kwilson | hogan,vennekate,ganey | ashleya,vennekate,ganey,hogan,kdavis,forehand,kwilson
[6 empty] | HEP Nb Concentration Calculator ; History | https://jlabdoc.jlab.org/docushare/dsweb/View/Collection-29772
[6 empty] | SPEC HEP OperatingManual8148_2020.pdf | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-219641/HEP_OperatingManual8148_2020.pdf
Y | Y |  | Cavity High Pressure Rinse | L2HE-CHEM-CAV-HPR | R1 |  |  |  |  | WILDESON | ASHLEYA |  | HOGAN |  | ashleya,kwilson | hogan,vennekate,ganey | ashleya,vennekate,ganey,hogan,kdavis,forehand,kwilson | CAV
Y | Y |  | Cavity High Pressure Rinse | L2HE-CHEM-CAV-HPR | R2 | CP-STP-CAV-CHEM-HPR-R2 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-125424/CP-STP-CAV-CHEM-HPR-R2.pdf |  |  | WILDESON | ASHLEYA |  | HOGAN |  | ashleya,kwilson | hogan,vennekate,ganey | ashleya,vennekate,ganey,hogan,kdavis,forehand,kwilson | CAV
|  |  | Laping | L2HE-CHEM-CAV-LAP | R1 |  |  | 2021-07-15 |  | WILDESON | ASHLEYA |  | HOGAN |  | ashleya,kwilson | hogan,vennekate,ganey | ashleya,vennekate,ganey,hogan,kdavis,forehand,kwilson
Y | Y |  | L2HE Cavity Ultrasonic Cleaning | L2HE-CHEM-CAV-USC | R1 | CP-C75-CAV-CHEM-USC-R2 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-212978/CP-C75-CAV-CHEM-USC-R1.pdf |  |  | WILDESON | ASHLEYA |  | HOGAN |  | ashleya,kwilson | hogan,vennekate,ganey | ashleya,vennekate,ganey,hogan,kdavis,forehand,kwilson
Y | Y |  | L2HE Cavity Ultrasonic Cleaning | L2HE-CHEM-CAV-USC | R2 | CP-C75-CAV-CHEM-USC-R2 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-212978/CP-C75-CAV-CHEM-USC-R1.pdf |  |  | WILDESON | ASHLEYA |  | HOGAN |  | ashleya,kwilson | hogan,vennekate,ganey | ashleya,vennekate,ganey,hogan,kdavis,forehand,kwilson
Y | Y |  | Components Cleaning | L2HE-CHEM-COMP-DEGR | R1 | CP-C75-CAV-BCP-ER | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-150777/CP-C75-CAV-BCP-ER-R1.pdf | 2021-07-01 |  | ASHLEYA | WILDESON |  | HOGAN |  | ashleya | hogan,ari | ashleya,ari,hogan,kdavis,forehand
[6 empty] | CP-L2PRD-CAV-CHEM-CLN-COMP | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-127640/CP-L2PRD-CAV-CHEM-CLN-COMP-R1.pdf
|  | X | Laping | L2HE-CHEM-COMP-LAP | R1 |  |  | 2021-08-15 | 2021-11-01 | WILDESON | ASHLEYA |  | HOGAN |  | ashleya,kwilson | hogan,vennekate,ganey | ashleya,vennekate,ganey,hogan,kdavis,forehand,kwilson
|  |  | Cavity String Gate Valve Leak Test | L2HE-CLNRM-AMGV-LEAK | R1 |  |  | 2021-12-01 | 2021-04-29 | FOREHAND |  |  | HOGAN
|  |  | BPM Magnet sub-assembly | L2HE-CLNRM-BPM-ASSY | R1 |  |  | 2021-12-01 |  | FOREHAND |  |  | HOGAN
Y | Y |  | Cavity 1st Assembly | L2HE-CLNRM-CAV-ASSY1 | R1 | Leak testing with an RGA procedure | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-27678/CP-C100-CAV-LKTS.pdf | 2021-06-01 |  | FOREHAND | DREYFUSS |  | KWILSON
[6 empty] | Ionized Nitrogen Cleaning Procedure | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-129170/CP-L2PRD-CST-IONCLN-R1.pdf
Y | Y |  | Cavity 2nd Assembly | L2HE-CLNRM-CAV-ASSY2 | R1 | Leak testing with an RGA procedure | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-27678/CP-C100-CAV-LKTS.pdf | 2021-06-01 |  | FOREHAND | DREYFUSS |  | KWILSON
[6 empty] | Ionized Nitrogen Cleaning Procedure | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-129170/CP-L2PRD-CST-IONCLN-R1.pdf
|  | X | Cavity Evacuation & Leak Test | L2HE-CLNRM-CAV-LEAK | R1 |  |  | 2021-09-01 | 2021-10-01 | FOREHAND | DREYFUSS |  | KWILSON
Y | Y |  | Transfer of L2PRD 9-cell cavities to Test Stands | L2HE-CLNRM-CAV-TSTD | R1 |  |  | 2021-06-01 |  | FOREHAND | DREYFUSS |  | KWILSON
Y | Y |  | Transfer of L2PRD 9-cell cavities to Test Stands | L2HE-CLNRM-CAV-TSTD | R2 |  |  | 2021-06-01 |  | FOREHAND | DREYFUSS |  | KWILSON
Y | Y |  | Transfer of L2PRD 9-cell cavities to Test Stands for Dewar 5 | L2HE-CLNRM-CAV-TSTD5 | R1 |  |  | 2021-06-01 |  | FOREHAND | DREYFUSS |  | KWILSON
|  |  | Cavity String Assembly (MAJOR CHANGE) | L2HE-CLNRM-CST-ASSY | R1 |  |  | 2021-12-01 |  | FOREHAND |  |  | HOGAN
|  |  | String Pump down, leak test and transfer to phase 1 | L2HE-CLNRM-CST-LEAK | R1 |  |  | 2021-12-01 |  | FOREHAND |  |  | HOGAN
Y | Y |  | FPC COLD PART | L2HE-CLNRM-FPCC-INSP | R1 | Solair 3100 Gen E Manual | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242798/Solair%203100%20Gen%20E%20Manual.pdf | 2021-05-24 | 2020-05-15 | HUQUE |  |  | HOGAN |  |  |  |  | FPCC
[6 empty] | CP-C100-CAV-LKTS | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-243276/CP-C100-CAV-LKTS.pdf
[6 empty] | CP-L2PRD-CLN-PUMP | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-243275/CP-L2PRD-CLN-PUMP.docx
[6 empty] | LCLSII-HE-1.2-ES-0059 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242805/LCLSII-HE-1.2-ES-0059.pdf
[6 empty] | Vacuum-005-2008 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242799/Vacuum-005-2008%20Guidelines%20for%20UHV-Components%20at%20DESY.pdf
[6 empty] | CP-STP-CAV-CHEM-DEGR-R3 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242804/CP-STP-CAV-CHEM-DEGR-R3.pdf
[6 empty] | L2HE-PR-INSP-FPCC | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-243519/L2HE-PR-INSP-FPCC-R1.pdf
[6 empty] | CP-L2PRO-CST-CHEM-CLN-ION | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-243277/CP-L2PRO-CST-CHEM-CLN-ION-R1.pdf
[6 empty] | CP-L2PRD-CM-SLBUP-R2 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242801/CP-L2PRD-CM-SLBUP-R2.pdf
Y | Y |  | FPC COLD PART | L2HE-CLNRM-FPCC-INSP | R2 | CP-L2PRD-CLN-PUMP | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-243275/CP-L2PRD-CLN-PUMP.docx | 2021-05-24 | 2020-05-15 | HUQUE |  |  | HOGAN |  |  |  |  | FPCC
[6 empty] | LCLSII-HE-1.2-ES-0059 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242805/LCLSII-HE-1.2-ES-0059.pdf
[6 empty] | CP-C100-CAV-LKTS | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-243276/CP-C100-CAV-LKTS.pdf
[6 empty] | Vacuum-005-2008 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242799/Vacuum-005-2008%20Guidelines%20for%20UHV-Components%20at%20DESY.pdf
[6 empty] | Solair 3100 Gen E Manual | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242798/Solair%203100%20Gen%20E%20Manual.pdf
[6 empty] | CP-L2PRO-CST-CHEM-CLN-ION | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-243277/CP-L2PRO-CST-CHEM-CLN-ION-R1.pdf
[6 empty] | CP-L2PRD-CM-SLBUP-R2 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242801/CP-L2PRD-CM-SLBUP-R2.pdf
[6 empty] | CP-STP-CAV-CHEM-DEGR-R3 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242804/CP-STP-CAV-CHEM-DEGR-R3.pdf
Y | Y |  | Cavity Beam Line Bellows PRCM Leak Test | L2HE-CMA-BLBP-LEAK | R1 | 11141S0029-B | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245701/11141S0029-B%202e-10%20Leak%20Check%20Final.pdf | 2021-08-15 | 2021-08-01 | MARCHLIK | WILCOX |  | KWILSON | MARCHLIK | Ari, Reece | Marchlik, Wilson | Marchlik, Wilson
[6 empty] | F10041075-H (WELDMENT BELLOWS-PrCM | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245700/F10041075_H_DWG1%20PrCM%20Bellows.pdf
Y | Y |  | Cavity Beam Line Bellows Short | L2HE-CMA-BLBS-LEAK | R1 | F10023437 (WELDMENT BELLOWS-Short | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245702/F10023437_H_DWG1%20Short%20Bellows.pdf | 2021-08-15 | 2021-08-01 | MARCHLIK | WILCOX |  | KWILSON | MARCHLIK | Ari, Reece | Marchlik, Wilson | Marchlik, Wilson
[6 empty] | 11141S0029-B | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245701/11141S0029-B%202e-10%20Leak%20Check%20Final.pdf
Y | Y |  | Cavity String Weldment Upstream Bellows | L2HE-CMA-BLBU-LEAK | R1 | 11141S0029-B | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-241599/11141-S-0029.pdf | 2021-08-15 | 2021-05-10 | MARCHLIK | WILCOX |  | KWILSON | MARCHLIK | Ari, Reece | Marchlik, Wilson | Marchlik, Wilson
[6 empty] | F10075494-C (WELDMENT BELLOWS-US END | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-241595/F10075494_C_DWG1___.pdf
Y | Y |  | String Beam Line Extension Downstream | L2HE-CMA-BLXD-LEAK | R1 | F10052775 (WELDMENT EXTENSION-DS | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245703/F10052775_H_DWG1%20Spool.pdf | 2021-08-15 | 2021-08-01 | MARCHLIK | WILCOX |  | KWILSON | MARCHLIK | Ari, Reece | Marchlik, Wilson | Marchlik, Wilson
[6 empty] | 11141S0029-B | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245701/11141S0029-B%202e-10%20Leak%20Check%20Final.pdf
|  |  | CM Assembly First | L2HE-CMA-CM-ASSY1 | R1 |  |  | 2022-02-01 |  | FISCHER | WORLAND |  | HOGAN
|  |  | CM Assembly Second | L2HE-CMA-CM-ASSY2 | R1 |  |  | 2022-02-01 |  | FISCHER | WORLAND |  | HOGAN
|  |  | CM Assembly Final | L2HE-CMA-CM-ASSYF | R1 |  |  | 2022-02-01 |  | FISCHER | WORLAND |  | HOGAN
|  | N/A | Cryomodule Rework Traveler | L2HE-CMA-CM-REW | R1 |  |  | 2022-02-01 |  | FISCHER |  |  | HOGAN
|  | N/A | Cryomodule Retrofit Traveler | L2HE-CMA-CM-RFIT | R1 |  |  | 2022-02-01 |  | FISCHER |  |  | HOGAN
|  |  | Cryomodule Prep and Shipping to SLAC | L2HE-CMA-CM-SHIP | R1 |  |  | 2022-02-01 |  | JARED | FISCHER |  | HOGAN
|  |  | FPC Warm Installation | L2HE-CMA-FPCW-ASSY | R1 |  |  | 2022-02-01 | 2022-02-01 | HUQUE |  |  | HOGAN
|  | N/A | FPCW AC Diassemble/Removal | L2HE-CMA-FPCW-DISA | R1 |  |  | 2022-02-01 | 2020-05-15 | HUQUE |  |  | HOGAN
Y | Y |  | FPC WARM PART | L2HE-CMA-FPCW-INSP | R1 | LCLSII-HE-1.2-ES-0059 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242805/LCLSII-HE-1.2-ES-0059.pdf | 2021-05-24 | 2020-05-15 | HUQUE |  |  | HOGAN
[6 empty] | L2HE-PR-CMA -FPCW-INSP | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-244733/L2HE-PR-CMA-FPCW-INSP-R1.pdf
Y | Y |  | Cavity Field Probe Feedthru Receiving Inspection | L2HE-CMA-FPFT-LEAK | R1 | Drawing GMM-9434A | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-225208/GMM-B9434A.pdf | 2020-10-21 |  | HKPARK | WILCOX |  | KWILSON | ZHAO | Ari, Reece | Park, Wilson | Park, Wilson
Y | Y |  | Cavity HOM Feedthru Receiving Inspection | L2HE-CMA-HMFT-LEAK | R1 | Drawing GMM-9433A | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-225207/GMM-B9433A.pdf | 2020-10-21 |  | HKPARK | WILCOX |  | KWILSON | ZHAO | Ari, Reece | Park, Wilson | Park, Wilson
Y | Y |  | Upper Cold Mass Magnetic Hygiene Control | L2HE-CMA-UCM-DMAG | R1 | LCLS-II HE Upper Cold Mass Drawings | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242872/LCLS-II%20HE%20Upper%20Cold%20Mass%20drawings.pdf | 2021-05-28 |  | CHENG | FISCHER |  | HOGAN | CHENG | Wilson, Hogan | Fischer, Cheng | Fischer, Cheng
[6 empty] | Small parts Demagnetization OSP | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242285/operational_safety_procedure_form_102532.pdf
Y | Y |  | Upper Cold Mass CMA Inspection | L2HE-CMA-UCM-INSP | R1 | Upper Cold Mass Specification ED0003252 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242873/ED0003252-E-SPEC.pdf | 2021-05-28 |  | CHENG | FISCHER |  | HOGAN | CHENG | Katherine, Hogan | Gary, Fischer | Gary, Fischer
[6 empty] | LCLS-II HE Upper Cold Mass Drawings | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242872/LCLS-II%20HE%20Upper%20Cold%20Mass%20drawings.pdf
[6 empty] | reportlistUC002 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242874/report%20listUC-002.pdf
[6 empty] | reportlistUC-002-010 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242875/report%20listUC-002-010.pdf
|  |  | Cryomodule Vacuum Vessel Assembly | L2HE-CMA-VV-ASSY | R1 |  |  | 2022-02-01 |  | FISCHER | WORLAND |  | HOGAN
Y | Y |  | Receiving CMA Inspection CM Vacuum Vessel | L2HE-CMA-VV-INSP | R1 | LCLS-II HE Vacuum Vessel drawings | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242984/LCLS-II%20HE%20Vacuum%20Vessel%20Drawings.pdf | 2021-05-28 |  | CHENG | FISCHER |  | HOGAN | CHENG | Katherine, Hogan | Gary, Fischer | Gary, Fischer | FPCW
[6 empty] | Vacuum Vessel_QC | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-132917/VacuumVessel_QC_Task%20List.xlsx
[6 empty] | LCLS-II HE Vacuum Vessel Specification ED0002342 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242985/ED0002342---LCLS-II_VacVessel_SPEC.pdf
[6 empty] | Vendors document list | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242986/report%20listVV-002..pdf
Y | Y |  | Upper Cold Mass Weld Inspection? | L2HE-CWI-UCM | R1 | LCLS-II HE Upper Cold Mass Drawings | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242872/LCLS-II%20HE%20Upper%20Cold%20Mass%20drawings.pdf | 2021-05-28 |  | CHENG | JENORD | FISCHER | HOGAN | CHENG | Katherine, Hogan | Gary, Fischer | Gary, Fischer
[6 empty] | Upper Cold Mass Specification ED0003252 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242873/ED0003252-E-SPEC.pdf
[6 empty] | Drawings for accessible welds | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242958/UCM%20Weld%20Insp%20Drawings.pdf
[6 empty] | UCM weldmap with accessible welds circled | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242957/UCM%20Weld%20Maps%20w%20highlights%20indicate%20borescope%20videos%20to%20be%20made%20by%20WXCX%20and%20accesible%20welds%20circled_05-14-21.pdf
Y | Y |  | Vacuum Vessel Receiving Weld Inspection | L2HE-CWI-VV | R1 | Vacuum Vessel Weldmap | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-244274/Weld%20Maps%20-%20VV%20-%2011.19.pdf |  |  | CHENG | JENORD | FISCHER | HOGAN |  | Kwilson, hogan | Cheng, fischer | Cheng, fischer
[6 empty] | LCLS-II HE Vacuum Vessel drawings | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242984/LCLS-II%20HE%20Vacuum%20Vessel%20Drawings.pdf
| Y |  | D3 Report | L2HE-D3 | R2 |  |  |  |  | MEGAN | BOOKWALT |  | MCEWEN
Y | Y |  | Cavity Beam Line Bellows PRCM | L2HE-INSP-BLBP | R1 | F10041075-H (WELDMENT BELLOWS PrCM) | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245700/F10041075_H_DWG1%20PrCM%20Bellows.pdf | 2021-07-26 | 2021-08-01 | MARCHLIK | GEORGED | ZHAO | HOGAN | REECE | Hannesv, Reece | Lzhao, Wilson | Lzhao, Wilson
[6 empty] | F10041076 (BELLOWS) | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245705/F10041076___DWG1.pdf
[6 empty] | F10023440 (FLANGE RING) | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-241598/F10023440_B_DWG1.pdf
[6 empty] | F10023439 (FLANGE ROTATABLE) | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-241597/F10023439_B_DWG1.pdf
[6 empty] | F10023436 (FLANGE NR) | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245706/F10023436_B_DWG1.pdf
Y | Y |  | Cavity Beam Line Bellows Short | L2HE-INSP-BLBS | R1 | F10023440 (FLANGE RING) | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-241598/F10023440_B_DWG1.pdf | 2021-07-26 | 2021-08-01 | MARCHLIK | GEORGED | ZHAO | HOGAN | MARCHLIK
[6 empty] | F10023420 (BELLOWS SHORT) | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245707/F10023420_B_DWG1.pdf
[6 empty] | F10023439 (FLANGE ROTATABLE) | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-241597/F10023439_B_DWG1.pdf
[6 empty] | F10023436 (FLANGE NR) | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245706/F10023436_B_DWG1.pdf
[6 empty] | F10023437-H (WELDMENT BELLOWS SHORT) | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245702/F10023437_H_DWG1%20Short%20Bellows.pdf
Y | Y |  | Cavity String Weldment Upstream Bellows | L2HE-INSP-BLBU | R1 | F10075494-C (WELDMENT BELLOWS-US END) | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-241595/F10075494_C_DWG1___.pdf | 2021-07-01 | 2021-05-10 | MARCHLIK | GEORGED | ZHAO | HOGAN | MARCHLIK
[6 empty] | F10023439-B (FLANGE ROTATABLE) | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-241597/F10023439_B_DWG1.pdf
[6 empty] | F10023440-B (FLANGE RING) | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-241598/F10023440_B_DWG1.pdf
[6 empty] | F10075498 (BELLOWS SHORT-US END) | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-241594/F10075498___DWG1.pdf
[6 empty] | F10075500-B (FLANGE NR-US END) | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-241596/F10075500_B_DWG1.pdf
Y | Y |  | String Beam Line Extension Downstream | L2HE-INSP-BLXD | R1 | F10052775-H (WELDMENT EXTENSION - DS) | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245703/F10052775_H_DWG1%20Spool.pdf | 2021-07-01 |  | MARCHLIK | GEORGED | ZHAO | HOGAN | MARCHLIK
[6 empty] | F10009427 (TUBE LONG) | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245710/F10009427_B_DWG1.pdf
[6 empty] | F10019991 (FLANGE) | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245711/F10019991_F_DWG1.pdf
[6 empty] | F10054235 (FLANGE ROTATABLE) | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245709/F10054235___DWG1.pdf
[6 empty] | F10020274 (FLANGE RING BP) | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245708/F10020274_B_DWG1.pdf
Y | Y |  | Cavity Inspection | L2HE-INSP-CAV | R1 |  |  | 2021-08-01 |  | KWILSON |  |  | HOGAN |  |  |  |  | CAV
Y | Y |  | Cavity Inspection | L2HE-INSP-CAV | R2 | Cavity Drawing Package F10023864_rev_M | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-240000/Cavity%20Drawing%20Package%20F10023864_rev_M_drawing_package.pdf | 2021-08-01 |  | KWILSON |  |  | HOGAN |  |  |  |  | CAV
Y | Y |  | Cavity Inspection | L2HE-INSP-CAV | R3 | Cavity Drawing Package F10023864_rev_M | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-240000/Cavity%20Drawing%20Package%20F10023864_rev_M_drawing_package.pdf | 2021-08-01 |  | KWILSON |  |  | HOGAN |  |  |  |  | CAV
Y | Y |  | Cryomodule Cool Down Cryogenic Valve (CDV) | L2HE-INSP-CDV | R1 | 226924-0010 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-243142/226924-0010.pdf | 2021-05-17 |  | JTKENT | FISCHER | MCEWEN | HOGAN | JTKENT | Katherine, Hogan | Kent, Wilson | Kent, Fischer
[6 empty] | F10088731 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-243144/F10088731-A-DWG1.pdf
[6 empty] | F10088841 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-243145/F10088841.pdf
Y | Y |  | 300K Current Leads CF Flange Inspection | L2HE-INSP-CFL | R1 | F10046899.pdf | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-241391/F10046899.pdf.pdf | 2021-04-01 |  | LALITHA | KING | MORRONE | HOGAN | LALITHA | hogan,kwilson | lalitha,king | lalitha,king,fisher,morrone
[6 empty] | F10022642-Rev G.pdf | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-241390/F10022642-Rev%20G.pdf.pdf
[6 empty] | F10046761-Rev A.pdf | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-241392/F10046761-Rev%20A.pdf.pdf
Y | Y |  | LCLS-II HE 2K Clamp Assembly Kit Inspection | L2HE-INSP-CLMP02K | R1 | F10040841-Rev G.pdf | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-244189/F10040841_Rev%20G_DWG1-SPQA%202K%20Clamp%20assembly-210505.pdf |  |  | LALITHA | KING | FISCHER | HOGAN | LALITHA | Kwilson,hogan | lalitha,king | lalitha,king,fischer
[6 empty] | F10041603-Rev D.pdf | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-244188/_6-F10041603_D_DWG1-Weldment-2K%20Clamping%20strip.pdf
Y | Y |  | LCLS-II HE 5K Clamp Assembly Kit Inspection Traveler | L2HE-INSP-CLMP05K | R1 | F10045240-Rev C.pdf | file:///X:/Facilities/SRF%20Institute/01%20-%20SRF%20Projects/01%20-%20Open/1.21.01.XXX%20LCLS-II%20HE%20Project%20-%20High%20Energy%20(Preble%5eHogan)/05%20-%20Preliminary%20Drawings%20(L2HE)/F10045240-RevC.pdf |  |  | LALITHA | KING | FISCHER | HOGAN | LALITHA | Kwilson,hogan | lalitha,king | lalitha,king,fischer
Y | Y |  | LCLS-II HE 50 K Clamp Assembly Kit Inspection Traveler | L2HE-INSP-CLMP50K | R1 | F10045240-Rev C.pdf | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-244213/F10045240-Rev%20C.pdf |  |  | LALITHA | KING | FISCHER | HOGAN | LALITHA | Kwilson,hogan | lalitha,king | lalitha,king,fischer
Y | Y |  | LCLS-II HE Split-Quad Clamp Kit Inspection Traveler | L2HE-INSP-CLMPSQ | R1 | F10042265-Rev B.pdf | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-244230/F10042265-RevB.pdf |  |  | LALITHA | KING | FISCHER | HOGAN | LALITHA | Kwilson,hogan | lalitha,king | lalitha,king,fischer
[6 empty] | F10042073-Rev B.pdf | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-244229/F10042073-RevB.pdf
Y | Y |  | FPC Waveguide Incoming Inspection | L2HE-INSP-FPCWG | R1 | PF-490-703-62_CMM | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-235950/PF-490-703-62_CMM.pdf | 2021-10-15 | 2021-01-27 | HUQUE | STIRBET |  | HOGAN | HUQUE
[6 empty] | SA-375-600-90_CMM | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-235951/SA-375-600-90_CMM.pdf
[6 empty] | PF-490-703-61_CMM | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-235949/PF-490-703-61_CMM.pdf
[6 empty] | PF-375-602-45_CMM | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-235948/PF-375-602-45_CMM.pdf
[6 empty] | PF-375-602-38_CMM | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-235947/PF-375-602-38_CMM.pdf
[6 empty] | PF-375-600-93_CMM | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-235946/PF-375-600-93_CMM.pdf
[6 empty] | PF-375-600-92_CMM | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-235952/PF-375-600-92_CMM.pdf
[6 empty] | SA-375-602-49 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-234671/SA-375-602-49.pdf
[6 empty] | SA-375-600-90 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-234670/SA-375-600-90.pdf
[6 empty] | PF-490-703-61 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-234668/PF-490-703-61.pdf
[6 empty] | PF-375-602-45 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-234667/PF-375-602-45.pdf
[6 empty] | PF-375-602-44 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-234666/PF-375-602-44.pdf
[6 empty] | PF-490-703-62 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-234669/PF-490-703-62.pdf
[6 empty] | PF-375-602-38 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-234665/PF-375-602-38.pdf
[6 empty] | PF-375-600-93 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-234664/PF-375-600-93.pdf
[6 empty] | PF-375-600-92 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-234663/PF-375-600-92.pdf
[6 empty] | SA-375-600-90-SOW | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-234662/SA-375-600-90-SOW.pdf
Y | Y |  | Cavity Field Probe Feedthru Receiving Inspection | L2HE-INSP-FPFT | R1 |  |  | 2020-10-16 |  | ZHAO | GEORGED |  | KWILSON | ZHAO | hannesv, Reece | lzhao, Wilson | lzhao, Wilson
Y | Y |  | Cavity HOM Feedthru Receiving Inspection | L2HE-INSP-HMFT | R1 | GMM-9433A | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-225207/GMM-B9433A.pdf | 2020-10-16 |  | ZHAO | GEORGED |  | KWILSON | ZHAO | hannesv, Reece | lzhao, Wilson | lzhao, Wilson
Y | Y |  | Receiving Inspection CM Magnetic Shield Assembly | L2HE-INSP-IMAG | R1 | Cavity 1 tuner end magnetic shield-1 drawings | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242287/Cavity%201%20Tuner%20End%20Mag%20Shield-1%20Drawings.pdf | 2021-05-14 |  | CHENG | GEORGED | FISCHER | HOGAN | CHENG | Katherine, Hogan | Gary, Fischer | Gary, Fischer
[6 empty] | SRF-20-102532-OSP | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242285/operational_safety_procedure_form_102532.pdf
[6 empty] | Data Log | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-113580/On-axis%20mag%20field%20measurement%20data%20log.xlsx
[6 empty] | ED0004281 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-113579/ED0004281--Procedure%20for%20Beam%20Axis%20Measurement%20of%20the%20Magnetic%20Field%20for%20Qualification%20of%20Magnetic%20Shields-v0.pdf
[6 empty] | F10048652 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242286/LCLS-II%20HE%20Magnetic%20Shield%20Drawings.pdf
[6 empty] | Cavity 6 tuner end magnetic shield drawings | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242289/Cavity%206%20Tuner%20End%20Mag%20Shield%20drawings.pdf
[6 empty] | Cavity 1 tuner end magnetic shield-2 drawings | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-242288/Cavity%201%20Tuner%20End%20Mag%20Shield-2%20drawings.pdf
|  | X | Receiving Inspection CM Rod Invar 2-Phase Long | L2HE-INSP-IROD2L | R1 |  |  | 2021-08-01 |  | OBRIEN |  |  | HOGAN
|  | X | Receiving Inspection CM Rod Invar 2-Phase | L2HE-INSP-IROD2P | R1 |  |  | 2021-08-01 |  | OBRIEN |  |  | HOGAN |  |  |  |  | FPCWG
Y |  |  | Receiving Inspection CM Assembly, JT Cryogenic Valve | L2HE-INSP-JTV | R1 |  |  | 2021-05-17 |  | JTKENT | FISCHER | MCEWEN | HOGAN | JTKENT | Katherine, Hogan | Kent, Wilson | Kent, Fischer
|  | X | Receiving Inspection CM Assembly, JT Valve Tube Kit | L2HE-INSP-JTVTK | R1 |  |  | 2021-08-01 |  | JTKENT | FISCHER | MCEWEN | HOGAN | JTKENT | Katherine, Hogan | Kent, Wilson | Kent, Fischer
Y | Y |  | Tuner Piezo Actuator Assembly Inspection | L2HE-INSP-PIEZO | R1 | LCLSII HE Piezo Wiring Diagram | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-241999/LCLSII%20HE%20Piezo%20Wiring%20Diagram_3450.pdf | 2021-03-05 | 2021-05-31 | KING | POWEN | HUQUE | HOGAN | POWEN | huque,kwilson | Powen, King | Powen, Huque, Wilson
|  |  | Quadrapole Magnet Inspection | L2HE-INSP-QUAD | R1 | Platinum RTD sensor DIN IEC 751 curve | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-241864/Pt100%20Pt103%20platinum%20RTD%20sensor%20DIN%20IEC751%20curve.pdf | 2021-08-30 |  | LALITHA | KING | MORRONE | HOGAN | LALITHA |  | Lakshmi, Wilson | Lakshmi, Wilson
Y | Y |  | End Lever Tuner Motor | L2HE-INSP-SM | R1 | Phytron stepper motor datasheet_VSS VSH.pdf | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-241846/Phytron%20stepper%20motor%20datasheet_VSS%20VSH.pdf | 2021-04-01 | 2021-04-30 | KING | POWEN | HUQUE | HOGAN | POWEN | huque,kwilson | Powen, King | Powen, Huque, Wilson
[6 empty] | LCLSII HE Stepper Motor Wiring Diagram | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-241847/LCLSII%20HE%20Stepper%20Motor%20Wiring%20Diagram_3456.pdf
https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-241864/Pt100%20Pt103%20platinum%20RTD%20sensor%20DIN%20IEC751%20curve.pdf
Y | Y |  | End Lever Tuner Mechanical Frame Inspection | L2HE-INSP-TUNC | R1 | F10147500 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245346/F10147500___DWG1.pdf | 2021-07-14 | 2021-08-15 | POWEN | GEORGED | HUQUE | HOGAN | POWEN | kwilson | Powen, Huque, georged | Powen, Huque, Wilson
[6 empty] | F10132292 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245330/F10132292_B_DWG1.pdf
[6 empty] | F10008764 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245310/F10008764_E_DWG1.pdf
[6 empty] | ED0004463 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-123152/ED0004463-REV-A--Specification%20and%20Measurement%20Procedures%20of%20Magnetic%20Properties%20of%20Parts%20for%20LCLS%20II%20Cryomodule%20Assembly(1).doc
[6 empty] | F10132301 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245334/F10132301___DWG1.pdf
[6 empty] | F10147498 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245344/F10147498___DWG1.pdf
[6 empty] | F10147497 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245343/F10147497_A_DWG1.pdf
[6 empty] | F10007032 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245301/F10007032_C_DWG1.pdf
[6 empty] | F10147499 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245345/F10147499_A_DWG1.pdf
Y | Y |  | End Lever Tuner Extended Mechanical Frame Inspection Traveler | L2HE-INSP-TUNCX | R1 | F10138922 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245336/F10138922_A_DWG1.pdf | 2021-07-14 | 2021-08-15 | POWEN | GEORGED | HUQUE | HOGAN
[6 empty] | F10077236 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245328/F10077236_B_DWG1.pdf
[6 empty] | F10008764 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245310/F10008764_E_DWG1.pdf
[6 empty] | ED0004463 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-123152/ED0004463-REV-A--Specification%20and%20Measurement%20Procedures%20of%20Magnetic%20Properties%20of%20Parts%20for%20LCLS%20II%20Cryomodule%20Assembly(1).doc
[6 empty] | F10132292 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245330/F10132292_B_DWG1.pdf
[6 empty] | F10077237 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245329/F10077237_B_DWG1.pdf
[6 empty] | F10138923 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245337/F10138923_A_DWG1.pdf
[6 empty] | F10007032 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245301/F10007032_C_DWG1.pdf
[6 empty] | F10132301 | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-245334/F10132301___DWG1.pdf
| Y |  | Inspection Summary Report | L2HE-INSR | R1
Y | Y |  | All Metal Gate Valve Inventory | L2HE-INV-AMGV | R1 |  |  | 2021-05-01 |  | MDICKEY | CBARNES |  | HOGAN | DSAVR | Mdicky,Hogan | Kwilson,Dsavr
Y | Y |  | Cavity Beam Line Bellows PRCM Inventory | L2HE-INV-BLBP | R1 |  |  | 2021-07-26 | 2021-08-01 | MDICKEY | CBARNES |  | HOGAN
Y | Y |  | Cavity Beam Line Bellows Short Inventory | L2HE-INV-BLBS | R1 |  |  | 2021-07-26 | 2021-08-01 | MDICKEY | CBARNES |  | HOGAN
Y | Y |  | Cavity String Weldment Upstream Bellows Inventory | L2HE-INV-BLBU | R1 |  |  | 2021-05-01 | 2021-05-10 | MDICKEY | CBARNES |  | HOGAN
Y | Y |  | String Beam Line Extension Downstream Inventory | L2HE-INV-BLXD | R1 |  |  | 2021-07-01 |  | MDICKEY | CBARNES |  | HOGAN
Y | Y |  | Inventory BP2PH | L2HE-INV-BP2PH | R1 |  |  |  |  | MDICKEY | CBARNES |  | HOGAN
Y | Y |  | Cavity Inventory | L2HE-INV-CAV | R1 |  |  | 2021-08-01 | 2020-05-15 | HANNESV
Y |  |  | LCLS-II HE Cernox Inventory Traveler | L2HE-INV-CERNOX | R1 |  |  | 2021-08-15 | 2021-10-01 | MDICKEY | CBARNES | KING | HOGAN | KING
Y | Y |  | FPC COLD PART Inventory | L2HE-INV-FPCC | R1 |  |  | 2021-05-24 | 2020-05-15 | HUQUE | MDICKEY | CBARNES | HOGAN | HUQUE | Dickey,Hogan,kwilson | Huque | Huque,Hogan,kwilson
Y | Y |  | FPC WARM PART Inventory | L2HE-INV-FPCW | R1 |  |  | 2021-05-24 | 2020-05-15 |  |  |  | HOGAN | HUQUE
Y | Y |  | FPC Waveguide Inventory | L2HE-INV-FPCWG | R1 |  |  | 2021-05-01 | 2021-01-27 | MDICKEY | CBARNES |  | KWILSON |  | Wislon | Huque,Fischer | Huque,Fisher
Y | Y | ? | Cavity Field Probe Feedthru Receiving Inventory | L2HE-INV-FPFT | R1 |  |  | 2021-05-19 |  | MDICKEY | CBARNES |  | HOGAN | ZHAO | hannesv, Reece | lzhao, Wilson | lzhao, Wilson
Y | Y | ? | Cavity HOM Feedthru Receiving Inventory | L2HE-INV-HMFT | R1 |  |  | 2021-05-19 |  | MDICKEY | CBARNES |  | HOGAN | ZHAO | hannesv,reece | lzhao, Wilson | lzhao, Wilson
Y | Y |  | CM Magnetic Shield Assembly Inventory | L2HE-INV-IMAG | R1 |  |  | 2021-05-14 |  | MDICKEY | CBARNES |  | HOGAN | CHENG | Katherine, Hogan | Gary, Fischer | Gary, Fischer
Y | Y |  | CM Assembly, JT Valve Tube Kit Inventory | L2HE-INV-JTVTK | R1 |  |  | 2021-08-01 |  | MDICKEY | CBARNES |  | HOGAN
Y | Y |  | Inventory LLDS | L2HE-INV-LLDS | R1 |  |  |  |  | MDICKEY | CBARNES |  | HOGAN
Y | Y |  | Inventory LLNDS | L2HE-INV-LLNDS | R1 |  |  |  |  | MDICKEY | CBARNES |  | HOGAN
Y | Y |  | Inventory LLNUS | L2HE-INV-LLNUS | R1 |  |  |  |  | MDICKEY | CBARNES |  | HOGAN
Y | Y |  | Inventory LLUS | L2HE-INV-LLUS | R1 |  |  |  |  | MDICKEY | CBARNES |  | HOGAN
Y | Y |  | Tuner Piezo Actuator Inventory | L2HE-INV-PIEZO | R1 |  |  | 2021-05-01 | 2021-05-31 | MDICKEY | CBARNES |  | HOGAN | POWEN | mdickey,Hogan,areilly | powen | Hogan,powen,areilly
Y | Y |  | Quadrapole Magnet Inventory | L2HE-INV-QUAD | R1 |  |  | 2021-06-15 |  | MDICKEY | CBARNES | MORRONE | HOGAN | LALITHA |  | Lakshmi, Wilson | Lakshmi, Wilson
Y | Y |  | End Lever Tuner Mechanical Frame Inventory | L2HE-INV-TUNC | R1 |  |  | 2021-05-14 |  | MDICKEY | CBARNES | POWEN | HOGAN |  | kwilson,hogan | cheng,fischer,powen | cheng,fischer
Y | Y |  | L2HE Extended Cold Tuner Inventory Traveler | L2HE-INV-TUNCX | R1 |  |  | 2021-05-14 |  | MDICKEY | CBARNES |  | HOGAN | POWEN | kwilson,hogan | cheng,fischer,powen | cheng,fischer
Y | Y |  | Upper Cold Mass CMA Inventory | L2HE-INV-UCM | R1 |  |  | 2021-05-18 |  | MDICKEY | CBARNES |  | HOGAN
Y | Y |  | CM Vacuum Vessel Inventory | L2HE-INV-VV | R1 |  |  | 2021-05-18 |  | MDICKEY | CBARNES |  | HOGAN
|  |  | Cryomodule Acceptance Test LERF | L2HE-LERF-CM-ACTS | R1 |  |  | 2021-09-01 |  | DRURY |  |  | HOGAN
|  |  | Production Cryomodule Demagnetization | L2HE-LERF-CM-DMAG | R1 |  |  | 2021-07-31 |  | CHENG | FISCHER |  | HOGAN | CHENG | Wilson, Hogan | Fischer, Cheng | Fischer, Cheng
| Y |  | Cavity Non-conformance Report | L2HE-NCR | R12 |  |  |  |  | MEGAN | BOOKWALT |  | MCEWEN
Y |  |  | Copper Plated String Components Cleaning Procedure | L2HE-PR-CHEM-CST-DEGR | R1 |  | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-247435/L2HE-PR-CHEM-CST-DEGR-R1.pdf |  |  | Ganey | Mitchell | Fiedler | Hogan
Y |  |  | FPC WARM PART PROCEDURE | L2HE-PR-CMA-FPCW-INSP | R1 |  | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-244733/L2HE-PR-CMA-FPCW-INSP-R1.pdf
Y |  |  |  | L2HE-PR-INSP-FPCC | R1 |  | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-243519/L2HE-PR-INSP-FPCC-R1.pdf
Y |  |  | Inspection Procedure for LCLS-II-HE Cold Fundamental Power Coupler | L2HE-PR-INSP-FPCC | R2 |  | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-246229/L2HE-PR-INSP-FPCC-R2.pdf | 2021-05-24 | 2020-05-15
Y |  |  | Production Cavity Vertical Testing Procedure | L2HE-PR-VTA-CAV-VTRF | R1 |  | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-247438/L2HE-PR-VTA-CAV-VTRF-R1.docx | 2021-05-21 |  | C. WILSON | K. DAVIS |  | K. WILSON
Y | Y |  | Cavity RF Inspection | L2HE-TUNE-CAV-RFIN | R1 |  |  | 2021-05-01 |  |  |  |  | HOGAN |  |  |  |  | CAV
Y | Y |  | Cavity RF Inspection | L2HE-TUNE-CAV-RFIN | R2 |  |  | 2021-05-01 |  |  |  |  | HOGAN |  |  |  |  | CAV
|  |  | Cavity HOM Measurements and Tuning | L2HE-TUNE-HOM | R1 |  |  | 2021-11-01 |  | FOREHAND | OVERTON |  | KWILSON
Y | Y |  | Cavity Cooldown | L2HE-VTA-CAV-COOL | R1 | VTA SOP | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-42664/A-09-001-SOP%20Operation%20of%20the%20Test%20Lab%20VTA%20Document-21542%5B1%5D.pdf | 2021-05-01 |  | JTKENT | HANNESV |  | KWILSON |  | hogan,kwilson | hogan,kwilson | hogan,kwilson,kdavis,jtkent
[6 empty] | VTA Cryo Procedures | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-42665/VTA%20Cryo%20Use%20Procedures%2011132008%5B1%5D.pdf
|  | X | Cavity Production VTA HOM Survey (PROCEDURES NEEDED) | L2HE-VTA-CAV-HOM | R1 |  |  | 2021-05-21 |  | POWEN | HANNESV |  | KWILSON
Y | Y |  | Cavity VTA Test | L2HE-VTA-CAV-VTRF | R1 | VTA SOP | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-27461/A-09-001-SOP%20Operation%20of%20the%20Test%20Lab%20VTA%20Document-21542.pdf | 2021-05-01 |  | JTKENT | HANNESV |  | KWILSON
[6 empty] | LCLSII VTA RF Testing Procedure | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-241341/CP-L2HE-VTA-CAV-VTRF-R1.docx
[6 empty] | 9-Cell Quench Analysis | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-148149/L2_xyzModeAnalysismm_dd_yyyy.xlsx
[6 empty] | Excel spreadsheet template for VTA RF measurements | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-98189/SpreadsheetTemplate%20for%20STP-CAV-VTRF_12Nov2014.xlsm
Y | Y |  | Cavity Field Probe Feedthru Receiving Inspection | L2HE-VTA-FPFT-CSHK | R1 | Drawing GMM-9434A | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-225208/GMM-B9434A.pdf | 2020-10-22 |  | HKPARK | FOREHAND | JTKENT | KWILSON | HKPARK | Ari, Reece | Park, Wilson | Park, Wilson
Y | Y |  | Cavity HOM Feedthru Receiving Inspection | L2HE-VTA-HMFT-CSHK | R1 | Drawing GMM-9433A | https://jlabdoc.jlab.org/docushare/dsweb/Get/Document-225207/GMM-B9433A.pdf | 2020-10-23 |  | HKPARK | FOREHAND | JTKENT | KWILSON | HKPARK | Ari, Reece | Park, Wilson | Park, Wilson

## TECH REPS
System | JLab | EXPECTED 1ST DELIVERY? | VENDOR DOCUMENTATION | FNAL | SLAC
Dressed Cavities | John Vannekate/ Charlie Reece |  |  | Mattia Checchin / Chuck Grimm | Dan Gonnella
Feedthroughs | Liang |  |  | Mattia Checchin / Chuck Grimm | Dan Gonnella
Couplers | Naeem Huque |  |  | Ken Premo | Jeff Tice
(Nikolay Solyak – SME)
Cavity String Bellows and Spools | Matt Marchlik |  |  | Ken Premo / Andrei Lunin | Maniscalco
Cavity String Hardware and Seals | Mike Dickey |  |  | Damon Bice | Maniscalco
Magnet | Lakshmi Lalitha |  |  | John Amann | Tommy Hiatt
BPM | HyeKyoung Park |  |  | Andrei Lunin | Tommy Hiatt
Gate Valves | David Savransky |  |  | Damon Bice | Tommy Hiatt
2-Phase Pipe Components | Adam O’Brien |  |  | Chuck Grimm | Tommy Hiatt
End Lever Tuner | Peter Owen |  |  | Yuriy Pischalnikov | Maniscalco
Magnetic Shielding | Gary Cheng |  |  | Saravan Chandrasekaran / Yi Xie | Maniscalco
Cold Mass and Components | Gary Cheng |  |  | Ken Premo | Dan Gonnella
Vacuum Vessel and Components | Gary Cheng |  |  | Ken Premo | Dan Gonnella
Instrumentation | Larry King |  |  | Fred Lewis | Maniscalco
Cryogenic Valves | Justin Kent |  |  | Greg Johnson | Tommy Hiatt
Vacuum Equipment | Adam O’Brien |  |  | Ken Premo | Tommy Hiatt

## ASSY CHART
FORECAST AS OF August 1 2021 DD
FNAL Start | Var BL | FNAL Finish | Var BL | 1.3 GHz vCM | JLAB Start | Var BL | JLAB Finish | Var BL | Major Processes for HE | Start date
23-Sep-20 A | -11 | 05-Nov-20 A | -15 | WS1 | N/A | N/A | N/A | N/A | Cavity Prep & Test | 2020-11-17 | 2021-09-01
06-Nov-20 A | -16 | 27-Jan-21 A | -44 | WS2 | N/A | N/A | N/A | N/A | String Assembly | 2021-07-27 | 2021-12-01
28-Jan-21 A | -45 | 10-Feb-21 A | -31 | WS3 | N/A | N/A | N/A | N/A | CM Assembly | 2021-05-15 | 2022-02-01
11-Feb-21 A | -32 | 12-Feb-21 A | -27 | WS4 | N/A | N/A | N/A | N/A | Testing | 2022-05-17 | 2021-10-01
16-Feb-21 A | -28 | 26-Feb-21 A | -12 | WS5 | N/A | N/A | N/A | N/A
09-Mar-21 A | -16 | 2021-10-29 | -82 | Testing | N/A | N/A | N/A | N/A
FNAL Start | Var BL | FNAL Finish | Var BL | 1.3 GHz CM1 (FA) | JLAB Start | Var BL | JLAB Finish | Var BL
2021-12-06 | -22 | 2021-12-28 | -22 | WS1 | 2022-02-24 | -54 | 2022-04-13 | -54
2021-12-29 | -22 | 2022-01-25 | -22 | WS2 | 2022-04-14 | -54 | 2022-06-09 | -54
2022-01-26 | -22 | 2022-02-25 | -22 | WS3 | 2022-06-10 | -54 | 2022-08-05 | -54
2022-02-28 | -22 | 2022-03-07 | -22 | WS4 | 2022-08-08 | -54 | 2022-10-03 | -54
2022-03-08 | -22 | 2022-03-30 | -22 | WS5 | 2022-10-04 | -54 | 2022-11-30 | -54
2022-04-04 | -22 | 2022-05-27 | -22 | Testing | 2022-12-01 | -54 | 2023-02-09 | -54
FNAL Start | Var BL | FNAL Finish | Var BL | 1.3 GHz CM2 | JLAB Start | Var BL | JLAB Finish | Var BL
2022-03-01 | -38 | 2022-03-21 | -38 | WS1 | 2022-04-14 | -54 | 2022-06-02 | -54
2022-03-22 | -38 | 2022-04-20 | -38 | WS2 | 2022-06-10 | -54 | 2022-08-05 | -54
2022-04-21 | -38 | 2022-05-20 | -38 | WS3 | 2022-08-08 | -54 | 2022-10-03 | -54
2022-05-23 | -38 | 2022-05-31 | -38 | WS4 | 2022-10-04 | -54 | 2022-11-30 | -54
2022-06-01 | -38 | 2022-06-23 | -38 | WS5 | 2022-12-01 | -54 | 2023-02-09 | -54
2022-06-28 | -38 | 2022-08-16 | -38 | Testing | 2023-02-10 | -54 | 2023-04-07 | -54
FNAL Start | Var BL | FNAL Finish | Var BL | 1.3 GHz CM3 | JLAB Start | Var BL | JLAB Finish | Var BL
2022-04-12 | -38 | 2022-05-02 | -38 | WS1 | 2022-06-10 | -54 | 2022-07-29 | -54
2022-05-03 | -38 | 2022-06-02 | -38 | WS2 | 2022-08-08 | -54 | 2022-10-03 | -54
2022-06-03 | -38 | 2022-07-05 | -38 | WS3 | 2022-10-04 | -54 | 2022-11-30 | -54
2022-07-06 | -38 | 2022-07-13 | -38 | WS4 | 2022-12-01 | -54 | 2023-02-09 | -54
2022-07-14 | -38 | 2022-08-05 | -38 | WS5 | 2023-02-10 | -54 | 2023-04-07 | -54
2022-08-17 | -38 | 2022-10-05 | -38 | Testing | 2023-04-10 | -54 | 2023-06-05 | -54
FNAL Start | Var BL | FNAL Finish | Var BL | 1.3 GHz CM4 | JLAB Start | Var BL | JLAB Finish | Var BL
2022-05-25 | -27 | 2022-06-15 | -27 | WS1 | 2022-08-08 | -54 | 2022-09-26 | -54
2022-06-16 | -27 | 2022-07-18 | -27 | WS2 | 2022-10-04 | -54 | 2022-11-30 | -54
2022-07-19 | -27 | 2022-08-17 | -27 | WS3 | 2022-12-01 | -54 | 2023-02-09 | -54
2022-08-18 | -27 | 2022-08-25 | -27 | WS4 | 2023-02-10 | -54 | 2023-04-07 | -54
2022-08-26 | -27 | 2022-09-20 | -27 | WS5 | 2023-04-10 | -54 | 2023-06-05 | -54
2022-10-06 | -36 | 2022-11-23 | -36 | Testing | 2023-06-06 | -54 | 2023-07-18 | -54
FNAL Start | Var BL | FNAL Finish | Var BL | 1.3 GHz CM5 | JLAB Start | Var BL | JLAB Finish | Var BL
2022-07-08 | -27 | 2022-07-28 | -27 | WS1 | 2022-10-04 | -54 | 2022-11-21 | -54
2022-07-29 | -27 | 2022-08-29 | -27 | WS2 | 2022-12-01 | -54 | 2023-02-09 | -54
2022-08-30 | -27 | 2022-09-29 | -27 | WS3 | 2023-02-10 | -54 | 2023-04-07 | -54
2022-09-30 | -27 | 2022-10-07 | -27 | WS4 | 2023-04-10 | -54 | 2023-06-05 | -54
2022-10-10 | -27 | 2022-11-01 | -27 | WS5 | 2023-06-06 | -54 | 2023-08-01 | -54
2022-11-28 | -36 | 2023-01-19 | -36 | Testing | 2023-08-02 | -54 | 2023-09-13 | -54
FNAL Start | Var BL | FNAL Finish | Var BL | 1.3 GHz CM6 | JLAB Start | Var BL | JLAB Finish | Var BL
2022-08-19 | -27 | 2022-09-09 | -27 | WS1 | 2022-12-01 | -54 | 2023-02-02 | -54
2022-09-12 | -27 | 2022-10-11 | -27 | WS2 | 2023-02-10 | -54 | 2023-04-07 | -54
2022-10-12 | -27 | 2022-11-10 | -27 | WS3 | 2023-04-10 | -54 | 2023-06-05 | -54
2022-11-11 | -27 | 2022-11-18 | -27 | WS4 | 2023-06-06 | -54 | 2023-08-01 | -54
2022-11-21 | -27 | 2022-12-15 | -27 | WS5 | 2023-08-02 | -54 | 2023-09-27 | -54
2023-01-20 | -36 | 2023-03-10 | -36 | Testing | 2023-09-28 | -54 | 2023-11-08 | -54
FNAL Start | Var BL | FNAL Finish | Var BL | 1.3 GHz CM7 | JLAB Start | Var BL | JLAB Finish | Var BL
2022-10-03 | -27 | 2022-10-21 | -27 | WS1 | 2023-02-10 | -54 | 2023-03-31 | -54
2022-10-24 | -27 | 2022-11-22 | -27 | WS2 | 2023-04-10 | -54 | 2023-05-19 | -54
2022-11-23 | -27 | 2022-12-28 | -27 | WS3 | 2023-06-06 | -54 | 2023-07-18 | -54
2022-12-29 | -27 | 2023-01-06 | -27 | WS4 | 2023-08-02 | -54 | 2023-09-13 | -54
2023-01-09 | -27 | 2023-02-01 | -27 | WS5 | 2023-09-28 | -54 | 2023-11-08 | -54
2023-03-13 | -36 | 2023-04-28 | -36 | Testing | 2023-11-09 | -54 | 2024-01-08 | -54
FNAL Start | Var BL | FNAL Finish | Var BL | 1.3 GHz CM8 | JLAB Start | Var BL | JLAB Finish | Var BL
2022-11-14 | -27 | 2022-12-06 | -27 | WS1 | 2023-04-10 | -54 | 2023-05-26 | -54
2022-12-07 | -27 | 2023-01-10 | -27 | WS2 | 2023-05-30 | -54 | 2023-07-11 | -54
2023-01-11 | -27 | 2023-02-10 | -27 | WS3 | 2023-07-19 | -54 | 2023-08-29 | -54
2023-02-13 | -27 | 2023-02-21 | -27 | WS4 | 2023-09-14 | -54 | 2023-10-25 | -54
2023-02-22 | -27 | 2023-03-16 | -27 | WS5 | 2023-11-09 | -54 | 2024-01-08 | -54
2023-05-01 | -36 | 2023-06-19 | -36 | Testing | 2024-01-09 | -54 | 2024-02-21 | -54
FNAL Start | Var BL | FNAL Finish | Var BL | 1.3 GHz CM9 | JLAB Start | Var BL | JLAB Finish | Var BL
2023-01-02 | -27 | 2023-01-23 | -27 | WS1 | 2023-06-06 | -54 | 2023-07-25 | -54
2023-01-24 | -27 | 2023-02-23 | -27 | WS2 | 2023-07-26 | -54 | 2023-09-06 | -54
2023-02-24 | -27 | 2023-03-27 | -27 | WS3 | 2023-09-07 | -54 | 2023-10-18 | -54
2023-03-28 | -27 | 2023-04-04 | -27 | WS4 | 2023-10-26 | -54 | 2023-12-08 | -54
2023-04-05 | -27 | 2023-04-27 | -27 | WS5 | 2024-01-09 | -54 | 2024-02-21 | -54
2023-06-20 | -36 | 2023-08-08 | -36 | Testing | 2024-02-22 | -54 | 2024-04-03 | -54
FNAL Start | Var BL | FNAL Finish | Var BL | 1.3 GHz CM10 | JLAB Start | Var BL | JLAB Finish | Var BL
2023-02-14 | -27 | 2023-03-07 | -27 | WS1 | 2023-07-26 | -54 | 2023-09-13 | -54
2023-03-08 | -27 | 2023-04-06 | -27 | WS2 | 2023-09-14 | -54 | 2023-10-25 | -54
2023-04-07 | -27 | 2023-05-08 | -27 | WS3 | 2023-10-26 | -54 | 2023-12-08 | -54
2023-05-09 | -27 | 2023-05-16 | -27 | WS4 | 2023-12-11 | -54 | 2024-02-06 | -54
2023-05-17 | -27 | 2023-06-09 | -27 | WS5 | 2024-02-22 | -54 | 2024-04-03 | -54
2023-08-09 | -36 | 2023-09-27 | -36 | Testing | 2024-04-04 | -54 | 2024-05-15 | -54
FNAL Start | Var BL | FNAL Finish | Var BL | 1.3 GHz CM11 | JLAB Start | Var BL | JLAB Finish | Var BL
2023-08-14 | 0 | 2023-09-01 | 0 | WS1 | 2023-09-14 | -14 | 2023-11-01 | -14
2023-09-05 | 0 | 2023-10-04 | 0 | WS2 | 2023-11-02 | -11 | 2024-01-16 | -11
2023-10-05 | 0 | 2023-11-03 | 0 | WS3 | 2024-01-17 | -11 | 2024-03-13 | -11
2023-11-06 | 9 | 2023-11-13 | 9 | WS4 | 2024-03-14 | -11 | 2024-05-08 | -11
2023-11-14 | 9 | 2023-12-08 | 9 | WS5 | 2024-05-09 | -11 | 2024-07-05 | -11
2023-12-15 | 7 | 2024-02-07 | 7 | Testing | 2024-07-08 | -11 | 2024-08-16 | -11
FNAL Start | Var BL | FNAL Finish | Var BL | 1.3 GHz CM12 | JLAB Start | Var BL | JLAB Finish | Var BL
2023-09-26 | 0 | 2023-10-16 | 0 | WS1 | N/A | N/A | N/A | N/A
2023-10-17 | 0 | 2023-11-15 | 0 | WS2 | N/A | N/A | N/A | N/A
2023-11-16 | 0 | 2023-12-19 | 0 | WS3 | N/A | N/A | N/A | N/A
2023-12-20 | 0 | 2023-12-28 | 0 | WS4 | N/A | N/A | N/A | N/A
2024-01-02 | 0 | 2024-01-25 | 0 | WS5 | N/A | N/A | N/A | N/A
2024-02-08 | 7 | 2024-03-28 | 7 | Testing | N/A | N/A | N/A | N/A
FNAL Start | Var BL | FNAL Finish | Var BL | 1.3 GHz CM13 | JLAB Start | Var BL | JLAB Finish | Var BL
2023-11-07 | 0 | 2023-11-29 | 0 | WS1 | N/A | N/A | N/A | N/A
2023-11-30 | 0 | 2024-01-03 | 0 | WS2 | N/A | N/A | N/A | N/A
2024-01-04 | 0 | 2024-02-05 | 0 | WS3 | N/A | N/A | N/A | N/A
2024-02-06 | 0 | 2024-02-13 | 0 | WS4 | N/A | N/A | N/A | N/A
2024-02-14 | 0 | 2024-03-08 | 0 | WS5 | N/A | N/A | N/A | N/A
2024-03-29 | 7 | 2024-05-16 | 7 | Testing | N/A | N/A | N/A | N/A
NOTE: 1) Var BL means Variance to Baseline Start or Finish dates. If the number is “0” the forecast dates are right on schedule with the baseline schedule. If the number is a ”+” the forecast dates are ahead of the baseline schedule by that many work days. If the number is a “-” the forecast dates are behind the baseline schedule by that many work days. 2) Shaded cell EQUALS COMPLETED

## HE Cav Names
LCLS II HE Cavity Naming Convention | 2021-05-14
Single Cells
material and/or furnace qualification
HE-SC-XX
Nine Cells
Cavities from LCLS II Production (previously tested)
HE-CAV0XXX
New Production Cavities
HE-CAVRXXX

## DELIVERIES
Component | FNAL | JLAB | SLAC | QTY | SOTR | Date for First Lot at JLAB
Niobium (Prototype) - existing cavities | NA | [5 empty] | L2HE-INV-*
Niobium (Production) | X | [5 empty] | AMGV
Cavities (Prototype) - existing cavities | NA |  |  |  | Ari Palczewski |  | FPCWG
Helium Vessels (Prototype) | X |  |  |  | Ari Palczewski |  | PIEZO
Cavities w/Helium Vessels -VTS Ready (Production) |  | X |  | 80 | Ari Palczewski | 2021-04-29
Cavity Feedthroughs |  | X |  |  | Ari Palczewski | 2020-11-02
Cavity Flanges & Assoc. Hardware/Seals (VTS & HTS compatible) |  | X |  |  |  |  | SNs From PRIMeS
Fundamental Power Coupler (FPC) |  |  | X |  |  | 2021-05-28 | AMGV*
Cavity String Interconnecting Bellows |  | X |  |  | Matt Marchlick | 2021-04-19 | AV15
Cavity String Assembly Hardware & Seals | X |  |  |  | Mike Dickey |  | C12P
SC Magnet Assembly | X |  |  |  | Lakshmi Latitha | 2021-02-12 | CAV
Beam Position Monitor (BPM) | X |  |  |  | HyeKyoung Park | 2021-02-22 | CDV
Gate Valves |  | X |  |  | David Savransky | 2021-04-09 | CFL
Beamline Vac. Monitoring Manifold & Gauge | X | [5 empty] | FPCWG*
Two-phase Pipe Bellows | X |  |  |  | Gary Cheng ? |  | FPFT
Tuner, actuator, piezos (Prototype) | X |  |  |  | Peter Owen | 2021-07-19 | FT06P
Tuner , actuator, piezos (Production) |  | X |  |  | Peter Owen |  | HMFT
Magnetic Shielding | X |  |  | 10 | Gary Cheng | 2021-08-27 | IP75SD
GRHP Sub-assembly | X | [5 empty] | JTV
Vacuum Vessel | X |  |  | 10 | Gary Cheng | 2021-03-23 | TSCPLR
Coupler Pumping Lines & Pumps (ion+TSP) + vacuum gauges | X | [5 empty] | TSHMSM
Instrumentation | X |  |  |  | Larry King
Liquid Level Probes & JT Valve | X
Beamline Interconnect Parts including Aluminum Heat Shields | X
HOM Absorber |  | X |  |  |  | 2021-01-12
Shipping Frames & End Caps + Shock Log Devices |  | X
X = Lead Lab (to be confrimed)
BLAs (will JLAB be required to inspect & Process these ? ) |  |  |  |  | ??? | 2021-04-28
Cyrogenic Valves |  |  |  |  | Naeem Huque
Vacuum Equipment |  |  |  |  | Gary Cheng
JT & Cool Down Valves |  |  |  |  | ?? | 2021-04-20

## TIFFANY
Below is my understanding of the status of all the travelers we need in place now for the refurbishment cavities currently working towards a VTRF (CAV040, 295, and 331). The Pansophy team has the official tracking on the status of all the L2HE travelers and procedures so they can provide a better / corrected status update if needed.
Process Step | L2HE Traveler ID | Based on Traveler | L2HE Traveler Status | Comments
RF Inspection | L2HE-TUNE-CAV-RFIN |  | Issued | for as-received from vendor; use D3 for refurbishment cavities
CMM | L2HE-INSP-CAV |  | Issued | for as-received from vendor; use D3 for refurbishment cavities
Dual USC (Liquinox + DI) | L2HE-CHEM-CAV-USC | C100R-CAV-CHEM-USC | Draft needed based on C100R
2-pass HPR | L2HE-CHEM-CAV-HPR | C100R-CAV-CHEM-HPR | Draft needed based on C100R
First Assembly (FP, FPC, HOM) | L2HE-CLNRM-CAV-FRST | L2PRD-CAV-ASSY-FRST | Draft needed based on L2PRD
Second Assy | L2HE-CLNRM-CAV-SCND | L2PRD-CAV-ASSY-SCND | Draft needed based on L2PRD
Transfer to Test Stand | L2HE-CLNRM-CAV-TSTD and L2HE-CLNRM-CAV-TSTD-D5 | L2PRD-CAV-TRANS-TSTD and L2PRD-CAV-TRANS-TSTD-D5 | Draft needed based on L2PRD
Cooldown to 2K (including sensor install and checkout) | L2HE-VTA-CAV-COOL | L2PRD-CAV-VTA-COOL | Justin has draft; needs to be uploaded to DocuShare | L2PRD parameters need to be updated for L2HE
VTRF | L2HE-VTA-CAV-VTRF | L2PRD-CAV-VTRF | In Approvals | L2PRD parameters need to be updated for L2HE
HOM Survey | L2HE-VTA-CAV-HOM | L2PRD-CAV-VTA-HOM | Draft needed based on L2PRD
· Italicized L2HE Traveler IDs are traveler that do not currently exist and are my best guess at what the ID needs to be based on the current naming convention guidance.
Tiffany Ganey

## COMPARISON
L2HE |  | L2PRD | MASTER LIST L2PRD | MASTER LIST L2HE
CHEMISTRY |  |  | L2PRD-CAV-ASSY-FRST | L2HE-CHEM-CAV-DEGR
L2HE-CHEM-CAV-DEGR |  |  | L2PRD-CAV-ASSY-SCND | L2HE-CHEM-CAV-HEP
L2HE-CHEM-CAV-HEP |  |  | L2PRD-CAV-HOM-TUNE | L2HE-CHEM-CAV-HPR
L2HE-CHEM-CAV-HPR |  |  | L2PRD-CAV-INSP-BLA | L2HE-CHEM-CAV-USC
L2HE-CHEM-CAV-USC |  |  | L2PRD-CAV-INSP-CAV | L2HE-CHEM-COMP-DEGR
L2HE-CHEM-COMP-DEGR |  |  | L2PRD-CAV-INSP-FPC | L2HE-CHEM-COMP-HPR
L2HE-CHEM-COMP-HPR |  |  | L2PRD-CAV-INSP-FPCWG | L2HE-CHEM-COMP-LAP
L2HE-CHEM-COMP-LAP |  |  | L2PRD-CAV-INSP-FPFT | L2HE-CLNRM-CAV-ASSY1
|  |  | L2PRD-CAV-INSP-HELV | L2HE-CLNRM-CAV-ASSY2
CLEAN ROOM |  |  | L2PRD-CAV-INSP-HMFT | L2HE-CLNRM-CAV-LEAK
L2HE-CLNRM-CAV-ASSY1 |  | L2PRD-CAV-ASSY-FRST | L2PRD-CAV-RECV-CAV | L2HE-CLNRM-CAV-TSTD
L2HE-CLNRM-CAV-ASSY2 |  | L2PRD-CAV-ASSY-SCND | L2PRD-CAV-RECV-CAVEZ2-HLDPT1 | L2HE-CLNRM-CAV-TSTD5
L2HE-TUNE-HOM |  | L2PRD-CAV-HOM-TUNE | L2PRD-CAV-RECV-CAVEZ2-HLDPT2 | L2HE-CLNRM-FPCC-INSP
L2HE-TUNE-CAV-RFIN |  | L2PRD-CAV-RFIN | L2PRD-CAV-RECV-CAVEZ2-HLDPT3 | L2HE-CMA-BLBP-LEAK
L2HE-CLNRM-CAV-LEAK |  |  | L2PRD-CAV-RECV-CAVEZ3-HLDPT2 | L2HE-CMA-BLBS-LEAK
L2HE-CLNRM-CAV-TSTD |  | L2PRD-CAV-TRANS-TSTD | L2PRD-CAV-RECV-CAVEZ4-HLDPT2 | L2HE-CMA-BLBU-LEAK
L2HE-CLNRM-CAV-TSTD5 |  | L2PRD-CAV-TRANS-TSTD-D5 | L2PRD-CAV-RECV-CAVEZ-HLDPT1 | L2HE-CMA-BLXD-LEAK
|  | L2PRD-CM-DISA-FPCW | L2PRD-CAV-RECV-CAVEZ-HLDPT2 | L2HE-CMA-FNAL
L2HE-CST-ASSY |  | L2PRD-CST-ASSY | L2PRD-CAV-RECV-CAVEZ-HLDPT3 | L2HE-CMA-FPCW
L2HE-CST-ASSY-BPM |  | L2PRD-CST-ASSY-BPM | L2PRD-CAV-RECV-CAV-HLDPT1 | L2HE-CMA-FPCW-DISA
L2HE-CST-ASSY-LEAK |  | L2PRD-CST-ASSY-LEAK | L2PRD-CAV-RECV-CAV-HLDPT2 | L2HE-CMA-FPCW-INSP
L2HE-CST-LEAK-AMGV |  | L2PRD-CST-LEAK-AMGV | L2PRD-CAV-RECV-CAV-HLDPT3 | L2HE-CMA-FPFT-LEAK
moved to insp |  | L2PRD-CST-MAG-QUAD | L2PRD-CAV-RECV-DRT | L2HE-CMA-FRST
L2HE-CLNRM-FPCC-INSP |  |  | L2PRD-CAV-RECV-FPC | L2HE-CMA-HMFT-LEAK
TESTING |  |  | L2PRD-CAV-RECV-FPCWG | L2HE-CMA-REW
L2HE-VTA-CAV-COOL |  | L2PRD-CAV-VTA-COOL | L2PRD-CAV-RECV-FPFT | L2HE-CMA-RFIT
L2HE-VTA-CAV-HOM |  | L2PRD-CAV-VTA-HOM | L2PRD-CAV-RECV-HELV | L2HE-CMA-SCND
L2HE-VTA-CAV-VTRF |  | L2PRD-CAV-VTRF | L2PRD-CAV-RECV-HMFT | L2HE-CMA-SHIP
L2HE-VTA-FPFT-CSHK |  |  | L2PRD-CAV-RECV-NB55 | L2HE-CMA-UCM-DMAG
L2HE-VTA-HMFT-CSHK |  |  | L2PRD-CAV-RFIN | L2HE-CMA-UCM-INSP
|  | L2PRD-CM-ACTS | L2PRD-CAV-TRANS-TSTD | L2HE-CMA-VV
L2HE-LERF-CM-ACTS |  | L2PRD-CM-ACTS-LERF | L2PRD-CAV-TRANS-TSTD-D5 | L2HE-CMA-VV-INSP
|  | L2PRD-CM-ACTS-PREP | L2PRD-CAV-VTA-COOL | L2HE-CST-ASSY
L2HE-LERF-CM-DMAG |  | L2PRD-CM-DMAG-LERF | L2PRD-CAV-VTA-HOM | L2HE-CST-ASSY-BPM
|  |  | L2PRD-CAV-VTRF | L2HE-CST-ASSY-LEAK
CRYOMODULE |  |  | L2PRD-CM-ACTS | L2HE-CST-LEAK-AMGV
L2HE-CMA-FNAL |  | L2PRD-CM-ASSY-FNAL | L2PRD-CM-ACTS-LERF | L2HE-CWI-UCM
L2HE-CMA-FPCW |  | L2PRD-CM-ASSY-FPCW | L2PRD-CM-ACTS-PREP | L2HE-D3
L2HE-CMA-FRST |  | L2PRD-CM-ASSY-FRST | L2PRD-CM-ASSY-FNAL | L2HE-INSP-BLBP
L2HE-CMA-REW |  | L2PRD-CM-ASSY-REW | L2PRD-CM-ASSY-FNAL | L2HE-INSP-BLBS
L2HE-CMA-RFIT |  | L2PRD-CM-ASSY-RFIT | L2PRD-CM-ASSY-FPCW | L2HE-INSP-BLBU
L2HE-CMA-SCND |  | L2PRD-CM-ASSY-SCND | L2PRD-CM-ASSY-FRST | L2HE-INSP-BLXD
L2HE-CMA-SHIP |  | L2PRD-CM-ASSY-SHIP | L2PRD-CM-ASSY-REW | L2HE-INSP-CAV
L2HE-CMA-VV |  | L2PRD-CM-ASSY-VV | L2PRD-CM-ASSY-RFIT | L2HE-INSP-CDV
|  | L2PRD-CM-DMAG-CM | L2PRD-CM-ASSY-SCND | L2HE-INSP-CFL
L2HE-CMA-BLBP-LEAK |  |  | L2PRD-CM-ASSY-SHIP | L2HE-INSP-FPCWG
L2HE-CMA-BLBS-LEAK |  |  | L2PRD-CM-ASSY-VV | L2HE-INSP-FPFT
L2HE-CMA-BLBU-LEAK |  |  | L2PRD-CM-DISA-FPCW | L2HE-INSP-HMFT
L2HE-CMA-BLXD-LEAK |  |  | L2PRD-CM-DMAG-CM | L2HE-INSP-IMAG
L2HE-CMA-FPFT-LEAK |  |  | L2PRD-CM-DMAG-LERF | L2HE-INSP-IROD2L
L2HE-CMA-HMFT-LEAK |  |  | L2PRD-CM-DMAG-UCM | L2HE-INSP-IROD2P
L2HE-CMA-FPCW-DISA |  |  | L2PRD-CM-DMAG-VV | L2HE-INSP-JTV
L2HE-CMA-UCM-DMAG |  |  | L2PRD-CM-INSP-BLA | L2HE-INSP-JTVTK
L2HE-CMA-FPCW-INSP |  | MOVED FROM INSP | L2PRD-CM-INSP-BLAV | L2HE-INSP-PIEZO
L2HE-CMA-UCM-INSP |  | MOVED FROM INSP | L2PRD-CM-INSP-BP2PH | L2HE-INSP-QUAD
L2HE-CMA-VV-INSP |  | MOVED FROM INSP | L2PRD-CM-INSP-CDV | L2HE-INSP-SM
|  |  | L2PRD-CM-INSP-DK12P | L2HE-INSP-TUNC
|  |  | L2PRD-CM-INSP-DK22P | L2HE-INSR
INSPECTIONS |  |  | L2PRD-CM-INSP-EDCP | L2HE-INV-AMGV
|  | L2PRD-CM-INSP-BLA | L2PRD-CM-INSP-FDCP | L2HE-INV-BLBP
|  | L2PRD-CAV-INSP-BLA | L2PRD-CM-INSP-FPCW | L2HE-INV-BLBS
|  | L2PRD-CM-INSP-BLAV | L2PRD-CM-INSP-FPCWG | L2HE-INV-BLBU
|  | L2PRD-CM-INSP-BP2PH | L2PRD-CM-INSP-IMAG | L2HE-INV-BLXD
L2HE-INSP-CDV |  | L2PRD-CM-INSP-CDV | L2PRD-CM-INSP-IROD2L | L2HE-INV-CAV
| 0 | L2PRD-CM-INSP-DK12P | L2PRD-CM-INSP-IROD2P | L2HE-INV-FPCC
| 0 | L2PRD-CM-INSP-DK22P | L2PRD-CM-INSP-JTV | L2HE-INV-FPCW
| 0 | L2PRD-CM-INSP-EDCP | L2PRD-CM-INSP-JTVTK | L2HE-INV-FPCWG
| 0 | L2PRD-CM-INSP-FDCP | L2PRD-CM-INSP-LLDS | L2HE-INV-FPFT
moved to CMA |  | L2PRD-CM-INSP-FPCW | L2PRD-CM-INSP-LLNDS | L2HE-INV-HMFT
|  | L2PRD-CM-INSP-FPCWG | L2PRD-CM-INSP-LLNUS | L2HE-INV-IMAG
L2HE-INSP-FPCWG |  | L2PRD-CAV-INSP-FPCWG | L2PRD-CM-INSP-LLUS | L2HE-INV-JTVTK
L2HE-INSP-IMAG |  | L2PRD-CM-INSP-IMAG | L2PRD-CM-INSP-MCCLA | L2HE-INV-PIEZO
L2HE-INSP-IROD2L |  | L2PRD-CM-INSP-IROD2L | L2PRD-CM-INSP-PEC2P | L2HE-INV-QUAD
L2HE-INSP-IROD2P |  | L2PRD-CM-INSP-IROD2P | L2PRD-CM-INSP-UCM | L2HE-INV-TUNC
L2HE-INSP-JTV |  | L2PRD-CM-INSP-JTV | L2PRD-CM-INSP-VV | L2HE-INV-TUNCX
L2HE-INSP-JTVTK |  | L2PRD-CM-INSP-JTVTK | L2PRD-CM-RECV | L2HE-INV-UCM
|  | L2PRD-CM-INSP-LLDS | L2PRD-CM-RECV-BP2PH | L2HE-INV-VV
|  | L2PRD-CM-INSP-LLNDS | L2PRD-CM-RECV-C12P | L2HE-LERF-CM-ACTS
|  | L2PRD-CM-INSP-LLNUS | L2PRD-CM-RECV-CDV | L2HE-LERF-CM-DMAG
|  | L2PRD-CM-INSP-LLUS | L2PRD-CM-RECV-DCXCU | L2HE-NCR
|  | L2PRD-CM-INSP-MCCLA | L2PRD-CM-RECV-DCXSD | L2HE-PR-INSP-FPCC
|  | L2PRD-CM-INSP-PEC2P | L2PRD-CM-RECV-DDTCU | L2HE-PR-VTA-CAV-VTRF
MOVED TO CMA |  | L2PRD-CM-INSP-UCM | L2PRD-CM-RECV-DDTSD | L2HE-TUNE-CAV-RFIN
MOVED TO CMA |  | L2PRD-CM-INSP-VV | L2PRD-CM-RECV-DK12P | L2HE-TUNE-HOM
L2HE-INSP-CAV |  | L2PRD-CAV-INSP-CAV | L2PRD-CM-RECV-DK22P | L2HE-VTA-CAV-COOL
MOVED TO CLNRM |  | L2PRD-CAV-INSP-FPC | L2PRD-CM-RECV-FT06P | L2HE-VTA-CAV-HOM
L2HE-INSP-FPFT |  | L2PRD-CAV-INSP-FPFT | L2PRD-CM-RECV-HLS | L2HE-VTA-CAV-VTRF
|  | L2PRD-CAV-INSP-HELV | L2PRD-CM-RECV-IMAG | L2HE-VTA-FPFT-CSHK
L2HE-INSP-HMFT |  | L2PRD-CAV-INSP-HMFT | L2PRD-CM-RECV-IP75SD | L2HE-VTA-HMFT-CSHK
|  | L2PRD-CST-INSP-BLBL | L2PRD-CM-RECV-IROD2L
L2HE-INSP-BLBP |  | L2PRD-CST-INSP-BLBP | L2PRD-CM-RECV-IROD2P
L2HE-INSP-BLBS |  | L2PRD-CST-INSP-BLBS | L2PRD-CM-RECV-JTV
L2HE-INSP-BLBU |  | L2PRD-CST-INSP-BLBU | L2PRD-CM-RECV-JTVTK
L2HE-INSP-BLXD |  | L2PRD-CST-INSP-BLXD | L2PRD-CM-RECV-LLDS
|  | L2PRD-CST-INSP-BLXU | L2PRD-CM-RECV-LLNDS
|  | L2PRD-CST-INSP-BPMFT | L2PRD-CM-RECV-LLNUS
L2HE-INSP-CFL |  | L2PRD-CST-INSP-CFL | L2PRD-CM-RECV-LLUS
L2HE-INSP-TUNC |  | L2PRD-CST-INSP-TUNMC | L2PRD-CM-RECV-MCCLA
L2HE-INSP-SM |  | L2PRD-CST-INSP-TUNMT | L2PRD-CM-RECV-P2PH
L2HE-INSP-PIEZO |  | L2PRD-CST-INSP-TUNPZ | L2PRD-CM-RECV-PEC2P
|  | L2PRD-CST-RINSP-BLBP | L2PRD-CM-RECV-TSCPLR
|  | L2PRD-CST-RINSP-BLBS | L2PRD-CM-RECV-TSHMSM
| 0 | L2PRD-CST-RINSP-BLXD | L2PRD-CM-RECV-UCM
L2HE-INSP-QUAD |  |  | L2PRD-CM-RECV-VV
L2PRD-CST-ASSY
RECEIVING |  |  | L2PRD-CST-ASSY-BPM
L2HE-INV-CAV |  | L2PRD-CAV-RECV-CAV | L2PRD-CST-ASSY-LEAK
|  | L2PRD-CAV-RECV-CAVEZ2-HLDPT1 | L2PRD-CST-INSP-BLBL
|  | L2PRD-CAV-RECV-CAVEZ2-HLDPT2 | L2PRD-CST-INSP-BLBP
|  | L2PRD-CAV-RECV-CAVEZ2-HLDPT3 | L2PRD-CST-INSP-BLBS
|  | L2PRD-CAV-RECV-CAVEZ3-HLDPT2 | L2PRD-CST-INSP-BLBU
|  | L2PRD-CAV-RECV-CAVEZ4-HLDPT2 | L2PRD-CST-INSP-BLXD
|  | L2PRD-CAV-RECV-CAVEZ-HLDPT1 | L2PRD-CST-INSP-BLXU
|  | L2PRD-CAV-RECV-CAVEZ-HLDPT2 | L2PRD-CST-INSP-BPMFT
|  | L2PRD-CAV-RECV-CAVEZ-HLDPT3 | L2PRD-CST-INSP-CFL
|  | L2PRD-CAV-RECV-CAV-HLDPT1 | L2PRD-CST-INSP-TUNMC
|  | L2PRD-CAV-RECV-CAV-HLDPT2 | L2PRD-CST-INSP-TUNMT
|  | L2PRD-CAV-RECV-CAV-HLDPT3 | L2PRD-CST-INSP-TUNPZ
|  | L2PRD-CAV-RECV-DRT | L2PRD-CST-LEAK-AMGV
L2HE-INV-FPCC |  | L2PRD-CAV-RECV-FPC | L2PRD-CST-MAG-QUAD
L2HE-INV-FPCW |  |  | L2PRD-CST-RECV
L2HE-INV-FPCWG |  | L2PRD-CAV-RECV-FPCWG | L2PRD-CST-RECV-AMGV
L2HE-INV-FPFT |  | L2PRD-CAV-RECV-FPFT | L2PRD-CST-RECV-BLA
|  | L2PRD-CAV-RECV-HELV | L2PRD-CST-RECV-BLACRM
L2HE-INV-HMFT |  | L2PRD-CAV-RECV-HMFT | L2PRD-CST-RECV-BLBP
|  | L2PRD-CAV-RECV-NB55 | L2PRD-CST-RECV-BLBS
| 0 | L2PRD-CM-RECV | L2PRD-CST-RECV-BLXD
|  | L2PRD-CM-RECV-BP2PH | L2PRD-CST-RECV-BLXU
| 0 | L2PRD-CM-RECV-C12P | L2PRD-CST-RECV-BPM
|  | L2PRD-CM-RECV-CDV | L2PRD-CST-RECV-BPMFT
|  | L2PRD-CM-RECV-DCXCU | L2PRD-CST-RECV-CFL
|  | L2PRD-CM-RECV-DCXSD | L2PRD-CST-RECV-TUNMC
|  | L2PRD-CM-RECV-DDTCU | L2PRD-CST-RECV-TUNMT
|  | L2PRD-CM-RECV-DDTSD | L2PRD-CST-RECV-TUNPZ
| 0 | L2PRD-CM-RECV-DK12P | L2PRD-CST-RINSP-BLBP
| 0 | L2PRD-CM-RECV-DK22P | L2PRD-CST-RINSP-BLBS
|  | L2PRD-CM-RECV-FT06P | L2PRD-CST-RINSP-BLXD
| 0 | L2PRD-CM-RECV-HLS | L2PRD-D3
L2HE-INV-IMAG |  | L2PRD-CM-RECV-IMAG | L2PRD-INSR
|  | L2PRD-CM-RECV-IP75SD | L2PRD-NCR
| 0 | L2PRD-CM-RECV-IROD2L
| 0 | L2PRD-CM-RECV-IROD2P
L2PRD-CM-RECV-JTV
L2HE-INV-JTVTK |  | L2PRD-CM-RECV-JTVTK
L2PRD-CM-RECV-LLDS
L2PRD-CM-RECV-LLNDS
L2PRD-CM-RECV-LLNUS
L2PRD-CM-RECV-LLUS
L2PRD-CM-RECV-MCCLA
L2PRD-CM-RECV-P2PH
L2PRD-CM-RECV-PEC2P
| 0 | L2PRD-CM-RECV-TSCPLR
| 0 | L2PRD-CM-RECV-TSHMSM
L2HE-INV-UCM |  | L2PRD-CM-RECV-UCM
L2HE-INV-VV |  | L2PRD-CM-RECV-VV
| 0 | L2PRD-CST-RECV
L2HE-INV-AMGV |  | L2PRD-CST-RECV-AMGV
L2PRD-CST-RECV-BLA
L2PRD-CST-RECV-BLACRM
L2HE-INV-BLBP |  | L2PRD-CST-RECV-BLBP
L2HE-INV-BLBS |  | L2PRD-CST-RECV-BLBS
L2HE-INV-BLBU
L2HE-INV-BLXD |  | L2PRD-CST-RECV-BLXD
L2PRD-CST-RECV-BLXU
L2PRD-CST-RECV-BPM
L2PRD-CST-RECV-BPMFT
L2PRD-CST-RECV-CFL
L2HE-INV-TUNC |  | L2PRD-CST-RECV-TUNMC
L2HE-INV-TUNCX
L2PRD-CST-RECV-TUNMT
L2HE-INV-PIEZO |  | L2PRD-CST-RECV-TUNPZ
L2HE-INV-QUAD

## TRAVS OLD
| Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author | Reviewer | Reviewer | Project Manager | Tech Rep (SOTR) | NCR Informative | NCR Dispositioners | D3 Emails | Procedure(s), Name (if known) | Drawing(s), Name (if known) | Acronym from INV | Notes | Status | Section
Cavity Preparation
| Processing | [17 empty] | SS
OD | Cavity HOM Measurements and Tuning | L2HE-TUNE-HOM | R1 | 2021-05-01 |  | D. FOREHAND | R. OVERTON |  | K. WILSON
CP | Cavity RF Inspection | L2HE-TUNE-CAV-RFIN | R1 | 2021-05-01 |  |  |  |  | Hogan | [6 empty] | CAV | Cavities arrive in Aug2021 per KW | CP
| Chemistry | [17 empty] | SS
NR | Cavity High Pressure Rinse | L2HE-CHEM-CAV-HPR | R1 | [12 empty] | CAV |  | NR
CP | L2HE Cavity Ultrasonic Cleaning | L2HE-CHEM-CAV-USC | R1 |  |  | A. Wildeson | A. Mitchell | T. Ganey | K. Wilson |  | ashleya | kwilson,ganey | kwilson,ganey,ashleya,forehand |  |  |  |  | CP
OA | L2HE Cavity Degrease | L2HE-CHEM-CAV-DEGR | R1 |  |  | A. Mitchell | T. Ganey |  | K. Wilson |  | forehand,kdavis | ganey,kwilson,ashleya | Ganey,kwilson,ashleya |  |  |  |  | OA
OA | L2HE Cavity Horizontal Electropolish | L2HE-CHEM-CAV-HEP | R1 |  |  | A. Mitchell | T. Ganey |  | K. Wilson |  | forehand,kdavis | ganey,kwilson,ashleya | Ganey,kwilson,ashleya |  |  |  |  | OA
| Assembly | [17 empty] | SS
CP | Cavity 1st Assembly | L2HE-CLNRM-CAV-ASSY1 | R1 | 2021-06-01 |  | D. FOREHAND | C. DREYFUSS |  | K. WILSON | [8 empty] | CP
CP | Cavity 2nd Assembly | L2HE-CLNRM-CAV-ASSY2 | R1 | 2021-06-01 |  | D. FOREHAND | C. DREYFUSS |  | K. WILSON | [8 empty] | CP
OD | Cavity Evacuation & Leak Test | L2HE-CLNRM-CAV-LEAK | R1 | 2021-06-01 |  | D. FOREHAND | C. DREYFUSS |  | K. WILSON
CP | Transfer of L2PRD 9-cell cavities to Test Stands | L2HE-CLNRM-CAV-TSTD | R1 | 2021-06-01 |  | D. FOREHAND | C. DREYFUSS |  | K. WILSON | [8 empty] | CP
CP | Transfer of L2PRD 9-cell cavities to Test Stands for Dewar 5 | L2HE-CLNRM-CAV-TSTD5 | R1 | 2021-06-01 |  | D. FOREHAND | C. DREYFUSS |  | K. WILSON | [8 empty] | CP
| Testing | [17 empty] | SS
CP | Cavity Cooldown | L2HE-VTA-CAV-COOL | R1 | 2021-05-01 |  | JT. KENT | J. VENNEKATE |  | K. WILSON |  | hogan,kwilson | hogan,kwilson | hogan,kwilson,kdavis,jtkent |  |  |  |  | CP
OD | Cavity Production VTA HOM Survey (PROCEDURES NEEDED) | L2HE-VTA-CAV-HOM | R1 | 2021-05-21 |  | P. Owen | J. VENNEKATE |  | K. WILSON
CP | Cavity VTA Test | L2HE-VTA-CAV-VTRF | R1 | 2021-05-01 |  | JT. KENT | J. VENNEKATE |  | K. WILSON | [8 empty] | CP
OA | Production Cavity Vertical Testing Procedure | L2HE-PR-VTA-CAV-VTRF | R1 | 2021-05-21 |  | C. WILSON | K. DAVIS |  | K. WILSON | [8 empty] | OA
| Component Preparation | [17 empty] | SH
| Inspection | [17 empty] | SS
CP | Cavity Inspection | L2HE-INSP-CAV | R1 | 2021-08-01 |  | K. WILSON |  |  | Hogan | [6 empty] | CAV |  | CP
OD | Cavity Inventory | L2HE-INV-CAV | R1 | 2021-05-01 | 2020-05-15 | J. VENNEKATE
OD | FPC WARM PART | L2HE-CMA-FPCW-INSP | R1 | 2021-05-24 | 2020-05-15 | N. HUQUE |  |  | Hogan | [5 empty] | 341081, P96394 | FPCW
CP | FPC WARM PART Inventory | L2HE-INV-FPCW | R1 | 2021-05-24 | 2020-05-15 | N. HUQUE | [11 empty] | CP
CP | FPC COLD PART | L2HE-CLNRM-FPCC-INSP | R1 | 2021-05-24 | 2020-05-15 | N. HUQUE | [8 empty] | 341082, P96406 | FPCC |  | CP
CP | Inspection Procedure for LCLS-II-HE Cold Fundamental Power Coupler | L2HE-PR-INSP-FPCC | R1 | 2021-05-24 | 2020-05-15 | [12 empty] | CP
CP | FPC COLD PART Inventory | L2HE-INV-FPCC | R1 | 2021-05-24 | 2020-05-15 | N. HUQUE | M. Dickey | C. Barnes | J. Hogan | N. Huque | Dickey,Hogan,kwilson | Huque | Huque,Hogan,kwilson |  |  |  |  | CP
CP | FPC Waveguide Incoming Inspection | L2HE-INSP-FPCWG | R1 | 2021-10-15 | 2021-01-27 | Huque | Stirbet |  | Hogan | Huque | [5 empty] | FPCWG |  | CP
CP | FPC Waveguide Inventory | L2HE-INV-FPCWG | R1 | 2021-05-01 | 2021-01-27 | Dickey | Barnes |  | Wilson |  | Wislon | Huque,Fischer | Huque,Fisher |  |  |  |  | CP
CP | Cavity Field Probe Feedthru Receiving Inspection | L2HE-INSP-FPFT | R1 | 2020-10-16 |  | Liang | DeKerlegand | N/A | Wilson | Liang | hannesv, Reece | lzhao, Wilson | lzhao, Wilson | No | GMM-9434A |  |  | CP
CP | Cavity Field Probe Feedthru Receiving Inventory | L2HE-INV-FPFT | R1 | 2021-05-19 |  | M. Dickey | C. Barnes |  | J. Hogan | L.Zhao | hannesv, Reece | lzhao, Wilson | lzhao, Wilson |  |  |  |  | CP
CP | Cavity HOM Feedthru Receiving Inspection | L2HE-INSP-HMFT | R1 | 2020-10-16 |  | Liang | DeKerlegand | N/A | Wilson | Liang | hannesv, Reece | lzhao, Wilson | lzhao, Wilson | No | GMM-9433A |  |  | CP
CP | Cavity HOM Feedthru Receiving Inventory | L2HE-INV-HMFT | R1 | 2021-05-19 |  | M. Dickey | C. Barnes |  | J. Hogan | L.Zhao | hannesv,reece | lzhao, Wilson | lzhao, Wilson |  |  |  |  | CP
OD | Cavity Beam Line Bellows PRCM | L2HE-INSP-BLBP | R1 | 2021-07-01 | 2021-08-01 | Marchlik | DeKerlegand | Zhao | Hogan | Reece | Hannesv, Reece | Lzhao, Wilson | Lzhao, Wilson
OD | Cavity Beam Line Bellows PRCM Inventory | L2HE-INV-BLBP | R1 | 2021-07-01 | 2021-08-01
OD | Cavity Beam Line Bellows Short | L2HE-INSP-BLBS | R1 | 2021-07-01 | 2021-08-01 | Marchlik | DeKerlegand | Zhao | Hogan | Marchlik
OD | Cavity Beam Line Bellows Short Inventory | L2HE-INV-BLBS | R1 | 2021-07-01 | 2021-08-01
CP | Cavity String Weldment Upstream Bellows | L2HE-INSP-BLBU | R1 | 2021-07-01 | 2021-05-10 | Marchlik | DeKerlegand | Zhao | Hogan | Marchlik | [7 empty] | CP
OD | Cavity String Weldment Upstream Bellows Inventory | L2HE-INV-BLBU | R1 | 2021-05-01 | 2021-05-10
OD | String Beam Line Extension Downstream | L2HE-INSP-BLXD | R1 | 2021-07-01 |  | Marchlik | DeKerlegand | Zhao | Hogan | Marchlik
OD | String Beam Line Extension Downstream Inventory | L2HE-INV-BLXD | R1 | 2021-07-01
CP | 300K Current Leads CF Flange Inspection | L2HE-INSP-CFL | R1 | 2021-04-01 |  | Lakshmi | King | Morrone | Hogan | Lakshmi | hogan,kwilson | lalitha,king | lalitha,king,fisher,morrone |  |  |  |  | CP
OD | End Lever Tuner Mechanical Frame Inspection | L2HE-INSP-TUNC | R1 | 2021-05-14 |  | Powen | DeKerlegand | Huque | Hogan | Powen | kwilson | Powen, Huque, georged | Powen, Huque, Wilson |  | F10132292-B, F10138922-A
CP | End Lever Tuner Mechanical Frame Inventory | L2HE-INV-TUNC | R1 | 2021-05-14 |  | M. Dickey | C. Barnes | J. Hogan | P. Owen |  | kwilson,hogan | cheng,fischer,powen | cheng,fischer |  |  |  |  | CP
CP | L2HE Extended Cold Tuner Inventory Traveler | L2HE-INV-TUNCX | R1 | 2021-05-14 |  | M. Dickey | C. Barnes | J. Hogan | P. Owen |  | kwilson,hogan | cheng,fischer,powen | cheng,fischer |  |  |  |  | CP
CP | End Lever Tuner Motor | L2HE-INSP-SM | R1 | 2021-04-01 | 2021-04-30 | King | Powen | Huque | Hogan | Powen | huque,kwilson | Powen, King | Powen, Huque, Wilson |  |  |  | Will be a batch traveler | CP
CP | Tuner Piezo Actuator Assembly Inspection | L2HE-INSP-PIEZO | R1 | 2021-03-05 | 2021-05-31 | King | Powen | Huque | Hogan | Powen | huque,kwilson | Powen, King | Powen, Huque, Wilson |  |  |  | Will be a batch traveler | CP
CP | Tuner Piezo Actuator Inventory | L2HE-INV-PIEZO | R1 | 2021-05-01 | 2021-05-31 | M. Dickey | C. Barnes |  | John Hogan | Peter Owen | mdickey,Hogan,areilly | powen | Hogan,powen,areilly |  |  |  |  | CP
OD | Quadrapole Magnet Inspection | L2HE-INSP-QUAD | R1 | 2021-07-15 |  | Lakshmi | King | Morrone | Hogan | Lakshmi |  | Lakshmi, Wilson | Lakshmi, Wilson
CP | Quadrapole Magnet Inventory | L2HE-INV-QUAD | R1 | 2021-06-15 |  | Dickey | Barnes | Morrone | Hogan | Lakshmi |  | Lakshmi, Wilson | Lakshmi, Wilson |  |  |  |  | CP
CP | Cryomodule Cool Down Cryogenic Valve (CDV) | L2HE-INSP-CDV | R1 | 2021-05-17 |  | Kent | Fischer | McEwen | Hogan | Kent | Katherine, Hogan | Kent, Wilson | Kent, Fischer |  |  |  |  | CP
CP | Receiving Inspection CM Magnetic Shield Assembly | L2HE-INSP-IMAG | R1 | 2021-05-14 |  | Gary | DeKerlegand | Fischer | Hogan | Gary | Katherine, Hogan | Gary, Fischer | Gary, Fischer |  | F10048652 |  |  | CP
CP | CM Magnetic Shield Assembly Inventory | L2HE-INV-IMAG | R1 | 2021-05-14 |  | M. Dickey | C. Barnes |  | J. Hogan | G. Cheng | Katherine, Hogan | Gary, Fischer | Gary, Fischer |  |  |  |  | CP
OD | Receiving Inspection CM Rod Invar 2-Phase Long | L2HE-INSP-IROD2L | R1 | 2021-05-01 |  | O'Brien |  |  | Hogan | [7 empty] | Waiting on FERMI for response
OD | Receiving Inspection CM Rod Invar 2-Phase | L2HE-INSP-IROD2P | R1 | 2021-05-01 |  | O'Brien |  |  | Hogan | [7 empty] | Waiting on FERMI for response
CP | Receiving Inspection CM Assembly, JT Cryogenic Valve | L2HE-INSP-JTV | R1 | 2021-05-17 |  | Kent | Fischer | McEwen | Hogan | Kent | Katherine, Hogan | Kent, Wilson | Kent, Fischer |  |  |  |  | CP
OD | Receiving Inspection CM Assembly, JT Valve Tube Kit | L2HE-INSP-JTVTK | R1 | 2021-06-01 |  | Kent | Fischer | McEwen | Hogan | Kent | Katherine, Hogan | Kent, Wilson | Kent, Fischer
OD | CM Assembly, JT Valve Tube Kit Inventory | L2HE-INV-JTVTK | R1 | 2021-06-01
OA | Upper Cold Mass CMA Inspection | L2HE-CMA-UCM-INSP | R1 | 2021-05-28 |  | Gary | Fischer | N/A | Hogan | Gary | Katherine, Hogan | Gary, Fischer | Gary, Fischer |  | F10009954 |  |  | OA
CP | Receiving CMA Inspection CM Vacuum Vessel | L2HE-CMA-VV-INSP | R1 | 2021-05-28 |  | Gary | Fischer | N/A | Hogan | Gary | Katherine, Hogan | Gary, Fischer | Gary, Fischer |  | F10026609 |  |  | CP
OD | Upper Cold Mass CMA Inventory | L2HE-INV-UCM | R1 | 2021-05-18
OD | CM Vacuum Vessel Inventory | L2HE-INV-VV | R1 | 2021-05-18
CP | All Metal Gate Valve Inventory | L2HE-INV-AMGV | R1 | 2021-05-01 |  | Dickey | Barnes |  | Hogan | Savransky | Mdicky,Hogan | Kwilson,Dsavr | [5 empty] | CP
| Chemistry | [17 empty] | SS
OD | High Pressure Rinse | L2HE-CHEM-COMP-HPR | R1 | 2021-07-01 |  | Mitchell | Wildeson |  | Hogan |  | ashleya | hogan,ari | ashleya,ari,hogan,kdavis,forehand
NR | Components Cleaning | L2HE-CHEM-COMP-DEGR | R1 | 2021-07-01 |  | Mitchell | Wildeson |  | Hogan |  | ashleya | hogan,ari | ashleya,ari,hogan,kdavis,forehand |  |  |  |  | NR
OD | Laping | L2HE-CHEM-COMP-LAP | R1 | 2021-07-01 |  | Wildeson | Mitchell |  | Hogan |  | ashleya | hogan,ari | ashleya,ari,hogan,kdavis,forehand
| Weld Inspection | [17 empty] | SS
CP | Upper Cold Mass Weld Inspection? | L2HE-CWI-UCM | R1 | 2021-05-28 |  | Gary | JENORD | Fischer | Hogan | Gary | Katherine, Hogan | Gary, Fischer | Gary, Fischer |  | F10009954 |  |  | CP
| Leak Checks | [17 empty] | SS
CP | Cavity Field Probe Feedthru Receiving Inspection | L2HE-CMA-FPFT-LEAK | R1 | 2020-10-21 |  | Park | Wilcox | N/A | Wilson | LIANG | Ari, Reece | Park, Wilson | Park, Wilson | Leak check spec 11141-S-0029 | GMM-9434A |  |  | CP
CP | Cavity HOM Feedthru Receiving Inspection | L2HE-CMA-HMFT-LEAK | R1 | 2020-10-21 |  | Park | Wilcox | N/A | Wilson | LIANG | Ari, Reece | Park, Wilson | Park, Wilson | Leak check spec 11141-S-0029 | GMM-9433A |  |  | CP
OD | Cavity Beam Line Bellows PRCM Leak Test | L2HE-CMA-BLBP-LEAK | R1 | 2021-08-15 | 2021-08-01 | Marchlik | WIlcox | N/A | Wilson | Marchlik | Ari, Reece | Marchlik, Wilson | Marchlik, Wilson | Leak check spec 11141-S-0029 | F10041075
OD | Cavity Beam Line Bellows Short | L2HE-CMA-BLBS-LEAK | R1 | 2021-08-15 | 2021-08-01 | Marchlik | WIlcox | N/A | Wilson | Marchlik | Ari, Reece | Marchlik, Wilson | Marchlik, Wilson | Leak check spec 11141-S-0029 | F10023437
OA | Cavity String Weldment Upstream Bellows | L2HE-CMA-BLBU-LEAK | R1 | 2021-08-15 | 2021-05-10 | Marchlik | WIlcox | N/A | Wilson | Marchlik | Ari, Reece | Marchlik, Wilson | Marchlik, Wilson | Leak check spec 11141-S-0029 | F10075494 |  |  | OA
OD | String Beam Line Extension Downstream | L2HE-CMA-BLXD-LEAK | R1 | 2021-08-15 | 2021-08-01 | Marchlik | WIlcox | N/A | Wilson | Marchlik | Ari, Reece | Marchlik, Wilson | Marchlik, Wilson | Leak check spec 11141-S-0029 | F10052775
| Cold Shock | [17 empty] | SS
CP | Cavity Field Probe Feedthru Receiving Inspection | L2HE-VTA-FPFT-CSHK | R1 | 2020-10-22 |  | Park | Forehand | Kent | Wilson | Park | Ari, Reece | Park, Wilson | Park, Wilson | No | GMM-9434A |  |  | CP
CP | Cavity HOM Feedthru Receiving Inspection | L2HE-VTA-HMFT-CSHK | R1 | 2020-10-23 |  | Park | Forehand | Kent | Wilson | Park | Ari, Reece | Park, Wilson | Park, Wilson | No | GMM-9433A |  |  | CP
| Cavity String | [17 empty] | SH
| Assembly | [17 empty] | SS
| Cavity String Assembly (MAJOR CHANGE) | L2HE-CST-ASSY | R1 | 2021-12-01 |  | Forehand |  |  | Hogan
| BPM Magnet sub-assembly | L2HE-CST-ASSY-BPM | R1 | 2021-12-01 |  | Forehand |  |  | Hogan
| String Pump down, leak test and transfer to phase 1 | L2HE-CST-ASSY-LEAK | R1 | 2021-12-01 |  | Forehand |  |  | Hogan
| Cavity String Gate Valve Leak Test | L2HE-CST-LEAK-AMGV | R1 | 2021-12-01 | 2021-04-29 | Forehand |  |  | Hogan
| Cryomodule | [17 empty] | SH
| Cryomodule Assembly | [17 empty] | SS
| CM Assembly First | L2HE-CMA-FRST | R1 | 2022-02-01 |  | Fischer | Worland |  | Hogan
| CM Assembly Second | L2HE-CMA-SCND | R1 | 2022-02-01 |  | Fischer | Worland |  | Hogan
| CM Assembly Final | L2HE-CMA-FNAL | R1 | 2022-02-01 |  | Fischer | Worland |  | Hogan
| Cryomodule Vacuum Vessel Assembly | L2HE-CMA-VV | R1 | 2022-02-01 |  | Fischer | Worland |  | Hogan
| FPC Warm Installation | L2HE-CMA-FPCW | R1 | 2022-02-01 | 2020-05-15 | Huque |  |  | Hogan
| Cryomodule Rework Traveler | L2HE-CMA-REW | R1 | 2022-02-01 |  | Fischer |  |  | Hogan
| Cryomodule Prep and Shipping to SLAC | L2HE-CMA-SHIP | R1 | 2022-02-01 |  | Martin | Fischer |  | Hogan
| Cryomodule Retrofit Traveler | L2HE-CMA-RFIT | R1 | 2022-02-01 |  | Fischer |  |  | Hogan
| FPCW AC Diassemble/Removal | L2HE-CMA-FPCW-DISA | R1 | 2022-02-01 | 2020-05-15 | Huque |  |  | Hogan
| Processing | [17 empty] | SS
OD | Production Cryomodule Demagnetization | L2HE-LERF-CM-DMAG | R1 | 2021-07-31 |  | Cheng | Fischer |  | Hogan | Cheng | Wilson, Hogan | Fischer, Cheng | Fischer, Cheng
CP | Upper Cold Mass Magnetic Hygiene Control | L2HE-CMA-UCM-DMAG | R1 | 2021-05-28 |  | Cheng | Fischer |  | Hogan | Cheng | Wilson, Hogan | Fischer, Cheng | Fischer, Cheng |  |  |  |  | CP
| Cryomodule Testing | [17 empty] | SS
OD | Cryomodule Acceptance Test LERF | L2HE-LERF-CM-ACTS | R1 | 2021-09-01 |  | Drury |  |  | Hogan
| Standard Project Travelers | [17 empty] | SH
CP | D3 Report | L2HE-D3 | R2 | [14 empty] | CP
CP | Cavity Non-conformance Report | L2HE-NCR | R11 | [14 empty] | CP
CP | Inspection Summary Report | L2HE-INSR | R1 | [14 empty] | CP
Color Legend |  | Count | Percent
CP | Complete (CP) | 44 | 49.44%
NR | New Revision Out for Approval (NR) | 2 | 2.247%
OA | Out for Approval (OA) | 5 | 5.618%
30 | Due in 30 Days | 0 | 0%
15 | Due in 15 Days | 0 | 0%
OD | Overdue | 27 | 30.34%
| Remaining | 13 | 14.61%
| Total Traveler IDs | 89

## L2PRD TRAVS
Traveler Id | Rev No | Traveler Name | Author | Date
L2PRD-CAV-ASSY-FRST | R2 | L2PRD Nine Cell Cavity First Assembly | D. Forehand | 12-Jul-2018
L2PRD-CAV-ASSY-SCND | R1 | L2PRD Nine Cell Cavity Second Assembly | D. Forehand | 09-Jul-2018
L2PRD-CAV-HOM-TUNE | R5 | LCLS-II cavity HOM measurements and tuning | A. Solopova | 23-Apr-2018
L2PRD-CAV-INSP-BLA | R4 | LCLSII HOM BLA incoming inspection, testing and storage | HyeKyong Park | 07-Feb-2019
L2PRD-CAV-INSP-CAV | R5 | L2PRD LCLS-II Cavity Receiving Inspection | K. Wilson | 25-Jul-2017
L2PRD-CAV-INSP-FPC | R1 | LCLSII FPC incoming inspection | M. Stirbet | 16-Jul-2015
L2PRD-CAV-INSP-FPCWG | R1 | L2PRD FPC waveguide incoming inspection | M.Stirbet | 08-Jun-2017
L2PRD-CAV-INSP-FPFT | R4 | LCLS-II Field Probe Feedthru Receiving Inspection | HK. Park | 21-Feb-2018
L2PRD-CAV-INSP-HELV | R3 | L2PRD LCLS-II Cavity Receiving Inspection | K. Wilson | 06-Jul-2016
L2PRD-CAV-INSP-HMFT | R3 | LCLS-II HOM Feedthru Receiving Inspection | HK. Park | 23-May-2016
L2PRD-CAV-RECV-CAV | R2 | L2PRD Dressed Cavity Inventory Traveler | K. Wilson | 21-Jun-2016
L2PRD-CAV-RECV-CAV-HLDPT1 | R1 | Cavity Vendor Holdpoint 1 Documentation | M. McDonald | 31-May-2016
L2PRD-CAV-RECV-CAV-HLDPT2 | R1 | Cavity Vendor Holdpoint 2 Documentation | M. McDonald | 22-Jun-2016
L2PRD-CAV-RECV-CAV-HLDPT3 | R1 | Cavity Vendor Holdpoint 3 Documentation | M. McDonald | 14-Jul-2016
L2PRD-CAV-RECV-CAVEZ-HLDPT1 | R1 | Receiving Cavity Vendor Documentation from Zanon for Holdpoint 1 | M. McDonald | 18-Oct-2016
L2PRD-CAV-RECV-CAVEZ-HLDPT2 | R1 | Receiving Cavity Vendor Documentation from Zanon for Holdpoint 2 | M. McDonald | 03-Nov-2016
L2PRD-CAV-RECV-CAVEZ-HLDPT3 | R1 | Receiving Cavity Vendor Documentation from Zanon for Holdpoint 3 | M. McDonald | 12-Dec-2017
L2PRD-CAV-RECV-CAVEZ2-HLDPT1 | R1 | Receiving Cavity Vendor Documentation from Zanon for Holdpoint 1 | M. McDonald | 29-Jan-2018
L2PRD-CAV-RECV-CAVEZ2-HLDPT2 | R1 | Receiving Cavity Vendor Documentation from Zanon for Holdpoint 2 | M. McDonald | 15-Nov-2016
L2PRD-CAV-RECV-CAVEZ2-HLDPT3 | R1 | Receiving Cavity Vendor Documentation from Zanon for Holdpoint 3 | M. McDonald | 18-Aug-2017
L2PRD-CAV-RECV-CAVEZ3-HLDPT2 | R1 | Receiving Cavity Vendor Documentation from Zanon for Holdpoint 2 | M. McDonald | 25-May-2017
L2PRD-CAV-RECV-CAVEZ4-HLDPT2 | R1 | Receiving Cavity Vendor Documentation from Zanon for Holdpoint 2 | M. McDonald | 29-Aug-2018
L2PRD-CAV-RECV-DRT | R1 | L2PRD Cernox RTD¿ Inventory Traveler | M. McDonald | 08-Feb-2016
L2PRD-CAV-RECV-FPC | R1 | L2PRD FPC receiving | M.Stirbet | 07-Sep-2016
L2PRD-CAV-RECV-FPCWG | R2 | L2PRD FPC Waveguide Inventory Traveler | M.Stirbet | 26-Aug-2016
L2PRD-CAV-RECV-FPFT | R1 | L2PRD Field Probe FeedThru Inventory Traveler | M. McDonald | 19-Feb-2015
L2PRD-CAV-RECV-HELV | R1 | L2PRD Dressed Cavity Inventory Traveler | M. McDonald | 26-Feb-2016
L2PRD-CAV-RECV-HMFT | R1 | L2PRD HOM FeedThru Inventory Traveler | M. McDonald | 19-Feb-2015
L2PRD-CAV-RECV-NB55 | R1 | L2PRD Niobium Inventory Traveler | M. McDonald | 26-Feb-2016
L2PRD-CAV-RFIN | R1 | L2PRD LCLS-II Cavity RF Incoming Inspection | F. Marhauser | 17-Jun-2016
L2PRD-CAV-TRANS-TSTD | R1 | L2PRD Nine Cell Cavity Transfer to Test Stand | D. Forehand | 23-Jul-2016
L2PRD-CAV-TRANS-TSTD-D5 | R2 | L2PRD Nine Cell Cavity Transfer to Test Stand for Dewar 5 | D. Forehand | 21-May-2019
L2PRD-CAV-VTA-COOL | R2 | LCLS Cavity VTA Cooldown | P. Kushnick | 04-Jun-2019
L2PRD-CAV-VTA-HOM | R1 | LCLSII Cavity Production VTA HOM Survey | M. Stirbet | 19-Aug-2016
L2PRD-CAV-VTRF | R4 | LCLSII (Production Cryomodule) Vertical cavity Testing | K. Davis | 09-May-2019
L2PRD-CM-ACTS | R4 | LCLS II Production Cryomodule Acceptance Testing | M. Drury | 23-Apr-2018
L2PRD-CM-ACTS-LERF | R1 | LCLS II Production Cryomodule Acceptance Testing in the LERF | M. Drury | 16-Jan-2019
L2PRD-CM-ACTS-PREP | R1 | LCLSII (Production Cryomodule) Install and Cool Down | M. Drury | 13-Apr-2017
L2PRD-CM-ASSY-FNAL | R5 | LCLS2 Production Cryomodule Final Assembly Traveler | J. Fischer | 01-Jun-2017
L2PRD-CM-ASSY-FNAL | R6 | LCLS2 Production Cryomodule Final Assembly Traveler | J. Fischer | 01-Jun-2017
L2PRD-CM-ASSY-FPCW | R3 | LCLSII L2PRD-CM-ASSY-FPCW installation | M. Stirbet | 17-Jul-2017
L2PRD-CM-ASSY-FRST | R10 | LCLS2 Production Cryomodule Assembly Traveler Cold Mass Phase 1 | John Fischer | 26-Jul-2018
L2PRD-CM-ASSY-REW | R1 | LCLS2 Production Cryomodule Rework Traveler | R. Legg | 01-Mar-2017
L2PRD-CM-ASSY-RFIT | R7 | LCLS2 Production Cryomodule Retrofit Traveler | Bob Legg | 01-Mar-2017
L2PRD-CM-ASSY-SCND | R7 | LCLS2 Production Cryomodule Assembly Traveler Cold Mass Phase 2 (WS3) | John Fischer | 03-Aug-2018
L2PRD-CM-ASSY-SHIP | R6 | LCLS2 Cryomodule Prep and Shipping to SLAC- WS6 | Jared Martin | 12-Dec-2017
L2PRD-CM-ASSY-VV | R4 | LCLS2 Production Cryomodule Vacuum Vessel Assembly Traveler | J. Fischer | 13-Apr-2017
L2PRD-CM-DISA-FPCW | R2 | LCLSII FPCW AC Disassemble/Removal | M. Stirbet | 03-Oct-2017
L2PRD-CM-DMAG-CM | R1 | LCLS-II Production Cryomodule Demagnetization | R. Legg | 21-Jul-2017
L2PRD-CM-DMAG-LERF | R1 | LCLS-II Production Cryomodule Demagnetization | R Legg | 07-Jan-2019
L2PRD-CM-DMAG-UCM | R1 | LCLS-II Upper Cold Mass Magnetic Hygiene Control | G. Cheng | 08-Feb-2017
L2PRD-CM-DMAG-VV | R1 | LCLS-II Production Cryomodule Vacuum Vessel Demagnetization | G. Cheng | 10-Jan-2016
L2PRD-CM-INSP-BLA | R2 | LCLSII HOM BLA incoming inspection, assembly, and testing | HyeKyoung Park | 13-Aug-2019
L2PRD-CM-INSP-BLAV | R1 | All metal right angle valve leak check traveler for LCLS-II BLA | HyeKyoung Park | 09-Aug-2019
L2PRD-CM-INSP-BP2PH | R1 | Receiving Inspection of LCLS-II Production Cryomodule Weldment , Bellows 2-Phase Pipe (BP2PH) | G. Cheng | 11-May-2016
L2PRD-CM-INSP-CDV | R1 | Receiving Inspection of LCLS-II Cryomodule Cool Down Cryogenic Valve (CDV) | G. Cheng | 20-Feb-2017
L2PRD-CM-INSP-DK12P | R1 | Receiving Inspection of LCLS-II Production Cryomodule Disk 2-Phase Support (DK12P) | G. Cheng | 06-Sep-2016
L2PRD-CM-INSP-DK22P | R1 | Receiving Inspection of LCLS-II Production Cryomodule Disk 2-Phase Support (DK22P) | G. Cheng | 06-Sep-2016
L2PRD-CM-INSP-EDCP | R1 | Shipping End Cap Inspection Traveler | N. Huque | 02-Nov-2016
L2PRD-CM-INSP-FDCP | R1 | Shipping Feed Cap Inspection Traveler | N. Huque | 02-Nov-2016
L2PRD-CM-INSP-FPCW | R2 | LCLSII warm FPC incoming inspection | M. Stirbet | 28-Sep-2015
L2PRD-CM-INSP-FPCWG | R1 | L2PRD FPC waveguide incoming inspection | M.Stirbet | 28-Sep-2016
L2PRD-CM-INSP-IMAG | R2 | Receiving Inspection of LCLS-II Production Cryomodule Magnetic Shield Assembly | G. Cheng | 14-Dec-2016
L2PRD-CM-INSP-IROD2L | R1 | Receiving Inspection of LCLS-II Production Cryomodule Rod Invar 2-Phase Long (IROD2L) | G. Cheng | 07-Sep-2016
L2PRD-CM-INSP-IROD2P | R1 | Receiving Inspection of LCLS-II Production Cryomodule Rod Invar 2-Phase (IROD2P) | G. Cheng | 07-Sep-2016
L2PRD-CM-INSP-JTV | R1 | Receiving Inspection of LCLS-II Cryomodule JT Cryogenic Valve (JTV) | G. Cheng | 10-Oct-2016
L2PRD-CM-INSP-JTVTK | R1 | Receiving Inspection of LCLS-II Production Cryomodule Assembly, JT Valve Tube Kit (JTVTK) | G. Cheng | 06-Sep-2016
L2PRD-CM-INSP-LLDS | R1 | Receiving Inspection of LCLS-II Production Cryomodule Assembly, Liquid He Level-DS (LLDS) | G. Cheng | 06-Sep-2016
L2PRD-CM-INSP-LLNDS | R1 | Receiving Inspection of LCLS-II Production Cryomodule Weldment Line Liquid Level DS (LLNDS) | G. Cheng | 07-Sep-2016
L2PRD-CM-INSP-LLNUS | R1 | Receiving Inspection of LCLS-II Production Cryomodule Weldment Line Liquid Level US (LLNUS) | G. Cheng | 06-Sep-2016
L2PRD-CM-INSP-LLUS | R1 | Receiving Inspection of LCLS-II Production Cryomodule Assembly, Liquid He Level-US (LLUS) | G. Cheng | 07-Sep-2016
L2PRD-CM-INSP-MCCLA | R1 | Receiving Inspection of LCLS-II Cryomodule MC Coupling Line Assembly (MCCLA) | G. Cheng | 27-Jun-2016
L2PRD-CM-INSP-PEC2P | R1 | Receiving Inspection of LCLS-II Production Cryomodule Weldment 2-Phase Pipe End Cap | G. Cheng | 06-Sep-2016
L2PRD-CM-INSP-UCM | R6 | LCLS-II Upper Cold Mass Incoming Inspection | Gary Cheng | 13-Mar-2018
L2PRD-CM-INSP-VV | R5 | Receiving Inspection of LCLS-II Production Cryomodule Vacuum Vessel | G. Cheng | 23-Oct-2017
L2PRD-CM-RECV | R1 | L2PRD General Inventory Traveler | M. McDonald | 06-Jan-2016
L2PRD-CM-RECV-BP2PH | R1 | L2PRD BeamPipe 2 Phase Inventory Traveler | V. Bookwalter | 01-Sep-2015
L2PRD-CM-RECV-C12P | R1 | L2PRD C12P Pressure Transducer Inventory Traveler | M. McDonald | 08-Jun-2016
L2PRD-CM-RECV-CDV | R1 | Cooldown Valve Inventory Receipt | M. McDonald | 11-Oct-2016
L2PRD-CM-RECV-DCXCU | R1 | L2PRD Diode CXCU Inventory Traveler | M. McDonald | 08-Feb-2016
L2PRD-CM-RECV-DCXSD | R1 | L2PRD Diode CXSD Inventory Traveler | M. McDonald | 08-Feb-2016
L2PRD-CM-RECV-DDTCU | R1 | L2PRD Diode DDTCU Inventory Traveler | M. McDonald | 08-Feb-2016
L2PRD-CM-RECV-DDTSD | R1 | L2PRD Diode DTSD Inventory Traveler | M. McDonald | 08-Feb-2016
L2PRD-CM-RECV-DK12P | R1 | Disk 2-Phase Support | M. McDonald | 13-Sep-2016
L2PRD-CM-RECV-DK22P | R1 | Disk 2-Phase Support | M. McDonald | 13-Sep-2016
L2PRD-CM-RECV-FT06P | R1 | L2PRD FT06P Inventory Traveler | M. McDonald | 31-May-2016
L2PRD-CM-RECV-HLS | R1 | L2PRD HLS Liquid Level Probes 12¿ (Helium Level Sensor) | M. McDonald | 14-Sep-2016
L2PRD-CM-RECV-IMAG | R1 | Assembly Magnetic Shield Cavity | M. McDonald | 13-Sep-2016
L2PRD-CM-RECV-IP75SD | R1 | L2PRD Ion Pump | M. McDonald | 19-Feb-2015
L2PRD-CM-RECV-IROD2L | R1 | Rod Invar 2-Phase Long | M. McDonald | 13-Sep-2016
L2PRD-CM-RECV-IROD2P | R1 | Rod Invar 2-Phase | M. McDonald | 13-Sep-2016
L2PRD-CM-RECV-JTV | R1 | JT Valve Inventory Receipt | M. McDonald | 11-Oct-2016
L2PRD-CM-RECV-JTVTK | R1 | Kit, JT Valve Tube | M. McDonald | 13-Sep-2016
L2PRD-CM-RECV-LLDS | R1 | Assembly, Liquid He Level - DS | M. McDonald | 13-Sep-2016
L2PRD-CM-RECV-LLNDS | R1 | Weldment Line Liquid Level - DS | M. McDonald | 13-Sep-2016
L2PRD-CM-RECV-LLNUS | R1 | Weldment Line Liquid Level - US | M. McDonald | 13-Sep-2016
L2PRD-CM-RECV-LLUS | R1 | Assembly, Liquid He Level - US | M. McDonald | 13-Sep-2016
L2PRD-CM-RECV-MCCLA | R1 | L2PRD LCLS-II MC Coupling Line Assembly Inventory Traveler | M. McDonald | 28-Jun-2016
L2PRD-CM-RECV-P2PH | R1 | L2PRD Pipe, 2-Phase Inventory Traveler | M. McDonald | 31-Aug-2016
L2PRD-CM-RECV-PEC2P | R1 | Weldment 2-Phase Pipe End Cap | M. McDonald | 13-Sep-2016
L2PRD-CM-RECV-TSCPLR | R1 | L2PRD Coupler Thermal Strap Inventory Traveler | M. McDonald | 30-Jan-2017
L2PRD-CM-RECV-TSHMSM | R1 | L2PRD HOM Thermal Strap Inventory Traveler | M. McDonald | 30-Jan-2017
L2PRD-CM-RECV-UCM | R1 | Upper Coldmass Inventory Traveler | M. McDonald | 13-Sep-2016
L2PRD-CM-RECV-VV | R1 | L2PRD Vacuum Vessel Inventory Traveler | M. McDonald | 13-Jul-2016
L2PRD-CST-ASSY | R4 | LCLS-II Production Cavity String Traveler | Danny forehand | 10-Sep-2018
L2PRD-CST-ASSY-BPM | R3 | BPM Magnet Sub-assembly Traveler | D. Forehand | 30-Mar-2018
L2PRD-CST-ASSY-LEAK | R1 | LCLS-II Cavity string leak test and transfer to phase 1 | D. Forehand | 27-Feb-2017
L2PRD-CST-INSP-BLBL | R1 | LCLS-II Cavity String Weldment Bellows PrCM Inspection Traveler | K. Wilson | 06-May-2016
L2PRD-CST-INSP-BLBP | R4 | LCLS-II Cavity String Weldment Bellows PrCM Inspection Traveler | K. Wilson | 15-Oct-2016
L2PRD-CST-INSP-BLBS | R4 | LCLS-II Cavity String Weldment Bellows Short Inspection Traveler | K. Wilson | 15-Oct-2016
L2PRD-CST-INSP-BLBU | R1 | LCLS-II Cavity String Weldment Upstream Bellows Inspection Traveler | K. Wilson | 07-Jul-2017
L2PRD-CST-INSP-BLXD | R3 | LCLS-II Cavity String Weldment Extension-DS Inspection Traveler | K. Wilson | 03-Nov-2016
L2PRD-CST-INSP-BLXU | R5 | LCLS-II Cavity String Weldment Extension-US Inspection Traveler | K. Wilson | 09-Nov-2016
L2PRD-CST-INSP-BPMFT | R2 | BPM Feedthrough Incoming Inspection Traveler | HK. Park | 10-Aug-2016
L2PRD-CST-INSP-CFL | R1 | 300K Current Leads CF Flange Inspection | T. Hiatt | 26-Aug-2016
L2PRD-CST-INSP-TUNMC | R3 | End Lever Tuner Mechanical Frame Inspection Traveler | N. Huque | 29-Aug-2016
L2PRD-CST-INSP-TUNMT | R2 | LCLS-II Tuner Stepper Motor Assembly Inspection Traveler | N. Huque | 03-Jan-2017
L2PRD-CST-INSP-TUNPZ | R2 | LCLS-II Tuner Piezo Actuator Assembly Inspection Traveler | N. Huque | 29-Aug-2016
L2PRD-CST-LEAK-AMGV | R1 | LCLS-II Cavity string gate valve leak test | D. Forehand | 03-May-2017
L2PRD-CST-MAG-QUAD | R1 | LCLS-II Production Quadrupole Magnet Detailed Inspection | T. Hiatt | 29-Aug-2016
L2PRD-CST-RECV | R1 | L2PRD General Inventory Traveler | M. McDonald | 06-Jan-2016
L2PRD-CST-RECV-AMGV | R1 | L2PRD All Metal Gate Valve | M. McDonald | 02-Nov-2015
L2PRD-CST-RECV-BLA | R1 | L2PRD Beam Line Absorber | M. Dickey | 12-Apr-2018
L2PRD-CST-RECV-BLACRM | R1 | L2PRD HOM Ceramic Beam Line Absorber | M. McDonald | 17-Feb-2017
L2PRD-CST-RECV-BLBP | R1 | L2PRD Beam Line Bellows Production | M. McDonald | 15-Apr-2016
L2PRD-CST-RECV-BLBS | R1 | L2PRD Beam Line Bellows Short | M. McDonald | 15-Apr-2016
L2PRD-CST-RECV-BLXD | R1 | L2PRD Beam Line Extension Downstream | M. McDonald | 15-Apr-2016
L2PRD-CST-RECV-BLXU | R1 | L2PRD Beam Line Extension Upstream | M. McDonald | 15-Apr-2016
L2PRD-CST-RECV-BPM | R1 | L2PRD BPM Inventory Traveler | M. McDonald | 06-Sep-2016
L2PRD-CST-RECV-BPMFT | R1 | L2PRD BPM FeedThru Inventory Traveler | M. McDonald | 02-Aug-2016
L2PRD-CST-RECV-CFL | R1 | L2PRD 300K Current Leads CF Flange Inventory Traveler | M. McDonald | 07-Sep-2016
L2PRD-CST-RECV-TUNMC | R1 | L2PRD End Lever Tuner Mechanical Frame Inventory Traveler | M. McDonald | 06-Sep-2016
L2PRD-CST-RECV-TUNMT | R1 | L2PRD End Lever Tuner Motor Inventory Traveler | M. McDonald | 06-Sep-2016
L2PRD-CST-RECV-TUNPZ | R1 | L2PRD End Lever Tuner Piezo Actuator Assembly Inventory Traveler | M. McDonald | 06-Sep-2016
L2PRD-CST-RINSP-BLBP | R1 | LCLS-II Cavity String Weldment Bellows PrCM Inspection Traveler | Katherine Wilson | 22-Mar-2019
L2PRD-CST-RINSP-BLBS | R1 | LCLS-II Cavity String Weldment Bellows Short Re-Inspection Traveler | Katherine Wilson | 22-Mar-2019
L2PRD-CST-RINSP-BLXD | R1 | LCLS-II Cavity String Weldment Extension-DS Inspection Traveler | Katherine Wilson | 22-Mar-2019
L2PRD-D3 | R1 | Detours, Deviations and Discrepancies (D3) | V. Bookwalter | 08-Jul-2013
L2PRD-INSR | R1 | Inspection Summary Report | G. DeKerlegand | 21-Mar-2016
L2PRD-NCR | R10 | Non-Conformance Report for Multiple Reworks | V. Bookwalter | 26-Feb-2018

## TRAVELERSold (hidden)
Traveler Name | Traveler ID (SEPARATE BY WORKCENTERS) | Procedure(s), Name (if known) OR Yes/No | Drawing(s), Name (if known) OR Yes/No | SOP/TOSP/OSP/THA | Revision | Author | Reviewer | Project Manager | SOTR | Due | D3 ?? (USERNAME) | NCR Dispositioners (USERNAME) | NCR Informative (USERNAME) | Traveler (Holdpoint) Closer (USERNAME) | Notes
Receiving Travelers
Cavity
Helium Vessel Receiving Traveler | SNSPPU-CAV-RECV-HELV |  |  |  | R1
Cavity String
Bellows Receiving Traveler | SNSPPU-CST-RECV-(bellows) |  |  |  | R1
Gate Valves Receiving Traveler | SNSPPU-CST-RECV-(gate valve) |  |  |  | R1
FPC Receiving Traveler | SNSPPU-CST-RECV-FPC |  |  |  | R1
Cryomodule
Diode CXCU Inventory Traveler | SNSPPU-CM-RECV-DCXCU |  |  |  | R1 | M. Dickey | C. Barnes | E. Daly | P. Owen | 2020-01-02 |  | powen,king,edaly,kwilson,mdickey,areilly
Disassembly Travelers
Cavity
Cavity String
Cryomodule
Leak Check Travelers
Cavity
Cavity String
Bellows Leak Check Traveler | SNSPPU-CST-LEAK-(bellows) |  |  |  | R1
Gate Valves Leak Check Traveler | SNSPPU-CST-LEAK-(gate valves) |  |  |  | R1
FPC Leak Check Traveler | SNSPPU-CST-LEAK-FPC |  |  |  | R1
Cryomodule
Inspection Travelers
Cavity
Visual and CMM Inspection of Cavity | SNSPPU-CAV-INSP-CAV |  | 104211800-M8U-8200-A00X |  | R1 |  |  |  | K. Wilson | 2020-02-01
Visual/CMM Inspection of Helium Vessel | SNSPPU-CAV-INSP-HELV | TI CLEANING | 104211700-M8U-8200-A026 |  | R1 |  |  |  | K. Wilson | 2020-02-01
Receiving Inspection Cavity RF | SNSPPU-CAV-RFIN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
TUNER FRAME / STEPPER MOTORS / HARMONIC DRIVE |  | SS CLEANING
Cavity String
Receiving Inspection Bellows | SNSPPU-CST-INSP-(bellows) |  |  |  | R1 |  |  |  | K. Wilson | 2020-05-01
SNS FPC Visual Inspection | SNSPPU-CST-INSP-FPC |  | 104211600-M8U-8200-A00X |  | R1 |  |  |  | K. Wilson | 2019-12-01
Cryomodule
Space Frame Visual and Dimensional Inspection | SNSPPU-CM-INSP-SFR | SS CLEANING | 104210900-M8U-8200-A001 |  | R1 |  |  |  | M. Marchlik | 2020-10-01
Vacuum Vessel Visual Inspection | SNSPPU-CM-INSP-VV | LEAK CHECK; SS CLEANING | 104210800-M8U-8200-A001 |  | R1 |  |  |  | M. Marchlik | 2020-07-01
SNS Return End Can Visual/CMM Inspection | SNSPPU-CM-INSP-RENC |  | 104210700-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-11-01
SNS Supply End Can Visual/CMM Inspection | SNSPPU-CM-INSP-SENC |  | 104210600-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-06-01
SNS Outer Magnetic Shield Visual Inspection | SNSPPU-CM-INSP-OMAG |  | 104211000-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-05-01
SNS Inner Magnetic Shield Visual Inspection | SNSPPU-CM-INSP-IMAG |  | 104211200-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-05-01
SNS Thermal Shield Visual/CMM Inspection | SNSPPU-CM-INSP-THRM | HIGH SENSITIVITY LEAK CHECK | 104211100-M8U-8200-A002 104211100-M8U-8200-A014 104211100-M8U-8200-A025 |  | R1 |  |  |  | M. Marchlik | 2020-08-01
Chemistry Travelers
Cavity
Cavity High Pressure Rinse (New HPR) Traveler | SNSPPU-CAV-CHEM-HPRN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Components Cleaning Traveler | SNSPPU-CAV-CHEM-CLN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Ultra Sonic Clean Traveler | SNSPPU-CAV-CHEM-USC |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
CMM Workcenter ?
IS there a cav RFIN traveler?
Furnace Workcenter ? | changed CHEM to PROC
Bakeout before RF processing | SNSPPU-CAV-PROC-BAKE |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Cavity Heat Treatment | SNSPPU-CAV-PROC-HEAT |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Processing Travelers
Cavity
Cavity RF Tuning | SNSPPU-CAV-TUNE |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
IS there a cav RFIN traveler? |  |  |  |  | R1
Cavity String
Cryomodule
RF Processing (FPC RF Processing) | SNSPPU-CM-CST-FPC-HPRF |  |  |  | R1 |  |  |  | K. Wilson
Assembly Travelers
Cavity
SNS Helium Vessel Installation Traveler | SNSPPU-CAV-ASSY-HELV |  | 104211700-M8U-8200-A026 |  | R1 |  |  |  |  | 2020-02-01
High Beta Cavity Assembly for VTA testing | SNSPPU-CAV-ASSY (look at old SNS) |  | 104211800-M8U-8200-A00X |  | R1 |  |  |  |  | 2020-02-01
transfer to test stand
Cavity String
SNS High Beta Cavity String Traveler | SNSPPU-CST-ASSY |  |  |  | R1 |  |  |  |  | 2020-07-01
Cryomodule
Cryomodule Assembly | SNSPPU-CM-ASSY |  |  |  | R1 |  |  |  | M. Marchlik | 2020-12-01
Cold Mass Assembly | SNSPPU-CM-ASSY-CMAS |  |  |  | R1 |  |  |  |  | 2020-08-01
Cryomodule Thermal Shield-Spaceframe Assembly Traveler | SNSPPU-CM-ASSY-THRM |  | 104211100-M8U-8200-A002 104211100-M8U-8200-A014 104211100-M8U-8200-A025 |  | R1 |  |  |  | M. Marchlik
SNS High Beta Cryomodule Vacuum Vessel-End Can Assembly Traveler | SNSPPU-CM-ASSY-VV |  | 104210800-M8U-8200-A001 |  | R1
cm assy ship (rf, instrumentation)
Testing Travelers
Vertical Cavity Testing | SNSPPU-CAV-VTRF |  |  |  | R1 |  |  |  |  | 2020-04-01
Cavity VTA Cooldown | SNSPPU-CAV-VTA-COOL |  |  |  | R1 |  |  |  |  | 2020-02-01
Installation/Shipping Travelers
SNS Cryomodule Shipping | SNSPPU-CM-ASSY-SHIP |  |  |  | R1 |  |  |  |  | 2020-05-01
Standard Project Travelers
Detours, Deviations and Discrepancies (D3) | SNSPPU-D3 |  |  |  | R2 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A
Inspection Summary Report | SNSPPU-INSR |  |  |  | R1 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A
Inspection Nonconformance Report | SNSPPU-NCR |  |  |  | R10 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A