## Slide 1: SNSPPU
Color Legend |  | Count | Percent
CP | Complete (CP) | 73 | 96.05%
NR | New Revision Out for Approval (NR) | 0 | 0.00%
OA | Out for Approval (OA) | 0 | 0.00%
30 | Due in 30 Days | 0 | 0.00%
15 | Due in 15 Days | 0 | 0.00%
OD | Overdue | 2 | 2.63%
 | Remaining | 1 | 1.32%
 | Total Traveler IDs | 76 | 
Out for Approval/New Revision
NONE
Approaching Overdue
NONE
Overdue
SNSPPU-CM-ASSY-R1
SNSPPU-CM-ACTS-R1
Please Submit any changes or questions to pansophy@jlab.org
Note:
Project Masterlist can be found in the project docushare folder
Traveler Acronym list can be found in Pansophy, under the User Tools > Traveler Tools drop downs

## Slide 2
Out for Approval |  |  |  |  |  |  |  | 
Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author | Reviewer | Reviewer | Proj Manager
Overdue |  |  |  |  |  |  |  | 
Final Cryomodule Assembly | SNSPPU-CM-ASSY | R1 | 7/22/21 | 10/1/21 | J. Fischer | M. Marchlik | M. Wiseman | E. Daly
Cryomodule Acceptance Test | SNSPPU-CM-ACTS | R1 | 10/1/21 | 11/1/21 | Drury | King |  | Reilly
Approaching Due Date |  |  |  |  |  |  |  | 
SNSPPU Traveler Listing