## Sheet1
TRAVELER NAME | TRAVELER ID |  |  | Transfer
Laping | L2HE-CHEM-CAV-LAP | R1 | C75-CHEM-CAV-FLAP | DONE
Cavity String Gate Valve Leak Test | L2HE-CLNRM-AMGV-LEAK | R1 | ready for approvals
BPM Magnet sub-assembly | L2HE-CLNRM-BPM-ASSY | R1 | L2PRD-CST-ASSY-BPM | DONE
Cavity Evacuation & Leak Test | L2HE-CLNRM-CAV-LEAK | R1 | ASK DANNY
Cavity String Assembly (MAJOR CHANGE) | L2HE-CLNRM-CST-ASSY | R1 | L2PRD-CST-ASSY | DONE
String Pump down, leak test and transfer to phase 1 | L2HE-CLNRM-CST-LEAK | R1 | L2PRD-CST-ASSY-LEAK | DONE
CM Assembly First | L2HE-CMA-CM-ASSY1 | R1 | L2PRD-CM-ASSY-FRST | DONE
CM Assembly Second | L2HE-CMA-CM-ASSY2 | R1 | L2PRD-CM-ASSY-SCND | DONE
CM Assembly Final | L2HE-CMA-CM-ASSYF | R1 | L2PRD-CM-ASSY-FNAL | DONE
Cryomodule Rework Traveler | L2HE-CMA-CM-REW | R1 | L2PRD-CM-ASSY-REW | DONE
Cryomodule Retrofit Traveler | L2HE-CMA-CM-RFIT | R1 | L2PRD-CM-ASSY-RFIT | DONE
Cryomodule Prep and Shipping to SLAC | L2HE-CMA-CM-SHIP | R1 | L2PRD-CM-ASSY-SHIP | DONE
Cavity HOM Measurements and Tuning | L2HE-CMA-HOM-TUNE | R1 | L2PRD-CAV-HOM-TUNE | DONE | IS CMA Correct??
Cryomodule Vacuum Vessel Assembly | L2HE-CMA-VV-ASSY | R1 | L2PRD-CM-ASSY-VV | DONE
Quadrapole Magnet Inspection | L2HE-INSP-QUAD | R1 | ready for approvals
LCLS-II HE Cernox Inventory Traveler | L2HE-INV-CERNOX | R1 | NORMAL INV
Receiving Inspection CM Rod Invar 2-Phase Long | L2HE-INV-IROD2L | R1 | HOLD
Receiving Inspection CM Rod Invar 2-Phase | L2HE-INV-IROD2P | R1 | HOLD
Production Cryomodule Demagnetization | L2HE-LERF-CM-DMAG | R1 | L2PRD-CM-DMAG-LERF-R1 | DONE
Cavity String Gate Valve Leak Test Procedure (C100/C75) | L2HE-PR-CLNRM-AMGV-LEAK | R1
Cavity 1st Assembly Procedure | L2HE-PR-CLNRM-CAV-ASSY1
Cavity 2nd Assembly Procedure | L2HE-PR-CLNRM-CAV-ASSY2
Cavity String Assembly Procedure | L2HE-PR-CLNRM-CST-ASSY | R1
Ionized Nitrogen Parts Cleaning | L2HE-PR-CLNRM-CST-IONCLN | R1
Cavity String Assembly Tooling Preparation | L2HE-PR-CLNRM-CST-PREP
Upstream Gate Valve Sub-Assembly | L2HE-PR-CLNRM-GV1SA-ASSY | R0
Downstream Gate Valve Sub-Assembly | L2HE-PR-CLNRM-GV2SA-ASSY | R0
NEG Pump Manifold Assembly | L2HE-PR-CLNRM-NEG-ASSY | R0
FPC Warm Installation | L2HE-PR-CMA-FPCW-ASSY |  | PROCEDURE NEEDED (WORK ADDED TO CMA | InPro
Cavity HOM Measurements and Tuning Procedure | L2HE-PR-CMA-HOM-TUNE
LSLS-II Valve alignment and installation procedure | CP-L2PRO-CST-ASSY-VLV?
Note on A21: Homer Samuels: David Sarvasky looking over
Note on B14: Homer Samuels: pull the prd and freshen up
Note on B18: Homer Samuels: Hold Still?
Note on B20: Homer Samuels: pull from L2PRD
Note on B22: Homer Samuels: linked in prototype travelers. Update to latest procedure template and send out