## TheNumbers
Color Legend | TRAVELERS | Count | Percent |  | TRAVELERS | PROCEDURES | CHEMISTRY | CLNRM | CMA | INSP | INV | LERF/VTA | CWI
CP | Complete (CP) | 81 | 71.05% | Complete (CP) | 81 | 4 | 4 | 6 | 10 | 22 | 26 | 5 | 2
NR | New Revision OA (NR) | 1 | 0.8772% | New Revision OA (NR) | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
OA | Out for Approval (OA) | 6 | 5.263% | Out for Approval (OA) | 6 | 0 | 1 | 1 | 0 | 1 | 3 | 0 | 0
30 | Due in 30 Days | 0 | 0% | Due in 30 Days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Due in 15 Days | 9 | 7.895% | Due in 15 Days | 9 | 8 | 0 | 0 | 0 | 0 | 0 | 1 | 0
OD | Overdue | 4 | 3.509% | Overdue | 4 | 3 | 0 | 1 | 0 | 0 | 0 | 0 | 0
R0 | R0 Draft | 13 | 11.4% | R0 Draft | 13 | 3 | 0 | 1 | 8 | 0 | 0 | 1 | 0
| Remaining | 0 | 0% | Remaining | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Traveler IDs | 114 |  | TOTAL | 114 | 18 | 5 | 10 | 18 | 23 | 29 | 7 | 2
Color Legend | PROCEDURES | Count | Percent
CP | Complete (CP) | 4 | 22.22%
NR | New Revision Out for Approval (NR) | 0 | 0%
OA | Out for Approval (OA) | 0 | 0%
30 | Due in 30 Days | 0 | 0%
15 | Due in 15 Days | 8 | 44.44%
OD | Overdue | 3 | 16.67%
R0 | R0 Draft | 3 | 16.67%
| Remaining | 0 | 0%
| Total Traveler IDs | 18
Color Legend | CHEMISTRY | Count | Percent
CP | Complete (CP) | 4 | 80%
NR | New Revision Out for Approval (NR) | 0 | 0%
OA | Out for Approval (OA) | 1 | 20%
30 | Due in 30 Days | 0 | 0%
15 | Due in 15 Days | 0 | 0%
OD | Overdue | 0 | 0%
R0 | R0 Draft | 0 | 0%
| Remaining | 0 | 0%
| Total Traveler IDs | 5
Color Legend | CLNRM | Count | Percent
CP | Complete (CP) | 6 | 60%
NR | New Revision Out for Approval (NR) | 1 | 10%
OA | Out for Approval (OA) | 1 | 10%
30 | Due in 30 Days | 0 | 0%
15 | Due in 15 Days | 0 | 0%
OD | Overdue | 1 | 10%
R0 | R0 Draft | 1 | 10%
| Remaining | 0 | 0%
| Total Traveler IDs | 10
Color Legend | CMA | Count | Percent
CP | Complete (CP) | 10 | 55.56%
NR | New Revision Out for Approval (NR) | 0 | 0%
OA | Out for Approval (OA) | 0 | 0%
30 | Due in 30 Days | 0 | 0%
15 | Due in 15 Days | 0 | 0%
OD | Overdue | 0 | 0%
R0 | R0 Draft | 8 | 44.44%
| Remaining | 0 | 0%
| Total Traveler IDs | 18
Color Legend | INSP | Count | Percent
CP | Complete (CP) | 22 | 95.65%
NR | New Revision Out for Approval (NR) | 0 | 0%
OA | Out for Approval (OA) | 1 | 4.348%
30 | Due in 30 Days | 0 | 0%
15 | Due in 15 Days | 0 | 0%
OD | Overdue | 0 | 0%
R0 | R0 Draft | 0 | 0%
| Remaining | 0 | 0%
| Total Traveler IDs | 23
Color Legend | INV | Count | Percent
CP | Complete (CP) | 26 | 89.66%
NR | New Revision Out for Approval (NR) | 0 | 0%
OA | Out for Approval (OA) | 3 | 10.34%
30 | Due in 30 Days | 0 | 0%
15 | Due in 15 Days | 0 | 0%
OD | Overdue | 0 | 0%
R0 | R0 Draft | 0 | 0%
| Remaining | 0 | 0%
| Total Traveler IDs | 29
Color Legend | TESTING (LERF/VTA) | Count | Percent
CP | Complete (CP) | 5 | 71.43%
NR | New Revision Out for Approval (NR) | 0 | 0%
OA | Out for Approval (OA) | 0 | 0%
30 | Due in 30 Days | 0 | 0%
15 | Due in 15 Days | 1 | 14.29%
OD | Overdue | 0 | 0%
R0 | R0 Draft | 1 | 14.29%
| Remaining | 0 | 0%
| Total Traveler IDs | 7
Color Legend | CWI | Count | Percent
CP | Complete (CP) | 2 | 100%
NR | New Revision Out for Approval (NR) | 0 | 0%
OA | Out for Approval (OA) | 0 | 0%
30 | Due in 30 Days | 0 | 0%
15 | Due in 15 Days | 0 | 0%
OD | Overdue | 0 | 0%
R0 | R0 Draft | 0 | 0%
| Remaining | 0 | 0%
| Total Traveler IDs | 2

## TRAVELERS
| Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author | SME | PRODUCTION LEAD | PROJECT LEAD | Tech Rep (SOTR) | NCR Informative | NCR Dispositioners | D3 Emails | Procedure(s), Name (if known) | Drawing(s), Name (if known) | Acronym from INV | Notes | Status | Section
CP | L2HE Cavity Horizontal Electropolish | L2HE-CHEM-CAV-HEP | R1 | 2021-08-01 | 2021-08-01 | A. Mitchell | T. Ganey | T. Ganey | J. Hogan |  | ashleya,kwilson | J. Hogan,vennekate,ganey | ashleya,vennekate,ganey,J. Hogan,kdavis,forehand,kwilson |  |  |  | HEP is not anticipated for the L2HE production run; however, is available if needed for any refurbishment cavities or other situations as may be required to support the project. No changes to reference documents is required. | CP
CP | Cavity High Pressure Rinse | L2HE-CHEM-CAV-HPR | R2 | 2021-09-15 |  | A. Wildeson | A. Mitchell | T. Ganey | J. Hogan |  | ashleya,kwilson | J. Hogan,vennekate,ganey | ashleya,vennekate,ganey,J. Hogan,kdavis,forehand,kwilson |  |  | CAV | Cavities that require reprocessing after a VTRF will receive a HPR - as was done in the L2PRD project. For L2PRD, this HPR was not captured in a traveler. For L2HE, chemistry travelers were created to capture the re-work steps for cavity vertical testing. The chemistry travelers follow standard chemistry processes and were only modified from other project travelers to reflect any 9-cell / L2HE specifics. HPR traveler does not have any references to update. | CP
OA | Laping | L2HE-CHEM-CAV-LAP | R1 | 2021-07-15 |  | A. Wildeson | A. Mitchell | T. Ganey | J. Hogan |  | ashleya,kwilson | J. Hogan,vennekate,ganey | ashleya,vennekate,ganey,J. Hogan,kdavis,forehand,kwilson |  |  |  | ROUTE WHEN DRAFT COMES | OA
CP | L2HE Cavity Ultrasonic Cleaning | L2HE-CHEM-CAV-USC | R2 | 2021-09-15 |  | A. Wildeson | A. Mitchell | T. Ganey | J. Hogan |  | ashleya,kwilson | J. Hogan,vennekate,ganey | ashleya,vennekate,ganey,J. Hogan,kdavis,forehand,kwilson |  |  |  | Cavities that require reprocessing after a VTRF with high radiation and/or very low FE onset may receive an USC prior to HPR - as was done in the L2PRD project. For L2PRD, this USC was not captured in a traveler. For L2HE, chemistry travelers were created to capture the re-work steps for cavity vertical testing. The chemistry travelers follow standard chemistry processes and were only modified from other project travelers to reflect any 9-cell / L2HE specifics. Cavities recieved from vendor will only require external clean / wipedown prior to VTRF. Therefore the traveler was revised to include directions for if the cavity is under vacuum and a YES/NO data field. | CP
CP | Components Cleaning | L2HE-CHEM-COMP-DEGR | R1 | 2021-07-01 |  | A. Mitchell | A. Wildeson |  | J. Hogan |  | ashleya | J. Hogan,ari | ashleya,ari,J. Hogan,kdavis,forehand |  |  |  | Chemistry work was not captured in travelers for L2PRD. Cavity components that require cleaning will be captured in this traveler. The traveler will be based on current component cleaning travelers and standard practices. | CP
OA | Cavity String Gate Valve Leak Test | L2HE-CLNRM-AMGV-LEAK | R1 | 2021-10-11 | 2021-10-26 | D. Sarvansky | D. Forehand | K. Davis | J. Hogan | [7 empty] | L2PRD-CST-LEAK-AMGV | OA
R0 | BPM Magnet sub-assembly | L2HE-CLNRM-BPM-ASSY | R0 | 2021-10-11 | 2021-10-26 | D. FOREHAND | C. Dreyfuss | K. Davis | J. Hogan | [7 empty] | L2PRD-CST-ASSY-BPM | R0
NR | Cavity 1st Assembly | L2HE-CLNRM-CAV-ASSY1 | R2 | 2021-06-01 |  | D. Forehand | C. Dreyfuss |  | K. Wilson | [7 empty] | This traveler will be used with refurbishment and re-processed / cleaned cavities. It is not to be used with cavities arriving directly from the vendor. Due to the different length field probe tips that were in circulation during the refurbishment work, a statement to replace the field probe with the proper length if required was added to the traveler. A Yes/No data field was also added to capture if the FP was changed. Due to the use of purge-only string assembly and the removal of HPR prior to string assemlby, it was identified that the right angle valve must be positioned correctly (in accordance with the cavity drawing package) in order to fit up with the purge system during string assembly. Instructions will be added to this traveler to ensure that the valve is installed in accordance with the drawing. | NR
CP | Cavity 2nd Assembly | L2HE-CLNRM-CAV-ASSY2 | R1 | 2021-06-01 |  | D. Forehand | C. Dreyfuss |  | K. Wilson | [7 empty] | This traveler will be used with refurbishment and re-processed / cleaned cavities. It is not to be used with cavities arriving directly from the vendor. No changes from L2PRD traveler | CP
OD | Cavity Evacuation & Leak Test | L2HE-CLNRM-CAV-LEAK | R1 | 2021-09-01 | 2021-10-01 | D. Forehand | C. Dreyfuss |  | K. Wilson | [7 empty] | Since cavity tests will frequently occur on the dewar 5 test stand and occassionally cavities are prepared for a test stand before the test stand is available, a separate traveler will be used to capture the pump down (if applicable) and leak check. Cavities from the vendor will not require the pump down as these cavities will arrive under vacuum. Cavities that were reprocessed for an additional VTRF will need to be pumped down. All cavities will recieve a leak check. This traveler aims to simplify capturing of the evacuation and leak check data by consolidating all use cases into a single traveler.
CP | Transfer of L2PRD 9-cell cavities to Test Stands | L2HE-CLNRM-CAV-TSTD | R2 | 2021-06-01 |  | D. Forehand | C. Dreyfuss |  | K. Wilson | [7 empty] | Several changes from the L2PRD traveler were identified and suggested. The traveler was updated to allow single cells to be captured in addition to 9-cells. The RGA scan range was updated to the current standard range used at JLab. The decision to seperate out the evacuation and leak check data into a standalone travler will require that this traveler be revised. Also the acceptable leak rate will be updated to reflect the leak rate spec provided in the cavity assembly drawings. | CP
CP | Transfer of L2PRD 9-cell cavities to Test Stands for Dewar 5 | L2HE-CLNRM-CAV-TSTD5 | R1 | 2021-06-01 |  | D. Forehand | C. Dreyfuss |  | K. Wilson | [7 empty] | Several changes from the L2PRD traveler were identified and suggested. The traveler was updated to allow single cells to be captured in addition to 9-cells. The decision to seperate out the evacuation and leak check data into a standalone travler will require that this traveler be revised. Also the acceptable leak rate will be updated to reflect the leak rate spec provided in the cavity assembly drawings. | CP
CP | Cavity String Assembly (MAJOR CHANGE) | L2HE-CLNRM-CST-ASSY | R0 | 2021-11-01 | 2021-11-01 | T. Ganey | D. Forehand | K. Davis | J. Hogan | [7 empty] | Will require a major revision to include use of purge system without HPR | R0
CP | String Pump down, leak test and transfer to phase 1 | L2HE-CLNRM-CST-LEAK | R0 | 2021-11-01 | 2021-11-01 | D. Forehand | C. Dreyfuss | K. Davis | J. Hogan | [7 empty] | L2PRD-CST-ASSY-LEAK-R1 | R0
CP | FPC COLD PART | L2HE-CLNRM-FPCC-INSP | R3 | 2021-05-24 | 2020-05-15 | N. HUQUE | [8 empty] | 341082, P96406 | FPCC |  | CP
CP | Cavity Beam Line Bellows PRCM Leak Test | L2HE-CMA-BLBP-LEAK | R1 | 2021-08-15 | 2021-08-01 | M. Marchlik | C. WIlcox | N/A | K. Wilson | M. Marchlik | Ari, Reece | Marchlik, Wilson | Marchlik, Wilson | Leak check spec 11141-S-0029 | F10041075 |  |  | CP
CP | Cavity Beam Line Bellows Short | L2HE-CMA-BLBS-LEAK | R1 | 2021-08-15 | 2021-08-01 | M. Marchlik | C. WIlcox | N/A | K. Wilson | M. Marchlik | Ari, Reece | Marchlik, Wilson | Marchlik, Wilson | Leak check spec 11141-S-0029 | F10023437 |  |  | CP
CP | Cavity String Weldment Upstream Bellows | L2HE-CMA-BLBU-LEAK | R1 | 2021-08-15 | 2021-05-10 | M. Marchlik | C. WIlcox | N/A | K. Wilson | M. Marchlik | Ari, Reece | Marchlik, Wilson | Marchlik, Wilson | Leak check spec 11141-S-0029 | F10075494 |  |  | CP
CP | String Beam Line Extension Downstream | L2HE-CMA-BLXD-LEAK | R1 | 2021-08-15 | 2021-08-01 | M. Marchlik | C. WIlcox | N/A | K. Wilson | M. Marchlik | Ari, Reece | Marchlik, Wilson | Marchlik, Wilson | Leak check spec 11141-S-0029 | F10052775 |  |  | CP
R0 | CM Assembly First | L2HE-CMA-CM-ASSY1 | R1 | 2021-10-26 |  | J. Fischer | N. Huque | A. Reilly | J. Hogan | [7 empty] | L2PRD-CM-ASSY-FRST | R0
R0 | CM Assembly Second | L2HE-CMA-CM-ASSY2 | R1 | 2021-10-26 |  | J. Fischer | N. Huque | A. Reilly | J. Hogan | [7 empty] | L2PRD-CM-ASSY-SCND | R0
R0 | CM Assembly Final | L2HE-CMA-CM-ASSYF | R1 | 2021-10-26 |  | J. Fischer | N. Huque | A. Reilly | J. Hogan | [7 empty] | L2PRD-CM-ASSY-FNAL | R0
R0 | Cryomodule Rework Traveler | L2HE-CMA-CM-REW | R1 | 2021-10-26 |  | J. Fischer | N. Huque | A. Reilly | J. Hogan | [7 empty] | L2PRD-CM-ASSY-REW | R0
R0 | Cryomodule Retrofit Traveler | L2HE-CMA-CM-RFIT | R1 | 2021-10-26 |  | J. Fischer | N. Huque | A. Reilly | J. Hogan | [7 empty] | L2PRD-CM-ASSY-RFIT | R0
R0 | Cryomodule Prep and Shipping to SLAC | L2HE-CMA-CM-SHIP | R1 | 2021-10-26 |  | J. Fischer | N. Huque | A. Reilly | J. Hogan | [7 empty] | L2PRD-CM-ASSY-SHIP | R0
CP | FPC WARM PART | L2HE-CMA-FPCW-INSP | R1 | 2021-05-24 | 2020-05-15 | N. HUQUE |  |  | J. Hogan | [5 empty] | 341081, P96394 | FPCW |  | CP
CP | Cavity Field Probe Feedthru Receiving Inspection | L2HE-CMA-FPFT-LEAK | R1 | 2020-10-21 |  | H. Park | C. WIlcox | N/A | K. Wilson | L. Zhao | Ari, Reece | Park, Wilson | Park, Wilson | Leak check spec 11141-S-0029 | GMM-9434A |  |  | CP
CP | Cavity HOM Feedthru Receiving Inspection | L2HE-CMA-HMFT-LEAK | R1 | 2020-10-21 |  | H. Park | C. WIlcox | N/A | K. Wilson | L. Zhao | Ari, Reece | Park, Wilson | Park, Wilson | Leak check spec 11141-S-0029 | GMM-9433A |  |  | CP
R0 | Cavity HOM Measurements and Tuning | L2HE-CMA-HOM-TUNE | R1 | 2021-10-26 | 2022-02-01 | P. Owen | D. Forehand | D. Forehand | J. Hogan | [7 empty] | L2PRD-CAV-HOM-TUNE | R0
CP | Upper Cold Mass Magnetic Hygiene Control | L2HE-CMA-UCM-DMAG | R1 | 2021-05-28 |  | G. Cheng | J. Fischer |  | J. Hogan | Cheng | Wilson, J. Hogan | Fischer, Cheng | Fischer, Cheng |  |  |  |  | CP
CP | Upper Cold Mass CMA Inspection | L2HE-CMA-UCM-INSP | R1 | 2021-05-28 |  | G. Cheng | J. Fischer | N/A | J. Hogan | G. Cheng | Katherine, J. Hogan | Gary, Fischer | Gary, Fischer |  | F10009954 |  |  | CP
R0 | Cryomodule Vacuum Vessel Assembly | L2HE-CMA-VV-ASSY | R1 | 2021-10-26 |  | J. Fischer | G. Cheng | A. Reilly | J. Hogan | [7 empty] | L2PRD-CM-ASSY-VV | R0
CP | Receiving CMA Inspection CM Vacuum Vessel | L2HE-CMA-VV-INSP | R1 | 2021-05-28 |  | G. Cheng | J. Fischer | N/A | J. Hogan | G. Cheng | Katherine, J. Hogan | Gary, Fischer | Gary, Fischer |  | F10026609 |  |  | CP
CP | Upper Cold Mass Weld Inspection? | L2HE-CWI-UCM | R1 | 2021-05-28 |  | G. Cheng | A. JENORD | Fischer | J. Hogan | G. Cheng | Katherine, J. Hogan | Gary, Fischer | Gary, Fischer |  | F10009954 |  |  | CP
CP | Vacuum Vessel Receiving Weld Inspection | L2HE-CWI-VV | R1 |  |  | G. Cheng | A. JENORD | Fischer | J. Hogan |  | Kwilson, J. Hogan | Cheng, fischer | Cheng, fischer |  |  |  |  | CP
CP | D3 Report | L2HE-D3 | R2 | [14 empty] | CP
CP | Cavity Beam Line Bellows PRCM | L2HE-INSP-BLBP | R1 | 2021-07-26 | 2021-08-01 | M. Marchlik | G. DeKerlegand | L. Zhao | J. Hogan | C. Reece | Hannesv, Reece | Lzhao, Wilson | Lzhao, Wilson |  |  |  |  | CP
CP | Cavity Beam Line Bellows Short | L2HE-INSP-BLBS | R1 | 2021-07-26 | 2021-08-01 | M. Marchlik | G. DeKerlegand | L. Zhao | J. Hogan | M. Marchlik | [7 empty] | CP
CP | Cavity String Weldment Upstream Bellows | L2HE-INSP-BLBU | R1 | 2021-07-01 | 2021-05-10 | M. Marchlik | G. DeKerlegand | L. Zhao | J. Hogan | M. Marchlik | [7 empty] | CP
CP | String Beam Line Extension Downstream | L2HE-INSP-BLXD | R1 | 2021-07-01 |  | M. Marchlik | G. DeKerlegand | L. Zhao | J. Hogan | M. Marchlik | [7 empty] | CP
CP | Cavity Inspection | L2HE-INSP-CAV | R3 | 2021-08-01 |  | K. WILSON |  |  | J. Hogan | [6 empty] | CAV | Revision to add instructions to visually verify the right angle valve position. Since the cavity may not be disassembled prior to string assembly and the valve position is critical for fit up with the purge system, the valve position needs to be verified during the initial inspection (and flagged with an NCR if valve position is not correct). | CP
CP | Cryomodule Cool Down Cryogenic Valve (CDV) | L2HE-INSP-CDV | R1 | 2021-05-17 |  | J. Kent | J. Fischer | McEwen | J. Hogan | J. Kent | Katherine, J. Hogan | Kent, Wilson | Kent, Fischer |  |  |  |  | CP
CP | 300K Current Leads CF Flange Inspection | L2HE-INSP-CFL | R1 | 2021-04-01 |  | L. Lalitha | L. King | Morrone | J. Hogan | L. Lalitha | J. Hogan,kwilson | lalitha,king | lalitha,king,fisher,morrone |  |  |  |  | CP
CP | LCLS-II HE 2K Clamp Assembly Kit Inspection | L2HE-INSP-CLMP02K | R1 |  |  | L. Lalitha | L. King | J. Fischer | J. Hogan | L. Lalitha | Kwilson,J. Hogan | lalitha,king | lalitha,king,fischer |  |  |  |  | CP
CP | LCLS-II HE 5K Clamp Assembly Kit Inspection Traveler | L2HE-INSP-CLMP05K | R1 |  |  | L. Lalitha | L. King | J. Fischer | J. Hogan | L. Lalitha | Kwilson,J. Hogan | lalitha,king | lalitha,king,fischer |  |  |  |  | CP
CP | LCLS-II HE 50 K Clamp Assembly Kit Inspection Traveler | L2HE-INSP-CLMP50K | R1 |  |  | L. Lalitha | L. King | J. Fischer | J. Hogan | L. Lalitha | Kwilson,J. Hogan | lalitha,king | lalitha,king,fischer |  |  |  |  | CP
CP | LCLS-II HE Split-Quad Clamp Kit Inspection Traveler | L2HE-INSP-CLMPSQ | R1 |  |  | L. Lalitha | L. King | J. Fischer | J. Hogan | L. Lalitha | Kwilson,J. Hogan | lalitha,king | lalitha,king,fischer |  |  |  |  | CP
CP | FPC Waveguide Incoming Inspection | L2HE-INSP-FPCWG | R1 | 2021-10-15 | 2021-01-27 | N. HUQUE | M. Stirbet |  | J. Hogan | N. Huque | [5 empty] | FPCWG |  | CP
CP | Cavity Field Probe Feedthru Receiving Inspection | L2HE-INSP-FPFT | R1 | 2020-10-16 |  | L. Zhao | G. DeKerlegand | N/A | Wilson | L. Zhao | hannesv, Reece | lzhao, Wilson | lzhao, Wilson | No | GMM-9434A |  |  | CP
CP | Cavity HOM Feedthru Receiving Inspection | L2HE-INSP-HMFT | R1 | 2020-10-16 |  | L. Zhao | G. DeKerlegand | N/A | Wilson | L. Zhao | hannesv, Reece | lzhao, Wilson | lzhao, Wilson | No | GMM-9433A |  |  | CP
CP | Receiving Inspection CM Magnetic Shield Assembly | L2HE-INSP-IMAG | R1 | 2021-05-14 |  | G. Cheng | G. DeKerlegand | J. Fischer | J. Hogan | G. Cheng | Katherine, J. Hogan | Gary, Fischer | Gary, Fischer |  | F10048652 |  |  | CP
CP | Receiving Inspection CM Assembly, JT Cryogenic Valve | L2HE-INSP-JTV | R1 | 2021-05-17 |  | J. Kent | J. Fischer | A. McEwen | J. Hogan | J. Kent | Katherine, J. Hogan | Kent, Wilson | Kent, Fischer |  |  |  |  | CP
CP | Tuner Piezo Actuator Assembly Inspection | L2HE-INSP-PIEZO | R1 | 2021-03-05 | 2021-05-31 | J. Kent | P. Owen | N. Huque | J. Hogan | P. Owen | huque,kwilson | Powen, King | Powen, Huque, Wilson |  |  |  | Will be a batch traveler | CP
OA | Quadrapole Magnet Inspection | L2HE-INSP-QUAD | R1 | 2021-10-08 |  | L. Lalitha | L. King | M. Morrone | J. Hogan | L. Lalitha |  | Lakshmi, Wilson | Lakshmi, Wilson |  |  |  |  | OA
CP | End Lever Tuner Motor | L2HE-INSP-SM | R1 | 2021-04-01 | 2021-04-30 | L. King | P. Owen | N. Huque | J. Hogan | P. Owen | huque,kwilson | Powen, King | Powen, Huque, Wilson |  |  |  | Will be a batch traveler | CP
CP | End Lever Tuner Mechanical Frame Inspection | L2HE-INSP-TUNC | R1 | 2021-07-14 | 2021-08-15 | P. Owen | G. Dekerlegand | N. Huque | J. Hogan | P. Owen | kwilson | Powen, Huque, georged | Powen, Huque, Wilson |  | F10132292-B, F10138922-A |  |  | CP
CP | End Lever Tuner Extended Mechanical Frame Inspection Traveler | L2HE-INSP-TUNCX | R1 | 2021-07-14 | 2021-08-15 | P. Owen | G. Dekerlegand | N. Huque | Wilson / J. Hogan | [8 empty] | CP
CP | Inspection Summary Report | L2HE-INSR | R1 | [14 empty] | CP
CP | All Metal Gate Valve Inventory | L2HE-INV-AMGV | R1 | 2021-05-01 |  | M. Dickey | C. Barnes |  | J. Hogan | D. Savransky | Mdicky,J. Hogan | Kwilson,Dsavr | [5 empty] | CP
CP | Cavity Beam Line Bellows PRCM Inventory | L2HE-INV-BLBP | R1 | 2021-07-26 | 2021-08-01 | [12 empty] | CP
CP | Cavity Beam Line Bellows Short Inventory | L2HE-INV-BLBS | R1 | 2021-07-26 | 2021-08-01 | [12 empty] | CP
CP | Cavity String Weldment Upstream Bellows Inventory | L2HE-INV-BLBU | R1 | 2021-05-01 | 2021-05-10 | [12 empty] | CP
CP | String Beam Line Extension Downstream Inventory | L2HE-INV-BLXD | R1 | 2021-07-01 | [13 empty] | CP
CP | 2 Phase Beam Pipe Inventory | L2HE-INV-BP2PH | R1 | [14 empty] | CP
CP | Cavity Inventory | L2HE-INV-CAV | R1 | 2021-08-01 | 2020-05-15 | J. VENNEKATE | [11 empty] | CP
OA | LCLS-II HE Cernox Inventory Traveler | L2HE-INV-CERNOX | R1 | 2021-08-15 | 2021-10-01 | M. Dickey | C. Barnes | L. King | J. Hogan | L. King | [6 empty] | regular INV traveler | OA
CP | Current Lead Flange Inventory | L2HE-INV-CFL | R1 |  |  | M. Dickey | C. Barnes | J.Hogan | L. Lalitha |  | Mdickey,Hogan,kwilson | Lalitha,king | Lalitha,king,fischer,morrone |  |  |  |  | CP
CP | FPC COLD PART Inventory | L2HE-INV-FPCC | R1 | 2021-05-24 | 2020-05-15 | N. HUQUE | M. Dickey | C. Barnes | J. Hogan | N. Huque | Dickey,J. Hogan,kwilson | Huque | Huque,J. Hogan,kwilson |  |  |  |  | CP
CP | FPC WARM PART Inventory | L2HE-INV-FPCW | R1 | 2021-05-24 | 2020-05-15 |  |  |  | J. Hogan | N. HUQUE | [7 empty] | CP
CP | FPC Waveguide Inventory | L2HE-INV-FPCWG | R1 | 2021-05-01 | 2021-01-27 | Dickey | Barnes |  | Wilson |  | Wislon | Huque,Fischer | Huque,Fisher |  |  |  |  | CP
CP | Cavity Field Probe Feedthru Receiving Inventory | L2HE-INV-FPFT | R1 | 2021-05-19 |  | M. Dickey | C. Barnes |  | J. Hogan | L. Zhao | hannesv, Reece | lzhao, Wilson | lzhao, Wilson |  |  |  |  | CP
CP | Cavity HOM Feedthru Receiving Inventory | L2HE-INV-HMFT | R1 | 2021-05-19 |  | M. Dickey | C. Barnes |  | J. Hogan | L. Zhao | hannesv,reece | lzhao, Wilson | lzhao, Wilson |  |  |  |  | CP
CP | CM Magnetic Shield Assembly Inventory | L2HE-INV-IMAG | R1 | 2021-05-14 |  | M. Dickey | C. Barnes |  | J. Hogan | G. Cheng | Katherine, J. Hogan | Gary, Fischer | Gary, Fischer |  |  |  |  | CP
OA | Receiving Inspection CM Rod Invar 2-Phase Long | L2HE-INV-IROD2L | R1 | 2021-08-01 |  | A. O'Brien |  |  | J. Hogan | [7 empty] | Waiting on FERMI for response | OA
OA | Receiving Inspection CM Rod Invar 2-Phase | L2HE-INV-IROD2P | R1 | 2021-08-01 |  | A. O'Brien |  |  | J. Hogan | [7 empty] | Waiting on FERMI for response | OA
CP | CM Assembly, JT Valve Tube Kit Inventory | L2HE-INV-JTVTK | R1 | 2021-08-01 | [13 empty] | CP
CP | JT Cryogenic Valve Tube Kit Inventory | L2HE-INV-JTVTK | R1 | [14 empty] | CP
CP | Liquid He Level Downstream Inventory | L2HE-INV-LLDS | R1 | [14 empty] | CP
CP | Line Liquid Level Downstream Inventory | L2HE-INV-LLNDS | R1 | [14 empty] | CP
CP | Line Liquid Level Upstream Inventory | L2HE-INV-LLNUS | R1 | [14 empty] | CP
CP | Liquid He Level Upstream Inventory | L2HE-INV-LLUS | R1 | [14 empty] | CP
CP | Tuner Piezo Actuator Inventory | L2HE-INV-PIEZO | R1 | 2021-05-01 | 2021-05-31 | M. Dickey | C. Barnes |  | J. Hogan | P. Owen | mdickey,J. Hogan,areilly | powen | J. Hogan,powen,areilly |  |  |  |  | CP
CP | Quadrapole Magnet Inventory | L2HE-INV-QUAD | R1 | 2021-06-15 |  | M. Dickey | C. Barnes | M. Morrone | J. Hogan | L. Lalitha |  | Lakshmi, Wilson | Lakshmi, Wilson |  |  |  |  | CP
CP | End Lever Tuner Mechanical Frame Inventory | L2HE-INV-TUNC | R1 | 2021-05-14 |  | M. Dickey | C. Barnes | J. Hogan | P. Owen |  | kwilson,J. Hogan | cheng,fischer,powen | cheng,fischer |  |  |  |  | CP
CP | L2HE Extended Cold Tuner Inventory Traveler | L2HE-INV-TUNCX | R1 | 2021-05-14 |  | M. Dickey | C. Barnes |  | J. Hogan | P. Owen | kwilson,J. Hogan | cheng,fischer,powen | cheng,fischer |  |  |  |  | CP
CP | Upper Cold Mass CMA Inventory | L2HE-INV-UCM | R1 | 2021-05-18 | [13 empty] | CP
CP | CM Vacuum Vessel Inventory | L2HE-INV-VV | R1 | 2021-05-18 | [13 empty] | CP
CP | Cryomodule Acceptance Test LERF | L2HE-LERF-CM-ACTS | R1 | 2021-09-01 |  | M. Drury | G. Ciovatti | J. Vennekatte | J. Hogan | [8 empty] | CP
R0 | Production Cryomodule Demagnetization | L2HE-LERF-CM-DMAG | R1 | 2021-08-31 |  | G. Cheng | J. Fischer | M. Drury | J. Hogan | Cheng | Wilson, J. Hogan | Fischer, Cheng | Fischer, Cheng |  |  |  | L2PRD-CM-DMAG-LERF-R1 | R0
CP | Cavity Non-conformance Report | L2HE-NCR | R11 | [14 empty] | CP
OD | Ultra Sonic Cleaning Cavity Procedure | L2HE-PR-CHEM-CAV-USC |  | 2021-09-15 | [12 empty] | L2PRD/STP PULL FROM
OD | L2HE Cavity Degreasing | L2HE-PR-CHEM-COMP-DEGR | R1 | 2021-09-15 | 2021-10-01
CP | Copper Plated String Components Cleaning Procedure | L2HE-PR-CHEM-CST-DEGR | R1 |  |  | T. Ganey | A. Mitchell | R. Fiedler | J. Hogan | [7 empty] | Process developed for L2PRD will be used. Combines bellow specific instructions with instructions for all copper plated string components. | CP
OD | Cavity String Gate Valve Leak Test Procedure (C100/C75) | L2HE-PR-CLNRM-AMGV-LEAK | R1 | 2021-10-11 | 2021-10-26 | D. Sarvansky | D. Forehand | K. Davis | J. Hogan
R0 | Cavity 1st Assembly Procedure | L2HE-PR-CLNRM-CAV-ASSY1 | R1 | 2021-12-01 | [12 empty] | linked in prototype travelers. Update to latest procedure template and send out | R0
R0 | Cavity 2nd Assembly Procedure | L2HE-PR-CLNRM-CAV-ASSY2 | R1 | 2021-12-01 | [12 empty] | CLNRM-CAV-ASSY2 traveler references this document but I have been unable to locate it to move it into the L2HE folder | R0
15 | Cavity String Assembly Procedure | L2HE-PR-CLNRM-CST-ASSY | R1 | 2021-10-26 | 2021-10-26 | T. Ganey | D. Forehand | K. Davis | J. Hogan | [7 empty] | Complete re-write of JLab L2PRD string assembly process to use purge system, without HPR, including new upstream and downstream manifolds
15 | Ionized Nitrogen Parts Cleaning | L2HE-PR-CLNRM-CST-IONCLN | R1 | 2021-10-26 | 2021-10-26 | D. Forehand | C. Dreyfuss | K. Davis | J. Hogan | [7 empty] | No significant changes from L2PRD procedure anticipated
R0 | Cavity String Assembly Tooling Preparation | L2HE-PR-CLNRM-CST-PREP | R1 | 2021-12-01 | 2022-02-01 | [11 empty] | Delete? | R0
15 | Upstream Gate Valve Sub-Assembly | L2HE-PR-CLNRM-GV1SA-ASSY | R0 | 2021-10-26 | 2021-10-26 | T. Ganey | C. Dreyfuss | K. Davis | J. Hogan | [7 empty] | Changes are required to support the purge system string assembly and use of Faraday Window Manifold (or alternate upstream manifold)
15 | Downstream Gate Valve Sub-Assembly | L2HE-PR-CLNRM-GV2SA-ASSY | R0 | 2021-10-26 | 2021-10-26 | T. Ganey | C. Dreyfuss | K. Davis | J. Hogan | [7 empty] | Changes are required to support the purge system string assembly and use of Faraday Window Manifold (or alternate upstream manifold)
15 | NEG Pump Manifold Assembly | L2HE-PR-CLNRM-NEG-ASSY | R0 | 2021-10-26 | 2021-10-26 | T. Ganey | C. Dreyfuss | K. Davis | J. Hogan
15 | FPC Warm Installation | L2HE-PR-CMA-FPCW-ASSY | R1 | 2021-10-26 | 2022-02-01 | N. Huque | K. DAVIS | J. Fischer | J. Hogan
CP | FPC WARM PART PROCEDURE | L2HE-PR-CMA-FPCW-INSP | R1 | [14 empty] | CP
15 | Cavity HOM Measurements and Tuning Procedure | L2HE-PR-CMA-HOM-TUNE | R1 | 2021-10-26 | 2022-02-01 | P. Owen | D. Forehand | D. Forehand | J. Hogan | [7 empty] | Procedure to go with L2HE-TUNE-HOM. Needs to be revised to reflect new software.
CP | FPC COLD PART PROCEDURE | L2HE-PR-INSP-FPCC | R3 | 2021-05-24 | 2020-05-15 | N. HUQUE | D. Forehand | K. Davis | C. Dreyfuss | K. Wilson | [7 empty] | CP
CP | Production Cavity Vertical Testing Procedure | L2HE-PR-VTA-CAV-VTRF | R1 | 2021-05-21 |  | C. WILSON | K. Davis |  | K. Wilson | [7 empty] | Procedure was updated to L2HE cavity vertical test specs and general VTA / RF testing instructions were updated to reflect current standard testing practices. | CP
CP | Cavity RF Inspection | L2HE-TUNE-CAV-RFIN | R2 | 2021-05-01 |  | J. Vennekate | D. Forehand | J. Hogan | K. WILSON | [6 empty] | CAV | This traveler is used to measure the cavity passband frequencies once it has arrived from the vendor. The RFIN measurements are compared to the pre-shipment vendor measurement, accounting for enviromental condition differences. If the RFIN measurments are in agreement with the vendor data, then it is assumed that the cavity was not damaged during shipment and can proceed toward VTRF. Discussions were had on whether a general spec for passband frequencies could be used instead of the vendor measurement; however, it was determined that comparision to the vendor measurements would continue to be used. No additional changes to the RFIN traveler or its calculation spreadsheet are required for the L2HE project. | CP
CP | Cavity Cooldown | L2HE-VTA-CAV-COOL | R1 | 2021-05-01 |  | J. KENT | J. Vennekate |  | K. Wilson |  | J. Hogan,kwilson | J. Hogan,kwilson | J. Hogan,kwilson,kdavis,jtkent |  |  |  | No changes from L2PRD traveler | CP
15 | VTA Single Cell Thermal Cycles | L2HE-VTA-CAV-THRMCYC | R1 | 2021-10-26 |  | D. Sarvansky | J. Vennekate | J. Kent
CP | Cavity VTA Test | L2HE-VTA-CAV-VTRF | R2 | 2021-05-01 |  | J. KENT | J. Vennekate |  | K. Wilson | [7 empty] | Traveler was updated to L2HE cavity vertical test specs and general VTA / RF testing instructions were updated to reflect current standard testing practices. Additional revision will be made to ensure traveler is in alignment with procedure and updated VTRF common format | CP
CP | Cavity Field Probe Feedthru Receiving Inspection | L2HE-VTA-FPFT-CSHK | R1 | 2020-10-22 |  | H. Park | D. Forehand | J. Kent | K. Wilson | H. Park | Ari, Reece | Park, Wilson | Park, Wilson | No | GMM-9434A |  |  | CP
CP | Cavity HOM Feedthru Receiving Inspection | L2HE-VTA-HMFT-CSHK | R1 | 2020-10-23 |  | H. Park | D. Forehand | J. Kent | K. Wilson | H. Park | Ari, Reece | Park, Wilson | Park, Wilson | No | GMM-9433A |  |  | CP
15 | SRFOPS Cavity Degreasing Procedure | SRFOPS-PR-CHEM-CAV-DEGR | R1 | 2021-10-26
Color Legend |  | Count | Percent
CP | Complete (CP) | 81 | 71.05%
NR | New Revision Out for Approval (NR) | 1 | 0.8772%
OA | Out for Approval (OA) | 6 | 5.263%
30 | Due in 30 Days | 0 | 0%
15 | Due in 15 Days | 9 | 7.895%
OD | Overdue | 4 | 3.509%
R0 | R0 Draft | 13 | 11.4%
| Remaining | 0 | 0%
| Total Traveler IDs | 114
Note on C32: Homer Samuels: Hold. Peter to Redo
Note on C82: Homer Samuels: Hold Still?
Note on C98: Homer Samuels: pull from L2PRD
Note on B105: Homer Samuels: David Sarvasky looking over
Note on C106: Homer Samuels: linked in prototype travelers. Update to latest procedure template and send out
Note on G124: Homer Samuels: Validate Author Name. Ganey?

## PROCEDURES
| PROCEDURE NAME | Procedure ID PROJ-PR-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author | SME | PRODUCTION LEAD | PROJECT LEAD | Tech Rep (SOTR) | NCR Informative | NCR Dispositioners | D3 Emails | Procedure(s), Name (if known) | Drawing(s), Name (if known) | Acronym from INV | Notes | Status | Section
OD | Ultra Sonic Cleaning Cavity Procedure | L2HE-PR-CHEM-CAV-USC |  | 2021-09-15 | [12 empty] | L2PRD/STP PULL FROM
OD | L2HE Cavity Degreasing | L2HE-PR-CHEM-COMP-DEGR | R1 | 2021-09-15 | 2021-10-01
CP | Copper Plated String Components Cleaning Procedure | L2HE-PR-CHEM-CST-DEGR | R1 |  |  | T. Ganey | A. Mitchell | R. Fiedler | J. Hogan | [7 empty] | Process developed for L2PRD will be used. Combines bellow specific instructions with instructions for all copper plated string components. | CP
OD | Cavity String Gate Valve Leak Test Procedure (C100/C75) | L2HE-PR-CLNRM-AMGV-LEAK | R1 | 2021-10-11 | 2021-10-26 | D. Sarvansky | D. Forehand | K. Davis | J. Hogan
R0 | Cavity 1st Assembly Procedure | L2HE-PR-CLNRM-CAV-ASSY1 | R1 | 2021-12-01 | [12 empty] | linked in prototype travelers. Update to latest procedure template and send out | R0
R0 | Cavity 2nd Assembly Procedure | L2HE-PR-CLNRM-CAV-ASSY2 | R1 | 2021-12-01 | [12 empty] | CLNRM-CAV-ASSY2 traveler references this document but I have been unable to locate it to move it into the L2HE folder | R0
15 | Cavity String Assembly Procedure | L2HE-PR-CLNRM-CST-ASSY | R1 | 2021-10-26 | 2021-10-26 | T. Ganey | D. Forehand | K. Davis | J. Hogan | [7 empty] | Complete re-write of JLab L2PRD string assembly process to use purge system, without HPR, including new upstream and downstream manifolds
15 | Ionized Nitrogen Parts Cleaning | L2HE-PR-CLNRM-CST-IONCLN | R1 | 2021-10-26 | 2021-10-26 | D. Forehand | C. Dreyfuss | K. Davis | J. Hogan | [7 empty] | No significant changes from L2PRD procedure anticipated
R0 | Cavity String Assembly Tooling Preparation | L2HE-PR-CLNRM-CST-PREP | R1 | 2021-12-01 | 2022-02-01 | [11 empty] | Delete? | R0
15 | Upstream Gate Valve Sub-Assembly | L2HE-PR-CLNRM-GV1SA-ASSY | R0 | 2021-10-26 | 2021-10-26 | T. Ganey | C. Dreyfuss | K. Davis | J. Hogan | [7 empty] | Changes are required to support the purge system string assembly and use of Faraday Window Manifold (or alternate upstream manifold)
15 | Downstream Gate Valve Sub-Assembly | L2HE-PR-CLNRM-GV2SA-ASSY | R0 | 2021-10-26 | 2021-10-26 | T. Ganey | C. Dreyfuss | K. Davis | J. Hogan | [7 empty] | Changes are required to support the purge system string assembly and use of Faraday Window Manifold (or alternate upstream manifold)
15 | NEG Pump Manifold Assembly | L2HE-PR-CLNRM-NEG-ASSY | R0 | 2021-10-26 | 2021-10-26 | T. Ganey | C. Dreyfuss | K. Davis | J. Hogan
15 | FPC Warm Installation | L2HE-PR-CMA-FPCW-ASSY | R1 | 2021-10-26 | 2022-02-01 | N. Huque | K. DAVIS | J. Fischer | J. Hogan
CP | FPC WARM PART PROCEDURE | L2HE-PR-CMA-FPCW-INSP | R1 | [14 empty] | CP
15 | Cavity HOM Measurements and Tuning Procedure | L2HE-PR-CMA-HOM-TUNE | R1 | 2021-10-26 | 2022-02-01 | P. Owen | D. Forehand | D. Forehand | J. Hogan | [7 empty] | Procedure to go with L2HE-TUNE-HOM. Needs to be revised to reflect new software.
CP | FPC COLD PART PROCEDURE | L2HE-PR-INSP-FPCC | R3 | 2021-05-24 | 2020-05-15 | N. HUQUE | D. Forehand | K. Davis | C. Dreyfuss | K. Wilson | [7 empty] | CP
CP | Production Cavity Vertical Testing Procedure | L2HE-PR-VTA-CAV-VTRF | R1 | 2021-05-21 |  | C. WILSON | K. Davis |  | K. Wilson | [7 empty] | Procedure was updated to L2HE cavity vertical test specs and general VTA / RF testing instructions were updated to reflect current standard testing practices. | CP
15 | SRFOPS Cavity Degreasing Procedure | SRFOPS-PR-CHEM-CAV-DEGR | R1 | 2021-10-26
Color Legend |  | Count | Percent
CP | Complete (CP) | 4 | 22.22%
NR | New Revision Out for Approval (NR) | 0 | 0%
OA | Out for Approval (OA) | 0 | 0%
30 | Due in 30 Days | 0 | 0%
15 | Due in 15 Days | 8 | 44.44%
OD | Overdue | 3 | 16.67%
R0 | R0 Draft | 3 | 16.67%
| Remaining | 0 | 0%
| Total Traveler IDs | 18
Note on B5: Homer Samuels: David Sarvasky looking over
Note on C6: Homer Samuels: linked in prototype travelers. Update to latest procedure template and send out

## CHEM
| Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author | SME | PRODUCTION LEAD | PROJECT LEAD | Tech Rep (SOTR) | NCR Informative | NCR Dispositioners | D3 Emails | Procedure(s), Name (if known) | Drawing(s), Name (if known) | Acronym from INV | Notes | Status | Section
CP | L2HE Cavity Horizontal Electropolish | L2HE-CHEM-CAV-HEP | R1 | 2021-08-01 | 2021-08-01 | A. Mitchell | T. Ganey | T. Ganey | J. Hogan |  | ashleya,kwilson | J. Hogan,vennekate,ganey | ashleya,vennekate,ganey,J. Hogan,kdavis,forehand,kwilson |  |  |  | HEP is not anticipated for the L2HE production run; however, is available if needed for any refurbishment cavities or other situations as may be required to support the project. No changes to reference documents is required. | CP
CP | Cavity High Pressure Rinse | L2HE-CHEM-CAV-HPR | R2 | 2021-09-15 |  | A. Wildeson | A. Mitchell | T. Ganey | J. Hogan |  | ashleya,kwilson | J. Hogan,vennekate,ganey | ashleya,vennekate,ganey,J. Hogan,kdavis,forehand,kwilson |  |  | CAV | Cavities that require reprocessing after a VTRF will receive a HPR - as was done in the L2PRD project. For L2PRD, this HPR was not captured in a traveler. For L2HE, chemistry travelers were created to capture the re-work steps for cavity vertical testing. The chemistry travelers follow standard chemistry processes and were only modified from other project travelers to reflect any 9-cell / L2HE specifics. HPR traveler does not have any references to update. | CP
OA | Laping | L2HE-CHEM-CAV-LAP | R1 | 2021-07-15 |  | A. Wildeson | A. Mitchell | T. Ganey | J. Hogan |  | ashleya,kwilson | J. Hogan,vennekate,ganey | ashleya,vennekate,ganey,J. Hogan,kdavis,forehand,kwilson |  |  |  | ROUTE WHEN DRAFT COMES | OA
CP | L2HE Cavity Ultrasonic Cleaning | L2HE-CHEM-CAV-USC | R2 | 2021-09-15 |  | A. Wildeson | A. Mitchell | T. Ganey | J. Hogan |  | ashleya,kwilson | J. Hogan,vennekate,ganey | ashleya,vennekate,ganey,J. Hogan,kdavis,forehand,kwilson |  |  |  | Cavities that require reprocessing after a VTRF with high radiation and/or very low FE onset may receive an USC prior to HPR - as was done in the L2PRD project. For L2PRD, this USC was not captured in a traveler. For L2HE, chemistry travelers were created to capture the re-work steps for cavity vertical testing. The chemistry travelers follow standard chemistry processes and were only modified from other project travelers to reflect any 9-cell / L2HE specifics. Cavities recieved from vendor will only require external clean / wipedown prior to VTRF. Therefore the traveler was revised to include directions for if the cavity is under vacuum and a YES/NO data field. | CP
CP | Components Cleaning | L2HE-CHEM-COMP-DEGR | R1 | 2021-07-01 |  | A. Mitchell | A. Wildeson |  | J. Hogan |  | ashleya | J. Hogan,ari | ashleya,ari,J. Hogan,kdavis,forehand |  |  |  | Chemistry work was not captured in travelers for L2PRD. Cavity components that require cleaning will be captured in this traveler. The traveler will be based on current component cleaning travelers and standard practices. | CP
Color Legend |  | Count | Percent
CP | Complete (CP) | 4 | 80%
NR | New Revision Out for Approval (NR) | 0 | 0%
OA | Out for Approval (OA) | 1 | 20%
30 | Due in 30 Days | 0 | 0%
15 | Due in 15 Days | 0 | 0%
OD | Overdue | 0 | 0%
R0 | R0 Draft | 0 | 0%
| Remaining | 0 | 0%
| Total Traveler IDs | 5

## CLNRM
| Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author | SME | PRODUCTION LEAD | PROJECT LEAD | Tech Rep (SOTR) | NCR Informative | NCR Dispositioners | D3 Emails | Procedure(s), Name (if known) | Drawing(s), Name (if known) | Acronym from INV | Notes | Status | Section
OA | Cavity String Gate Valve Leak Test | L2HE-CLNRM-AMGV-LEAK | R1 | 2021-10-11 | 2021-10-26 | D. Sarvansky | D. Forehand | K. Davis | J. Hogan | [7 empty] | L2PRD-CST-LEAK-AMGV | OA
R0 | BPM Magnet sub-assembly | L2HE-CLNRM-BPM-ASSY | R0 | 2021-10-11 | 2021-10-26 | D. FOREHAND | C. Dreyfuss | K. Davis | J. Hogan | [7 empty] | L2PRD-CST-ASSY-BPM | R0
NR | Cavity 1st Assembly | L2HE-CLNRM-CAV-ASSY1 | R2 | 2021-06-01 |  | D. Forehand | C. Dreyfuss |  | K. Wilson | [7 empty] | This traveler will be used with refurbishment and re-processed / cleaned cavities. It is not to be used with cavities arriving directly from the vendor. Due to the different length field probe tips that were in circulation during the refurbishment work, a statement to replace the field probe with the proper length if required was added to the traveler. A Yes/No data field was also added to capture if the FP was changed. Due to the use of purge-only string assembly and the removal of HPR prior to string assemlby, it was identified that the right angle valve must be positioned correctly (in accordance with the cavity drawing package) in order to fit up with the purge system during string assembly. Instructions will be added to this traveler to ensure that the valve is installed in accordance with the drawing. | NR
CP | Cavity 2nd Assembly | L2HE-CLNRM-CAV-ASSY2 | R1 | 2021-06-01 |  | D. Forehand | C. Dreyfuss |  | K. Wilson | [7 empty] | This traveler will be used with refurbishment and re-processed / cleaned cavities. It is not to be used with cavities arriving directly from the vendor. No changes from L2PRD traveler | CP
OD | Cavity Evacuation & Leak Test | L2HE-CLNRM-CAV-LEAK | R1 | 2021-09-01 | 2021-10-01 | D. Forehand | C. Dreyfuss |  | K. Wilson | [7 empty] | Since cavity tests will frequently occur on the dewar 5 test stand and occassionally cavities are prepared for a test stand before the test stand is available, a separate traveler will be used to capture the pump down (if applicable) and leak check. Cavities from the vendor will not require the pump down as these cavities will arrive under vacuum. Cavities that were reprocessed for an additional VTRF will need to be pumped down. All cavities will recieve a leak check. This traveler aims to simplify capturing of the evacuation and leak check data by consolidating all use cases into a single traveler.
CP | Transfer of L2PRD 9-cell cavities to Test Stands | L2HE-CLNRM-CAV-TSTD | R2 | 2021-06-01 |  | D. Forehand | C. Dreyfuss |  | K. Wilson | [7 empty] | Several changes from the L2PRD traveler were identified and suggested. The traveler was updated to allow single cells to be captured in addition to 9-cells. The RGA scan range was updated to the current standard range used at JLab. The decision to seperate out the evacuation and leak check data into a standalone travler will require that this traveler be revised. Also the acceptable leak rate will be updated to reflect the leak rate spec provided in the cavity assembly drawings. | CP
CP | Transfer of L2PRD 9-cell cavities to Test Stands for Dewar 5 | L2HE-CLNRM-CAV-TSTD5 | R1 | 2021-06-01 |  | D. Forehand | C. Dreyfuss |  | K. Wilson | [7 empty] | Several changes from the L2PRD traveler were identified and suggested. The traveler was updated to allow single cells to be captured in addition to 9-cells. The decision to seperate out the evacuation and leak check data into a standalone travler will require that this traveler be revised. Also the acceptable leak rate will be updated to reflect the leak rate spec provided in the cavity assembly drawings. | CP
CP | Cavity String Assembly (MAJOR CHANGE) | L2HE-CLNRM-CST-ASSY | R0 | 2021-11-01 | 2021-11-01 | T. Ganey | D. Forehand | K. Davis | J. Hogan | [7 empty] | Will require a major revision to include use of purge system without HPR | R0
CP | String Pump down, leak test and transfer to phase 1 | L2HE-CLNRM-CST-LEAK | R0 | 2021-11-01 | 2021-11-01 | D. Forehand | C. Dreyfuss | K. Davis | J. Hogan | [7 empty] | L2PRD-CST-ASSY-LEAK-R1 | R0
CP | FPC COLD PART | L2HE-CLNRM-FPCC-INSP | R3 | 2021-05-24 | 2020-05-15 | N. HUQUE | [8 empty] | 341082, P96406 | FPCC |  | CP
Color Legend |  | Count | Percent
CP | Complete (CP) | 6 | 60%
NR | New Revision Out for Approval (NR) | 1 | 10%
OA | Out for Approval (OA) | 1 | 10%
30 | Due in 30 Days | 0 | 0%
15 | Due in 15 Days | 0 | 0%
OD | Overdue | 1 | 10%
R0 | R0 Draft | 1 | 10%
| Remaining | 0 | 0%
| Total Traveler IDs | 10

## CMA
| Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author | SME | PRODUCTION LEAD | PROJECT LEAD | Tech Rep (SOTR) | NCR Informative | NCR Dispositioners | D3 Emails | Procedure(s), Name (if known) | Drawing(s), Name (if known) | Acronym from INV | Notes | Status | Section
CP | Cavity Beam Line Bellows PRCM Leak Test | L2HE-CMA-BLBP-LEAK | R1 | 2021-08-15 | 2021-08-01 | M. Marchlik | C. WIlcox | N/A | K. Wilson | M. Marchlik | Ari, Reece | Marchlik, Wilson | Marchlik, Wilson | Leak check spec 11141-S-0029 | F10041075 |  |  | CP
CP | Cavity Beam Line Bellows Short | L2HE-CMA-BLBS-LEAK | R1 | 2021-08-15 | 2021-08-01 | M. Marchlik | C. WIlcox | N/A | K. Wilson | M. Marchlik | Ari, Reece | Marchlik, Wilson | Marchlik, Wilson | Leak check spec 11141-S-0029 | F10023437 |  |  | CP
CP | Cavity String Weldment Upstream Bellows | L2HE-CMA-BLBU-LEAK | R1 | 2021-08-15 | 2021-05-10 | M. Marchlik | C. WIlcox | N/A | K. Wilson | M. Marchlik | Ari, Reece | Marchlik, Wilson | Marchlik, Wilson | Leak check spec 11141-S-0029 | F10075494 |  |  | CP
CP | String Beam Line Extension Downstream | L2HE-CMA-BLXD-LEAK | R1 | 2021-08-15 | 2021-08-01 | M. Marchlik | C. WIlcox | N/A | K. Wilson | M. Marchlik | Ari, Reece | Marchlik, Wilson | Marchlik, Wilson | Leak check spec 11141-S-0029 | F10052775 |  |  | CP
R0 | CM Assembly First | L2HE-CMA-CM-ASSY1 | R1 | 2021-10-26 |  | J. Fischer | N. Huque | A. Reilly | J. Hogan | [7 empty] | L2PRD-CM-ASSY-FRST | R0
R0 | CM Assembly Second | L2HE-CMA-CM-ASSY2 | R1 | 2021-10-26 |  | J. Fischer | N. Huque | A. Reilly | J. Hogan | [7 empty] | L2PRD-CM-ASSY-SCND | R0
R0 | CM Assembly Final | L2HE-CMA-CM-ASSYF | R1 | 2021-10-26 |  | J. Fischer | N. Huque | A. Reilly | J. Hogan | [7 empty] | L2PRD-CM-ASSY-FNAL | R0
R0 | Cryomodule Rework Traveler | L2HE-CMA-CM-REW | R1 | 2021-10-26 |  | J. Fischer | N. Huque | A. Reilly | J. Hogan | [7 empty] | L2PRD-CM-ASSY-REW | R0
R0 | Cryomodule Retrofit Traveler | L2HE-CMA-CM-RFIT | R1 | 2021-10-26 |  | J. Fischer | N. Huque | A. Reilly | J. Hogan | [7 empty] | L2PRD-CM-ASSY-RFIT | R0
R0 | Cryomodule Prep and Shipping to SLAC | L2HE-CMA-CM-SHIP | R1 | 2021-10-26 |  | J. Fischer | N. Huque | A. Reilly | J. Hogan | [7 empty] | L2PRD-CM-ASSY-SHIP | R0
CP | FPC WARM PART | L2HE-CMA-FPCW-INSP | R1 | 2021-05-24 | 2020-05-15 | N. HUQUE |  |  | J. Hogan | [5 empty] | 341081, P96394 | FPCW |  | CP
CP | Cavity Field Probe Feedthru Receiving Inspection | L2HE-CMA-FPFT-LEAK | R1 | 2020-10-21 |  | H. Park | C. WIlcox | N/A | K. Wilson | L. Zhao | Ari, Reece | Park, Wilson | Park, Wilson | Leak check spec 11141-S-0029 | GMM-9434A |  |  | CP
CP | Cavity HOM Feedthru Receiving Inspection | L2HE-CMA-HMFT-LEAK | R1 | 2020-10-21 |  | H. Park | C. WIlcox | N/A | K. Wilson | L. Zhao | Ari, Reece | Park, Wilson | Park, Wilson | Leak check spec 11141-S-0029 | GMM-9433A |  |  | CP
R0 | Cavity HOM Measurements and Tuning | L2HE-CMA-HOM-TUNE | R1 | 2021-10-26 | 2022-02-01 | P. Owen | D. Forehand | D. Forehand | J. Hogan | [7 empty] | L2PRD-CAV-HOM-TUNE | R0
CP | Upper Cold Mass Magnetic Hygiene Control | L2HE-CMA-UCM-DMAG | R1 | 2021-05-28 |  | G. Cheng | J. Fischer |  | J. Hogan | Cheng | Wilson, J. Hogan | Fischer, Cheng | Fischer, Cheng |  |  |  |  | CP
CP | Upper Cold Mass CMA Inspection | L2HE-CMA-UCM-INSP | R1 | 2021-05-28 |  | G. Cheng | J. Fischer | N/A | J. Hogan | G. Cheng | Katherine, J. Hogan | Gary, Fischer | Gary, Fischer |  | F10009954 |  |  | CP
R0 | Cryomodule Vacuum Vessel Assembly | L2HE-CMA-VV-ASSY | R1 | 2021-10-26 |  | J. Fischer | G. Cheng | A. Reilly | J. Hogan | [7 empty] | L2PRD-CM-ASSY-VV | R0
CP | Receiving CMA Inspection CM Vacuum Vessel | L2HE-CMA-VV-INSP | R1 | 2021-05-28 |  | G. Cheng | J. Fischer | N/A | J. Hogan | G. Cheng | Katherine, J. Hogan | Gary, Fischer | Gary, Fischer |  | F10026609 |  |  | CP
Color Legend |  | Count | Percent
CP | Complete (CP) | 10 | 55.56%
NR | New Revision Out for Approval (NR) | 0 | 0%
OA | Out for Approval (OA) | 0 | 0%
30 | Due in 30 Days | 0 | 0%
15 | Due in 15 Days | 0 | 0%
OD | Overdue | 0 | 0%
R0 | R0 Draft | 8 | 44.44%
| Remaining | 0 | 0%
| Total Traveler IDs | 18
Note on C15: Homer Samuels: Hold. Peter to Redo

## INSP
| Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author | SME | PRODUCTION LEAD | PROJECT LEAD | Tech Rep (SOTR) | NCR Informative | NCR Dispositioners | D3 Emails | Procedure(s), Name (if known) | Drawing(s), Name (if known) | Acronym from INV | Notes | Status | Section
CP | Cavity RF Inspection | L2HE-TUNE-CAV-RFIN | R2 | 2021-05-01 |  | J. Vennekate | D. Forehand | J. Hogan | K. WILSON | [6 empty] | CAV | This traveler is used to measure the cavity passband frequencies once it has arrived from the vendor. The RFIN measurements are compared to the pre-shipment vendor measurement, accounting for enviromental condition differences. If the RFIN measurments are in agreement with the vendor data, then it is assumed that the cavity was not damaged during shipment and can proceed toward VTRF. Discussions were had on whether a general spec for passband frequencies could be used instead of the vendor measurement; however, it was determined that comparision to the vendor measurements would continue to be used. No additional changes to the RFIN traveler or its calculation spreadsheet are required for the L2HE project. | CP
CP | Cavity Beam Line Bellows PRCM | L2HE-INSP-BLBP | R1 | 2021-07-26 | 2021-08-01 | M. Marchlik | G. DeKerlegand | L. Zhao | J. Hogan | C. Reece | Hannesv, Reece | Lzhao, Wilson | Lzhao, Wilson |  |  |  |  | CP
CP | Cavity Beam Line Bellows Short | L2HE-INSP-BLBS | R1 | 2021-07-26 | 2021-08-01 | M. Marchlik | G. DeKerlegand | L. Zhao | J. Hogan | M. Marchlik | [7 empty] | CP
CP | Cavity String Weldment Upstream Bellows | L2HE-INSP-BLBU | R1 | 2021-07-01 | 2021-05-10 | M. Marchlik | G. DeKerlegand | L. Zhao | J. Hogan | M. Marchlik | [7 empty] | CP
CP | String Beam Line Extension Downstream | L2HE-INSP-BLXD | R1 | 2021-07-01 |  | M. Marchlik | G. DeKerlegand | L. Zhao | J. Hogan | M. Marchlik | [7 empty] | CP
CP | Cavity Inspection | L2HE-INSP-CAV | R3 | 2021-08-01 |  | K. WILSON |  |  | J. Hogan | [6 empty] | CAV | Revision to add instructions to visually verify the right angle valve position. Since the cavity may not be disassembled prior to string assembly and the valve position is critical for fit up with the purge system, the valve position needs to be verified during the initial inspection (and flagged with an NCR if valve position is not correct). | CP
CP | Cryomodule Cool Down Cryogenic Valve (CDV) | L2HE-INSP-CDV | R1 | 2021-05-17 |  | J. Kent | J. Fischer | McEwen | J. Hogan | J. Kent | Katherine, J. Hogan | Kent, Wilson | Kent, Fischer |  |  |  |  | CP
CP | 300K Current Leads CF Flange Inspection | L2HE-INSP-CFL | R1 | 2021-04-01 |  | L. Lalitha | L. King | Morrone | J. Hogan | L. Lalitha | J. Hogan,kwilson | lalitha,king | lalitha,king,fisher,morrone |  |  |  |  | CP
CP | LCLS-II HE 2K Clamp Assembly Kit Inspection | L2HE-INSP-CLMP02K | R1 |  |  | L. Lalitha | L. King | J. Fischer | J. Hogan | L. Lalitha | Kwilson,J. Hogan | lalitha,king | lalitha,king,fischer |  |  |  |  | CP
CP | LCLS-II HE 5K Clamp Assembly Kit Inspection Traveler | L2HE-INSP-CLMP05K | R1 |  |  | L. Lalitha | L. King | J. Fischer | J. Hogan | L. Lalitha | Kwilson,J. Hogan | lalitha,king | lalitha,king,fischer |  |  |  |  | CP
CP | LCLS-II HE 50 K Clamp Assembly Kit Inspection Traveler | L2HE-INSP-CLMP50K | R1 |  |  | L. Lalitha | L. King | J. Fischer | J. Hogan | L. Lalitha | Kwilson,J. Hogan | lalitha,king | lalitha,king,fischer |  |  |  |  | CP
CP | LCLS-II HE Split-Quad Clamp Kit Inspection Traveler | L2HE-INSP-CLMPSQ | R1 |  |  | L. Lalitha | L. King | J. Fischer | J. Hogan | L. Lalitha | Kwilson,J. Hogan | lalitha,king | lalitha,king,fischer |  |  |  |  | CP
CP | FPC Waveguide Incoming Inspection | L2HE-INSP-FPCWG | R1 | 2021-10-15 | 2021-01-27 | N. HUQUE | M. Stirbet |  | J. Hogan | N. Huque | [5 empty] | FPCWG |  | CP
CP | Cavity Field Probe Feedthru Receiving Inspection | L2HE-INSP-FPFT | R1 | 2020-10-16 |  | L. Zhao | G. DeKerlegand | N/A | Wilson | L. Zhao | hannesv, Reece | lzhao, Wilson | lzhao, Wilson | No | GMM-9434A |  |  | CP
CP | Cavity HOM Feedthru Receiving Inspection | L2HE-INSP-HMFT | R1 | 2020-10-16 |  | L. Zhao | G. DeKerlegand | N/A | Wilson | L. Zhao | hannesv, Reece | lzhao, Wilson | lzhao, Wilson | No | GMM-9433A |  |  | CP
CP | Receiving Inspection CM Magnetic Shield Assembly | L2HE-INSP-IMAG | R1 | 2021-05-14 |  | G. Cheng | G. DeKerlegand | J. Fischer | J. Hogan | G. Cheng | Katherine, J. Hogan | Gary, Fischer | Gary, Fischer |  | F10048652 |  |  | CP
CP | Receiving Inspection CM Assembly, JT Cryogenic Valve | L2HE-INSP-JTV | R1 | 2021-05-17 |  | J. Kent | J. Fischer | A. McEwen | J. Hogan | J. Kent | Katherine, J. Hogan | Kent, Wilson | Kent, Fischer |  |  |  |  | CP
CP | Tuner Piezo Actuator Assembly Inspection | L2HE-INSP-PIEZO | R1 | 2021-03-05 | 2021-05-31 | J. Kent | P. Owen | N. Huque | J. Hogan | P. Owen | huque,kwilson | Powen, King | Powen, Huque, Wilson |  |  |  | Will be a batch traveler | CP
OA | Quadrapole Magnet Inspection | L2HE-INSP-QUAD | R1 | 2021-10-08 |  | L. Lalitha | L. King | M. Morrone | J. Hogan | L. Lalitha |  | Lakshmi, Wilson | Lakshmi, Wilson |  |  |  |  | OA
CP | End Lever Tuner Motor | L2HE-INSP-SM | R1 | 2021-04-01 | 2021-04-30 | L. King | P. Owen | N. Huque | J. Hogan | P. Owen | huque,kwilson | Powen, King | Powen, Huque, Wilson |  |  |  | Will be a batch traveler | CP
CP | End Lever Tuner Mechanical Frame Inspection | L2HE-INSP-TUNC | R1 | 2021-07-14 | 2021-08-15 | P. Owen | G. Dekerlegand | N. Huque | J. Hogan | P. Owen | kwilson | Powen, Huque, georged | Powen, Huque, Wilson |  | F10132292-B, F10138922-A |  |  | CP
CP | End Lever Tuner Extended Mechanical Frame Inspection Traveler | L2HE-INSP-TUNCX | R1 | 2021-07-14 | 2021-08-15 | P. Owen | G. Dekerlegand | N. Huque | Wilson / J. Hogan | [8 empty] | CP
CP | Inspection Summary Report | L2HE-INSR | R1 | [14 empty] | CP
Color Legend |  | Count | Percent
CP | Complete (CP) | 22 | 95.65%
NR | New Revision Out for Approval (NR) | 0 | 0%
OA | Out for Approval (OA) | 1 | 4.348%
30 | Due in 30 Days | 0 | 0%
15 | Due in 15 Days | 0 | 0%
OD | Overdue | 0 | 0%
R0 | R0 Draft | 0 | 0%
| Remaining | 0 | 0%
| Total Traveler IDs | 23

## INV
| Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author | SME | PRODUCTION LEAD | PROJECT LEAD | Tech Rep (SOTR) | NCR Informative | NCR Dispositioners | D3 Emails | Procedure(s), Name (if known) | Drawing(s), Name (if known) | Acronym from INV | Notes | Status | Section
CP | All Metal Gate Valve Inventory | L2HE-INV-AMGV | R1 | 2021-05-01 |  | M. Dickey | C. Barnes |  | J. Hogan | D. Savransky | Mdicky,J. Hogan | Kwilson,Dsavr | [5 empty] | CP
CP | Cavity Beam Line Bellows PRCM Inventory | L2HE-INV-BLBP | R1 | 2021-07-26 | 2021-08-01 | [12 empty] | CP
CP | Cavity Beam Line Bellows Short Inventory | L2HE-INV-BLBS | R1 | 2021-07-26 | 2021-08-01 | [12 empty] | CP
CP | Cavity String Weldment Upstream Bellows Inventory | L2HE-INV-BLBU | R1 | 2021-05-01 | 2021-05-10 | [12 empty] | CP
CP | String Beam Line Extension Downstream Inventory | L2HE-INV-BLXD | R1 | 2021-07-01 | [13 empty] | CP
CP | 2 Phase Beam Pipe Inventory | L2HE-INV-BP2PH | R1 | [14 empty] | CP
CP | Cavity Inventory | L2HE-INV-CAV | R1 | 2021-08-01 | 2020-05-15 | J. VENNEKATE | [11 empty] | CP
OA | LCLS-II HE Cernox Inventory Traveler | L2HE-INV-CERNOX | R1 | 2021-08-15 | 2021-10-01 | M. Dickey | C. Barnes | L. King | J. Hogan | L. King | [6 empty] | regular INV traveler | OA
CP | Current Lead Flange Inventory | L2HE-INV-CFL | R1 |  |  | M. Dickey | C. Barnes | J.Hogan | L. Lalitha |  | Mdickey,Hogan,kwilson | Lalitha,king | Lalitha,king,fischer,morrone |  |  |  |  | CP
CP | FPC COLD PART Inventory | L2HE-INV-FPCC | R1 | 2021-05-24 | 2020-05-15 | N. HUQUE | M. Dickey | C. Barnes | J. Hogan | N. Huque | Dickey,J. Hogan,kwilson | Huque | Huque,J. Hogan,kwilson |  |  |  |  | CP
CP | FPC WARM PART Inventory | L2HE-INV-FPCW | R1 | 2021-05-24 | 2020-05-15 |  |  |  | J. Hogan | N. HUQUE | [7 empty] | CP
CP | FPC Waveguide Inventory | L2HE-INV-FPCWG | R1 | 2021-05-01 | 2021-01-27 | Dickey | Barnes |  | Wilson |  | Wislon | Huque,Fischer | Huque,Fisher |  |  |  |  | CP
CP | Cavity Field Probe Feedthru Receiving Inventory | L2HE-INV-FPFT | R1 | 2021-05-19 |  | M. Dickey | C. Barnes |  | J. Hogan | L. Zhao | hannesv, Reece | lzhao, Wilson | lzhao, Wilson |  |  |  |  | CP
CP | Cavity HOM Feedthru Receiving Inventory | L2HE-INV-HMFT | R1 | 2021-05-19 |  | M. Dickey | C. Barnes |  | J. Hogan | L. Zhao | hannesv,reece | lzhao, Wilson | lzhao, Wilson |  |  |  |  | CP
CP | CM Magnetic Shield Assembly Inventory | L2HE-INV-IMAG | R1 | 2021-05-14 |  | M. Dickey | C. Barnes |  | J. Hogan | G. Cheng | Katherine, J. Hogan | Gary, Fischer | Gary, Fischer |  |  |  |  | CP
OA | Receiving Inspection CM Rod Invar 2-Phase Long | L2HE-INV-IROD2L | R1 | 2021-08-01 |  | A. O'Brien |  |  | J. Hogan | [7 empty] | Waiting on FERMI for response | OA
OA | Receiving Inspection CM Rod Invar 2-Phase | L2HE-INV-IROD2P | R1 | 2021-08-01 |  | A. O'Brien |  |  | J. Hogan | [7 empty] | Waiting on FERMI for response | OA
CP | CM Assembly, JT Valve Tube Kit Inventory | L2HE-INV-JTVTK | R1 | 2021-08-01 | [13 empty] | CP
CP | JT Cryogenic Valve Tube Kit Inventory | L2HE-INV-JTVTK | R1 | [14 empty] | CP
CP | Liquid He Level Downstream Inventory | L2HE-INV-LLDS | R1 | [14 empty] | CP
CP | Line Liquid Level Downstream Inventory | L2HE-INV-LLNDS | R1 | [14 empty] | CP
CP | Line Liquid Level Upstream Inventory | L2HE-INV-LLNUS | R1 | [14 empty] | CP
CP | Liquid He Level Upstream Inventory | L2HE-INV-LLUS | R1 | [14 empty] | CP
CP | Tuner Piezo Actuator Inventory | L2HE-INV-PIEZO | R1 | 2021-05-01 | 2021-05-31 | M. Dickey | C. Barnes |  | J. Hogan | P. Owen | mdickey,J. Hogan,areilly | powen | J. Hogan,powen,areilly |  |  |  |  | CP
CP | Quadrapole Magnet Inventory | L2HE-INV-QUAD | R1 | 2021-06-15 |  | M. Dickey | C. Barnes | M. Morrone | J. Hogan | L. Lalitha |  | Lakshmi, Wilson | Lakshmi, Wilson |  |  |  |  | CP
CP | End Lever Tuner Mechanical Frame Inventory | L2HE-INV-TUNC | R1 | 2021-05-14 |  | M. Dickey | C. Barnes | J. Hogan | P. Owen |  | kwilson,J. Hogan | cheng,fischer,powen | cheng,fischer |  |  |  |  | CP
CP | L2HE Extended Cold Tuner Inventory Traveler | L2HE-INV-TUNCX | R1 | 2021-05-14 |  | M. Dickey | C. Barnes |  | J. Hogan | P. Owen | kwilson,J. Hogan | cheng,fischer,powen | cheng,fischer |  |  |  |  | CP
CP | Upper Cold Mass CMA Inventory | L2HE-INV-UCM | R1 | 2021-05-18 | [13 empty] | CP
CP | CM Vacuum Vessel Inventory | L2HE-INV-VV | R1 | 2021-05-18 | [13 empty] | CP
Color Legend |  | Count | Percent
CP | Complete (CP) | 26 | 89.66%
NR | New Revision Out for Approval (NR) | 0 | 0%
OA | Out for Approval (OA) | 3 | 10.34%
30 | Due in 30 Days | 0 | 0%
15 | Due in 15 Days | 0 | 0%
OD | Overdue | 0 | 0%
R0 | R0 Draft | 0 | 0%
| Remaining | 0 | 0%
| Total Traveler IDs | 29
Note on C17: Homer Samuels: Hold Still?

## TESTING
| Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author | SME | PRODUCTION LEAD | PROJECT LEAD | Tech Rep (SOTR) | NCR Informative | NCR Dispositioners | D3 Emails | Procedure(s), Name (if known) | Drawing(s), Name (if known) | Acronym from INV | Notes | Status | Section
CP | Cryomodule Acceptance Test LERF | L2HE-LERF-CM-ACTS | R1 | 2021-09-01 |  | M. Drury | G. Ciovatti | J. Vennekatte | J. Hogan | [8 empty] | CP
R0 | Production Cryomodule Demagnetization | L2HE-LERF-CM-DMAG | R1 | 2021-08-31 |  | G. Cheng | J. Fischer | M. Drury | J. Hogan | Cheng | Wilson, J. Hogan | Fischer, Cheng | Fischer, Cheng |  |  |  | L2PRD-CM-DMAG-LERF-R1 | R0
CP | Cavity Cooldown | L2HE-VTA-CAV-COOL | R1 | 2021-05-01 |  | J. KENT | J. Vennekate |  | K. Wilson |  | J. Hogan,kwilson | J. Hogan,kwilson | J. Hogan,kwilson,kdavis,jtkent |  |  |  | No changes from L2PRD traveler | CP
15 | VTA Single Cell Thermal Cycles | L2HE-VTA-CAV-THRMCYC | R1 | 2021-10-26 |  | D. Sarvansky | J. Vennekate | J. Kent
CP | Cavity VTA Test | L2HE-VTA-CAV-VTRF | R2 | 2021-05-01 |  | J. KENT | J. Vennekate |  | K. Wilson | [7 empty] | Traveler was updated to L2HE cavity vertical test specs and general VTA / RF testing instructions were updated to reflect current standard testing practices. Additional revision will be made to ensure traveler is in alignment with procedure and updated VTRF common format | CP
CP | Cavity Field Probe Feedthru Receiving Inspection | L2HE-VTA-FPFT-CSHK | R1 | 2020-10-22 |  | H. Park | D. Forehand | J. Kent | K. Wilson | H. Park | Ari, Reece | Park, Wilson | Park, Wilson | No | GMM-9434A |  |  | CP
CP | Cavity HOM Feedthru Receiving Inspection | L2HE-VTA-HMFT-CSHK | R1 | 2020-10-23 |  | H. Park | D. Forehand | J. Kent | K. Wilson | H. Park | Ari, Reece | Park, Wilson | Park, Wilson | No | GMM-9433A |  |  | CP
Color Legend |  | Count | Percent
CP | Complete (CP) | 5 | 71.43%
NR | New Revision Out for Approval (NR) | 0 | 0%
OA | Out for Approval (OA) | 0 | 0%
30 | Due in 30 Days | 0 | 0%
15 | Due in 15 Days | 1 | 14.29%
OD | Overdue | 0 | 0%
R0 | R0 Draft | 1 | 14.29%
| Remaining | 0 | 0%
| Total Traveler IDs | 7
Note on C3: Homer Samuels: pull from L2PRD
Note on G6: Homer Samuels: Validate Author Name. Ganey?

## CWI
| Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author | SME | PRODUCTION LEAD | PROJECT LEAD | Tech Rep (SOTR) | NCR Informative | NCR Dispositioners | D3 Emails | Procedure(s), Name (if known) | Drawing(s), Name (if known) | Acronym from INV | Notes | Status | Section
CP | Upper Cold Mass Weld Inspection? | L2HE-CWI-UCM | R1 | 2021-05-28 |  | G. Cheng | A. JENORD | Fischer | J. Hogan | G. Cheng | Katherine, J. Hogan | Gary, Fischer | Gary, Fischer |  | F10009954 |  |  | CP
CP | Vacuum Vessel Receiving Weld Inspection | L2HE-CWI-VV | R1 |  |  | G. Cheng | A. JENORD | Fischer | J. Hogan |  | Kwilson, J. Hogan | Cheng, fischer | Cheng, fischer |  |  |  |  | CP
Color Legend |  | Count | Percent
CP | Complete (CP) | 2 | 100%
NR | New Revision Out for Approval (NR) | 0 | 0%
OA | Out for Approval (OA) | 0 | 0%
30 | Due in 30 Days | 0 | 0%
15 | Due in 15 Days | 0 | 0%
OD | Overdue | 0 | 0%
R0 | R0 Draft | 0 | 0%
| Remaining | 0 | 0%
| Total Traveler IDs | 2