## WorkLoading
|  |  |  | 2021 |  |  | 2022 | [11 empty] | 2023
|  |  |  | FY22 / Q1 |  |  | FY22 / Q2 |  |  | FY22 / Q3 |  |  | FY22 / Q4 |  |  | FY23 / Q1 |  |  | FY23 / Q2 |  |  | FY22 / Q3 |  |  | FY22 / Q4 |  |  | FY23 / Q1
TASK | LOE% | Start | End | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
P-Team Lead
MANAGEMENT RESPONSIBILITIES | 50%
Supervise
Software Projects (Design,Research,Plan)
Servers (CF & Oracle)
DocuShare (Access/Permissions)
PROGRAMMING RESPONSIBILITIES | 50%
Core Software |  | Now | Ongoing
CAPA |  | Now | 2022-01-30
SamTraxs II |  | Now | 2022-12-01 | bar: FY22 / Q4 JUL to FY23 / Q1 NOV
TPQM |  | Now | 2022-06-01
Quality WCDs |  | Now | 2022-06-01
Data Mining |  | 2022-01-30 | 2022-06-30
Security |  | 2022-06-30 | 2023-06-30 | bar: FY22 / Q4 JUL to FY22 / Q3 JUN
Documentation Coordinator (Allen)
Travelers | 50% | Now | ongoing
WCDs | 25% | Now | 2022-11-01 | bar: FY22 / Q4 JUL to FY23 / Q1 OCT
QMS | 10% | 2022-02-01 | 2023-02-02 | bar: FY22 / Q4 JUL to FY23 / Q2 JAN
COMMUNICATIONS | 15%
Training Slides |  | 2022-02-01 | 2022-06-01
Pansophy User Guides |  | 2022-06-01 | 2022-12-01 | bar: FY22 / Q4 JUL to FY23 / Q1 NOV
Pansophy Online Help |  | 2022-12-01 | 2023-06-01 | bar: FY23 / Q1 DEC to FY22 / Q3 MAY
Programmer (Megan)
Traveler Software (Conversion) | 50% | 2022-01-01 | 2022-06-01
D3-R3 | 15% | 2022-01-01 | 2022-03-01
NCR-R12 | 15% | 2022-03-01 | 2022-05-01
Data Mining Software (Grids/Graphs/Exports) | 20% | 2022-06-01 | 2022-12-01 | bar: FY22 / Q4 JUL to FY23 / Q1 NOV
Programmer (David/Contractor) |  |  | 2022-03-30
Project Portal: | 75% | Now | 2022-03-30
Production Reports: | 25% | 2022-01-01 | 2022-03-30
CCI Students (An, Sabrina, Abdulla)
SamTraxs (Current 3 students) |  | Now | 2021-12-17
SamTraxs Cont. | ?? | 2022-01-01 | 2022-12-30 |  |  |  | UNSUPPORTED | bar: FY22 / Q4 JUL to FY23 / Q1 DEC
HS Students (Paul, Yunseo)
QMS Documentation (Paul) |  | Now | 2022-05-30
Trams/Prams (Yunseo) |  | Now | 2022-05-30
Unsupported/Unassigned
Documentation:
Project Requriements for Pansophy
Serialization/Traceability
SRF Web Page
Programmers Manual for all of Pansophy
Programming:
FABrication Travelers
Process Flow
Component Traceability
QMS: Competence
QMS: Calibration
Data Mining Rework (Modularity)
Upgraded User Defined Query
New Forms: SNs, Acronyms, Component Reports
Upgraded Menu system
Backward Compatibility for Data Mining
Report Integrity & Validation
Batch Processing (Travelers/NCRs)
Data Assimilation (CMTF/VTRF/CMM)

## timeline
|  |  | P-Team LEAD | MEGAN | ISO Baseline | ALLEN | ISO Audit | MIKE | ALL | CCI Students | DAVID (6MO) | TERM1 (JAN) | TERM2 (MAR)
|  |  |  | 2022 | [5 empty] | 2023 |  |  |  | 2024
| TASKS | LOE % | FY22 | [5 empty] | FY23 |  |  |  | FY24 |  |  |  | FY24
|  |  | OCT-DEC | JAN-MAR |  | APR-JUN |  | JUL-SEP | OCT-DEC | JAN-MAR | APR-JUN | JUL-SEP | OCT-DEC | JAN-MAR | APR-JUN | JUL-SEP | OCT-DEC
MANAGEMENT | MANAGEMENT RESPONSIBILITIES
| PROGRAMMERS / CORE SOFTWARE | 15
| CCI STUDENTS (3) / SAMTRAXS | 10
| HSSSP STUDENTS (2) /WCDs & TPQM | 10
| SRFOPS / QMS | 15
SERVERS | MAINTENANCE / UPGRADES
MIS/CC | CF Security Patches / server reboots | ONGOING
| Upgrade to CF2021 | [8 empty] | 2023?
CORE | PANSOPHY CORE DEVELOPMENT
ISO MAJOR NON-CONFORMANCE (TRAV_OWNERS)
GRID / GRAPH UPGRADE/FIX
SECURITY | PANSOPHY SECURITY
ADD KEY SECURITY TO ALL PAGES
LOGIN SECURITY
DATA SECURITY
URL SECURITY
SQL INJECTION SECURITY
TRAVELERS | AUTOMATION / MAINTENANCE / UPGRADES
TBD | TRAV_ID is drop-down menus only
Traveler Template Updates (SNs)
Master Traveler/Procedure Acronyms (CLARIFY FORMAT)
SN Acronyms (update database & automate)
TBD | FABrication Travelers
Gigi has Danny filling out 2 travelers for every cavity assembly; The ASSY and the FAB travelers
Can something automatic be put into place?
Can Gigi be satisfied with a status board?
How to track cavity processing (when in pseudo-research)?
Paper traveler/checklist with part (BEING DONE NOW!)
TBD | Moving of Inventory from one project to another - how to trace?
UPGRADE OLD/ACTIVE PROJECTS TO NEW TRAV_ID
NCR UPGRADE (R12) - TO ALL PROJECTS
D3 UPGRADE (R3) - COMPLETE & TO ALL PROJECTS
TRAVELER HTML5 FORM FIELDS UPGRADE
TRAVELER "REQUIRED FIELDS" HIGHLIGHTED
REQUIRED FIELDS IN D3 AND NCR - MAKE AN EVENT POPUP VS HAVING TO SUBMIT THE PAGE, GET ERROR AND LOSE DATA
USERNAME - UPGRADE DROPDOWN LISTS
COMPLETE TRAVELERIZATION UPGRADE
NEW MULTI-FILE UPLOAD TO REPLACE FLASH VERSION
NCR/D3 AUTOMATED STATUS EMAILS
CLOSED PROJECT CONFIGURATION
traveler selection more options for searching
Batch Traveler Closing - more slection options
Batch Traveler Closing - ensuring data is complete
Batch Traveler Closing - is closer valid
?? | User choice email (new) adlib select
?? | Electronically signed word docs
?? | Favorites area for Pansophy Users
TRAVELER PRECHECK
?? | PETE HAS 200 FEEDTHRU TRAVELERS TO MODIFY, NO GROUP EDIT MODE
INVENTORY | PRIMeS |  | TBD
Components are not always going through inventory, which is where Serial Numbers are added to the database for Traveler usage.
Leaving components in old project areas is difficult for the system to track or have available in new project areas
!! | Acronyms are being randomly generated (WORK WITH TRAVELER SYSTEM)
!! | NO USE OF SYSTEM BY OPERATIONS TEAM (ON THE FLOOR)
USER PAGES (ENTRY FORMS) - TRAINING / REQUIRED USE OF
?? | SCANNERS AND/OR PHONE APP
STATUS ONLY (EX. PART INFORMATION/NCRS)
INTERACTION (EX. PART MOVING)
Modify Serialzation Procedure modification (Phil?)
PARTS | PART TRACEABILITY |  | TBD
PROCESS FLOW
C75 (Gigi) has a process flow for cavities, we didn't know, nor does it appear that traveler users know, therefore parts may not be advancing as expected.
No process flow for other components - this could be added to travelers
AUP/P1 travelers are together rather than separated by WCA to handle process flow - is this a standard convention we want to continue? Should we drop separating? Which projects can use? Large projects (production environment) separate travelers by WCA?
TRACEABILITY - WHAT / HOW ?
PROJECT TRAVELERS | TRAVELERS / REPORTS (SRFOPS PRODUCTION AREA)
| C20 | ACTIVE
TRAVELERS/PROCEDURES
| C20 | ACTIVE
| C50R | ACTIVE
| C75 | ACTIVE
MERGE INTO ER5C
ER5C (C20/C50R/C75)
| C100R | ACTIVE
OPERATIONS STATUS BOARDS/REPORTS/KPIs/CM DELIVERY
| C20 | ACTIVE
| C50R | ACTIVE
| C75 | ACTIVE
MERGE INTO ER5C
ER5C (C20/C50R/C75)
| C100R | ACTIVE
| SNS-PPU | ACTIVE
TRAVELERS/PROCEDURES
OPERATIONS STATUS BOARDS/REPORTS
VENDOR DATA
| LCLS-II HE | ACTIVE
TRAVELERS/PROCEDURES
OPERATIONS STATUS BOARDS/REPORTS
VENDOR DATA
| AUP | ACTIVE
TRAVELERS/PROCEDURES
OPERATIONS STATUS BOARDS/REPORTS
WMGRDR
TRAVELERS/PROCEDURES
OPERATIONS STATUS BOARDS/REPORTS
| NB3SN | ACTIVE
TRAVELERS/PROCEDURES
OPERATIONS STATUS BOARDS/REPORTS
| SRFRD ( R&D SMALL PROJECTS AREA) (EBW) (Move STP travelers here? Jacob questions STP usage) | ACTIVE
OPERATIONS STATUS BOARDS/REPORTS
| STP (for other Chemistry & Cavity processing) | ACTIVE
PROJECTS | PROJECT PORTAL AREA (EXTERNAL CUSTOMER'S AREA)
Project (SOWs & SQUAPs) What is being promised to customers for reports, data transfer, NCR reporting, access
PROCEDURALIZE "PANSOPHY REQUESTS OF PROJECTS" TO MAKE IT A STANDARD DOCUMENT
| SNS-PPU | ACTIVE
STATUS BOARDS
REPORTS/KPIS
DELIVERY DATA Report Per CM
| LCLS-II HE | ACTIVE
STATUS BOARDS
REPORTS/KPIS
DELIVERY DATA Report Per CM
| AUP | ACTIVE
STATUS BOARDS
REPORTS/KPIS
DELIVERY DATA
| NB3SN | ACTIVE
STATUS BOARDS
REPORTS/KPIS
DELIVERY DATA
DATA MINING | SRFOPS PRODUCTION AREA
REPORT INTEGRITY
STATUS BOARDS GRID FORMAT CHANGES
NCRS BY CM
CAV COMPARISON GRAPH
Automate TPQM (TRAMS/PRAMS)
USER-DEFINED QUERY
CMTF Canned Report
CM Locations update request (Ed) - New Project?
AUTO GENERATE/SIMPLIFY USER-CANNED REPORTS
AUTO GENERATE/SIMPLIFY STATUS BOARD CREATION
NCR OP/CL BY ENGR - NEEDS FIXED
NCR OP/CL DOES NOT EXPORT (LINKS ARE PART OF QUERY)
GRIDS - LINKS NOT WORKING CORRECTLY (LINKS ARE PART OF QUERY)
DATA MINING
DEPRECATED FEATURES
NEW NAMING CONVENTION
NEW WORK CENTER AREAS
QUALITY | QUALITY REPORTS/PROCESSES
ISO COMPLIANCE - OTHER GROUPS NEED TO UNDERSTAND (SRFOPS INS/OUTS)
QUALITY BOARD REPORTS
Numbers between reports don't match - what priority is this compared to other work?
Proposed New NCR graph (J. Harris)
COMPENTENCY
CALIBRATON
COMMS | DOCUMENTATION / TRAINING / HELP FILES
| USER ASSISTANCE PANSOPHY/DOCUSHARE | ONGOING
UPDATE PANSOPHY HELP PAGES (FASTHELP)
UPDATE PANSOPHY TRAINING SLIDES
| DocuShare Maintenance / Support | ONGOING
SRF WEB PAGE
PERIODIC PANSOPHY TRAINING SESSIONS
ASSIMILATION | AUTOMATION OF DATA TRANSFER FROM NATIVE FILE TO DB
VTA Dictionary ( create help files)
CMTF Dictionary (create help files)
CMM Data
CMTF xcel processing spreadsheet (Chris' Java Program)
CMTF traveler instantiation automation
VTA traveler instantiation automation
VTA SPEADSHEET TWEAKS (TPOWERS)
C50 CMTF AUTO DATA MACRO (2/18/18) (MCEWEN)
C50 ACTS SUMMARY SHEET (9/6/18)
SAMTRAXS | REVAMP PROJECT
EDX
READ/DISPLAY ORIGINAL DATA
DESIGN/BUILD NEW INPUT INTERFACE
DESIGN/BUILD NEW OUTPUT INTERFACE
OTHER | OTHER
KYOTO CAMERA USEAGE LOG
WAND CAMERA USEAGE LOG
CLEAN ROOM APP
LEARN TO BUILD APPS (UNITY)
NCR linked back to Originating Traveler
Web Usage reports (by user, by date, by area, by project)
Electronically Signed PDF Procedures/Travelers
Linked comment boxes
Menu Editor
Update license for SQLXL
M:drive Management/Permissions
UNIX groups/user permissions
DSDrive
Problem: macro enabled traveler doesn't email properly
a. SRF Website started by CC
i. Who should be invovled in designing requirements
ii. What is most important to do first
b. Pansophy Front Page
i. Video Viewer for VTRF results
ii. QA Board Stats
iii. Other SRFOPS announcements?

## decoder
VALERIE | PANSOPHY MANAGEMENT | SECURITY | CORE SOFTWARE
MEGAN | CORE SOFTWARE | DATA MINING | TRAVELER PROCESSING
ISO Baseline
ALLEN | TRAVELERS | TECH WRITER | WCDs
ISO Audit
MIKE
ALL
CCI Students | SAMTRAXS |  | (20hrs/wk 10wks)
DAVID (6MO) | PROJECT PORTAL | REPORTS | QMS
TERM1 (JAN) | S&T | SAMTRAXS | QMS
TERM2 (MAR) | PROJECT PORTAL | REPORTS | QMS
PAUL(HSSSP) | WCDs | QMS | (4-6hrs/wk sep-may)
YUNSEO (HSSSP) | WCDs | TRAMS/PRAMS | (4-6hrs/wk sep-may)
expected completion

## notes
VALERIE | MEGAN | DAVID | TERM | ALLEN | CCI STUDENTS | PAUL(HSSSP) | YUNSEO (HSSSP) | MIKE
PANSOPHY MANAGEMENT | CORE SOFTWARE | PROJECT PORTAL | S&T | TRAVELERS | SAMTRAXS | WCDs | WCDs | PRIMeS
SECURITY | DATA MINING | REPORTS | SAMTRAXS | TECH WRITER |  | QMS | TRAMS/PRAMS
CORE SOFTWARE | TRAVELER PROCESSING | QMS | QMS | WCDs | (20hrs/wk 10wks) | (4-6hrs/wk sep-may) | (4-6hrs/wk sep-may) | BACKUP PROGRAMMER
CAPA (2) UPGRADE TRAVELER MANAGEMENT | GRID/GRAPH UPGRADES (NEW SOFTWARE) | Batch Traveler Closing - more slection options | NCR Summary report for Projects | Electronically signed word docs | SAMTRAXS | Jacob wants help with ISO Process Owner Documentation (Carolyn?) | TRAV_ID is drop-down menus only | Components are not always going through inventory, which is where Serial Numbers are added to the database for Traveler usage.
SECURITY (LOGIN, SQL INJECTION, URLs, DATA/WEB FILE SYSTEM | FABrication Travelers | Batch Traveler Closing - ensuring data is complete | VTA Test (tester?) (Jacob says No) | VTA Dictionary ( create help files) | READ/DISPLAY ORIGINAL DATA | WCDs (L2HE, SRFOPS, etc) | Traveler Template Updates (SNs) | Leaving components in old project areas is difficult for the system to track or have available in new project areas
PROCESS FLOW | UPGRADE OLD/ACTIVE PROJECTS TO NEW TRAV_ID | Batch Traveler Closing - is closer valid | VTA reports (Jacob says no) (Justin's reporting) | CMTF Dictionary (create help files) | DESIGN/BUILD NEW INPUT INTERFACE | TRAVELERS/PROCEDURES UPGRADES | Master Traveler/Procedure Acronyms (CLARIFY FORMAT) | Acronyms are being randomly generated (WORK WITH TRAVELER SYSTEM)
C75 (Gigi) has a process flow for cavities, we didn't know, nor does it appear that traveler users know, therefore parts may not be advancing as expected. | NCR UPGRADE (R12) - TO ALL PROJECTS | MERGE INTO ER5C (C20/C50R/C75) | QUALITY BOARD REPORTS | TRAVELER PRECHECK | DESIGN/BUILD NEW OUTPUT INTERFACE |  | SN Acronyms (update database & automate) | NO USE OF SYSTEM BY OPERATIONS TEAM (ON THE FLOOR)
No process flow for other components - this could be added to travelers | D3 UPGRADE (R3) - COMPLETE & TO ALL PROJECTS | PRODUCTION REPORTS (C20/C50R/C75/ER5C/C100R/WMGRDR) | MetricsTBD | PETE HAS 200 FEEDTHRU TRAVELERS TO MODIFY, NO GROUP EDIT MODE |  |  | Automate TPQM (TRAMS/PRAMS) | USER PAGES (ENTRY FORMS) - TRAINING / REQUIRED USE OF
AUP/P1 travelers are together rather than separated by WCA to handle process flow - is this a standard convention we want to continue? Should we drop separating? Which projects can use? Large projects (production environment) separate travelers by WCA? | TRAVELER HTML5 FORM FIELDS UPGRADE | STATUS BOARDS/KPIs S(C20/C50R/C75/ER5C/C100R/WMGRDR) | Mircea's report | TRAVELERS/PROCEDURES (C20/C50R/C75/ER5C/C100R/WMGRDR/L2HE/SNSPPU/AUP/NB3SN/SRFRD/STP) |  |  |  | SCANNERS AND/OR PHONE APP
TRACEABILITY - WHAT / HOW ? | TRAVELER "REQUIRED FIELDS" HIGHLIGHTED | REPORTS BY CRYOMODULE | Proposed New Traveler graph (age) | VENDOR DATA |  |  |  | STATUS ONLY (EX. PART INFORMATION/NCRS)
Project (SOWs & SQUAPs) What is being promised to customers for reports, data transfer, NCR reporting, access | REQUIRED FIELDS IN D3 AND NCR - MAKE AN EVENT POPUP VS HAVING TO SUBMIT THE PAGE, GET ERROR AND LOSE DATA | PRODUCTION FLOOR PROCESS FLOW | Proposed New NCR graph (J. Harris will use Excel) | DOCUMENTATION / TRAINING / HELP FILES |  |  |  | INTERACTION (EX. PART MOVING)
PROCEDURALIZE "PANSOPHY REQUESTS OF PROJECTS" TO MAKE IT A STANDARD DOCUMENT | USERNAME - UPGRADE DROPDOWN LISTS | Menu Editor | CALIBRATION | SRFPJS Team Administrative (meetings/reports) |  |  |  | Modify Serialzation Procedure modification (Phil?)
a. SRF Website started by CC | COMPLETE TRAVELERIZATION UPGRADE | USER-DEFINED QUERY | COMPENTENCY | User Assistance/Help Docs/User questions
i. Who should be invovled in designing requirements | ER5C MERGE COMPLETION | CMTF Canned Report | PROJECT MANAGEMENT (no software, JH; WCDs/Masterlists) | USER ASSISTANCE PANSOPHY ERRORS
ii. What is most important to do first | NEW MULTI-FILE UPLOAD TO REPLACE FLASH VERSION | AUTO GENERATE/SIMPLIFY USER-CANNED REPORTS | TRACEABILITY - WHAT / HOW ? | Tuesday Tidbit (especially for authors)
b. Pansophy Front Page | NCR/D3 AUTOMATED STATUS EMAILS | AUTO GENERATE/SIMPLIFY STATUS BOARD CREATION | OPERATIONS (no software, JH) | UPDATE PANSOPHY HELP PAGES (FASTHELP)
i. Video Viewer for VTRF results | CLOSED PROJECT CONFIGURATION | DATA MINING | SUPPLIERS (no software, JH) | UPDATE PANSOPHY TRAINING SLIDES
ii. QA Board Stats | traveler selection more options for searching | DEPRECATED FEATURES | CAPA (no software, JH) | DocuShare Maintenance / Support
iii. Other SRFOPS announcements? | SRFOPS PRODUCTION AREA | NEW NAMING CONVENTION | SAMTRAXS | SRF WEB PAGE
| REPORT INTEGRITY | NEW WORK CENTER AREAS | READ/DISPLAY ORIGINAL DATA | PERIODIC PANSOPHY TRAINING SESSIONS
| STATUS BOARDS GRID FORMAT CHANGES | OTHER | DESIGN/BUILD NEW INPUT INTERFACE | GO THROUGH OFFICIAL HTML COURSE TO GET CERTIFIED.
| NCRS BY CM | KYOTO CAMERA USEAGE LOG | DESIGN/BUILD NEW OUTPUT INTERFACE
| CAV COMPARISON GRAPH | WAND CAMERA USEAGE LOG
| NCR OP/CL BY ENGR - NEEDS FIXED | CLEAN ROOM APP
| NCR OP/CL DOES NOT EXPORT (LINKS ARE PART OF QUERY) | NCR linked back to Originating Traveler
| GRIDS - LINKS NOT WORKING CORRECTLY (LINKS ARE PART OF QUERY) | Linked comment boxes