## Slide 1: L2HE
Color Legend |  | Count | Percent
CP | Complete (CP) | 79 | 69.30%
NR | New Revision Out for Approval (NR) | 1 | 0.88%
OA | Out for Approval (OA) | 7 | 6.14%
30 | Due in 30 Days | 0 | 0.00%
15 | Due in 15 Days | 0 | 0.00%
OD | Overdue | 12 | 10.53%
R0 | R0 Draft | 15 | 13.16%
 | Remaining | 0 | 0.00%
 | Total Traveler IDs | 114 | 
Please Submit any changes or questions to pansophy@jlab.org
Note:
Project Masterlist can be found in the project docushare folder
Traveler Acronym list can be found in Pansophy, under the User Tools > Traveler Tools drop downs
Due to the large number of approaching overdue and overdue travelers, the normal list cannot fit on this page. Please reference the subsequent pages for the traveler names

## Slide 2
Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author | Reviewer | Reviewer | Proj Manager
Out for Approval |  |  |  |  |  |  |  | 
Receiving Inspection CM Rod Invar 2-Phase Long | L2HE-INV-IROD2L | R1 | 8/1/21 |  | O'Brien |  |  | Hogan
Cryomodule Acceptance Test LERF | L2HE-LERF-CM-ACTS | R1 | 9/1/21 |  | M. Drury | G. Ciovatti | J. Vennekatte | J. Hogan
Laping | L2HE-CHEM-CAV-LAP | R1 | 7/15/21 |  | A. Wildeson | A. Mitchell | T. Ganey | J. Hogan
Cavity 1st Assembly | L2HE-CLNRM-CAV-ASSY1 | R2 | 6/1/21 |  | D. Forehand | C. Dreyfuss |  | K. Wilson
Quadrapole Magnet Inspection | L2HE-INSP-QUAD | R1 | 10/8/21 |  | L. Lalitha | L. King | M. Morrone | J. Hogan
LCLS-II HE Cernox Inventory Traveler | L2HE-INV-CERNOX | R1 | 8/15/21 | 10/1/21 | M. Dickey | C. Barnes | L. King | J. Hogan
Cavity String Gate Valve Leak Test | L2HE-CLNRM-AMGV-LEAK | R1 | 10/11/21 | 10/26/21 | D. Sarvansky | D. Forehand | K. Davis | J. Hogan
Receiving Inspection CM Rod Invar 2-Phase | L2HE-INV-IROD2P | R1 | 8/1/21 |  | A. O'Brien |  |  | J. Hogan
L2HE Traveler Listing

## Slide 3
Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author | Reviewer | Reviewer | Proj Manager
Overdue |  |  |  |  |  |  |  | 
 | L2HE-PR-CHEM-CAV-USC |  | 9/15/21 |  |  |  |  | 
L2HE Cavity Degreasing | L2HE-PR-CHEM-COMP-DEGR | R1 | 9/15/21 | 10/1/21 |  |  |  | 
Cavity Evacuation & Leak Test | L2HE-CLNRM-CAV-LEAK | R1 | 9/1/21 | 10/1/21 | D. Forehand | C. Dreyfuss |  | K. Wilson
VTA Single Cell Thermal Cycles | L2HE-VTA-CAV-THRMCYC | R1 | 10/26/21 |  | D. Sarvansky | J. Vennekate | J. Kent | 
Cavity HOM Measurements and Tuning Procedure | L2HE-PR-CMA-HOM-TUNE | R1 | 10/26/21 | 2/1/22 | P. Owen | D. Forehand | D. Forehand | J. Hogan
Cavity String Gate Valve Leak Test Procedure (C100/C75) | L2HE-PR-CLNRM-AMGV-LEAK | R1 | 10/11/21 | 10/26/21 | D. Sarvansky | D. Forehand | K. Davis | J. Hogan
Cavity String Assembly Procedure | L2HE-PR-CLNRM-CST-ASSY | R1 | 10/26/21 | 10/26/21 | T. Ganey | D. Forehand | K. Davis | J. Hogan
Ionized Nitrogen Parts Cleaning | L2HE-PR-CLNRM-CST-IONCLN | R1 | 10/26/21 | 10/26/21 | D. Forehand | C. Dreyfuss | K. Davis | J. Hogan
Upstream Gate Valve Sub-Assembly | L2HE-PR-CLNRM-GV1SA-ASSY | R0 | 10/26/21 | 10/26/21 | T. Ganey | C. Dreyfuss | K. Davis | J. Hogan
Downstream Gate Valve Sub-Assembly | L2HE-PR-CLNRM-GV2SA-ASSY | R0 | 10/26/21 | 10/26/21 | T. Ganey | C. Dreyfuss | K. Davis | J. Hogan
NEG Pump Manifold Assembly | L2HE-PR-CLNRM-NEG-ASSY | R0 | 10/26/21 | 10/26/21 | T. Ganey | C. Dreyfuss | K. Davis | J. Hogan
FPC Warm Installation | L2HE-PR-CMA-FPCW-ASSY | R1 | 10/26/21 | 2/1/22 | N. Huque | K. DAVIS | J. Fischer | J. Hogan
SRFOPS Cavity Degreasing Procedure | SRFOPS-PR-CHEM-CAV-DEGR | R1 | 10/26/21 |  |  |  |  | 
L2HE Traveler Listing Cont

## Slide 4
Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author | Reviewer | Reviewer | Proj Manager
R0 |  |  |  |  |  |  |  | 
Cavity 1st Assembly Procedure | L2HE-PR-CLNRM-CAV-ASSY1 | R1 | 12/1/21 |  |  |  |  | 
Cavity 2nd Assembly Procedure | L2HE-PR-CLNRM-CAV-ASSY2 | R1 | 12/1/21 |  |  |  |  | 
Cavity String Assembly Tooling Preparation | L2HE-PR-CLNRM-CST-PREP | R1 | 12/1/21 | 2/1/22 |  |  |  | 
Cavity HOM Measurements and Tuning | L2HE-CMA-HOM-TUNE | R1 | 10/26/21 | 2/1/22 | P. Owen | D. Forehand | D. Forehand | J. Hogan
BPM Magnet sub-assembly | L2HE-CLNRM-BPM-ASSY | R0 | 10/11/21 | 10/26/21 | D. FOREHAND | C. Dreyfuss | K. Davis | J. Hogan
Cavity String Assembly (MAJOR CHANGE) | L2HE-CLNRM-CST-ASSY | R0 | 11/1/21 | 11/1/21 | T. Ganey | D. Forehand | K. Davis | J. Hogan
String Pump down, leak test and transfer to phase 1 | L2HE-CLNRM-CST-LEAK | R0 | 11/1/21 | 11/1/21 | D. Forehand | C. Dreyfuss | K. Davis | J. Hogan
CM Assembly First | L2HE-CMA-CM-ASSY1 | R1 | 10/26/21 |  | J. Fischer | N. Huque | A. Reilly | J. Hogan
CM Assembly Second | L2HE-CMA-CM-ASSY2 | R1 | 10/26/21 |  | J. Fischer | N. Huque | A. Reilly | J. Hogan
CM Assembly Final | L2HE-CMA-CM-ASSYF | R1 | 10/26/21 |  | J. Fischer | N. Huque | A. Reilly | J. Hogan
Cryomodule Rework Traveler | L2HE-CMA-CM-REW | R1 | 10/26/21 |  | J. Fischer | N. Huque | A. Reilly | J. Hogan
Cryomodule Retrofit Traveler | L2HE-CMA-CM-RFIT | R1 | 10/26/21 |  | J. Fischer | N. Huque | A. Reilly | J. Hogan
Cryomodule Prep and Shipping to SLAC | L2HE-CMA-CM-SHIP | R1 | 10/26/21 |  | J. Fischer | N. Huque | A. Reilly | J. Hogan
Cryomodule Vacuum Vessel Assembly | L2HE-CMA-VV-ASSY | R1 | 10/26/21 |  | J. Fischer | G. Cheng | A. Reilly | J. Hogan
Production Cryomodule Demagnetization | L2HE-LERF-CM-DMAG | R1 | 8/31/21 |  | G. Cheng | J. Fischer | M. Drury | J. Hogan
L2HE Traveler Listing Cont Cont