## Slide 1: SNSPPU
Color Legend |  | Count | Percent
CP | Complete (CP) | 78 | 96.30%
NR | New Revision Out for Approval (NR) | 1 | 1.23%
OA | Out for Approval (OA) | 1 | 1.23%
30 | Due in 30 Days | 1 | 1.23%
15 | Due in 15 Days | 0 | 0.00%
OD | Overdue | 1 | 1.23%
 | Remaining | 0 | 0.00%
 | Total Traveler IDs | 81 | 
Out for Approval/New Revision
SNSPPU-CHEM-CAV-DEGR-R1*
SNSPPU-INSP-SFR-R1**
Approaching Overdue
SNSPPU-CMA-CM-SHIP-R1
Overdue
SNSPPU-CM-ACTS-R1
Please Submit any changes or questions to pansophy@jlab.org
Note:
Project Masterlist can be found in the project docushare folder
Traveler Acronym list can be found in Pansophy, under the User Tools > Traveler Tools drop downs
*The SNSPPU-CHEM-CAV-DEGR-R1 routing is overdue
**SNSPPU-INSP-SFR-R1 is approved and in the upload queue

## Slide 2
Out for Approval |  |  |  |  |  |  |  |  | 
Traveler Name |  | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author | Reviewer | Reviewer | Proj Manager
Cavity Degrease | SNSPPU-CHEM-CAV-DEGR | R1 |  |  | A. Mitchell | P. Dhakal | K. Davis | E. Daly | 
Space Frame Inspection | SNSPPU-INSP-SFR | R2 | 7/21/20 |  | M. Marchlik | J. Fischer | G. DeKerlegand | E. Daly | M. Marchlik
Overdue |  |  |  |  |  |  |  |  | 
Cryomodule Acceptance Test | SNSPPU-CM-ACTS | R1 | 11/1/21 | 11/1/21 | M. Drury | L. King |  | E. Daly | 
Approaching Due Date |  |  |  |  |  |  |  |  | 
Cryomodule Shipping | SNSPPU-CMA-CM-SHIP | R1 | 12/15/21 | 1/15/22 | J. Fischer | M. Marchlik | M. Wiseman | E. Daly | N. Huque
SNSPPU Traveler Listing