## Sheet1
NCR SEQ NUM | NCR OPEN DATE | NCR CLOSE DATE | TRAVELER ID | PART DESCRIPTION | SN | DESCRIBE COMMENT | INITIAL DISPOSITION | INITIAL DISPOSITION COMMENT | FINAL DISPOSITION | FINAL COMMENT
1 | 2020-11-08 | 2020-12-04 | AUP-PREP-DAMP-ITUBE | UNKN | 001 | DIM8 & DIM9 ARE POINTS ON THE 74.11 DIA PLANE WHERE THERE ARE 2 UNDERCUTS ON THE PLANE SURFACE. SEE ATTACHED PHOTOS. | Use As Is | Damaged area will be machined down in subsequent machining step
2 | 2020-11-08 | 2020-11-09 | AUP-PREP-DAMP-ITUBE | UNKN | 02 | OAL DIM 147.05 OOT. SEE ATTACHED REPORT. | Use As Is | Length will be shortened in downstream machining step. OOT length will allow this to occur
3 | 2020-11-08 | 2020-11-09 | AUP-PREP-DAMP-ITUBE | UNKN | 03 | OAL DIM 147.05 OOT. SEE ATTACHED REPORT. | Use As Is | Length will be machined to a shorter length in a downstream machining step
4 | 2021-01-08 | 2021-01-08 | AUP-PREP-DAMP-LDMCH | NIOBIUM CAN LID FINAL | 01 |  | Use As Is
5 | 2021-01-08 | 2021-01-08 | AUP-PREP-DAMP-LDMCH | NIOBIUM CAN LID FINAL | 02 | OOT dimensions in the attached file | Use As Is
6 | 2021-01-08 | 2021-01-08 | AUP-PREP-DAMP-LDMCH | NIOBIUM CAN LID FINAL | 03 | OOT dimensions in attached file | Use As Is
7 | 2021-01-08 | 2021-01-08 | AUP-PREP-DAMP-ITUBE | UNKN | 01 | Yield strength and elongation of raw material below spec. See attached | Use As Is | A non-conformance report was sent to CERN and uploaded in EDMS. The material was approved for use.
8 | 2021-01-08 | 2021-01-08 | AUP-PREP-DAMP-ITUBE | HHOM INNER TUBE | 02 | Material yield strength and elongation below spec. See attached | Use As Is | A non-conformance report was sent to CERN and uploaded to EDMS (see attached). The material was approved for use
9 | 2021-01-08 | 2021-01-08 | AUP-PREP-DAMP-ITUBE | HHOM INNER TUBE | 03 | Material yield strength and elongation are below spec (see attached) | Use As Is | Non-conformance report sent to CERN and uploaded to EDMS (see attached). Material was approved for use.
10 | 2021-02-01 | 2021-02-01 | AUP-PREP-DAMP-TEE |  | 002 | Dimensional non-conforming. Please see attached PDF. | Use As Is
11 | 2021-02-01 | 2021-04-23 | AUP-PREP-DAMP-TEE |  | 001 | Dimensional non-conforming. Please see attached. | Use As Is
12 | 2021-02-01 | 2021-02-01 | AUP-PREP-DAMP-TEE |  | 003 | Dimensional non-conforming. Please see attached. | Use As Is
13 | 2021-02-02 | 2021-05-06 | AUP-PREP-DAMP-TEE |  | 003 | Scratch/ding present. Please see attached picture. | Hold/Modify | Polish scratches | Use As Is
14 | 2021-04-13 | 2021-04-14 | AUP-PREP-CMN-DSCCRM | CERAMIC D40D14 | 08 | Found crack on S/N 08,see attached picture on step No 5 | Reject
15 | 2021-04-29 | 2021-06-08 | AUP-PREP-CMN-DSCCRM |  | 02 | Dimension OOT, see attached report. | Use As Is
16 | 2021-04-29 | 2021-04-29 | AUP-PREP-CMN-DSCCRM |  | 07 | Dimension OOT, see attached report. | Use As Is
17 | 2021-04-29 | 2021-06-09 | AUP-PREP-CMN-DSCCRM | CERAMIC D40D14 | 09 | Dimension OOT, see attached report. | Use As Is
18 | 2021-04-29 | 2021-04-29 | AUP-PREP-CMN-DSCCRM |  | 12 | Dimension OOT, see attached report. | Use As Is
19 | 2021-04-29 | 2021-04-29 | AUP-PREP-CMN-DSCCRM |  | 13 | Dimension OOT, see attached report. | Use As Is
20 | 2021-04-29 | 2021-05-05 | AUP-PREP-CMN-DSCCRM |  | 14 | Dimension OOT, see attached report. | Use As Is
21 | 2021-04-29 | 2021-06-09 | AUP-PREP-CMN-DSCCRM | CERAMIC D40D14 | 3Y | Dimension OOT, see attached report. | Use As Is
22 | 2021-05-21 | 2021-06-08 | AUP-ASSY-DAMP-HKTEE | HOOK AND TEE WELDMENT | 01 | NCR generated for dimensional non-conforming. Please see attached. | Use As Is
23 | 2021-07-02 |  | AUP-ASSY-DAMP-HKTEE |  | 02 | See attached inspection report for non-conforming dimensions.
24 | 2021-07-02 |  | AUP-ASSY-DAMP-HKTEE |  | 03 | See attached inspection report for non-conforming dimensions.
25 | 2021-08-06 | 2021-08-06 | AUP-ASSY-CMN-FLBRZ | CERAMIC D40D14 | 01 | Unbrazed area greater than 10% of brazed joint | Reject
26 | 2021-08-09 | 2021-08-09 | AUP-ASSY-CMN-FLBRZ | CERAMIC D40D14 | 10 | Ultrasonic inspection of the braze showed 89.48% brazed area. The spec is >90% | Use As Is | NCR has been sent to CERN for review
27 | 2021-08-10 | 2021-08-10 | AUP-ASSY-CMN-BRZAS | CERAMIC D40D14 | 01 | Failed leak check after brazing. Leaks around inside diameter of ceramic. Ceramic used was s/n 2X (without inner diameter chamfer) | Reject
28 | 2021-08-10 |  | AUP-ASSY-HHOMFT-HFTBRZ | CERAMIC D40D14 | 01 | Failed leak check after brazing. Leaks around inside diameter of ceramic. Ceramic used was s/n 1X (without inner diameter chamfer)
29 | 2021-09-27 | 2021-09-27 | AUP-ASSY-CMN-BRZAS | CERAMIC D40D14 | 05 | Large void of braze alloy around outside diameter of ceramic; excessive radial gap (.005") between ceramic OD and copper/stainless flange ID | Reject | Send to Inventory with a Red Tag