## Slide 1: SNSPPU
Color Legend |  | Count | Percent
CP | Complete (CP) | 79 | 96.34%
NR | New Revision Out for Approval (NR) | 0 | 0.00%
OA | Out for Approval (OA) | 2 | 2.44%
30 | Due in 30 Days | 0 | 0.00%
15 | Due in 15 Days | 0 | 0.00%
OD | Overdue | 1 | 1.22%
 | Remaining | 0 | 0.00%
 | Total Traveler IDs | 82 | 
Out for Approval/New Revision
SNSPPU-PR-CMTF-CM-WARM-R1*
SNSPPU-PR-CMTF-CM-COOL-R1*
Approaching Overdue
NONE
Overdue
SNSPPU-CMA-CM-SHIP-R1
Please Submit any changes or questions to pansophy@jlab.org
Note:
Project Masterlist can be found in the project docushare folder
Traveler Acronym list can be found in Pansophy, under the User Tools > Traveler Tools drop downs
*The two procedures out for approval are currently overdue

## Slide 2
Out for Approval |  |  |  |  |  |  |  |  | 
Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author | Reviewer | Reviewer | Proj Manager | SOTR
SNS-PPU CM Warmup Procedure | SNSPPU-PR-CMTF-CM-WARM | R1 |  |  | D. Savransky | N. Huque | M. Drury | E. Daly | 
SNS-PPU CM Cooldown Procedure | SNSPPU-PR-CMTF-CM-COOL | R1 |  |  | D. Savransky | N. Huque | M. Drury | E. Daly | 
Overdue |  |  |  |  |  |  |  |  | 
Cryomodule Shipping | SNSPPU-CMA-CM-SHIP | R1 | 12/15/21 | 1/15/22 | J. Fischer | M. Marchlik | M. Wiseman | E. Daly | N. Huque
Approaching Due Date |  |  |  |  |  |  |  |  | 
SNSPPU Traveler Listing