## Slide 1: L2HE
Color Legend |  | Count | Percent
CP | Complete (CP) | 92 | 83.64%
NR | New Revision Out for Approval (NR) | 0 | 0.00%
OA | Out for Approval (OA) | 1 | 0.91%
30 | Due in 30 Days | 0 | 0.00%
15 | Due in 15 Days | 0 | 0.00%
OD | Overdue | 6 | 5.45%
R0 | R0 Draft | 11 | 10.00%
 | Remaining | 0 | 0.00%
 | Total Traveler IDs | 110 | 
Please Submit any changes or questions to pansophy@jlab.org
Note:
Project Masterlist can be found in the project docushare folder
Traveler Acronym list can be found in Pansophy, under the User Tools > Traveler Tools drop downs
Due to the large number of approaching overdue and overdue travelers, the normal list cannot fit on this page. Please reference the subsequent pages for the traveler names

## Slide 2
Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author | Reviewer | Reviewer | Proj Manager | SOTR
Out for Approval |  |  |  |  |  |  |  |  | 
BPM Magnet sub-assembly | L2HE-CLNRM-BPM-ASSY | R1 | 10/11/21 | 10/26/21 | D. FOREHAND | C. Dreyfuss | K. Davis | J. Hogan | 
L2HE Traveler Listing
*The L2HE-CLNRM-BPM-ASSY routing is overdue.

## Slide 3
Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author | Reviewer | Reviewer | Proj Manager | SOTR
Overdue |  |  |  |  |  |  |  |  | 
L2HE Cavity Ultrasonic Cleaning Procedure | L2HE-PR-CHEM-CAV-USC |  | 9/15/21 |  |  |  |  |  | 
L2HE Cavity Degreasing | L2HE-PR-CHEM-COMP-DEGR | R1 | 9/15/21 | 10/1/21 |  |  |  |  | 
Cavity HOM Measurements and Tuning Procedure | L2HE-PR-CMA-HOM-TUNE | R1 | 10/26/21 | 2/1/22 | P. Owen | D. Forehand | D. Forehand | J. Hogan | 
Cavity String Gate Valve Leak Test Procedure (C100/C75) | L2HE-PR-CLNRM-AMGV-LEAK | R1 | 10/11/21 | 10/26/21 | D. Sarvansky | D. Forehand | K. Davis | J. Hogan | 
Cavity String Assembly Procedure | L2HE-PR-CLNRM-CST-ASSY | R1 | 10/26/21 | 10/26/21 | T. Ganey | D. Forehand | K. Davis | J. Hogan | 
FPC Warm Installation | L2HE-PR-CMA-FPCW-ASSY | R1 | 10/26/21 | 2/1/22 | N. Huque | K. DAVIS | J. Fischer | J. Hogan | 
SRFOPS Cavity Degreasing Procedure | SRF-MSPR-CHEM-CAV-DEGR | R1 | 10/26/21 |  |  |  |  |  | 
L2HE Traveler Listing Cont

## Slide 4
Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author | Reviewer | Reviewer | Proj Manager | SOTR
R0 |  |  |  |  |  |  |  |  | 
Cavity String Assembly (MAJOR CHANGE) | L2HE-CLNRM-CST-ASSY | R0 | 11/1/21 | 11/1/21 | T. Ganey | D. Forehand | K. Davis | J. Hogan | 
String Pump down, leak test and transfer to phase 1 | L2HE-CLNRM-CST-LEAK | R0 | 11/1/21 | 11/1/21 | D. Forehand | C. Dreyfuss | K. Davis | J. Hogan | 
CM Assembly First | L2HE-CMA-CM-ASSY1 | R1 | 10/26/21 |  | J. Fischer | N. Huque | A. Reilly | J. Hogan | 
CM Assembly Second | L2HE-CMA-CM-ASSY2 | R1 | 10/26/21 |  | J. Fischer | N. Huque | A. Reilly | J. Hogan | 
CM Assembly Final | L2HE-CMA-CM-ASSYF | R1 | 10/26/21 |  | J. Fischer | N. Huque | A. Reilly | J. Hogan | 
Cryomodule Rework Traveler | L2HE-CMA-CM-REW | R1 | 10/26/21 |  | J. Fischer | N. Huque | A. Reilly | J. Hogan | 
Cryomodule Retrofit Traveler | L2HE-CMA-CM-RFIT | R1 | 10/26/21 |  | J. Fischer | N. Huque | A. Reilly | J. Hogan | 
Cryomodule Prep and Shipping to SLAC | L2HE-CMA-CM-SHIP | R1 | 10/26/21 |  | J. Fischer | N. Huque | A. Reilly | J. Hogan | 
Cryomodule Vacuum Vessel Assembly | L2HE-CMA-VV-ASSY | R1 | 10/26/21 |  | J. Fischer | G. Cheng | A. Reilly | J. Hogan | 
Cavity HOM Measurements and Tuning | L2HE-CMA-HOM-TUNE | R1 | 10/26/21 | 2/1/22 | P. Owen | D. Forehand | D. Forehand | J. Hogan | 
L2HE Traveler Listing Cont Cont