## TRAVELERS
| Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author | Reviewer | Reviewer | Project Manager | SOTR | NCR Informative | NCR Dispositioners | D3 Emails | Procedure(s), Name (if known) | Drawing(s), Name (if known) | Acronym from INV | Notes | Status | Section
| Inventory | [17 empty] | SH
CP | C75 Cavity Receiving | C75-CAV-RECV-CAV | R1 | 2020-03-22 |  | G. Ciovati | M. Dickey |  | K. Macha | [8 empty] | CP
CP | Magnetic Shield Receive Traveler | C75-CAV-RECV-IMAG | R1 | 2020-05-12 |  | M. Dickey | G. Cheng |  | K. Macha | [7 empty] | Data needs to be backfilled | CP
CP | Nextor Pump for waveguide | C75-CPR-RECV-NEXTOR | R1 | 2020-06-30 |  | M. Dickey | G. Ciovati |  | K. Macha | [8 empty] | CP
CP | Capacitorr Pump for BL | C75-CM-RECV-CAPTOR | R1 | 2020-06-30 |  | M. Dickey | G. Ciovati |  | K. Macha | [8 empty] | CP
CP | Cavity MDC gate valve | C75-CPR-RECV-GV40 | R1 | 2020-05-12 |  | M. Dickey | G. Ciovati |  | K. Macha | [8 empty] | CP
| Disassembly | [17 empty] | SH
CP | C20 Cavity pair disassembly | C20-CPR-DISA | R1 | 2020-08-20 |  | D. Forhand | K. Davis |  | K. Macha | [8 empty] | CP
| C20 Cryounit Disassmbly | C20-CU-DISA | R2 |  |  | J. Fischer | K. Worland |  | K. Macha | [7 empty] | R2 is Ready for approval, R1 is in use (Talk with John, is this ready?) RadCon update?
CP | C20 Cryomodule Disassembly | C20-CM-DISA | R1 | 2019-10-21 |  | J. Fischer | K. Worland |  | K. Macha | [8 empty] | CP
CP | Cavity Pair Disasseembly | C75-CPR-DISA | R1 | 2019-02-16 |  | D. Forehand | K. Davis |  | K. Macha | [7 empty] | Danny to revise. Belongs in C20 project. May require C75 disassembly some day | CP
CP | Cryounit Disassmbly | C75-CU-DISA | R2 | 2017-10-05 |  | J. Fischer | K. Worland |  | K. Macha | [8 empty] | CP
| Cryomodule Disassembly | C75-CM-DISA | R2 |  |  | J. Fischer | K. Worland |  | K. Macha
Cavity Disasseembly
| Cavity Fabrication | [17 empty] | SH
CP | Weld Prep BCP | C75-CAV-BCP-COMP | R2 | 2018-03-16 |  | G. Ciovati | J. Follkie |  | K. Macha | [8 empty] | CP
CP | BCP of C75 Dumbbells | C75-CAV-BCP-DBEL | R1 | 2018-07-30 |  | G. Giovati | A. Mitchell |  | K. Macha | [8 empty] | CP
CP | BCP Half Cell | C75-CAV-CHEM-BCP-HCEL | R1 | 2018-01-18 |  | G. Ciovati | A. Mitchell |  | K. Macha | [8 empty] | CP
CP | BCP of C75 Cavity Flanges | C75-CAV-CHEM-BCP-FLNG | R1 | 2019-05-20 |  | G. Ciovati | A. Mitchell |  | K. Macha | [8 empty] | CP
CP | Cavity Fabrication | C75-CAV-FAB | R1 | 2018-02-01 |  | G. Ciovati | B. Clemens |  | K. Macha | [8 empty] | CP
CP | Deep Draw Cell Half | C75-CAV-FAB-HCEL | R3 | 2017-10-31 |  | G. Ciovati | S. Williams |  | K. Macha | [8 empty] | CP
CP | C75 Half-Cells Heat Tratment | C75-CAV-HEAT-HCEL | R1 | 2018-01-30 |  | G. Ciovati | D. Forehand |  | K. Macha | [8 empty] | CP
CP | Dumbbell Dimensional Inspection | C75-CAV-INSP-DBEL | R1 | 2018-07-23 |  | A. DeKerlegand | G. Ciovati |  | K. Macha | [8 empty] | CP
CP | FPC Beamtube Inspection | C75-CAV-INSP-FPCBT | R1 | 2018-04-17 |  | A. DeKerlegand | G. Ciovati |  | K. Macha | [8 empty] | CP
CP | Inspect C20 End group after machining prep for C75 | C75-CAV-INSP-FPCEG | R1 | 2018-09-14 |  | A. DeKerlegand | G. Ciovati |  | K. Macha | [8 empty] | CP
CP | half-cell inspection | C75-CAV-INSP-HCEL | R4 | 2018-03-01 |  | A. DeKerlegand | G. Ciovati |  | K. Macha | [8 empty] | CP
CP | Material receipt inspection - Nb Discs | C75-CAV-INSP-NB | R1 | 2017-12-12 |  | A. DeKerlegand | G. Ciovati |  | K. Macha | [8 empty] | CP
CP | Material receipt inspection - Nb Ingot | C75-CAV-INSP-NBI | R1 | 2017-12-12 |  | G. Cheng | G. Ciovati |  | K. Macha | [8 empty] | CP
CP | Inspection Stiffening rings | C75-CAV-INSP-SRING | R1 | 2018-02-23 |  | A. DeKerlegand | G. Ciovati |  | K. Macha | [8 empty] | CP
CP | Dumbbell RF measurement | C75-CAV-RFIN-DBEL | R1 | 2018-02-02 |  | G. Ciovati | F. Marhauser |  | K. Macha | [8 empty] | CP
CP | Half Cell RF Measurement | C75-CAV-RFIN-HCEL | R1 | 2018-03-06 |  | G. Ciovati | F. Marhauser |  | K. Macha | [8 empty] | CP
CP | End Half Cell RF Measurement | C75-CAV-RFIN-EHCEL | R1 | 2018-03-06 |  | G. Ciovati | F. Marhauser |  | K. Macha | [8 empty] | CP
CP | C75 Processing | C75-CAV-PROC | R2 | 2018-01-16 |  | V. Bookwalter | K. Davis |  | K. Macha | [8 empty] | CP
CP | C75 Half-Cell and tube forming | CP-C75-CAV-FAB-HCEL | R1 | 2017-10-24 |  | G. Ciovati | S. Williams |  | K. Macha | [8 empty] | CP
CP | C75 Dumb-Bell and end half cells RF inspection | CP-C75-CAV-RFIN | R1 | 2018-06-11 |  | G. Ciovati | F. Marhauser |  | K. Macha | [8 empty] | CP
CP | C75 Half-Cells Insepection, Grinding and Polishing | C75-CAV-PROC-POL-DBEL | R2 | 2018-07-27 |  | G. Ciovati | A. Palczewski |  | K. Macha | [8 empty] | CP
| Component Prepreation | [17 empty] | SH
| Inspection | [17 empty] | SS
CP | C75 Cavity Optical Inspection | C75-CAV-INSP-OPTK | R1 | 2019-04-08 |  | G. Ciovati | R. Geng |  | K. Macha | [8 empty] | CP
CP | C75 Cavity Flange Component inspection | C75-INSP-FLG-COMP | R1 | 2020-08-18 |  | A. DeKerlegand | K. Macha |  | K. Macha | [8 empty] | CP
CP | Cebaf Cryomodule Dogleg Assembly Inspection | C75-CPR-INSP-DGLG | R6 | 2019-04-30 |  | A. DeKerlegand | S.Williams |  | K. Macha | [8 empty] | CP
CP | Dogleg Waveguide Cavity Flange Inspection | C75-CPR-INSP-DLCF | R1 | 2018-03-28 |  | A. DeKerlegand | S.Williams |  | K. Macha | [8 empty] | CP
CP | Dogleg Waveguide Window Flange Inspection | C75-CPR-INSP-DLWF | R1 | 2019-04-05 |  | A. DeKerlegand | S.Williams |  | K. Macha | [8 empty] | CP
CP | Dogleg Window Waveguide Section | C75-CPR-INSP-DLWS | R2 | 2020-10-15 |  | A. DeKerlegand | S.Williams |  | K. Macha | [7 empty] | Need PDF | CP
CP | Cryomodule End Dish and Bellows Assembly Dimensional Inspection | C75-CPR-INSP-ENDD | R1 | 2017-10-31 |  | A. DeKerlegand | G. Ciovati |  | K. Macha | [8 empty] | CP
CP | HOM Elbow Assembly Dimensional Inspection | C75-CPR-INSP-HOME | R1 | 2017-10-31 |  | A. DeKerlegand | G. Ciovati |  | K. Macha | [8 empty] | CP
CP | HOM Load Assembly Inspection | C75-CPR-INSP-HOML | R1 | 2017-10-31 |  | A. DeKerlegand | G. Ciovati |  | K. Macha | [8 empty] | CP
CP | Inner Adapter Dimensional Inspection | C75-CPR-INSP-INAD | R1 | 2020-04-28 |  | A. Dekerlegand | G. Ciovati |  | K. Macha | [8 empty] | CP
CP | Cryomodule Dogleg Window Ceramic Inspection | C75-CPR-INSP-WNCR | R1 | 2017-11-07 |  | A. Dekerlegand | G. Ciovati |  | K. Macha | [8 empty] | CP
CP | Cryomodule Dogleg Window Eyelet Inspection | C75-CPR-INSP-WNEY | R1 | 2017-10-31 |  | A. Dekerlegand | G. Ciovati |  | K. Macha | [8 empty] | CP
CP | Dogleg VTA Cold Testing | C75-CPR-VTRF-DGLG | R1 | 2018-02-19 |  | D. Forehand | F. Marhauser |  | K. Macha | [8 empty] | CP
CP | 5-Cell Cavity Dimensional Inspection | C75-CAV-INSP | R6 | 2020-05-06 |  | A. Dekerlegand | G. Ciovati |  | K. Macha | [8 empty] | CP
| Chemistry | [17 empty] | SS
CP | Acid Etching at the Chemical Fume Hood procedure | CP-STP-CAV-CHEM-ACID | R1 | 2017-07-25 |  | A. Mitchel | J. Follkie |  | K. Macha |  | ashleya,forehand,kdavis | macha,gciovati, | macha,gciovati,ashleya,forehand,kdavis |  |  |  |  | CP
CP | C75 Cavity Thickness Measurement | C75-CAV-CHEM-THK | R2 | 2019-01-25 |  | G. Ciovati | A. Mitchell |  | K. Macha |  | ashleya,forehand,kdavis | macha,gciovati, | macha,gciovati,ashleya,forehand,kdavis |  |  |  |  | CP
CP | C75 Chemistry HEP | C75-CAV-CHEM-HEP | R3 | 2020-10-20 |  | G. Ciovati | A. Mitchell |  | K. Macha |  | ashleya,forehand,kdavis | macha,gciovati, | macha,gciovati,ashleya,forehand,kdavis |  |  |  |  | CP
CP | C75 Cavity Degreasing | C75-CAV-CHEM-DEGR | R2 | 2018-02-21 |  | A. Mitchell | G. Ciovati |  | K. Macha |  | ashleya,forehand,kdavis | macha,gciovati, | macha,gciovati,ashleya,forehand,kdavis |  |  |  |  | CP
CP | C75 Cavity De-greasing | CP-C75-CAV-CHEM-USC | R2 | 2020-06-01 |  | A. Wildeson | G. Ciovati |  | K. Macha |  | ashleya,forehand,kdavis | macha,gciovati, | macha,gciovati,ashleya,forehand,kdavis |  |  |  |  | CP
CP | C75 HPR | C75-CHEM-CAV-HPR | R1 | 2018-02-21 |  | A. Mitchell | G. Ciovati |  | K. Macha |  | ashleya,forehand,kdavis | macha,gciovati, | macha,gciovati,ashleya,forehand,kdavis |  |  |  |  | CP
| C75 HPR Procedure | CP-C75-CHEM-CAV-HPR | R2 |  |  | A. Mitchell | G. Ciovati | K. Davis | [9 empty] | CP
CP | C75 Cavity Pair HPR Procedure | CP-C75-CPR-CHEM-HPR | R1 | 2020-02-19 |  | A. Mitchel | G. Ciovati |  | K. Macha |  | ashleya,forehand,kdavis | macha,gciovati, | macha,gciovati,ashleya,forehand,kdavis |  |  |  |  | CP
CP | C75 Cavity HPR Procedure | CP-C75-CAV-CHEM-HPR | R1 | 2020-02-01 |  | A. Mitchel | G. Ciovati |  | K. Macha |  | ashleya,forehand,kdavis | macha,gciovati, | macha,gciovati,ashleya,forehand,kdavis |  |  |  |  | CP
CP | C75 Cavity Flange Final Lapping Traveler | C75-CAV-CHEM-FLAP | R1 | 2019-05-17 |  | A. Wildeson | A. Mitchell |  | K. Macha |  | ashleya,forehand,kdavis | macha,gciovati, | macha,gciovati,ashleya,forehand,kdavis |  |  |  |  | CP
CP | C75 Cavity flange lapping procedure. | CP-C75-CAV-CHEM-FLAP | R1 | 2020-06-01 |  | A. Wildeson | A. Mitchell |  | G. Ciovati |  | ashleya,forehand,kdavis | macha,gciovati, | macha,gciovati,ashleya,forehand,kdavis |  |  |  |  | CP
CP | Dog Leg Flange Lapping Traveler | C75-CAV-LAP-DGLG | R1 | 2019-10-30 |  | A. Wildeson | A. Mitchell |  | K. Macha |  | ashleya,forehand,kdavis | macha,gciovati, | macha,gciovati,ashleya,forehand,kdavis |  |  |  |  | CP
CP | Field Probe Flange Lapping Traveler | C75-CAV-LAP-FPFT | R1 | 2019-10-30 |  | A. Wildeson | A. Mitchell |  | K. Macha |  | ashleya,forehand,kdavis | macha,gciovati, | macha,gciovati,ashleya,forehand,kdavis |  |  |  |  | CP
CP | End Dish Flange Lapping Traveler | C75-CAV-LAP-ENDD | R1 | 2019-10-30 |  | A. Wildeson | A. Mitchell |  | K. Macha |  | ashleya,forehand,kdavis | macha,gciovati, | macha,gciovati,ashleya,forehand,kdavis |  |  |  |  | CP
CP | Inner Adapter Flange Lapping Traveler | C75-CAV-LAP-INAD | R1 | 2019-10-30 |  | A. Wildeson | A. Mitchell |  | K. Macha |  | ashleya,forehand,kdavis | macha,gciovati, | macha,gciovati,ashleya,forehand,kdavis |  |  |  |  | CP
CP | Warm Window Assembly Lapping Traveler | C75-CAV-LAP-WIN | R1 | 2019-11-06 |  | A. Wildeson | A. Mitchell |  | K. Macha |  | ashleya,forehand,kdavis | macha,gciovati, | macha,gciovati,ashleya,forehand,kdavis |  |  |  |  | CP
CP | Warm Window Lapping Traveler | C75-CAV-LAP-WINW | R1 | 2019-11-06 |  | A. Wildeson | A. Mitchell |  | K. Macha |  | ashleya,forehand,kdavis | macha,gciovati, | macha,gciovati,ashleya,forehand,kdavis |  |  |  |  | CP
CP | C75 Components flange lapping procedure. | CP-C75-CPR-LAP-COMP | R1 | 2020-06-01 |  | A. Wildeson | A. Mitchell |  | K. Macha |  | ashleya,forehand,kdavis | macha,gciovati, | macha,gciovati,ashleya,forehand,kdavis |  |  |  |  | CP
CP | C75 Flange BCP Procedure | CP-C75-CAV-CHEM-BCPFL | R1 | 2020-08-11 |  | A. Mitchell | G. Ciovati |  | K. Macha |  | ashleya,forehand,kdavis | macha,gciovati, | macha,gciovati,ashleya,forehand,kdavis |  |  |  |  | CP
OD | Baking in nitrogen oven | CP-STP-CAV-CHEM-BAKE | R1 | 2021-08-27 |  | A. Mitchell | K. Davis |  | K. Macha |  | ashleya,forehand,kdavis | macha,gciovati, | macha,gciovati,ashleya,forehand,kdavis |  |  |  | Working on this
CP | C75 Gate Valve Degreasing | CP-C75-CPR-DEGR-GV15 | R1 | 2020-05-04 |  | G. Gross | A. Mitchell |  | K. Macha |  | ashleya,forehand,kdavis | macha,gciovati, | macha,gciovati,ashleya,forehand,kdavis |  |  |  |  | CP
CP | C75 HOM Load Degreasing Procedure | CP-C75-CPR-CHEM-DEGR-HOML | R1 | 2020-06-01 |  | G. Gross | A. Mitchell |  | K. Macha |  | ashleya,forehand,kdavis | macha,gciovati, | macha,gciovati,ashleya,forehand,kdavis |  |  |  |  | CP
CP | C75 BCP Weld-prep etch | CP-C75-CAV-BCP-COMP-R1 | R1 | 2018-03-16 |  | G. Ciovati | R. Geng |  | K. Macha |  | ashleya,forehand,kdavis | macha,gciovati, | macha,gciovati,ashleya,forehand,kdavis |  |  |  |  | CP
CP | Acid Etch rate measurement | CP-C75-CAV-BCP-ER | R1 | 2017-12-08 |  | G. Ciovati | J. Follkie |  | K. Macha |  | ashleya,forehand,kdavis | macha,gciovati, | macha,gciovati,ashleya,forehand,kdavis |  |  |  |  | CP
CP | C75 Cavity Pair HPR Procedure | CP-C75-CPR-CHEM-HPR | R1 | 2020-02-19 |  | A. Mitchel | G. Ciovati |  | K. Macha |  | ashleya,forehand,kdavis | macha,gciovati, | macha,gciovati,ashleya,forehand,kdavis |  |  |  |  | CP
CP | C75 Waveguide Extensions/ Adapter | CP-C75-CHEM-WGDX | R1 | 2020-06-01 |  | A. Wildeson | G. Ciovati |  | K. Macha |  | ashleya,forehand,kdavis | macha,gciovati, | macha,gciovati,ashleya,forehand,kdavis |  |  |  | Long Copper plated waveguide. Let Kurt know how you title. | CP
OD | C75 HEP procedure | CP-CAV-CHEM-HEP | R1 | 2021-08-27 |  | A. Mitchell | A. Wildeson |  | K. Macha |  | ashleya,forehand,kdavis | macha,gciovati, | macha,gciovati,ashleya,forehand,kdavis |  |  |  | Ask Ashley if this is needed?
CP | C75 UHV parts cleaning procedure | CP-STP-CAV-CHEM-DEGR | R1 |  |  | A. Mitchell | J. Follkie |  | K. Macha |  | ashleya,forehand,kdavis | macha,gciovati, | macha,gciovati,ashleya,forehand,kdavis |  |  |  | Locate and verify good | CP
CP | C75 Dogleg Chemisty & Degreasing | CP-C75-CPR-CHEM-DGLG | R1 | 2020-10-27 |  | A. Mitchell | G. Ciovati |  | K. Macha |  | ashleya,forehand,kdavis | macha,gciovati, | macha,gciovati,ashleya,forehand,kdavis |  |  |  |  | CP
CP | Warm Window Degreasing | CP-C75-CPR-CHEM-WIND | R1 | 2020-06-01 |  | A. Wildeson | G. Ciovati |  | K. Macha |  | ashleya,forehand,kdavis | macha,gciovati, | macha,gciovati,ashleya,forehand,kdavis |  |  |  |  | CP
CP | C75 HOM Elbow Lapping Procedure | C75-CHEM-HOME-LAP | R1 | 2020-09-22 |  | A. Wildeson | G. Ciovati |  | K. Macha |  | ashleya,forehand,kdavis | macha,gciovati, | macha,gciovati,ashleya,forehand,kdavis |  |  |  |  | CP
CP | C75 End Dish acid etching Procedure | CP-C75-CHEM-ENDD | R2 | 2020-09-15 |  | G. Gross | A. Mitchell |  | K. Macha |  | ashleya,forehand,kdavis | macha,gciovati, | macha,gciovati,ashleya,forehand,kdavis |  |  |  |  | CP
CP | C75 Elbow buffered chemistry polish Procedure | CP-C75-CPR-BCP-HOME | R1 | 2020-06-01 |  | G. Gross | A. Mitchell |  | K. Macha |  | ashleya,forehand,kdavis | macha,gciovati, | macha,gciovati,ashleya,forehand,kdavis |  |  |  | Need pictures | CP
CP | C75 Pair Components Preparation | C75-CHEM-COMP-DEGR | R2 | 2020-10-13 |  | A. Mitchell | G. Ciovati |  | K. Macha |  | ashleya,forehand,kdavis | macha,gciovati, | macha,gciovati,ashleya,forehand,kdavis |  |  |  |  | CP
CP | Centrifugal Barrel Polishing of C75 cavities | C75-CHEM-CAV-CBP | R1 |  |  | G. Ciovati | A. Mitchell |  | K. Macha |  | kdavis | Gciovati,macha,ashleya | Gciovati,kdavis,macha,ashleya | Centrifugal Barrel Polishing of C75 cavities Procedure |  |  |  | CP
CP | Centrifugal Barrel Polishing of C75 cavities Procedure | C75-PR-CHEM-CAV-CBP | R1 |  |  | A. Mitchell | G. Ciovati |  | K. Macha | [8 empty] | CP
CP | C75 Components Lapping Procedure | CP-C75-CHEM-COM-LAP | R1 |  |  | A. Wildeson | A. Mitchell | Ciovati | Macha | [8 empty] | CP
| Weld Inspection | [17 empty] | SS
| Leak Checks | [17 empty] | SS
| Assembly | [17 empty] | SS
CP | 5-Cell Cavity assembly for VTA test | C75-CLNRM-CAV-ASSY | R1 | 2020-09-28 |  | C. Dreyfuss | G. Ciovati |  | K. Macha | [8 empty] | CP
CP | 5 Cell Single Cavity Assembly | CP-C75-CAV-ASSY | R1 | 2020-09-28 |  | C. Dreyfuss | G. Ciovati |  | K. Macha | [8 empty] | CP
CP | C75 5-cell transfer to test stand | C75-CLNRM-CAV-TSTD | R1 | 2020-06-01 |  | C. Dreyfuss | G. Ciovati |  | K. Macha | [8 empty] | CP
CP | C75 Cavity Cage Install | CP-C75-CAV-ASSY-CAGE | R1 | 2020-06-01 |  | C. Dreyfuss | G. Ciovati |  | K. Macha | [8 empty] | CP
CP | Warm Cavity RF Tuning | C75-CAV-TUNE | R5 | 2019-05-20 |  | G. Ciovati | D. Forehand |  | K. Macha | [8 empty] | CP
CP | RF Tuning procedure | CP-C75-CAV-TUNE | [6 empty] | K. Macha | [7 empty] | Roland to work on this procedure 80% | CP
CP | Warm Window Brazed Assembly | C75-CU-BRAZ-WINW | R1 | 2018-08-20 |  | S. Williams | F. Maurhauser |  | K. Macha | [8 empty] | CP
CP | Dogleg Assembly | C75-CPR-ASSY-DGLG | R2 | 2020-05-05 |  | S. Williams | A. DeKerlegand |  | K. Macha | [8 empty] | CP
CP | C75 Parts Grinding | CP-C75-CAV-POL | R1 | 2018-01-31 |  | A. Polczewski | S. Williams | [10 empty] | CP
CP | Dogleg Ceramic/Eyelet Window Subassembly | C75-CPR-ASSY-WNCR | R2 | 2018-04-10 |  | S. Williams | A. DeKerlegand |  | K. Macha | [8 empty] | CP
CP | C75 Cavity Heattreat | C75-CAV-HEAT | R1 | 2018-07-26 |  | G. Ciovati | D. Forehand |  | K. Macha | [8 empty] | CP
CP | C75 HOM Load Brazing/ Assy | C75-FURN-HOML-BRAZ | R2 | 2020-05-05 |  | S. Williams | J. Guo |  | K. Macha | [8 empty] | CP
| Cavity Pair | [17 empty] | SH
| Assembly | [17 empty] | SS
CP | Pair Assembly - Cavity Evacuation and Leak Test | C75-CPR-ASSY-EVAC | R2 | 2020-06-01 |  | C. Dreyfus | G. Ciovati |  | K. Macha | [7 empty] | Ready for review within Danny's group | CP
CP | End Dish and MDC valve sub-assembly | C75-CLNRM-ENDD-ASSY | R1 | 2020-09-04 |  | C. Dreyfus | G. Ciovati |  | K. Macha | [7 empty] | Ready for approval | CP
CP | Pair Assembly | C75-CPR-ASSY-FNAL | R3 |  |  | C. Dreyfuss | D. Forehand |  | K. Macha | [7 empty] | Renamed to: C75-CPR-ASSY 1st assy, 2nd assy will be combined into this traveler to create one assy traveler. Need to add gauss check boxes appropriately. | CP
CP | C75 Ionized Nitrongen Component Cleaning Procedure | CP-C75-CPR-CLN-ION | R1 | 2020-02-22 |  | D. Forehand | C. Dreyfuss |  | K. Macha | [8 empty] | CP
CP | C75 Indium Pressing Procedure | CP-C75-CPR-ASSY-INPP | R1 | 2020-09-01 |  | C. Dreyfuss | D. Forehand |  | K. Macha | [8 empty] | CP
CP | Indium wire Cleaning | CP-C75-CPR-CLN-INWC | R1 | 2020-04-27 |  | C. Dreyfuss | D. Forehand |  | K. Macha | [7 empty] | Possible revision to reflect assembly time after cleaning | CP
CP | Cavity Pair Strongback setup procedure | CP-C75-CPR-ASSY-STBK | R1 | 2020-10-20 |  | C. Dreyfuss | D. Forehand |  | K. Macha | [8 empty] | CP
CP | C75 Cavity Pair Magnetic Hygiene Procedure | CP-C75-CPR-HYG-COMP | R1 | 2020-06-24 |  | G. Cheng | G. Ciovati |  | K. Macha | [8 empty] | CP
CP | C75 Inner adapter size/ prep | CP-C75-CPR-FAB-INPP | R1 | 2020-10-30 |  | C. Dreyfuss | D. Forehand |  | K. Macha | [7 empty] | In approval, Kirk and Tony | CP
CP | Pair Assembly Stack up | C75-CPR-ASSY-STKU | R1 |  |  | D. Forehand | G. Ciovati |  | K. Macha | [7 empty] | Danny wants to revise | CP
CP | Pair Warm Dewar Leak Test | C75-VTA-CPR-LEAKW | R1 | 2020-08-25 |  | G. Ciovati | D. Forehand |  | K. Macha | [8 empty] | CP
CP | C75 cavity pair desorption leak test | C75-VTA-CPR-LEAKD | R2 | 2020-08-25 |  | G. Ciovati | D. Forehand |  | K. Macha | [8 empty] | CP
CP | Pair Assembly Preparation for Turnover | C75-CPR-ASSY-TOVR | R2 |  |  | D. Forehand | G. Ciovati |  | K. Macha | [7 empty] | What's the deal here? In Pansophy but not being used. | CP
CP | Pair Assembly Transfer to Test Stand | C75-CLNRM-CAV-TSTD | R1 | 2020-10-29 |  | D. Forehand | G. Ciovati |  | K. Macha | [8 empty] | CP
CP | Leak check of C75 dogleg | C75-CPR-DGLG-LEAK | R1 | 2020-08-25 |  | G. Ciovati | D. Forehand |  | K. Macha | [8 empty] | CP
| Testing | [17 empty] | SS
CP | Cavity and Cavity Pair VTA Cooldown | C75-CPR-VTA-COOL | R1 | 2019-05-21 |  | P. Kushnick | G. Ciovati |  | K. Macha | [8 empty] | CP
| C75 cavity/ pair cooldown | CP-C75-VTA-COOL
CP | Cavities VTA RF Test | C75-CPR-VTRF | R4 | 2020-09-15 |  | G. Ciovati | F. Marhauser |  | K. Macha | [8 empty] | CP
CP | RF testing of C75 cavities in the VTA | CP-C75-CRP-VTRF | R2 | 2020-09-01 |  | G. Ciovati | K. Davis |  | K. Macha | [8 empty] | CP
CP | C75 Cavity Testing Using VTA RF Test Stand | CP-STP-CAV-VTA-OPS | R1 | 2019-07-15 |  | C. Wilson | G. Ciovati | [10 empty] | CP
| Inspection | [17 empty] | SS
CP | C75 Cavity Pair Inspection | C75-CPR-INSP | R2 | 2020-04-28 |  | A. DeKerlegand | G. Ciovati |  | K. Macha | [8 empty] | CP
| Cryounit | [17 empty] | SH
| Inspection | [17 empty] | SS
CP | Waveguide Extension Inspection | C75-CU-INSP-WGDX | R2 | 2017-10-31 |  | A. DeKerlegand | J. Fischer |  | K. Macha | [8 empty] | CP
CP | Warm Window Assembly Dimensional Inspection | C75-CU-INSP-WIN | R2 | 2017-10-31 |  | A. DeKerlegand | J. Fischer |  | K. Macha | [8 empty] | CP
CP | Warm Window Inspection | C75-CU-INSP-WINW | R2 | 2017-10-31 |  | A. DeKerlegand | J. Fischer |  | K. Macha | [8 empty] | CP
| Assembly | [17 empty] | SS
CP | Tuner Assembly | C75-CMACU-TUNE-ASSY | R1 | 2020-04-21 |  | J. Fischer | K. Worland |  | K. Macha | [8 empty] | CP
CP | C50 Ball Screw Drive Assembly Rebuild Procedure | CP-C75-CU-RWRK-CTUN | R1 | 2020-05-19 |  | J. Fischer | L. Page |  | K. Macha | [8 empty] | CP
CP | C75 Rotary Feed Thru Rebuilding | CP-C75-CU-RWRK-RTFT | R1 | 2020-05-19 |  | J. Fischer | K. Worland |  | K. Macha | [8 empty] | CP
CP | C75 Warm Tuning Procedure | CP-C75-CU-TUNE-TUNC | R2 | 2020-10-20 |  | J. Fischer | G. Ciovati |  | K. Macha | [7 empty] | In approval | CP
CP | Helium Vessel Assembly | C75-CMACU-HELV-ASSY | R1 | 2020-06-01 |  | J. Fischer | K. Worland |  | K. Macha | [8 empty] | CP
CP | CEBAF CM Rotary feedthru replacement | CP-C75-CU-RWRK-FTRT | R1 | 2020-04-23 |  | J. Fischer | K. Worland |  | K. Macha | [8 empty] | CP
CP | Vacuum Vessel Assembly | C75-CMACU-VV-ASSY | R1 | 2020-07-01 |  | J. Fischer | K. Worland |  | K. Macha | [7 empty] | Mostly written from C50, Needs revision | CP
CP | Waveguide Assembly | C75-CMACU-WG-ASSY | R1 | 2021-03-01 |  | J. Fischer | G. Ciovati |  | K. Macha | [7 empty] | Mostly written from C50, Needs revision | CP
CP | Cryomodule Beam Line Pumping procedure | CP-C75-CM-BPIP-PUMPSL | R1 | 2020-05-26 |  | C. Wilcox | J. Fischer |  | K. Macha | [8 empty] | CP
CP | Crymodule MLI Installation Procedure | CP-C75-CM-INST-MLI | R1 | 2020-06-09 |  | J. Fischer | K. Worland |  | K. Macha | [8 empty] | CP
CP | Activation of C75 FPC waveguide NEXTorr pump | CP-C75-CM-EVAC-NEG | R2 | 2020-04-09 |  | G. Ciovati | J. Fischer |  | K. Macha | [8 empty] | CP
OD | Beam line assembly procedure |  |  | 2021-08-15 |  | C. Wilcox | J. Fischer
OD | JT calibration procedure | CP-STP |  | 2021-08-15 |  | K. Worland | J. Fischer
OD | Bridging bellows | CP-C75-CMA-BRBP | R1 | 2021-08-15 |  | C. Wilcox | J. Fischer |  | K. Macha | [7 empty] | Ready for approval, John where is this?
CP | Return end can beam pipe assembly | C75-CMA-RTBP-ASSY | R1 | 2020-10-29 |  | C. Wilcox | J. Fischer |  | K. Macha | [8 empty] | CP
OD | Supply end can beam pipe assembly | C75-CMA-SUPBP-ASSY | R1 | 2021-08-15 |  | C. Wilcox | J. Fischer |  | K. Macha | [7 empty] | Ready for approval, John where is this?
OD | Supply end can pump drop assembly |  | R1 | 2021-08-15 |  | C. Wilcox | J. Fischer |  | K. Macha
CP | C75 Supply End Can Beam Pipe Pre-Assembly Traveler | C75-CMA-BPIP-ASSY | R1 |  |  | C. Wilcox | J. Fischer | K. Worland | K. Macha |  | macha,fischer.areilly | macha,fischer.jjcamp | wilcox,fischer,macha,jjcamp |  |  |  | Need to redo the NCRs | CP
| Cryomodule | [17 empty] | SH
| Inspection | [17 empty] | SS
CP | Inspection of C75 Cryomodule Cavity Magnetic Shield Assembly | C75-CM-INSP-CMAG | R1 | 2018-08-24 |  | G. Cheng | A. DeKerlegand |  | K. Macha | [8 empty] | CP
OD | End Can Rework | C75-CM-ASSY-ECRW |  | 2021-08-15 |  | J. Fischer | K. Worland |  | K. Macha
| Assembly | [17 empty] | SS
OD | Cryomodule Assembly | C75-CM-ASSY | R1 | 2021-08-15 |  | J. Fischer | K. Worland |  | K. Macha
CP | Cryomodule Acceptance Test | C75-CMTF-CM-ACTS | R1 | 2020-09-01 |  | M. Drury |  |  | K. Macha | [8 empty] | CP
CP | Cryomodule Comissioning | C75-ACC-CM-COMM | R1 |  |  | M. Drury | G. Ciovati |  | K. Macha |  | areilly,macha | drury,gciovati,fischer | areilly,drury,fischer,gciovati |  |  |  |  | CP
| Other | [17 empty] | SH
CP | Weld Qualification Record | C75-EBW-CERT | R1 | 2017-08-22 |  | W. Clemens | G. Ciovati |  | K. Macha | [8 empty] | CP
| Standard Project Travelers | [17 empty] | SH
Color Legend |  | Count | Percent
CP | Complete (CP) | 130 | 92.2%
NR | New Revision Out for Approval (NR) | 0 | 0%
OA | Out for Approval (OA) | 0 | 0%
30 | Due in 30 Days | 0 | 0%
15 | Due in 15 Days | 0 | 0%
OD | Overdue | 9 | 6.383%
| Remaining | 2 | 1.418%
| Total Traveler IDs | 141

## TRAVELERSold (hidden)
Traveler Name | Traveler ID (SEPARATE BY WORKCENTERS) | Procedure(s), Name (if known) OR Yes/No | Drawing(s), Name (if known) OR Yes/No | SOP/TOSP/OSP/THA | Revision | Author | Reviewer | Project Manager | SOTR | Due | D3 ?? (USERNAME) | NCR Dispositioners (USERNAME) | NCR Informative (USERNAME) | Traveler (Holdpoint) Closer (USERNAME) | Notes
Receiving Travelers
Cavity
Helium Vessel Receiving Traveler | SNSPPU-CAV-RECV-HELV |  |  |  | R1
Cavity String
Bellows Receiving Traveler | SNSPPU-CST-RECV-(bellows) |  |  |  | R1
Gate Valves Receiving Traveler | SNSPPU-CST-RECV-(gate valve) |  |  |  | R1
FPC Receiving Traveler | SNSPPU-CST-RECV-FPC |  |  |  | R1
Cryomodule
Diode CXCU Inventory Traveler | SNSPPU-CM-RECV-DCXCU |  |  |  | R1 | M. Dickey | C. Barnes | E. Daly | P. Owen | 2020-01-02 |  | powen,king,edaly,kwilson,mdickey,areilly
Disassembly Travelers
Cavity
Cavity String
Cryomodule
Leak Check Travelers
Cavity
Cavity String
Bellows Leak Check Traveler | SNSPPU-CST-LEAK-(bellows) |  |  |  | R1
Gate Valves Leak Check Traveler | SNSPPU-CST-LEAK-(gate valves) |  |  |  | R1
FPC Leak Check Traveler | SNSPPU-CST-LEAK-FPC |  |  |  | R1
Cryomodule
Inspection Travelers
Cavity
Visual and CMM Inspection of Cavity | SNSPPU-CAV-INSP-CAV |  | 104211800-M8U-8200-A00X |  | R1 |  |  |  | K. Wilson | 2020-02-01
Visual/CMM Inspection of Helium Vessel | SNSPPU-CAV-INSP-HELV | TI CLEANING | 104211700-M8U-8200-A026 |  | R1 |  |  |  | K. Wilson | 2020-02-01
Receiving Inspection Cavity RF | SNSPPU-CAV-RFIN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
TUNER FRAME / STEPPER MOTORS / HARMONIC DRIVE |  | SS CLEANING
Cavity String
Receiving Inspection Bellows | SNSPPU-CST-INSP-(bellows) |  |  |  | R1 |  |  |  | K. Wilson | 2020-05-01
SNS FPC Visual Inspection | SNSPPU-CST-INSP-FPC |  | 104211600-M8U-8200-A00X |  | R1 |  |  |  | K. Wilson | 2019-12-01
Cryomodule
Space Frame Visual and Dimensional Inspection | SNSPPU-CM-INSP-SFR | SS CLEANING | 104210900-M8U-8200-A001 |  | R1 |  |  |  | M. Marchlik | 2020-10-01
Vacuum Vessel Visual Inspection | SNSPPU-CM-INSP-VV | LEAK CHECK; SS CLEANING | 104210800-M8U-8200-A001 |  | R1 |  |  |  | M. Marchlik | 2020-07-01
SNS Return End Can Visual/CMM Inspection | SNSPPU-CM-INSP-RENC |  | 104210700-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-11-01
SNS Supply End Can Visual/CMM Inspection | SNSPPU-CM-INSP-SENC |  | 104210600-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-06-01
SNS Outer Magnetic Shield Visual Inspection | SNSPPU-CM-INSP-OMAG |  | 104211000-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-05-01
SNS Inner Magnetic Shield Visual Inspection | SNSPPU-CM-INSP-IMAG |  | 104211200-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-05-01
SNS Thermal Shield Visual/CMM Inspection | SNSPPU-CM-INSP-THRM | HIGH SENSITIVITY LEAK CHECK | 104211100-M8U-8200-A002 104211100-M8U-8200-A014 104211100-M8U-8200-A025 |  | R1 |  |  |  | M. Marchlik | 2020-08-01
Chemistry Travelers
Cavity
Cavity High Pressure Rinse (New HPR) Traveler | SNSPPU-CAV-CHEM-HPRN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Components Cleaning Traveler | SNSPPU-CAV-CHEM-CLN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Ultra Sonic Clean Traveler | SNSPPU-CAV-CHEM-USC |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
CMM Workcenter ?
IS there a cav RFIN traveler?
Furnace Workcenter ? | changed CHEM to PROC
Bakeout before RF processing | SNSPPU-CAV-PROC-BAKE |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Cavity Heat Treatment | SNSPPU-CAV-PROC-HEAT |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Processing Travelers
Cavity
Cavity RF Tuning | SNSPPU-CAV-TUNE |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
IS there a cav RFIN traveler? |  |  |  |  | R1
Cavity String
Cryomodule
RF Processing (FPC RF Processing) | SNSPPU-CM-CST-FPC-HPRF |  |  |  | R1 |  |  |  | K. Wilson
Assembly Travelers
Cavity
SNS Helium Vessel Installation Traveler | SNSPPU-CAV-ASSY-HELV |  | 104211700-M8U-8200-A026 |  | R1 |  |  |  |  | 2020-02-01
High Beta Cavity Assembly for VTA testing | SNSPPU-CAV-ASSY (look at old SNS) |  | 104211800-M8U-8200-A00X |  | R1 |  |  |  |  | 2020-02-01
transfer to test stand
Cavity String
SNS High Beta Cavity String Traveler | SNSPPU-CST-ASSY |  |  |  | R1 |  |  |  |  | 2020-07-01
Cryomodule
Cryomodule Assembly | SNSPPU-CM-ASSY |  |  |  | R1 |  |  |  | M. Marchlik | 2020-12-01
Cold Mass Assembly | SNSPPU-CM-ASSY-CMAS |  |  |  | R1 |  |  |  |  | 2020-08-01
Cryomodule Thermal Shield-Spaceframe Assembly Traveler | SNSPPU-CM-ASSY-THRM |  | 104211100-M8U-8200-A002 104211100-M8U-8200-A014 104211100-M8U-8200-A025 |  | R1 |  |  |  | M. Marchlik
SNS High Beta Cryomodule Vacuum Vessel-End Can Assembly Traveler | SNSPPU-CM-ASSY-VV |  | 104210800-M8U-8200-A001 |  | R1
cm assy ship (rf, instrumentation)
Testing Travelers
Vertical Cavity Testing | SNSPPU-CAV-VTRF |  |  |  | R1 |  |  |  |  | 2020-04-01
Cavity VTA Cooldown | SNSPPU-CAV-VTA-COOL |  |  |  | R1 |  |  |  |  | 2020-02-01
Installation/Shipping Travelers
SNS Cryomodule Shipping | SNSPPU-CM-ASSY-SHIP |  |  |  | R1 |  |  |  |  | 2020-05-01
Standard Project Travelers
Detours, Deviations and Discrepancies (D3) | SNSPPU-D3 |  |  |  | R2 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A
Inspection Summary Report | SNSPPU-INSR |  |  |  | R1 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A
Inspection Nonconformance Report | SNSPPU-NCR |  |  |  | R10 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A