## TRAVELERS
| Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author | Reviewer | Reviewer | Project Manager | SOTR | NCR Informative | NCR Dispositioners | D3 Emails | Procedure(s), Name (if known) | Drawing(s), Name (if known) | Acronym from INV | Notes | Status | Section
Disassembly Travelers
Cavity
CP | Cavity Disassembly | C100R-CAV-DISA | R3 | 2018-11-28 |  | Dreyfuss | Forehand |  | Davis |  | forehand,areilly,kdavis,marhause | [6 empty] | CP
| Cavity String | [17 empty] | SS
CP | Cavity String Disassembly |  |  | 2020-08-01 |  | Forehand | Dreyfuss |  | Davis | [8 empty] | CP
| Cryomodule | [17 empty] | SS
CP | C100R Disassembly Traveler | C100R-CM-DISA | R2 | 2018-09-24 |  | Fischer | Reilly | Worland | Hamlette |  | areilly | areilly,fischer,hamlette | areilly,fischer,hamlette |  |  |  |  | CP
| Cavity Preparation | [17 empty] | SH
| Inspection | [17 empty] | SS
CP | Cavity CMM Receiving Inspection | C100R-CAV-INSP | R1 | 2018-11-30 |  | DeKerlegand | Marhauser |  | Reilly |  | fischer,kdavis | [6 empty] | CP
CP | Cavity HOM Feedthru Receiving Inspection | C100R-CAV-INSP-HMFT | R3 | 2018-11-06 |  | Park | Davis |  | Reilly |  | Georged,areilly | hpark,kdavis | hpark,kdavis,areilly |  |  |  |  | CP
NR | Cavity RF Inspection Receiving Inspection | C100R-CAV-RFIN | R2 | 2018-12-05 |  | Overton | Marhauser |  | Davis |  | forehand,kdavis | [6 empty] | NR
CP | Secondary Waveguide Inspection (knife edge and sealing surface) | C100R-CAV-INSP-GVWG | R2 | 2019-01-15 |  | DeKerlegand | Davis | Fischer |  |  | kdavis,fischer,geroged | [6 empty] | CP
CP | Primary waveguide Inspection | C100R-CAV-INSP-WGD | R1 | 2019-01-16 |  | Williams | DeKerlegand |  | Davis |  | Kdavis,scott,forehand | [6 empty] | CP
CP | Recycled Waveguide Inspection - 12 GeV Upgrade Waveguides | C100R-CAV-INSP-WGD-RCYC | R1 | 2019-01-25 |  | Williams | DeKerlegand |  | Davis |  | Kdavis,scott,forehand | [6 empty] | CP
CP | Rework - 12 GeV Upgrade Waveguides | C100R-CAV-RWRK-WGD | R1 | 2019-02-21 |  | G. DeKerlegand | K. Davis |  | T. Reilly |  |  | kdavis,scott,forehand | [5 empty] | CP
CP | C100R HOM Feedthru Receiving Inspection | C100R-VTA-HMFT-CSHK | R1 |  |  | HyeKyoung Park | Danny Forehand | Justin Kent | Tony Reilly |  |  | lzhao,areilly | hkpark,areilly |  |  |  |  | CP
CP | C100R leak check inspection traveler | C100R-CMA-HMFT-LEAK-R1 | R1 |  |  | HyeKyoung Park | Chris Wilcox |  | Tony Reilly |  |  | lzhao,areilly | lzhao,areilly |  |  |  |  | CP
CP | C100R Window Recycled Visual Inspection | C100R-CAV-INSP-WIN-RCYC | R1 | 2019-01-16 |  | S. Williams | K. Davis |  | T. Reilly |  |  | Scott,kdavis,forehand | [5 empty] | CP
CP | Window Flange Inspection | C100R-INSP-WIN | R1 | 2020-09-23 |  | S. Williams | K. Macha |  | T. Reilly |  | areilly | scott,macha | areilly,scott,macha |  |  |  |  | CP
| Chemistry | [17 empty] | SS
CP | C100R Cavity Degreasing | C100R-CAV-CHEM-USC | R1 | 2019-01-08 |  | Fiedler | Mitchell |  | Davis |  | ashleya,kdavis | [6 empty] | CP
CP | C100R Cavity HPR | C100R-CAV-CHEM-HPR | R1 | 2019-01-08 |  | Fiedler | Mitchell |  | Davis |  | ashleya,kdavis | [6 empty] | CP
CP | C100R Cavity Flange Lapping | C100R-CAV-LAP | R2 | 2018-11-29 |  | Wildeson | Mitchell |  | Davis |  | ashleya,kdavis | [6 empty] | CP
CP | C100R Top Hat Flange Lapping | C100R-CHEM-TPHT-LAP | R1 | 2021-05-06 |  | A. Wildeson | A. Anderson |  | T. Reilly |  | ashleya,mcewen,kdavis | dreyfuss,forehand | dreyfuss,forehand,ashleya,mcewen |  |  |  |  | CP
| Assembly | [17 empty] | SS
CP | C100R Cavity Assembly | C100R-CAV-ASSY | R2 | 2018-11-06 |  | Forehand | Dreyfuss |  | Davis |  |  | Forehand,kdavis,areilly | [5 empty] | CP
CP | C100R Cavity Tuning | C100R-CAV-TUNE | R1 | 2018-11-06 |  | Overton | Forehand |  | Davis |  | forehand,kdavis | [6 empty] | CP
| Testing | [17 empty] | SS
| VTA HOM | C100R-CAV-VTA-HOM
CP | C100R Cavity VTA Test | C100R-CAV-VTRF | R2 | 2018-11-06 |  | Stirbet | C.Willson |  | Davis |  | areilly,forehand | kdavis,ganey | areilly,kdavis,ganey,forehand |  |  |  |  | CP
CP | RF testing of C100 cavities in the VTA | C100R-PR-VTA-CAV-VTRF | R2 |  |  | C. Wilson | K. Davis |  | K. Davis | [8 empty] | CP
| Component Preparation | [17 empty] | SH
| Inspection | [17 empty] | SS
CP | C100R Double Sided Rectangular Flange Receiving Inspection Traveler | C100R-CAV-INSP-DSRF | R1 | 2020-09-30 |  | S. Williams | A. DeKerlegand |  | T. Reilly |  | areilly | scott, georged | areilly, scott, georged |  |  |  |  | CP
CP | C100R Brazement Adapter Assembly Receiving Inspection Traveler | C100R-INSP-ADPT | R1 | 2020-09-03 |  | S. Williams | K. Macha |  | T. Reilly |  | areilly | scott,macha | areilly,scott,macha |  |  |  |  | CP
| Chemistry | [17 empty] | SS
CP | Pair Components Preparation | C100R-CHEM-COMP-DEGR | R1 |  |  | R. Fiedler | A. Mitchell | T. Ganey | T. Reilly |  | ashleya | areilly,ganey | areilly,ganey,ashleya |  |  |  |  | CP
CP | C100 components cleaning | C100R-CAV-CHEM-COMP | R1 | 2019-02-05 |  | A. Anderson Mitchell | K. Davis |  | T. Reilly |  |  | ashleya,kdavis | [5 empty] | CP
| Weld Inspection | [17 empty] | SS
CP | Waveguide and window Weldement Modification | C100R-WELD-WIN-ASSY | R1 | 2021-02-05 |  | Macha | Williams |  | Reilly |  | georged,lzhao | scott,edaly,forehand,areilly | scott,macha,areilly |  |  |  |  | CP
| Leak Checks | [17 empty] | SS
CP | C100R Cavity String All-Metal Gate Valve Leak Test | C100R-CLNRM-AMGV-LEAK | R1 |  |  | David Savransky | Danny Forehand | Tiffany Ganey | Tony Reilly |  | Dsavr,areilly,dreyfuss | forehand,ganey | dsavr,forehand,ganey,dreyfuss |  |  |  |  | CP
| Assembly | [17 empty] | SS
CP | C100R Helium Vessel Installation | C100R-CAV-ASSY-HELV | R2 | 2018-11-29 |  | Fischer | Legg | Worland | Reilly |  |  | Fischer,rlegg,worland,areilly | [5 empty] | CP
| Cavity String | [17 empty] | SH
| Inspection | [17 empty] | SS
#VALUE! | Valve INSP |  |  | Hold 2020
| Chemistry | [17 empty] | SS
| Assembly | [17 empty] | SS
CP | C100R Cavity Assembly & Leak Test | C100R-CST-ASSY | R1 | 2019-01-21 |  | D. Forehand | K. Davis |  | T. Reilly |  |  | Forehand,kdavis | [5 empty] | CP
CP | C100R Cavity string leak test | C100R-CST-ASSY-LEAK | R1 | 2019-02-27 |  | D. Forehand | K. Davis |  | T. Reilly |  |  | Forehand,kdavis | [5 empty] | CP
CP | C100R Waveguide Sub-Assembly & Leak Test | C100R-CST-ASSY-WGD | R1 | 2019-01-21 |  | D. Forehand | K. Davis |  | T. Reilly |  |  | Forehand,kdavis | [5 empty] | CP
| Cryomodule | [17 empty] | SH
| Inspection | [17 empty] | SS
| 12 GeV Guard Vacuum Waveguide | C100R-CM-INSP-GVWG | R2 | 2019-01-15 |  | A. DeKerlegand | K. Davis | J. Fischer |  |  |  | scott,forehand,kdavis | [5 empty] | CP
| Cryomodule Assembly | [17 empty] | SS
CP | C100R Cryomodule Final Assembly | C100R-CM-ASSY | R1 | 2019-02-11 |  | Fischer | [11 empty] | CP
CP | C100R Cold Mass Assembly | C100R-CM-ASSY-COLD | R1 | 2019-02-11 |  | Fischer | [11 empty] | CP
CP | C100R Thermal Shield and Space Frame Assembly | C100R-CM-ASSY-SFR | R1 | 2019-02-11 |  | Fischer | [11 empty] | CP
CP | C100R Vacuum Vessel and End Can Assembly | C100R-CM-ASSY-VV | R1 | 2019-02-11 |  | Fischer | [5 empty] | fischer,reilly,worland | [5 empty] | CP
OD | C100R Cryomodule Beampipe Assembly | C100R-CM-ASSY-BPIP | R1 | 2021-09-01 |  | Fischer
OD | C100R Cryomodule Final Assembly | C100R-CM-ASSY | R2 | 2021-09-01 |  | Fischer | Worland | Hamlette | Reilly |  |  | Fischer,Worland,areilly
OD | C100R Cold Mass Assembly | C100R-CM-ASSY-COLD | R2 | 2021-09-01 |  | Fischer | Worland | Hamlette | Reilly |  |  | fischer,rlegg,areilly,worland
OD | C100R Thermal Shield and Space Frame Assembly | C100R-CM-ASSY-SFR | R2 | 2021-09-01 |  | Fischer | Worland | Hamlette | Reilly |  |  | fischer,rlegg,areilly,worland
OD | C100R Vacuum Vessel and End Can Assembly | C100R-CM-ASSY-VV | R2 | 2021-09-01 |  | Fischer | Worland | Hamlette | Reilly |  |  | fischer,reilly,worland
OD | C100R Cryomodule Beampipe Assembly | C100R-CM-ASSY-BPIP | R2 | 2021-09-01 |  | Fischer | Worland | Hamlette | Reilly
| Cryomodule Testing | [17 empty] | SS
CP | C100R CM Cooldown Procedure | C100R-PR-CMTF-CM-COOL | R1 |  |  | D. Savransky | E. Daly | M. Drury | A. Reilly | [8 empty] | CP
CP | C100R CM Warm-Up Procedure | C100R-PR-CMTF-CM-WARM | R1 |  |  | D. Savransky | E. Daly | M. Drury | A. Reilly | [8 empty] | CP
CP | C100R Cryomodule Commissioning | C100R-CM-COMM | R1 | 2021-10-01 |  | M. Drury | A. Solopova |  | A. Reilly |  |  | areilly,drury | [5 empty] | CP
| Cryomodule Installation & Commisioning | [17 empty] | SS
OD | C100R Cryomodule Tunnel Installation | C100R-CM-INST | R1 | 2021-10-01 |  | F. Humpfry
CP | C100R Cryomodule Acceptance Test Cryocycle | C100R-CM-ACTS | R1 | 2019-10-28 |  | M. Drury | A. Solopova |  | T. Reilly |  |  | Drury,areilly | [5 empty] | CP
| Standard Project Travelers | [17 empty] | SH
CP | C100R Non-Conformance Report | C100R-NCR | R11 |  |  | V. Bookwalter | A. McEwen |  | A. Reilly |  | bookwalt,megan | bookwalt,megan | bookwalt,megan |  |  |  |  | CP
CP | C100R Detours, Deviations and Discrepencies | C100R-D3 | R2 |  |  | V. Bookwalter | A. McEwen |  | A. Reilly |  |  | bookwalt | [5 empty] | CP
CP | C100R Inspection Summary Report | C100R-INSR | R1 |  |  | A. DeKerlegand | A. McEwen |  | A. Reilly |  |  | areilly,georged | [5 empty] | CP
Color Legend |  | Count | Percent
CP | Complete (CP) | 43 | 84.31%
NR | New Revision Out for Approval (NR) | 1 | 1.961%
OA | Out for Approval (OA) | 0 | 0%
30 | Due in 30 Days | 0 | 0%
15 | Due in 15 Days | 0 | 0%
OD | Overdue | 7 | 13.73%
| Remaining | 1 | 1.961%
| Total Traveler IDs | 51

## INVENTORY TRAVELERS
Traveler Name | Traveler ID (SEPARATE BY WORKCENTERS) | Questions / Comments | Necessary Documentation | Author | Reviewer | Project Manager | SOTR | Date | D3 ?? (USERNAME) | NCR Dispositioners (USERNAME) | NCR Informative (USERNAME) | Notes

## PROCEDURES
PROCEDURE TITLE | PROCEDURE ID | REVISION | Author | Reviewer | Proj Lead | Due | Approved | CURRENT FILE LOCATION
Safety Procedures
Incoming inspection Procedures
Chemistry/ Cleaning Procedures
Cavity Procedures
String Production Procedures
Cryomodule Production Procedures
Cryomodule Testing Procedures
Cryomodule Shipping Procedures

## TRAVELERSold (hidden)
Traveler Name | Traveler ID (SEPARATE BY WORKCENTERS) | Procedure(s), Name (if known) OR Yes/No | Drawing(s), Name (if known) OR Yes/No | SOP/TOSP/OSP/THA | Revision | Author | Reviewer | Project Manager | SOTR | Due | D3 ?? (USERNAME) | NCR Dispositioners (USERNAME) | NCR Informative (USERNAME) | Traveler (Holdpoint) Closer (USERNAME) | Notes
Receiving Travelers
Cavity
Helium Vessel Receiving Traveler | SNSPPU-CAV-RECV-HELV |  |  |  | R1
Cavity String
Bellows Receiving Traveler | SNSPPU-CST-RECV-(bellows) |  |  |  | R1
Gate Valves Receiving Traveler | SNSPPU-CST-RECV-(gate valve) |  |  |  | R1
FPC Receiving Traveler | SNSPPU-CST-RECV-FPC |  |  |  | R1
Cryomodule
Diode CXCU Inventory Traveler | SNSPPU-CM-RECV-DCXCU |  |  |  | R1 | M. Dickey | C. Barnes | E. Daly | P. Owen | 2020-01-02 |  | powen,king,edaly,kwilson,mdickey,areilly
Disassembly Travelers
Cavity
Cavity String
Cryomodule
Leak Check Travelers
Cavity
Cavity String
Bellows Leak Check Traveler | SNSPPU-CST-LEAK-(bellows) |  |  |  | R1
Gate Valves Leak Check Traveler | SNSPPU-CST-LEAK-(gate valves) |  |  |  | R1
FPC Leak Check Traveler | SNSPPU-CST-LEAK-FPC |  |  |  | R1
Cryomodule
Inspection Travelers
Cavity
Visual and CMM Inspection of Cavity | SNSPPU-CAV-INSP-CAV |  | 104211800-M8U-8200-A00X |  | R1 |  |  |  | K. Wilson | 2020-02-01
Visual/CMM Inspection of Helium Vessel | SNSPPU-CAV-INSP-HELV | TI CLEANING | 104211700-M8U-8200-A026 |  | R1 |  |  |  | K. Wilson | 2020-02-01
Receiving Inspection Cavity RF | SNSPPU-CAV-RFIN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
TUNER FRAME / STEPPER MOTORS / HARMONIC DRIVE |  | SS CLEANING
Cavity String
Receiving Inspection Bellows | SNSPPU-CST-INSP-(bellows) |  |  |  | R1 |  |  |  | K. Wilson | 2020-05-01
SNS FPC Visual Inspection | SNSPPU-CST-INSP-FPC |  | 104211600-M8U-8200-A00X |  | R1 |  |  |  | K. Wilson | 2019-12-01
Cryomodule
Space Frame Visual and Dimensional Inspection | SNSPPU-CM-INSP-SFR | SS CLEANING | 104210900-M8U-8200-A001 |  | R1 |  |  |  | M. Marchlik | 2020-10-01
Vacuum Vessel Visual Inspection | SNSPPU-CM-INSP-VV | LEAK CHECK; SS CLEANING | 104210800-M8U-8200-A001 |  | R1 |  |  |  | M. Marchlik | 2020-07-01
SNS Return End Can Visual/CMM Inspection | SNSPPU-CM-INSP-RENC |  | 104210700-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-11-01
SNS Supply End Can Visual/CMM Inspection | SNSPPU-CM-INSP-SENC |  | 104210600-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-06-01
SNS Outer Magnetic Shield Visual Inspection | SNSPPU-CM-INSP-OMAG |  | 104211000-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-05-01
SNS Inner Magnetic Shield Visual Inspection | SNSPPU-CM-INSP-IMAG |  | 104211200-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-05-01
SNS Thermal Shield Visual/CMM Inspection | SNSPPU-CM-INSP-THRM | HIGH SENSITIVITY LEAK CHECK | 104211100-M8U-8200-A002 104211100-M8U-8200-A014 104211100-M8U-8200-A025 |  | R1 |  |  |  | M. Marchlik | 2020-08-01
Chemistry Travelers
Cavity
Cavity High Pressure Rinse (New HPR) Traveler | SNSPPU-CAV-CHEM-HPRN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Components Cleaning Traveler | SNSPPU-CAV-CHEM-CLN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Ultra Sonic Clean Traveler | SNSPPU-CAV-CHEM-USC |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
CMM Workcenter ?
IS there a cav RFIN traveler?
Furnace Workcenter ? | changed CHEM to PROC
Bakeout before RF processing | SNSPPU-CAV-PROC-BAKE |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Cavity Heat Treatment | SNSPPU-CAV-PROC-HEAT |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Processing Travelers
Cavity
Cavity RF Tuning | SNSPPU-CAV-TUNE |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
IS there a cav RFIN traveler? |  |  |  |  | R1
Cavity String
Cryomodule
RF Processing (FPC RF Processing) | SNSPPU-CM-CST-FPC-HPRF |  |  |  | R1 |  |  |  | K. Wilson
Assembly Travelers
Cavity
SNS Helium Vessel Installation Traveler | SNSPPU-CAV-ASSY-HELV |  | 104211700-M8U-8200-A026 |  | R1 |  |  |  |  | 2020-02-01
High Beta Cavity Assembly for VTA testing | SNSPPU-CAV-ASSY (look at old SNS) |  | 104211800-M8U-8200-A00X |  | R1 |  |  |  |  | 2020-02-01
transfer to test stand
Cavity String
SNS High Beta Cavity String Traveler | SNSPPU-CST-ASSY |  |  |  | R1 |  |  |  |  | 2020-07-01
Cryomodule
Cryomodule Assembly | SNSPPU-CM-ASSY |  |  |  | R1 |  |  |  | M. Marchlik | 2020-12-01
Cold Mass Assembly | SNSPPU-CM-ASSY-CMAS |  |  |  | R1 |  |  |  |  | 2020-08-01
Cryomodule Thermal Shield-Spaceframe Assembly Traveler | SNSPPU-CM-ASSY-THRM |  | 104211100-M8U-8200-A002 104211100-M8U-8200-A014 104211100-M8U-8200-A025 |  | R1 |  |  |  | M. Marchlik
SNS High Beta Cryomodule Vacuum Vessel-End Can Assembly Traveler | SNSPPU-CM-ASSY-VV |  | 104210800-M8U-8200-A001 |  | R1
cm assy ship (rf, instrumentation)
Testing Travelers
Vertical Cavity Testing | SNSPPU-CAV-VTRF |  |  |  | R1 |  |  |  |  | 2020-04-01
Cavity VTA Cooldown | SNSPPU-CAV-VTA-COOL |  |  |  | R1 |  |  |  |  | 2020-02-01
Installation/Shipping Travelers
SNS Cryomodule Shipping | SNSPPU-CM-ASSY-SHIP |  |  |  | R1 |  |  |  |  | 2020-05-01
Standard Project Travelers
Detours, Deviations and Discrepancies (D3) | SNSPPU-D3 |  |  |  | R2 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A
Inspection Summary Report | SNSPPU-INSR |  |  |  | R1 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A
Inspection Nonconformance Report | SNSPPU-NCR |  |  |  | R10 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A