## Slide 1: L2HE
Color Legend |  | Count | Percent
CP | Complete (CP) | 92 | 86.79%
NR | New Revision Out for Approval (NR) | 1 | 0.94%
OA | Out for Approval (OA) | 3 | 2.83%
30 | Due in 30 Days | 0 | 0.00%
15 | Due in 15 Days | 1 | 0.94%
OD | Overdue | 0 | 0.00%
R0 | R0 Draft | 8 | 7.55%
 | Remaining | 1 | 0.94%
 | Total Traveler IDs | 106 | 
Please Submit any changes or questions to pansophy@jlab.org
Note:
Project Masterlist can be found in the project docushare folder
Traveler Acronym list can be found in Pansophy, under the User Tools > Traveler Tools drop downs
Due to the large number of R0 travelers, the normal list cannot fit on this page. Please reference the subsequent pages for the traveler names

## Slide 2
Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author | Reviewer | Reviewer | Proj Manager | SOTR
Out for Approval |  |  |  |  |  |  |  |  | 
Cavity String Assembly (MAJOR CHANGE) | L2HE-CLNRM-CST-ASSY | R1 | 11/1/21 | 11/1/21 | T. Ganey | D. Forehand | K. Davis | J. Hogan | 
LCLSII-HE LERF Prep & Cooldown | L2HE-LERF-CM-PREP* | R1 |  |  | M. Weaks | N. Huque | L. King | M. Drury | J. Hogan
Cavity VTA Test | L2HE-VTA-CAV-VTRF** | R4 | 5/1/21 |  | J. KENT | J. Vennekate |  | K. Wilson | 
LCLS-II-HE Faraday Window Manifold Inspection Traveler | L2HE-INSP-FWM | R1 |  |  | T. Ganey | G. DeKerlegand | K. Wilson | J. Hogan | 
L2HE Traveler Listing
*The L2HE-LERF-CM-PREP has been disapproved. Please make the necessary revisions and upload a new version to ready for approvals.
**L2HE-VTA-CAV-VTRF has been approved and is in the queue for upload to pansophy.

## Slide 3
Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author | Reviewer | Reviewer | Proj Manager | SOTR
Overdue |  |  |  |  |  |  |  |  | 
Due in 15 Days |  |  |  |  |  |  |  |  | 
Cavity HOM Measurements and Tuning Procedure | L2HE-PR-CMA-HOM-TUNE | R1 | 3/1/22 | 4/1/22 | P. Owen | D. Forehand | D. Forehand | J. Hogan | 
L2HE Traveler Listing Cont

## Slide 4
Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author | Reviewer | Reviewer | Proj Manager | SOTR
R0 |  |  |  |  |  |  |  |  | 
Cavity HOM Measurements and Tuning | L2HE-CMA-HOM-TUNE | R1 | 3/1/22 | 4/1/22 | P. Owen | D. Forehand | D. Forehand | J. Hogan | 
CM Assembly First | L2HE-CMA-CM-ASSY1 | R1 | 10/26/21 |  | J. Fischer | N. Huque | A. Reilly | J. Hogan | 
CM Assembly Second | L2HE-CMA-CM-ASSY2 | R1 | 10/26/21 |  | J. Fischer | N. Huque | A. Reilly | J. Hogan | 
CM Assembly Final | L2HE-CMA-CM-ASSYF | R1 | 10/26/21 |  | J. Fischer | N. Huque | A. Reilly | J. Hogan | 
Cryomodule Rework Traveler | L2HE-CMA-CM-REW | R1 | 10/26/21 |  | J. Fischer | N. Huque | A. Reilly | J. Hogan | 
Cryomodule Retrofit Traveler | L2HE-CMA-CM-RFIT | R1 | 10/26/21 |  | J. Fischer | N. Huque | A. Reilly | J. Hogan | 
Cryomodule Prep and Shipping to SLAC | L2HE-CMA-CM-SHIP | R1 | 10/26/21 |  | J. Fischer | N. Huque | A. Reilly | J. Hogan | 
Cryomodule Vacuum Vessel Assembly | L2HE-CMA-VV-ASSY | R1 | 10/26/21 |  | J. Fischer | G. Cheng | A. Reilly | J. Hogan | 
L2HE Traveler Listing Cont Cont