## Slide 1: C50R
Color Legend |  | Count |  | Percent
CP | Complete (CP) | 82 | 96.47% | 
NR | New Revision Out for Approval (NR) | 0 | 0.00% | 
OA | Out for Approval (OA) | 0 | 0.00% | 
30 | Due in 30 Days | 0 | 0.00% | 
15 | Due in 15 Days | 0 | 0.00% | 
OD | Overdue | 3 | 3.53% | 
 | Remaining | 0 | 0.00% | 
 | Total Traveler IDs | 85 |  | 
Out for Approval/New Revision
NONE
Approaching Overdue
None
Overdue
C50R-CPR-BCP-SUBC-R1
C50R-CPR-CLN-SUBC-R1
C50R-CPR-CHEM-CPR-R1
Please Submit any changes or questions to pansophy@jlab.org
Note:
Project Masterlist can be found in the project docushare folder
Traveler Acronym list can be found in Pansophy, under the User Tools > Traveler Tools drop downs

## Slide 2
Out for Approval |  |  |  |  |  |  |  |  | 
Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author | Reviewer | Reviewer | Proj Manager | SOTR
Overdue |  |  |  |  |  |  |  |  | 
C50R Pair Component Etching and Cleaning | C50R-CPR-BCP-SUBC |  | 8/1/21 |  | A. Mitchell | Reilly |  | Reilly | 
C50R Subcomponent Cleaning | C50R-CPR-CLN-SUBC |  | 8/1/21 |  | A. Mitchell | Reilly |  | Reilly | 
C50R Cavity Pair Cleaning and Acid Etching | C50R-CPR-CHEM-CPR |  | 8/1/21 |  | A. Mitchell | Reilly |  | Reilly | 
Approaching Due Date |  |  |  |  |  |  |  |  | 
C50R Traveler Listing

## Slide 3: C75
Color Legend |  | Count |  | Percent
CP | Complete (CP) | 131 | 92.25% | 
NR | New Revision Out for Approval (NR) | 0 | 0.00% | 
OA | Out for Approval (OA) | 0 | 0.00% | 
30 | Due in 30 Days | 0 | 0.00% | 
15 | Due in 15 Days | 0 | 0.00% | 
OD | Overdue | 8 | 5.63% | 
 | Remaining | 3 | 2.11% | 
 | Total Traveler IDs | 142 |  | 
Out for Approval/New Revision
NONE
Approaching Overdue
NONE
Overdue
CP-STP-CAV-CHEM-BAKE
CP-CAV-CHEM-HEP
“Beam line assembly procedure”
CP-STP “JT calibration procedure”
CP-C75-CMA-BRBP
C75-CMA-SUPBP-ASSY
“Supply end can pump drop assembly”
C75-CM-ASSY-ECRW
Please Submit any changes or questions to pansophy@jlab.org
Note:
Project Masterlist can be found in the project docushare folder
Traveler Acronym list can be found in Pansophy, under the User Tools > Traveler Tools drop downs

## Slide 4
Out for Approval |  |  |  |  |  |  |  |  | 
Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author | Reviewer | Reviewer | Proj Manager | SOTR
Overdue |  |  |  |  |  |  |  |  | 
Baking in nitrogen oven | CP-STP-CAV-CHEM-BAKE | R1 | 8/27/21 |  | A. Mitchell | K. Davis |  | K. Macha | 
C75 HEP procedure | CP-CAV-CHEM-HEP | R1 | 8/27/21 |  | A. Mitchell | A. Wildeson |  | K. Macha | 
Beam line assembly procedure |  |  | 8/15/21 |  | C. Wilcox | J. Fischer |  |  | 
JT calibration procedure | CP-STP |  | 8/15/21 |  | K. Worland | J. Fischer |  |  | 
Bridging bellows | CP-C75-CMA-BRBP | R1 | 8/15/21 |  | C. Wilcox | J. Fischer |  | K. Macha | 
Supply end can beam pipe assembly | C75-CMA-SUPBP-ASSY | R1 | 8/15/21 |  | C. Wilcox | J. Fischer |  | K. Macha | 
Supply end can pump drop assembly |  | R1 | 8/15/21 |  | C. Wilcox | J. Fischer |  | K. Macha | 
End Can Rework | C75-CM-ASSY-ECRW |  | 8/15/21 |  | J. Fischer | K. Worland |  | K. Macha | 
Approaching Due Date |  |  |  |  |  |  |  |  | 
C75 Traveler Listing