## Slide 1: C100R
Color Legend |  | Count | Percent
CP | Complete (CP) | 43 | 93.48%
NR | New Revision Out for Approval (NR) | 4 | 8.70%
OA | Out for Approval (OA) | 0 | 0.00%
30 | Due in 30 Days | 0 | 0.00%
15 | Due in 15 Days | 0 | 0.00%
OD | Overdue | 2 | 4.35%
 | Remaining | 1 | 2.17%
 | Total Traveler IDs | 46 | 
Out for Approval/New Revision
C100R-CAV-RFIN-R2
C100R-CM-ASSY-COLD-R2
C100R-CM-ASSY-R2
C100R-CM-ASSY-SFR-R2
C100R-CM-ASSY-VV-R2
Approaching Overdue
NONE
Overdue
C100R-CM-ASSY-BPIP-R1
C100R-CM-INST-R1
Please Submit any changes or questions to pansophy@jlab.org
Note:
Project Masterlist can be found in the project docushare folder
Traveler Acronym list can be found in Pansophy, under the User Tools > Traveler Tools drop downs

## Slide 2
Out for Approval |  |  |  |  |  |  |  |  | 
Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author | Reviewer | Reviewer | Proj Manager | SOTR
Cavity RF Inspection Receiving Inspection | C100R-CAV-RFIN** | R2 | 12/5/18 |  | Overton | Marhauser |  | Davis | 
C100R Cryomodule Final Assembly | C100R-CM-ASSY* | R2 | 2/11/19 |  | J. Fischer | A. Reilly | J. Campbell | D. Hamlette | 
C100R Thermal Shield and Space Frame Assembly | C100R-CM-ASSY-SFR* | R2 | 2/11/19 |  | J. Fischer | A. Reilly | J. Campbell | D. Hamlette | 
C100R Vacuum Vessel and End Can Assembly | C100R-CM-ASSY-VV* | R2 | 2/11/19 |  | J. Fischer | A. Reilly | J. Campbell | D. Hamlette | 
Overdue |  |  |  |  |  |  |  |  | 
C100R Cryomodule Beampipe Assembly | C100R-CM-ASSY-BPIP | R1 | 9/1/21 |  | Fischer |  |  |  | 
C100R Cryomodule Tunnel Installation | C100R-CM-INST | R1 | 10/1/21 |  | F. Humpfry |  |  |  | 
Approaching Due Date |  |  |  |  |  |  |  |  | 
C100R Traveler Listing
*C100R-CM-ASSY, C100R-CM-ASSY-SFR, and C100R-CM-ASSY-VV's routings are overdue.
**C100R-CAV-ASSY-RFIN has been disapproved