## TRAVELERS
| Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author | SME | PRODUCTION LEAD | PROJECT LEAD | Tech Rep (SOTR) | NCR Informative | NCR Dispositioners | D3 Emails | Procedure(s), Name (if known) | Drawing(s), Name (if known) | Acronym from INV | Notes | Status | Section
Cavity Preparation
| Processing | [17 empty] | SS
CP | Cavity RF Inspection | L2HE-TUNE-CAV-RFIN | R2 | 2021-05-01 |  | J. Vennekate | D. Forehand | J. Hogan | K. WILSON | [6 empty] | CAV | This traveler is used to measure the cavity passband frequencies once it has arrived from the vendor. The RFIN measurements are compared to the pre-shipment vendor measurement, accounting for enviromental condition differences. If the RFIN measurments are in agreement with the vendor data, then it is assumed that the cavity was not damaged during shipment and can proceed toward VTRF. Discussions were had on whether a general spec for passband frequencies could be used instead of the vendor measurement; however, it was determined that comparision to the vendor measurements would continue to be used. No additional changes to the RFIN traveler or its calculation spreadsheet are required for the L2HE project. | CP
| Chemistry | [17 empty] | SS
CP | L2HE Cavity Horizontal Electropolish | L2HE-CHEM-CAV-HEP | R1 | 2021-08-01 | 2021-08-01 | A. Mitchell | T. Ganey | T. Ganey | J. Hogan |  | ashleya,kwilson | J. Hogan,vennekate,ganey | ashleya,vennekate,ganey,J. Hogan,kdavis,forehand,kwilson |  |  |  | HEP is not anticipated for the L2HE production run; however, is available if needed for any refurbishment cavities or other situations as may be required to support the project. No changes to reference documents is required. | CP
CP | Cavity High Pressure Rinse | L2HE-CHEM-CAV-HPR | R2 | 2021-09-15 |  | A. Wildeson | A. Mitchell | T. Ganey | J. Hogan |  | ashleya,kwilson | J. Hogan,vennekate,ganey | ashleya,vennekate,ganey,J. Hogan,kdavis,forehand,kwilson |  |  | CAV | Cavities that require reprocessing after a VTRF will receive a HPR - as was done in the L2PRD project. For L2PRD, this HPR was not captured in a traveler. For L2HE, chemistry travelers were created to capture the re-work steps for cavity vertical testing. The chemistry travelers follow standard chemistry processes and were only modified from other project travelers to reflect any 9-cell / L2HE specifics. HPR traveler does not have any references to update. | CP
CP | Cavity Lapping | L2HE-CHEM-CAV-LAP | R1 | 2021-07-15 |  | A. Wildeson | A. Mitchell | T. Ganey | J. Hogan |  | ashleya,kwilson | J. Hogan,vennekate,ganey | ashleya,vennekate,ganey,J. Hogan,kdavis,forehand,kwilson |  |  |  | ROUTE WHEN DRAFT COMES | CP
CP | L2HE Cavity Ultrasonic Cleaning | L2HE-CHEM-CAV-USC | R2 | 2021-09-15 |  | A. Wildeson | A. Mitchell | T. Ganey | J. Hogan |  | ashleya,kwilson | J. Hogan,vennekate,ganey | ashleya,vennekate,ganey,J. Hogan,kdavis,forehand,kwilson |  |  |  | Cavities that require reprocessing after a VTRF with high radiation and/or very low FE onset may receive an USC prior to HPR - as was done in the L2PRD project. For L2PRD, this USC was not captured in a traveler. For L2HE, chemistry travelers were created to capture the re-work steps for cavity vertical testing. The chemistry travelers follow standard chemistry processes and were only modified from other project travelers to reflect any 9-cell / L2HE specifics. Cavities recieved from vendor will only require external clean / wipedown prior to VTRF. Therefore the traveler was revised to include directions for if the cavity is under vacuum and a YES/NO data field. | CP
| Assembly | [17 empty] | SS
CP | Cavity 1st Assembly | L2HE-CLNRM-CAV-ASSY1 | R3 | 2021-06-01 |  | D. Forehand | C. Dreyfuss |  | K. Wilson | [7 empty] | This traveler will be used with refurbishment and re-processed / cleaned cavities. It is not to be used with cavities arriving directly from the vendor. Due to the different length field probe tips that were in circulation during the refurbishment work, a statement to replace the field probe with the proper length if required was added to the traveler. A Yes/No data field was also added to capture if the FP was changed. Due to the use of purge-only string assembly and the removal of HPR prior to string assemlby, it was identified that the right angle valve must be positioned correctly (in accordance with the cavity drawing package) in order to fit up with the purge system during string assembly. Instructions will be added to this traveler to ensure that the valve is installed in accordance with the drawing. | CP
CP | Cavity 1st Assembly Procedure | L2HE-PR-CLNRM-CAV-ASSY1 | R1 | 2021-12-01 |  | T. Ganey | C. Dreyfuss | D. Forehand | [9 empty] | CP
CP | Cavity 2nd Assembly | L2HE-CLNRM-CAV-ASSY2 | R2 | 2021-06-01 |  | D. Forehand | C. Dreyfuss |  | K. Wilson | [7 empty] | This traveler will be used with refurbishment and re-processed / cleaned cavities. It is not to be used with cavities arriving directly from the vendor. No changes from L2PRD traveler | CP
CP | Cavity 2nd Assembly Procedure | L2HE-PR-CLNRM-CAV-ASSY2 | R1 | 21/1/21 |  | T. Ganey | C. Dreyfuss | D. Forehand | [9 empty] | CP
CP | Transfer of L2PRD 9-cell cavities to Test Stands | L2HE-CLNRM-CAV-TSTD | R2 | 2021-06-01 |  | D. Forehand | C. Dreyfuss |  | K. Wilson | [7 empty] | Several changes from the L2PRD traveler were identified and suggested. The traveler was updated to allow single cells to be captured in addition to 9-cells. The RGA scan range was updated to the current standard range used at JLab. The decision to seperate out the evacuation and leak check data into a standalone travler will require that this traveler be revised. Also the acceptable leak rate will be updated to reflect the leak rate spec provided in the cavity assembly drawings. | CP
CP | Transfer of L2PRD 9-cell cavities to Test Stands for Dewar 5 | L2HE-CLNRM-CAV-TSTD5 | R1 | 2021-06-01 |  | D. Forehand | C. Dreyfuss |  | K. Wilson | [7 empty] | Several changes from the L2PRD traveler were identified and suggested. The traveler was updated to allow single cells to be captured in addition to 9-cells. The decision to seperate out the evacuation and leak check data into a standalone travler will require that this traveler be revised. Also the acceptable leak rate will be updated to reflect the leak rate spec provided in the cavity assembly drawings. | CP
| Testing | [17 empty] | SS
CP | Production Cavity Vertical Testing Procedure | L2HE-PR-VTA-CAV-VTRF | R1 | 2021-05-21 |  | C. WILSON | K. Davis |  | K. Wilson | [7 empty] | Procedure was updated to L2HE cavity vertical test specs and general VTA / RF testing instructions were updated to reflect current standard testing practices. | CP
CP | Cavity Cooldown | L2HE-VTA-CAV-COOL | R1 | 2021-05-01 |  | J. KENT | J. Vennekate |  | K. Wilson |  | J. Hogan,kwilson | J. Hogan,kwilson | J. Hogan,kwilson,kdavis,jtkent |  |  |  | No changes from L2PRD traveler | CP
CP | Cavity VTA Test | L2HE-VTA-CAV-VTRF | R4 | 2021-05-01 |  | A. Grabowski | J. Vennekate | K. Davis | J. Hogan | [7 empty] | Traveler was updated to L2HE cavity vertical test specs and general VTA / RF testing instructions were updated to reflect current standard testing practices. Additional revision will be made to ensure traveler is in alignment with procedure and updated VTRF common format | CP
CP | VTA Single Cell Thermal Cycles | L2HE-VTA-CAV-THRMCYC | R1 | 2021-10-26 |  | D. Sarvansky | J. Vennekate | J. Kent | [9 empty] | CP
CP | VTA Single Cell Thermal Cycles | L2HE-PR-VTA-CAV-THRMCYC | R1 | 2021-10-26 |  | D. Sarvansky | J. Vennekate | J. Kent | J. Hogan | [8 empty] | CP
| Component Preparation | [17 empty] | SH
| Inspection / INVentory | [17 empty] | SS
CP | FPC COLD PART | L2HE-CLNRM-FPCC-INSP | R3 | 2021-05-24 | 2020-05-15 | N. Huque | D. Forehand | K. Davis | J. Hogan | [5 empty] | 341082, P96406 | FPCC |  | CP
CP | FPC COLD PART PROCEDURE | L2HE-PR-INSP-FPCC | R3 | 2021-05-24 | 2020-05-15 | N. Huque | D. Forehand | K. Davis | C. Dreyfuss | K. Wilson | [7 empty] | CP
CP | FPC WARM PART | L2HE-CMA-FPCW-INSP | R1 | 2021-05-24 | 2020-05-15 | N. Huque | J. Fischer | K. Davis | J. Hogan | K. Wilson |  |  |  |  | 341081, P96394 | FPCW |  | CP
CP | Upper Cold Mass CMA Inspection | L2HE-CMA-UCM-INSP | R1 | 2021-05-28 |  | G. Cheng | J. Fischer | A. Dekerlegand | J. Hogan | G. Cheng | Katherine, J. Hogan | Gary, Fischer | Gary, Fischer |  | F10009954 |  |  | CP
CP | Receiving CMA Inspection CM Vacuum Vessel | L2HE-CMA-VV-INSP | R1 | 2021-05-28 |  | G. Cheng | J. Fischer | A. Dekerlegand | J. Hogan | G. Cheng | Katherine, J. Hogan | Gary, Fischer | Gary, Fischer |  | F10026609 |  |  | CP
CP | Cavity Beam Line Bellows PRCM | L2HE-INSP-BLBP | R1 | 2021-07-26 | 2021-08-01 | M. Marchlik | G. DeKerlegand | L. Zhao | J. Hogan | C. Reece | Hannesv, Reece | Lzhao, Wilson | Lzhao, Wilson |  |  |  |  | CP
CP | Cavity Beam Line Bellows Short | L2HE-INSP-BLBS | R1 | 2021-07-26 | 2021-08-01 | M. Marchlik | G. DeKerlegand | L. Zhao | J. Hogan | M. Marchlik | [7 empty] | CP
CP | Cavity String Weldment Upstream Bellows | L2HE-INSP-BLBU | R1 | 2021-07-01 | 2021-05-10 | M. Marchlik | G. DeKerlegand | L. Zhao | J. Hogan | M. Marchlik | [7 empty] | CP
CP | String Beam Line Extension Downstream | L2HE-INSP-BLXD | R1 | 2021-07-01 |  | M. Marchlik | G. DeKerlegand | L. Zhao | J. Hogan | M. Marchlik | [7 empty] | CP
CP | Cavity Inspection | L2HE-INSP-CAV | R4 | 2021-08-01 |  | T. Ganey | A. DeKerlegand |  | J. Vennekate | J. Hogan | [5 empty] | CAV | Revision to add instructions to visually verify the right angle valve position. Since the cavity may not be disassembled prior to string assembly and the valve position is critical for fit up with the purge system, the valve position needs to be verified during the initial inspection (and flagged with an NCR if valve position is not correct). | CP
CP | Cryomodule Cool Down Cryogenic Valve (CDV) | L2HE-INSP-CDV | R1 | 2021-05-17 |  | J. Kent | J. Fischer | A. McEwen | J. Hogan | J. Kent | Katherine, J. Hogan | Kent, Wilson | Kent, Fischer |  |  |  |  | CP
CP | 300K Current Leads CF Flange Inspection | L2HE-INSP-CFL | R1 | 2021-04-01 |  | L. Lalitha | L. King | M. Morrone | J. Hogan | L. Lalitha | J. Hogan,kwilson | lalitha,king | lalitha,king,fisher,morrone |  |  |  |  | CP
CP | LCLS-II HE 2K Clamp Assembly Kit Inspection | L2HE-INSP-CLMP02K | R2 |  |  | L. Lalitha | L. King | J. Fischer | J. Hogan | L. Lalitha | Kwilson,J. Hogan | lalitha,king | lalitha,king,fischer |  |  |  |  | CP
CP | LCLS-II HE 5K Clamp Assembly Kit Inspection Traveler | L2HE-INSP-CLMP05K | R2 |  |  | L. Lalitha | L. King | J. Fischer | J. Hogan | L. Lalitha | Kwilson,J. Hogan | lalitha,king | lalitha,king,fischer |  |  |  |  | CP
CP | LCLS-II HE 50 K Clamp Assembly Kit Inspection Traveler | L2HE-INSP-CLMP50K | R2 |  |  | L. Lalitha | L. King | J. Fischer | J. Hogan | L. Lalitha | Kwilson,J. Hogan | lalitha,king | lalitha,king,fischer |  |  |  |  | CP
CP | LCLS-II HE Split-Quad Clamp Kit Inspection Traveler | L2HE-INSP-CLMPSQ | R2 |  |  | L. Lalitha | L. King | J. Fischer | J. Hogan | L. Lalitha | Kwilson,J. Hogan | lalitha,king | lalitha,king,fischer |  |  |  |  | CP
CP | FPC Waveguide Incoming Inspection | L2HE-INSP-FPCWG | R1 | 2021-10-15 | 2021-01-27 | N. Huque | M. Stirbet |  | J. Hogan | N. Huque | [5 empty] | FPCWG |  | CP
CP | Cavity Field Probe Feedthru Receiving Inspection | L2HE-INSP-FPFT | R1 | 2020-10-16 |  | L. Zhao | A. DeKerlegand | C. Reece | K. Wilson | L. Zhao | hannesv, Reece | lzhao, Wilson | lzhao, Wilson | No | GMM-9434A |  |  | CP
CP | Cavity HOM Feedthru Receiving Inspection | L2HE-INSP-HMFT | R1 | 2020-10-16 |  | L. Zhao | A. DeKerlegand | C. Reece | K. Wilson | L. Zhao | hannesv, Reece | lzhao, Wilson | lzhao, Wilson | No | GMM-9433A |  |  | CP
CP | Receiving Inspection CM Magnetic Shield Assembly | L2HE-INSP-IMAG | R1 | 2021-05-14 |  | G. Cheng | A. DeKerlegand | J. Fischer | J. Hogan | G. Cheng | Katherine, J. Hogan | Gary, Fischer | Gary, Fischer |  | F10048652 |  |  | CP
CP | Receiving Inspection CM Assembly, JT Cryogenic Valve | L2HE-INSP-JTV | R1 | 2021-05-17 |  | J. Kent | J. Fischer | A. McEwen | J. Hogan | J. Kent | Katherine, J. Hogan | Kent, Wilson | Kent, Fischer |  |  |  |  | CP
CP | Tuner Piezo Actuator Assembly Inspection | L2HE-INSP-PIEZO | R1 | 2021-03-05 | 2021-05-31 | J. Kent | P. Owen | N. Huque | J. Hogan | P. Owen | huque,kwilson | Powen, King | Powen, Huque, Wilson |  |  |  | Will be a batch traveler | CP
CP | Quadrapole Magnet Inspection | L2HE-INSP-QUAD | R1 | 2021-10-08 |  | L. Lalitha | L. King | M. Morrone | J. Hogan | L. Lalitha |  | Lakshmi, Wilson | Lakshmi, Wilson |  |  |  |  | CP
CP | End Lever Tuner Motor | L2HE-INSP-SM | R1 | 2021-04-01 | 2021-04-30 | L. King | P. Owen | N. Huque | J. Hogan | P. Owen | huque,kwilson | Powen, King | Powen, Huque, Wilson |  |  |  | Will be a batch traveler | CP
CP | End Lever Tuner Mechanical Frame Inspection | L2HE-INSP-TUNC | R1 | 2021-07-14 | 2021-08-15 | P. Owen | G. Dekerlegand | N. Huque | J. Hogan | P. Owen | kwilson | Powen, Huque, georged | Powen, Huque, Wilson |  | F10132292-B, F10138922-A |  |  | CP
CP | End Lever Tuner Extended Mechanical Frame Inspection Traveler | L2HE-INSP-TUNCX | R1 | 2021-07-14 | 2021-08-15 | P. Owen | G. Dekerlegand | N. Huque | K. Wilson | J. Hogan | [7 empty] | CP
CP | All Metal Gate Valve Inventory | L2HE-INV-AMGV | R1 | 2021-05-01 |  | M. Dickey | C. Barnes |  | J. Hogan | D. Savransky | Mdicky,J. Hogan | Kwilson,Dsavr | [5 empty] | CP
CP | Cavity Beam Line Bellows PRCM Inventory | L2HE-INV-BLBP | R1 | 2021-07-26 | 2021-08-01 | [12 empty] | CP
CP | Cavity Beam Line Bellows Short Inventory | L2HE-INV-BLBS | R1 | 2021-07-26 | 2021-08-01 | [12 empty] | CP
CP | Cavity String Weldment Upstream Bellows Inventory | L2HE-INV-BLBU | R1 | 2021-05-01 | 2021-05-10 | [12 empty] | CP
CP | String Beam Line Extension Downstream Inventory | L2HE-INV-BLXD | R1 | 2021-07-01 | [13 empty] | CP
CP | 2 Phase Beam Pipe Inventory | L2HE-INV-BP2PH | R1 | [14 empty] | CP
CP | Cavity Inventory | L2HE-INV-CAV | R1 | 2021-08-01 | 2020-05-15 | J. Vennekate | [11 empty] | CP
CP | Current Lead Flange Inventory | L2HE-INV-CFL | R1 |  |  | M. Dickey | C. Barnes | J.Hogan | L. Lalitha |  | Mdickey,Hogan,kwilson | Lalitha,king | Lalitha,king,fischer,morrone |  |  |  |  | CP
CP | LCLS-II HE Cernox Inventory Traveler | L2HE-INV-CERNOX | R1 | 2021-08-15 | 2021-10-01 | M. Dickey | C. Barnes | L. King | J. Hogan | L. King | [6 empty] | regular INV traveler | CP
CP | FPC COLD PART Inventory | L2HE-INV-FPCC | R1 | 2021-05-24 | 2020-05-15 | N. Huque | M. Dickey | C. Barnes | J. Hogan | N. Huque | Dickey,J. Hogan,kwilson | Huque | Huque,J. Hogan,kwilson |  |  |  |  | CP
CP | FPC Waveguide Inventory | L2HE-INV-FPCWG | R1 | 2021-05-01 | 2021-01-27 | M. Dickey | C. Barnes |  | K. Wilson |  | Wislon | Huque,Fischer | Huque,Fisher |  |  |  |  | CP
CP | Cavity Field Probe Feedthru Receiving Inventory | L2HE-INV-FPFT | R1 | 2021-05-19 |  | M. Dickey | C. Barnes |  | J. Hogan | L. Zhao | hannesv, Reece | lzhao, Wilson | lzhao, Wilson |  |  |  |  | CP
CP | Cavity HOM Feedthru Receiving Inventory | L2HE-INV-HMFT | R1 | 2021-05-19 |  | M. Dickey | C. Barnes |  | J. Hogan | L. Zhao | hannesv,reece | lzhao, Wilson | lzhao, Wilson |  |  |  |  | CP
CP | CM Magnetic Shield Assembly Inventory | L2HE-INV-IMAG | R1 | 2021-05-14 |  | M. Dickey | C. Barnes |  | J. Hogan | G. Cheng | Katherine, J. Hogan | Gary, Fischer | Gary, Fischer |  |  |  |  | CP
CP | CM Assembly, JT Valve Tube Kit Inventory | L2HE-INV-JTVTK | R1 | 2021-08-01 | [13 empty] | CP
CP | JT Cryogenic Valve Tube Kit Inventory | L2HE-INV-JTVTK | R1 | [14 empty] | CP
CP | Liquid He Level Downstream Inventory | L2HE-INV-LLDS | R1 | [14 empty] | CP
CP | Line Liquid Level Downstream Inventory | L2HE-INV-LLNDS | R1 | [14 empty] | CP
CP | Line Liquid Level Upstream Inventory | L2HE-INV-LLNUS | R1 | [14 empty] | CP
CP | Liquid He Level Upstream Inventory | L2HE-INV-LLUS | R1 | [14 empty] | CP
CP | Tuner Piezo Actuator Inventory | L2HE-INV-PIEZO | R1 | 2021-05-01 | 2021-05-31 | M. Dickey | C. Barnes |  | J. Hogan | P. Owen | mdickey,J. Hogan,areilly | powen | J. Hogan,powen,areilly |  |  |  |  | CP
CP | Quadrapole Magnet Inventory | L2HE-INV-QUAD | R1 | 2021-06-15 |  | M. Dickey | C. Barnes | M. Morrone | J. Hogan | L. Lalitha |  | Lakshmi, Wilson | Lakshmi, Wilson |  |  |  |  | CP
CP | End Lever Tuner Mechanical Frame Inventory | L2HE-INV-TUNC | R1 | 2021-05-14 |  | M. Dickey | C. Barnes | J. Hogan | P. Owen |  | kwilson,J. Hogan | cheng,fischer,powen | cheng,fischer |  |  |  |  | CP
CP | L2HE Extended Cold Tuner Inventory Traveler | L2HE-INV-TUNCX | R1 | 2021-05-14 |  | M. Dickey | C. Barnes |  | J. Hogan | P. Owen | kwilson,J. Hogan | cheng,fischer,powen | cheng,fischer |  |  |  |  | CP
CP | Upper Cold Mass CMA Inventory | L2HE-INV-UCM | R1 | 2021-05-18 | [13 empty] | CP
CP | CM Vacuum Vessel Inventory | L2HE-INV-VV | R1 | 2021-05-18 | [13 empty] | CP
CP | FPC WARM PART PROCEDURE | L2HE-PR-CMA-FPCW-INSP | R1 | [14 empty] | CP
CP | LCLS-II-HE Faraday Window Manifold Inspection Traveler | L2HE-INSP-FWM | R1 |  |  | T. Ganey | G. DeKerlegand | K. Wilson | J. Hogan |  | hogan | kwilson,ganey | hogan,kwilson,ganey |  |  |  |  | CP
| Chemistry | [17 empty] | SS
CP | Components Cleaning | L2HE-CHEM-COMP-DEGR | R1 | 2021-07-01 |  | A. Mitchell | A. Wildeson |  | J. Hogan |  | ashleya | J. Hogan,ari | ashleya,ari,J. Hogan,kdavis,forehand |  |  |  | Chemistry work was not captured in travelers for L2PRD. Cavity components that require cleaning will be captured in this traveler. The traveler will be based on current component cleaning travelers and standard practices. | CP
| Weld Inspection | [17 empty] | SS
CP | Upper Cold Mass Weld Inspection? | L2HE-CWI-UCM | R1 | 2021-05-28 |  | G. Cheng | A. Jenord | Fischer | J. Hogan | G. Cheng | Katherine, J. Hogan | Gary, Fischer | Gary, Fischer |  | F10009954 |  |  | CP
CP | Vacuum Vessel Receiving Weld Inspection | L2HE-CWI-VV | R1 |  |  | G. Cheng | A. Jenord | Fischer | J. Hogan |  | Kwilson, J. Hogan | Cheng, fischer | Cheng, fischer |  |  |  |  | CP
| Leak Checks | [17 empty] | SS
CP | Cavity Beam Line Bellows PRCM Leak Test | L2HE-CMA-BLBP-LEAK | R1 | 2021-08-15 | 2021-08-01 | M. Marchlik | C. WIlcox |  | K. Wilson | M. Marchlik | Ari, Reece | Marchlik, Wilson | Marchlik, Wilson | Leak check spec 11141-S-0029 | F10041075 |  |  | CP
CP | Cavity Beam Line Bellows Short | L2HE-CMA-BLBS-LEAK | R1 | 2021-08-15 | 2021-08-01 | M. Marchlik | C. WIlcox |  | K. Wilson | M. Marchlik | Ari, Reece | Marchlik, Wilson | Marchlik, Wilson | Leak check spec 11141-S-0029 | F10023437 |  |  | CP
CP | Cavity String Weldment Upstream Bellows | L2HE-CMA-BLBU-LEAK | R1 | 2021-08-15 | 2021-05-10 | M. Marchlik | C. WIlcox |  | K. Wilson | M. Marchlik | Ari, Reece | Marchlik, Wilson | Marchlik, Wilson | Leak check spec 11141-S-0029 | F10075494 |  |  | CP
CP | String Beam Line Extension Downstream | L2HE-CMA-BLXD-LEAK | R1 | 2021-08-15 | 2021-08-01 | M. Marchlik | C. WIlcox |  | K. Wilson | M. Marchlik | Ari, Reece | Marchlik, Wilson | Marchlik, Wilson | Leak check spec 11141-S-0029 | F10052775 |  |  | CP
CP | Cavity Field Probe Feedthru Receiving Inspection | L2HE-CMA-FPFT-LEAK | R1 | 2020-10-21 |  | H. Park | C. WIlcox |  | K. Wilson | L. Zhao | Ari, Reece | Park, Wilson | Park, Wilson | Leak check spec 11141-S-0029 | GMM-9434A |  |  | CP
CP | Cavity HOM Feedthru Receiving Inspection | L2HE-CMA-HMFT-LEAK | R1 | 2020-10-21 |  | H. Park | C. WIlcox |  | K. Wilson | L. Zhao | Ari, Reece | Park, Wilson | Park, Wilson | Leak check spec 11141-S-0029 | GMM-9433A |  |  | CP
R0 | Cavity HOM Measurements and Tuning | L2HE-CMA-HOM-TUNE | R1 | 2022-03-01 | 2022-04-01 | P. Owen | D. Forehand | D. Forehand | J. Hogan | [7 empty] | L2PRD-CAV-HOM-TUNE | R0
OD | Cavity HOM Measurements and Tuning Procedure | L2HE-PR-CMA-HOM-TUNE | R1 | 2022-03-01 | 2022-04-01 | P. Owen | D. Forehand | D. Forehand | J. Hogan | [7 empty] | Procedure to go with L2HE-TUNE-HOM. Needs to be revised to reflect new software.
| Cold Shock | [17 empty] | SS
CP | Cavity Field Probe Feedthru Receiving Inspection | L2HE-VTA-FPFT-CSHK | R1 | 2020-10-22 |  | H. Park | D. Forehand | J. Kent | K. Wilson | H. Park | Ari, Reece | Park, Wilson | Park, Wilson | No | GMM-9434A |  |  | CP
CP | Cavity HOM Feedthru Receiving Inspection | L2HE-VTA-HMFT-CSHK | R1 | 2020-10-23 |  | H. Park | D. Forehand | J. Kent | K. Wilson | H. Park | Ari, Reece | Park, Wilson | Park, Wilson | No | GMM-9433A |  |  | CP
| Cavity String | [17 empty] | SH
| Assembly | [17 empty] | SS
CP | Cavity String Gate Valve Leak Test | L2HE-CLNRM-AMGV-LEAK | R1 | 2021-10-11 | 2021-10-26 | D. Sarvansky | D. Forehand | K. Davis | J. Hogan | [7 empty] | L2PRD-CST-LEAK-AMGV | CP
NR | BPM Magnet sub-assembly | L2HE-CLNRM-GV2SA-ASSY | R2 | 2021-10-11 | 2021-10-26 | D. Forehand | C. Dreyfuss | K. Davis | J. Hogan | [7 empty] | L2PRD-CST-ASSY-BPM | NR
CP | Cavity String Assembly (MAJOR CHANGE) | L2HE-CLNRM-CST-ASSY | R1 | 2021-11-01 | 2021-11-01 | T. Ganey | D. Forehand | K. Davis | J. Hogan | [7 empty] | Will require a major revision to include use of purge system without HPR | CP
NR | Upstream Gate Valve Sub-Assembly | L2HE-PR-CLNRM-GV1SA-ASSY | R2 | 2021-10-26 | 2021-10-26 | T. Ganey | C. Dreyfuss | K. Davis | J. Hogan | [7 empty] | Changes are required to support the purge system string assembly and use of Faraday Window Manifold (or alternate upstream manifold) | NR
CP | Downstream Gate Valve Sub-Assembly | L2HE-PR-CLNRM-GV2SA-ASSY | R1 | 2021-10-26 | 2021-10-26 | T. Ganey | C. Dreyfuss | K. Davis | J. Hogan | [7 empty] | Changes are required to support the purge system string assembly and use of Faraday Window Manifold (or alternate upstream manifold) | CP
CP | NEG Pump Manifold Assembly | L2HE-PR-CLNRM-NEG-ASSY | R1 | 2021-10-26 | 2021-10-26 | T. Ganey | C. Dreyfuss | K. Davis | J. Hogan | [8 empty] | CP
| Chemistry | [17 empty] | SS
CP | Copper Plated String Components Cleaning Procedure | L2HE-PR-CHEM-CST-DEGR | R1 |  |  | T. Ganey | A. Mitchell | R. Fiedler | J. Hogan | [7 empty] | Process developed for L2PRD will be used. Combines bellow specific instructions with instructions for all copper plated string components. | CP
| Cryomodule | [17 empty] | SH
| Cryomodule Assembly | [17 empty] | SS
R0 | CM Assembly First | L2HE-CMA-CM-ASSY1 | R1 | 2021-10-26 |  | J. Fischer | N. Huque | A. Reilly | J. Hogan | [7 empty] | L2PRD-CM-ASSY-FRST | R0
R0 | CM Assembly Second | L2HE-CMA-CM-ASSY2 | R1 | 2021-10-26 |  | J. Fischer | N. Huque | A. Reilly | J. Hogan | [7 empty] | L2PRD-CM-ASSY-SCND | R0
R0 | CM Assembly Final | L2HE-CMA-CM-ASSYF | R1 | 2021-10-26 |  | J. Fischer | N. Huque | A. Reilly | J. Hogan | [7 empty] | L2PRD-CM-ASSY-FNAL | R0
R0 | Cryomodule Prep and Shipping to SLAC | L2HE-CMA-CM-SHIP | R1 | 2021-10-26 |  | J. Fischer | N. Huque | A. Reilly | J. Hogan | [7 empty] | L2PRD-CM-ASSY-SHIP | R0
| FPC Warm Installation | L2HE-PR-CMA-FPCW-ASSY | R1 | 2022-09-01 | 2022-10-01 | N. Huque | K. Davis | J. Fischer | J. Hogan
R0 | Cryomodule Vacuum Vessel Assembly | L2HE-CMA-VV-ASSY | R1 | 2021-10-26 |  | J. Fischer | G. Cheng | A. Reilly | J. Hogan | [7 empty] | L2PRD-CM-ASSY-VV | R0
CP | FPC WARM PART Inventory | L2HE-INV-FPCW | R1 | 2021-05-24 | 2020-05-15 |  |  |  | J. Hogan | N. Huque | [7 empty] | CP
| Processing | [17 empty] | SS
CP | Upper Cold Mass Magnetic Hygiene Control | L2HE-CMA-UCM-DMAG | R1 | 2021-05-28 |  | G. Cheng | J. Fischer |  | J. Hogan | Cheng | Wilson, J. Hogan | Fischer, Cheng | Fischer, Cheng |  |  |  |  | CP
OA | LCLSII-HE LERF Prep & Cooldown | L2HE-LERF-CM-PREP | R1 |  |  | M. Weaks | N. Huque | L. King | M. Drury | J. Hogan | Hogan,Huque | Drury | Hogan,Huque,Drury |  |  |  |  | OA
CP | Production Cryomodule Demagnetization | L2HE-LERF-CM-DMAG | R1 | 2021-08-31 |  | G. Cheng | J. Fischer | M. Drury | J. Hogan | Cheng | Wilson, J. Hogan | Fischer, Cheng | Fischer, Cheng |  |  |  | L2PRD-CM-DMAG-LERF-R1 | CP
| Cryomodule Testing | [17 empty] | SS
CP | Cryomodule Acceptance Test LERF | L2HE-LERF-CM-ACTS | R1 | 2021-09-01 |  | M. Drury | G. Ciovatti | J. Vennekatte | J. Hogan | [8 empty] | CP
| Standard Project Travelers | [17 empty] | SH
CP | D3 Report | L2HE-D3 | R2 | [14 empty] | CP
CP | Cavity Non-conformance Report | L2HE-NCR | R11 | [14 empty] | CP
CP | Inspection Summary Report | L2HE-INSR | R1 | [14 empty] | CP
Color Legend |  | Count | Percent
CP | Complete (CP) | 93 | 89.42%
NR | New Revision Out for Approval (NR) | 2 | 1.923%
OA | Out for Approval (OA) | 1 | 0.9615%
30 | Due in 30 Days | 0 | 0%
15 | Due in 15 Days | 0 | 0%
OD | Overdue | 1 | 0.9615%
R0 | R0 Draft | 6 | 5.769%
| Remaining | 1 | 0.9615%
| Total Traveler IDs | 104
Note on C91: Homer Samuels: Hold. Peter to Redo
Note on C118: Homer Samuels: pull from L2PRD

## COMPARISON
L2HE |  | L2PRD | MASTER LIST L2PRD | MASTER LIST L2HE
CHEMISTRY |  |  | L2PRD-CAV-ASSY-FRST | L2HE-CHEM-CAV-DEGR
L2HE-CHEM-CAV-DEGR |  |  | L2PRD-CAV-ASSY-SCND | L2HE-CHEM-CAV-HEP
L2HE-CHEM-CAV-HEP |  |  | L2PRD-CAV-HOM-TUNE | L2HE-CHEM-CAV-HPR
L2HE-CHEM-CAV-HPR |  |  | L2PRD-CAV-INSP-BLA | L2HE-CHEM-CAV-USC
L2HE-CHEM-CAV-USC |  |  | L2PRD-CAV-INSP-CAV | L2HE-CHEM-COMP-DEGR
L2HE-CHEM-COMP-DEGR |  |  | L2PRD-CAV-INSP-FPC | L2HE-CHEM-COMP-HPR
L2HE-CHEM-COMP-HPR |  |  | L2PRD-CAV-INSP-FPCWG | L2HE-CHEM-COMP-LAP
L2HE-CHEM-COMP-LAP |  |  | L2PRD-CAV-INSP-FPFT | L2HE-CLNRM-CAV-ASSY1
|  |  | L2PRD-CAV-INSP-HELV | L2HE-CLNRM-CAV-ASSY2
CLEAN ROOM |  |  | L2PRD-CAV-INSP-HMFT | L2HE-CLNRM-CAV-LEAK
L2HE-CLNRM-CAV-ASSY1 |  | L2PRD-CAV-ASSY-FRST | L2PRD-CAV-RECV-CAV | L2HE-CLNRM-CAV-TSTD
L2HE-CLNRM-CAV-ASSY2 |  | L2PRD-CAV-ASSY-SCND | L2PRD-CAV-RECV-CAVEZ2-HLDPT1 | L2HE-CLNRM-CAV-TSTD5
L2HE-TUNE-HOM |  | L2PRD-CAV-HOM-TUNE | L2PRD-CAV-RECV-CAVEZ2-HLDPT2 | L2HE-CLNRM-FPCC-INSP
L2HE-TUNE-CAV-RFIN |  | L2PRD-CAV-RFIN | L2PRD-CAV-RECV-CAVEZ2-HLDPT3 | L2HE-CMA-BLBP-LEAK
L2HE-CLNRM-CAV-LEAK |  |  | L2PRD-CAV-RECV-CAVEZ3-HLDPT2 | L2HE-CMA-BLBS-LEAK
L2HE-CLNRM-CAV-TSTD |  | L2PRD-CAV-TRANS-TSTD | L2PRD-CAV-RECV-CAVEZ4-HLDPT2 | L2HE-CMA-BLBU-LEAK
L2HE-CLNRM-CAV-TSTD5 |  | L2PRD-CAV-TRANS-TSTD-D5 | L2PRD-CAV-RECV-CAVEZ-HLDPT1 | L2HE-CMA-BLXD-LEAK
|  | L2PRD-CM-DISA-FPCW | L2PRD-CAV-RECV-CAVEZ-HLDPT2 | L2HE-CMA-FNAL
L2HE-CST-ASSY |  | L2PRD-CST-ASSY | L2PRD-CAV-RECV-CAVEZ-HLDPT3 | L2HE-CMA-FPCW
L2HE-CST-ASSY-BPM |  | L2PRD-CST-ASSY-BPM | L2PRD-CAV-RECV-CAV-HLDPT1 | L2HE-CMA-FPCW-DISA
L2HE-CST-ASSY-LEAK |  | L2PRD-CST-ASSY-LEAK | L2PRD-CAV-RECV-CAV-HLDPT2 | L2HE-CMA-FPCW-INSP
L2HE-CST-LEAK-AMGV |  | L2PRD-CST-LEAK-AMGV | L2PRD-CAV-RECV-CAV-HLDPT3 | L2HE-CMA-FPFT-LEAK
moved to insp |  | L2PRD-CST-MAG-QUAD | L2PRD-CAV-RECV-DRT | L2HE-CMA-FRST
L2HE-CLNRM-FPCC-INSP |  |  | L2PRD-CAV-RECV-FPC | L2HE-CMA-HMFT-LEAK
TESTING |  |  | L2PRD-CAV-RECV-FPCWG | L2HE-CMA-REW
L2HE-VTA-CAV-COOL |  | L2PRD-CAV-VTA-COOL | L2PRD-CAV-RECV-FPFT | L2HE-CMA-RFIT
L2HE-VTA-CAV-HOM |  | L2PRD-CAV-VTA-HOM | L2PRD-CAV-RECV-HELV | L2HE-CMA-SCND
L2HE-VTA-CAV-VTRF |  | L2PRD-CAV-VTRF | L2PRD-CAV-RECV-HMFT | L2HE-CMA-SHIP
L2HE-VTA-FPFT-CSHK |  |  | L2PRD-CAV-RECV-NB55 | L2HE-CMA-UCM-DMAG
L2HE-VTA-HMFT-CSHK |  |  | L2PRD-CAV-RFIN | L2HE-CMA-UCM-INSP
|  | L2PRD-CM-ACTS | L2PRD-CAV-TRANS-TSTD | L2HE-CMA-VV
L2HE-LERF-CM-ACTS |  | L2PRD-CM-ACTS-LERF | L2PRD-CAV-TRANS-TSTD-D5 | L2HE-CMA-VV-INSP
|  | L2PRD-CM-ACTS-PREP | L2PRD-CAV-VTA-COOL | L2HE-CST-ASSY
L2HE-LERF-CM-DMAG |  | L2PRD-CM-DMAG-LERF | L2PRD-CAV-VTA-HOM | L2HE-CST-ASSY-BPM
|  |  | L2PRD-CAV-VTRF | L2HE-CST-ASSY-LEAK
CRYOMODULE |  |  | L2PRD-CM-ACTS | L2HE-CST-LEAK-AMGV
L2HE-CMA-FNAL |  | L2PRD-CM-ASSY-FNAL | L2PRD-CM-ACTS-LERF | L2HE-CWI-UCM
L2HE-CMA-FPCW |  | L2PRD-CM-ASSY-FPCW | L2PRD-CM-ACTS-PREP | L2HE-D3
L2HE-CMA-FRST |  | L2PRD-CM-ASSY-FRST | L2PRD-CM-ASSY-FNAL | L2HE-INSP-BLBP
L2HE-CMA-REW |  | L2PRD-CM-ASSY-REW | L2PRD-CM-ASSY-FNAL | L2HE-INSP-BLBS
L2HE-CMA-RFIT |  | L2PRD-CM-ASSY-RFIT | L2PRD-CM-ASSY-FPCW | L2HE-INSP-BLBU
L2HE-CMA-SCND |  | L2PRD-CM-ASSY-SCND | L2PRD-CM-ASSY-FRST | L2HE-INSP-BLXD
L2HE-CMA-SHIP |  | L2PRD-CM-ASSY-SHIP | L2PRD-CM-ASSY-REW | L2HE-INSP-CAV
L2HE-CMA-VV |  | L2PRD-CM-ASSY-VV | L2PRD-CM-ASSY-RFIT | L2HE-INSP-CDV
|  | L2PRD-CM-DMAG-CM | L2PRD-CM-ASSY-SCND | L2HE-INSP-CFL
L2HE-CMA-BLBP-LEAK |  |  | L2PRD-CM-ASSY-SHIP | L2HE-INSP-FPCWG
L2HE-CMA-BLBS-LEAK |  |  | L2PRD-CM-ASSY-VV | L2HE-INSP-FPFT
L2HE-CMA-BLBU-LEAK |  |  | L2PRD-CM-DISA-FPCW | L2HE-INSP-HMFT
L2HE-CMA-BLXD-LEAK |  |  | L2PRD-CM-DMAG-CM | L2HE-INSP-IMAG
L2HE-CMA-FPFT-LEAK |  |  | L2PRD-CM-DMAG-LERF | L2HE-INSP-IROD2L
L2HE-CMA-HMFT-LEAK |  |  | L2PRD-CM-DMAG-UCM | L2HE-INSP-IROD2P
L2HE-CMA-FPCW-DISA |  |  | L2PRD-CM-DMAG-VV | L2HE-INSP-JTV
L2HE-CMA-UCM-DMAG |  |  | L2PRD-CM-INSP-BLA | L2HE-INSP-JTVTK
L2HE-CMA-FPCW-INSP |  | MOVED FROM INSP | L2PRD-CM-INSP-BLAV | L2HE-INSP-PIEZO
L2HE-CMA-UCM-INSP |  | MOVED FROM INSP | L2PRD-CM-INSP-BP2PH | L2HE-INSP-QUAD
L2HE-CMA-VV-INSP |  | MOVED FROM INSP | L2PRD-CM-INSP-CDV | L2HE-INSP-SM
|  |  | L2PRD-CM-INSP-DK12P | L2HE-INSP-TUNC
|  |  | L2PRD-CM-INSP-DK22P | L2HE-INSR
INSPECTIONS |  |  | L2PRD-CM-INSP-EDCP | L2HE-INV-AMGV
|  | L2PRD-CM-INSP-BLA | L2PRD-CM-INSP-FDCP | L2HE-INV-BLBP
|  | L2PRD-CAV-INSP-BLA | L2PRD-CM-INSP-FPCW | L2HE-INV-BLBS
|  | L2PRD-CM-INSP-BLAV | L2PRD-CM-INSP-FPCWG | L2HE-INV-BLBU
|  | L2PRD-CM-INSP-BP2PH | L2PRD-CM-INSP-IMAG | L2HE-INV-BLXD
L2HE-INSP-CDV |  | L2PRD-CM-INSP-CDV | L2PRD-CM-INSP-IROD2L | L2HE-INV-CAV
| 0 | L2PRD-CM-INSP-DK12P | L2PRD-CM-INSP-IROD2P | L2HE-INV-FPCC
| 0 | L2PRD-CM-INSP-DK22P | L2PRD-CM-INSP-JTV | L2HE-INV-FPCW
| 0 | L2PRD-CM-INSP-EDCP | L2PRD-CM-INSP-JTVTK | L2HE-INV-FPCWG
| 0 | L2PRD-CM-INSP-FDCP | L2PRD-CM-INSP-LLDS | L2HE-INV-FPFT
moved to CMA |  | L2PRD-CM-INSP-FPCW | L2PRD-CM-INSP-LLNDS | L2HE-INV-HMFT
|  | L2PRD-CM-INSP-FPCWG | L2PRD-CM-INSP-LLNUS | L2HE-INV-IMAG
L2HE-INSP-FPCWG |  | L2PRD-CAV-INSP-FPCWG | L2PRD-CM-INSP-LLUS | L2HE-INV-JTVTK
L2HE-INSP-IMAG |  | L2PRD-CM-INSP-IMAG | L2PRD-CM-INSP-MCCLA | L2HE-INV-PIEZO
L2HE-INSP-IROD2L |  | L2PRD-CM-INSP-IROD2L | L2PRD-CM-INSP-PEC2P | L2HE-INV-QUAD
L2HE-INSP-IROD2P |  | L2PRD-CM-INSP-IROD2P | L2PRD-CM-INSP-UCM | L2HE-INV-TUNC
L2HE-INSP-JTV |  | L2PRD-CM-INSP-JTV | L2PRD-CM-INSP-VV | L2HE-INV-TUNCX
L2HE-INSP-JTVTK |  | L2PRD-CM-INSP-JTVTK | L2PRD-CM-RECV | L2HE-INV-UCM
|  | L2PRD-CM-INSP-LLDS | L2PRD-CM-RECV-BP2PH | L2HE-INV-VV
|  | L2PRD-CM-INSP-LLNDS | L2PRD-CM-RECV-C12P | L2HE-LERF-CM-ACTS
|  | L2PRD-CM-INSP-LLNUS | L2PRD-CM-RECV-CDV | L2HE-LERF-CM-DMAG
|  | L2PRD-CM-INSP-LLUS | L2PRD-CM-RECV-DCXCU | L2HE-NCR
|  | L2PRD-CM-INSP-MCCLA | L2PRD-CM-RECV-DCXSD | L2HE-PR-INSP-FPCC
|  | L2PRD-CM-INSP-PEC2P | L2PRD-CM-RECV-DDTCU | L2HE-PR-VTA-CAV-VTRF
MOVED TO CMA |  | L2PRD-CM-INSP-UCM | L2PRD-CM-RECV-DDTSD | L2HE-TUNE-CAV-RFIN
MOVED TO CMA |  | L2PRD-CM-INSP-VV | L2PRD-CM-RECV-DK12P | L2HE-TUNE-HOM
L2HE-INSP-CAV |  | L2PRD-CAV-INSP-CAV | L2PRD-CM-RECV-DK22P | L2HE-VTA-CAV-COOL
MOVED TO CLNRM |  | L2PRD-CAV-INSP-FPC | L2PRD-CM-RECV-FT06P | L2HE-VTA-CAV-HOM
L2HE-INSP-FPFT |  | L2PRD-CAV-INSP-FPFT | L2PRD-CM-RECV-HLS | L2HE-VTA-CAV-VTRF
|  | L2PRD-CAV-INSP-HELV | L2PRD-CM-RECV-IMAG | L2HE-VTA-FPFT-CSHK
L2HE-INSP-HMFT |  | L2PRD-CAV-INSP-HMFT | L2PRD-CM-RECV-IP75SD | L2HE-VTA-HMFT-CSHK
|  | L2PRD-CST-INSP-BLBL | L2PRD-CM-RECV-IROD2L
L2HE-INSP-BLBP |  | L2PRD-CST-INSP-BLBP | L2PRD-CM-RECV-IROD2P
L2HE-INSP-BLBS |  | L2PRD-CST-INSP-BLBS | L2PRD-CM-RECV-JTV
L2HE-INSP-BLBU |  | L2PRD-CST-INSP-BLBU | L2PRD-CM-RECV-JTVTK
L2HE-INSP-BLXD |  | L2PRD-CST-INSP-BLXD | L2PRD-CM-RECV-LLDS
|  | L2PRD-CST-INSP-BLXU | L2PRD-CM-RECV-LLNDS
|  | L2PRD-CST-INSP-BPMFT | L2PRD-CM-RECV-LLNUS
L2HE-INSP-CFL |  | L2PRD-CST-INSP-CFL | L2PRD-CM-RECV-LLUS
L2HE-INSP-TUNC |  | L2PRD-CST-INSP-TUNMC | L2PRD-CM-RECV-MCCLA
L2HE-INSP-SM |  | L2PRD-CST-INSP-TUNMT | L2PRD-CM-RECV-P2PH
L2HE-INSP-PIEZO |  | L2PRD-CST-INSP-TUNPZ | L2PRD-CM-RECV-PEC2P
|  | L2PRD-CST-RINSP-BLBP | L2PRD-CM-RECV-TSCPLR
|  | L2PRD-CST-RINSP-BLBS | L2PRD-CM-RECV-TSHMSM
| 0 | L2PRD-CST-RINSP-BLXD | L2PRD-CM-RECV-UCM
L2HE-INSP-QUAD |  |  | L2PRD-CM-RECV-VV
L2PRD-CST-ASSY
RECEIVING |  |  | L2PRD-CST-ASSY-BPM
L2HE-INV-CAV |  | L2PRD-CAV-RECV-CAV | L2PRD-CST-ASSY-LEAK
|  | L2PRD-CAV-RECV-CAVEZ2-HLDPT1 | L2PRD-CST-INSP-BLBL
|  | L2PRD-CAV-RECV-CAVEZ2-HLDPT2 | L2PRD-CST-INSP-BLBP
|  | L2PRD-CAV-RECV-CAVEZ2-HLDPT3 | L2PRD-CST-INSP-BLBS
|  | L2PRD-CAV-RECV-CAVEZ3-HLDPT2 | L2PRD-CST-INSP-BLBU
|  | L2PRD-CAV-RECV-CAVEZ4-HLDPT2 | L2PRD-CST-INSP-BLXD
|  | L2PRD-CAV-RECV-CAVEZ-HLDPT1 | L2PRD-CST-INSP-BLXU
|  | L2PRD-CAV-RECV-CAVEZ-HLDPT2 | L2PRD-CST-INSP-BPMFT
|  | L2PRD-CAV-RECV-CAVEZ-HLDPT3 | L2PRD-CST-INSP-CFL
|  | L2PRD-CAV-RECV-CAV-HLDPT1 | L2PRD-CST-INSP-TUNMC
|  | L2PRD-CAV-RECV-CAV-HLDPT2 | L2PRD-CST-INSP-TUNMT
|  | L2PRD-CAV-RECV-CAV-HLDPT3 | L2PRD-CST-INSP-TUNPZ
|  | L2PRD-CAV-RECV-DRT | L2PRD-CST-LEAK-AMGV
L2HE-INV-FPCC |  | L2PRD-CAV-RECV-FPC | L2PRD-CST-MAG-QUAD
L2HE-INV-FPCW |  |  | L2PRD-CST-RECV
L2HE-INV-FPCWG |  | L2PRD-CAV-RECV-FPCWG | L2PRD-CST-RECV-AMGV
L2HE-INV-FPFT |  | L2PRD-CAV-RECV-FPFT | L2PRD-CST-RECV-BLA
|  | L2PRD-CAV-RECV-HELV | L2PRD-CST-RECV-BLACRM
L2HE-INV-HMFT |  | L2PRD-CAV-RECV-HMFT | L2PRD-CST-RECV-BLBP
|  | L2PRD-CAV-RECV-NB55 | L2PRD-CST-RECV-BLBS
| 0 | L2PRD-CM-RECV | L2PRD-CST-RECV-BLXD
|  | L2PRD-CM-RECV-BP2PH | L2PRD-CST-RECV-BLXU
| 0 | L2PRD-CM-RECV-C12P | L2PRD-CST-RECV-BPM
|  | L2PRD-CM-RECV-CDV | L2PRD-CST-RECV-BPMFT
|  | L2PRD-CM-RECV-DCXCU | L2PRD-CST-RECV-CFL
|  | L2PRD-CM-RECV-DCXSD | L2PRD-CST-RECV-TUNMC
|  | L2PRD-CM-RECV-DDTCU | L2PRD-CST-RECV-TUNMT
|  | L2PRD-CM-RECV-DDTSD | L2PRD-CST-RECV-TUNPZ
| 0 | L2PRD-CM-RECV-DK12P | L2PRD-CST-RINSP-BLBP
| 0 | L2PRD-CM-RECV-DK22P | L2PRD-CST-RINSP-BLBS
|  | L2PRD-CM-RECV-FT06P | L2PRD-CST-RINSP-BLXD
| 0 | L2PRD-CM-RECV-HLS | L2PRD-D3
L2HE-INV-IMAG |  | L2PRD-CM-RECV-IMAG | L2PRD-INSR
|  | L2PRD-CM-RECV-IP75SD | L2PRD-NCR
| 0 | L2PRD-CM-RECV-IROD2L
| 0 | L2PRD-CM-RECV-IROD2P
L2PRD-CM-RECV-JTV
L2HE-INV-JTVTK |  | L2PRD-CM-RECV-JTVTK
L2PRD-CM-RECV-LLDS
L2PRD-CM-RECV-LLNDS
L2PRD-CM-RECV-LLNUS
L2PRD-CM-RECV-LLUS
L2PRD-CM-RECV-MCCLA
L2PRD-CM-RECV-P2PH
L2PRD-CM-RECV-PEC2P
| 0 | L2PRD-CM-RECV-TSCPLR
| 0 | L2PRD-CM-RECV-TSHMSM
L2HE-INV-UCM |  | L2PRD-CM-RECV-UCM
L2HE-INV-VV |  | L2PRD-CM-RECV-VV
| 0 | L2PRD-CST-RECV
L2HE-INV-AMGV |  | L2PRD-CST-RECV-AMGV
L2PRD-CST-RECV-BLA
L2PRD-CST-RECV-BLACRM
L2HE-INV-BLBP |  | L2PRD-CST-RECV-BLBP
L2HE-INV-BLBS |  | L2PRD-CST-RECV-BLBS
L2HE-INV-BLBU
L2HE-INV-BLXD |  | L2PRD-CST-RECV-BLXD
L2PRD-CST-RECV-BLXU
L2PRD-CST-RECV-BPM
L2PRD-CST-RECV-BPMFT
L2PRD-CST-RECV-CFL
L2HE-INV-TUNC |  | L2PRD-CST-RECV-TUNMC
L2HE-INV-TUNCX
L2PRD-CST-RECV-TUNMT
L2HE-INV-PIEZO |  | L2PRD-CST-RECV-TUNPZ
L2HE-INV-QUAD

## L2PRD TRAVS
Traveler Id | Rev No | Traveler Name | Author | Date
L2PRD-CAV-ASSY-FRST | R2 | L2PRD Nine Cell Cavity First Assembly | D. Forehand | 12-Jul-2018
L2PRD-CAV-ASSY-SCND | R1 | L2PRD Nine Cell Cavity Second Assembly | D. Forehand | 09-Jul-2018
L2PRD-CAV-HOM-TUNE | R5 | LCLS-II cavity HOM measurements and tuning | A. Solopova | 23-Apr-2018
L2PRD-CAV-INSP-BLA | R4 | LCLSII HOM BLA incoming inspection, testing and storage | HyeKyong Park | 07-Feb-2019
L2PRD-CAV-INSP-CAV | R5 | L2PRD LCLS-II Cavity Receiving Inspection | K. Wilson | 25-Jul-2017
L2PRD-CAV-INSP-FPC | R1 | LCLSII FPC incoming inspection | M. Stirbet | 16-Jul-2015
L2PRD-CAV-INSP-FPCWG | R1 | L2PRD FPC waveguide incoming inspection | M.Stirbet | 08-Jun-2017
L2PRD-CAV-INSP-FPFT | R4 | LCLS-II Field Probe Feedthru Receiving Inspection | HK. Park | 21-Feb-2018
L2PRD-CAV-INSP-HELV | R3 | L2PRD LCLS-II Cavity Receiving Inspection | K. Wilson | 06-Jul-2016
L2PRD-CAV-INSP-HMFT | R3 | LCLS-II HOM Feedthru Receiving Inspection | HK. Park | 23-May-2016
L2PRD-CAV-RECV-CAV | R2 | L2PRD Dressed Cavity Inventory Traveler | K. Wilson | 21-Jun-2016
L2PRD-CAV-RECV-CAV-HLDPT1 | R1 | Cavity Vendor Holdpoint 1 Documentation | M. McDonald | 31-May-2016
L2PRD-CAV-RECV-CAV-HLDPT2 | R1 | Cavity Vendor Holdpoint 2 Documentation | M. McDonald | 22-Jun-2016
L2PRD-CAV-RECV-CAV-HLDPT3 | R1 | Cavity Vendor Holdpoint 3 Documentation | M. McDonald | 14-Jul-2016
L2PRD-CAV-RECV-CAVEZ-HLDPT1 | R1 | Receiving Cavity Vendor Documentation from Zanon for Holdpoint 1 | M. McDonald | 18-Oct-2016
L2PRD-CAV-RECV-CAVEZ-HLDPT2 | R1 | Receiving Cavity Vendor Documentation from Zanon for Holdpoint 2 | M. McDonald | 03-Nov-2016
L2PRD-CAV-RECV-CAVEZ-HLDPT3 | R1 | Receiving Cavity Vendor Documentation from Zanon for Holdpoint 3 | M. McDonald | 12-Dec-2017
L2PRD-CAV-RECV-CAVEZ2-HLDPT1 | R1 | Receiving Cavity Vendor Documentation from Zanon for Holdpoint 1 | M. McDonald | 29-Jan-2018
L2PRD-CAV-RECV-CAVEZ2-HLDPT2 | R1 | Receiving Cavity Vendor Documentation from Zanon for Holdpoint 2 | M. McDonald | 15-Nov-2016
L2PRD-CAV-RECV-CAVEZ2-HLDPT3 | R1 | Receiving Cavity Vendor Documentation from Zanon for Holdpoint 3 | M. McDonald | 18-Aug-2017
L2PRD-CAV-RECV-CAVEZ3-HLDPT2 | R1 | Receiving Cavity Vendor Documentation from Zanon for Holdpoint 2 | M. McDonald | 25-May-2017
L2PRD-CAV-RECV-CAVEZ4-HLDPT2 | R1 | Receiving Cavity Vendor Documentation from Zanon for Holdpoint 2 | M. McDonald | 29-Aug-2018
L2PRD-CAV-RECV-DRT | R1 | L2PRD Cernox RTD¿ Inventory Traveler | M. McDonald | 08-Feb-2016
L2PRD-CAV-RECV-FPC | R1 | L2PRD FPC receiving | M.Stirbet | 07-Sep-2016
L2PRD-CAV-RECV-FPCWG | R2 | L2PRD FPC Waveguide Inventory Traveler | M.Stirbet | 26-Aug-2016
L2PRD-CAV-RECV-FPFT | R1 | L2PRD Field Probe FeedThru Inventory Traveler | M. McDonald | 19-Feb-2015
L2PRD-CAV-RECV-HELV | R1 | L2PRD Dressed Cavity Inventory Traveler | M. McDonald | 26-Feb-2016
L2PRD-CAV-RECV-HMFT | R1 | L2PRD HOM FeedThru Inventory Traveler | M. McDonald | 19-Feb-2015
L2PRD-CAV-RECV-NB55 | R1 | L2PRD Niobium Inventory Traveler | M. McDonald | 26-Feb-2016
L2PRD-CAV-RFIN | R1 | L2PRD LCLS-II Cavity RF Incoming Inspection | F. Marhauser | 17-Jun-2016
L2PRD-CAV-TRANS-TSTD | R1 | L2PRD Nine Cell Cavity Transfer to Test Stand | D. Forehand | 23-Jul-2016
L2PRD-CAV-TRANS-TSTD-D5 | R2 | L2PRD Nine Cell Cavity Transfer to Test Stand for Dewar 5 | D. Forehand | 21-May-2019
L2PRD-CAV-VTA-COOL | R2 | LCLS Cavity VTA Cooldown | P. Kushnick | 04-Jun-2019
L2PRD-CAV-VTA-HOM | R1 | LCLSII Cavity Production VTA HOM Survey | M. Stirbet | 19-Aug-2016
L2PRD-CAV-VTRF | R4 | LCLSII (Production Cryomodule) Vertical cavity Testing | K. Davis | 09-May-2019
L2PRD-CM-ACTS | R4 | LCLS II Production Cryomodule Acceptance Testing | M. Drury | 23-Apr-2018
L2PRD-CM-ACTS-LERF | R1 | LCLS II Production Cryomodule Acceptance Testing in the LERF | M. Drury | 16-Jan-2019
L2PRD-CM-ACTS-PREP | R1 | LCLSII (Production Cryomodule) Install and Cool Down | M. Drury | 13-Apr-2017
L2PRD-CM-ASSY-FNAL | R5 | LCLS2 Production Cryomodule Final Assembly Traveler | J. Fischer | 01-Jun-2017
L2PRD-CM-ASSY-FNAL | R6 | LCLS2 Production Cryomodule Final Assembly Traveler | J. Fischer | 01-Jun-2017
L2PRD-CM-ASSY-FPCW | R3 | LCLSII L2PRD-CM-ASSY-FPCW installation | M. Stirbet | 17-Jul-2017
L2PRD-CM-ASSY-FRST | R10 | LCLS2 Production Cryomodule Assembly Traveler Cold Mass Phase 1 | John Fischer | 26-Jul-2018
L2PRD-CM-ASSY-REW | R1 | LCLS2 Production Cryomodule Rework Traveler | R. Legg | 01-Mar-2017
L2PRD-CM-ASSY-RFIT | R7 | LCLS2 Production Cryomodule Retrofit Traveler | Bob Legg | 01-Mar-2017
L2PRD-CM-ASSY-SCND | R7 | LCLS2 Production Cryomodule Assembly Traveler Cold Mass Phase 2 (WS3) | John Fischer | 03-Aug-2018
L2PRD-CM-ASSY-SHIP | R6 | LCLS2 Cryomodule Prep and Shipping to SLAC- WS6 | Jared Martin | 12-Dec-2017
L2PRD-CM-ASSY-VV | R4 | LCLS2 Production Cryomodule Vacuum Vessel Assembly Traveler | J. Fischer | 13-Apr-2017
L2PRD-CM-DISA-FPCW | R2 | LCLSII FPCW AC Disassemble/Removal | M. Stirbet | 03-Oct-2017
L2PRD-CM-DMAG-CM | R1 | LCLS-II Production Cryomodule Demagnetization | R. Legg | 21-Jul-2017
L2PRD-CM-DMAG-LERF | R1 | LCLS-II Production Cryomodule Demagnetization | R Legg | 07-Jan-2019
L2PRD-CM-DMAG-UCM | R1 | LCLS-II Upper Cold Mass Magnetic Hygiene Control | G. Cheng | 08-Feb-2017
L2PRD-CM-DMAG-VV | R1 | LCLS-II Production Cryomodule Vacuum Vessel Demagnetization | G. Cheng | 10-Jan-2016
L2PRD-CM-INSP-BLA | R2 | LCLSII HOM BLA incoming inspection, assembly, and testing | HyeKyoung Park | 13-Aug-2019
L2PRD-CM-INSP-BLAV | R1 | All metal right angle valve leak check traveler for LCLS-II BLA | HyeKyoung Park | 09-Aug-2019
L2PRD-CM-INSP-BP2PH | R1 | Receiving Inspection of LCLS-II Production Cryomodule Weldment , Bellows 2-Phase Pipe (BP2PH) | G. Cheng | 11-May-2016
L2PRD-CM-INSP-CDV | R1 | Receiving Inspection of LCLS-II Cryomodule Cool Down Cryogenic Valve (CDV) | G. Cheng | 20-Feb-2017
L2PRD-CM-INSP-DK12P | R1 | Receiving Inspection of LCLS-II Production Cryomodule Disk 2-Phase Support (DK12P) | G. Cheng | 06-Sep-2016
L2PRD-CM-INSP-DK22P | R1 | Receiving Inspection of LCLS-II Production Cryomodule Disk 2-Phase Support (DK22P) | G. Cheng | 06-Sep-2016
L2PRD-CM-INSP-EDCP | R1 | Shipping End Cap Inspection Traveler | N. Huque | 02-Nov-2016
L2PRD-CM-INSP-FDCP | R1 | Shipping Feed Cap Inspection Traveler | N. Huque | 02-Nov-2016
L2PRD-CM-INSP-FPCW | R2 | LCLSII warm FPC incoming inspection | M. Stirbet | 28-Sep-2015
L2PRD-CM-INSP-FPCWG | R1 | L2PRD FPC waveguide incoming inspection | M.Stirbet | 28-Sep-2016
L2PRD-CM-INSP-IMAG | R2 | Receiving Inspection of LCLS-II Production Cryomodule Magnetic Shield Assembly | G. Cheng | 14-Dec-2016
L2PRD-CM-INSP-IROD2L | R1 | Receiving Inspection of LCLS-II Production Cryomodule Rod Invar 2-Phase Long (IROD2L) | G. Cheng | 07-Sep-2016
L2PRD-CM-INSP-IROD2P | R1 | Receiving Inspection of LCLS-II Production Cryomodule Rod Invar 2-Phase (IROD2P) | G. Cheng | 07-Sep-2016
L2PRD-CM-INSP-JTV | R1 | Receiving Inspection of LCLS-II Cryomodule JT Cryogenic Valve (JTV) | G. Cheng | 10-Oct-2016
L2PRD-CM-INSP-JTVTK | R1 | Receiving Inspection of LCLS-II Production Cryomodule Assembly, JT Valve Tube Kit (JTVTK) | G. Cheng | 06-Sep-2016
L2PRD-CM-INSP-LLDS | R1 | Receiving Inspection of LCLS-II Production Cryomodule Assembly, Liquid He Level-DS (LLDS) | G. Cheng | 06-Sep-2016
L2PRD-CM-INSP-LLNDS | R1 | Receiving Inspection of LCLS-II Production Cryomodule Weldment Line Liquid Level DS (LLNDS) | G. Cheng | 07-Sep-2016
L2PRD-CM-INSP-LLNUS | R1 | Receiving Inspection of LCLS-II Production Cryomodule Weldment Line Liquid Level US (LLNUS) | G. Cheng | 06-Sep-2016
L2PRD-CM-INSP-LLUS | R1 | Receiving Inspection of LCLS-II Production Cryomodule Assembly, Liquid He Level-US (LLUS) | G. Cheng | 07-Sep-2016
L2PRD-CM-INSP-MCCLA | R1 | Receiving Inspection of LCLS-II Cryomodule MC Coupling Line Assembly (MCCLA) | G. Cheng | 27-Jun-2016
L2PRD-CM-INSP-PEC2P | R1 | Receiving Inspection of LCLS-II Production Cryomodule Weldment 2-Phase Pipe End Cap | G. Cheng | 06-Sep-2016
L2PRD-CM-INSP-UCM | R6 | LCLS-II Upper Cold Mass Incoming Inspection | Gary Cheng | 13-Mar-2018
L2PRD-CM-INSP-VV | R5 | Receiving Inspection of LCLS-II Production Cryomodule Vacuum Vessel | G. Cheng | 23-Oct-2017
L2PRD-CM-RECV | R1 | L2PRD General Inventory Traveler | M. McDonald | 06-Jan-2016
L2PRD-CM-RECV-BP2PH | R1 | L2PRD BeamPipe 2 Phase Inventory Traveler | V. Bookwalter | 01-Sep-2015
L2PRD-CM-RECV-C12P | R1 | L2PRD C12P Pressure Transducer Inventory Traveler | M. McDonald | 08-Jun-2016
L2PRD-CM-RECV-CDV | R1 | Cooldown Valve Inventory Receipt | M. McDonald | 11-Oct-2016
L2PRD-CM-RECV-DCXCU | R1 | L2PRD Diode CXCU Inventory Traveler | M. McDonald | 08-Feb-2016
L2PRD-CM-RECV-DCXSD | R1 | L2PRD Diode CXSD Inventory Traveler | M. McDonald | 08-Feb-2016
L2PRD-CM-RECV-DDTCU | R1 | L2PRD Diode DDTCU Inventory Traveler | M. McDonald | 08-Feb-2016
L2PRD-CM-RECV-DDTSD | R1 | L2PRD Diode DTSD Inventory Traveler | M. McDonald | 08-Feb-2016
L2PRD-CM-RECV-DK12P | R1 | Disk 2-Phase Support | M. McDonald | 13-Sep-2016
L2PRD-CM-RECV-DK22P | R1 | Disk 2-Phase Support | M. McDonald | 13-Sep-2016
L2PRD-CM-RECV-FT06P | R1 | L2PRD FT06P Inventory Traveler | M. McDonald | 31-May-2016
L2PRD-CM-RECV-HLS | R1 | L2PRD HLS Liquid Level Probes 12¿ (Helium Level Sensor) | M. McDonald | 14-Sep-2016
L2PRD-CM-RECV-IMAG | R1 | Assembly Magnetic Shield Cavity | M. McDonald | 13-Sep-2016
L2PRD-CM-RECV-IP75SD | R1 | L2PRD Ion Pump | M. McDonald | 19-Feb-2015
L2PRD-CM-RECV-IROD2L | R1 | Rod Invar 2-Phase Long | M. McDonald | 13-Sep-2016
L2PRD-CM-RECV-IROD2P | R1 | Rod Invar 2-Phase | M. McDonald | 13-Sep-2016
L2PRD-CM-RECV-JTV | R1 | JT Valve Inventory Receipt | M. McDonald | 11-Oct-2016
L2PRD-CM-RECV-JTVTK | R1 | Kit, JT Valve Tube | M. McDonald | 13-Sep-2016
L2PRD-CM-RECV-LLDS | R1 | Assembly, Liquid He Level - DS | M. McDonald | 13-Sep-2016
L2PRD-CM-RECV-LLNDS | R1 | Weldment Line Liquid Level - DS | M. McDonald | 13-Sep-2016
L2PRD-CM-RECV-LLNUS | R1 | Weldment Line Liquid Level - US | M. McDonald | 13-Sep-2016
L2PRD-CM-RECV-LLUS | R1 | Assembly, Liquid He Level - US | M. McDonald | 13-Sep-2016
L2PRD-CM-RECV-MCCLA | R1 | L2PRD LCLS-II MC Coupling Line Assembly Inventory Traveler | M. McDonald | 28-Jun-2016
L2PRD-CM-RECV-P2PH | R1 | L2PRD Pipe, 2-Phase Inventory Traveler | M. McDonald | 31-Aug-2016
L2PRD-CM-RECV-PEC2P | R1 | Weldment 2-Phase Pipe End Cap | M. McDonald | 13-Sep-2016
L2PRD-CM-RECV-TSCPLR | R1 | L2PRD Coupler Thermal Strap Inventory Traveler | M. McDonald | 30-Jan-2017
L2PRD-CM-RECV-TSHMSM | R1 | L2PRD HOM Thermal Strap Inventory Traveler | M. McDonald | 30-Jan-2017
L2PRD-CM-RECV-UCM | R1 | Upper Coldmass Inventory Traveler | M. McDonald | 13-Sep-2016
L2PRD-CM-RECV-VV | R1 | L2PRD Vacuum Vessel Inventory Traveler | M. McDonald | 13-Jul-2016
L2PRD-CST-ASSY | R4 | LCLS-II Production Cavity String Traveler | Danny forehand | 10-Sep-2018
L2PRD-CST-ASSY-BPM | R3 | BPM Magnet Sub-assembly Traveler | D. Forehand | 30-Mar-2018
L2PRD-CST-ASSY-LEAK | R1 | LCLS-II Cavity string leak test and transfer to phase 1 | D. Forehand | 27-Feb-2017
L2PRD-CST-INSP-BLBL | R1 | LCLS-II Cavity String Weldment Bellows PrCM Inspection Traveler | K. Wilson | 06-May-2016
L2PRD-CST-INSP-BLBP | R4 | LCLS-II Cavity String Weldment Bellows PrCM Inspection Traveler | K. Wilson | 15-Oct-2016
L2PRD-CST-INSP-BLBS | R4 | LCLS-II Cavity String Weldment Bellows Short Inspection Traveler | K. Wilson | 15-Oct-2016
L2PRD-CST-INSP-BLBU | R1 | LCLS-II Cavity String Weldment Upstream Bellows Inspection Traveler | K. Wilson | 07-Jul-2017
L2PRD-CST-INSP-BLXD | R3 | LCLS-II Cavity String Weldment Extension-DS Inspection Traveler | K. Wilson | 03-Nov-2016
L2PRD-CST-INSP-BLXU | R5 | LCLS-II Cavity String Weldment Extension-US Inspection Traveler | K. Wilson | 09-Nov-2016
L2PRD-CST-INSP-BPMFT | R2 | BPM Feedthrough Incoming Inspection Traveler | HK. Park | 10-Aug-2016
L2PRD-CST-INSP-CFL | R1 | 300K Current Leads CF Flange Inspection | T. Hiatt | 26-Aug-2016
L2PRD-CST-INSP-TUNMC | R3 | End Lever Tuner Mechanical Frame Inspection Traveler | N. Huque | 29-Aug-2016
L2PRD-CST-INSP-TUNMT | R2 | LCLS-II Tuner Stepper Motor Assembly Inspection Traveler | N. Huque | 03-Jan-2017
L2PRD-CST-INSP-TUNPZ | R2 | LCLS-II Tuner Piezo Actuator Assembly Inspection Traveler | N. Huque | 29-Aug-2016
L2PRD-CST-LEAK-AMGV | R1 | LCLS-II Cavity string gate valve leak test | D. Forehand | 03-May-2017
L2PRD-CST-MAG-QUAD | R1 | LCLS-II Production Quadrupole Magnet Detailed Inspection | T. Hiatt | 29-Aug-2016
L2PRD-CST-RECV | R1 | L2PRD General Inventory Traveler | M. McDonald | 06-Jan-2016
L2PRD-CST-RECV-AMGV | R1 | L2PRD All Metal Gate Valve | M. McDonald | 02-Nov-2015
L2PRD-CST-RECV-BLA | R1 | L2PRD Beam Line Absorber | M. Dickey | 12-Apr-2018
L2PRD-CST-RECV-BLACRM | R1 | L2PRD HOM Ceramic Beam Line Absorber | M. McDonald | 17-Feb-2017
L2PRD-CST-RECV-BLBP | R1 | L2PRD Beam Line Bellows Production | M. McDonald | 15-Apr-2016
L2PRD-CST-RECV-BLBS | R1 | L2PRD Beam Line Bellows Short | M. McDonald | 15-Apr-2016
L2PRD-CST-RECV-BLXD | R1 | L2PRD Beam Line Extension Downstream | M. McDonald | 15-Apr-2016
L2PRD-CST-RECV-BLXU | R1 | L2PRD Beam Line Extension Upstream | M. McDonald | 15-Apr-2016
L2PRD-CST-RECV-BPM | R1 | L2PRD BPM Inventory Traveler | M. McDonald | 06-Sep-2016
L2PRD-CST-RECV-BPMFT | R1 | L2PRD BPM FeedThru Inventory Traveler | M. McDonald | 02-Aug-2016
L2PRD-CST-RECV-CFL | R1 | L2PRD 300K Current Leads CF Flange Inventory Traveler | M. McDonald | 07-Sep-2016
L2PRD-CST-RECV-TUNMC | R1 | L2PRD End Lever Tuner Mechanical Frame Inventory Traveler | M. McDonald | 06-Sep-2016
L2PRD-CST-RECV-TUNMT | R1 | L2PRD End Lever Tuner Motor Inventory Traveler | M. McDonald | 06-Sep-2016
L2PRD-CST-RECV-TUNPZ | R1 | L2PRD End Lever Tuner Piezo Actuator Assembly Inventory Traveler | M. McDonald | 06-Sep-2016
L2PRD-CST-RINSP-BLBP | R1 | LCLS-II Cavity String Weldment Bellows PrCM Inspection Traveler | Katherine Wilson | 22-Mar-2019
L2PRD-CST-RINSP-BLBS | R1 | LCLS-II Cavity String Weldment Bellows Short Re-Inspection Traveler | Katherine Wilson | 22-Mar-2019
L2PRD-CST-RINSP-BLXD | R1 | LCLS-II Cavity String Weldment Extension-DS Inspection Traveler | Katherine Wilson | 22-Mar-2019
L2PRD-D3 | R1 | Detours, Deviations and Discrepancies (D3) | V. Bookwalter | 08-Jul-2013
L2PRD-INSR | R1 | Inspection Summary Report | G. DeKerlegand | 21-Mar-2016
L2PRD-NCR | R10 | Non-Conformance Report for Multiple Reworks | V. Bookwalter | 26-Feb-2018

## TECH REPS
System | JLab | EXPECTED 1ST DELIVERY? | VENDOR DOCUMENTATION | FNAL | SLAC
Dressed Cavities | John Vannekate/ Charlie Reece |  |  | Mattia Checchin / Chuck Grimm | Dan Gonnella
Feedthroughs | Liang |  |  | Mattia Checchin / Chuck Grimm | Dan Gonnella
Couplers | Naeem Huque |  |  | Ken Premo | Jeff Tice
(Nikolay Solyak – SME)
Cavity String Bellows and Spools | Matt Marchlik |  |  | Ken Premo / Andrei Lunin | Maniscalco
Cavity String Hardware and Seals | Mike Dickey |  |  | Damon Bice | Maniscalco
Magnet | Lakshmi Lalitha |  |  | John Amann | Tommy Hiatt
BPM | HyeKyoung Park |  |  | Andrei Lunin | Tommy Hiatt
Gate Valves | David Savransky |  |  | Damon Bice | Tommy Hiatt
2-Phase Pipe Components | Adam O’Brien |  |  | Chuck Grimm | Tommy Hiatt
End Lever Tuner | Peter Owen |  |  | Yuriy Pischalnikov | Maniscalco
Magnetic Shielding | Gary Cheng |  |  | Saravan Chandrasekaran / Yi Xie | Maniscalco
Cold Mass and Components | Gary Cheng |  |  | Ken Premo | Dan Gonnella
Vacuum Vessel and Components | Gary Cheng |  |  | Ken Premo | Dan Gonnella
Instrumentation | Larry King |  |  | Fred Lewis | Maniscalco
Cryogenic Valves | Justin Kent |  |  | Greg Johnson | Tommy Hiatt
Vacuum Equipment | Adam O’Brien |  |  | Ken Premo | Tommy Hiatt

## TIFFANY
Below is my understanding of the status of all the travelers we need in place now for the refurbishment cavities currently working towards a VTRF (CAV040, 295, and 331). The Pansophy team has the official tracking on the status of all the L2HE travelers and procedures so they can provide a better / corrected status update if needed.
Process Step | L2HE Traveler ID | Based on Traveler | L2HE Traveler Status | Comments
RF Inspection | L2HE-TUNE-CAV-RFIN |  | Issued | for as-received from vendor; use D3 for refurbishment cavities
CMM | L2HE-INSP-CAV |  | Issued | for as-received from vendor; use D3 for refurbishment cavities
Dual USC (Liquinox + DI) | L2HE-CHEM-CAV-USC | C100R-CAV-CHEM-USC | Draft needed based on C100R
2-pass HPR | L2HE-CHEM-CAV-HPR | C100R-CAV-CHEM-HPR | Draft needed based on C100R
First Assembly (FP, FPC, HOM) | L2HE-CLNRM-CAV-FRST | L2PRD-CAV-ASSY-FRST | Draft needed based on L2PRD
Second Assy | L2HE-CLNRM-CAV-SCND | L2PRD-CAV-ASSY-SCND | Draft needed based on L2PRD
Transfer to Test Stand | L2HE-CLNRM-CAV-TSTD and L2HE-CLNRM-CAV-TSTD-D5 | L2PRD-CAV-TRANS-TSTD and L2PRD-CAV-TRANS-TSTD-D5 | Draft needed based on L2PRD
Cooldown to 2K (including sensor install and checkout) | L2HE-VTA-CAV-COOL | L2PRD-CAV-VTA-COOL | Justin has draft; needs to be uploaded to DocuShare | L2PRD parameters need to be updated for L2HE
VTRF | L2HE-VTA-CAV-VTRF | L2PRD-CAV-VTRF | In Approvals | L2PRD parameters need to be updated for L2HE
HOM Survey | L2HE-VTA-CAV-HOM | L2PRD-CAV-VTA-HOM | Draft needed based on L2PRD
· Italicized L2HE Traveler IDs are traveler that do not currently exist and are my best guess at what the ID needs to be based on the current naming convention guidance.
Tiffany Ganey

## DELIVERIES
Component | FNAL | JLAB | SLAC | QTY | SOTR | Date for First Lot at JLAB
Niobium (Prototype) - existing cavities | NA | [5 empty] | L2HE-INV-*
Niobium (Production) | X | [5 empty] | AMGV
Cavities (Prototype) - existing cavities | NA |  |  |  | Ari Palczewski |  | FPCWG
Helium Vessels (Prototype) | X |  |  |  | Ari Palczewski |  | PIEZO
Cavities w/Helium Vessels -VTS Ready (Production) |  | X |  | 80 | Ari Palczewski | 2021-04-29
Cavity Feedthroughs |  | X |  |  | Ari Palczewski | 2020-11-02
Cavity Flanges & Assoc. Hardware/Seals (VTS & HTS compatible) |  | X |  |  |  |  | SNs From PRIMeS
Fundamental Power Coupler (FPC) |  |  | X |  |  | 2021-05-28 | AMGV*
Cavity String Interconnecting Bellows |  | X |  |  | Matt Marchlick | 2021-04-19 | AV15
Cavity String Assembly Hardware & Seals | X |  |  |  | Mike Dickey |  | C12P
SC Magnet Assembly | X |  |  |  | Lakshmi Latitha | 2021-02-12 | CAV
Beam Position Monitor (BPM) | X |  |  |  | HyeKyoung Park | 2021-02-22 | CDV
Gate Valves |  | X |  |  | David Savransky | 2021-04-09 | CFL
Beamline Vac. Monitoring Manifold & Gauge | X | [5 empty] | FPCWG*
Two-phase Pipe Bellows | X |  |  |  | Gary Cheng ? |  | FPFT
Tuner, actuator, piezos (Prototype) | X |  |  |  | Peter Owen | 2021-07-19 | FT06P
Tuner , actuator, piezos (Production) |  | X |  |  | Peter Owen |  | HMFT
Magnetic Shielding | X |  |  | 10 | Gary Cheng | 2021-08-27 | IP75SD
GRHP Sub-assembly | X | [5 empty] | JTV
Vacuum Vessel | X |  |  | 10 | Gary Cheng | 2021-03-23 | TSCPLR
Coupler Pumping Lines & Pumps (ion+TSP) + vacuum gauges | X | [5 empty] | TSHMSM
Instrumentation | X |  |  |  | Larry King
Liquid Level Probes & JT Valve | X
Beamline Interconnect Parts including Aluminum Heat Shields | X
HOM Absorber |  | X |  |  |  | 2021-01-12
Shipping Frames & End Caps + Shock Log Devices |  | X
X = Lead Lab (to be confrimed)
BLAs (will JLAB be required to inspect & Process these ? ) |  |  |  |  | ??? | 2021-04-28
Cyrogenic Valves |  |  |  |  | Naeem Huque
Vacuum Equipment |  |  |  |  | Gary Cheng
JT & Cool Down Valves |  |  |  |  | ?? | 2021-04-20

## MILESTONES
Major Processes for HE | Start date
Cavity Prep & Test | 2020-11-17 | 2021-09-01
String Assembly | 2021-07-27 | 2021-12-01
CM Assembly | 2021-05-15 | 2022-02-01
Testing | 2022-05-17 | 2021-10-01

## TRAVELERSold (hidden)
Traveler Name | Traveler ID (SEPARATE BY WORKCENTERS) | Procedure(s), Name (if known) OR Yes/No | Drawing(s), Name (if known) OR Yes/No | SOP/TOSP/OSP/THA | Revision | Author | Reviewer | Project Manager | SOTR | Due | D3 ?? (USERNAME) | NCR Dispositioners (USERNAME) | NCR Informative (USERNAME) | Traveler (Holdpoint) Closer (USERNAME) | Notes
Receiving Travelers
Cavity
Helium Vessel Receiving Traveler | SNSPPU-CAV-RECV-HELV |  |  |  | R1
Cavity String
Bellows Receiving Traveler | SNSPPU-CST-RECV-(bellows) |  |  |  | R1
Gate Valves Receiving Traveler | SNSPPU-CST-RECV-(gate valve) |  |  |  | R1
FPC Receiving Traveler | SNSPPU-CST-RECV-FPC |  |  |  | R1
Cryomodule
Diode CXCU Inventory Traveler | SNSPPU-CM-RECV-DCXCU |  |  |  | R1 | M. Dickey | C. Barnes | E. Daly | P. Owen | 2020-01-02 |  | powen,king,edaly,kwilson,mdickey,areilly
Disassembly Travelers
Cavity
Cavity String
Cryomodule
Leak Check Travelers
Cavity
Cavity String
Bellows Leak Check Traveler | SNSPPU-CST-LEAK-(bellows) |  |  |  | R1
Gate Valves Leak Check Traveler | SNSPPU-CST-LEAK-(gate valves) |  |  |  | R1
FPC Leak Check Traveler | SNSPPU-CST-LEAK-FPC |  |  |  | R1
Cryomodule
Inspection Travelers
Cavity
Visual and CMM Inspection of Cavity | SNSPPU-CAV-INSP-CAV |  | 104211800-M8U-8200-A00X |  | R1 |  |  |  | K. Wilson | 2020-02-01
Visual/CMM Inspection of Helium Vessel | SNSPPU-CAV-INSP-HELV | TI CLEANING | 104211700-M8U-8200-A026 |  | R1 |  |  |  | K. Wilson | 2020-02-01
Receiving Inspection Cavity RF | SNSPPU-CAV-RFIN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
TUNER FRAME / STEPPER MOTORS / HARMONIC DRIVE |  | SS CLEANING
Cavity String
Receiving Inspection Bellows | SNSPPU-CST-INSP-(bellows) |  |  |  | R1 |  |  |  | K. Wilson | 2020-05-01
SNS FPC Visual Inspection | SNSPPU-CST-INSP-FPC |  | 104211600-M8U-8200-A00X |  | R1 |  |  |  | K. Wilson | 2019-12-01
Cryomodule
Space Frame Visual and Dimensional Inspection | SNSPPU-CM-INSP-SFR | SS CLEANING | 104210900-M8U-8200-A001 |  | R1 |  |  |  | M. Marchlik | 2020-10-01
Vacuum Vessel Visual Inspection | SNSPPU-CM-INSP-VV | LEAK CHECK; SS CLEANING | 104210800-M8U-8200-A001 |  | R1 |  |  |  | M. Marchlik | 2020-07-01
SNS Return End Can Visual/CMM Inspection | SNSPPU-CM-INSP-RENC |  | 104210700-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-11-01
SNS Supply End Can Visual/CMM Inspection | SNSPPU-CM-INSP-SENC |  | 104210600-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-06-01
SNS Outer Magnetic Shield Visual Inspection | SNSPPU-CM-INSP-OMAG |  | 104211000-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-05-01
SNS Inner Magnetic Shield Visual Inspection | SNSPPU-CM-INSP-IMAG |  | 104211200-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-05-01
SNS Thermal Shield Visual/CMM Inspection | SNSPPU-CM-INSP-THRM | HIGH SENSITIVITY LEAK CHECK | 104211100-M8U-8200-A002 104211100-M8U-8200-A014 104211100-M8U-8200-A025 |  | R1 |  |  |  | M. Marchlik | 2020-08-01
Chemistry Travelers
Cavity
Cavity High Pressure Rinse (New HPR) Traveler | SNSPPU-CAV-CHEM-HPRN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Components Cleaning Traveler | SNSPPU-CAV-CHEM-CLN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Ultra Sonic Clean Traveler | SNSPPU-CAV-CHEM-USC |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
CMM Workcenter ?
IS there a cav RFIN traveler?
Furnace Workcenter ? | changed CHEM to PROC
Bakeout before RF processing | SNSPPU-CAV-PROC-BAKE |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Cavity Heat Treatment | SNSPPU-CAV-PROC-HEAT |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Processing Travelers
Cavity
Cavity RF Tuning | SNSPPU-CAV-TUNE |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
IS there a cav RFIN traveler? |  |  |  |  | R1
Cavity String
Cryomodule
RF Processing (FPC RF Processing) | SNSPPU-CM-CST-FPC-HPRF |  |  |  | R1 |  |  |  | K. Wilson
Assembly Travelers
Cavity
SNS Helium Vessel Installation Traveler | SNSPPU-CAV-ASSY-HELV |  | 104211700-M8U-8200-A026 |  | R1 |  |  |  |  | 2020-02-01
High Beta Cavity Assembly for VTA testing | SNSPPU-CAV-ASSY (look at old SNS) |  | 104211800-M8U-8200-A00X |  | R1 |  |  |  |  | 2020-02-01
transfer to test stand
Cavity String
SNS High Beta Cavity String Traveler | SNSPPU-CST-ASSY |  |  |  | R1 |  |  |  |  | 2020-07-01
Cryomodule
Cryomodule Assembly | SNSPPU-CM-ASSY |  |  |  | R1 |  |  |  | M. Marchlik | 2020-12-01
Cold Mass Assembly | SNSPPU-CM-ASSY-CMAS |  |  |  | R1 |  |  |  |  | 2020-08-01
Cryomodule Thermal Shield-Spaceframe Assembly Traveler | SNSPPU-CM-ASSY-THRM |  | 104211100-M8U-8200-A002 104211100-M8U-8200-A014 104211100-M8U-8200-A025 |  | R1 |  |  |  | M. Marchlik
SNS High Beta Cryomodule Vacuum Vessel-End Can Assembly Traveler | SNSPPU-CM-ASSY-VV |  | 104210800-M8U-8200-A001 |  | R1
cm assy ship (rf, instrumentation)
Testing Travelers
Vertical Cavity Testing | SNSPPU-CAV-VTRF |  |  |  | R1 |  |  |  |  | 2020-04-01
Cavity VTA Cooldown | SNSPPU-CAV-VTA-COOL |  |  |  | R1 |  |  |  |  | 2020-02-01
Installation/Shipping Travelers
SNS Cryomodule Shipping | SNSPPU-CM-ASSY-SHIP |  |  |  | R1 |  |  |  |  | 2020-05-01
Standard Project Travelers
Detours, Deviations and Discrepancies (D3) | SNSPPU-D3 |  |  |  | R2 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A
Inspection Summary Report | SNSPPU-INSR |  |  |  | R1 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A
Inspection Nonconformance Report | SNSPPU-NCR |  |  |  | R10 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A