## Slide 1: C50R
Color Legend |  | Count | Percent
CP | Complete (CP) | 81 | 100.00%
NR | New Revision Out for Approval (NR) | 0 | 0.00%
OA | Out for Approval (OA) | 0 | 0.00%
30 | Due in 30 Days | 0 | 0.00%
15 | Due in 15 Days | 0 | 0.00%
OD | Overdue | 0 | 0.00%
 | Remaining | 0 | 0.00%
 | Total Traveler IDs | 81 | 
Out for Approval/New Revision
NONE
Approaching Overdue
None
Overdue
NONE
Please Submit any changes or questions to pansophy@jlab.org
Note:
Project Masterlist can be found in the project docushare folder
Traveler Acronym list can be found in Pansophy, under the User Tools > Traveler Tools drop downs

## Slide 2
Out for Approval |  |  |  |  |  |  |  |  | 
Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author | Reviewer | Reviewer | Proj Manager | SOTR
Overdue |  |  |  |  |  |  |  |  | 
Approaching Due Date |  |  |  |  |  |  |  |  | 
C50R Traveler Listing

## Slide 3: C75
Color Legend |  | Count | Percent
CP | Complete (CP) | 138 | 95.83%
NR | New Revision Out for Approval (NR) | 0 | 0.00%
OA | Out for Approval (OA) | 2 | 1.39%
30 | Due in 30 Days | 0 | 0.00%
15 | Due in 15 Days | 0 | 0.00%
OD | Overdue | 2 | 1.39%
 | Remaining | 2 | 1.39%
 | Total Traveler IDs | 144 | 
Out for Approval/New Revision
C75-CMA-SUBP-ASSY1*
C75-CMA-SUBP-ASSY2*
Approaching Overdue
NONE
Overdue
“Beam line assembly procedure”
SRF-MSPR-CMA-JTV-CAL
Please Submit any changes or questions to pansophy@jlab.org
Note:
Project Masterlist can be found in the project docushare folder
Traveler Acronym list can be found in Pansophy, under the User Tools > Traveler Tools drop downs
*C75-CMA-SUBP-ASSY1 and 2 are approved and being uploaded to pansophy.

## Slide 4
Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author | Reviewer | Reviewer | Proj Manager | SOTR | Cost Account Manager
Out for Approval |  |  |  |  |  |  |  |  |  | 
Supply end can beam pipe assembly | C75-CMA-SUBP-ASSY1 | R1 | 8/15/21 |  | C. Wilcox | J. Fischer | J. Campbell | A. Reilly |  | 
Supply end can pump drop assembly | C75-CMA-SUBP-ASSY2 | R1 | 8/15/21 |  |  | J. Fischer |  | A. Reilly |  | 
Overdue |  |  |  |  |  |  |  |  |  | 
Beam line assembly procedure |  |  | 8/15/21 |  | C. Wilcox | J. Fischer |  |  |  | 
JT calibration procedure | SRF-MSPR-CMA-JTV-CAL |  | 8/15/21 |  | J. Campbell | J. Fischer |  |  |  | 
Approaching Due Date |  |  |  |  |  |  |  |  |  | 
C75 Traveler Listing