## Slide 1: L2HE
Color Legend |  | Count | Percent
CP | Complete (CP) | 98 | 91.59%
NR | New Revision Out for Approval (NR) | 0 | 0.00%
OA | Out for Approval (OA) | 3 | 2.80%
30 | Due in 30 Days | 0 | 0.00%
15 | Due in 15 Days | 0 | 0.00%
OD | Overdue | 0 | 0.00%
R0 | R0 Draft | 4 | 3.74%
 | Remaining | 2 | 1.87%
 | Total Traveler IDs | 107 | 
Please Submit any changes or questions to pansophy@jlab.org
Note:
Project Masterlist can be found in the project docushare folder
Traveler Acronym list can be found in Pansophy, under the User Tools > Traveler Tools drop downs
Due to the large number of R0 travelers, the normal list cannot fit on this page. Please reference the subsequent pages for the traveler names

## Slide 2
Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author | Reviewer | Reviewer | Proj Manager | SOTR
Out for Approval |  |  |  |  |  |  |  |  | 
LCLSII-HE LERF Prep & Cooldown* | L2HE-LERF-CM-PREP | R1 |  |  | M. Weaks | M. Drury | L. King | J. Hogan | N. Huque
Cavity HOM Measurements and Tuning* | L2HE-CMA-HOM-TUNE | R1 | 3/1/22 | 4/1/22 | P. Owen | D. Forehand | D. Forehand | J. Hogan | 
LCLSII-HE BPM Housing Leak Testing Traveler* | L2HE-CMA-BPM-LEAK | R1 |  |  | M. Oast | L. Zhao | K. Wilson | J. Hogan | 
L2HE Traveler Listing
*The L2HE-LERF-CM-PREP, L2HE-CMA-HOM-TUNE, and L2HE-CMA-BPM-LEAK travelers have been approved and are in the queue to be uploaded to pansophy.

## Slide 3
Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author | Reviewer | Reviewer | Proj Manager | SOTR
Overdue |  |  |  |  |  |  |  |  | 
Due in 15 Days |  |  |  |  |  |  |  |  | 
L2HE Traveler Listing Cont

## Slide 4
Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author | Reviewer | Reviewer | Proj Manager | SOTR
R0 |  |  |  |  |  |  |  |  | 
CM Assembly Second | L2HE-CMA-CM-ASSY2 | R1 | 10/26/21 |  | J. Fischer | N. Huque | A. Reilly | J. Hogan | 
CM Assembly Final | L2HE-CMA-CM-ASSYF | R1 | 10/26/21 |  | J. Fischer | N. Huque | A. Reilly | J. Hogan | 
Cryomodule Prep and Shipping to SLAC | L2HE-CMA-CM-SHIP | R1 | 10/26/21 |  | J. Fischer | N. Huque | A. Reilly | J. Hogan | 
Cryomodule Vacuum Vessel Assembly | L2HE-CMA-VV-ASSY | R1 | 10/26/21 |  | J. Fischer | G. Cheng | A. Reilly | J. Hogan | 
L2HE Traveler Listing Cont Cont