## Slide 1: L2HE
Color Legend |  | Count | Percent
CP | Complete (CP) | 101 | 90.99%
NR | New Revision Out for Approval (NR) | 3 | 2.70%
OA | Out for Approval (OA) | 1 | 0.90%
30 | Due in 30 Days | 0 | 0.00%
15 | Due in 15 Days | 0 | 0.00%
OD | Overdue | 0 | 0.00%
R0 | R0 Draft | 4 | 3.60%
 | Remaining | 2 | 1.80%
 | Total Traveler IDs | 111 | 
Please Submit any changes or questions to pansophy@jlab.org
Note:
Project Masterlist can be found in the project docushare folder
Traveler Acronym list can be found in Pansophy, under the User Tools > Traveler Tools drop downs
Due to the large number of R0 travelers, the normal list cannot fit on this page. Please reference the subsequent pages for the traveler names

## Slide 2
Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author | Reviewer | Reviewer | Proj Manager | SOTR
Out for Approval |  |  |  |  |  |  |  |  | 
FPC COLD PART | L2HE-CLNRM-FPCC-INSP | R4 | 5/24/21 | 5/15/20 | N. Huque | D. Forehand | K. Davis | J. Hogan | N. Huque
FPC COLD PART PROCEDURE | L2HE-PR-INSP-FPCC | R4 | 5/13/22 |  | N. Huque | D. Forehand | K. Davis | C. Dreyfuss | A. Grabowski
LCLSII-HE BPM Housing Leak Testing Traveler | L2HE-CMA-BPM-LEAK | R2 | 5/12/22 |  | M. Oast | C. Wilcox | K. Wilson | J. Hogan | 
Establish Purge in L2HE String | L2HE-PR-CLNRM-CST-PURGE | R1 | 5/13/22 |  | T. Ganey | P. Owen | D. Forehand | J. Hogan | 
L2HE Traveler Listing

## Slide 3
Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author | Reviewer | Reviewer | Proj Manager | SOTR
Overdue |  |  |  |  |  |  |  |  | 
Due in 15 Days |  |  |  |  |  |  |  |  | 
L2HE Traveler Listing Cont

## Slide 4
Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author | Reviewer | Reviewer | Proj Manager | SOTR
R0 |  |  |  |  |  |  |  |  | 
CM Assembly Second | L2HE-CMA-CM-ASSY2 | R1 | 10/26/21 |  | J. Fischer | N. Huque | A. Reilly | J. Hogan | 
CM Assembly Final | L2HE-CMA-CM-ASSYF | R1 | 10/26/21 |  | J. Fischer | N. Huque | A. Reilly | J. Hogan | 
Cryomodule Prep and Shipping to SLAC | L2HE-CMA-CM-SHIP | R1 | 10/26/21 |  | J. Fischer | N. Huque | A. Reilly | J. Hogan | 
Cryomodule Vacuum Vessel Assembly | L2HE-CMA-VV-ASSY | R1 | 10/26/21 |  | J. Fischer | G. Cheng | A. Reilly | J. Hogan | 
L2HE Traveler Listing Cont Cont