## Slide 1: C75
Color Legend |  | Count | Percent
CP | Complete (CP) | 142 | 96.60%
NR | New Revision Out for Approval (NR) | 2 | 1.36%
OA | Out for Approval (OA) | 1 | 0.68%
30 | Due in 30 Days | 0 | 0.00%
15 | Due in 15 Days | 0 | 0.00%
OD | Overdue | 2 | 1.36%
 | Remaining | 2 | 1.36%
 | Total Traveler IDs | 147 | 
Out for Approval/New Revision
C75-CLNRM-GV40-LEAK-ASSY-R1
C75-CLNRM-ENDD-ASSY-R2
C75-CPR-ASSY-TOVR-R3*
*C75-CPR-ASSY-TOVR-R3 has been approved and is in the queue for upload.
Approaching Overdue
NONE
Overdue
“Beam line assembly procedure”
SRF-MSPR-CMA-JTV-CAL
Please Submit any changes or questions to pansophy@jlab.org
Note:
Project Masterlist can be found in the project docushare folder
Traveler Acronym list can be found in Pansophy, under the User Tools > Traveler Tools drop downs

## Slide 2
Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author | Reviewer | Reviewer | Proj Manager | SOTR | Cost Account Manager
Out for Approval |  |  |  |  |  |  |  |  |  | 
Cavity Gate Valve Leak Check and Assembly to EndDish | C75-CLNRM-GV40-LEAK-ASSY | R1 |  |  | C Dreyfuss | D. Forehand |  | K. Davis |  | 
End Dish and MDC valve sub-assembly | C75-CLNRM-ENDD-ASSY | R2 | 9/5/20 |  | C. Dreyfus | G. Ciovati |  | K. Davis |  | 
Pair Assembly Preparation for Turnover | C75-CPR-ASSY-TOVR | R3 |  |  | C. Dreyfuss | D. Forehand |  | K. Davis |  | 
Overdue |  |  |  |  |  |  |  |  |  | 
Beam line assembly procedure |  |  | 8/15/21 |  | C. Wilcox | J. Fischer |  |  |  | 
JT calibration procedure | SRF-MSPR-CMA-JTV-CAL |  | 8/15/21 |  | J. Campbell | J. Fischer |  |  |  | 
Approaching Due Date |  |  |  |  |  |  |  |  |  | 
C75 Traveler Listing