## Slide 1: C100R
Color Legend |  | Count | Percent
CP | Complete (CP) | 49 | 98.00%
NR | New Revision Out for Approval (NR) | 0 | 0.00%
OA | Out for Approval (OA) | 0 | 0.00%
30 | Due in 30 Days | 0 | 0.00%
15 | Due in 15 Days | 0 | 0.00%
OD | Overdue | 1 | 2.00%
 | Remaining | 0 | 0.00%
 | Total Traveler IDs | 50 | 
Out for Approval/New Revision
NONE
Approaching Overdue
NONE
Overdue
C100R-CM-ASSY-BPIP-R1
Please Submit any changes or questions to pansophy@jlab.org
Note:
Project Masterlist can be found in the project docushare folder
Traveler Acronym list can be found in Pansophy, under the User Tools > Traveler Tools drop downs
C100R-FURN-WINW-BRAZ-R1 has been approved and is in the queue for upload to pansophy.

## Slide 2
Out for Approval |  |  |  |  |  |  |  |  |  | 
Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author | SME | Production Lead | Proj Manager | Tech Rep | Cost Account Manager
Overdue |  |  |  |  |  |  |  |  |  | 
C100R Cryomodule Beampipe Assembly | C100R-CM-ASSY-BPIP | R1 | 9/1/21 |  | J. Fischer |  |  |  |  | 
Approaching Due Date |  |  |  |  |  |  |  |  |  | 
C100R Traveler Listing