## report-2
Status Report for C100R-INSP-WIN on 18-Aug-22
TRAV_SEQ_NUM | WINSN | WBASN | DSRFSN | PRE_COMM | WELD_NAME | WELD_DATE | ASSY_VIS_PASS | ASSY_LEAK_TECHNAME | ASSY_LEAK_PASS | ASSY_LEAK_FILE | WELD_COMM | ASSY_RF_SMPL | ASSY_RF_TECH | ASSY_RF_DATE | ASSY_RF_FILE | ASSY_RF_PASS | RF_COMM | ASSY_FLEAK_TECH | ASSY_FLEAK_DATE | ASSY_FLEAK_PASS | ASSY_FLEAK_FILE | LEAK_COMM | ASSY_READY | ASSY_COMM
1 | ASSEM0035-190 | JL104 | FLG0037-278 |  | Austin | 2021-05-07 | Yes | Prosper | Yes | 1FE1EDEB-DF40-3402-B50B0D2C61FCDE53
2 | ASSEM0035-194 | JL109 | FLG0037-276 |  | Austin | 2021-05-07 | Yes | Prosper | Yes | 1FF5B91F-F45A-3D71-8AA40C05C9919B7C
3 | ASSEM0035-193 | JL111 | FLG0037-280Â Â Â Â Â Â Â Â Â Â Â Â |  | Austin | 2021-05-07 | Yes | Prosper | Yes | 20242483-07F7-EA88-EAF32114FE9C0441
4 | ASSEM0035-192 | JL100 | FLG0037-279 |  | Austin | 2021-05-07 | Yes | Prosper | Yes
5 | ASSEM0035-191 | JL107 | FLG0037-275 |  | Austin | 2021-05-07 | Yes | Prosper | Yes | 204F1753-0783-28B3-41CD7C8604119499
6 |  | JL107 | FLG0037-275 |  | Austin | 2021-05-07 | Yes | Prosper | Yes
7 | ASSEM0035-195 | JL102 | FLG0037-277 |  | Austin | 2021-05-07 | Yes | Prosper | Yes | 20129EC0-D774-4FD0-A272137859806252
8 | ASSEM0035-196 | JL110 | FLG0037-240 |  | Austin | 2021-05-07 | Yes | Prosper | Yes | [8 empty] | PROSPER | 2021-09-14 | Yes | 1F816145-C4F1-89D0-AC2DF32A17215751
9 |  | JL114 | FLG0037-238 |  | Austin | 2021-05-07 | Yes | Prosper | Yes
10 | ASSEM0035-198 | JL108 | FLG0037-241 |  | Austin | 2021-05-07 | Yes | Prosper | Yes | 1FB0FD71-A50D-2487-FBBC2F30CFC65865
11 | ASSEM0035-199 | JL106 | FLG0037-239 |  | Austin | 2021-05-07 | Yes | Prosper | Yes | 1F9F1A83-F334-C104-374B9B2F12242054
12 | ASSEM0035-197 | JLAB-69 |  | DSRFSN = FLG0037-253 was not in the drop-down window at time of initiating traveler. | Austin | 2021-05-07 | Yes | Prosper | Yes | 1FCA18FB-F2F2-C143-F0FF17A2F1320705
13 |  |  | FLG0037-275 | [17 empty] | E72E500A-CA42-5B7D-61F3B477B9A49314
14 |  | JL105 |  | FRAME NUMBER- FLG0037-252 Not is dropdown | mmorgan | 2022-02-10 | Yes |  | Yes
15 |  | JL112 |  | FLG0037-250 Not in dropdown | mmorgan | 2022-02-10 | Yes
16 |  | JL120 |  | FLG0037-251 Not in dropdown | mmorgan | 2022-02-10 | Yes
17 |  | JL116 |  | FLG0037-248 Not in dropdown | mmorgan | 2022-02-10 | Yes
18 |  | JL118 |  | FLG0037-249 | MMORGAN | 2022-02-10 | Yes
19 |  | JL117 |  | FLG0037-246 | mmorgan | 2022-02-10 | Yes
20 |  | JL119 |  | FLG0037-247 | mmorgan | 2022-02-10 | Yes
21 |  | JL101 | FLG0037-242 |  | mmorgan | 2022-02-10 | Yes
22 |  | JLAB-78 | FLG0037-244 |  | mmorgan | 2022-02-10 | Yes
23 |  | JL103 | FLG0037-243 |  | mmorgan | 2022-02-10 | Yes