## report-1
Status Report for C100R-FURN-WINW-BRAZ on 18-Aug-22
TRAV_SEQ_NUM | DATACAPTURETECH | WINWSN | CERAMICPO | METALIZATIONPO | EYELETBATCHNO | DATACAPTUREDATE | DATACAPTURECOMM | PARTSCLEANED | DATECLEANINGSTATUS | CLEANSTATUSCOMM | VISINSPTECH | VISINSPDATE | VISINSPTCOMM | FITTESTTECH | FITTESTDATE | FITTESTCOMM | BRAZEFOILEYEASSYTECH | BRAZEFOILEYEASSYDATE | BRAZEEYEASSYCOMM | CEREYEASSYTECH | DATE_CEREYEASSEMBLY2 | CEREYEASSYCOMM | BRAZERUNTECH | BRAZERUNDATE | BRAZERUNCOMM | PROFILEDATATECH | CEBRZSN | FURNACEUSED | PROGRAMNAMELITTLEBLUE | PROGRAMPROFILENOBIGBLUE | PROFILEFILETEMP | QUANTITYOFPARTSRAN | PROFILEDATADATE | PROFILEDATACOMM | LEAKTESTTECH | LEAKTESTPASSED | RECOINTECH | RECOINDATE | CEREYEPARTSCLEANED | CEREYECLEANINGTECH | CEREYECLEANDATE | SUBASSYREADYTECH | SUBASSYREADYDATE | FRAMESERIALTECH | DSRFSN | REWORKEDFLANGE | FRAMESERIALDATE | SETUPTECH | SETUPDATE | FINALSETUPTECH | FINALSETUPDATE | FINALBRAZETECH | FINALBRAZEDATE | FINALBRAZECOMM | PROFILEDATAFINAL | FURNACEUSEDFINAL | LITTLEBLUEPROGRAMNAMEFINAL | BIGBLUEPROGRAMPROFILENAMEFINAL | TEMPERATUREPROFILEFILEFINAL | QUANTITYOFPARTSRANFINAL | PROFILEDATADATEFINAL | PROFILEDATACOMMFINAL | LEAKTESTTECHFINAL | LEAKTESTDATEFINAL | LEAKTESTFILEFINAL | PASSEDLEAKTESTFINAL | LEAKTESTCOMMFINAL | CLEANUPBLASTINGTECH | CLEANUPBLASTINGDATE | CLEANUPBLASTINGCOMM | UHVCLEANINGCHEMTECH | UHVCLEANINGDATE | UHVCLEANINGCOMM | RFTESTINGTECH | RFTESTINGDATE | RFTESTINGFILE | PASSEDRFTESTING | FINALLEAKTESTTECH | FINALLEAKTESTDATE | FINALLEAKTESTFILE | PASSEDFINALLEAKTEST | FINALLEAKTESTCOMM | LAPPINGTECH | LAPPINGDATE | LAPPINGCOMM | INSPTECH | INSPDATE | INSPCOMM | UHVCLEANINGCHEMTECHFINAL | UHVCLEANINGDATEFINAL | UHVCLEANINGCOMMFINAL | CERAMICEYELETBRAZEMENTSN
1 | GROSE | JL-121 | 22-M0756-0 | 407522 | 82020 | 2022-06-15 | JL-121 051722-01 | Yes | 2022-05-16 |  | GROSE | 2022-06-15 |  | GROSE | 2022-05-16 |  | GROSE | 2022-05-16 |  | GROSE | 2022-05-16 |  | GROSE | 2022-05-17 |  | GROSE |  | Big Blue |  | 1 |  | 5 | 2022-05-17 |  | PROSPER | Yes | GROSE | 2022-06-07 | Yes | TMHARRIS | 2022-06-06 | GROSE | 2022-06-07 |  |  |  |  | GROSE | 2022-06-07 | GROSE | 2022-06-07 | GROSE | 2022-06-07 |  | GROSE | Big Blue | 0 |  |  | 5 | 2022-06-07 |  | PROSPER | 2022-06-13 |  | Yes |  | GROSE | 2022-06-14 |  | TMHARRIS | 2022-06-15 | [19 empty] | 051722-01
2 | GROSE | JL-122 | 22-M0756-0 | 407522 | 82020 | 2022-07-28 | JL-122 051722-02 | Yes | 2022-05-16 |  | GROSE | 2022-05-15 |  | GROSE | 2022-05-16 |  | GROSE | 2022-05-16 |  | GROSE | 2022-05-16 |  | GROSE | 2022-05-17 |  | GROSE |  | Big Blue |  | 1 |  | 5 | 2022-05-17 |  | PROSPER | Yes | GROSE | 2022-06-10 | Yes | TMHARRIS | 2022-06-06 | GROSE | 2022-06-07 |  |  |  |  | GROSE | 2022-06-07 | GROSE | 2022-06-07 | GROSE | 2022-06-07 |  | GROSE | Big Blue |  |  |  | 5 | 2022-06-07 |  | PROSPER | 2022-06-13 |  | Yes |  | GROSE | 2022-06-14 |  | TMHARRIS | 2022-06-15 | [19 empty] | 051722-02
3 | GROSE | JL-123 | 22-M0756-0 | 407522 | 82020 | 2022-07-28 | JL-123 051722-03 | Yes | 2022-05-16 |  | GROSE | 2022-05-16 |  | GROSE | 2022-05-16 |  | GROSE | 2022-05-16 |  | GROSE | 2022-05-16 |  | GROSE | 2022-05-17 |  | GROSE |  | Big Blue |  | 1 |  | 5 | 2022-05-17 |  | PROSPER | Yes | GROSE | 2022-06-10 | Yes | TMHARRIS | 2022-06-06 | GROSE | 2022-06-07 | GROSE |  |  |  | GROSE | 2022-06-07 | GROSE | 2022-06-07 | GROSE | 2022-06-07 |  | GROSE | Big Blue |  |  |  | 5 | 2022-06-07 |  | PROSPER | 2022-07-12 |  | Yes |  | GROSE | 2022-07-12 |  | TMHARRIS | 2022-07-13 | [19 empty] | 051722-03
4 | GROSE | JL-124 | 22-M0756-0 | 407522 | 82020 | 2022-07-28 | JL-124 051722-05 | Yes | 2022-05-16 |  | GROSE | 2022-05-16 |  | GROSE | 2022-05-16 |  | GROSE | 2022-05-16 |  | GROSE | 2022-05-16 |  | GROSE | 2022-05-17 |  | GROSE |  | Big Blue |  | 1 |  | 5 | 2022-05-17 |  | PROSPER | Yes | GROSE | 2022-06-10 | Yes | TMHARRIS | 2022-06-06 | GROSE | 2022-06-07 | GROSE |  |  |  | GROSE | 2022-06-07 | GROSE | 2022-06-07 | GROSE | 2022-06-07 |  | GROSE | Big Blue |  |  |  | 5 | 2022-06-07 |  | PROSPER | 2022-06-14 |  | Yes |  | GROSE | 2022-07-12 |  | TMHARRIS | 2022-07-13 | [19 empty] | 051722-05
5 |  | JL-125 | 22-M0756-0 | 407522 | 21122 | 2022-05-25 | 052522-01 | Yes | 2022-05-25 |  | GROSE | 2022-05-25 |  | GROSE | 2022-05-25 |  | GROSE | 2022-05-25 |  | GROSE | 2022-05-25 |  | GROSE | 2022-05-25 |  | GROSE |  | Big Blue |  | 1 |  | 7 | 2022-05-25 |  | PROSPER | Yes | GROSE | 2022-06-07 | Yes | TMHARRIS | 2022-06-06 | GROSE | 2022-06-07 |  |  |  |  | GROSE | 2022-06-07 | GROSE | 2022-06-07 | GROSE | 2022-06-07 |  | GROSE | Big Blue |  | 1 |  | 7 | 2022-06-07 |  | PROSPER | 2022-06-13 | B392BDC6-F84D-2284-294B6F10BFD9BB9C | Yes |  | GROSE | 2022-06-14 |  | TMHARRIS | 2022-06-15 | [19 empty] | 052522-01
6 |  | JL-126 | 22-M0756-0 | 407522 | 21122 | 2022-05-25 | 052522-02 | Yes | 2022-05-25 |  | GROSE | 2022-05-25 |  | GROSE | 2022-05-25 |  | GROSE | 2022-05-25 |  | GROSE | 2022-05-25 |  | GROSE | 2022-05-25 |  | GROSE |  | Big Blue |  | 1 |  | 7 | 2022-05-25 |  | PROSPER | Yes | GROSE | 2022-06-10 | Yes | TMHARRIS | 2022-06-06 | GROSE | 2022-06-07 |  |  |  |  | GROSE | 2022-06-10 | GROSE | 2022-06-10 | GROSE | 2022-06-10 |  | GROSE | Big Blue |  | 1 |  | 7 | 2022-06-10 |  | PROSPER | 2022-06-13 |  | Yes |  | GROSE | 2022-06-14 |  | TMHARRIS | 2022-06-15
7 | GROSE | JL-127 | 22-M0756-0 | 407522 | 21122 | 2022-05-25 | 052522-03 | Yes | 2022-05-25 |  | GROSE | 2022-05-25 |  | GROSE | 2022-05-25 |  | GROSE | 2022-05-25 |  | GROSE | 2022-05-25 |  | GROSE | 2022-05-25 |  | GROSE |  | Big Blue |  | 1 |  | 7 | 2022-05-25 |  | PROSPER | Yes | GROSE | 2022-06-07 | Yes | TMHARRIS | 2022-06-06 | GROSE | 2022-06-07 |  |  |  |  | GROSE | 2022-06-07 | GROSE | 2022-06-07 | GROSE | 2022-06-07 |  | GROSE | Big Blue |  | 1 | E3433A4E-0EA6-3E88-67DFD97B9280F668 | 7 | 2022-06-07 |  | PROSPER | 2022-06-10 | E34E6A50-CB0F-B3A3-E13B58FE69ED35BA | Yes |  | GROSE | 2022-07-12 |  | TMHARRIS | 2022-06-15
8 | GROSE | JL-128 | 22-M0756-0 | 407522 | 21122 | 2022-05-25 | 052522-04 | Yes | 2022-05-25 |  | GROSE | 2022-05-25 |  | GROSE | 2022-05-25 |  | GROSE | 2022-05-25 |  | GROSE | 2022-05-25 |  | GROSE | 2022-05-25 |  | GROSE |  | Big Blue |  | 1 |  | 7 | 2022-05-25 |  | PROSPER | Yes | GROSE | 2022-06-07 | Yes | TMHARRIS | 2022-06-06 | GROSE | 2022-06-07 |  |  |  |  | GROSE | 2022-06-07 | GROSE | 2022-06-07 | GROSE | 2022-06-07 |  | GROSE | Big Blue |  | 1 |  | 7 | 2022-06-07 |  | PROSPER | 2022-06-10 | E379B1B2-F215-D1C8-54DA070BC14CAA97 | Yes |  | GROSE | 2022-07-12 |  | TMHARRIS | 2022-07-13
9 |  | JL-129 | 22-M0756-0 | 407522 | 21122 | 2022-05-25 | 052522-05 | Yes | 2022-05-25 |  | GROSE | 2022-05-25 |  | GROSE | 2022-05-25 |  | GROSE | 2022-05-25 |  | GROSE | 2022-05-25 |  | GROSE | 2022-05-25 |  | GROSE |  | Big Blue |  | 1 |  | 7 | 2022-05-25 |  | PROSPER | Yes | GROSE | 2022-06-07 | Yes | TMHARRIS | 2022-06-06 | GROSE | 2022-06-07 |  |  | No |  | GROSE | 2022-06-07 | GROSE | 2022-06-07 | GROSE | 2022-06-07 |  | GROSE | Big Blue |  | 1 |  |  | 2022-06-07 |  | PROSPER | 2022-06-10 | E38CE7F9-BEEE-F3DA-596B46A6763EB247 | Yes |  | GROSE | 2022-07-12 |  | TMHARRIS | 2022-07-13
10 | GROSE | JL-130 | 22-M0756-0 | 407522 | 21122 | 2022-05-25 | 052522-06 | Yes | 2022-05-25 |  | GROSE | 2022-05-25 |  | GROSE | 2022-05-25 |  | GROSE | 2022-05-25 |  | GROSE | 2022-05-25 |  | GROSE | 2022-05-25 |  | GROSE |  | Big Blue |  | 1 |  | 7 | 2022-05-25 |  | PROSPER | Yes | GROSE | 2022-05-31 | Yes | TMHARRIS | 2022-06-06 | GROSE | 2022-06-10 |  |  |  |  | GROSE | 2022-06-10 | GROSE | 2022-06-10 | GROSE | 2022-06-10 |  | GROSE | Big Blue |  | 1 |  | 7 | 2022-06-10 |  | PROSPER | 2022-07-12 | E3A3EE59-CFA9-1365-FD9771D716944304 | Yes |  | GROSE | 2022-07-14 |  | TMHARRIS | 2022-07-15
11 | GROSE | JL-131 | 22-M0756-0 | 407522 | 21122 | 2022-05-25 | 052522-07 | Yes | 2022-05-25 |  | GROSE | 2022-05-25 |  | GROSE | 2022-05-25 |  | GROSE | 2022-05-25 |  | GROSE | 2022-05-25 |  | GROSE | 2022-05-25 |  | GROSE |  | Big Blue |  | 1 |  | 7 | 2022-05-25 |  | PROSPER | Yes | GROSE | 2022-06-10 | Yes | TMHARRIS | 2022-06-06 | GROSE | 2022-06-10 |  |  |  |  | GROSE | 2022-06-10 | GROSE | 2022-06-10 | GROSE | 2022-06-10 |  | GROSE | Big Blue |  | 1 |  | 7 | 2022-06-10 |  | PROSPER | 2022-06-13 | E3BFE522-F87B-4395-5E9D56443FA28F9E | Yes |  | GROSE | 2022-06-14 |  | TMHARRIS | 2022-06-15
12 | GROSE | JL-132 | 22-M0756-0 | 407522 | 82020 | 2022-06-14 | 061422-01 | Yes | 2022-06-14 |  | GROSE | 2022-06-14 |  | GROSE | 2022-06-14 |  | GROSE | 2022-06-14 |  | GROSE | 2022-06-14 |  | GROSE | 2022-06-14 |  | GROSE |  | Big Blue |  | 1 |  | 7 | 2022-06-14 |  | PROSPER | Yes | GROSE | 2022-07-20 | Yes | TMHARRIS | 2022-07-15 | GROSE | 2022-07-20 |  |  |  |  | GROSE | 2022-07-20 | GROSE | 2022-07-20 | GROSE | 2022-07-20 |  | GROSE | Big Blue |  | 1 |  | 7 | 2022-07-20 |  | PROSPER | 2022-07-25 | E3D6924B-F28C-F032-728CEF0743E1880B | Yes |  | GROSE | 2022-07-25 |  | TMHARRIS | 2022-07-26
13 | GROSE | JL-133 | 22-M0756-0 | 407522 | 82020 | 2022-06-14 | 061422-02 | Yes | 2022-06-14 |  | GROSE | 2022-06-14 |  | GROSE | 2022-06-14 |  | GROSE | 2022-06-14 |  | GROSE | 2022-06-14 |  | GROSE | 2022-06-14 |  | GROSE |  | Big Blue |  | 1 |  | 7 | 2022-06-14 |  | PROSPER | Yes | GROSE | 2022-07-20 | Yes | TMHARRIS | 2022-07-15 | GROSE | 2022-07-20 |  |  |  |  | GROSE | 2022-07-20 | GROSE | 2022-07-20 | GROSE | 2022-07-20 |  | GROSE | Big Blue |  | 1 |  | 7 | 2022-07-20 |  | PROSPER | 2022-07-25 | E3EFECFD-EC84-F153-371467E358E2C8C4 | Yes |  | GROSE | 2022-07-25 |  | TMHARRIS | 2022-07-26
14 | GROSE | JL-134 | 22-M0756-0 | 407522 | 82020 | 2022-06-14 | 061422-03 | Yes | 2022-06-14 |  | GROSE | 2022-06-14 |  | GROSE | 2022-06-14 |  | GROSE | 2022-06-14 |  | GROSE | 2022-06-14 |  | GROSE | 2022-06-14 |  | GROSE |  | Big Blue |  | 1 |  | 7 | 2022-06-14 |  | PROSPER | Yes | GROSE | 2022-07-20 | Yes | TMHARRIS | 2022-07-15 | GROSE | 2022-07-20 |  |  |  |  | GROSE | 2022-07-20 | GROSE | 2022-07-20 | GROSE | 2022-07-20 |  | GROSE | Big Blue |  | 1 |  | 7 | 2022-07-20 |  | PROSPER | 2022-07-25 | E408842A-D4B7-D8D1-E64F154E86C6DEBE | Yes |  | GROSE | 2022-07-25 |  | TMHARRIS | 2022-07-26
15 | GROSE | JL-135 | 22-M0756-0 | 407522 | 82020 | 2022-06-14 | 061422-04 | Yes | 2022-06-14 |  | GROSE | 2022-06-14 |  | GROSE | 2022-06-14 |  | GROSE | 2022-06-14 |  | GROSE | 2022-06-14 |  | GROSE | 2022-06-14 |  | GROSE |  | Big Blue |  | 1 |  | 7 | 2022-06-14 |  | PROSPER | Yes | GROSE | 2022-07-20 | Yes | TMHARRIS | 2022-07-15 | GROSE | 2022-07-20 |  |  |  |  | GROSE | 2022-07-20 | GROSE | 2022-07-20 | GROSE | 2022-07-20 |  | GROSE | Big Blue |  | 1 |  | 7 | 2022-07-20 |  | PROSPER | 2022-07-25 | E5FC9C59-DD81-EC8D-DFA2DFFB1EBD2012 | Yes |  | GROSE | 2022-07-25 |  | TMHARRIS | 2022-07-26
16 | GROSE | JL-136 | 22-M0756-0 | 407522 | 82020 | 2022-06-14 | 061422-05 | Yes | 2022-06-14 |  | GROSE | 2022-06-14 |  | GROSE | 2022-06-14 |  | GROSE | 2022-06-14 |  | GROSE | 2022-06-14 |  | GROSE | 2022-06-14 |  | GROSE |  | Big Blue |  | 1 |  | 7 | 2022-06-14 |  | PROSPER | Yes | GROSE | 2022-07-20 | Yes | TMHARRIS | 2022-07-15 | GROSE | 2022-07-20 |  |  |  |  | GROSE | 2022-07-20 | GROSE | 2022-07-20 | GROSE | 2022-07-20 |  | GROSE | Big Blue |  | 1 |  | 7 | 2022-07-20 |  | PROSPER | 2022-07-21 | E61EC32D-EBF4-3565-29F28BB2B146EF0C | Yes |  | GROSE | 2022-07-23 |  | TMHARRIS | 2022-07-26
17 | GROSE | JL-137 | 22-M0756-0 | 407522 | 82020 | 2022-06-14 | 061422-06 | Yes | 2022-06-14 |  | GROSE | 2022-06-14 |  | GROSE | 2022-06-14 |  | GROSE | 2022-06-14 |  | GROSE | 2022-06-14 |  | GROSE | 2022-06-14 |  | GROSE |  | Big Blue |  | 1 |  | 7 | 2022-06-14 |  | PROSPER | Yes | GROSE | 2022-07-20 | Yes | TMHARRIS | 2022-07-15 | GROSE | 2022-07-20 |  |  |  |  | GROSE | 2022-07-20 | GROSE | 2022-07-20 | GROSE | 2022-07-20 |  | GROSE | Big Blue |  | 1 |  | 7 | 2022-07-20 |  | PROSPER | 2022-07-21 | E63C338F-B189-E5EB-7694385714C0180F | Yes |  | GROSE | 2022-07-23 |  | TMHARRIS | 2022-07-26
18 | GROSE | JL-138 | 22-M0756-0 | 407522 | 82020 | 2022-06-14 | 061422-07 | Yes | 2022-06-14 |  | GROSE | 2022-06-14 |  | GROSE | 2022-06-14 |  | GROSE | 2022-06-14 |  | GROSE | 2022-06-14 |  | GROSE | 2022-06-14 |  | GROSE |  | Big Blue |  | 1 |  | 7 | 2022-06-14 |  | PROSPER | Yes | GROSE | 2022-07-20 | Yes | TMHARRIS | 2022-07-15 | GROSE | 2022-07-20 |  |  |  |  | GROSE | 2022-07-20 | GROSE | 2022-07-20 | GROSE | 2022-07-20 |  | GROSE | Big Blue |  | 1 |  | 7 | 2022-07-20 |  | PROSPER | 2022-07-21 | E654DE43-AB65-A605-A19DD043D4B141E1 | Yes |  | GROSE | 2022-07-23 |  | TMHARRIS | 2022-07-26
19 | GROSE | JL-139 | 22-M0756-0 | 407522 | 82020 | 2022-06-22 | 062222-01 | Yes | 2022-06-22 |  | GROSE | 2022-06-22 |  | GROSE | 2022-06-22 |  | GROSE | 2022-06-22 |  | GROSE | 2022-06-22 |  | GROSE | 2022-06-22 |  | GROSE |  | Big Blue |  | 1 |  | 7 | 2022-06-22 |  | PROSPER | Yes | GROSE | 2022-07-27 | Yes | TMHARRIS | 2022-07-26 | GROSE | 2022-07-27 |  |  |  |  | GROSE | 2022-07-27 | GROSE | 2022-07-27 | GROSE | 2022-07-27 |  | GROSE | Big Blue |  | 1 |  | 7 | 2022-07-27 |  | PROSPER | 2022-08-01 | 175F5FEF-E2E9-1079-883870E3F07A8C71 | Yes |  | GROSE | 2022-08-01 |  | TMHARRIS | 2022-08-02
20 | GROSE | JL-140 | 22-M0756-0 | 407522 | 82020 | 2022-06-22 | 062222-02 | Yes | 2022-06-22 |  | GROSE | 2022-06-22 |  | GROSE | 2022-06-22 |  | GROSE | 2022-06-22 |  | GROSE | 2022-06-22 |  | GROSE | 2022-06-22 |  | GROSE |  | Big Blue |  | 1 |  | 7 | 2022-06-22 |  | PROSPER | Yes | GROSE | 2022-07-27 | Yes | TMHARRIS | 2022-07-26 | GROSE | 2022-07-27 |  |  |  |  | GROSE | 2022-07-27 | GROSE | 2022-07-27 | GROSE | 2022-07-27 |  | GROSE | Big Blue |  | 1 |  | 7 | 2022-07-27 |  | PROSPER | 2022-08-01 | 1790AB8D-088E-8667-4C4616026394B550 | Yes |  | GROSE | 2022-08-01 |  | TMHARRIS | 2022-08-02
21 | GROSE | JL-141 | 22-M0756-0 | 407522 | 82020 | 2022-06-22 | 062222-03 | Yes | 2022-06-22 |  | GROSE | 2022-06-22 |  | GROSE | 2022-06-22 |  | GROSE | 2022-06-22 |  | GROSE | 2022-06-22 |  | GROSE | 2022-06-22 |  | GROSE |  | Big Blue |  | 1 |  | 7 | 2022-06-22 |  | PROSPER | Yes | GROSE | 2022-07-27 | Yes | TMHARRIS | 2022-07-26 | GROSE | 2022-07-27 |  |  |  |  | GROSE | 2022-07-27 | GROSE | 2022-07-27 | GROSE | 2022-07-27 |  | GROSE | Big Blue |  | 1 |  | 7 | 2022-07-27 |  | PROSPER | 2022-08-01 | 1A993A90-9BEB-1CEA-2AD13DD5C3EA00B1 | Yes |  | GROSE | 2022-08-01 |  | TMHARRIS | 2022-08-02
22 | GROSE | JL-142 | 22-M0756-0 | 407522 | 82020 | 2022-06-22 | 062222-04 | Yes | 2022-06-22 |  | GROSE | 2022-06-22 |  | GROSE | 2022-06-22 |  | GROSE | 2022-06-22 |  | GROSE | 2022-06-22 |  | GROSE | 2022-06-22 |  | GROSE |  | Big Blue |  | 1 |  | 7 | 2022-06-22 |  | PROSPER | Yes | GROSE | 2022-07-27 | Yes | TMHARRIS | 2022-07-26 | GROSE | 2022-07-27 |  |  |  |  | GCIOVATI | 2022-07-27 | GROSE | 2022-07-27 | GROSE | 2022-07-27 |  | GROSE | Big Blue |  | 1 |  | 7 | 2022-07-27 |  | PROSPER | 2022-08-01 | 1AAEABF5-AFB4-5918-CC7EDA3FAD7CE6CD | Yes |  | GROSE | 2022-08-01 |  | TMHARRIS | 2022-08-02
23 | GROSE | JL-143 | 22-M0756-0 | 407522 | 82020 | 2022-06-22 | 062222-05 | Yes | 2022-06-22 |  | GROSE | 2022-06-22 |  | GROSE | 2022-06-22 |  | GROSE | 2022-06-22 |  | GROSE | 2022-06-22 |  | GROSE | 2022-06-22 |  | GROSE |  | Big Blue |  | 1 |  | 7 | 2022-06-22 |  | PROSPER | Yes | GROSE | 2022-07-27 | Yes | TMHARRIS | 2022-07-26 | GROSE | 2022-07-27 |  |  |  |  | GROSE | 2022-07-27 | GROSE | 2022-07-27 | GROSE | 2022-07-27 |  | GROSE | Big Blue |  | 1 |  | 7 | 2022-07-27 |  | PROSPER | 2022-08-01 | 1AC7C418-057C-2223-2DB980B76C9AE050 | Yes |  | GROSE | 2022-08-01 |  | TMHARRIS | 2022-08-02
24 | GROSE | JL-144 | 22-M0756-0 | 407522 | 82020 | 2022-06-22 | 062222-06 | Yes | 2022-06-22 |  | GROSE | 2022-06-22 |  | GROSE | 2022-06-22 |  | GROSE | 2022-06-22 |  | GROSE | 2022-06-22 |  | GROSE | 2022-06-22 |  | GROSE |  | Big Blue |  | 1 |  | 7 | 2022-06-22 |  | PROSPER | Yes | GROSE | 2022-07-27 | Yes | TMHARRIS | 2022-07-26 | GROSE | 2022-07-27 |  |  |  |  | GROSE | 2022-07-27 | GROSE | 2022-07-27 | GROSE | 2022-07-27 |  | GROSE | Big Blue |  | 1 |  | 7 | 2022-07-27 |  | PROSPER | 2022-08-01 | 1CE1C328-B591-7E02-AAF09E6D75ECC6FB | Yes |  | GROSE | 2022-08-01 |  | TMHARRIS | 2022-08-02
25 | GROSE | JL-145 | 22-M0756-0 | 407522 | 82020 | 2022-06-22 | 062222-07 | Yes | 2022-06-22 |  | GROSE | 2022-06-22 |  | GROSE | 2022-06-22 |  | GROSE | 2022-06-22 |  | GROSE | 2022-06-22 |  | GROSE | 2022-06-22 |  | GROSE |  | Big Blue |  | 1 |  | 7 | 2022-06-22 |  | PROSPER | Yes | GROSE | 2022-07-27 | Yes | TMHARRIS | 2022-07-26 | GROSE | 2022-07-27 |  |  |  |  | GROSE | 2022-07-27 | GROSE | 2022-07-27 | GCIOVATI | 2022-07-27 |  | GROSE | Big Blue |  | 1 |  | 7 | 2022-07-27 |  | PROSPER | 2022-08-01 | 1CFEDF42-E0AF-7243-B32B4B31E49961D1 | Yes |  | GROSE | 2022-08-01 |  | TMHARRIS | 2022-08-02
26 | [64 empty] | 1D1A8EC2-E98A-1371-4CBA841BFD253CF2 | Yes
27 | [64 empty] | 49BE8137-937E-4B0E-BF6130F6492C69FF | Yes
28 | [64 empty] | 49D18657-D1C5-F27C-F3FF620CFEC04EC3 | Yes