## report
Status Report for C100R-INSP-ADPT on 18-Aug-22
TRAV_SEQ_NUM | TECHNICIANNAME | DATETIME | CONTAINERDAMAGED | CONTAINERPICS | SHIPDOCOK | SHIPDOCDETAIL | WBASN | VISUALCLEAN | VISUALCERAMIC | VISUALPICS | VISUALCOMMENT | SWEEPPASS | DIM_WIDTH | DIM_LENGTH | DIM_THK | DIM_RADIUS1 | DIM_RADIUS2 | DIM_RADIUS3 | DIM_RADIUS4 | DIM_WIDTHPASSED | DIM_LENGTHPASSED | DIM_THKPASSED | DIM_RADIUS1PASSED | DIM_RADIUS2PASSED | DIM_RADIUS3PASSED | DIM_RADIUS4PASSED | DIM_OPENING_1 | DIM_OPENING_2 | DIM_OPENING_3 | DIM_OPENING_1PASSED | DIM_OPENING_2PASSED | DIM_OPENING_3PASSED | DIM_CERTHK_1 | DIM_CERTHK_2 | DIM_CERTHK_3 | DIM_CERTHK_1PASSED | DIM_CERTHK_2PASSED | DIM_CER_THK_2 | INITIALLEAKTECHNAME | INITIALLEAKPASS | INITIALLEAKFILE | RF_TECHNAME | RF1_TIME | UPLOADRF_FILE | RF_TESTCOMMENT | FINALLEAKTECHNAME | FINALLEAKTIME | FINALLEAKPASS | FINALLEAKFILE | SHIPIONTECHNAME | SHIPIONDATE | TITECHNAME | TIDATE | TICONTAINEROK | TIVISPASS | TICOMMENT | TI_RF_SMPL | TI_ILEAK_TECH | TI_ILEAK_DATE | TI_ILEAK_PASS | TI_RF_TECH | TI_RF_DATE | TI_RF_FILE | TI_RF_PASS | TI_FLEAK_TECH | TI_FLEAK_DATE | TI_FLEAK_PASS | SHIP_ANTI | SHIP_ANTI_DATE | TIO2_TECH_NAME | TIO2_DATE | TIO2_CONTAINEROK | TIO2_VISPASS | TIO2_COMMENT | TIO2_RF_SMPL | TIO2_ILEAKTECH | TIO2_ILEAKDATE | TIO2_ILEAKPASS | TIO2_RF_TECH | TIO2_RF_DATE | TIO2_RF_FILE | TIO2_RF_PASS | TIO2_FLEAKTECH | TIO2_FLEAKDATE | TIO2_FLEAKPASS | TIO2_FLEAKFILE | WELD_READY
1 | GEORGED | 2020-11-09 | No |  |  | Plastic container okay. NOTE - Step 5 dimensional check radius measurements skipped as per Scott Williams. Go/noGo Fit up check was done in place of measurements. Fit up was done with double-sided flange (FLG0037-279). | JL100 | Yes | Yes |  | Visual okay. | Yes | 1.719 | 5.532 | 0.624 |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0.987 | 0.983 | 0.987 | Yes | Yes | Yes | 0.095 | 0.095 | 0.095 | Yes | Yes | Yes | PROSPER | Yes | 99CB7E42-B9AD-3F8F-074E9635B79C6F1D | LPAGE | 2020-10-08 |  | Eyelet tested 126'C at 12kW | PROSPER | 2021-02-10 | Yes | DFE4E973-D0B9-6B93-EAE3CBED7CF8071E | [7 empty] | Yes |  |  |  | LPAGE | 2020-12-10 |  | Yes
2 | GEORGED | 2020-11-10 | No |  |  | Plastic container okay. NOTE - Step 5 dimensional check radius measurements skipped as per Scott Williams. Go/noGo Fit up check was done in place of measurements. Fit up was done with double-sided flange (FLG0037-279). | JL101 | Yes | Yes |  | Visual okay. | Yes | 1.718 | 5.534 | 0.627 |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0.99 | 0.988 | 0.989 | Yes | Yes | Yes | 0.095 | 0.095 | 0.095 | Yes | Yes | Yes | PROSPER | Yes | 99E0D4B8-AC68-281F-09CACA8AED86D690 | LPAGE | 2020-10-10 |  | Eyelet tested 126'C at 12kW | [11 empty] | Yes |  |  |  | LPAGE | 2020-12-16 |  | Yes
3 | GEORGED | 2020-11-10 | No |  |  | Plastic container okay. NOTE - Step 5 dimensional check radius measurements skipped as per Scott Williams. Go/noGo Fit up check was done in place of measurements. Fit up was done with double-sided flange (FLG0037-279). | JL102 | Yes | Yes |  | Okay. | Yes | 1.718 | 5.534 | 0.625 |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0.99 | 0.99 | 0.988 | Yes | Yes | Yes | 0.095 | 0.095 | 0.095 | Yes | Yes | Yes | PROSPER | Yes | 99EFEE10-C034-6E89-AA78A44D05B5C3C8 | LPAGE | 2020-10-09 |  | Eyelet tested 126'C at 12kW | PROSPER | 2021-01-11 | Yes | E02F9BB5-EF55-330C-49D6E9459F5EE41D | [7 empty] | Yes |  |  |  | LPAGE | 2020-12-11 |  | Yes
4 | GEORGED | 2020-11-10 | No |  |  | Plastic container okay. NOTE - Step 5 dimensional check radius measurements skipped as per Scott Williams. Go/noGo Fit up check was done in place of measurements. Fit up was done with double-sided flange (FLG0037-279). | JL103 | Yes | Yes |  | OK. | Yes | 1.718 | 5.534 | 0.625 |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0.99 | 0.988 | 0.988 | Yes | Yes | Yes | 0.095 | 0.095 | 0.095 | Yes | Yes | Yes | PROSPER | Yes | 9A24C725-B238-B81C-AB703BB426F82FF7 | LPAGE | 2020-10-07 |  | Eyelet tested 130'C at 12kW | PROSPER | 2020-08-31 | Yes | 1FE24A8E-E821-C75B-38AC54ADC79887B3 | [7 empty] | Yes |  |  |  | LPAGE | 2020-12-14 |  | Yes
5 | GEORGED | 2020-11-10 | No |  |  | Plastic container okay. NOTE - Step 5 dimensional check radius measurements skipped as per Scott Williams. Go/noGo Fit up check was done in place of measurements. Fit up was done with double-sided flange (FLG0037-279). | JL104 | Yes | Yes |  | Ok. | Yes | 1.718 | 5.534 | 0.624 |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0.987 | 0.988 | 0.988 | Yes | Yes | Yes | 0.095 | 0.095 | 0.095 | Yes | Yes | Yes | PROSPER | Yes | 9A3316C7-B872-BFE4-8528B0D942758C62 | LPAGE | 2020-10-07 |  | Eyelet tested 129'C at 12kW | PROSPER | 2021-01-11 | Yes | E03EB55A-994A-54BB-8612BF3493F4E7D1 | [7 empty] | Yes |  |  |  | LPAGE | 2020-12-14 |  | Yes
6 | GEORGED | 2020-11-10 | No |  |  | Plastic container okay. NOTE - Step 5 dimensional check radius measurements skipped as per Scott Williams. Go/noGo Fit up check was done in place of measurements. Fit up was done with double-sided flange (FLG0037-279). | JL105 | Yes | Yes |  | Okay. | Yes | 1.718 | 5.533 | 0.625 |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0.99 | 0.991 | 0.99 | Yes | Yes | Yes | 0.095 | 0.095 | 0.095 | Yes | Yes | Yes | PROSPER | Yes | 9B528A49-9505-00E1-DAC2D3128E8CB32F | LPAGE | 2020-10-07 |  | Eyelet tested 128'C at 12kW | PROSPER | 2020-12-21 | Yes | 133E5D1F-A210-65C6-15C5D442DE4ADB74 | [11 empty] | LPAGE | 2020-12-16 |  | Yes
7 | GEORGED | 2020-11-10 | No |  |  | Plastic container okay. NOTE - Step 5 dimensional check radius measurements skipped as per Scott Williams. Go/noGo Fit up check was done in place of measurements. Fit up was done with double-sided flange (FLG0037-279). | JL106 | Yes | Yes |  | Okay. | Yes | 1.718 | 5.533 | 0.622 |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0.988 | 0.989 | 0.99 | Yes | Yes | Yes | 0.095 | 0.095 | 0.095 | Yes | Yes | Yes | PROSPER | Yes | 9B6FF214-C666-9FE6-0A91B1D6A30E6D90 | LPAGE | 2020-10-09 |  | Eyelet tested 133'C at 12kW | PROSPER | 2020-12-21 | Yes | 13306628-F8E3-318B-79C495BC3DF12615 | [11 empty] | LPAGE | 2020-12-16 |  | Yes
8 | GEORGED | 2020-11-10 | No |  |  | Plastic container okay. NOTE - Step 5 dimensional check radius measurements skipped as per Scott Williams. Go/noGo Fit up check was done in place of measurements. Fit up was done with double-sided flange (FLG0037-279). | JL107 | Yes | Yes |  | Okay. | Yes | 1.719 | 5.533 | 0.624 |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0.99 | 0.99 | 0.991 | Yes | Yes | Yes | 0.095 | 0.095 | 0.095 | Yes | Yes | Yes | PROSPER | Yes | 9B8A05D9-B6D1-4CFA-AB2F8F24B02EF78C | LPAGE | 2020-10-08 |  | Eyelet tested 131'C at 12kW | PROSPER | 2020-12-21 | Yes | 131FC4EA-9594-C72D-6005B8312F259447 | [7 empty] | Yes |  |  |  | LPAGE | 2020-12-17 |  | Yes
9 | GEORGED | 2020-11-11 | No |  |  | Plastic container okay. NOTE - Step 5 dimensional check radius measurements skipped as per Scott Williams. Go/noGo Fit up check was done in place of measurements. Fit up was done with double-sided flange (FLG0037-279). | JL108 | Yes | Yes |  | Ok | Yes | 1.719 | 5.533 | 0.625 |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0.988 | 0.988 | 0.989 | Yes | Yes | Yes | 0.095 | 0.095 | 0.095 | Yes | Yes | Yes | PROSPER | Yes | 9B9994E7-F198-5210-9CDA1D5FC18077E2 | LPAGE | 2020-10-09 |  | Eyelet tested 125'C at 12kW | PROSPER | 2020-12-18 | Yes | 13076447-BF05-AB82-FEA2BF03A1E20A20 | [7 empty] | Yes |  |  |  | LPAGE | 2020-12-17 |  | Yes
10 | GEORGED | 2020-11-11 | No |  |  | Plastic container okay. NOTE - Step 5 dimensional check radius measurements skipped as per Scott Williams. Go/noGo Fit up check was done in place of measurements. Fit up was done with double-sided flange (FLG0037-279). | JLAB-69 | Yes | Yes |  | Okay. Note - weld spatter on face of flange. | Yes | 1.718 | 5.532 | 0.626 |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0.988 | 0.989 | 0.99 | Yes | Yes | Yes | 0.095 | 0.095 | 0.095 | Yes | Yes | Yes |  |  |  | LPAGE | 2020-10-06 |  | Eyelet tested 134'C at 12kW | PROSPER | 2021-01-07 | Yes | B24B9DAD-0F4B-4A6A-64A7D905503F104C | [7 empty] | Yes |  |  |  | LPAGE | 2021-01-06 |  | Yes
11 | GEORGED | 2020-11-11 | No |  |  | Plastic container okay. NOTE - Step 5 dimensional check radius measurements skipped as per Scott Williams. Go/noGo Fit up check was done in place of measurements. Fit up was done with double-sided flange (FLG0037-279). | JL109 | Yes | Yes |  | Ok | Yes | 1.718 | 5.534 | 0.625 |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0.989 | 0.988 | 0.99 | Yes | Yes | Yes | 0.095 | 0.096 | 0.095 | Yes | Yes | Yes | PROSPER | Yes | 9BAB1FE6-969C-0B46-90E8CBFC2E910714 | LPAGE | 2020-10-14 |  | Eyelet tested 127'C at 12kW | PROSPER | 2021-01-06 | Yes | 7C96FAC3-C251-DD04-C0F5F1BC41E877E0 | [7 empty] | Yes |  |  |  | LPAGE | 2020-12-17 |  | Yes
12 | GEORGED | 2020-11-11 | No |  |  | Plastic container okay. NOTE - Step 5 dimensional check radius measurements skipped as per Scott Williams. Go/noGo Fit up check was done in place of measurements. Fit up was done with double-sided flange (FLG0037-279). | JL110 | Yes | Yes |  | Ok | Yes | 1.718 | 5.534 | 0.625 |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0.988 | 0.988 | 0.988 | Yes | Yes | Yes | 0.095 | 0.095 | 0.095 | Yes | Yes | Yes | PROSPER | Yes | 9BB972B2-A4E7-3A47-84E768256A744A88 | LPAGE | 2020-10-14 |  | Eyelet tested 125'C at 12kW | PROSPER | 2021-01-06 | Yes | 7CA3156F-CAB7-CA6D-11F3952504B2F83E | [7 empty] | Yes |  |  |  | LPAGE | 2020-12-18 |  | Yes
13 | GEORGED | 2020-11-11 | No |  |  | Plastic container okay. NOTE - Step 5 dimensional check radius measurements skipped as per Scott Williams. Go/noGo Fit up check was done in place of measurements. Fit up was done with double-sided flange (FLG0037-279). | JL111 | Yes | Yes |  | Ok | Yes | 1.717 | 5.533 | 0.624 |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0.988 | 0.989 | 0.989 | Yes | Yes | Yes | 0.095 | 0.096 | 0.095 | Yes | Yes | Yes | PROSPER | Yes | 9BEDE788-E8E0-A9D9-2BF9F5A5F28B213F | LPAGE | 2020-10-15 |  | Eyelet tested 131'C at 12kW | PROSPER | 2021-01-06 | Yes | 7CAEC385-017C-B30D-E10D48D8D983406C | [7 empty] | Yes |  |  |  | LPAGE | 2020-12-18 |  | Yes
14 | GEORGED | 2020-11-11 | No |  |  | Plastic container okay. NOTE - Step 5 dimensional check radius measurements skipped as per Scott Williams. Go/noGo Fit up check was done in place of measurements. Fit up was done with double-sided flange (FLG0037-279). | JL112 | Yes | Yes |  | Ok. | Yes | 1.717 | 5.533 | 0.625 |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0.99 | 0.99 | 0.99 | Yes | Yes | Yes | 0.095 | 0.096 | 0.096 | Yes | Yes | Yes | PROSPER | Yes | 9C1F1FF7-F33B-9E6A-3358D10D31715406 | LPAGE | 2020-10-15 |  | Eyelet tested 129'C at 12kW | PROSPER | 2021-01-06 | Yes | 7CBBBEFD-FB52-C181-6E8819037783F249 | [7 empty] | Yes |  |  |  | LPAGE | 2020-12-21 |  | Yes
15 | GEORGED | 2020-11-11 | No |  |  | Plastic container okay. NOTE - Step 5 dimensional check radius measurements skipped as per Scott Williams. Go/noGo Fit up check was done in place of measurements. Fit up was done with double-sided flange (FLG0037-279). | JL113 | Yes | Yes |  | Ok. | Yes | 1.718 | 5.533 | 0.624 |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0.989 | 0.988 | 0.99 | Yes | Yes | Yes | 0.095 | 0.095 | 0.096 | Yes | Yes | Yes | PROSPER | Yes | 9C3F846F-ED01-2420-C916721EC2172372 | LPAGE | 2020-10-15 |  | Eyelet tested 129'C at 12kW | PROSPER | 2021-01-06 | Yes | 7CCC0770-9765-83C0-1A1F0EDDDDDBA9B9 | [7 empty] | Yes |  |  |  | LPAGE | 2020-12-21 |  | Yes
16 | GEORGED | 2020-11-11 | No |  |  | Plastic container okay. NOTE - Step 5 dimensional check radius measurements skipped as per Scott Williams. Go/noGo Fit up check was done in place of measurements. Fit up was done with double-sided flange (FLG0037-279). | JL114 | Yes | Yes |  | Ok | Yes | 1.718 | 5.533 | 0.624 |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0.99 | 0.988 | 0.989 | Yes | Yes | Yes | 0.096 | 0.096 | 0.096 | Yes | Yes | Yes |  |  |  | LPAGE | 2020-10-16 |  | Eyelet tested 129'C at 12kW | PROSPER | 2021-01-07 | Yes | B1CDE6CD-AD5C-B5C4-DF0F5161B54D67B1 | [7 empty] | Yes |  |  |  | LPAGE | 2020-12-21 |  | Yes
17 | GEORGED | 2020-11-11 | No |  |  | Plastic container okay. NOTE - Step 5 dimensional check radius measurements skipped as per Scott Williams. Go/noGo Fit up check was done in place of measurements. Fit up was done with double-sided flange (FLG0037-279). | JL115 | Yes | Yes |  | Ok | Yes | 1.718 | 5.533 | 0.624 |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0.988 | 0.99 | 0.99 | Yes | Yes | Yes | 0.095 | 0.096 | 0.096 | Yes | Yes | Yes |  |  |  | LPAGE | 2020-10-19 |  | Eyelet tested 132'C at 12kW | PROSPER | 2021-01-07 | Yes | B1DD7933-9743-0512-2C04735C6113EC80 | [7 empty] | Yes |  |  |  | LPAGE | 2020-12-22 |  | Yes
18 | GEORGED | 2020-11-11 | No |  |  | Plastic container okay. NOTE - Step 5 dimensional check radius measurements skipped as per Scott Williams. Go/noGo Fit up check was done in place of measurements. Fit up was done with double-sided flange (FLG0037-279). | JL116 | Yes | Yes |  | Ok | Yes | 1.718 | 5.534 | 0.625 |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0.99 | 0.99 | 0.99 | Yes | Yes | Yes | 0.095 | 0.095 | 0.095 | Yes | Yes | Yes |  |  |  | LPAGE | 2020-10-19 |  | Eyelet tested 127'C at 12kW | PROSPER | 2021-01-07 | Yes | B1EEE51F-FCE6-7F26-4406A817D93DE038 | [7 empty] | Yes |  |  |  | LPAGE | 2020-12-22 |  | Yes | PROSPER | 2021-02-17 | Yes
19 | GEORGED | 2020-11-11 | No |  |  | Plastic container okay. NOTE - Step 5 dimensional check radius measurements skipped as per Scott Williams. Go/noGo Fit up check was done in place of measurements. Fit up was done with double-sided flange (FLG0037-279). | JL117 | Yes | Yes |  | Okay. | Yes | 1.717 | 5.533 | 0.625 |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0.988 | 0.988 | 0.988 | Yes | Yes | Yes | 0.095 | 0.095 | 0.095 | Yes | Yes | Yes |  |  |  | LPAGE | 2020-10-20 |  | Eyelet tested 127'C at 12kW | PROSPER | 2021-01-07 | Yes | B214EECA-C17C-2F82-5434C41E53D473AD | [7 empty] | Yes | PROSPER | 2021-02-17 | Yes | LPAGE | 2020-12-23 |  | Yes | PROSPER | 2021-02-17 | Yes
20 | GEORGED | 2020-11-11 | No |  |  | Plastic container okay. NOTE - Step 5 dimensional check radius measurements skipped as per Scott Williams. Go/noGo Fit up check was done in place of measurements. Fit up was done with double-sided flange (FLG0037-279). | JL118 | Yes | Yes |  | OK. | Yes | 1.718 | 5.533 | 0.624 |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0.99 | 0.99 | 0.99 | Yes | Yes | Yes | 0.095 | 0.095 | 0.095 | Yes | Yes | Yes |  |  |  | LPAGE | 2020-10-21 |  | Eyelet tested 125'C at 12kW | PROSPER | 2021-01-07 | Yes | B232B572-C890-A505-A20F51C868C77BE4 | [7 empty] | Yes |  |  |  | LPAGE | 2021-01-04 |  | Yes
21 | GEORGED | 2020-11-11 | No |  |  | Plastic container okay. NOTE - Step 5 dimensional check radius measurements skipped as per Scott Williams. Go/noGo Fit up check was done in place of measurements. Fit up was done with double-sided flange (FLG0037-279). | JL119 | Yes | Yes |  | OK | Yes | 1.717 | 5.533 | 0.624 |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0.988 | 0.988 | 0.99 | Yes | Yes | Yes | 0.096 | 0.095 | 0.096 | Yes | Yes | Yes |  |  |  | LPAGE | 2020-10-22 |  | Eyelet tested 129'C at 12kW | PROSPER | 2021-01-11 | Yes | 7B8EB6AA-EA6F-A84C-4F3D0A96EFB8416F | [7 empty] | Yes |  |  |  | LPAGE | 2021-01-05 |  | Yes | [18 empty] | PROSPER | 2021-01-11 | Yes | EDA29CD5-005C-B783-B2FD3FF3A2B1C627
22 | GEORGED | 2020-11-11 | No |  |  | Plastic container okay. NOTE - Step 5 dimensional check radius measurements skipped as per Scott Williams. Go/noGo Fit up check was done in place of measurements. Fit up was done with double-sided flange (FLG0037-279). | JL120 | Yes | Yes |  | OK | Yes | 1.718 | 5.533 | 0.625 |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0.989 | 0.989 | 0.99 | Yes | Yes | Yes | 0.095 | 0.096 | 0.096 | Yes | Yes | Yes |  |  |  | LPAGE | 2020-10-22 |  | Eyelet tested 125'C at 12kW | PROSPER | 2021-01-11 | Yes | 7B9A8419-FFD9-185F-DBE988A5B4BD5715 | [33 empty] | PROSPER | 2021-01-11 | Yes | EDCA951E-AC4E-8130-046A84B8557EAD88