## TRAVELERS
| Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author | Reviewer | Reviewer | Project Manager | Tech Rep (SOTR) | NCR Informative | NCR Dispositioners | D3 Emails | Procedure(s), Name (if known) | Drawing(s), Name (if known) | Acronym from INV | Notes | Status | Section
Cavity Preparation
Inspection
| Chemistry | [17 empty] | SS
| Assembly | [17 empty] | SS
| Testing | [17 empty] | SS
| Component Prepreation | [17 empty] | SH
| Inspection | [17 empty] | SS
| Chemistry | [17 empty] | SS
| Weld Inspection | [17 empty] | SS
| Leak Checks | [17 empty] | SS
| Assembly | [17 empty] | SS
| Cavity String | [17 empty] | SH
| Inspection | [17 empty] | SS
| Chemistry | [17 empty] | SS
| Cryomodule | [17 empty] | SH
| Inspection | [17 empty] | SS
| Cryomodule Assembly | [17 empty] | SS
| Cryomodule Testing | [17 empty] | SS
| Cryomodule Installation & Commisioning | [17 empty] | SS
| Standard Project Travelers | [17 empty] | SH
Color Legend |  | Count | Percent
CP | Complete (CP) | 0 | #DIV/0!
NR | New Revision Out for Approval (NR) | 0 | #DIV/0!
OA | Out for Approval (OA) | 0 | #DIV/0!
30 | Due in 30 Days | 0 | #DIV/0!
15 | Due in 15 Days | 0 | #DIV/0!
OD | Overdue | 0 | #DIV/0!
| Remaining | 0 | #DIV/0!
| Total Traveler IDs | 0

## INVENTORY TRAVELERS
Traveler Name | Traveler ID (SEPARATE BY WORKCENTERS) | Questions / Comments | Necessary Documentation | Author | Reviewer | Project Manager | SOTR | Date | D3 ?? (USERNAME) | NCR Dispositioners (USERNAME) | NCR Informative (USERNAME) | Notes

## PROCEDURES
PROCEDURE TITLE | PROCEDURE ID | REVISION | Author | Reviewer | Proj Lead | Due | Approved | CURRENT FILE LOCATION
Safety Procedures
Incoming inspection Procedures
Chemistry/ Cleaning Procedures
Cavity Procedures
String Production Procedures
Cryomodule Production Procedures
Cryomodule Testing Procedures
Cryomodule Shipping Procedures

## TRAVELERSold (hidden)
Traveler Name | Traveler ID (SEPARATE BY WORKCENTERS) | Procedure(s), Name (if known) OR Yes/No | Drawing(s), Name (if known) OR Yes/No | SOP/TOSP/OSP/THA | Revision | Author | Reviewer | Project Manager | SOTR | Due | D3 ?? (USERNAME) | NCR Dispositioners (USERNAME) | NCR Informative (USERNAME) | Traveler (Holdpoint) Closer (USERNAME) | Notes
Receiving Travelers
Cavity
Helium Vessel Receiving Traveler | SNSPPU-CAV-RECV-HELV |  |  |  | R1
Cavity String
Bellows Receiving Traveler | SNSPPU-CST-RECV-(bellows) |  |  |  | R1
Gate Valves Receiving Traveler | SNSPPU-CST-RECV-(gate valve) |  |  |  | R1
FPC Receiving Traveler | SNSPPU-CST-RECV-FPC |  |  |  | R1
Cryomodule
Diode CXCU Inventory Traveler | SNSPPU-CM-RECV-DCXCU |  |  |  | R1 | M. Dickey | C. Barnes | E. Daly | P. Owen | 2020-01-02 |  | powen,king,edaly,kwilson,mdickey,areilly
Disassembly Travelers
Cavity
Cavity String
Cryomodule
Leak Check Travelers
Cavity
Cavity String
Bellows Leak Check Traveler | SNSPPU-CST-LEAK-(bellows) |  |  |  | R1
Gate Valves Leak Check Traveler | SNSPPU-CST-LEAK-(gate valves) |  |  |  | R1
FPC Leak Check Traveler | SNSPPU-CST-LEAK-FPC |  |  |  | R1
Cryomodule
Inspection Travelers
Cavity
Visual and CMM Inspection of Cavity | SNSPPU-CAV-INSP-CAV |  | 104211800-M8U-8200-A00X |  | R1 |  |  |  | K. Wilson | 2020-02-01
Visual/CMM Inspection of Helium Vessel | SNSPPU-CAV-INSP-HELV | TI CLEANING | 104211700-M8U-8200-A026 |  | R1 |  |  |  | K. Wilson | 2020-02-01
Receiving Inspection Cavity RF | SNSPPU-CAV-RFIN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
TUNER FRAME / STEPPER MOTORS / HARMONIC DRIVE |  | SS CLEANING
Cavity String
Receiving Inspection Bellows | SNSPPU-CST-INSP-(bellows) |  |  |  | R1 |  |  |  | K. Wilson | 2020-05-01
SNS FPC Visual Inspection | SNSPPU-CST-INSP-FPC |  | 104211600-M8U-8200-A00X |  | R1 |  |  |  | K. Wilson | 2019-12-01
Cryomodule
Space Frame Visual and Dimensional Inspection | SNSPPU-CM-INSP-SFR | SS CLEANING | 104210900-M8U-8200-A001 |  | R1 |  |  |  | M. Marchlik | 2020-10-01
Vacuum Vessel Visual Inspection | SNSPPU-CM-INSP-VV | LEAK CHECK; SS CLEANING | 104210800-M8U-8200-A001 |  | R1 |  |  |  | M. Marchlik | 2020-07-01
SNS Return End Can Visual/CMM Inspection | SNSPPU-CM-INSP-RENC |  | 104210700-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-11-01
SNS Supply End Can Visual/CMM Inspection | SNSPPU-CM-INSP-SENC |  | 104210600-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-06-01
SNS Outer Magnetic Shield Visual Inspection | SNSPPU-CM-INSP-OMAG |  | 104211000-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-05-01
SNS Inner Magnetic Shield Visual Inspection | SNSPPU-CM-INSP-IMAG |  | 104211200-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-05-01
SNS Thermal Shield Visual/CMM Inspection | SNSPPU-CM-INSP-THRM | HIGH SENSITIVITY LEAK CHECK | 104211100-M8U-8200-A002 104211100-M8U-8200-A014 104211100-M8U-8200-A025 |  | R1 |  |  |  | M. Marchlik | 2020-08-01
Chemistry Travelers
Cavity
Cavity High Pressure Rinse (New HPR) Traveler | SNSPPU-CAV-CHEM-HPRN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Components Cleaning Traveler | SNSPPU-CAV-CHEM-CLN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Ultra Sonic Clean Traveler | SNSPPU-CAV-CHEM-USC |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
CMM Workcenter ?
IS there a cav RFIN traveler?
Furnace Workcenter ? | changed CHEM to PROC
Bakeout before RF processing | SNSPPU-CAV-PROC-BAKE |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Cavity Heat Treatment | SNSPPU-CAV-PROC-HEAT |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Processing Travelers
Cavity
Cavity RF Tuning | SNSPPU-CAV-TUNE |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
IS there a cav RFIN traveler? |  |  |  |  | R1
Cavity String
Cryomodule
RF Processing (FPC RF Processing) | SNSPPU-CM-CST-FPC-HPRF |  |  |  | R1 |  |  |  | K. Wilson
Assembly Travelers
Cavity
SNS Helium Vessel Installation Traveler | SNSPPU-CAV-ASSY-HELV |  | 104211700-M8U-8200-A026 |  | R1 |  |  |  |  | 2020-02-01
High Beta Cavity Assembly for VTA testing | SNSPPU-CAV-ASSY (look at old SNS) |  | 104211800-M8U-8200-A00X |  | R1 |  |  |  |  | 2020-02-01
transfer to test stand
Cavity String
SNS High Beta Cavity String Traveler | SNSPPU-CST-ASSY |  |  |  | R1 |  |  |  |  | 2020-07-01
Cryomodule
Cryomodule Assembly | SNSPPU-CM-ASSY |  |  |  | R1 |  |  |  | M. Marchlik | 2020-12-01
Cold Mass Assembly | SNSPPU-CM-ASSY-CMAS |  |  |  | R1 |  |  |  |  | 2020-08-01
Cryomodule Thermal Shield-Spaceframe Assembly Traveler | SNSPPU-CM-ASSY-THRM |  | 104211100-M8U-8200-A002 104211100-M8U-8200-A014 104211100-M8U-8200-A025 |  | R1 |  |  |  | M. Marchlik
SNS High Beta Cryomodule Vacuum Vessel-End Can Assembly Traveler | SNSPPU-CM-ASSY-VV |  | 104210800-M8U-8200-A001 |  | R1
cm assy ship (rf, instrumentation)
Testing Travelers
Vertical Cavity Testing | SNSPPU-CAV-VTRF |  |  |  | R1 |  |  |  |  | 2020-04-01
Cavity VTA Cooldown | SNSPPU-CAV-VTA-COOL |  |  |  | R1 |  |  |  |  | 2020-02-01
Installation/Shipping Travelers
SNS Cryomodule Shipping | SNSPPU-CM-ASSY-SHIP |  |  |  | R1 |  |  |  |  | 2020-05-01
Standard Project Travelers
Detours, Deviations and Discrepancies (D3) | SNSPPU-D3 |  |  |  | R2 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A
Inspection Summary Report | SNSPPU-INSR |  |  |  | R1 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A
Inspection Nonconformance Report | SNSPPU-NCR |  |  |  | R10 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A