## Checklists
Meta procedure for processing cavities in the Tunnel {CMTF}
This checklist provides an overview of the actions required to plasma process a C100 cryomodule in either the CEBAB tunnel or the CMTF. The procedure with the detailed steps for each action is also provided. Vacuum work shall be performed by personnel trained to perform particulate-free beamline work in portable cleanrooms. Personnel trained to perform plasma processing shall perform actions listed for Plasma Processing and may provide guidance on vacuum work as it pertains to the plasma processing equipment.
Vacuum work: Connect plasma processing carts
1 | Assemble a portable clean hood covering the area around the upstream and down stream girders. | FM-WMGRDR-CLNRM-SETUP
2 | Using appropriate clean hood and clean assembly techniques connect the cavity to the vacuum cart to the valve located on the ion pump just upstream of the cryomodule. | PLACLN-PR-CM-CONN
3 | Pump out the line to UHV and open the valve between the pump cart and the ion pump.
4 | Ensure that the “B” beam line valve just upstream of the cryomodule is closed and unplugged* from the control system. *Unplugging it makes it such that no one from operations can open the valve while we have the cryomodule beam line up to 0.3 Torr.
5 | Using appropriate clean hood and clean assembly techniques, connect the supply line manifold to the closed valve located on the downstream ion pump {downstream beam line valve}.
6 | Pump out the supply manifold {for CMTF do this with the right-angle valve attached to the beam line open}.
7 | Using a local* valve control box, open the valve connected to the downstream ion pump {for the CMTF open the downstream beam line valve. *Using a local box ensures that no one from ops can close the valve when we are flowing gas through the cryomodule.
8 | Turn off the two ion pumps - one just upstream of the cryomodule and one just down stream of the cryomodule - and unplug them from their respective power supplies.
9 | Log into EPICS and start a Live Plot of the beamline vacuum for the adjacent cryomodules. If the pressures increase when gas flow is established, stop the gas flow and assess the situation.
Vacuum work: Disconnect plasma processing carts
1 | Assemble a portable clean hood covering the area around the upstream and down stream girders. | FM-WMGRDR-CLNRM-SETUP
2 | When the gas supply and pump out manifolds are below 10 mTorr, open the main valve to turbo pump B. | PLACLN-PR-CM-DISC
3 | When the system is at UHV close the valve between the downstream ion pump and the gas supply manifold {in the CMTF close the downstream beam line gate valve.}
4 | Turn on the two ion pumps {CMTF turn on the ion pump}
5 | Close the valve on the upstream ion pump.
6 | Using a flow of less than 70 SCCM backfill the supply manifold to slightly over 1 ATM. {CMTF While someone is watching the ion pump pressure backfill the supply manifold with 70 SCCM of inert gas.} If the pressure on the ion pump increases stop and evaluate the situation.
7 | Turn off the RGA.
8 | Turn off the turbo pumps and let them spin down for 20 minutes.
9 | Turn off the backing pumps on the turbo cart.
10 | Backfill pump out manifold with nitrogen.
11 | Using appropriate clean hood and clean assembly techniques disconnect the vacuum manifold and gas supply manifold from the beam line {cryomodule} and apply blank conflat flanges to all open ports.
12 | Open the ion pump valves and return gate valves to normal control.
Plasma Processing: Prepare for plasma processing a cryomodule accelerator tunnel {and CMTF}
1 | Using appropriate LOTO procedures remove a section of waveguide upstream of the one-half to full-height waveguide transition. Place a metal blank on the upstream waveguide and a waveguide to type-N transition on the downstream waveguide. (EES-RF {SRF cryomodule assembly} group task)
2 | Log into EPICS and start a Live Plot of the beamline vacuum for the adjacent cryomodules. If the pressures increase when gas flow is established, stop the gas flow and assess the situation. | PLACLN-PR-CM-PREP
3 | Using established procedures establish gas flow to the cavity and process the cavity and adjust the oxygen percentage.
4 | Adjacent cavities cannot be processed simultaneously. Plan the cavity processing sequence and RF cart movements in advance.
5 | Using established procedures, calibrate the Network Analyzer. | PLACLN-PR-NA-CAL
6 | Using established procedures, calibrate the RF cables. | PLACLN-PR-CAV-CCAL
7 | Using a calibrated network analyzer S1 port connected to the HOM coupler being used to drive the cavity and connect the motorized phase shifter to the second HOM port use the established procedure to measure S11 and S21 as a function of phase shifter position for all 8 cavities. The phase shifter position shall be varied between 0 and 360 degrees of two-way phase shift in 5 degree increments. | PLACLN-PR-CAV-PHASE
8 | Using established procedures determine the optimal phase shift position for processing each cavity.
9 | Connect the output of the RF system to the selected HOM and the input to the RF system to the waveguide top-hat. | PLACLN-PR-CM-PREP
10 | Using established procedures, process each cell or combination of two cells for one hour. Up to four cavities can be processed at the simultaneously. Adjacent cavities cannot be processed simultaneously. | PLACLN-PR-CM-PROC
11 | The RF controls must be attended at all times when the coupler interlock is not engaged.
12 | Process all of the cavities twice with at least a 24-hour break between processing cycles on individual cavities.
Plasma Processing: Beginning of Day Checklist
1 | Verify the cryomodule's upstream gate valve (near the plasma vacuum cart) is closed and the cryomodule's downstream gate valve (near the plasma gas cart) is open. Verify the gate valves are under local control only. | PLACLN-PR-CM-PROC
2 | Verify the cryomodule's ion pumps are off and unplugged.
3 | Verify the PlasmaMain software is running and reading all sensors, meters, gauges, etc. correctly.
4 | Verify the RGA is running and the filament is on.
5 | Verify the cryomodule's pressure is in the E-5 Torr or lower range and the plasma gas cart is reading 0.1 Torr (bottom of scale).
6 | Verify all pumps are on and running properly.
7 | Verify the MFC is closed.
8 | Close the plasma gas cart valves to the scroll pump (Pump Main and VN2). Open the gas tanks, VA1, VA2, VM1, and VM2.
9 | Monitor the EPICS Live Plot of the beamline vacuum for the adjacent cryomodules. If the pressures increase when gas flow is established, stop the gas flow and assess the situation.
10 | Slowly open the valve on the gas cart manifold between the plasma gas cart and the girder isolation valve. Verify the cryomodule's pressure remains steady. If any significant change in the cryomodule's pressure is observed, close the gas cart manifold valve and seek assistance to troubleshoot.
11 | Using the PlasmaMain software, set the MFC set point to the value used on the previous plasma processing day. Verify the pressure set point is correct. Start gas flow with the PlasmaMain software.
12 | Once the gas flow is regulating at the correct pressure, check the O2%. Adjust the gas cart slowly as needed to ensure the O2% is in the target range.
13 | Move the RF input and phase shifter cables to the cavities to be processed.
14 | Load the correct mode files to the PlasmaMain software and set the phase shifter position for each cavity.
15 | Turn on the amplifier(s).
16 | In the PlasmaMain software, set the network analyzer S21 baseline trace and modes for frequency shift calculation.
17 | Verify the RGA is reading good baseline partial pressures. Begin plasma processing in accordance with the procedure.
Plasma Processing: End of Day Checklist
1 | Stop gas flow by closing the MFC. Note the MFC set point on the PlasmaMain program. Close the gas tanks and the valves on the gas cart. Continue pumping the cryomodule with the plasma vacuum cart. | PLACLN-PR-CM-PROC
2 | Close the valve on the plasma manifold between the gas cart and the girder isolation valve. Leave the isolation valve open.
3 | Using the scroll pump on the gas cart, pump out the gas line from VA2, VM2 through to the closed gas cart manifold valve.
4 | Once the capacitive manometer on the plasma vacuum cart manifold reads below 10mTorr, fully open the V21 valve on the vacuum cart.
5 | Turn off the amplifier(s).
6 | Back up files.
7 | Create Elog entry noting which cavities and cells were processed, the gas pressure, gas flow, and O2% used.
8 | Complete fields in the traveler PLACLN-CMTF-CM-PLSM for work performed.

## Revisions
Revision # | Description of Changes | Revision Effective Date
- | Initial Issue | 2023-03-28

## Approvals
Approved By: | Name: | Signature / Date:
Checklist Author | T. Ganey | In DocuShare
Work Center Lead | M. Drury | In DocuShare
Process Owner | T. Powers | In DocuShare