## TRAVELERS
| Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | Author | Reviewer | Reviewer | Project Manager | SOTR | NCR Informative | NCR Dispositioners | D3 Emails | Procedure(s), Name (if known) | Drawing(s), Name (if known) | Acronym from INV | Notes | Status | Section
H-HOM Feedthrough
CP | H-HOM Feedthrough 25ohm Rod | AUP-PREP-HHMFT-FTHMRD | R1 | 2020-10-16 | Matthew Weaks | Scott Williams |  | Naeem Huque | [5 empty] | JL0089755 |  |  | CP
| H-HOM Feedthrough 25ohm Rod | AUP-INV-FTHMRD | R1 | 2020-06-15 | Mike Dickey | Calvin Barnes |  | Naeem Huque |  | mdicky,cbarnes | huque,scott | huque,scott |  |  |  |  | CP
| H-HOM Feedthrough Brazing Assembly | AUP-ASSY-HHMFT-BRZAS | R1 |  | Matthew Weaks | Scott Williams |  | Naeem Huque | [5 empty] | JL0089751
CP | H-HOM Feedthrough Assembly | AUP-ASSY-HHMFT | R2 | 2020-10-31 | Matthew Weaks | Scott Williams |  | Naeem Huque | [5 empty] | JL0093243 |  |  | CP
CP | H-HOM Feedthrough 25ohm Pince Revised | AUP-PREP-HHMFT-FTPCR | R1 | 2020-10-31 | Matthew Weaks | Scott Williams |  | Naeem Huque | [5 empty] | JL0101223 |  |  | CP
| H-HOM Field Antenna | [16 empty] | SS
CP | Field Antenna 25ohm Hook | AUP-PREP-FANT-FA25H | R1 | 2020-10-16 | Matthew Weaks | Scott Williams |  | Naeem Huque | [5 empty] | JL0090341 |  |  | CP
| Feedthrough Pince Cable 25ohm | AUP-PREP-FANT-FTPC | R1 |  | Matthew Weaks | Scott Williams |  | Naeem Huque | [5 empty] | JL0090344
CP | Feedthrough Cable Connector | AUP-PREP-FANT-CNCTR | R1 | 2020-10-23 | Matthew Weaks | Scott Williams |  | Naeem Huque | [5 empty] | JL0090343 |  |  | CP
CP | Field Antenna 25ohm | AUP-ASSY-FANT | R2 | 2020-10-31 | Matthew Weaks | Scott Williams |  | Naeem Huque | [5 empty] | JL0090340 |  |  | CP
| V-HOM Coupler | [16 empty] | SS
OD | V-HOM Couple 25ohm Hook | AUP-PREP-VHOM-VH25SN | R1 | 2020-10-16 | Matthew Weaks | Scott Williams |  | Naeem Huque | [5 empty] | JL0090122
CP | V-HOM Couple 25ohm | AUP-ASSY-VHOM-VCASSY | R1 | 2020-10-31 | Matthew Weaks | Scott Williams |  | Naeem Huque | [5 empty] | JL0089940 |  |  | CP
AUP-ASSY-VHOM
| H-HOM Damper | [16 empty] | SS
CP | HOM Niobium Hook | AUP-PREP-DAMP-HOOK | R1 | 2020-10-12 | Matthew Weaks | Scott Williams |  | Naeem Huque | [5 empty] | JL0086021 |  |  | CP
CP | HOM Tee | AUP-PREP-DAMP-TEE | R1 | 2020-10-12 | Matthew Weaks | Scott Williams |  | Naeem Huque | [5 empty] | JL0083868 |  |  | CP
CP | Niobium Can Lid | AUP-PREP-DAMP-NBLID | R1 | 2020-10-16 | Matthew Weaks | Scott Williams |  | Naeem Huque | [5 empty] | JL0086010 |  |  | CP
CP | Niobium Can Lid Final Machining | AUP-PREP-DAMP-LDMCH | R1 | 2020-10-31 | Matthew Weaks | Scott Williams |  | Naeem Huque | [5 empty] | JL0088326 |  |  | CP
CP | Outer Can Lid | AUP-PREP-DAMP-OCLID | R1 | 2020-10-16 | Matthew Weaks | Scott Williams |  | Naeem Huque | [5 empty] | JL0088271 |  |  | CP
CP | Niobium Lid Brazing Assembly | AUP-ASSY-DAMP-NLASSY | R2 | 2020-10-31 | Matthew Weaks | Scott Williams |  | Naeem Huque | [5 empty] | JL0088238 |  | NOT IN DOC REPO | CP
CP | Niobium Can Lid Machining Assembly | AUP-ASSY-DAMP-CLASSY | R1 | 2020-10-31 | Matthew Weaks | Scott Williams |  | Naeem Huque | [5 empty] | JL0088600 |  |  | CP
CP | H-HOM Inner Tube | AUP-PREP-DAMP-ITUBE | R1 | 2020-10-08 | Matthew Weaks | Scott Williams |  | Naeem Huque | [5 empty] | JL0086026 |  |  | CP
CP | H-HOM Flange DN100 | AUP-PREP-DAMP-DN100 | R1 | 2020-10-16 | Matthew Weaks | Scott Williams |  | Naeem Huque | [5 empty] | JL0086025 |  | NO INSPECTION REQ (NO ACRONYM) | CP
CP | DN100 Braze Assembly | AUP-ASSY-DAMP-FLGWLD | R1 | 2020-10-31 | Matthew Weaks | Scott Williams |  | Naeem Huque | [5 empty] | JL0088274 |  |  | CP
CP | DN100 Machining | AUP-ASSY-DAMP-FLMCH | R1 | 2020-10-31 | Matthew Weaks | Scott Williams |  | Naeem Huque | [5 empty] | JL0088272 |  |  | CP
CP | Hook and Tee Weldment | AUP-ASSY-DAMP-HKTEE | R2 | 2020-10-31 | Matthew Weaks | Scott Williams |  | Naeem Huque | [5 empty] | JL0088266 |  |  | CP
CP | Inner Can Assembly | AUP-ASSY-DAMP-INCAN | R1 | 2020-10-31 | Matthew Weaks | Scott Williams |  | Naeem Huque | [5 empty] | JL0088602 |  |  | CP
CP | HOM H External Pipe | AUP-PREP-DAMP-EXPIPE | R1 | 2020-10-16 | Matthew Weaks | Scott Williams |  | Naeem Huque | [5 empty] | JL0086009 |  |  | CP
CP | Outlet Tube | AUP-PREP-DAMP-OTUBE | R1 | 2020-10-31 | Matthew Weaks | Scott Williams |  | Naeem Huque | [5 empty] | JL0088598 |  |  | CP
CP | Outer Tube Assembly | AUP-ASSY-DAMP-TBASSY | R2 | 2020-10-31 | Matthew Weaks | Scott Williams |  | Naeem Huque | [5 empty] | JL0088268 |  |  | CP
CP | AUP RFD H-HOM Damper | AUP-ASSY-DAMP-FASSY | R2 | 2020-10-31 | Matthew Weaks | Scott Williams | [7 empty] | JL0086007 |  |  | CP
CP | DN100 Braze Assembly | AUP-ASSY-DAMP-FLGBRZ | R2 |  | Matthew Weaks | Scott Williams |  | Naeem Huque |  | jharris | huque,scott | huque |  |  |  |  | CP
| Common Travelers | [16 empty] | SS
OD | Pince Feedthrough | AUP-PREP-CMN-FTPC | R1 | 2020-10-31 | Matthew Weaks | Scott Williams |  | Naeem Huque | [5 empty] | JL0101223 |  | (IS THIS SAME AS ABOVE LN 10 ?)
CP | Copper Ring | AUP-PREP-CMN-CURING | R1 | 2020-09-20 | Matthew Weaks | Scott Williams |  | Naeem Huque | [5 empty] | JL0089865 |  |  | CP
CP | Copper Ring Inspection | AUP-INSP-CMN-CURING | R1 | 2020-06-02 | Matthew Weaks | Scott Williams |  | Naeem Huque |  | weaksmc | huque,scott | huque,scott,weaksmc |  |  |  |  | CP
CP | Copper Ring Inventory | AUP-INV-CURING | R1 | 2020-06-15 | Mike Dickey | Calvin Barnes |  | Naeem Huque |  | mdicky,cbarnes | huque,scott | huque,scott |  |  |  |  | CP
CP | Feedthrough 25ohm Rod | AUP-PREP-CMN-FTROD | R1 | 2020-09-20 | Matthew Weaks | Scott Williams |  | Naeem Huque | [5 empty] | JL0090118 |  |  | CP
CP | Feedthrough 25ohm Rod Inspection | AUP-INSP-CMN-FTROD | R1 | 2020-06-17 | Matthew Weaks | Scott Williams |  | Naeem Huque |  | weaksmc | huque,scott | huque,scott,weaksmc |  |  |  |  | CP
| Feedthrough 25ohm Rod Inventory | AUP-INV-FTROD | R1 | 2020-06-15 | Mike Dickey | Calvin Barnes |  | Naeem Huque |  | mdicky,cbarnes | huque,scott | huque,scott |  |  |  |  | CP
CP | Custom DN40 Flange | AUP-PREP-CMN-DN40F | R2 | 2020-10-16 | Matthew Weaks | Scott Williams |  | Naeem Huque | [5 empty] | JL0089760 |  |  | CP
CP | Ceramic D40d14 | AUP-PREP-CMN-DSCCRM | R1 | 2020-09-20 | Matthew Weaks | Scott Williams |  | Naeem Huque | [5 empty] | LHCACFHC0206 |  | NOT IN DOC REPO | CP
CP | Ceramic D40d14 Inspection | AUP-INSP-CMN-DSCCRM | R1 | 2020-06-02 | Matthew Weaks | Scott Williams |  | Naeem Huque |  | weaksmc | huque,scott | huque,scott,weaksmc |  |  |  |  | CP
CP | Ceramic D40d14 Inventory | AUP-INV-DSCCRM | R1 | 2020-06-15 | Mike Dickey | Calvin Barnes |  | Naeem Huque |  | mdicky,cbarnes | huque,scott | huque,scott |  |  |  |  | CP
CP | Flange Brazing Assembly | AUP-ASSY-CMN-FLBRZ | R1 | 2020-10-08 | Matthew Weaks | Scott Williams |  | Naeem Huque | [5 empty] | JL0092614 |  |  | CP
CP | Feedthrough 25ohm Brazing Assembly | AUP-ASSY-CMN-BRZAS | R1 | 2020-10-31 | Matthew Weaks | Scott Williams |  | Naeem Huque | [5 empty] | JL0090121 |  |  | CP
CP | V-HOM Coupler 25 Ohm Hook | AUP-INV-VH25H | R1 | 2020-07-19 | Mike Dickey | Calvin Barnes |  | Naeem Huque |  | mdicky,cbarnes | huque,scott | huque,scott |  |  |  |  | CP
CP | AUP H-HOM Damper Final Tuning and Shipping Prep | AUP-ASSY-DAMP-FPREP | R1 |  | N. Huque | D. Forehand | A. Mitchell | E. Daly |  | jharris | huque | huque |  |  |  |  | CP
CP | AUP Liquid Nitrogen Thermal Shock Procedure | AUP-PR-LEAK-CMA-LN2 | R1 | 2022-04-27 | N. Huque | J. Harris |  | J. Fischer | [8 empty] | CP
CP | AUP Acid Etching at the Chemical Fume Hood Procedure | CP-AUP-CAV-CHEM-ACID | R1 | 2020-06-10 | A. Mitchell | T. Harris |  | N. Huque | [8 empty] | CP
CP | AUP Acid Etching at the Chemical Fume Hood Procedure | CP-AUP-CAV-CHEM-ACID | R2 | 2022-06-10 | A. Mitchell |  |  | N. Huque | A. Reilly | [7 empty] | CP
CP | AUP Cavity Components and Parts Degreasing Procedure | CP-AUP-CAV-CHEM-DEGR | R1 | 2020-06-10 | A. Mitchell | T. Harris |  | N. Huque | [8 empty] | CP
CP | AUP Cavity Components and Parts Degreasing Procedure | CP-AUP-CAV-CHEM-DEGR | R2 | 2022-06-10 | A. Mitchell |  |  | N. Huque | A. Reilly | [7 empty] | CP
| Standard Project Travelers | [16 empty] | SH
Color Legend |  | Count | Percent
CP | Complete (CP) | 43 | 86%
NR | New Revision Out for Approval (NR) | 0 | 0%
OA | Out for Approval (OA) | 0 | 0%
30 | Due in 30 Days | 0 | 0%
15 | Due in 15 Days | 0 | 0%
OD | Overdue | 2 | 4%
| Remaining | 5 | 10%
| Total Traveler IDs | 50

## INVENTORY TRAVELERS
Traveler Name | Traveler ID (SEPARATE BY WORKCENTERS) | Questions / Comments | Necessary Documentation | Author | Reviewer | Project Manager | SOTR | Date | D3 ?? (USERNAME) | NCR Dispositioners (USERNAME) | NCR Informative (USERNAME) | Notes

## PROCEDURES
PROCEDURE TITLE | PROCEDURE ID | REVISION | Author | Reviewer | Proj Lead | Due | Approved | CURRENT FILE LOCATION
Safety Procedures
Incoming inspection Procedures
Chemistry/ Cleaning Procedures
Cavity Procedures
String Production Procedures
Cryomodule Production Procedures
Cryomodule Testing Procedures
Cryomodule Shipping Procedures

## TRAVELERSold (hidden)
Traveler Name | Traveler ID (SEPARATE BY WORKCENTERS) | Procedure(s), Name (if known) OR Yes/No | Drawing(s), Name (if known) OR Yes/No | SOP/TOSP/OSP/THA | Revision | Author | Reviewer | Project Manager | SOTR | Due | D3 ?? (USERNAME) | NCR Dispositioners (USERNAME) | NCR Informative (USERNAME) | Traveler (Holdpoint) Closer (USERNAME) | Notes
Receiving Travelers
Cavity
Helium Vessel Receiving Traveler | SNSPPU-CAV-RECV-HELV |  |  |  | R1
Cavity String
Bellows Receiving Traveler | SNSPPU-CST-RECV-(bellows) |  |  |  | R1
Gate Valves Receiving Traveler | SNSPPU-CST-RECV-(gate valve) |  |  |  | R1
FPC Receiving Traveler | SNSPPU-CST-RECV-FPC |  |  |  | R1
Cryomodule
Diode CXCU Inventory Traveler | SNSPPU-CM-RECV-DCXCU |  |  |  | R1 | M. Dickey | C. Barnes | E. Daly | P. Owen | 2020-01-02 |  | powen,king,edaly,kwilson,mdickey,areilly
Disassembly Travelers
Cavity
Cavity String
Cryomodule
Leak Check Travelers
Cavity
Cavity String
Bellows Leak Check Traveler | SNSPPU-CST-LEAK-(bellows) |  |  |  | R1
Gate Valves Leak Check Traveler | SNSPPU-CST-LEAK-(gate valves) |  |  |  | R1
FPC Leak Check Traveler | SNSPPU-CST-LEAK-FPC |  |  |  | R1
Cryomodule
Inspection Travelers
Cavity
Visual and CMM Inspection of Cavity | SNSPPU-CAV-INSP-CAV |  | 104211800-M8U-8200-A00X |  | R1 |  |  |  | K. Wilson | 2020-02-01
Visual/CMM Inspection of Helium Vessel | SNSPPU-CAV-INSP-HELV | TI CLEANING | 104211700-M8U-8200-A026 |  | R1 |  |  |  | K. Wilson | 2020-02-01
Receiving Inspection Cavity RF | SNSPPU-CAV-RFIN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
TUNER FRAME / STEPPER MOTORS / HARMONIC DRIVE |  | SS CLEANING
Cavity String
Receiving Inspection Bellows | SNSPPU-CST-INSP-(bellows) |  |  |  | R1 |  |  |  | K. Wilson | 2020-05-01
SNS FPC Visual Inspection | SNSPPU-CST-INSP-FPC |  | 104211600-M8U-8200-A00X |  | R1 |  |  |  | K. Wilson | 2019-12-01
Cryomodule
Space Frame Visual and Dimensional Inspection | SNSPPU-CM-INSP-SFR | SS CLEANING | 104210900-M8U-8200-A001 |  | R1 |  |  |  | M. Marchlik | 2020-10-01
Vacuum Vessel Visual Inspection | SNSPPU-CM-INSP-VV | LEAK CHECK; SS CLEANING | 104210800-M8U-8200-A001 |  | R1 |  |  |  | M. Marchlik | 2020-07-01
SNS Return End Can Visual/CMM Inspection | SNSPPU-CM-INSP-RENC |  | 104210700-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-11-01
SNS Supply End Can Visual/CMM Inspection | SNSPPU-CM-INSP-SENC |  | 104210600-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-06-01
SNS Outer Magnetic Shield Visual Inspection | SNSPPU-CM-INSP-OMAG |  | 104211000-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-05-01
SNS Inner Magnetic Shield Visual Inspection | SNSPPU-CM-INSP-IMAG |  | 104211200-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-05-01
SNS Thermal Shield Visual/CMM Inspection | SNSPPU-CM-INSP-THRM | HIGH SENSITIVITY LEAK CHECK | 104211100-M8U-8200-A002 104211100-M8U-8200-A014 104211100-M8U-8200-A025 |  | R1 |  |  |  | M. Marchlik | 2020-08-01
Chemistry Travelers
Cavity
Cavity High Pressure Rinse (New HPR) Traveler | SNSPPU-CAV-CHEM-HPRN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Components Cleaning Traveler | SNSPPU-CAV-CHEM-CLN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Ultra Sonic Clean Traveler | SNSPPU-CAV-CHEM-USC |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
CMM Workcenter ?
IS there a cav RFIN traveler?
Furnace Workcenter ? | changed CHEM to PROC
Bakeout before RF processing | SNSPPU-CAV-PROC-BAKE |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Cavity Heat Treatment | SNSPPU-CAV-PROC-HEAT |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Processing Travelers
Cavity
Cavity RF Tuning | SNSPPU-CAV-TUNE |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
IS there a cav RFIN traveler? |  |  |  |  | R1
Cavity String
Cryomodule
RF Processing (FPC RF Processing) | SNSPPU-CM-CST-FPC-HPRF |  |  |  | R1 |  |  |  | K. Wilson
Assembly Travelers
Cavity
SNS Helium Vessel Installation Traveler | SNSPPU-CAV-ASSY-HELV |  | 104211700-M8U-8200-A026 |  | R1 |  |  |  |  | 2020-02-01
High Beta Cavity Assembly for VTA testing | SNSPPU-CAV-ASSY (look at old SNS) |  | 104211800-M8U-8200-A00X |  | R1 |  |  |  |  | 2020-02-01
transfer to test stand
Cavity String
SNS High Beta Cavity String Traveler | SNSPPU-CST-ASSY |  |  |  | R1 |  |  |  |  | 2020-07-01
Cryomodule
Cryomodule Assembly | SNSPPU-CM-ASSY |  |  |  | R1 |  |  |  | M. Marchlik | 2020-12-01
Cold Mass Assembly | SNSPPU-CM-ASSY-CMAS |  |  |  | R1 |  |  |  |  | 2020-08-01
Cryomodule Thermal Shield-Spaceframe Assembly Traveler | SNSPPU-CM-ASSY-THRM |  | 104211100-M8U-8200-A002 104211100-M8U-8200-A014 104211100-M8U-8200-A025 |  | R1 |  |  |  | M. Marchlik
SNS High Beta Cryomodule Vacuum Vessel-End Can Assembly Traveler | SNSPPU-CM-ASSY-VV |  | 104210800-M8U-8200-A001 |  | R1
cm assy ship (rf, instrumentation)
Testing Travelers
Vertical Cavity Testing | SNSPPU-CAV-VTRF |  |  |  | R1 |  |  |  |  | 2020-04-01
Cavity VTA Cooldown | SNSPPU-CAV-VTA-COOL |  |  |  | R1 |  |  |  |  | 2020-02-01
Installation/Shipping Travelers
SNS Cryomodule Shipping | SNSPPU-CM-ASSY-SHIP |  |  |  | R1 |  |  |  |  | 2020-05-01
Standard Project Travelers
Detours, Deviations and Discrepancies (D3) | SNSPPU-D3 |  |  |  | R2 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A
Inspection Summary Report | SNSPPU-INSR |  |  |  | R1 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A
Inspection Nonconformance Report | SNSPPU-NCR |  |  |  | R10 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A