## WorkControlDocuments
Document Title | Document Type | Document ID | Author / Owner | Reviewer 1 (SRFOPS SME or WCL) | Reviewer 2 (SRFOPS WCL or Group Lead) | Project Representative | NCR Informative | NCR Dispositioners | D3 Emails | NOTES
Disassembly Documents
Cavity
Cavity Disassembly | Traveler | C100R-CAV-DISA | C. Dreyfuss | D. Forehand | K. Davis | A. Reilly | dreyfuss,areilly | forehand,kdavis,ganey | dreyfuss,forehand,kdavis,areilly,ganey
Cryomodule
C100R Disassembly Traveler | Traveler | C100R-CM-DISA | J. Fischer | J. Campbell | J. Fischer | A. Reilly | areilly | fischer,jjcamp,ganey | fischer,jjcamp,areilly,ganey
Cavity and Component Refurbishment Documents
Welding and Brazing
Waveguide and Window
C100R Brazed Ceramic Assembly | Traveler | C100R-FURN-CEBRZ-BRAZ | G. Grose |  | S. Williams | A. Reilly | areilly | grose,scott,ganey | grose,scott,ganey,areilly
C100R Window Brazement Adapter | Traveler | C100R-FURN-WBA-BRZ | G. Grose |  | S. Williams | A. Reilly | areilly | grose,scott,ganey | grose,scott,ganey,areilly
C100R Window Brazement Assembly Inspection | Traveler | C100R-FURN-WBA-INSP | G. Grose |  | S. Williams | A. Reilly | areilly | scott,grose,ganey | areilly,scott,grose,ganey
C100R Window Assembly | Traveler | C100R-FURN-WIN-ASSY | G. Grose |  | S. Williams | A. Reilly | areilly | scott,grose,ganey | areilly,scott,grose,ganey
C100R Welded Window Waveguide Assembly | Traveler | C100R-FURN-WINWGD-ASSY | G. Grose |  | S. Williams | A. Reilly | areilly,dreyfuss,forehand | scott,grose,ganey | areilly,dreyfuss,forehand,scott,grose,ganey
C100R Window and Waveguide Electron Beam Welding | Traveler | C100R-EBW-WINWGD | S. Williams | G. Grose | A. O'Brien | A. Reilly | areilly | grose,scott,ganey,aobrien | areilly,grose,scott,ganey,aobrien
Helium Vessel
C100R Helium Vessel Installation | Traveler | C100R-CAV-ASSY-HELV | J. Fischer | J. Campbell | A. Auston | A. Reilly | forehand,areilly | fischer,auston,ganey | areilly,ganey,forehand,fischer,auston
Inspection (CMM WC)
Cavity
Cavity CMM Receiving Inspection | Traveler | C100R-CAV-INSP | T. Ganey | G. Dekerlegand | A. McEwen | A. Reilly | areilly | ganey,kdavis | areilly,ganey,kdavis
Feedthrus
Cavity HOM Feedthru Receiving Inspection | Traveler | C100R-CAV-INSP-HMFT | L. Zhao | G. Dekerlegand | A. McEwen | A. Reilly | areilly | lzhao,kdavis,ganey | ,areilly,lzhao,kdavis,ganey
Waveguide and Window
C100R Double Sided Rectangular Flange Receiving Inspection Traveler | Traveler | C100R-INSP-DSRF | S. Williams | E. Mosby | A. McEwen | A. Reilly | areilly,fischer | scott,grose,ganey | areilly,fischer,scott,grose,ganey
Waveguide Inspection Prior to Welding to a Primary Window | Traveler | C100R-INSP-WGD | S. Williams | E. Mosby | A. McEwen | A. Reilly | areilly | scott,grose,ganey,lzhao | areilly,scott,grose,ganey,lzhao
Welded Window to Waveguide Inspection | Traveler | C100R-INSP-WINWGD | S. Williams | E. Mosby | A. McEwen | A. Reilly | areilly | scott,grose,ganey,dreyfuss,forehand | areilly,scott,grose,ganey,dreyfuss,forehand
Recycled Waveguide Inspection - 12 GeV Upgrade Waveguides | Traveler | C100R-CAV-INSP-WGD-RCYC | S. Williams | G. Dekerlegand | A. McEwen | A. Reilly | areilly | scott,grose,ganey | areilly,scott,grose,ganey
Helium Vessel
Receiving Inspection of C100 Cryomodule Helium Vessel | Traveler | C100R-CMA-HELV-INSP | G. Cheng | G. Dekerlegand | A. McEwen | A. Reilly | areilly | cheng,fischer,ganey | cheng,fischer,areilly,ganey
C100 cryomodule return header bellows receiving inspection traveler | Traveler | C100R-CMA-HERB-INSP | G. Cheng | G. Dekerlegand | A. McEwen | A. Reilly | areilly | cheng,fischer,ganey | cheng,fischer,areilly,ganey
C100 cryomodule supply header bellows receiving inspection traveler | Traveler | C100R-CMA-HESB-INSP | G. Cheng | G. Dekerlegand | A. McEwen | A. Reilly | areilly | cheng,fischer,ganey | cheng,fischer,areilly,ganey
CMA
C100R leak check inspection traveler | Traveler | C100R-CMA-HMFT-LEAK-R1 | L. Zhao | C. Wilcox | J. Fischer | A. Reilly | jtkent,wilcox,areilly,forehand,kdavis | lzhao,fisher,ganey | wilcox,forehand,areilly,lzhao,kdavis,ganey
C100R Window and Waveguide Leak Check Traveler | Traveler | C100R-CMA-WINWGD-LEAK | G. Grose | S. Williams | C. Wilcox | A. Reilly | areilly,wilcox | scott,gross,forehand,dreyfuss,ganey | areilly,wilcox,scott,grose,forehand,dreyfuss,ganey
Window Flange Welding | Traveler | C100R-CMA-WIN-WELD | S. Williams | A. Auston | J. Fischer | A. Reilly | areilly,fischer | scott,grose,ganey | areilly,fischer,scott,grose,ganey | Currently does not exist in Pansophy
RF Inspection / Tuning
Cavity RF Inspection Receiving Inspection | Traveler | C100R-CAV-RFIN | R. Overton | D. Forehand | K. Davis | A. Reilly | areilly | forehand,kdavis,ganey | forehand,areilly,overton,kdavis,ganey
C100R Cavity Tuning | Traveler | C100R-CAV-TUNE | R. Overton | D. Forehand | K. Davis | A. Reilly | areilly | forehand,kdavis,ganey | forehand,areilly,overton,kdavis,ganey
Chemistry
Cavity
C100R Cavity Degreasing | Traveler | C100R-CAV-CHEM-USC | A. Wildeson | T. Ganey | A. Mitchell | A. Reilly | fiedler,wildeson,areilly | ashleya,kdavis,ganey | fiedler,wildeson,areilly,ashleya,kdavis,ganey
C100R Cavity HPR | Traveler | C100R-CAV-CHEM-HPR | R. Fiedler | A. Wildeson | A. Mitchell | A. Reilly | fiedler,wildeson,areilly,forehand | ashleya,kdavis,ganey | fiedler,wildeson,areilly,ashleya,kdavis,forehand,ganey
C100R Production Cavity HPR Procedure | Procedure | CP-C100R-CAV-CHEM-HPR | R. Fiedler | A. Wildeson | A. Mitchell | A. Reilly
C100R Cavity Flange Lapping | Traveler | C100R-CAV-LAP | D. Duchenko | A. Wildeson | A. Mitchell | A. Reilly | fiedler,wildeson,areilly | ashleya,forehand,ganey | fiedler,wildeson,areilly,ashleya,kdavis,ganey
C100R Cavity Horizontal Electropolish | Traveler | C100R-CHEM-CAV-HEP | R. Fiedler | A. Wildeson | A. Mitchell | A. Reilly | fiedler,wildeson,areilly | ashleya,kdavis,ganey | fiedler,wildeson,areilly,ashleya,kdavis,ganey
Feedthrus and Top Hat
C100R Top Hat Flange Lapping | Traveler | C100R-CHEM-TPHT-LAP | D. Duchenko | A. Wildeson | A. Mitchell | A. Reilly | fiedler,wildeson,areilly | ashleya,forehand,ganey | fiedler,wildeson,areilly,ashleya,kdavis,ganey
General Components
Pair Components Preparation | Traveler | C100R-CHEM-COMP-DEGR | R. Fiedler | T. Ganey | A. Mitchell | A. Reilly | ganey,areilly | kdavis,ashleya | areilly,ganey,ashleya,kdavis | Why delete this one? This is good ID
C100 components cleaning | Traveler | C100R-CAV-CHEM-COMP | R. Fiedler | T. Ganey | A. Mitchell | A. Reilly | areilly | kdavis,ashleya,ganey | areilly,ganey,ashleya,kdavis | This ID is not preferred.
Assembly (CLNRM)
C100R Cavity Assembly | Traveler | C100R-CAV-ASSY | C. Dreyfuss | T. Ganey | D. Forehand | A. Reilly | dreyfuss,areilly | forehand,kdavis,ganey | dreyfuss,ganey,areilly,forehand,kdavis
C100R Cavity Assembly, Evacuation, and Leak Test | Traveler | C100R-CAV-ASSY2 | C. Dreyfuss | T. Ganey | D. Forehand | A. Reilly | dreyfuss,areilly | forehand,kdavis,ganey | dreyfuss,ganey,areilly,forehand,kdavis
C100 Final Cavity Assembly Procedure for VTA Qualification | Procedure | C100R-PR-CLNRM-CAV-ASSY2 | C. Dreyfuss | T. Ganey | D. Forehand | A. Reilly
Cavity Installation into Test Stand Procedure | Procedure | C100R-PR-CLNRM-CAV-TSTD
C100R Cavity String All-Metal Gate Valve Leak Test | Traveler | C100R-CLNRM-AMGV-LEAK | D. Savransky | C. Dreyfuss | D. Forehand | A. Reilly | areilly,dreyfuss | dsavr,forehand,ganey | dsavr,forehand,ganey,dreyfuss,areilly
VTA
VTA HOM Survey | Traveler | C100R-VTA-HOM | P. Owen | T. Ganey | K. Davis | A. Reilly | areilly | kdavis,powen,ganey | powen,ganey,kdavis,areilly
C100R Cavity VTA Test | Traveler | C100R-CAV-VTRF | C. Willson | T. Ganey | K. Davis | A. Reilly | areilly,forehand | kdavis,ganey | areilly,kdavis,ganey,forehand
RF testing of C100 cavities in the VTA Procedure | Procedure | C100R-PR-VTA-CAV-VTRF | C. Wilson | P. Owen | K. Davis | A. Reilly
C100R HOM Feedthru Receiving Inspection - Cold Shock | Traveler | C100R-VTA-HMFT-CSHK | L. Zhao | J. Kent | K. Davis | A. Reilly | jtkent,forehand,areilly | lzhao,kdavis,ganey | jtkent,forehand,areilly,lzhao,kdavis,ganey
CMTF / High Power Window Test Stand
C100R Window and Waveguide RF Test Traveler | Traveler | C100R-CMTF-WINWGD-HPRF | M. Drury | M. McCaughan | M. Drury | A. Reilly | areilly,michaelm | scott,grose,drury,ganey | areilly,michaelm,scott,grose,drury,ganey
Cavity String Documents
Assembly
C100R Cavity String Assembly | Traveler | C100R-CST-ASSY | D. Forehand | C. Dreyfuss | K. Davis | A. Reilly | areilly | forehand,kdavis,ganey | ganey,areilly,forehand,kdavis
C100R Cavity string leak test | Traveler | C100R-CST-ASSY-LEAK | D. Forehand | C. Dreyfuss | K. Davis | A. Reilly | areilly | forehand,kdavis,ganey | ganey,areilly,forehand,kdavis
Radial Wedge Flange Clamp Installation | Procedure | C100R-PR-CLNRM-FWFC-INST | T. Ganey | C. Dreyfuss | D. Forehand | A. Reilly
C100 Beamline Assembly | Procedure | C100R-PR-CLNRM-CST-ASSY | T. Ganey | C. Dreyfuss | D. Forehand | A. Reilly
C100 Ion Pump Pre-Assembly, Installation, and Starting | Procedure | C100R-PR-CLNRM-CST-ION | T. Ganey | C. Dreyfuss | D. Forehand | A. Reilly
Cover a C100 Cavity | Procedure | C100R-PR-CLNRM-CAV-COV | T. Ganey | C. Dreyfuss | D. Forehand | A. Reilly
C100 Cavity installation into the Lift Cart and Cavity Transfer to the Rail | Procedure | C100R-PR-CLNRM-CAV-LIFT | T. Ganey | C. Dreyfuss | D. Forehand | A. Reilly
C100 Waveguide Assembly onto the Cavity | Procedure | C100R-PR-CLNRM-WGD-ASSY | T. Ganey | C. Dreyfuss | D. Forehand | A. Reilly
Cryomodule Documents
Inspection
12 GeV Guard Vacuum Waveguide | Traveler | C100R-CM-INSP-GVWG | A. Dekerlegand | S. Williams | A. McEwen | A. Reilly | areilly | scott,grose,ganey | areilly,kdavis,scott,grose,ganey
Cryomodule Assembly
C100R Cryomodule Final Assembly | Traveler | C100R-CM-ASSY | J. Fischer | J. Campbell | J. Fischer | A. Reilly | areilly,drury,fhumphry | fischer,jjcamp,ganey | fischer,jjcamp,drury,fhumphry,ganey
C100R Cold Mass Assembly | Traveler | C100R-CM-ASSY-COLD | J. Fischer | J. Campbell | J. Fischer | A. Reilly | areilly,drury,fhumphry | fischer,jjcamp,ganey | fischer,jjcamp,drury,fhumphry,ganey
C100R Thermal Shield and Space Frame Assembly | Traveler | C100R-CM-ASSY-SFR | J. Fischer | J. Campbell | J. Fischer | A. Reilly | areilly,drury,fhumphry | fischer,jjcamp,ganey | fischer,jjcamp,drury,fhumphry,ganey
C100R Vacuum Vessel and End Can Assembly | Traveler | C100R-CM-ASSY-VV | J. Fischer | J. Campbell | J. Fischer | A. Reilly | areilly,drury,fhumphry | fischer,jjcamp,ganey | fischer,jjcamp,drury,fhumphry,ganey
C100R Cryomodule Beampipe Assembly | Traveler | C100R-CM-ASSY-BPIP | J. Fischer | J. Campbell | J. Fischer | A. Reilly | areilly,drury,fhumphry | fischer,jjcamp,ganey | fischer,jjcamp,drury,fhumphry,ganey | Currently does not exist in Pansophy
Cryomodule Testing
C100R CM Cooldown Procedure | Procedure | C100R-PR-CMTF-CM-COOL | D. Savransky | M. McCaughan | M. Drury | A. Reilly
C100R CM Warm-Up Procedure | Procedure | C100R-PR-CMTF-CM-WARM | D. Savransky | M. McCaughan | M. Drury | A. Reilly
C100R Cryomodule Acceptance Test Cryocycle | Traveler | C100R-CMTF-CM-ACTS | M. Drury | M. McCaughan | M. Drury | A. Reilly | areilly,michaelm | areilly,drury,ganey | areilly,drury,michaelm,ganey
Cryomodule Installation & Commissioning
C100R Cryomodule Tunnel Installation | Traveler | C100R-INSTA-CM | F. Humpfry | M. McCaughan | M. Drury | A. Reilly | areilly,michaelm | drury,ganey | areilly,drury,michaelm,ganey
C100R Cryomodule Commissioning | Traveler | C100R-CM-COMM | M. Drury | M. McCaughan | M. Drury | A. Reilly | areilly,michaelm | areilly,drury,ganey | areilly,drury,michaelm,ganey
Standard Project Travelers
C100R Non-Conformance Report | Traveler | C100R-NCR | M. McDonald | M. Dickey | V. Bookwalter | A. Reilly | bookwalt,megan | bookwalt,megan | bookwalt,megan
C100R Detours, Deviations and Discrepancies | Traveler | C100R-D3 | M. McDonald | M. Dickey | V. Bookwalter | A. Reilly |  | bookwalt
C100R Inspection Summary Report | Traveler | C100R-INSR | A. Dekerlegand | A. McEwen |  | A. Reilly |  | areilly,georged
OBSOLETED
Waveguide and Window Weldment Modification | 2023-01-18 | C100R-WELD-WIN-ASSY | S. Williams | A. Obrien | S. Williams | A. Reilly | forehand,areilly,daly | scott,grose,ganey | forehand,scott,areilly,grose,daly,ganey
C100R Warm Window Brazed Assembly | 2023-01-18 | C100R-FURN-WINW-BRAZ | S. Williams | G. Grose | S. Williams | A. Reilly | areilly,daly | scott,grose,ganey | scott,areilly,grose,daly,ganey
C100R Double Sided Rectangular Flange Receiving Inspection Traveler | 2023-01-18 | C100R-CAV-INSP-DSRF | S. Williams | G. Dekerlegand | A. McEwen | A. Reilly | areilly | scott,grose,ganey | areilly,scott,grose,ganey
Primary Waveguide Inspection | 2023-01-18 | C100R-CAV-INSP-WGD | S. Williams | G. Dekerlegand | A. McEwen | A. Reilly | areilly | scott,grose,ganey | areilly,scott,grose,ganey
C100R Window Recycled Visual Inspection | 2023-01-18 | C100R-CAV-INSP-WIN-RCYC | S. Williams | G. Dekerlegand | A. McEwen | A. Reilly | areilly | scott,grose,ganey | areilly,scott,grose,ganey
Rework - 12 GeV Upgrade Waveguides | 2023-01-18 | C100R-CAV-RWRK-WGD | S. Williams | G. Dekerlegand | S. Williams | A. Reilly | areilly | scott,grose,ganey | areilly,scott,grose,ganey
Window Flange Inspection | 2023-01-18 | C100R-INSP-WIN | S. Williams | G. Dekerlegand | A. McEwen | A. Reilly | areilly | scott,grose,ganey | areilly,scott,grose,ganey
C100R Brazement Adapter Assembly Receiving Inspection Traveler | 2023-01-18 | C100R-INSP-ADPT | S. Williams | G. Dekerlegand | A. McEwen | A. Reilly | areilly | scott,grose,ganey | areilly,scott,grose,ganey
C100R Waveguide Sub-Assembly & Leak Test | 2023-01-18 | C100R-CST-ASSY-WGD | D. Forehand | C. Dreyfuss | K. Davis | A. Reilly | areilly | forehand,kdavis,ganey | ganey,areilly,forehand,kdavis
Note on A49: Tiffany Ganey: Archive this traveler
Note on A53: Tiffany Ganey: Traveler is in Pansophy but was not on the spreadsheet.

## ChangeLog
Change # | Change Effective Date | Description of Changes
- | 2022-12-13 | Initial version
1 | 2023-02-16 | Pansophy validation of list (VDB)
|  | C100R-WELD-WIN-ASSY | Archived 18-Jan-2023
|  | C100R-FURN-WINW-BRAZ | Archived 18-Jan-2023
|  | C100R-CAV-INSP-DSRF | Archived 18-Jan-2023
|  | C100R-CAV-INSP-WGD | Archived 18-Jan-2023
|  | C100R-CAV-INSP-WIN-RCYC | Archived 18-Jan-2023
|  | C100R-CAV-RWRK-WGD | Archived 18-Jan-2023
|  | C100R-INSP-WIN | Archived 18-Jan-2023
|  | C100R-INSP-ADPT | Archived 18-Jan-2023
|  | C100R-CST-ASSY-WGD | Archived 18-Jan-2023
|  | C100R-CM-ASSY-BPIP | Currently does not exist in Pansophy
|  | C100R-CHEM-COMP-DEGR | Why delete this one? This is good ID
|  | C100R-CAV-CHEM-COMP | This ID is not preferred.
|  | C100R-CMA-WIN-WELD | Currently does not exist in Pansophy

## TRAVELERS (hidden)
| Traveler Name | Traveler ID PROJ-WCA-COMP-JOB/TASK | Revision | Due - 1 month prior to part arriving | First Expected date | Author | Reviewer 1 (SRFOPS SME or WCL) | Reviewer 2 (SRFOPS WCL or Group Lead) | Project Representative | Tech Rep | Cost Account Manager | NCR Informative | NCR Dispositioners | D3 Emails | Procedure(s), Name (if known) | Drawing(s), Name (if known) | Other References | Acronym from INV | Notes | Status | Section
Disassembly Travelers
Cavity
CP | Cavity Disassembly | C100R-CAV-DISA | R3 | 2018-11-28 |  | C. Dreyfuss | D. Forehand | K. Davis | A. Reilly |  |  | dreyfuss,areilly,ganey | forehand,kdavis | dreyfuss,dorehand,kdavis,areilly,ganey | [5 empty] | CP
| Cavity String | [19 empty] | SS
CP | Cavity String Disassembly |  |  | 2020-08-01 |  | D. Forehand | C. Dreyfuss | K. Davis | A. Reilly |  |  | dreyfuss,areilly | forehand,kdavis | dreyfuss,dorehand,kdavis,areilly | [5 empty] | CP
| Cryomodule | [19 empty] | SS
CP | C100R Disassembly Traveler | C100R-CM-DISA | R2 | 2018-09-24 |  | J. Fischer | J. Campbell | J. Fischer | A. Reilly |  |  | jjcamp,areilly,ganey | fischer | fischer,jjcamp,areilly,ganey | [5 empty] | CP
| Cavity Preparation | [19 empty] | SH
| Inspection | [19 empty] | SS
CP | Cavity CMM Receiving Inspection | C100R-CAV-INSP | R1 | 2018-11-30 |  | T. Ganey | G. Dekerlegand | A. McEwen | A. Reilly |  |  | areilly | ganey,kdavis | georged,areilly,mosby,ganey,kdavis | [5 empty] | CP
CP | Cavity HOM Feedthru Receiving Inspection | C100R-CAV-INSP-HMFT | R3 | 2018-11-06 |  | L. Zhao | G. Dekerlegand | A. McEwen | A. Reilly |  |  | areilly,ganey | lzhao,kdavis | georged,mosby,areilly,lzhao,kdavis | [5 empty] | CP
CP | Cavity RF Inspection Receiving Inspection | C100R-CAV-RFIN | R2 | 2018-12-05 |  | T. Ganey | R. Overton | D. Forehand | A. Reilly |  |  | forehand,areilly,ganey | overton,kdavis | forehand,areilly,overton,kdavis,ganey | [5 empty] | CP
CP | Secondary Waveguide Inspection (knife edge and sealing surface) | C100R-CAV-INSP-GVWG | R2 | 2019-01-15 |  | A. Dekerlegand | S. Williams | J. Fischer | A. Reilly |  |  | georged,mosby,areilly | fischer,scott | georged,mosby,areilly,fischer,scott | [5 empty] | CP
CP | Primary waveguide Inspection | C100R-CAV-INSP-WGD | R1 | 2019-01-16 |  | S. Williams | G. Dekerlegand | A. McEwen | A. Reilly |  |  | areilly,ganey | scott,kdavis,grose | georged,mosby,areilly,scott,kdavis,ganey | [5 empty] | CP
CP | Recycled Waveguide Inspection - 12 GeV Upgrade Waveguides | C100R-CAV-INSP-WGD-RCYC | R2 | 2019-01-25 |  | S. Williams | G. Dekerlegand | A. McEwen | A. Reilly |  |  | areilly,ganey | scott,kdavis,grose | georged,mosby,areilly,scott,kdavis,ganey | scott,kdavis,grose |  |  |  |  | CP
CP | Rework - 12 GeV Upgrade Waveguides | C100R-CAV-RWRK-WGD | R1 | 2019-02-21 |  | S. Williams | G. Dekerlegand | S. Williams | A. Reilly |  |  | areilly,ganey | scott,kdavis,grose | areilly,scott,kdavis,ganey | [5 empty] | CP
CP | C100R HOM Feedthru Receiving Inspection - Cold Shock | C100R-VTA-HMFT-CSHK | R1 |  |  | L. Zhao | G. Dekerlegand | J. Kent | A. Reilly |  |  | jtkent,forehand,areilly | lzhao,kdavis | jtkent,forehand,areilly,lzhao,kdavis | [5 empty] | CP
CP | C100R leak check inspection traveler | C100R-CMA-HMFT-LEAK-R1 | R1 |  |  | L. Zhao | D. Forehand | J. Fischer | A. Reilly |  |  | jtkent,wilcox,areilly,forehand | lzhao,kdavis | wilcox,forehand,areilly,lzhao,kdavis | [5 empty] | CP
CP | C100R Window Recycled Visual Inspection | C100R-CAV-INSP-WIN-RCYC | R1 | 2019-01-16 |  | S. Williams | K. Davis |  | A. Reilly |  |  | georged,mosby,areilly | scott,kdavis,grose | georged,mosby,areilly,scott,kdavis | [5 empty] | CP
CP | Window Flange Inspection | C100R-INSP-WIN | R1 | 2020-09-23 |  | S. Williams | A. Dekerlegand | A. McEwen | A. Reilly |  |  | areilly,ganey | scott,kdavis,grose | georged,mosby,areilly,scott,kdavis | [5 empty] | CP
CP | Receiving Inspection of C100 Cryomodule Helium Vessel | C100R-CMA-HELV-INSP | R1 |  |  | G. Cheng | A. DeKerlegand | A. McEwen | A. Reilly |  |  | areilly | cheng,fischer | cheng,fischer,areilly | [5 empty] | CP
CP | C100 cryomodule return header bellows receiving inspection traveler | C100R-CMA-HERB-INSP | R1 |  |  | G. Cheng | A. DeKerlegand | A. McEwen | A. Reilly |  |  | areilly | Cheng,fischer | Cheng,fischer,areilly | [5 empty] | CP
CP | C100 cryomodule supply header bellows receiving inspection traveler | C100R-CMA-HESB-INSP | R1 |  |  | G. Cheng | A. DeKerlegand | A. McEwen | A. Reilly |  |  | areilly | Cheng,fischer | Cheng,fischer,areilly | [5 empty] | CP
| Chemistry | [19 empty] | SS
CP | C100R Cavity Degreasing | C100R-CAV-CHEM-USC | R1 | 2019-01-08 |  | A. Wildeson | T. Ganey | A. Mitchell | A. Reilly |  |  | fiedler,wildeson,areilly,ganey | ashleya,kdavis | fiedler,wildeson,areilly,ashleya,kdavis,ganey | [5 empty] | CP
CP | C100R Cavity HPR | C100R-CAV-CHEM-HPR | R1 | 2019-01-08 |  | A. Wildeson | T. Ganey | A. Mitchell | A. Reilly |  |  | fiedler,wildeson,areilly,forehand,ganey | ashleya,kdavis | fiedler,wildeson,areilly,ashleya,kdavis,forehand,ganey | [5 empty] | CP
CP | C100R Cavity Flange Lapping | C100R-CAV-LAP | R2 | 2018-11-29 |  | A. Wildeson | D. Forehand | A. Mitchell | A. Reilly |  |  | fiedler,wildeson,areilly,ganey | ashleya,kdavis | fiedler,wildeson,areilly,ashleya,kdavis,ganey | [5 empty] | CP
CP | C100R Top Hat Flange Lapping | C100R-CHEM-TPHT-LAP | R1 | 2021-05-06 |  | A. Wildeson | D. Forehand | A. Mitchell | A. Reilly |  |  | fiedler,wildeson,areilly,ganey | ashleya,kdavis | fiedler,wildeson,areilly,ashleya,kdavis,ganey | [5 empty] | CP
| Assembly | [19 empty] | SS
CP | C100R Cavity Assembly | C100R-CAV-ASSY | R2 | 2018-11-06 |  | C. Dreyfuss | T. Ganey | D. Forehand | A. Reilly |  |  | dreyfuss,ganey,areilly | forehand,kdavis | dreyfuss,ganey,areilly,forehand,kdavis | [5 empty] | CP
| C100R Cavity Assembly, Evacuation, and Leak Test | C100R-CAV-ASSY2 | R1 |  |  | C. Dreyfuss | T. Ganey | D. Forehand | A. Reilly |  |  | dreyfuss,ganey,areilly | forehand,kdavis | dreyfuss,ganey,areilly,forehand,kdavis
CP | C100R Cavity Tuning | C100R-CAV-TUNE | R1 | 2018-11-06 |  | R. Overton | P. Owen | D. Forehand | A. Reilly |  |  | ganey,overton,powen,areilly | forehand,kdavis | ganey,overton,powen,forehand,kdavis,areilly | [5 empty] | CP
| Testing | [19 empty] | SS
CP | VTA HOM Survey | C100R-VTA-HOM | R1 |  |  | P. Owen | T. Ganey | K. Davis | A. Reilly |  |  | ganey,areilly | kdavis,powen | powen,ganey,kdavis,areilly | [5 empty] | CP
CP | C100R Cavity VTA Test | C100R-CAV-VTRF | R2 | 2018-11-06 |  | C. Willson | T. Ganey | K. Davis | A. Reilly |  |  | areilly,forehand | kdavis,ganey | areilly,kdavis,ganey,forehand | [5 empty] | CP
CP | RF testing of C100 cavities in the VTA | C100R-PR-VTA-CAV-VTRF | R2 |  |  | C. Wilson | K. Davis |  | A. Reilly | [10 empty] | CP
| Component Preparation | [19 empty] | SH
| Inspection | [19 empty] | SS
CP | C100R Double Sided Rectangular Flange Receiving Inspection Traveler | C100R-CAV-INSP-DSRF | R1 | 2020-09-30 |  | S. Williams | A. Dekerlegand | A. McEwen | A. Reilly |  |  | areilly | scott,grose | areilly,scott,grose | [5 empty] | CP
CP | C100R Brazement Adapter Assembly Receiving Inspection Traveler | C100R-INSP-ADPT | R1 | 2020-09-03 |  | S. Williams | A. Dekerlegand | A. McEwen | A. Reilly |  |  | areilly | scott,grose | areilly,scott,grose | [5 empty] | CP
| Chemistry | [19 empty] | SS
CP | Pair Components Preparation | C100R-CHEM-COMP-DEGR | R1 |  |  | R. Fiedler | T. Ganey | A. Mitchell | A. Reilly |  |  | ganey,areilly | kdavis,ashleya | areilly,ganey,ashleya,kdavis | [5 empty] | CP
CP | C100 components cleaning | C100R-CAV-CHEM-COMP | R1 | 43501 |  | R. Fiedler | T. Ganey | A. Mitchell | A. Reilly |  |  | ganey,areilly | kdavis,ashleya | areilly,ganey,ashleya,kdavis | [5 empty] | CP
| Weld Inspection | [19 empty] | SS
CP | Waveguide and window Weldement Modification | C100R-WELD-WIN-ASSY | R1 | 2021-02-05 |  | S. Williams | A. Obrien | S. Williams | A. Reilly |  |  | forehand,areilly | scott,grose | scott,areilly,grose | [5 empty] | CP
| Leak Checks | [19 empty] | SS
CP | C100R Cavity String All-Metal Gate Valve Leak Test | C100R-CLNRM-AMGV-LEAK | R1 |  |  | D. Savransky | C. Dreyfuss | D. Forehand | A. Reilly |  |  | Dsavr,areilly,dreyfuss | forehand,ganey | dsavr,forehand,ganey,dreyfuss,areilly | [5 empty] | CP
| Assembly | [19 empty] | SS
CP | C100R Helium Vessel Installation | C100R-CAV-ASSY-HELV | R2 | 2018-11-29 |  | J. Fischer | J. Campbell | J. Fischer | A. Reilly |  |  | areilly,ganey,forehand | Fischer,jjcamp | areilly,ganey,forehand,fischer,jjcamp | [5 empty] | CP
CP | C100R Warm Window Brazed Assembly | C100R-FURN-WINW-BRAZ | R1 | 2022-05-27 |  | S. Williams | G. Grose | S. Williams | A. Reilly |  |  | areilly | Grose,Scott | Grose,Scott,areilly | [5 empty] | CP
| Cavity String | [19 empty] | SH
| Assembly | [19 empty] | SS
CP | C100R Cavity String Assembly | C100R-CST-ASSY | R1 | 2019-01-21 |  | D. Forehand | C. Dreyfuss | K. Davis | A. Reilly |  |  | ganey,areilly | Forehand,kdavis | ganey,areilly,forehand,kdavis | [5 empty] | CP
CP | C100R Cavity string leak test | C100R-CST-ASSY-LEAK | R1 | 2019-02-27 |  | D. Forehand | C. Dreyfuss | K. Davis | A. Reilly |  |  | ganey,areilly | Forehand,kdavis | ganey,areilly,forehand,kdavis | [5 empty] | CP
CP | C100R Waveguide Sub-Assembly & Leak Test | C100R-CST-ASSY-WGD | R1 | 2019-01-21 |  | D. Forehand | C. Dreyfuss | K. Davis | A. Reilly |  |  | ganey,areilly | Forehand,kdavis | ganey,areilly,forehand,kdavis | [5 empty] | CP
| Cryomodule | [19 empty] | SH
| Inspection | [19 empty] | SS
| 12 GeV Guard Vacuum Waveguide | C100R-CM-INSP-GVWG | R2 | 2019-01-15 |  | A. Dekerlegand | S. Williams | J. Fischer | A. Reilly |  |  | areilly,kdavis | scott,forehand,grose | areilly,kdavis | [5 empty] | CP
| Cryomodule Assembly | [19 empty] | SS
CP | C100R Cryomodule Final Assembly | C100R-CM-ASSY | R2 | 2019-02-11 |  | J. Fischer | J. Campbell | J. Fischer | A. Reilly |  |  | areilly,drury | fischer,jjcamp | fischer,jjcamp,drury,fhumphry | [5 empty] | CP
CP | C100R Cold Mass Assembly | C100R-CM-ASSY-COLD | R2 | 2019-02-11 |  | J. Fischer | J. Campbell | J. Fischer | A. Reilly |  |  | areilly,drury | fischer,jjcamp | fischer,jjcamp,drury,fhumphry | [5 empty] | CP
CP | C100R Thermal Shield and Space Frame Assembly | C100R-CM-ASSY-SFR | R2 | 2019-02-11 |  | J. Fischer | J. Campbell | J. Fischer | A. Reilly |  |  | areilly,drury | fischer,jjcamp | fischer,jjcamp,drury,fhumphry | [5 empty] | CP
CP | C100R Vacuum Vessel and End Can Assembly | C100R-CM-ASSY-VV | R2 | 2019-02-11 |  | J. Fischer | J. Campbell | J. Fischer | A. Reilly |  |  | areilly,drury | fischer,jjcamp | fischer,jjcamp,drury,fhumphry | [5 empty] | CP
OD | C100R Cryomodule Beampipe Assembly | C100R-CM-ASSY-BPIP | R1 | 2021-09-01 |  | J. Fischer | J. Campbell | J. Fischer | A. Reilly |  |  | areilly,drury | fischer,jjcamp | fischer,jjcamp,drury,fhumphry
| Cryomodule Testing | [19 empty] | SS
CP | C100R CM Cooldown Procedure | C100R-PR-CMTF-CM-COOL | R1 |  |  | D. Savransky | M. McCaughan | M. Drury | A. Reilly | [10 empty] | CP
CP | C100R CM Warm-Up Procedure | C100R-PR-CMTF-CM-WARM | R1 |  |  | D. Savransky | M. McCaughan | M. Drury | A. Reilly | [10 empty] | CP
CP | C100R Cryomodule Commissioning | C100R-CM-COMM | R1 | 2021-10-01 |  | M. Drury | M. McCaughan | M. Drury | A. Reilly |  |  | areilly,michaelm | drury | areilly,drury,michaelm | [5 empty] | CP
| Cryomodule Installation & Commisioning | [19 empty] | SS
CP | C100R Cryomodule Tunnel Installation | C100R-INSTA-CM | R1 | 2021-10-01 |  | F. Humpfry | M. McCaughan | M. Drury | A. Reilly |  |  | areilly,michaelm | drury | areilly,drury,michaelm | [5 empty] | CP
CP | C100R Cryomodule Acceptance Test Cryocycle | C100R-CM-ACTS | R1 | 2019-10-28 |  | M. Drury | M. McCaughan | M. Drury | A. Reilly |  |  | areilly,michaelm | drury | areilly,drury,michaelm | [5 empty] | CP
| Standard Project Travelers | [19 empty] | SH
CP | C100R Non-Conformance Report | C100R-NCR | R11 |  |  | M. McDonald |  | V. Bookwalter | A. Reilly |  |  | bookwalt,megan | bookwalt,megan | bookwalt,megan | [5 empty] | CP
CP | C100R Detours, Deviations and Discrepencies | C100R-D3 | R2 |  |  | M. McDonald |  | V. Bookwalter | A. Reilly |  |  |  | bookwalt | [6 empty] | CP
CP | C100R Inspection Summary Report | C100R-INSR | R1 |  |  | A. Dekerlegand | A. McEwen |  | A. Reilly |  |  |  | areilly,georged | [6 empty] | CP
Color Legend |  | Count | Percent
CP | Complete (CP) | 49 | 96.08%
NR | New Revision Out for Approval (NR) | 0 | 0%
OA | Out for Approval (OA) | 0 | 0%
30 | Due in 30 Days | 0 | 0%
15 | Due in 15 Days | 0 | 0%
OD | Overdue | 1 | 1.961%
| Remaining | 1 | 1.961%
| Total Traveler IDs | 51
Note on B6: Tiffany Ganey: No traveler exists in Pansophy
Note on B14: Tiffany Ganey: Traveler does not exist in Pansophy
Note on B32: Tiffany Ganey: Traveler is in Pansophy but was not on the spreadsheet.
Note on B44: Tiffany Ganey: The data in this traveler should be migrated to C100R-CHEM-COMP-DEGR. This traveler should be deleted from Pansophy and this list.
Note on C76: Tiffany Ganey: Traveler not used for C100R

## TRAVELERSold (hidden)
Traveler Name | Traveler ID (SEPARATE BY WORKCENTERS) | Procedure(s), Name (if known) OR Yes/No | Drawing(s), Name (if known) OR Yes/No | SOP/TOSP/OSP/THA | Revision | Author | Reviewer | Project Manager | SOTR | Due | D3 ?? (USERNAME) | NCR Dispositioners (USERNAME) | NCR Informative (USERNAME) | Traveler (Holdpoint) Closer (USERNAME) | Notes
Receiving Travelers
Cavity
Helium Vessel Receiving Traveler | SNSPPU-CAV-RECV-HELV |  |  |  | R1
Cavity String
Bellows Receiving Traveler | SNSPPU-CST-RECV-(bellows) |  |  |  | R1
Gate Valves Receiving Traveler | SNSPPU-CST-RECV-(gate valve) |  |  |  | R1
FPC Receiving Traveler | SNSPPU-CST-RECV-FPC |  |  |  | R1
Cryomodule
Diode CXCU Inventory Traveler | SNSPPU-CM-RECV-DCXCU |  |  |  | R1 | M. Dickey | C. Barnes | E. Daly | P. Owen | 2020-01-02 |  | powen,king,edaly,kwilson,mdickey,areilly
Disassembly Travelers
Cavity
Cavity String
Cryomodule
Leak Check Travelers
Cavity
Cavity String
Bellows Leak Check Traveler | SNSPPU-CST-LEAK-(bellows) |  |  |  | R1
Gate Valves Leak Check Traveler | SNSPPU-CST-LEAK-(gate valves) |  |  |  | R1
FPC Leak Check Traveler | SNSPPU-CST-LEAK-FPC |  |  |  | R1
Cryomodule
Inspection Travelers
Cavity
Visual and CMM Inspection of Cavity | SNSPPU-CAV-INSP-CAV |  | 104211800-M8U-8200-A00X |  | R1 |  |  |  | K. Wilson | 2020-02-01
Visual/CMM Inspection of Helium Vessel | SNSPPU-CAV-INSP-HELV | TI CLEANING | 104211700-M8U-8200-A026 |  | R1 |  |  |  | K. Wilson | 2020-02-01
Receiving Inspection Cavity RF | SNSPPU-CAV-RFIN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
TUNER FRAME / STEPPER MOTORS / HARMONIC DRIVE |  | SS CLEANING
Cavity String
Receiving Inspection Bellows | SNSPPU-CST-INSP-(bellows) |  |  |  | R1 |  |  |  | K. Wilson | 2020-05-01
SNS FPC Visual Inspection | SNSPPU-CST-INSP-FPC |  | 104211600-M8U-8200-A00X |  | R1 |  |  |  | K. Wilson | 2019-12-01
Cryomodule
Space Frame Visual and Dimensional Inspection | SNSPPU-CM-INSP-SFR | SS CLEANING | 104210900-M8U-8200-A001 |  | R1 |  |  |  | M. Marchlik | 2020-10-01
Vacuum Vessel Visual Inspection | SNSPPU-CM-INSP-VV | LEAK CHECK; SS CLEANING | 104210800-M8U-8200-A001 |  | R1 |  |  |  | M. Marchlik | 2020-07-01
SNS Return End Can Visual/CMM Inspection | SNSPPU-CM-INSP-RENC |  | 104210700-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-11-01
SNS Supply End Can Visual/CMM Inspection | SNSPPU-CM-INSP-SENC |  | 104210600-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-06-01
SNS Outer Magnetic Shield Visual Inspection | SNSPPU-CM-INSP-OMAG |  | 104211000-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-05-01
SNS Inner Magnetic Shield Visual Inspection | SNSPPU-CM-INSP-IMAG |  | 104211200-M8U-8200-A00X |  | R1 |  |  |  | G. Cheng | 2020-05-01
SNS Thermal Shield Visual/CMM Inspection | SNSPPU-CM-INSP-THRM | HIGH SENSITIVITY LEAK CHECK | 104211100-M8U-8200-A002 104211100-M8U-8200-A014 104211100-M8U-8200-A025 |  | R1 |  |  |  | M. Marchlik | 2020-08-01
Chemistry Travelers
Cavity
Cavity High Pressure Rinse (New HPR) Traveler | SNSPPU-CAV-CHEM-HPRN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Components Cleaning Traveler | SNSPPU-CAV-CHEM-CLN |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Ultra Sonic Clean Traveler | SNSPPU-CAV-CHEM-USC |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
CMM Workcenter ?
IS there a cav RFIN traveler?
Furnace Workcenter ? | changed CHEM to PROC
Bakeout before RF processing | SNSPPU-CAV-PROC-BAKE |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Cavity Heat Treatment | SNSPPU-CAV-PROC-HEAT |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
Processing Travelers
Cavity
Cavity RF Tuning | SNSPPU-CAV-TUNE |  |  |  | R1 |  |  |  | K. Wilson | 2020-02-01
IS there a cav RFIN traveler? |  |  |  |  | R1
Cavity String
Cryomodule
RF Processing (FPC RF Processing) | SNSPPU-CM-CST-FPC-HPRF |  |  |  | R1 |  |  |  | K. Wilson
Assembly Travelers
Cavity
SNS Helium Vessel Installation Traveler | SNSPPU-CAV-ASSY-HELV |  | 104211700-M8U-8200-A026 |  | R1 |  |  |  |  | 2020-02-01
High Beta Cavity Assembly for VTA testing | SNSPPU-CAV-ASSY (look at old SNS) |  | 104211800-M8U-8200-A00X |  | R1 |  |  |  |  | 2020-02-01
transfer to test stand
Cavity String
SNS High Beta Cavity String Traveler | SNSPPU-CST-ASSY |  |  |  | R1 |  |  |  |  | 2020-07-01
Cryomodule
Cryomodule Assembly | SNSPPU-CM-ASSY |  |  |  | R1 |  |  |  | M. Marchlik | 2020-12-01
Cold Mass Assembly | SNSPPU-CM-ASSY-CMAS |  |  |  | R1 |  |  |  |  | 2020-08-01
Cryomodule Thermal Shield-Spaceframe Assembly Traveler | SNSPPU-CM-ASSY-THRM |  | 104211100-M8U-8200-A002 104211100-M8U-8200-A014 104211100-M8U-8200-A025 |  | R1 |  |  |  | M. Marchlik
SNS High Beta Cryomodule Vacuum Vessel-End Can Assembly Traveler | SNSPPU-CM-ASSY-VV |  | 104210800-M8U-8200-A001 |  | R1
cm assy ship (rf, instrumentation)
Testing Travelers
Vertical Cavity Testing | SNSPPU-CAV-VTRF |  |  |  | R1 |  |  |  |  | 2020-04-01
Cavity VTA Cooldown | SNSPPU-CAV-VTA-COOL |  |  |  | R1 |  |  |  |  | 2020-02-01
Installation/Shipping Travelers
SNS Cryomodule Shipping | SNSPPU-CM-ASSY-SHIP |  |  |  | R1 |  |  |  |  | 2020-05-01
Standard Project Travelers
Detours, Deviations and Discrepancies (D3) | SNSPPU-D3 |  |  |  | R2 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A
Inspection Summary Report | SNSPPU-INSR |  |  |  | R1 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A
Inspection Nonconformance Report | SNSPPU-NCR |  |  |  | R10 | BOOKWALT | MCEWEN | AREILLY |  |  |  | N/A | N/A | N/A